## Main North
Visual Inspection Checklist, PIN-3 Main Landfill
DEW LINE CLEANUP: POST-CONSTRUCTION-LANDFILL MONITORING
VISUAL INSPECTION CHECKLIST
INSPECTION REPORT
Site Name |  |  | PIN-3 Lady Franklin Point |  | Landfill Designation |  |  | Main Landfill
Date of Inspection |  |  | 2011-08-24 |  | Date of Previous Inspection |  |  | 2009
Inspected by |  |  | Jared Peterson |  | Report Prepared by |  |  | N/A
The inspector/ reporter represents to the best of their knowledge, the following statements and observations are true and correct and to the best of the preparer's actual knowledge, no material facts have been suppressed or misstated.
Checklist Item | Feature | Present | Location | Length (m) | Width (cm) | Depth (cm) | Extent relative to Area of Landfill (%) | Description | Photo Reference | Additional Comments
Settlement |  | N
Erosion | A | Y | Southeast slope |  | 5 | 3-5 | <1 | Erosion feature appears to have been filled in partially | A1
| B | Y | West slope | 15 | 5 | 5 | <1 | Minor erosion | A9
Frost Action |  | N
Sloughing and Cracking |  | N
Animal Burrows |  | N
Vegetation |  | Y | Across landfill surface |  |  |  |  | Sparse vegetation in some areas | A11, A13, A15
Staining |  | N
Vegetation Stress |  | N
Seepage Points |  | N
Debris Exposed |  | N
Presence/ Condition of Monitoring Instruments |  | Y | Various locations | [5 empty] | A14, A15, A16, A17
Other Features of Note |  | N
NSC - "No Significant Change"
Preliminary Stability Assessment
Additional photos: A2-A8, A10, A12 | [7 empty] | Feature | Severity Rating | Extent
[8 empty] | Settlement | Not observed | N/A
[8 empty] | Erosion | Acceptable | Isolated
[8 empty] | Frost Action | Not observed | N/A
[8 empty] | Staining | Not observed | N/A
[8 empty] | Vegetation Stress | Not observed | N/A
[8 empty] | Seepage/Ponded Water | Not observed | N/A
[8 empty] | Debris exposure | Not observed | N/A
[8 empty] | Overall Landfill Performance | Acceptable