## Main North
Visual Inspection Checklist, PIN-3 South Landfill - East
DEW LINE CLEANUP: POST-CONSTRUCTION-LANDFILL MONITORING
VISUAL INSPECTION CHECKLIST
INSPECTION REPORT
Site Name |  |  | PIN-3 Lady Franklin Point |  | Landfill Designation |  |  | South Landfill - East
Date of Inspection |  |  | 2011-08-25 |  | Date of Previous Inspection |  |  | 2009
Inspected by |  |  | Jared Peterson |  | Report Prepared by |  |  | N/A
The inspector/ reporter represents to the best of their knowledge, the following statements and observations are true and correct and to the best of the preparer's actual knowledge, no material facts have been suppressed or misstated.
Checklist Item | Feature | Present | Location | Length (m) | Width (cm) | Depth (cm) | Extent relative to Area of Landfill (%) | Description | Photo Reference | Additional Comments
Settlement |  | N
Erosion |  | N
Frost Action |  | N
Sloughing and Cracking |  | N
Animal Burrows |  | N
Vegetation |  | Y | Across landfill surface |  |  |  | <1 | Sparse vegetation in some areas
Staining |  | Y | Feature A, Feature B, Feature C, Feature D |  |  |  | 1-2 | Features A and B: iron oxide staining and sheen; Features C and D: sheen on water | G4, G14, G16-G19
Vegetation Stress |  | N
Seepage Points | A | Y | Southeastern toe |  |  |  |  | Ponded water | G1, G2
| B | Y | Southwestern toe |  |  |  |  | Ponded water | G5, G6, G8
| C | Y | Along eastern toe |  |  |  |  | Ponded water | G12
| D | Y | Along southern toe |  |  |  |  | Ponded water | G13
Debris Exposed | E | Y | North of northern toe | 0.4 | 40 |  | <1 | Exposed rusted 45 gallon drum | G15
Presence/ Condition of Monitoring Instruments |  | N
Other Features of Note |  | N
NSC - "No Significant Change"
Preliminary Stability Assessment
Additional photos: G3, G7-G11 | [7 empty] | Feature | Severity Rating | Extent
[8 empty] | Settlement | Not observed | N/A
[8 empty] | Erosion | Not observed | N/A
[8 empty] | Frost Action | Not observed | N/A
[8 empty] | Staining | Acceptable | Isolated
[8 empty] | Vegetation Stress | Not observed | N/A
[8 empty] | Seepage/Ponded Water | Acceptable | Isolated
[8 empty] | Debris exposure | Acceptable | Isolated
[8 empty] | Overall Landfill Performance | Acceptable