## Main North
Visual Inspection Checklist, PIN-3 Non-hazardous Waste Landfill
DEW LINE CLEANUP: POST-CONSTRUCTION-LANDFILL MONITORING
VISUAL INSPECTION CHECKLIST
INSPECTION REPORT
Site Name |  |  | PIN-3 Lady Franklin Point |  | Landfill Designation |  |  | Non-hazardous Waste Landfill
Date of Inspection |  |  | 2011-08-24 |  | Date of Previous Inspection |  |  | 2009
Inspected by |  |  | Jared Peterson |  | Report Prepared by |  |  | N/A
The inspector/ reporter represents to the best of their knowledge, the following statements and observations are true and correct and to the best of the preparer's actual knowledge, no material facts have been suppressed or misstated.
Checklist Item | Feature | Present | Location | Length (m) | Width (cm) | Depth (cm) | Extent relative to Area of Landfill (%) | Description | Photo Reference | Additional Comments
Settlement |  | N
Erosion | A | Y | Eastern side of north slope | 0.4 | 25 | 10 | <1 | Diagnosed in previous report as an erosion feature. Upon further investigation, feature appears to be scour mark from adjacent boulder | D1
Frost Action |  | N
Sloughing and Cracking |  | N
Animal Burrows |  | N
Vegetation |  | Y | Across landfill surface |  |  |  | <1 | Sparse vegetation in some areas
Staining |  | N
Vegetation Stress |  | N
Seepage Points |  | N
Debris Exposed |  | N
Presence/ Condition of Monitoring Instruments |  | Y | Various locations |  |  |  |  | Four monitoring wells in good condition | D11-D14
Other Features of Note | B | Y | Southern toe |  |  |  |  | Ponded water | D6
NSC - "No Significant Change"
Preliminary Stability Assessment
Additional photos: D2,D3,D5, D7-D10 | [7 empty] | Feature | Severity Rating | Extent
[8 empty] | Settlement | Not observed | N/A
[8 empty] | Erosion | Acceptable | Isolated
[8 empty] | Frost Action | Not observed | N/A
[8 empty] | Staining | Not observed | N/A
[8 empty] | Vegetation Stress | Not observed | N/A
[8 empty] | Seepage/Ponded Water | Acceptable | Isolated
[8 empty] | Debris exposure | Not observed | N/A
[8 empty] | Overall Landfill Performance | Acceptable