## Main North
Visual Inspection Checklist, PIN-3 Tier II Soil Disposal Facility
DEW LINE CLEANUP: POST-CONSTRUCTION-LANDFILL MONITORING
VISUAL INSPECTION CHECKLIST
INSPECTION REPORT
Site Name |  |  | PIN-3 Lady Franklin Point |  | Landfill Designation |  |  | Tier II Soil Disposal Facility
Date of Inspection |  |  | 2011-08-25 |  | Date of Previous Inspection |  |  | 2009
Inspected by |  |  | Jared Peterson |  | Report Prepared by |  |  | N/A
The inspector/ reporter represents to the best of their knowledge, the following statements and observations are true and correct and to the best of the preparer's actual knowledge, no material facts have been suppressed or misstated.
Checklist Item | Feature | Present | Location | Length (m) | Width (cm) | Depth (cm) | Extent relative to Area of Landfill (%) | Description | Photo Reference | Additional Comments
Settlement | A | Y | Southern crest | 4 | 70 | 25 | <1 |  | B1
| B | Y | Southwestern crest | 3 | 50 | 25 | <1 |  | B2
| E | Y | Eastern side of north slope | 7 | 50 | 30 | <1 |  | B5
Erosion | C | Y | South slope | 0.3 | 30 | 10 | <1 | Diagnosed in previous report as an erosion feature. Upon further investigation, feature appears to be scour mark from adjacent boulder | B3
| D | Y | Western side fo north slope | 3 | 30 | 15 | <1 | Diagnosed in previous report as an erosion feature. Upon further investigation, feature appears to be scour mark from adjacent boulder | B4
Frost Action |  | N
Sloughing and Cracking |  | N
Animal Burrows |  | N
Vegetation |  | N
Staining |  | N
Vegetation Stress |  | N
Seepage Points |  | N
Debris Exposed |  | N
Presence/ Condition of Monitoring Instruments |  | Y | Various locations |  |  |  |  | Four monitoring wells and four thermistors in good condition | B12-B14
Other Features of Note | F | Y | Southwest corner of landfill |  |  |  |  | Ponded water | B6-B7 | No visible sheen
NSC - "No Significant Change"
Preliminary Stability Assessment
Additional photos: B8-B11 | [7 empty] | Feature | Severity Rating | Extent
[8 empty] | Settlement | Acceptable | Isolated
[8 empty] | Erosion | Acceptable | Isolated
[8 empty] | Frost Action | Not observed | N/A
[8 empty] | Staining | Not observed | N/A
[8 empty] | Vegetation Stress | Not observed | N/A
[8 empty] | Seepage/Ponded Water | Acceptable | Isolated
[8 empty] | Debris exposure | Not observed | N/A
[8 empty] | Overall Landfill Performance | Acceptable