## Feuil1
TIMETABLE - NWB Water Licence Type B #1BR-IIA1518 | FORECAST |  | ACTUAL
| Start | Finish | Start | Finish
Arch Culvert Geomembrane Installation | 2015-08-29 | 2015-10-15
Water diversion at Carney Creek | 2015-08-28 | 2015-09-28
Holding Basins installation (No. 1 and 2) | 2015-08-26 | 2015-09-04
Taxiway F decontamination (ship hazardous material down South to approved facility) | 2015-09-11 | 2015-09-22
Monitoring wells installation | 2015-09-14 | 2015-09-18
Water Samplings for Water extraction | 2015-08-14 | 2015-09-03
Monitoring for well sampling | 2015-09-23 | 2015-09-23
Water sampling for Arch Culvert | 2015-08-16 | 2015-08-16
Water sampling upstream and downstream | 2015-08-16 | 2015-08-16
Containment Cell Cover replacement | 2015-10-16 | 2015-10-21
Formulas:
Finish = [Start]
Finish = [Start]+5