## StationW LF Photos
TABLE XII: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-1, Jenny Lind Island
Landfill: | Station West Landfill
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis, P. Eng.
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C111_4118 | 2011-08-13 | 389052.7 | 7620924 |  | Panoramic view looking southwest to northwest from east side across Station West Landfill
2 |  | C111_4119 | 2011-08-13 | 389050.4 | 7620935.2 |  | View looking northwest at three depressions (0.4-0.7m L, 0.15-0.2m W, 0.05m D) - Feature A; and minor erosion (2m L, 0.1m W, 0.03m D) - Feature D on east side slope of Station West Landfill
3 |  | C111_4120 | 2011-08-13 | 389041.3 | 7620940.9 |  | View looking east at three depressions (0.4-0.7m L, 0.15-0.2m W, 0.05m D) - Feature A; and minor erosion (2m L, 0.1m W, 0.03m D) - Feature D on east side slope of Station West Landfill
4 |  | C111_4121 | 2011-08-13 | 389038.6 | 7620953.5 |  | Small isolated depression on east side slope of Station West Landfill (0.2m L, 0.2m W, 0.1m D) - Feature A
5 |  | C111_4122 | 2011-08-13 | 389043.4 | 7620945.6 |  | View looking northwest at depression on east side slope of Station West Landfill (0.2m L, 0.2m W, 0.1m D) - Feature A
6 |  | C111_4123 | 2011-08-13 | 389039.2 | 7620950 |  | Linear depression on east side slope of Station West Landfill (0.8m L, 0.2m W, 0.05-0.1m D) - Feature A
7 |  | C111_4124 | 2011-08-13 | 389033.9 | 7620951.8 |  | View looking east at linear depression on east side slope of Station West Landfill (0.8m L, 0.2m W, 0.05-0.1m D) - Feature A
8 |  | C111_4125 | 2011-08-13 | 389031.7 | 7620962.1 |  | View looking southeast along east toe of Station West Landfill. Erosion of fines along toe from seasonal ponding (7m L, 1m W, 0.05m D) - Feature E
9 |  | C111_4126 | 2011-08-13 | 389031.1 | 7620962.1 |  | View looking west-southwest along north side slope of Station West Landfill
10 |  | C111_4127 | 2011-08-13 | 389030.7 | 7620956.7 |  | Panoramic view looking west to southeast from north side across Station West Landfill (0.7-1m L, 0.2-0.3m W, 0.05-0.1m D) - Feature B
11 |  | C111_4128 | 2011-08-13 | 389013.1 | 7620956.9 |  | View looking south-southwest along west side slope of Station West Landfill. Note minor depression on surface
12 |  | C111_4129 | 2011-08-13 | 389012.7 | 7620948.2 |  | Minor depression on west side slope (0.5m L, 0.3m W, 0.1m D) - Feature B
13 |  | C111_4130 | 2011-08-13 | 389012.6 | 7620943.8 |  | View looking southwest at heavy equipment tracks west of Station West Landfill
14 |  | C111_4131 | 2011-08-13 | 389012.7 | 7620923.2 |  | View looking west at linear stain on surface of Station West Landfill (4m L, 0.3m W) - Feature F
15 |  | C111_4132 | 2011-08-13 | 389009.4 | 7620922.5 |  | View looking southwest at uneven surface on southwest corner of Station West Landfill (5m L, 5m W, 0.05-0.15m D) - Feature C
16 |  | C111_4133 | 2011-08-13 | 389012 | 7620916.5 |  | View looking northwest at uneven surface on southwest corner of Station West Landfill (5m L, 5m W, 0.05-0.15m D) - Feature C
17 |  | C111_4134 | 2011-08-13 | 389004 | 7620920.2 |  | Panoramic view looking northeast to southeast from southwest corner across Station West Landfill
18 |  | C111_4135 | 2011-08-13 | 389000.6 | 7620918.2 |  | View looking southeast along south side slope of Station West Landfill
19 |  | C111_4136 | 2011-08-13 | 389000.2 | 7620919.2 |  | View looking north-northeast along west side slope of Station West Landfill
20 |  | C111_4137 | 2011-08-13 | 389023.3 | 7620905.5 |  | View looking east at parallel cracks on south side slope of Station West Landfill (7m L, 3-5mm W) - Feature G
21 |  | C111_4138 | 2011-08-13 | 389030 | 7620903.8 |  | Parallel cracks on south side slope of Station West Landfill (7m L, 3-5mm W) amd 0.3m apart - Feature G
22 |  | C111_4139 | 2011-08-13 | 389037.7 | 7620901.4 |  | View looking west-northwest at parallel cracks on south side slope of Station West Landfill (7m L, 3-5mm W) - Feature G
23 |  | C111_4140 | 2011-08-13 | 389039.1 | 7620905.6 |  | Panoramic view looking northwest to northeast from south side across Station West Landfill
24 |  | C111_4142 | 2011-08-13 | 389040.1 | 7620902 |  | Single crack on south side slope of Station West Landfill (4m L, 2-4mm W) - Feature G
25 |  | C111_4143 | 2011-08-13 | 389037.4 | 7620891.1 |  | View looking north at area with cracks on south side slope of Station West Landfill
Aerial
A3 |  | C111_4275 | 2011-08-13 | 388927.3 | 7620966.3 |  | Aerial view looking west southeast at Station West Landfill