## Main LF Photos
TABLE XXVI: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | Cam-1, Jenny Lind Island
Landfill: | Main Landfill
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis P. Eng.
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C111_4217 | 2011-08-13 | 389655.9 | 7620719.7 |  | View looking northeast along northwest side slope of Main LF
2 |  | C111_4218 | 2011-08-13 | 389655.1 | 7620719.1 |  | View looking southwest along northwest side slope of Main LF
3 |  | C111_4220 | 2011-08-13 | 389639.1 | 7620706.7 |  | View looking southwest along northwest side slope of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (25m L, 0.3m W, 0.03m D) - Feature A
4 |  | C111_4221 | 2011-08-13 | 389617.5 | 7620687.1 |  | View looking northeast along northwest side slope of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (25m L, 0.3m W, 0.03m D) - Feature A
5 |  | C111_4222 | 2011-08-13 | 389617.4 | 7620686.6 |  | View looking south along west toe of Main LF
6 |  | C111_4223 | 2011-08-13 | 389623 | 7620685.6 |  | Panoramic view looking northeast to south from west corner across Main LF
7 |  | C111_4224 | 2011-08-13 | 389621.3 | 7620680.3 |  | Minor erosion (washing of fines) on northwest corner of Main LF (25m L, 1m W, 0.05m D) - Feature A
8 |  | C111_4225 | 2011-08-13 | 389621.7 | 7620630.4 |  | Panoramic view looking north to southeast from west side across Main LF
9 |  | C111_4226 | 2011-08-13 | 389618.3 | 7620624.9 |  | View looking east-northeast along southwest toe of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (30m L, 0.3m W, 0.03m D) - Feature B
10 |  | C111_4227 | 2011-08-13 | 389617.5 | 7620625.3 |  | View looking north along west toe of Main LF
11 |  | C111_4228 | 2011-08-13 | 389640.7 | 7620631.2 |  | Minor erosion (washing of fines) along southwest toe of Main LF (30m L, 0.3m W, 0.03m D) - Feature B
12 |  | C111_4229 | 2011-08-13 | 389657.4 | 7620619.9 |  | View looking west along southwest toe of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (30m L, 0.3m W, 0.03m D) - Feature B
13 |  | C111_4230 | 2011-08-13 | 389657.9 | 7620619.1 |  | View looking south along west toe of Main LF
14 |  | C111_4231 | 2011-08-13 | 389666.2 | 7620592.6 |  | Panoramic view looking north to east from south side across Main LF
15 |  | C111_4232 | 2011-08-13 | 389688.3 | 7620588.8 |  | View looking northeast along south to of Main LF
16 |  | C111_4233 | 2011-08-13 | 389687.3 | 7620588.2 |  | View looking west along south toe of Main LF. Note deposition of gravel and cobbles along toe from seasonal ponding
17 |  | C111_4234 | 2011-08-13 | 389703.1 | 7620611.2 |  | View looking southwest along south to of Main LF
18 |  | C111_4235 | 2011-08-13 | 389704.4 | 7620611.2 |  | View looking southeast along south side slope of Main LF
19 |  | C111_4236 | 2011-08-13 | 389743.7 | 7620591.6 |  | View looking northwest at southeast end of Main LF
20 |  | C111_4237 | 2011-08-13 | 389731.8 | 7620619.1 |  | View northeast along east side slope of Main LF
21 |  | C111_4238 | 2011-08-13 | 389744.3 | 7620654 |  | Panoramic view looking south to northwest from south side across Main LF
22 |  | C111_4240 | 2011-08-13 | 389715.1 | 7620695.9 |  | View looking northwest along northeast toe of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (12m L, 0.5-1.5m W, 0.02-0.05m D) - Feature C
23 |  | C111_4241 | 2011-08-13 | 389715.9 | 7620695.1 |  | View looking southeast along northeast toe of Main LF
24 |  | C111_4242 | 2011-08-13 | 389686.4 | 7620712.4 |  | View looking northeast at minor erosion near northeast corner of Main LF (6m L, 0.1m W, 0.02-0.05m D) - Feature C
25 |  | C111_4243 | 2011-08-13 | 389689.4 | 7620723.5 |  | View looking southeast along northeast toe of Main LF. Note minor erosion (fines washing) along toe from seasonal ponding (12m L, 0.5-1.5m W, 0.02-0.05m D) - Feature C
Aerial
A8 |  | C111_4272 | 2011-08-13 | 389330.4 | 7620611.6 |  | Aerial view looking northeast at Main Landfill and Station East Landfill (background)