## NE LF Photos
TABLE IX: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-1, Jenny Lind Island
Landfill: | Northeast Landfill
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis P. Eng
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
Lobes 1 & 3
9 |  | C111_4181 | 2011-08-13 | 389541.4 | 7621196.1 |  | Panoramic view looking southeast to southwest from north of NE Landfill - Lobes 1&3
10 |  | C111_4179 | 2011-08-13 | 389558.3 | 7621160.6 |  | View looking southwest along south toe of NE Landfill - Lobes 1&3
11 |  | C111_4180 | 2011-08-13 | 389557.8 | 7621168 |  | View looking west along east toe of NE Landfill - Lobes 1&3
12 |  | C111_4178 | 2011-08-13 | 389542.4 | 7621156.4 |  | View looking northwest at minor settlement on inside side slope (2m L x 1m W x 0.2m D) - FEATURE A
13 |  | C111_4177 | 2011-08-13 | 389536.1 | 7621153.9 |  | View looking north at minor settlement on inside side slope (2m L x 1m W x 0.2m D) - FEATURE A
14 |  | C111_4167 | 2011-08-13 | 389535.5 | 7621159.8 |  | View looking northeast along north toe of NE Landfill - Lobes 1&3
15 |  | C111_4166 | 2011-08-13 | 389534.9 | 7621160.3 |  | View looking northwest along north toe of NE Landfill - Lobes 1&3
16 |  | C111_4171 | 2011-08-13 | 389512.8 | 7621168.8 |  | Panoramic view looking east to southwest from north side across NE Landfill - Lobes 1&3
17 |  | C111_4168 | 2011-08-13 | 389511.8 | 7621173.9 |  | View looking southeast along north toe of NE Landfill - Lobes 1&3
18 |  | C111_4169 | 2011-08-13 | 389511.1 | 7621173.8 |  | View looking southest along north toe of NE Landfill - Lobes 1&3
19 |  | C111_4170 | 2011-08-13 | 389507.5 | 7621176.8 |  | View looking south at uneven side slope on northwest corner of NE Landfill - Lobes 1&3 (4m L, 4m W)
20 |  | C111_4172 | 2011-08-13 | 389481 | 7621139.2 |  | Panoramic view looking northeast to south-southeast from southwest corner across NE Landfill - Lobes 1&3
21 |  | C111_4174 | 2011-08-13 | 389476.4 | 7621140.2 |  | View looking northeast along west toe of NE Landfill - Lobes 1&3
22 |  | C111_4173 | 2011-08-13 | 389476.1 | 7621139.3 |  | View looking southeast along west toe of NE Landfill - Lobes 1&3
23 |  | C111_4176 | 2011-08-13 | 389487.4 | 7621122 |  | View looking northwest along west toe of NE Landfill - Lobes 1&3
24 |  | C111_4175 | 2011-08-13 | 389488.3 | 7621121.8 |  | View looking west along south toe of NE Landfill - Lobes 1&3
Lobe 2
1 |  | C111_4182 | 2011-08-13 | 389582.2 | 7621150.9 |  | View looking southwest along centerline of NE Landfill - Lobe 2
2 |  | C111_4183 | 2011-08-13 | 389578 | 7621154.3 |  | View looking southwest along west toe of NE Landfill - Lobe 2
3 |  | C111_4184 | 2011-08-13 | 389584.9 | 7621146.4 |  | View looking southwest along east toe of NE Landfill - Lobe 2
4 |  | C111_4185 | 2011-08-13 | 389542.9 | 7621117.2 |  | View looking northeast along centerline of NE Landfill - Lobe 2
5 |  | C111_4186 | 2011-08-13 | 389542.5 | 7621116.7 |  | View looking southwest along centerline of NE Landfill - Lobe 2
6 |  | C111_4187 | 2011-08-13 | 389499.4 | 7621081.1 |  | View looking northeast along centerline of NE Landfill - Lobe 2
7 |  | C111_4188 | 2011-08-13 | 389496.1 | 7621085.8 |  | View looking northeast along west toe of NE Landfill - Lobe 2
8 |  | C111_4189 | 2011-08-13 | 389504.7 | 7621076.6 |  | View looking northeast along east toe of NE Landfill - Lobe 2
Aerial
A2 |  | C111_4276 | 2011-08-13 | 389378 | 7621118.3 |  | Aerial view looking east at Northeast Landfill