## NHWLF Photos
TABLE XV: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-1, Jenny Lind Island
Landfill: | NHWLF
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis P. Eng.
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C111_4144 | 2011-08-13 | 389244.5 | 7620945.2 |  | Panoramic view looking northeast to southeast from west corner across NHWLF
2 |  | C111_4145 | 2011-08-13 | 389240 | 7620944.3 |  | View looking southeast along southwest side of NHWLF
3 |  | C111_4146 | 2011-08-13 | 389240 | 7620945.1 |  | View looking northeast along northwest side slope of NHWLF
4 |  | C111_4147 | 2011-08-13 | 389231.9 | 7620949.4 |  | View looking northeast along northwest toe of NHWLF
5 |  | C111_4148 | 2011-08-13 | 389258.3 | 7620982.5 |  | View looking northwest at MW-04 at NHWLF
6 |  | C111_4149 | 2011-08-13 | 389284.9 | 7620997.4 |  | View looking northeast at MW-03 at NHWLF
7 |  | C111_4150 | 2011-08-13 | 389280.1 | 7621003.6 |  | View looking southwest along northwest side slope of NHWLF
8 |  | C111_4151 | 2011-08-13 | 389281.7 | 7621003.2 |  | View looking southeast along northeast side slope of NHWLF
9 |  | C111_4152 | 2011-08-13 | 389280.5 | 7620982.2 |  | Panoramic view looking southeast to southwest from north corner across NHWLF
10 |  | C111_4155 | 2011-08-13 | 389296.3 | 7620955.2 |  | Exposed geotextile material on northeast cover area of NHWLF - Feature A
11 |  | C111_4156 | 2011-08-13 | 389298.7 | 7620962 |  | View looking southeast at exposed geotextile material on northeast cover area of NHWLF - Feature A
12 |  | C111_4157 | 2011-08-13 | 389323.6 | 7620937.2 |  | Panoramic view looking southwest to northwest from east corner across NHWLF. Note exposed geotextile material in foreground.
13 |  | C111_4158 | 2011-08-13 | 389335.2 | 7620939.8 |  | View looking northwest along northeast side slope of NHWLF
14 |  | C111_4159 | 2011-08-13 | 389334.7 | 7620938.4 |  | View looking southwest along southeast side slope of NHWLF
15 |  | C111_4160 | 2011-08-13 | 389318 | 7620939.5 |  | Exposed geotextile material on east cover area of NHWLF - Feature A
16 |  | C111_4161 | 2011-08-13 | 389324.9 | 7620941.6 |  | View looking west at exposed geotextile material on east cover area of NHWLF - Feature A
17 |  | C111_4162 | 2011-08-13 | 389335.7 | 7620976 |  | View looking south-southwest at MW-02 at NHWLF
18 |  | C111_4163 | 2011-08-13 | 389283.1 | 7620900.6 |  | Panoramic view looking northwest to northeast from south corner across NHWLF.
19 |  | C111_4164 | 2011-08-13 | 389253.9 | 7620936.3 |  | Exposed geotextile material on west cover area of NHWLF - Feature A
20 |  | C111_4165 | 2011-08-13 | 389250 | 7620940.5 |  | View looking southeast at exposed geotextile material on west cover area of NHWLF - Feature A
Aerial
A4 |  | C111_3991 | 2011-08-13 | 389105.5 | 7620974.2 |  | Aerial view looking east at Non-Hazardous Waste Landfill
A5 |  | C111_4274 | 2011-08-13 | 389146.4 | 7620878.9 |  | Aerial view looking northeast at Non-Hazardous Waste Landfill