## StationE LF Photos
TABLE XXIX: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-1, Jenny Lind Island
Landfill: | Station East Landfill
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis P. Eng.
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C111_4239 | 2011-08-13 | 389754.8 | 7620655 |  | Panoramic view looking north to east from southwest of Station East Landfill
2 |  | C111_4245 | 2011-08-13 | 389748.5 | 7620753.3 |  | View looking northeast along west toe of Station East Landfill. Note minor erosion of fines (3m L, 1.5m W, 0.03m D) - Feature E
3 |  | C111_4246 | 2011-08-13 | 389748.6 | 7620752.4 |  | View looking southeast along southwest toe of Station East Landfill
4 |  | C111_4247 | 2011-08-13 | 389764.3 | 7620787.1 |  | View looking south along west toe of Station East Landfill
5 |  | C111_4248 | 2011-08-13 | 389763.5 | 7620785.6 |  | View looking northeast along northwest toe of Station East Landfill
6 |  | C111_4249 | 2011-08-13 | 389767.2 | 7620784.3 |  | Panoramic view looking northeast to south from west side across Station East Landfill
7 |  | C111_4250 | 2011-08-13 | 389804.3 | 7620803.5 |  | View looking southwest along northwest toe of Station East Landfill
8 |  | C111_4251 | 2011-08-13 | 389806.4 | 7620803 |  | View looking east-southeast along north toe of Station East Landfill. Note linear depressions on right (2-4m L, 0.1-0.15m W, 0.05-0.07m D) - Feature D
9 |  | C111_4252 | 2011-08-13 | 389849.6 | 7620786 |  | View looking southeast along northeast toe of Station East Landfill
10 |  | C111_4253 | 2011-08-13 | 389848.6 | 7620786.9 |  | View looking northwest along north toe of Station East Landfill
11 |  | C111_4254 | 2011-08-13 | 389822.9 | 7620790.8 |  | View looking northwest at area of linear depressions on north side of Station East Landfill (2-4m L, 0.1-0.15m W, 0.05-0.07m D) - Feature D
12 |  | C111_4255 | 2011-08-13 | 389836.3 | 7620775.3 |  | View looking east at minor depression on northeast cover area of Station East Landfill (0.5m L, 0.4m W, 0.07 m D) - Feature D
13 |  | C111_4256 | 2011-08-13 | 389867.2 | 7620759.6 |  | View looking northwest along northeast toe of Station East Landfill
14 |  | C111_4257 | 2011-08-13 | 389867.6 | 7620757.5 |  | View looking south along east toe of Station East Landfill
15 |  | C111_4258 | 2011-08-13 | 389865.9 | 7620739.4 |  | View looking southwest along southeast toe of Station East Landfill
16 |  | C111_4259 | 2011-08-13 | 389825 | 7620715.3 |  | Panoramic view looking northwest to northeast from southeast side across Station East Landfill
17 |  | C111_4260 | 2011-08-13 | 389795.7 | 7620664.4 |  | Panoramic view looking west to northeast from south corner across Station East Landfill
18 |  | C111_4261 | 2011-08-13 | 389800.9 | 7620662.7 |  | View looking northeast along southeast side sloope of Station East Landfill
19 |  | C111_4262 | 2011-08-13 | 389800.2 | 7620662.2 |  | View looking west along south toe of Station East Landfill
20 |  | C111_4263 | 2011-08-13 | 389775.9 | 7620660 |  | View looking north-northeast along west side slope of Station East Landfill
21 |  | C111_4264 | 2011-08-13 | 389788.9 | 7620716.2 |  | View looking northwest along southwest side slope of Station East Landfill
22 |  | C111_4265 | 2011-08-13 | 389789.3 | 7620715.4 |  | View looking south along west side slope of Station East Landfill
Aerial
A8 |  | C111_4272 | 2011-08-13 | 389330.4 | 7620611.6 |  | Aerial view looking east at Main Landfill and Station East Landfill (background)