## Tier II DF Photos
TABLE XVIII: LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-1, Jenny Lind Island
Landfill: | Tier II Soil Disposal Facility
Date Inspected: August 13, 2011
Inspected by: Andrew Passalis P. Eng.
Photo | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C111_4048 | 2011-08-13 | 389177.4 | 7620721.3 |  | View looking west-northwest at east side of Tier II DF
2 |  | C111_4049 | 2011-08-13 | 389183.9 | 7620731.4 |  | Panoramic view looking southwest to northeast at east side of Tier II DF
3 |  | C111_4050 | 2011-08-13 | 389160.3 | 7620727.2 |  | View looking west-northwest at east side of Tier II DF
4 |  | C111_4059 | 2011-08-13 | 389053.4 | 7620726.5 |  | View looking west at MW-05 at Tier II DF
5 |  | C111_4062 | 2011-08-13 | 389146.9 | 7620770.7 |  | Panoramic view looking west to northwest from east corner across Tier II DF
6 |  | C111_4063 | 2011-08-13 | 389148.8 | 7620756.1 |  | View looking south at MW-05 located on southeast side of Tier II DF
7 |  | C111_4064 | 2011-08-13 | 389135.7 | 7620788.4 |  | View looking northwest at MW-06 located on the north side of Tier II DF
8 |  | C111_4066 | 2011-08-13 | 389144.1 | 7620770.7 |  | View looking northwest at VT-3 located on east cover of Tier II DF
9 |  | C111_4067 | 2011-08-13 | 389112.6 | 7620788.3 |  | Panoramic view looking east to southwest from north corner across Tier II DF
10 |  | C111_4068 | 2011-08-13 | 389113.2 | 7620782.4 |  | View looking northwest at minor erosion on northwest side slope of Tier II DF (7m L, 0.05-0.15m W, 0.01-0.03m D) - Feature B
11 |  | C111_4069 | 2011-08-13 | 389096.7 | 7620791.1 |  | View looking southeast at minor erosion on northwest side slope of Tier II DF (7m L, 0.05-0.15m W, 0.01-0.03m D) - Feature B
12 |  | C111_4070 | 2011-08-13 | 389110.9 | 7620777.8 |  | View looking northwest at minor erosion on northwest side slope of Tier II DF (10m L, 0.05-0.1m W, 0.01-0.03m D) - Feature B
13 |  | C111_4071 | 2011-08-13 | 389092.2 | 7620787.5 |  | View looking southeast at minor erosion on northwest side slope of Tier II DF (10m L, 0.05-0.1m W, 0.01-0.03m D) - Feature B
14 |  | C111_4072 | 2011-08-13 | 389098.8 | 7620763.7 |  | View looking southeast at VT-2 (foreground) and VT-4 (background) on central cover of Tier II DF
15 |  | C111_4073 | 2011-08-13 | 389100 | 7620757.6 |  | View looking northwest at minor erosion on northwest side slope of Tier II DF (8 L, 0.05-0.1m W, 0.01-0.02m D) - Feature B
16 |  | C111_4074 | 2011-08-13 | 389081.8 | 7620766.4 |  | View looking southeast at minor erosion on northwest side slope of Tier II DF (8m L, 0.05-0.1m W, 0.01-0.02m D) - Feature B
17 |  | C111_4075 | 2011-08-13 | 389083.8 | 7620737.4 |  | Panoramic view looking northeast to southeast from west corner across Tier II DF. VT-1 visible on right
18 |  | C111_4076 | 2011-08-13 | 389085.7 | 7620732.5 |  | View of VT-1 on west cover of Tier II DF
19 |  | C111_4077 | 2011-08-13 | 389080.3 | 7620735.5 |  | View looking west-southwest down slope on west corner of Tier II DF
20 |  | C111_4078 | 2011-08-13 | 389117.9 | 7620719.8 |  | Panoramic view looking west to northeast from south corner across Tier II DF
21 |  | C111_4079 | 2011-08-13 | 389119.3 | 7620716.4 |  | View looking southsoutheast down slope on south corner of Tier II DF
22 |  | C111_4080 | 2011-08-13 | 389122.1 | 7620736.8 |  | Minor depression on southeast cover of Tier II DF (0.2m L, 0.2m W, 0.03m D) - Feature A
23 |  | C111_4081 | 2011-08-13 | 389120.8 | 7620730.4 |  | View looking north-northeast at minor depression on southeast cover of Tier II DF (0.2m L, 0.2m W, 0.03m D) - Feature A
24 |  | C111_4082 | 2011-08-13 | 389129.7 | 7620689.4 |  | View looking northeast along east toe of Tier II DF
25 |  | C111_4083 | 2011-08-13 | 389129 | 7620688.7 |  | View looking northwest along south toe of Tier II DF
26 |  | C111_4084 | 2011-08-13 | 389072.9 | 7620684.2 |  | View looking northeast at south side of Tier II DF
27 |  | C111_4085 | 2011-08-13 | 389054.9 | 7620730.8 |  | View looking southeast along south toe of Tier II DF
28 |  | C111_4086 | 2011-08-13 | 389054.8 | 7620731.7 |  | View looking northeast along west toe of Tier II DF
29 |  | C111_4087 | 2011-08-13 | 389038.7 | 7620783.4 |  | View looking southeast at west side of Tier II DF. MW-07 visible in back center.
30 |  | C111_4088 | 2011-08-13 | 389052.3 | 7620803.6 |  | View looking southeast at west side of Tier II DF
31 |  | C111_4089 | 2011-08-13 | 389100.2 | 7620821.5 |  | View looking southwest along west toe of Tier II DF
32 |  | C111_4090 | 2011-08-13 | 389101.1 | 7620822 |  | View looking southeast along north toe of Tier II DF
33 |  | C111_4091 | 2011-08-13 | 389155 | 7620817.5 |  | View looking southwest at north side of Tier II DF
34 |  | C111_4092 | 2011-08-13 | 389175.3 | 7620777.9 |  | View looking northwest along north toe of Tier II DF
35 |  | C111_4093 | 2011-08-13 | 389175.3 | 7620776.7 |  | View looking southwest along east toe of Tier II DF
36 |  | C111_4266 | 2011-08-13 | 389134.9 | 7620659.7 |  | View looking northwest from access road at Tier II DF
Aerial
A6 |  | C111_4273 | 2011-08-13 | 389028.6 | 7620643.3 |  | Aerial view looking north northeast at Tier II Disposal Facility
Soil Sampling
5W |  | C111_4051 | 2011-08-13 | 389156.9 | 7620734.2 |  | Sampling location C111-5W located upgradient of Tier II DF
MW5 |  | C111_4052 | 2011-08-13 | 389160.1 | 7620739.5 |  | View southwest at C111-5W soil sample location
6W |  | C111_4054 | 2011-08-13 | 389127.5 | 7620815.4 |  | Sampling location C111-6W located downgradient of Tier II DF
MW6 |  | C111_4055 | 2011-08-13 | 389122.9 | 7620819.4 |  | View southeast at C111-6W soil sample location
7W |  | C111_4057 | 2011-08-13 | 389165.9 | 7620781.3 |  | Sampling location C111-7W located downgradient of Tier II DF
MW7 |  | C111_4058 | 2011-08-13 | 389066.1 | 7620787.9 |  | View southeast at C111-7W soil sample location
8W |  | C111_4060 | 2011-08-13 | 389048.2 | 7620730 |  | Sampling location C111-8W located downgradient of Tier II DF
MW8 |  | C111_4061 | 2011-08-13 | 389044.1 | 7620733.5 |  | View southeast at C111-8W soil sample location