## Lower site Landfill - South
Checklist Item | Present (Yes/No) | Location | Length (m) | Width (m) | Depth (m) | Extent | Description | Photographic Record | Severity Rating | Additional Comments
Settlement | Yes | Feature C | 0.40 - 1.0 | 0.20 - 0.60 | 0.10 - 0.20 | Occasional | Minor Depressions | 5, 6 | Acceptable | New Observation: Two minor Depressions (potholes) on the surface of lobe.
|  | Feature D | 6.00 | 0.15 - 0.40 | 0.05 - 0.15 |  | Minor Depression | 7, 8 | Acceptable | New Observation: Linear depression.
|  | Feature E | 0.5 | 0.5 | 0.2 |  | Minor Depressions | 11, 12 | Acceptable | New Observation: Two minor Depression (potholes) on the surface of lobe.
Erosion | Yes | Feature A | 8.00 | 4.00 | 0.3 | Occasional | Minor Superficial Erosion | 1 | Acceptable | New Observation: Minor erosion along west toe and access road, suspected location of culvert or French drain used during remediation contract.
|  | Feature H | 60.00 | 0.10- 4.00 | 0.05 - 0.25 |  | Large erosion channel | 24-28 | Marginal | Large erosion channel extending along the western toe of the landfill, with a marginal severity rating.
|  | Feature I | 4.00 | 3.00 | 0.05-0.10 |  | Minor | 32, 33 | Acceptable | New Observation: Minor erosion channel on the northwestern toe of the landfill – self armouring.
|  | Feature J | 10.00 | 0.20 - 0.75 | 0.1 |  | Minor | 14, 15 | Acceptable | New Observation: Minor erosion channel on the landfill surface extending to the crest of the eastern side slope
Frost Action | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Animal Burrows | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vegetation | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Staining | Yes | Feature G | 1.00 - 4.00 | 10.00 | N/A | Isolated | Rust coloured staining and bacterial sheen | 21 | Acceptable | New Observation: Rust coloured staining and bacterial sheen present in ponded water at the toe of east slope of the landfill.
Vegetation Stress | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Seepage Points | Yes | Feature G | 10.00 - 15.00 | 2.00 - 5.00 | N/A | Occasional | Seepage along toe and slope | 17 |  | 2 distinct wetted areas on the eastern slope and toe of the lobe, associated with Feature F.
Debris Exposed | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Presence/Condition of Monitoring Instruments | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other Feature of Note | Yes | Feature B | 2 | 0.005 - 0.02 | Unknown | Occasional | Tension crack | 2, 3 | Acceptable | New Observation: Small tension crack running perpendicular to the landfill toe.
|  | Feature F | 0.50 - 50 | 0.01- 0.02 | 0.01 - 0.05 |  | Tensile cracking | 18 - 20, 22 | Marginal | Discontinuous tensile crack running perpendicular to the east slope, from within 1 m to 3 m from the landfill toe. Discontinuous cracks present in conjunction with suspected slumping.
Additional Photographs | Yes | As indicated on CAM-5.2 | N/A | N/A | N/A | N/A | General Photographic record | N/A | N/A | No features of note, general photos of the landfill lobe for record keeping purposes
Overall Landfill Performance | Acceptable

## NHWL
Checklist Item | Present (Yes/No) | Location | Length (m) | Width (m) | Depth (m) | Extent | Description | Photographic Record | Severity Rating | Additional Comments
Settlement | Yes | Feature G | 1.25 | 0.15 | 0.05 | Isolated | Linear depression | 26, 27 | Acceptable | New Observation: Linear depression running parallel to the west side of the landfill.
Erosion | Yes | Feature A | 8.00 | 0.20 - 0.40 | 0.05 - 0.10 | Occasional | Minor erosion channel | 38, 39 | Acceptable | Minor self armouring erosion channel.
|  | Feature B | 8.00 | 0.1 | 0.05 |  | 2 minor erosion channels | 15, 16 |  | 2 minor erosion channels extending the length of the north slope of the landfill. Appear to be self armouring.
|  | Feature H | 8.00 | 1.00- 4.00 | 0.01 - 0.05 |  | 2 minor converging erosion channels | 35, 36, 37 |  | New Observation: 2 erosion channels 2 m apart at the landfill surface converge to form one 4 m wide channel 3 m from the toe. Self armouring.
|  | Feature I | 8.00 | 0.05 | 0.01 |  | Minor erosion channel | 33, 34 |  | New Observation: Self armouring erosion channel on the south slope of the landfill.
|  | Feature J | 4.00 | 0.5 | 0.05 - 0.10 |  | Minor erosion | 32, 43 - 45 |  | New Observation: Water running along toe at SW corner of landfill, within the reshaped area.
Frost Action | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Animal Burrows |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vegetation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Staining | Yes | Feature F | 0.6 | 0.2 | N/A | Isolated | Hydrocarbon Stain | 6, 7 | Acceptable | New Observation: Type A hydrocarbon stain, most likely the result of a vehicle leak.
Vegetation Stress | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Seepage Points | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Debris Exposed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Presence/Condition of Monitoring Instruments | Yes | N/A | N/A | N/A | N/A | N/A | Monitoring wells | Various | N/A | Monitoring well casings are in good condition.
Other Feature of Note | Yes | Feature C | 28.00 | 0.01 | 0.01 - 0.03 | Isolated | Tension crack | 17 | Acceptable | Tension crack extending 3/4s of the length of the northern side of the landfill, ranging 1 - 2 m from the toe.
|  | Feature D | 50 | 10 | Unknown | Isolated | Surface wetting | 25,26 | Acceptable | Approximatly 30% of the surface of the NHWL is damp, assumed to be caused by preciptation event on August 28, 2012.
|  | Feature E | 45 | 2.00 - 4.00 | 0.05 - 0.30 | Isolated | Ponded Water | 40, 44 | Acceptable | Previosuly observed ponded water at south toe of landfill.
Additional Photographs | Yes | As indicated on CAM-5.3 | N/A | N/A | N/A | N/A | General Photographic record | N/A | N/A | No features of note, general photos of the landfill lobe for record keeping purposes.
Overall Landfill Performance | Acceptable

## USAF
Checklist Item | Present (Yes/No) | Location | Length (m) | Width (m) | Depth (m) | Extent | Description | Photographic Record | Severity Rating | Additional Comments
Settlement | Yes | Feature A | 2.00 | 0.6 | 0.2 | Isolated | Linear depression | 8 | Acceptable | New Observation: Linear depression at access to Asbestos landfill, possibly caused by machinery during construction of cap.
|  | Feature C | 0.10, 1.00, 2.00 | 0.2 | 0.1 | Isolated | Minor depressions | 16 - 18 | Acceptable | New Observation: 2 linear depressions and 1 small pot hole 5 m from the western toe.
Erosion | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Frost Action |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Animal Burrows |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vegetation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Staining | Yes | Feature B | 0.4 | 0.2 | N/A | Isolated | Hydrocarbon Stain | 12 | Acceptable | New Observation: Hydrocarbon stain potentially caused by leaking equipment.
Vegetation Stress | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Seepage Points |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Debris Exposed | Yes | Feature D | 0.05 | 0.05 | Unknown | Isolated | Wood Debris | 4 | Acceptable | New Observation: Wooden Survey stake, used during construction that was not removed prior to compaction.
|  | Feature F | 0.10 | 0.15 | 0.10 (exposed) | Isolated | Landfill plaque | 3 | Acceptable | New Observation: DIAND Landfill corner mark, permit # N92X741.
Presence/Condition of Monitoring Instruments | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Other Features of Note | Yes | Feature E | 1.00 - 20.00 | 0.20 - 0.50 | 0.05 - 0.15 | Marginal | Vehicle tracks | 7, 9, 10, 20 - 22 | Acceptable | New Observation: Vehicle tracks are present at several locations on the landfill surface and rutting is present on the surrounding tundra.
|  | Feature F | 1.00 | 1.00 | 0.2 | Isolated | Granular fertilizer | 24, 25 | Acceptable | New Observation: A small pile of granular fertilizer remains at the North-east corner of the regrade, presumably leftover from land farming activities on site and poorly spread on the regrade to promote plant growth.
Additional Photographs | Yes | As indicated on CAM-5.4 | N/A | N/A | N/A | N/A | General Photographic record | N/A | N/A | No features of note, general photos of the landfill lobe for record keeping purposes.
Overall Landfill Performance | Acceptable

## Tier II
Checklist Item | Present (Yes/No) | Location | Length (m) | Width (m) | Depth (m) | Extent | Description | Photographic Record | Severity Rating | Additional Comments
Settlement | Yes | Feature A | 0.30 - 0.60 | 0.20 - 0.30 | 0.05 - 0.10 | Isolated | 4 areas of settlement (pot holes, 2 areas were observed during the baseline investigation) | 26 - 30 | Acceptable | Each area of settlement is associated with a large cobble in the landfill cover, which may have interfered with compaction resulting in the small potholes.
Erosion | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Frost Action |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Animal Burrows |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vegetation |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Staining | Yes | Feature C | 0.45 | 0.3 | N/A | Isolated | Hydrocarbon Stain | 44, 45 | Acceptable | New Observation: Hydrocarbon stain.
Vegetation Stress | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Seepage Points | Yes | Feature B | 4.00 | 3.00 | N/A | Isolated | Wet area extending from toe of landfill | 15, 16 | Acceptable | New Observation: Area of surface wetting on the south slope of the landfill and extending from the toe.
Debris Exposed | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Presence/Condition of Monitoring Instruments | Yes | N/A | N/A | N/A | N/A | N/A | Groundwater monitoring wells and thermistors | Various | N/A | Monitoring wells and thermistor casings are in good condition.
Other Features of Note | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Additional Photographs | Yes | As indicated on CAM-5.5 | N/A | N/A | N/A | N/A | General Photographic record | N/A | N/A | N/A
Overall Landfill Performance | Acceptable