{"text_format":"1","workbook":"xlsx","n_sheets":28,"sheets":["Notes for Use","Standard Form","GPS Coordinates","Format Control","Aerial Photo","Aerial photo 2","Landfarm detail","Cell volumes","Future Plans","Research","New product","MW1-MW6","New wells 2012","All Monitoring wells","Nun 1","Discharge tests","Nun 2","Nun 3","Nun 4","Nun 4 +","Nun 5 soils","Nun 5a","Nun 6","Nun 7","Nun 8","Nun 8+","Nun 9","Sheet3"],"not_rendered":{"charts":0,"images":6,"macros":1,"external_links":10,"defined_names":8,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Notes for Use","index":0,"n_rows":28,"n_cols":3,"rows_kept":28,"cut":false,"hidden":false,"merged":[[10,1,10,7],[0,0,0,5],[1,0,1,7],[4,0,4,7],[6,0,6,7],[8,0,8,7],[12,1,12,7],[14,1,14,7],[16,1,16,7],[27,2,27,4],[18,1,18,7],[24,1,24,7],[25,1,25,7],[26,1,26,7],[20,0,20,7],[21,1,21,7],[23,1,23,7],[22,1,22,7]]}
["Nunavut Water Board "]
["Standard Form for Annual Reporting Requirements of NWB2 Exploration Water Licenses"]
[]
[]
["Under the terms of your water licence issued by the Nunavut Water Board (\"NWB\") for the use of water and the disposal of waste into water associated with mineral exploration (NWB2 Licenses), Licensees are required to submit to the NWB an Annual Report no later than March 31st of the year following the calendar year being reported."]
[]
["In order to aid the Licensee with the preparation of the Annual Report and facilitate its review by the NWB, Licensees are required to use the following form."]
[]
["Recommendation and Helpful tips for use:"]
[]
[null,"Metric units shall be used to report any relevant data."]
[]
[null,"How to Add additional space within Text boxes - Right click mouse on the row number (directly to the left of your screen) which falls within the text box range and click insert. Do not drag or drop text box to modify size of the text box because formatting will not be maintained and data will be lost. If you have large amounts of data recommend adding additional worksheets.  Go to the help menu for assistance. "]
[]
[null,"Electronic versions should be submitted in Adobe to ensure protection of your information.  If you do not have shortcut keys to save as a PDF.  Go to print menu . Choose to print \"Entire Worksheet\" then select printer option Adobe PDF and you will be prompted to save the document as a PDF document.  Reminder ensure you have saved your document in Excel so that future changes can be made. "]
[]
[null,"Modify the Header - Select \"View\" then \"Header\" from the main menu. Select \"Custom Header\" and change to reflect the valid Water Licence No. "]
[]
[null,"Textboxes denoted with * are optional.  "]
[]
["Annual Reports shall be submitted by either fax, mail or email in adobe acrobat or Excel format to: "]
[null,"Nunavut Water Board"]
[null,"c/o Manager of Licensing"]
[null,"P.O. Box 119"]
[null,"Gjoa Haven, NU X0B 1J0"]
[null,"Tel: 867-360-6338"]
[null,"Fax:867-360-6369"]
[null,"Email: licensing@nwb.nunavut.ca ","licensing@nunavutwaterboard.org"]

{"sheet":"Standard Form","index":1,"n_rows":153,"n_cols":7,"rows_kept":153,"cut":false,"hidden":false,"merged":[[76,0,76,9],[77,1,77,8],[54,1,54,4],[52,2,52,3],[52,4,52,7],[53,2,53,3],[54,5,54,6],[45,3,45,8],[51,0,51,9],[60,0,60,9],[68,0,68,9],[0,0,0,1],[0,4,0,6],[7,2,7,7],[2,1,2,3],[2,4,2,5],[3,4,3,5],[34,3,34,4],[35,3,35,4],[34,5,34,8],[35,5,35,9],[9,3,9,7],[13,3,13,7],[3,6,3,7],[2,6,2,7],[5,1,5,2],[18,0,18,9],[14,1,14,8],[98,1,98,9],[87,0,87,9],[89,1,89,9],[150,0,150,1],[121,0,121,9],[129,0,129,9],[137,0,137,9],[113,1,113,9],[150,3,150,7],[36,5,36,8],[37,5,37,8],[36,3,36,4],[37,3,37,4],[28,0,28,8],[31,0,31,9],[32,3,32,8],[151,3,151,7],[152,3,152,7],[148,0,148,1],[149,0,149,1],[148,2,148,3],[149,2,149,7]]}
["NWB Annual Report",null,null,null,"Year being reported: "]
[]
["License No:","NWB4NUN0511 - Type \"B\"",null,null,"Issued Date:",null,"2005-09-13"]
[null,null,null,null,"Expiry Date: ",null,"2011-12-13"]
[]
[null,"Project Name:"]
[]
[null,"Licensee:"]
[]
[null,"Mailing Address:"]
[]
[]
[]
[]
[null,"Name of Company filing Annual Report (if different from Name of Licensee please clarify relationship between the two entities, if applicable): "]
[]
[]
[]
["General Background Information on the Project (*optional):"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Licence Requirements: the licensee must provide the following information in accodance with "]
[]
[]
["A summary report of water use and waste disposal activities, including, but not limited to: methods of obtaining water; sewage and greywater management; drill waste management; solid and hazardous waste management."]
[null,"Water Source(s):",null,"Run-off water, contaminated water from clean-up site"]
[]
[null,"Water Quantity:",null," ",null,"Quantity Allowable Domestic (cu.m)"]
[null,null,null,null,null,"Actual Quantity Used Domestic (cu.m)"]
[null,null,null,null,null,"Quantity Allowable Drilling (cu.m)"]
[null,null,null,null,null,"Total Quantity Used Drilling (cu.m)"]
[]
[null,"Waste Management and/or Disposal"]
[]
[]
[]
[]
[]
[null,null,null,"Hydrocarbon Contaminated Water from numerous sources in Iqaluit"]
[null,"Additional Details:"]
[]
[]
[]
[]
["A list of unauthorized discharges and a summary of follow-up actions taken."]
[null,"Spill No.: ",0,null,"(as reported to the Spill Hot-line)"]
[null,"Date of Spill:"]
[null,"Date of Notification to an Inspector: "]
[null,"Additional Details: (impacts to water, mitigation measures, short/long term monitoring, etc)"]
[]
[]
[]
[]
["Revisions to the Spill Contingency Plan "]
[]
[]
[null,"Additional Details: "]
[]
[]
[]
[]
["Revisions to the Abandonment and Restoration Plan"]
[]
[]
[null,"Additional Details: "]
[]
[]
[]
[]
["Progressive Reclamation Work Undertaken"]
[null,"Additional Details (i.e., work completed and future works proposed)"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Results of the Monitoring Program including:"]
[]
[null,"The GPS Co-ordinates (in degrees, minutes and seconds of latitude and longitude) of each location where sources of water are utilized; "]
[]
[]
[null,"Additional Details:"]
[]
[]
[]
[]
[]
[null,"The GPS Co-ordinates (in degrees, minutes and seconds of latitude and longitude) of each location where wastes associated with the licence are deposited; "]
[]
[]
[null,"Additional Details:"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[1]
[]
[null,"Results of any additional sampling and/or analysis that was requested by an Inspector"]
[]
[]
[null,"Additional Details: (date of request, analysis of results, data attached, etc)"]
[]
[]
[]
[]
["Any other details on water use or waste disposal requested by the Board by November 1 of the year being reported."]
[]
[]
[null,"Additional Details: (Attached or provided below)"]
[]
[]
[]
[]
["Any responses or follow-up actions on inspection/compliance reports"]
[]
[]
[null,"Additional Details: (Dates of Report, Follow-up by the Licensee)"]
[]
[]
[]
[]
["Any additional comments or information for the Board to consider"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Date Submitted:",null,"Jan 20 2013"]
["Submitted/Prepared by: ",null,"Nunatta Environmental Services Inc, Iqaluit,Nu"]
["Contact Information:",null,"Tel:","867-979-1488"]
[null,null,"Fax:","867-979-1478"]
[null,null,"email:","nunatta@northwestel.net"]

{"sheet":"GPS Coordinates","index":2,"n_rows":22,"n_cols":8,"rows_kept":22,"cut":false,"hidden":false,"merged":[[1,0,1,9],[16,0,16,9],[18,2,18,4],[18,5,18,7],[18,1,20,1],[3,2,3,4],[3,5,3,7]]}
[]
["GPS Coordinates for water sources utilized"]
[]
[null,null,"Latitude",null,null,"Longitude"]
[null,"Source Description","Deg","Min","Sec","Deg","Min","Sec"]
[null,null,"º","΄","˝","º","΄","˝"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["GPS Locations of areas of waste disposal"]
[]
[null,"Location Description (type)","Latitude",null,null,"Longitude"]
[null,null,"Deg","Min","Sec","Deg","Min","Sec"]
[null,null,"º","΄","˝","º","΄","˝"]
[null," Treated water discharge point",68,32,46.47,63,45,49.9]

{"sheet":"Format Control","index":3,"n_rows":37,"n_cols":5,"rows_kept":37,"cut":false,"hidden":true,"merged":[[10,0,10,5],[9,0,9,5],[11,0,11,5],[12,0,12,5],[21,0,21,5],[18,0,18,5],[19,0,19,5],[13,0,13,5],[16,0,16,5],[15,0,15,5],[17,0,17,5],[22,0,22,5],[34,0,34,5],[35,0,35,5],[36,0,36,5],[30,0,30,5],[31,0,31,5],[32,0,32,5],[33,0,33,5],[25,0,25,5],[29,0,29,5],[26,0,26,5],[27,0,27,5],[28,0,28,5]]}
["Select","Select",null,"Part A","Item 1"]
["Yes",2004,null,"Part B","Item 2"]
["No",2005,null,"Part C","Item 3"]
[null,2006,null,"Select","Select"]
[null,2007]
[null,2008]
[null,2009]
[null,2010]
[]
["No Spill Contingency Plan (SCP) submitted or approved"]
["SCP submitted and approved - no revision required or proposed"]
["SCP addendum attached for Board consideration"]
["Other: (see additional details)"]
["N/A - not applicable"]
["Select"]
["No Abandonment and Restoration (AR) Plan submitted or approved"]
["AR plan submitted and approved - no revision required or proposed"]
["AR addendum attached for Board consideration"]
["Other: (see additional details)"]
["N/A - not applicable "]
[]
["No additional sampling requested by an Inspector or the Board"]
["Additional sampling requested by an Inspector or the Board (See below)"]
["Select"]
[]
["No inspection and/or compliance report issued by INAC"]
["No inspection report issued by INAC"]
["No compliance report issued by INAC"]
["Inspection and Compliance Report received by the Licensee (Date):"]
["Inspection Report received by the Licensee (Date):"]
["Compliance Report received by the Licensee (Date):"]
["Select"]
[]
["Select"]
["Not Applicable (N/A)"]
["Details described below"]
["Details attached"]

{"sheet":"Aerial Photo","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Aerial photo 2","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Landfarm detail","index":6,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Cell volumes","index":7,"n_rows":20,"n_cols":7,"rows_kept":20,"cut":false,"hidden":false,"merged":[]}
["Volume of soil in landfarm"]
[]
["Cell  #","Cell Size","Material Pile","Working Volume","Rocks ","Protective layer "]
[null,"Meters","Meters","cubic M","Cubic M","cubic M"]
[1,"60x30","40x25x1.5",1500,60,500]
[]
[2,"50x25","40x20x4",1056,1056,425]
[]
[3,"90x30","60x15x4",1188,40,850]
[]
[4,"60x30","50x25x4",5000,0,500]
[null,"  "]
[null,"Total in Cubic Metres",null,{"$f":"SUM(D5:D12)","v":8744},{"$f":"SUM(E5:E12)","v":1156},{"$f":"SUM(F5:F12)","v":2275},{"$f":"SUM(D13:F13)","v":12175}]
[]
["Summary"]
["Landfarm contains    1156 cubic metres of stones and rocks"]
[null,null,"2275 Cubic metres of soil is undisturbed  to act as a protection for the geotextile liner below."]
[null,null,"8744 Cubic Metres of soil is undergoing remediation treatment"]
[]
["Grand Total",null,"12175 Cubic metres of soil and rocks contained in landfarm cells"]

{"sheet":"Future Plans","index":8,"n_rows":7,"n_cols":2,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
[]
[null,"Future Plans"]
[null,"For the next 2 years we will continue with our research with the University of Saskatchewan in testing bone Bio-Char in the remediation of hydrocarbon contaminated soils. This summer past we were delayed by the influx of heavy ocean ice which delayed the supply ships and kept us from getting our supplies early in the season. We were able to complete the trials just before freeze up. These trials involve mixing our contaminated soils with fertilizers and Bio-char at different ratio's and leaving them outdoors for the winter to test the results we got in the laboratory. In the Laboratory we found the soils we mixed with Bone Bio-Char continued to degrade the hydrocarbons with the storage temperature kept at -20C. This is well beyond the degradation levels achieved in normal soil remediation attempt in the Arctic. We believe this should allow soils contaminated by fuel spills can be returned to the environment in 1/2 the time as soils not treated. Also we have identified an enzyme unique to South Baffin Island which consumes  hydrocarbons. Inoculation of incoming soils with this enzyme will also be researched and results published."]
[]
[null,"We are looking into a way to ease the handling of waste water. By using more/larger tanks to store and treat water especially in spring of the year during the melt. We will be looking  into the construction of a holding pool, where water can  stored, tested and treated prior to discharge into the environment."]
[]
[null,"At some point we would like to explore the idea of removing cell #1 and cell #2 and creating one large cell. This would allow us room to operate our screening plants and room to store more water and even a pad on which to place barrels of waste products until a south bound ship can be arranged. Before this is attempted we will have to have an engineering firm consulted as well as the Geotextile line company for the best advice on material and construction practices."]

{"sheet":"Research","index":9,"n_rows":4,"n_cols":2,"rows_kept":4,"cut":false,"hidden":false,"merged":[]}
[null,"Research into using Bone Bio Char to remediate Arctic Soil"]
[null,"The soils at Nunatta’s Landfarm have been going through a lot of changes in the past few years. We have purchased new equipment to handle the job of aeration and screening, which has sped up the remediation process and reduced labour and equipment cost. This past summer we experienced a wet cool summer and had supply delays extend into September. This kept us from getting supplies from down south and made for a lot of work in last few weeks before freeze up. Test trials were completed but not early enough in the season to be able to chart results, this does get them started in the 2012 season so they will match the time sequence for the same test conducted in Whitehorse at Yukon College. We received some soil from a fresh spill at the Iqaluit airport and mixed these soils with some we had at the landfarm to give us a blended mixture to use in our tests. Test trials were divided into 5 groups. Two of these with different ratio's of Bone Bio-Char, one was a Wood Bio-Char, one was just fertilizers and one was untreated for baseline comparison. These trials will be monitored by University of Saskatchewan, soil toxicology department, under the watchful eye of Dr Steven Siciliano. All results will be noted here at the end of this 3 year trial period. "]
[null,"The aim of this research is to doccument our findings for an accelerated method of remediating hydrocarbon contaminated soils in Arctic conditions. In the past soils have been contained and sometimes aerated but not cleaned up enough to be released back into the envirnoment so they just sit inside containment cells until a solution can be found or they are removed and shipped south for treatment. We have found a solution and tested this in labratory environment and found results to exceed anything we could have expected in fact 3 times the degradation  achieved during summer months in this part of the world. This is because we have found a way of keeping enzymes working longer into freeze up and starting earlier before there is a complete thaw. This extends our remediation time from 3 months to 7  months. this is"]
[null,"like getting 2 years in one. The least we can expect is to cut normal remediation time in half. Our intention is to show it is possible even during freezing conditions hydrocarbon contaminated soils can be remediated in a reasonable length of time with materials availlable in the Arctic."]

{"sheet":"New product","index":10,"n_rows":7,"n_cols":2,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
[null,"New Product to be introduced to clean up hydrocarbons"]
[null,"In addition to the soil remediation we are negotiating with a company from Mexico (Canadian Owned) who has developed a new hydrocarbon bonding product called Cas 100.  This new product will aid in the clean up of fuel spills and reduce the amount of contaminated soil entering our landfarm. This new polymer will remove all oils and even the sheen from water.This will also help us in having to deal with absorbents ( booms and pads) which have become saturated with fuels."]
[null,"This product (Cas 100) is a tri-polymer that bonds to any hydrocarbon and then sets up into a rubber like product in two minutes and can be picked up and removed immediatly. After the bonding process takes place the resulting rubber can be burned to produce heat or can be disposed of in any Landfill. This bonding process will not allow hydrocarbons to be released even after many years. Cas 100 has tested to be an environmentally friendly compound."]
[null,"This white fluffy  product will absorb 3 times its weight in 30 seconds and 5 times its weight in 3 minutes and end results is 14 times its weight when allowed to continue saturation. It will float on water both before and after it has absorbed hydrocarbons. Not listed as dangerous goods before or after it has absorbed hydrocarbons. "]
[null,"Not affected by cold, no special storage required."]
[null,"Almost indefinite shelf life (affected only by direct sunlight)."]
[null,"Nunatta will be stocking this product this summer and may become the Canadian distributor."]

{"sheet":"MW1-MW6","index":11,"n_rows":26,"n_cols":14,"rows_kept":26,"cut":false,"hidden":false,"merged":[[7,12,7,13]]}
[]
[]
[null,"TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,"TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc."]
["Monitoring well ","PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,"New installation well 2012","PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
["well # 08-3","WORKORDER: 1242083",null,"PROJECT: Water Well",null,null,null,"wells #12-1, 12-2","WORKORDER: 1241199",null,"PROJECT: Water Wells New"]
[null,"REPORT DATE: 10/19/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,"REPORT DATE: 10/17/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
[null,"Parameter","Units","MDL","Regulation","Sample",null,null,"Parameter","Units","MDL","Regulation","Sample"]
[null,null,null,null,null,"MW08-3\n1242083-01",null,null,null,null,null,null,"12-1\n1241199-01","12-2\n1241199-02"]
[null,"Sample Date (m/d/y)",null,null,"Select Reg","10/13/2012",null,null,"Sample Date (m/d/y)",null,null,"Select Reg","10/10/2012","10/10/2012"]
[null,"Volatiles",null,null,null,null,null,null,"Volatiles"]
[null,"Benzene","ug/L","0.5","REGS","ND (0.5)",null,null,"Benzene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)",null,null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"Toluene","ug/L","0.5","REGS","ND (0.5)",null,null,"Toluene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)",null,null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)","ND (0.5)"]
[null,"Hydrocarbons",null,null,null,null,null,null,"Hydrocarbons"]
[null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)",null,null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)","ND (25)"]
[null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)",null,null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)","ND (100)"]
[null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)",null,null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)","ND (100)"]
[null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)",null,null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)","ND (100)"]
[null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)",null,null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)","ND (125)"]
[null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)",null,null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)","ND (200)"]
[]
[null,"This is the only well which contained enough water for testing",null,null,null,null,null,null,"These are the water results from the new wells created 2012"]

{"sheet":"New wells 2012","index":12,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["New monitoring wells installed in 2012."]

{"sheet":"All Monitoring wells","index":13,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["Location of monitoring wells used in 2012"]

{"sheet":"Nun 1","index":14,"n_rows":23,"n_cols":20,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
["2012 Water Discharge from Landfarm "]
[null,"              "]
["Date","From","To","Permission By"," Litres","cu/M","Lab Ref #","Special conditions",null,null,null,null,null,null,null,null,null,"Capacity "]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Tank","size","Litres"," "]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Black","9'x26.5'",47793]
["May 28th","Black tank","West fence","Melissa Joy",46000,46,1220208,null,"All water discharged from Landfarm was passed through",null,null,null,null,null,null,null,"Green","6'x14.5'",11476]
[null,null,null,null,null,null,null,null,"activated carbon filters even if it passed the Lab tests",null,null,null,null,null,null,null,"white","4'2\"x12'2\"",4600]
["May 28th","Green tank","West fence","Melissa Joy",11000,11,1220208,null,"this was done to ensure there was no chance of contamination."]
[null,null,null,null,null,null,null,null,"to the receiving environment"]
["Aug 9th","Black tank","West fence","Melissa Joy",45000,45,1229078]
[]
["Aug 9th","Green tank","West fence","Melissa Joy",10000,10,1229078]
[]
["Sept 24th","Green tank","West fence","Melissa Joy",10000,10,1238086]
[]
["sept 28th","Black tank","West fence","Melissa Joy/Andrew Keim",45000,45,1239019]
[]
["Oct 10th","Green tank","West fence","Melissa Joy",11000,45,1239182]
[]
["Oct 14th","Black tank","West fence","Melissa Joy",45000,45,1242082]
[null,null,null,null,null,null,null,null,"Lab results can be viewed on tab called Discharge test results"]
[null,null,null,"Totals",{"$f":"SUM(E6:E21)","v":223000},223]
[null,null,null,null,"Litres","C/m"]

{"sheet":"Discharge tests","index":15,"n_rows":49,"n_cols":23,"rows_kept":49,"cut":false,"hidden":false,"merged":[[7,5,7,7],[7,15,7,16]]}
["Discharge test results"]
[]
[null,"2023-05-01",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,null,null,null,"July 20th",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,"Sept 21st",null,"CLIENT: Nunatta Environmental Services Inc."]
[null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
[null,"WORKORDER: 1220208",null,"PROJECT: Discharge Water 2012",null,null,null,null,null,null,null,"WORKORDER: 1229078",null,"PROJECT: Discharge Water",null,null,null,null,"WORKORDER: 1238086",null,"PROJECT: Landfarm Discharge"]
[null,"REPORT DATE: 05/23/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,null,null,null,"REPORT DATE: 07/20/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,"REPORT DATE: 09/21/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
[null,"Parameter","Units","MDL","Regulation","Sample",null,null,null,null,null,"Parameter","Units","MDL","Regulation","Sample",null,null,"Parameter","Units","MDL","Regulation","Sample"]
[null,null,null,null,null,"Black Tank\n1220208-01","Green Tank\n1220208-02",null,null,null,null,null,null,null,null,"Black Tank\n1229078-01","Green Tank\n1229078-02",null,null,null,null,null,"Green Tank\n1238086-01"]
[null,"Sample Date (m/d/y)",null,null,"CCME Fresh Water Aquatic","05/16/2012","05/16/2012",null,null,null,null,"Sample Date (m/d/y)",null,null,"Select Reg","07/13/2012","07/13/2012",null,"Sample Date (m/d/y)",null,null,"Select Reg","09/17/2012"]
[null,"Volatiles",null,null,null,null,null,null,null,null,null,"Volatiles",null,null,null,null,null,null,"Volatiles"]
[null,"Benzene","ug/L","0.5","370 ug/L","ND (0.5)","ND (0.5)",null,null,null,null,"Benzene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"Benzene","ug/L","0.5","REGS","ND (0.5)"]
[null,"Ethylbenzene","ug/L","0.5","90 ug/L","ND (0.5)","ND (0.5)",null,null,null,null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)"]
[null,"Toluene","ug/L","0.5","2 ug/L","ND (0.5)","ND (0.5)",null,null,null,null,"Toluene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"Toluene","ug/L","0.5","REGS","ND (0.5)"]
[null,"m/p-Xylene","ug/L","0.5",null,"ND (0.5)","ND (0.5)",null,null,null,null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)"]
[null,"o-Xylene","ug/L","0.5",null,"ND (0.5)","ND (0.5)",null,null,null,null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)"]
[null,"Xylenes, total","ug/L","0.5",null,"ND (0.5)","ND (0.5)",null,null,null,null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)","ND (0.5)",null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)"]
[null,"Hydrocarbons",null,null,null,null,null,null,null,null,null,"Hydrocarbons",null,null,null,null,null,null,"Hydrocarbons"]
[null,"F1 PHCs (C6-C10)","ug/L","25",null,"ND (25)","ND (25)",null,null,null,null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)","ND (25)",null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)"]
[null,"F2 PHCs (C10-C16)","ug/L","100",null,"ND (100)","ND (100)",null,null,null,null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)","ND (100)",null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)"]
[null,"F3 PHCs (C16-C34)","ug/L","100",null,"ND (100)","ND (100)",null,null,null,null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)","ND (100)",null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)"]
[null,"F4 PHCs (C34-C50)","ug/L","100",null,"ND (100)","ND (100)",null,null,null,null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)","100",null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)"]
[null,"F1 + F2 PHCs","ug/L","125",null,"ND (125)","ND (125)",null,null,null,null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)","ND (125)",null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)"]
[null,"F3 + F4 PHCs","ug/L","200",null,"ND (200)","ND (200)",null,null,null,null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)","ND (200)",null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)"]
["Scroll down for more results"]
[]
[]
[null,"Sept 21st",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,null,null,null,"Oct 02nd",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,"Oct 14th",null,"CLIENT: Nunatta Environmental Services Inc."]
[null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
[null,"WORKORDER: 1239019",null,"PROJECT: Black Tank Discharge",null,null,null,null,null,null,null,"WORKORDER: 1239182",null,"PROJECT: Green Tank",null,null,null,null,"WORKORDER: 1242082",null,"PROJECT: Discharge Black Tank"]
[null,"REPORT DATE: 09/27/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,null,null,null,"REPORT DATE: 10/02/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,"REPORT DATE: 10/19/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
[null,"Parameter","Units","MDL","Regulation","Sample",null,null,null,null,null,"Parameter","Units","MDL","Regulation","Sample",null,null,"Parameter","Units","MDL","Regulation","Sample"]
[null,null,null,null,null,"Black Tank\n1239019-01",null,null,null,null,null,null,null,null,null,"Green Tank\n1239182-01",null,null,null,null,null,null,"Black Tank\n1242082-01"]
[null,"Sample Date (m/d/y)",null,null,"Select Reg","09/23/2012",null,null,null,null,null,"Sample Date (m/d/y)",null,null,"Select Reg","09/26/2012",null,null,"Sample Date (m/d/y)",null,null,"Select Reg","10/14/2012"]
[null,"Volatiles",null,null,null,null,null,null,null,null,null,"Volatiles",null,null,null,null,null,null,"Volatiles"]
[null,"Benzene","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"Benzene","ug/L","0.5","REGS","ND (0.5)",null,null,"Benzene","ug/L","0.5","REGS","3.1"]
[null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)",null,null,"Ethylbenzene","ug/L","0.5","REGS","ND (0.5)"]
[null,"Toluene","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"Toluene","ug/L","0.5","REGS","ND (0.5)",null,null,"Toluene","ug/L","0.5","REGS","7.5"]
[null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,"m/p-Xylene","ug/L","0.5","REGS","ND (0.5)"]
[null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)",null,null,"o-Xylene","ug/L","0.5","REGS","ND (0.5)"]
[null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)",null,null,null,null,null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)",null,null,"Xylenes, total","ug/L","0.5","REGS","ND (0.5)"]
[null,"Hydrocarbons",null,null,null,null,null,null,null,null,null,"Hydrocarbons",null,null,null,null,null,null,"Hydrocarbons"]
[null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)",null,null,null,null,null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)",null,null,"F1 PHCs (C6-C10)","ug/L","25","REGS","ND (25)"]
[null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)",null,null,null,null,null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)",null,null,"F2 PHCs (C10-C16)","ug/L","100","REGS","ND (100)"]
[null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)",null,null,null,null,null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)",null,null,"F3 PHCs (C16-C34)","ug/L","100","REGS","ND (100)"]
[null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)",null,null,null,null,null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)",null,null,"F4 PHCs (C34-C50)","ug/L","100","REGS","ND (100)"]
[null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)",null,null,null,null,null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)",null,null,"F1 + F2 PHCs","ug/L","125","REGS","ND (125)"]
[null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)",null,null,null,null,null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)",null,null,"F3 + F4 PHCs","ug/L","200","REGS","ND (200)"]

{"sheet":"Nun 2","index":16,"n_rows":13,"n_cols":4,"rows_kept":13,"cut":false,"hidden":false,"merged":[]}
["Water pumped from cell #1"]
[]
["Date","Litres pumped","From","To"]
["May 7th",6000,"cell#1","Black tank"]
["May 8th",40000,null,"cell #4"]
["May 9th",10000,null,"cell #4"]
["May 9th",5000,null,"cell #4"]
["May 10th",6000,null,"cell #4"]
["May 10th",12000,null,"cell #4"]
["May 10th",9000,null,"cell #4"]
["May 10th",18000,null,"cell #4"]
["Total Litres",{"$f":"SUM(B4:B11)","v":106000},null,"cell #4"]
["Total Cu/M","106 C/M"]

{"sheet":"Nun 3","index":17,"n_rows":18,"n_cols":4,"rows_kept":18,"cut":false,"hidden":false,"merged":[]}
["Water pumped from cell #2"]
[]
["Date","Litres pumped","From","To"]
["May 7th",8000,"Cell #2","Black Tank"]
[null,7000,null,"Black Tank"]
[null,8000,null,"Black Tank"]
[null,7000,null,"Black Tank"]
[null,12000,null,"Green tank"]
["May 8th",4500,null,"White tank"]
[null,4500,null,"Grey tank"]
[null,45000,null,"Cell 4"]
["May 9th",20000,null,"Cell 4"]
["May 10th",9000,null,"Cell 4"]
[null,8000,null,"Cell 4"]
["May 14th",5000,null,"Black Tank"]
[]
["Total Litres",{"$f":"SUM(B4:B15)","v":138000}]
["Total Cu/M",138]

{"sheet":"Nun 4","index":18,"n_rows":17,"n_cols":4,"rows_kept":17,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["Water pumpred from Cell #3"]
[]
["Date","Litres pumped","From","To"]
["May 7th",11500,"Cell #3","Green tank"]
["May 9th",20000,null,"Cell #4"]
["May 9th",5000,null,"Cell #4"]
["May 10th",30000,null,"cell #4"]
["May 10th",9000,null,"Cell #4"]
["May 14th",30000,null,"Black Tank"]
["May 14th",10000,null,"Black tank"]
["May 10th ",11400,null,"Green tank"]
[]
[]
[]
[]
["Total Litres",{"$f":"SUM(B4:B15)","v":126900}]
["Total Cu/M",126.9]

{"sheet":"Nun 4 +","index":19,"n_rows":23,"n_cols":5,"rows_kept":23,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["water pumped from cell #4"]
[]
["Date","Litres pumped","From","To"]
["May 29th",30000,"Cell# 4","Black Tank"]
[null,17500,null,"Black Tank"]
[null,11700,null,"Green Tank","Cell# 2 contains all our screened out rocks. Water from cell 4 is used to wash contaminated soils from these rocks."]
["June 19th",46000,null,"Black Tank"]
[null,11400,null,"Green Tank"]
[null,90000,null,"Cell# 1"]
["July 16th",50000,null,"Cell# 2","Washing rocks"]
[null,30000,null,"Cell# 2","washing rocks"]
[null,130000,null,"Cell# 1"]
["Aug 10th",45000,null,"Black Tank"]
[null,11000,null,"Green Tank"]
["Aug 25th",45000,null,"Black Tank"]
[null,11000,null,"Green Tank"]
["Sept 5th",90000,null,"Cell# 2","washing rocks"]
["Sept 11th",60000,null,"Cell# 2","washing rocks"]
["Sept 24th",11000,null,"Green Tank"]
["Sept 28th",45000,null,"Black Tank"]
[]
["Total Litres",{"$f":"SUM(B4:B20)","v":734600}]
["Total Cu/M",735.6]

{"sheet":"Nun 5 soils","index":20,"n_rows":33,"n_cols":4,"rows_kept":33,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,null,null,"Nunatta Environmental Services Inc."]
[]
[]
[]
[null,null,"Received, Oil - Impacted Soil"]
[null,null,null,"As of December 31, 2012"]
[]
[]
["Soils received in 2012"]
[]
[null,null,"CUSTOMER","SOILS"]
[null,null,null,"c/m"]
[]
[]
[null,"Project #"]
[null,"12-01","Paul Murphy 2488",1.25]
[null,"12-02","Andrew Tagak 2412",88.5]
[null,"12-07","Kudlik Construction",4]
[null,"12-09","Qulliq Energy Corp",27]
[null,"12-14","City Arena",220.5]
[null,"12-17","Solomon Awa 4148",61.25]
[null,"12-21","Qulliq Energy Corp",2]
[null,"12-22","IQA house 219",124]
[null,"12-30","Dowland con. 135 C",2]
[null,"12-32","Peregrine Diamonds",6]
[null,"12-45","Qikiqtaaluk Logistics",287.89999999999998]
[null,"12-36","Nunavut Excavating",5]
[null,"12-40,","Peregrine Diamonds",2.5]
[null,null,"2012 year end  Total ",{"$f":"SUM(D20:D32)","v":831.9}]

{"sheet":"Nun 5a","index":21,"n_rows":26,"n_cols":5,"rows_kept":26,"cut":false,"hidden":false,"merged":[]}
["Snow and water received in 2012"]
[]
[]
[]
[null,null,null,"Nunatta Environmental Services Inc."]
[]
[]
[]
[null,null,"Received , Oil - Impacted Snow and water"]
[null,null,null,"As of December 31, 2012"]
[]
[]
[]
[]
[null,"Project #","CUSTOMER","Snow","Water"]
[null,null,null,"Cm","C/M"]
[]
[]
[]
[null,"12-01","Paul Murphy 2488",3.54,1.25]
[null,"12-14","City Arena",10,21.73]
[null,"12-17","Solomon Awa 4148",8,49.4]
[null,"12-21","Qulliq Energy Corp",null,118.2]
[null,"12-33","Kudlik Construction",null,19.2]
[null,"12-50","Ministry of Environment",64]
[null,null,"Total cubic metres ",{"$f":"SUM(D20:D25)","v":85.539999999999992},{"$f":"SUM(E20:E25)","v":209.77999999999997}]

{"sheet":"Nun 6","index":22,"n_rows":83,"n_cols":13,"rows_kept":83,"cut":false,"hidden":false,"merged":[[7,4,7,5],[7,11,7,12]]}
["Soils in Cell# 1","Spring of 2012",null,null,null,null,null,"Soils in Cell# 1","Fall of 2012"]
[]
["TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,"TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc."]
["PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
["WORKORDER: 1228083",null,"PROJECT: Land Farm Thaw",null,null,null,null,"WORKORDER: 1242094",null,"PROJECT: Soils Land Farm Cell 3, 4, 1"]
["REPORT DATE: 07/18/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,"REPORT DATE: 10/19/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
["Parameter","Units","MDL","Regulation","Sample",null,null,"Parameter","Units","MDL","Regulation","Sample"]
[null,null,null,null,"Cell #1 Front\n1228083-01","Cell #1 Back\n1228083-02",null,null,null,null,null,"Cell 1 Front\n1242094-05","Cell 1 Back\n1242094-06"]
["Sample Date (m/d/y)",null,null,"Select Reg","07/07/2012","07/07/2012",null,"Sample Date (m/d/y)",null,null,"Select Reg","10/13/2012","10/13/2012"]
["Physical Characteristics",null,null,null,null,null,null,"Physical Characteristics"]
["% Solids","% by Wt.","0.1","REGS","94.8","73.4",null,"% Solids","% by Wt.","0.1","REGS","92.0","90.7"]
["Microbiological Parameters",null,null,null,null,null,null,"Microbiological Parameters"]
["Standard Plate Count","CFU/g","1000","REGS","ND (10000)","ND (10000)",null,"Standard Plate Count","CFU/g","1000","REGS","94000","46000"]
["General Inorganics",null,null,null,null,null,null,"General Inorganics"]
["Nitrogen, Total","ug/g","11","REGS","208","177",null,"Nitrogen, Total","ug/g","21","REGS","N/A","N/A"]
["Phosphorus, total","ug/g dry","1","REGS","692","401",null,"Phosphorus, total","ug/g dry","1","REGS","N/A","N/A"]
["Total Kjeldahl Nitrogen","ug/g dry","10","REGS","208","177",null,"Total Kjeldahl Nitrogen","ug/g dry","10","REGS","N/A","N/A"]
["Anions",null,null,null,null,null,null,"Anions"]
["Nitrate as N","ug/g dry","1","REGS","ND (1)","ND (1)",null,"Nitrate as N","ug/g dry","1","REGS","N/A","N/A"]
["Metals",null,null,null,null,null,null,"Metals"]
["Antimony","ug/g dry","1","REGS","ND (1)","ND (1)",null,"Antimony","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Arsenic","ug/g dry","1","REGS","1","ND (1)",null,"Arsenic","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Barium","ug/g dry","1","REGS","24","31",null,"Barium","ug/g dry","1","REGS","24","25"]
["Beryllium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)",null,"Beryllium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)"]
["Boron","ug/g dry","5","REGS","ND (5.0)","ND (5.0)",null,"Boron","ug/g dry","5","REGS","ND (5.0)","ND (5.0)"]
["Cadmium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)",null,"Cadmium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)"]
["Chromium","ug/g dry","5","REGS","13","16",null,"Chromium","ug/g dry","5","REGS","22","19"]
["Cobalt","ug/g dry","1","REGS","4","4",null,"Cobalt","ug/g dry","1","REGS","5","4"]
["Copper","ug/g dry","5","REGS","10","10",null,"Copper","ug/g dry","5","REGS","11","11"]
["Iron","ug/g dry","200","REGS","14100","15800",null,"Iron","ug/g dry","200","REGS","15600","14800"]
["Lead","ug/g dry","1","REGS","7","7",null,"Lead","ug/g dry","1","REGS","10","9"]
["Molybdenum","ug/g dry","1","REGS","2","ND (1)",null,"Molybdenum","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Nickel","ug/g dry","5","REGS","6","7",null,"Nickel","ug/g dry","5","REGS","8","7"]
["Potassium","ug/g dry","200","REGS","453","553",null,"Potassium","ug/g dry","200","REGS","N/A","N/A"]
["Selenium","ug/g dry","1","REGS","1","ND (1)",null,"Selenium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Silver","ug/g dry","0.3","REGS","ND (0.3)","ND (0.3)",null,"Silver","ug/g dry","0.3","REGS","ND (0.3)","ND (0.3)"]
["Thallium","ug/g dry","1","REGS","ND (1)","ND (1)",null,"Thallium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Tin","ug/g dry","5","REGS","ND (5)","ND (5)",null,"Tin","ug/g dry","5","REGS","ND (5)","ND (5)"]
["Uranium","ug/g dry","1","REGS","ND (1)","ND (1)",null,"Uranium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Vanadium","ug/g dry","10","REGS","27","33",null,"Vanadium","ug/g dry","10","REGS","46","42"]
["Zinc","ug/g dry","20","REGS","31","34",null,"Zinc","ug/g dry","20","REGS","37","45"]
["Volatiles",null,null,null,null,null,null,"Volatiles"]
["Benzene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzene","ug/g dry","0.02","REGS","N/A","N/A"]
["Ethylbenzene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"Ethylbenzene","ug/g dry","0.05","REGS","N/A","N/A"]
["Toluene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"Toluene","ug/g dry","0.05","REGS","N/A","N/A"]
["m/p-Xylene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"m/p-Xylene","ug/g dry","0.05","REGS","N/A","N/A"]
["o-Xylene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"o-Xylene","ug/g dry","0.05","REGS","N/A","N/A"]
["Xylenes, total","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"Xylenes, total","ug/g dry","0.05","REGS","N/A","N/A"]
["Benzene","ug/g dry","0.002","REGS","N/A","N/A",null,"Benzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Ethylbenzene","ug/g dry","0.002","REGS","N/A","N/A",null,"Ethylbenzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Toluene","ug/g dry","0.002","REGS","N/A","N/A",null,"Toluene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["m/p-Xylene","ug/g dry","0.002","REGS","N/A","N/A",null,"m/p-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["o-Xylene","ug/g dry","0.002","REGS","N/A","N/A",null,"o-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Xylenes, total","ug/g dry","0.002","REGS","N/A","N/A",null,"Xylenes, total","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Hydrocarbons",null,null,null,null,null,null,"Hydrocarbons"]
["F1 PHCs (C6-C10)","ug/g dry","7","REGS","10","19",null,"F1 PHCs (C6-C10)","ug/g dry","7","REGS","ND (7)","ND (7)"]
["F2 PHCs (C10-C16)","ug/g dry","4","REGS","129","433",null,"F2 PHCs (C10-C16)","ug/g dry","4","REGS","214","231"]
["F3 PHCs (C16-C34)","ug/g dry","8","REGS","80","144",null,"F3 PHCs (C16-C34)","ug/g dry","8","REGS","452","457"]
["F4 PHCs (C34-C50)","ug/g dry","6","REGS","6","ND (6)",null,"F4 PHCs (C34-C50)","ug/g dry","6","REGS","211","158"]
["Semi-Volatiles",null,null,null,null,null,null,"Semi-Volatiles"]
["Acenaphthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Acenaphthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Acenaphthylene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Acenaphthylene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Benzo[a]anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzo[a]anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Benzo[a]pyrene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzo[a]pyrene","ug/g dry","0.02","REGS","0.02","0.02"]
["Benzo[b]fluoranthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzo[b]fluoranthene","ug/g dry","0.02","REGS","0.03","ND (0.02)"]
["Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","0.02","0.05"]
["Benzo[k]fluoranthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Benzo[k]fluoranthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["1,1-Biphenyl","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"1,1-Biphenyl","ug/g dry","0.02","REGS","0.04","ND (0.02)"]
["Chrysene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Chrysene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Fluoranthene","ug/g dry","0.02","REGS","0.02","ND (0.02)",null,"Fluoranthene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Fluorene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Fluorene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","ND (0.02)","0.04"]
["1-Methylnaphthalene","ug/g dry","0.02","REGS","0.04","ND (0.02)",null,"1-Methylnaphthalene","ug/g dry","0.02","REGS","0.06","0.05"]
["2-Methylnaphthalene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)",null,"2-Methylnaphthalene","ug/g dry","0.02","REGS","0.05","0.06"]
["Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","0.06","ND (0.04)",null,"Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","0.11","0.11"]
["Naphthalene","ug/g dry","0.01","REGS","ND (0.01)","ND (0.01)",null,"Naphthalene","ug/g dry","0.01","REGS","ND (0.01)","0.03"]
["Phenanthrene","ug/g dry","0.02","REGS","0.02","ND (0.02)",null,"Phenanthrene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Pyrene","ug/g dry","0.02","REGS","0.02","ND (0.02)",null,"Pyrene","ug/g dry","0.02","REGS","0.03","0.02"]
["PCBs",null,null,null,null,null,null,"PCBs"]
["PCBs, total","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)",null,"PCBs, total","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)"]

{"sheet":"Nun 7","index":23,"n_rows":3,"n_cols":1,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["Cell #2 is now used for rock and cobble storage."]
[]
["No samples were taken from this cell this year as depositing of rocks and cobbles lasted well into freeze up. Soils washed from rocks will be deposited in bottom of pile and will be tested in the event the rocks are to be removed from the cell for use in crushing or filling of large holes or in road construction."]

{"sheet":"Nun 8","index":24,"n_rows":83,"n_cols":14,"rows_kept":83,"cut":false,"hidden":false,"merged":[[7,4,7,5],[7,12,7,13]]}
["Cell# 3 spring 2012",null,null,null,null,null,null,null,"Cell# 3 Fall 2012"]
[]
["TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,null,"TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc."]
["PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
["WORKORDER: 1228083",null,"PROJECT: Land Farm Thaw",null,null,null,null,null,"WORKORDER: 1242094",null,"PROJECT: Soils Land Farm Cell 3, 4, 1"]
["REPORT DATE: 07/18/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,null,"REPORT DATE: 10/19/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
["Parameter","Units","MDL","Regulation",null,null,null,null,"Parameter","Units","MDL","Regulation","Sample"]
[null,null,null,null,"Cell #3 Front\n1228083-03","Cell #3 Back\n1228083-04",null,null,null,null,null,null,"Cell 3 South\n1242094-01","Cell 3 North\n1242094-02"]
["Sample Date (m/d/y)",null,null,"Select Reg","07/07/2012","07/07/2012",null,null,"Sample Date (m/d/y)",null,null,"Select Reg","10/13/2012","10/13/2012"]
["Physical Characteristics",null,null,null,null,null,null,null,"Physical Characteristics"]
["% Solids","% by Wt.","0.1","REGS","92.8","92.1",null,null,"% Solids","% by Wt.","0.1","REGS","90.5","89.6"]
["Microbiological Parameters",null,null,null,null,null,null,null,"Microbiological Parameters"]
["Standard Plate Count","CFU/g","1000","REGS","ND (10000)","ND (10000)",null,null,"Standard Plate Count","CFU/g","1000","REGS","ND (10000)","ND (10000)"]
["General Inorganics",null,null,null,null,null,null,null,"General Inorganics"]
["Nitrogen, Total","ug/g","11","REGS","400","400",null,null,"Nitrogen, Total","ug/g","21","REGS","490","534"]
["Phosphorus, total","ug/g dry","1","REGS","670","681",null,null,"Phosphorus, total","ug/g dry","1","REGS","735","616"]
["Total Kjeldahl Nitrogen","ug/g dry","10","REGS","400","400",null,null,"Total Kjeldahl Nitrogen","ug/g dry","10","REGS","487","534"]
["Anions",null,null,null,null,null,null,null,"Anions"]
["Nitrate as N","ug/g dry","1","REGS","ND (1)","ND (1)",null,null,"Nitrate as N","ug/g dry","1","REGS","3","ND (1)"]
["Metals",null,null,null,null,null,null,null,"Metals"]
["Antimony","ug/g dry","1","REGS","N/A","N/A",null,null,"Antimony","ug/g dry","1","REGS","N/A","N/A"]
["Arsenic","ug/g dry","1","REGS","N/A","N/A",null,null,"Arsenic","ug/g dry","1","REGS","N/A","N/A"]
["Barium","ug/g dry","1","REGS","N/A","N/A",null,null,"Barium","ug/g dry","1","REGS","N/A","N/A"]
["Beryllium","ug/g dry","0.5","REGS","N/A","N/A",null,null,"Beryllium","ug/g dry","0.5","REGS","N/A","N/A"]
["Boron","ug/g dry","5","REGS","N/A","N/A",null,null,"Boron","ug/g dry","5","REGS","N/A","N/A"]
["Cadmium","ug/g dry","0.5","REGS","N/A","N/A",null,null,"Cadmium","ug/g dry","0.5","REGS","N/A","N/A"]
["Chromium","ug/g dry","5","REGS","N/A","N/A",null,null,"Chromium","ug/g dry","5","REGS","N/A","N/A"]
["Cobalt","ug/g dry","1","REGS","N/A","N/A",null,null,"Cobalt","ug/g dry","1","REGS","N/A","N/A"]
["Copper","ug/g dry","5","REGS","N/A","N/A",null,null,"Copper","ug/g dry","5","REGS","N/A","N/A"]
["Iron","ug/g dry","200","REGS","N/A","N/A",null,null,"Iron","ug/g dry","200","REGS","N/A","N/A"]
["Lead","ug/g dry","1","REGS","N/A","N/A",null,null,"Lead","ug/g dry","1","REGS","N/A","N/A"]
["Molybdenum","ug/g dry","1","REGS","N/A","N/A",null,null,"Molybdenum","ug/g dry","1","REGS","N/A","N/A"]
["Nickel","ug/g dry","5","REGS","N/A","N/A",null,null,"Nickel","ug/g dry","5","REGS","N/A","N/A"]
["Potassium","ug/g dry","200","REGS","631","657",null,null,"Potassium","ug/g dry","200","REGS","415","620"]
["Selenium","ug/g dry","1","REGS","N/A","N/A",null,null,"Selenium","ug/g dry","1","REGS","N/A","N/A"]
["Silver","ug/g dry","0.3","REGS","N/A","N/A",null,null,"Silver","ug/g dry","0.3","REGS","N/A","N/A"]
["Thallium","ug/g dry","1","REGS","N/A","N/A",null,null,"Thallium","ug/g dry","1","REGS","N/A","N/A"]
["Tin","ug/g dry","5","REGS","N/A","N/A",null,null,"Tin","ug/g dry","5","REGS","N/A","N/A"]
["Uranium","ug/g dry","1","REGS","N/A","N/A",null,null,"Uranium","ug/g dry","1","REGS","N/A","N/A"]
["Vanadium","ug/g dry","10","REGS","N/A","N/A",null,null,"Vanadium","ug/g dry","10","REGS","N/A","N/A"]
["Zinc","ug/g dry","20","REGS","N/A","N/A",null,null,"Zinc","ug/g dry","20","REGS","N/A","N/A"]
["Volatiles",null,null,null,null,null,null,null,"Volatiles"]
["Benzene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzene","ug/g dry","0.02","REGS","N/A","N/A"]
["Ethylbenzene","ug/g dry","0.05","REGS","N/A","N/A",null,null,"Ethylbenzene","ug/g dry","0.05","REGS","N/A","N/A"]
["Toluene","ug/g dry","0.05","REGS","N/A","N/A",null,null,"Toluene","ug/g dry","0.05","REGS","N/A","N/A"]
["m/p-Xylene","ug/g dry","0.05","REGS","N/A","N/A",null,null,"m/p-Xylene","ug/g dry","0.05","REGS","N/A","N/A"]
["o-Xylene","ug/g dry","0.05","REGS","N/A","N/A",null,null,"o-Xylene","ug/g dry","0.05","REGS","N/A","N/A"]
["Xylenes, total","ug/g dry","0.05","REGS","N/A","N/A",null,null,"Xylenes, total","ug/g dry","0.05","REGS","N/A","N/A"]
["Benzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"Benzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Ethylbenzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"Ethylbenzene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Toluene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"Toluene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["m/p-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"m/p-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["o-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"o-Xylene","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Xylenes, total","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)",null,null,"Xylenes, total","ug/g dry","0.002","REGS","ND (0.002)","ND (0.002)"]
["Hydrocarbons",null,null,null,null,null,null,null,"Hydrocarbons"]
["F1 PHCs (C6-C10)","ug/g dry","7","REGS","ND (7)","ND (7)",null,null,"F1 PHCs (C6-C10)","ug/g dry","7","REGS","ND (7)","ND (7)"]
["F2 PHCs (C10-C16)","ug/g dry","4","REGS","153","196",null,null,"F2 PHCs (C10-C16)","ug/g dry","4","REGS","32","149"]
["F3 PHCs (C16-C34)","ug/g dry","8","REGS","433","404",null,null,"F3 PHCs (C16-C34)","ug/g dry","8","REGS","177","777"]
["F4 PHCs (C34-C50)","ug/g dry","6","REGS","75","81",null,null,"F4 PHCs (C34-C50)","ug/g dry","6","REGS","101","205"]
["Semi-Volatiles",null,null,null,null,null,null,null,"Semi-Volatiles"]
["Acenaphthene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Acenaphthene","ug/g dry","0.02","REGS","N/A","N/A"]
["Acenaphthylene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Acenaphthylene","ug/g dry","0.02","REGS","N/A","N/A"]
["Anthracene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Anthracene","ug/g dry","0.02","REGS","N/A","N/A"]
["Benzo[a]anthracene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzo[a]anthracene","ug/g dry","0.02","REGS","N/A","N/A"]
["Benzo[a]pyrene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzo[a]pyrene","ug/g dry","0.02","REGS","N/A","N/A"]
["Benzo[b]fluoranthene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzo[b]fluoranthene","ug/g dry","0.02","REGS","N/A","N/A"]
["Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","N/A","N/A"]
["Benzo[k]fluoranthene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Benzo[k]fluoranthene","ug/g dry","0.02","REGS","N/A","N/A"]
["1,1-Biphenyl","ug/g dry","0.02","REGS","N/A","N/A",null,null,"1,1-Biphenyl","ug/g dry","0.02","REGS","N/A","N/A"]
["Chrysene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Chrysene","ug/g dry","0.02","REGS","N/A","N/A"]
["Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","N/A","N/A"]
["Fluoranthene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Fluoranthene","ug/g dry","0.02","REGS","N/A","N/A"]
["Fluorene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Fluorene","ug/g dry","0.02","REGS","N/A","N/A"]
["Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","N/A","N/A"]
["1-Methylnaphthalene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"1-Methylnaphthalene","ug/g dry","0.02","REGS","N/A","N/A"]
["2-Methylnaphthalene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"2-Methylnaphthalene","ug/g dry","0.02","REGS","N/A","N/A"]
["Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","N/A","N/A",null,null,"Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","N/A","N/A"]
["Naphthalene","ug/g dry","0.01","REGS","N/A","N/A",null,null,"Naphthalene","ug/g dry","0.01","REGS","N/A","N/A"]
["Phenanthrene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Phenanthrene","ug/g dry","0.02","REGS","N/A","N/A"]
["Pyrene","ug/g dry","0.02","REGS","N/A","N/A",null,null,"Pyrene","ug/g dry","0.02","REGS","N/A","N/A"]
["PCBs",null,null,null,null,null,null,null,"PCBs"]
["PCBs, total","ug/g dry","0.05","REGS","N/A","N/A",null,null,"PCBs, total","ug/g dry","0.05","REGS","N/A","N/A"]

{"sheet":"Nun 8+","index":25,"n_rows":83,"n_cols":13,"rows_kept":83,"cut":false,"hidden":false,"merged":[[7,11,7,12]]}
["Cell# 4 Spring 2012",null,null,null,null,null,null,"Cell# 4 Fall 2012"]
[]
["TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc.",null,null,null,null,"TABLE 1",null,"CLIENT: Nunatta Environmental Services Inc."]
["PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson",null,null,null,null,"PARACEL LABORATORIES LTD.",null,"ATTENTION: Jim Wilson"]
["WORKORDER: 1228083",null,"PROJECT: Land Farm Thaw",null,null,null,null,"WORKORDER: 1242094",null,"PROJECT: Soils Land Farm Cell 3, 4, 1"]
["REPORT DATE: 07/18/2012",null,"REFERENCE: Preferred Supplier Pricing",null,null,null,null,"REPORT DATE: 10/19/2012",null,"REFERENCE: Preferred Supplier Pricing"]
[]
["Parameter","Units","MDL","Regulation",null,null,null,"Parameter","Units","MDL","Regulation"]
[null,null,null,null,"Cell #4\n1228083-05",null,null,null,null,null,null,"Cell 4 South\n1242094-03","Cell 4 North\n1242094-04"]
["Sample Date (m/d/y)",null,null,"Select Reg","07/07/2012",null,null,"Sample Date (m/d/y)",null,null,"Select Reg","10/13/2012","10/13/2012"]
["Physical Characteristics",null,null,null,null,null,null,"Physical Characteristics"]
["% Solids","% by Wt.","0.1","REGS","84.8",null,null,"% Solids","% by Wt.","0.1","REGS","89.0","88.3"]
["Microbiological Parameters",null,null,null,null,null,null,"Microbiological Parameters"]
["Standard Plate Count","CFU/g","1000","REGS","N/A",null,null,"Standard Plate Count","CFU/g","1000","REGS",">200000","10000"]
["General Inorganics",null,null,null,null,null,null,"General Inorganics"]
["Nitrogen, Total","ug/g","11","REGS","N/A",null,null,"Nitrogen, Total","ug/g","21","REGS","508","385"]
["Phosphorus, total","ug/g dry","1","REGS","N/A",null,null,"Phosphorus, total","ug/g dry","1","REGS","603","644"]
["Total Kjeldahl Nitrogen","ug/g dry","10","REGS","N/A",null,null,"Total Kjeldahl Nitrogen","ug/g dry","10","REGS","508","385"]
["Anions",null,null,null,null,null,null,"Anions"]
["Nitrate as N","ug/g dry","1","REGS","N/A",null,null,"Nitrate as N","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Metals",null,null,null,null,null,null,"Metals"]
["Antimony","ug/g dry","1","REGS","N/A",null,null,"Antimony","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Arsenic","ug/g dry","1","REGS","N/A",null,null,"Arsenic","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Barium","ug/g dry","1","REGS","N/A",null,null,"Barium","ug/g dry","1","REGS","27","28"]
["Beryllium","ug/g dry","0.5","REGS","N/A",null,null,"Beryllium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)"]
["Boron","ug/g dry","5","REGS","N/A",null,null,"Boron","ug/g dry","5","REGS","ND (5.0)","ND (5.0)"]
["Cadmium","ug/g dry","0.5","REGS","N/A",null,null,"Cadmium","ug/g dry","0.5","REGS","ND (0.5)","ND (0.5)"]
["Chromium","ug/g dry","5","REGS","N/A",null,null,"Chromium","ug/g dry","5","REGS","21","20"]
["Cobalt","ug/g dry","1","REGS","N/A",null,null,"Cobalt","ug/g dry","1","REGS","5","6"]
["Copper","ug/g dry","5","REGS","N/A",null,null,"Copper","ug/g dry","5","REGS","15","33"]
["Iron","ug/g dry","200","REGS","N/A",null,null,"Iron","ug/g dry","200","REGS","16500","23500"]
["Lead","ug/g dry","1","REGS","N/A",null,null,"Lead","ug/g dry","1","REGS","10","17"]
["Molybdenum","ug/g dry","1","REGS","N/A",null,null,"Molybdenum","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Nickel","ug/g dry","5","REGS","N/A",null,null,"Nickel","ug/g dry","5","REGS","8","10"]
["Potassium","ug/g dry","200","REGS","N/A",null,null,"Potassium","ug/g dry","200","REGS","546","680"]
["Selenium","ug/g dry","1","REGS","N/A",null,null,"Selenium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Silver","ug/g dry","0.3","REGS","N/A",null,null,"Silver","ug/g dry","0.3","REGS","ND (0.3)","ND (0.3)"]
["Thallium","ug/g dry","1","REGS","N/A",null,null,"Thallium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Tin","ug/g dry","5","REGS","N/A",null,null,"Tin","ug/g dry","5","REGS","ND (5)","ND (5)"]
["Uranium","ug/g dry","1","REGS","N/A",null,null,"Uranium","ug/g dry","1","REGS","ND (1)","ND (1)"]
["Vanadium","ug/g dry","10","REGS","N/A",null,null,"Vanadium","ug/g dry","10","REGS","42","44"]
["Zinc","ug/g dry","20","REGS","N/A",null,null,"Zinc","ug/g dry","20","REGS","58","126"]
["Volatiles",null,null,null,null,null,null,"Volatiles"]
["Benzene","ug/g dry","0.02","REGS","N/A",null,null,"Benzene","ug/g dry","0.02","REGS","ND (0.02)","ND (0.02)"]
["Ethylbenzene","ug/g dry","0.05","REGS","N/A",null,null,"Ethylbenzene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)"]
["Toluene","ug/g dry","0.05","REGS","N/A",null,null,"Toluene","ug/g dry","0.05","REGS","ND (0.05)","ND (0.05)"]
["m/p-Xylene","ug/g dry","0.05","REGS","N/A",null,null,"m/p-Xylene","ug/g dry","0.05","REGS","ND (0.05)","0.38"]
["o-Xylene","ug/g dry","0.05","REGS","N/A",null,null,"o-Xylene","ug/g dry","0.05","REGS","ND (0.05)","0.41"]
["Xylenes, total","ug/g dry","0.05","REGS","N/A",null,null,"Xylenes, total","ug/g dry","0.05","REGS","ND (0.05)","0.79"]
["Benzene","ug/g dry","0.002","REGS","ND (0.002)",null,null,"Benzene","ug/g dry","0.002","REGS","N/A","N/A"]
["Ethylbenzene","ug/g dry","0.002","REGS","ND (0.002)",null,null,"Ethylbenzene","ug/g dry","0.002","REGS","N/A","N/A"]
["Toluene","ug/g dry","0.002","REGS","ND (0.002)",null,null,"Toluene","ug/g dry","0.002","REGS","N/A","N/A"]
["m/p-Xylene","ug/g dry","0.002","REGS","ND (0.002)",null,null,"m/p-Xylene","ug/g dry","0.002","REGS","N/A","N/A"]
["o-Xylene","ug/g dry","0.002","REGS","ND (0.002)",null,null,"o-Xylene","ug/g dry","0.002","REGS","N/A","N/A"]
["Xylenes, total","ug/g dry","0.002","REGS","ND (0.002)",null,null,"Xylenes, total","ug/g dry","0.002","REGS","N/A","N/A"]
["Hydrocarbons",null,null,null,null,null,null,"Hydrocarbons"]
["F1 PHCs (C6-C10)","ug/g dry","7","REGS","ND (7)",null,null,"F1 PHCs (C6-C10)","ug/g dry","7","REGS","63","221"]
["F2 PHCs (C10-C16)","ug/g dry","4","REGS","273",null,null,"F2 PHCs (C10-C16)","ug/g dry","4","REGS","1290","3540"]
["F3 PHCs (C16-C34)","ug/g dry","8","REGS","319",null,null,"F3 PHCs (C16-C34)","ug/g dry","8","REGS","449","883"]
["F4 PHCs (C34-C50)","ug/g dry","6","REGS","61",null,null,"F4 PHCs (C34-C50)","ug/g dry","6","REGS","228","759"]
["Semi-Volatiles",null,null,null,null,null,null,"Semi-Volatiles"]
["Acenaphthene","ug/g dry","0.02","REGS","N/A",null,null,"Acenaphthene","ug/g dry","0.02","REGS","0.13","0.22"]
["Acenaphthylene","ug/g dry","0.02","REGS","N/A",null,null,"Acenaphthylene","ug/g dry","0.02","REGS","ND (0.02)","0.15"]
["Anthracene","ug/g dry","0.02","REGS","N/A",null,null,"Anthracene","ug/g dry","0.02","REGS","0.42","0.44"]
["Benzo[a]anthracene","ug/g dry","0.02","REGS","N/A",null,null,"Benzo[a]anthracene","ug/g dry","0.02","REGS","0.87","1.48"]
["Benzo[a]pyrene","ug/g dry","0.02","REGS","N/A",null,null,"Benzo[a]pyrene","ug/g dry","0.02","REGS","0.72","1.03"]
["Benzo[b]fluoranthene","ug/g dry","0.02","REGS","N/A",null,null,"Benzo[b]fluoranthene","ug/g dry","0.02","REGS","1.10","3.19"]
["Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","N/A",null,null,"Benzo[g,h,i]perylene","ug/g dry","0.02","REGS","0.58","1.17"]
["Benzo[k]fluoranthene","ug/g dry","0.02","REGS","N/A",null,null,"Benzo[k]fluoranthene","ug/g dry","0.02","REGS","0.53","1.99"]
["1,1-Biphenyl","ug/g dry","0.02","REGS","N/A",null,null,"1,1-Biphenyl","ug/g dry","0.02","REGS","0.09","0.55"]
["Chrysene","ug/g dry","0.02","REGS","N/A",null,null,"Chrysene","ug/g dry","0.02","REGS","1.36","2.22"]
["Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","N/A",null,null,"Dibenzo[a,h]anthracene","ug/g dry","0.02","REGS","0.19","0.40"]
["Fluoranthene","ug/g dry","0.02","REGS","N/A",null,null,"Fluoranthene","ug/g dry","0.02","REGS","2.51","5.65"]
["Fluorene","ug/g dry","0.02","REGS","N/A",null,null,"Fluorene","ug/g dry","0.02","REGS","0.21","0.26"]
["Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","N/A",null,null,"Indeno[1,2,3-cd]pyrene","ug/g dry","0.02","REGS","0.58","1.22"]
["1-Methylnaphthalene","ug/g dry","0.02","REGS","N/A",null,null,"1-Methylnaphthalene","ug/g dry","0.02","REGS","0.30","2.50"]
["2-Methylnaphthalene","ug/g dry","0.02","REGS","N/A",null,null,"2-Methylnaphthalene","ug/g dry","0.02","REGS","0.20","2.40"]
["Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","N/A",null,null,"Methylnaphthalene (1&2)","ug/g dry","0.04","REGS","0.50","4.90"]
["Naphthalene","ug/g dry","0.01","REGS","N/A",null,null,"Naphthalene","ug/g dry","0.01","REGS","ND (0.01)","ND (0.01)"]
["Phenanthrene","ug/g dry","0.02","REGS","N/A",null,null,"Phenanthrene","ug/g dry","0.02","REGS","1.50","1.51"]
["Pyrene","ug/g dry","0.02","REGS","N/A",null,null,"Pyrene","ug/g dry","0.02","REGS","2.43","5.03"]
["PCBs",null,null,null,null,null,null,"PCBs"]
["PCBs, total","ug/g dry","0.05","REGS","N/A",null,null,"PCBs, total","ug/g dry","0.05","REGS","ND (0.05)","ND (0.08)"]

{"sheet":"Nun 9","index":26,"n_rows":3,"n_cols":1,"rows_kept":3,"cut":false,"hidden":false,"merged":[[0,0,0,1]]}
["Nun 9 (rock reject stockpile)"]
[]
["All rocks and cobbles are stored in Cell #2 this cell has only a base layer to protect the liner from damage and then all rocks and cobbles are piled on top and washed through out the summer months. During the winter months the harsh conditions of freezing and thawing helps removes the contaminated earth even better than washing with water. The air circulating through the stone piles also assists in removing hydrocarbon contaminated soils. Samples will be taken in the summer of 2013 and at that time it can be determined if the stones are ready to be removed from this cell. It is our plan to remove the stones and dig up all the earth contained inside the cell and reconstruct a new cell with larger length and depth to permit storage of water during spring runoff."]

{"sheet":"Sheet3","index":27,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}