## SA NHWLF Photos
LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-4 Pelly Bay
Landfill: | Station Area Non-Hazardous Waste Landfill
Date Inspected: | August 18-20, 2011
Inspected by: | Andrew Passalis, P.Eng.
Sila Remediation Inc.
(SNH-) | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C411_4765 | 2011-08-18 | 388772.9 | 7594415 | 676 | View looking looking N at SA NHWLF from top of Tier II Disposal Facility
2 |  | C411_4805 | 2011-08-18 | 388797.5 | 7594547.5 | 677 | Panoramic view looking SW to WNW from east of SA NHWLF
3 |  | C411_4888 | 2011-08-20 | 388807.8 | 7594505.6 | 678 | View looking SW along drainage feature extending along southeast side of landfill - FEATURE D
4 |  | C411_4889 | 2011-08-20 | 388809.5 | 7594507.7 |  | View looking NE along southeast toe from south corner of landfill
5 |  | C411_4890 | 2011-08-20 | 388807.5 | 7594510.1 |  | View looking NW along northeast toe from east corner of landfill
6 |  | C411_4891 | 2011-08-20 | 388780.8 | 7594510.9 | 680 | Panoramic view looking NW to SW across surface from east corner of landfill
7 |  | C411_4894 | 2011-08-20 | 388729.9 | 7594549 | 681 | View looking N at rust-coloured staining on northeast side slope, discontinous/patchy starting 5m below crest to toe. - FEATURE C
8 |  | C411_4895 | 2011-08-20 | 388731.7 | 7594544.9 | 682 | View looking NE at minor settlement below crest on northeast side slope (0.5m L, 0.15m W, 0051m D) - FEATURE B
9 |  | C411_4896 | 2011-08-20 | 388740.7 | 7594553.2 | 683 | View looking NE at minor settlement on northeast side slope (0.3m L, 0.3m W, 0.1m D) - FEATURE B
10 |  | C411_4897 | 2011-08-20 | 388732 | 7594566.6 | 684 | View looking SW at rust-coloured staining at seepage point near north toe of landfill (staining 4m wide at base) - FEATURE C
11 |  | C411_4898 | 2011-08-20 | 388729.6 | 7594562.8 | 684 | Rust-coloured staining at seepage point near north toe of landfill. - FEATURE C
12 |  | C411_4899 | 2011-08-20 | 388714 | 7594564.4 | 685 | View looking E along north toe of landfill
13 |  | C411_4900 | 2011-08-20 | 388711.2 | 7594562.9 | 685 | View looking SW along northwest toe of landfill
14 |  | C411_4901 | 2011-08-20 | 388721 | 7594543.8 | 686 | Panoramic view looking E to SW across surface from north corner of landfill
15 |  | C411_4902 | 2011-08-20 | 388703.9 | 7594522.1 | 687 | View looking NE at area of missing erosion resistant cover material on west crest of landfill - FEATURE G
16 |  | C411_4903 | 2011-08-20 | 388699.1 | 7594506.9 | 687 | Panoramic view looking NE to SE across surface from west corner of landfill
17 |  | C411_4904 | 2011-08-20 | 388694.8 | 7594539.3 | 688 | View looking SSW along northwest toe of landfill
18 |  | C411_4905 | 2011-08-20 | 388695.3 | 7594540.7 | 689 | View looking NNE along northwest toe of landfill
19 |  | C411_4906 | 2011-08-20 | 388689.3 | 7594505.1 | 689 | View looking SE along southwest toe from west corner of landfill
20 |  | C411_4907 | 2011-08-20 | 388709.9 | 7594497.3 |  | View looking SE at linear depression located along southwest crest of landfill (3m L, 0.5m W, 15cm D) - FEATURE A
21 |  | C411_4908 | 2011-08-20 | 388722 | 7594488.1 | 690 | View looking SE at linear depression located along southwest crest of landfill (2m L, 1m W, 15cm D) - FEATURE A
22 |  | C411_4909 | 2011-08-20 | 388730.3 | 7594480.3 | 690 | View looking NW at linear depression located along southwest crest of landfill (2m L, 1m W, 15cm D) - FEATURE A
23 |  | C411_4910 | 2011-08-20 | 388727.5 | 7594484.4 | 691 | View of exposed steel bar on southwest crest of landfill (6cm L, 2cm dia.) - FEATURE D
24 |  | C411_4911 | 2011-08-20 | 388727.2 | 7594473.8 | 691 | View looking NW at minor ponding along soutwest toe of landfill
25 |  | C411_4912 | 2011-08-20 | 388750 | 7594471.9 | 692 | Panoramic view looking NW to NE across surface from south corner of landfill
26 |  | C411_4913 | 2011-08-20 | 388746.8 | 7594460.3 | 693 | View looking NW along southwest toe from south corner of landfill
27 |  | C411_4914 | 2011-08-20 | 388749.4 | 7594459.8 | 693 | View looking NE along southest toe from south corner of landfill
28 |  | C411_4915 | 2011-08-20 | 388743.3 | 7594458 | C4-16W | Partially exposed geotextile located near south corner of landfill
29 |  | C411_4943 | 2011-08-20 | 388752 | 7594421.8 |  | Panoramic view looking NW to NE at SA NHWLF from north corner of Tier II Disposal Facility
Soil Sampling
MW-3 |  | C411_4801 | 2011-08-18 | 388816.8 | 7594521.8 |  | Sampling location C4-3W located downgradient of SA NHWLF
3W |  | C411_4802 | 2011-08-18 | 388820.2 | 7594526.1 |  | View looking looking SW at C4-3W soil sample location
MW-4 |  | C411_4803 | 2011-08-18 | 388806 | 7594533.7 |  | Sampling location C4-4W located downgradient of SA NHWLF
4W |  | C411_4804 | 2011-08-18 | 388808.9 | 7594538.1 |  | View looking looking SW at C4-4W soil sample location
MW-2 |  | C411_4806 | 2011-08-18 | 388763.7 | 7594557.6 |  | Sampling location C4-2W located downgradient of SA NHWLF
2W |  | C411_4807 | 2011-08-18 | 388759.3 | 7594555.4 |  | View looking looking NE at C4-2W soil sample location
MW-6 |  | C411_4808 | 2011-08-18 | 388753.1 | 7594574 |  | Sampling location C4-6W located downgradient of SA NHWLF
6W |  | C411_4809 | 2011-08-18 | 388759.5 | 7594575.3 |  | View looking looking WSW at C4-6W soil sample location
MW-1 |  | C411_4810 | 2011-08-18 | 388705.1 | 7594581.2 |  | Sampling location C4-1W located downgradient of SA NHWLF
1W |  | C411_4811 | 2011-08-18 | 388705 | 7594586 |  | View looking looking S at C4-1W soil sample location
MW-7 |  | C411_4812 | 2011-08-18 | 388696.4 | 7594562.8 |  | Sampling location C4-7W located downgradient of SA NHWLF
7W |  | C411_4813 | 2011-08-18 | 388697.7 | 7594568.3 |  | View looking looking S at C4-7W soil sample location
BMW-1 |  | C411_4814 | 2011-08-18 | 388700.9 | 7594470.6 |  | Sampling location C4-BMW1 located upgradient of SA NHWLF
B1 |  | C411_4815 | 2011-08-18 | 388704.6 | 7594473.6 |  | View looking looking SW at C4-BMW1 soil sample location