## USAF Photos
LANDFILL VISUAL INSPECTION PHOTO LOG
Site Name: | CAM-3, Shepherd Bay
Landfill: | USAF Landfill
Date Inspected: | August 15, 2011
Inspected by: | Andrew Passalis, P.Eng.
EGE Engineering Ltd.
Photo (USAF-) | Thumbnail | Filename | Date | Vantage Point |  |  | Caption
|  |  |  | Easting | Northing | Waypoint
1 |  | C311_4331 | 2011-08-15 | 12220.5 | 11441.9 | 522 | View looking NE at VT-1. NWS Landfill in background.
2 |  | C311_4332 | 2011-08-15 | 12233.1 | 11415.8 | 523 | View looking W at VT-2
3 |  | C311_4333 | 2011-08-15 | 12291 | 11410.1 | 524 | View looking N at VT-3
4 |  | C311_4334 | 2011-08-15 | 12312.6 | 11421.6 | 525 | View looking E at VT-4. NWS Landfill in background.
5 |  | C311_4335 | 2011-08-15 | 12228 | 11525.6 | 526 | Panoramic view looking SE to SW from northeast of USAF Landfill
6 |  | C311_4336 | 2011-08-15 | 12206.7 | 11512.3 | 527 | View looking SE at northwest side of landfill
7 |  | C311_4337 | 2011-08-15 | 12196 | 11505.2 | 528 | View looking SE at northwest side of landfill
8 |  | C311_4338 | 2011-08-15 | 12176.5 | 11484.2 | 529 | View looking SE at northwest side of landfill
9 |  | C311_4339 | 2011-08-15 | 12163.4 | 11466.1 | 530 | View looking SE at northwest side of landfill
10 |  | C311_4340 | 2011-08-15 | 12155.2 | 11429.7 | 531 | Panoramic view looking NE to SE from access road west of landfill
11 |  | C311_4341 | 2011-08-15 | 12174.2 | 11406.8 | 532 | View looking NE at southwest side of landfill
12 |  | C311_4342 | 2011-08-15 | 12197.3 | 11385.4 | 533 | View looking NE at southwest side of landfill. VT-2 visible on right.
13 |  | C311_4343 | 2011-08-15 | 12227.9 | 11375.7 |  | View looking NE at southwest side of landfill. VT-2 visible on left
14 |  | C311_4344 | 2011-08-15 | 12254.1 | 11369.1 | 534 | View looking NE at southwest side of landfill. MW-13 location visible in center.
15 |  | C311_4345 | 2011-08-15 | 12277.5 | 11362 | 535 | View looking N at south side of landfill
16 |  | C311_4346 | 2011-08-15 | 12314.1 | 11346.2 | 536 | Panoramic view looking NW to NE from southeast of landfill
17 |  | C311_4347 | 2011-08-15 | 12320.7 | 11358.4 | 537 | View looking NNW at south side of landfill
18 |  | C311_4348 | 2011-08-15 | 12342.5 | 11362.2 | 538 | View looking NW at southeast side of landfill
19 |  | C311_4349 | 2011-08-15 | 12358.6 | 11381.8 | 539 | View looking WNW at southeast side of landfill. Note vegetation on side slope.
20 |  | C311_4350 | 2011-08-15 | 12367.7 | 11403.8 | 542 | Panoramic view looking SW to NW from southeast of landfill
21 |  | C311_4351 | 2011-08-15 | 12361 | 11425.5 | 542 | View looking SW at northeast side of landfill. VT-4 visible on right.
22 |  | C311_4352 | 2011-08-15 | 12345.2 | 11441.2 | 543 | View looking SW at northeast side of landfill. VT-4 visible in center.
23 |  | C311_4353 | 2011-08-15 | 12332 | 11458.8 |  | View looking SW at northeast side of landfill. MW-15 visible center foreground.
24 |  | C311_4354 | 2011-08-15 | 12311.6 | 11474.6 | 545 | View looking SW at northeast side of landfill. VT-3 visible on far left.
25 |  | C311_4355 | 2011-08-15 | 12255.3 | 11497.8 | 545 | View looking SE along northeast toe of landfill. VT-4 visible in center background
26 |  | C311_4356 | 2011-08-15 | 12298.6 | 11458.9 | 546 | View looking E at rust coloured ponded area at northeast toe (1m L, 1m W) - FEATURE E
27 |  | C311_4357 | 2011-08-15 | 12288.5 | 11473.5 | 546 | View looking SE at minor erosion of fines along northeast toe (15m L, 0.5-1m W, 1-2cm D) - FEATURE D
28 |  | C311_4359 | 2011-08-15 | 12233.8 | 11482.4 | 549 | Panoramic view looking SE to SW across surface from northeast corner of landfill
29 |  | C311_4360 | 2011-08-15 | 12187.4 | 11447.1 | 550 | Panoramic view looking E to S from northwest corner of landfill. VT-1 visible in center background.
30 |  | C311_4361 | 2011-08-15 | 12185.1 | 11433 | 550 | View looking SE at cracks extending along west side of landfill (25-30m L, 3-10mm W) - FEATURE G
31 |  | C311_4362 | 2011-08-15 | 12188.1 | 11428.3 | 551 | View of crack extending along west side of landfill (3-10mm W) - FEATURE G
32 |  | C311_4363 | 2011-08-15 | 12209.7 | 11408.2 | 552 | View looking NW at cracks extending along west side of landfill (25-30m L, 3-10mm W) - FEATURE G
33 |  | C311_4364 | 2011-08-15 | 12201.9 | 11413.9 | 553 | View of 3 parallel cracks extending along west side of landfill (25-30m L, 3-10cm W) - FEATURE G
34 |  | C311_4365 | 2011-08-15 | 12222.6 | 11403.2 | 553 | View looking ESE at single crack extending along south side slope of landfill (15m L, 2-5mm W) - FEATURE G
35 |  | C311_4366 | 2011-08-15 | 12231.4 | 11402.3 | 554 | View of crack extending along south side slope of landfill (15m L, 2-5mm W) - FEATURE G
36 |  | C311_4367 | 2011-08-15 | 12242 | 11401.3 | 555 | View looking W at 2 cracks extending along south side slope of landfill (10-15m L, 2-5mm W) - FEATURE G
37 |  | C311_4368 | 2011-08-15 | 12238.9 | 11405 |  | View looking ESE at single crack extending along south side slope of landfill (10m L, 1-3mm W) - FEATURE G
38 |  | C311_4369 | 2011-08-15 | 12246.7 | 11402.2 |  | View of crack extending along south side slope of landfill (10m L, 1-3mm W) - FEATURE G
39 |  | C311_4370 | 2011-08-15 | 12249.9 | 11395.5 | 556 | View of cracks extending along south side slope of landfill (6m L, 2-15mm W) - FEATURE G
40 |  | C311_4371 | 2011-08-15 | 12255.6 | 11395.1 | 557 | View looking W at 3 cracks extending along south side slope of landfill (6m L, 2-15mm W) - FEATURE G
41 |  | C311_4372 | 2011-08-15 | 12268.7 | 11402.7 | 558 | View looking SW at minor erosion on southwest slope of landfill (15m L, 0.5m W, 2-3cm D) - FEATURE C
42 |  | C311_4373 | 2011-08-15 | 12281.1 | 11379.7 | 559 | View looking SE at single crack extending along south slope of landfill (14m L, 2-3mm W) - FEATURE G
43 |  | C311_4374 | 2011-08-15 | 12289.2 | 11378.7 | 559 | View of crack extending along south sloope of landfill (14m L, 2-3mm W) - FEATURE G
44 |  | C311_4375 | 2011-08-15 | 12298.6 | 11373.4 | 560 | View looking NW at single crack extending along south side of landfill (8m L, 2-5mm W) - FEATURE G
45 |  | C311_4376 | 2011-08-15 | 12327.9 | 11374.6 | 561 | View looking W at minor depression (0.4m L, 0.2m W, 5-7cm D) - FEATURE A
46 |  | C311_4377 | 2011-08-15 | 12334.8 | 11376.3 |  | View looking NE at single crack extending across southeast side slope (12m L, 3-5mm W) - FEATURE H
47 |  | C311_4378 | 2011-08-15 | 12339.9 | 11386.7 |  | View of single crack extending across southeast side slope (12m L, 3-5mm W) - FEATURE H
48 |  | C311_4379 | 2011-08-15 | 12343.8 | 11392.7 |  | View looking SW at single crack extending across southeast side slope (12m L, 3-5mm W) - FEATURE H
49 |  | C311_4380 | 2011-08-15 | 12327.4 | 11392.5 |  | Panoramic view looking W to NE across surface from southeast end of landfill
50 |  | C311_4381 | 2011-08-15 | 12328.5 | 11394 |  | View looking SE at minor erosion on east side slope of landfill (25m L, 0.1-0.2m W, 5-10cm D) - FEATURE C
51 |  | C311_4382 | 2011-08-15 | 12350 | 11387.6 |  | View looking NW at minor erosion on east side slope of landfill (25m L, 0.1-0.2m W, 5-10cm D) - FEATURE C
52 |  | C311_4385 | 2011-08-15 | 12342.3 | 11398.7 |  | View of cracks extending along east side slope of landfill (18m L, 3-10mm W) - FEATURE H
53 |  | C311_4386 | 2011-08-15 | 12340.8 | 11415.4 |  | View looking S at cracks extending along east side slope of landfill (18m L, 3-10mm W) - FEATURE H. Also note small depression on right (0.5m L, 0.5m W, 5cm D) - FEATURE A
54 |  | C311_4388 | 2011-08-15 | 12328.9 | 11401 |  | View looking SE at subtle depression on east side slope below crest (4-5m L, 3m W, 15cm D) - FEATURE A
55 |  | C311_4389 | 2011-08-15 | 12326.2 | 11408.4 |  | View looking ENE at minor erosion extending along east side slope of landfill (15m L, 0.1-0.15m W, 5cm D) - FEATURE C
56 |  | C311_4390 | 2011-08-15 | 12331.8 | 11419.8 |  | Partially exposed metal debris (crushed drum) on east side slope below VT-4 - FEATURE F
57 |  | C311_4391 | 2011-08-15 | 12337.7 | 11418 |  | View looking WNW at partially exposed metal debris (crushed drum) on east side slope below VT-4 - FEATURE F
58 |  | C311_4392 | 2011-08-15 | 12265.1 | 11436.2 |  | View looking E at subtle depression on central cover area of landfill (3m L, 1.5m W, 10-15cm D) - FEATURE B
59 |  | C311_4394 | 2011-08-15 | 12203.4 | 11433.1 |  | View looking NE at linear depression on southwest cover area of landfill (6m L, 1m W, 10cm D) - FEATURE B
60 |  | C311_4397 | 2011-08-15 | 12287.1 | 11522.3 |  | Panoramic View looking SE to SW at USAF Landfill from service road adjacent to NWS Landfill
|  | C311_4759 | 2011-08-15 | 12050 | 11510 |  | Aerial view looking SE at USAF Landfill
|  | C311_4761 | 2011-08-15 | 12640 | 11600 |  | Aerial view looking SW at USAF and NWS Landfills
Soil Sampling | [5 empty] | MW-4
MW-12 |  | C311_4320 | 2011-08-15 | 12191.6 | 11503.6 |  | Sampling location C311-12W located upgradient of USAF LF
12W |  | C311_4321 | 2011-08-15 | 12183.8 | 11503.7 | 312 | View looking E at MW-12 soil sample location
MW-13 |  | C311_4323 | 2011-08-15 | 12269.2 | 11375.6 |  | Sampling location C311-13W located downgradient of USAF LF
13W |  | C311_4324 | 2011-08-15 | 12269.4 | 11381.2 |  | View looking S at MW-13 soil sample location
MW-14 |  | C311_4326 | 2011-08-15 | 12351.9 | 11369.8 | 313 | Sampling location C311-14W located downgradient of USAF LF
14W |  | C311_4327 | 2011-08-15 | 12357.7 | 11371.4 |  | View looking SW at MW-14 soil sample location
MW-15 |  | C311_4329 | 2011-08-15 | 12329.5 | 11451.7 | 314 | Sampling location C311-15W located downgradient of USAF LF
15W |  | C311_4330 | 2011-08-15 | 12336 | 11452.2 | 330 | View looking W at MW-15 soil sample location
331
332
333