TURNER 2003 - BORDEN BASIN PROJECT - NON-TECHNICAL SUMMARY

Purpose: This is the first year of a proposed 3-year project in the Borden Basin, which is the geologic name for the rocks in the broad area between Arctic Bay and Pond Inlet. Its primary goals are: 1) investigating the properties of the rocks in the region, and what they can tell us about the geologic history of the area; and 2) understanding how the zinc and lead was transported to the area and deposited there, and what factors control where they are found in the region.  

Proposed duration of field work: The 2003 field season is proposed for June 12 - August 15.

Study area: Parts of NTS 48A,B,C, 47H, 38B, and 58C.

Activities: The work will be accomplished by 2 people travelling on foot on the land from small base camps. Rocks will be described, mapped, measured, and sampled (fist-sized pieces or smaller) using a rock hammer.

Base camps: A series of 9 small base camps is proposed over approximately 2 months (mid-June to mid-August). Each will consist of 2 tents, which will be removed each time the 2 researchers move camp. 

Transportation: Camp moves will be done using a helicopter based in either Pond Inlet or Resolute Bay. All transportation on the ground will be by foot.

Fuel: We will use approximately 5 litres of camping fuel for cooking at each camp location.

Remediation: Sewage and grey water will be buried, and garbage taken to a municipal landfill by helicopter each time the camp is moved. All other material used or collected will be removed from each site with each camp move.

