C-NGO Committee Bay Project 2002

The 3-year geological mapping project on the northeastern mainland of Nunavut was initiated in 2000, and has as a primary goal of producing new bedrock and surficial materials map coverage of the of the following NTS 1:250 000-scale map areas.



56J
Walker Lake



56K
Laughland Lake



56O
Armshow River



56P
Ellice Hills

2002 Study Area: 56P, 56J, 56O.


Field work: 
June 19 – August 21, 2002



Move-in: June 19-20



Field Work June 21 – August 18



Restoration & clean-up: August 18-21



Move-out: August 21-22

Staging area: Repulse Bay

Base camp: 24 sleeping tents, a kitchen tent, a storage tent and an office tent would be established on a gravel terrace of the Atorquait River, approx. 170km northwest of Repulse Bay (see attached map).   Machinery limited to: a helicopter (stationed well away from the lake), and 2 Honda generators for electrical power. Camp would be completely assembled and disassembled at the start and end of the field season, respectively. 

Daily activities: foot traverses with helicopter drop-offs and pick-ups; bedrock sampling (fist-sized pieces); compilation of data with computers in camp; no chemicals required.

Helicopter usage: drop-offs and pick-ups of traverse teams; sample collection, geophysical surveys; equipment and supplies movement; personnel moves to/from main camp.

Fuel: 150 sealed 205 litre drums of helicopter fuel would be moved by Twin Otter from the airstrip at Repulse Bay (sealift drop-off point in 2001) to the main camp before the start of the field season.  Fuel drums would be stored away from any surface drainage on a gravel pad.  All drums (empty and full) will be removed by Twin Otter at the end of field season and transported to Repulse Bay for re-use or disposal.

