## Sheet1
Checklist Showing Required Approvals for February 2013 Workplan
2013 Workplan Section | Location | 2013 Work Plan Phase | Work Plan Activity | Currently Approved | Required Approvals
[5 empty] | QIA Work Plan Approval | Amendment of Schedule B Existing QIA Commercial Lease | Proposed Type B Water Licence | QIA Commercial Production Lease | Type A Water Licence | Comments
3.1.1 | Mary River Mine Site | Pre-Sealift Site Preparation (April to July)
|  |  | Operate existing Mine Site exploration camp and related facilities | Ö
|  |  | Fly in prepackaged explosives |  | Ö |  |  |  |  | Approval from Mines Inspector required.
|  |  | Construct camp pad from local borrow sources |  | Ö | Ö | Ö |  |  | Preliminary design drawings submitted to NWB and QIA with Water Licence Application and Update to Management Plans. Update to Quarry Pit and Borrow Management Plan submitted to NWB and QIA.
3.1.2 | Tote Road | Pre-Sealift Site Preparation (April to July)
|  |  | Open Tote Road and freshet management | Ö
|  |  | Relocate crusher train | Ö
|  |  | Follow-up requirements for Fisheries Authorization | Ö
3.1.3 | Milne Port | Pre-Sealift Site Preparation (April to July)
|  |  | Develop laydown areas for storage of explosive magazines |  | Ö |  | Ö |  |  | Only minor upgrade required, locations used in 2007-2008.
|  |  | Open existing Milne Port Camp and related facilities. | Ö
|  |  | Construct a second PWSP |  | Ö |  | Ö |  |  | Design drawings submitted to NWB and QIA with Type B Water Licence Application.
|  |  | Begin development of Q1 Quarry and local borrow sources. |  | Ö | Ö | Ö |  |  | Quarry Pit and Borrow Management Plan and Quarry Management Plan Milne Inlet Quarry (Q1) submitted to QIA and NWB.
|  |  | Complete earthworks infrastructure including laydowns, camp pad, fuel tank farm secondary containment structure. |  | Ö |  | Ö |  |  | Design drawings submitted to NWB and QIA with Type B Water Licence Application.
|  |  | Construct one 5 ML steel tank. |  | Ö |  | Ö |  |  | Desgn drawings submitted to NWB and QIA with Type B Water Licence Application.
3.2.1 to 3.2.4, incl. | Milne Port | Sealifts (July to Oct)
|  |  | Receipt of prefabricated buildings and fold-away structures, heavy equipment and rolling stalk, and bulk fuel delivery. |  | Ö |  |  | Ö | Ö | To support bulk fuel delivery, revision to OPEP and submission to Transport Canada required.
3.3.1 | Milne Port | Construction (July to Dec)
|  |  | Installation of emergency response builiding. |  | Ö |  |  | Ö | Ö
|  |  | Install 3 to 4 -10 ML diesel fuel tanks, install and commission fuel dispensing system. |  | Ö |  |  | Ö | Ö
|  |  | Install and commission camp extension incl. STP and incinerator. |  | Ö |  |  | Ö | Ö
|  |  | Install concrete batch plant. |  | Ö |  |  | Ö | Ö
|  |  | Ongoing decommissioning of bladder farm. |  | Ö |  |  | Ö | Ö
|  |  | Install maintenance shops, trade shops, warming shed and parking garage, warehouse, administration buildings and field offices. |  | Ö |  |  | Ö | Ö
3.3.2 | Tote Road | Construction (July to Dec)
|  |  | Transporation of equimment, material, fuel and suplies to Mine Site |  | Ö |  |  | Ö | Ö
|  |  | Upgrade of Tote Road at select locations and crossings from Milne Port to Deposit No. 1. |  | Ö |  |  | Ö | Ö | DFO Fisheries Authorizations will be required.
|  |  | Possible use of 49 person camp along Tote Road as temporary construction camp. |  | Ö |  |  | Ö | Ö | Further approvals may be required for use of 49 person camp. Discusions with regulators ongoing.
3.3.2 | Mary River Mine Site | Construction (July to Dec)
|  |  | Development of QM2 quarry. See Note 1 below. |  | Ö |  |  | Ö | Ö | Quarry Pit and Borrow Management Plan submitted to QIA and DFO. Site specific quarry plan to be submitted. DFO authorization may be required for one of two access roads.
|  |  | Complete camp pad and installation of construction camp, STP, incinerator, treated sewage storage ponds, and discharge pipeline to Mary River, and potable water line and jetty in Camp Lake |  | Ö |  |  | Ö | Ö | Fisheries authorization required for Camp Lake jetty.
|  |  | Upgrade (extension) of Mine Site airstrip. |  | Ö |  |  | Ö | Ö
|  |  | Development of equipment laydown areas. |  | Ö |  |  | Ö | Ö
|  |  | Development of parking area for mobile equipment. |  | Ö |  |  | Ö | Ö
|  |  | Erect/Install emergency response building, concrete batch plant, emulsion plant, maintenance shop, trade shops, warming shed and parking garage, warehouses, admininstation buildings and field offices. |  | Ö |  |  | Ö | Ö
|  |  | Construct fuel tank secondary containment |  | Ö |  |  | Ö | Ö
|  |  | Install 4 - 500,000 L diesel fuel tanks and one 50,000 L jet A tank. |  | Ö |  |  | Ö | Ö
|  |  | Transfer of fuel from Milne Port to the Mine Site and installaton and commissioning of fuel dispensing system. |  | Ö |  |  | Ö | Ö
4 |  |  | Ongoing exploration and geotechnical activities | Ö
5 |  |  | Progressive reclamation of the exploration and bulk sample program. | Ö
Note: | 1. There may be an opportunity to develop a small portion (shown on attached Site Layout) of QM2 Quarry at the Mine Site prior to sealift assuming necessary management plans are submitted and approval is given by QIA. The QM2 Quarry was included in the new Type B Water Licence Application submitted March 9, 2013.