## Summary
SUMMARY OF COSTS
CAPITAL COSTS | COMPONENT NAME | INAC COST (March 2018) |  | TMAC Cost (November 2017) | COST DIFFERENCE | Proposed Cost (April 2018) | PROPOSED COST DIFFERENCE | COMMENTS
OPEN PIT |  | 0.0001 |  | 0 | 0 | 0 | 0.0001 | Carry forward TMAC cost
UNDERGROUND MINE |  | 63093.8501 |  | 62427.4944 | 666.3556 | 62427.4944 | 666.3557 | Carry forward INAC cost. See sheet for details.
TAILINGS FACILITY |  | 15267745.0581 |  | 15266954.4736 | 790.5844 | 15266954.4736 | 790.5845 | Carry forward TMAC cost
ROCK PILE | Waste Rock and Overburden Dump | 73984.5001 |  | 71969.3493 | 2015.1508 | 71969.3493 | 2015.1508 | Carry forward TMAC cost
BUILDINGS AND EQUIPMENT | Boston Mine | 6144259.5118 |  | 5317822.8266 | 826436.6851 | 5344932.0156 | 799327.4962 | See Comments in Worksheet
CHEMICALS AND CONTAMINATED SOIL MANAGEMENT |  | 636122.8397 |  | 465745.0328 | 170377.8068 | 473245.0328 | 162877.8069 | See Comments in Worksheet
SURFACE AND GROUNDWATER MANAGEMENT |  | 46772.3901 |  | 43717.2197 | 3055.1703 | 43717.2197 | 3055.1704 | Carry forward TMAC cost
INTERIM CARE AND MAINTENANCE |  | 4786320.0003 |  | 2427027.3758 | 2359292.6245 | 2429277.3758 | 2357042.6245 | Carry forward TMAC cost plus an annual communications fee. INAC estimate increased length of ICM period
Incorrectly included task |  |  |  | 1144.85 | -1144.85 | 0 | 0 | TMAC incorrectly included Madrid cost (Patch Lake regrading) in Boston estimate
| SUBTOTAL: Capital Costs | 27018298.1503 |  | 23656808.6223 | 3361489.5274 | 23692522.9612 | 3325775.1891
PERCENT OF SUBTOTAL
INDIRECT COSTS |  | COST |  | TMAC Cost (November 2017) | COST DIFFERENCE | Proposed Cost (April 2018) |  | COMMENTS
MOBILIZATION/DEMOBILIZATION |  | 5464605.0001 |  | 5138109.746 | 326495.254 | 5138109.746 | 326495.2541 | Carry forward TMAC cost. Worker travel time already accounted for in worker unit rate.
POST-CLOSURE MONITORING AND MAINTENANCE |  | 1345960.6613 |  | 1125561.3214 | 220399.3399 | 1125561.3214 | 220399.3399 | Carry forward TMAC cost.
ENGINEERING | 5% | 1350914.9075 |  | 0 | 1350914.9075 | 1184626.1481 | 166288.7595 | Omitted in TMAC estimate, carry forward Engineering cost at 5% of direct costs.
PROJECT MANAGEMENT | 5% | 1350914.9075 |  | 833297.5069 | 517617.4006 | 833297.5069 | 517617.4006 | Carry forward TMAC cost.
HEALTH AND SAFETY PLANS/MONITORING & QA/QC | 0% | 0 |  | 0 | 0 | 0 | 0
BONDING/INSURANCE | 0% | 0 |  | 0 | 0 | 0 | 0
CONTINGENCY | 20% | 5403659.6301 |  | 4731361.7237 | 672297.9064 | 4738504.5922 | 665155.0378 | Carry forward 20% of direct costs
MARKET PRICE FACTOR ADJUSTMENT | 0% | 0 |  | 0 | 0 |  | 0
| SUBTOTAL: Indirect Costs | 14916055.1065 |  | 11828330.2981 | 3087724.8084 | 13020099.3147 | 1895955.7919
TOTAL COSTS |  | 41934353.2568 |  | 35485138.9203 | 6449214.3358 | 36712622.2759 | 5221730.9809
Checking Against Memo Values:
| Direct Costs | 27018298 |  | 23656809
| Diff: | 0.1503 | 0 | -0.37774
| Indirect Costs | 14916055 |  | 11828330
| Diff: | 0.10653 | 0 | 0.29807
Y:\1CT022.022_2018 FEIS Post-Submission Support\Cost Estimates\[702774-000 Hope Bay P2 Boston RECLAIM_MODEL_VER_2_Mar_27_2018_Comparision_20180426.xlsx]Water Management

## UG Mine
1 | Underground Mine Name |  |  |  |  | UG Mine # | 1
| ACTIVITY/MATERIAL | Notes | Unit | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) | % Land | Land Cost | Water Cost | SRK Row Number | Facility Name | Task Description | Quantity | Unit | Unit Cost | Subtotal | TMAC Costs (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Costs
CONTROL ACCESS
| Fence |  | m |  | #N/A | 0 | 0 |  | 0 | 0
| Signs |  | each | 2 | SH | 37.08 | 74.16 | 100% | 74.16 | 0 | [7 empty] | 0 | 74.16 |  | 0
| Block roads |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Berm |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Concrete wall in portals |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Backfill portal #1 | BM-033 | m³ | 710 | TMAC | 24.53 | 17416.3 | 100% | 17416.3 | 0 | 1136 | Boston Portal and Underground Works | construct portal plug | 706.8 | m³ | 24.5293 | 17337.3212 | 17337.3212 | 78.9788 |  | 17337.3212
| Backfill portal #2 |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Cap Vent Raise | BM-028 | each | 1 | TMAC | 14293 | 14293 | 100% | 14293 | 0 | 1130 | Boston Vent Raise | construct a concrete cap (0.5 m thick reinforced concrete) to seal the top | 1 | each | 14292.6809 | 14292.6809 | 14292.6809 | 0.3191 |  | 14292.6809
| Cap raise #2 |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Cap shaft #1 |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Cap shaft #2 |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Grading at Vent Raise |  | m² | 2270 | TMAC | 1.23 | 2792.1 | 100% | 2792.1 | 0 | 1134 | Boston Vent Raise | regrade pads for positive drainage | 2270 | m² | 1.2273 | 2786.0845 | 2786.0845 | 6.0155 |  | 2786.0845
| Backfill open stope |  | m³ |  | sc3h | 14.2 | 0 |  | 0 | 0
| Concrete cap over open stope |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other - crown pillar study |  | LS |  | #N/A | 25000 | 0 |  | 0 | 0
REMOVE HAZARDOUS MATERIALS
| Remove hazardous materials, U/G labor |  | mandays |  | #N/A | 500 | 0 |  | 0 | 0
| Remove/decontam. stationary & elect. equip |  | lm | 200 | TMAC | 119.02 | 23804 | 100% | 23804 | 0 | 1129 | Boston Vent Raise | remove ducts, pipes, and cables | 100 | lm | 119.0155 | 11901.5528 | 23803.1056 | 0.89444 |  | 23803.1056
[11 empty] | 1135 | Boston Portal and Underground Works | remove ducts, pipes, electrical cables | 100 | lm | 119.0155 | 11901.5528
| Remove/decontam. mobile equipment |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Remove misc. haz. mat & explosives |  | kg |  | #N/A | 0 | 0 |  | 0 | 0
| Other | BM-028 & BM-033 Relocate debris and equipment to Roberts Bay | LS | 1 | TMAC | 4714.29 | 4714.29 | 100% | 4714.29 | 0 | 1132 | Boston Vent Raise | prepare units for shipping | 1 | each | 1368.9375 | 1368.9375 | 4208.3022 | 505.9878 | INAC unit cost assumes materials will be hauled to Roberts Bay rather than landfill. Carried forward TMAC cost. | 4208.3022
[11 empty] | 1131 | Boston Vent Raise | decommission and dismantle all ventilation and heating facilities | 4 | each | 679.516 | 2718.064
[11 empty] | 1133 | Boston Vent Raise | haul units to Boston landfill | 37.21 | m³ | 3.2599 | 121.3007
INSTALL BULKHEADS
| Bulkheads to control water flow |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Grout bulkhead |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
FLOOD MINE
| Supply/install pump |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Supply/install piping system |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Operate pumps to flood workings |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
INSTALL GROUNDWATER COLLECTION SYSTEM
| Excavate/install sumps |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Install pumping wells |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Install pumps/pipelines/power supply |  | LS |  | #N/A | 0 | 0 |  | 0 | 0
SPECIALIZED ITEMS
| Install water quality monitoring pipes |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Install permanent pumping system |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
[6 empty] | Total | 63093.8501 |  | 63093.85 | 0 | [5 empty] | Total | 62427.4944 |  | 666.3556 |  | 62427.4944
[6 empty] | % of Total |  |  | 100% | 0%

## Tailings
1 | Tailings Impoundment Name: |  |  |  |  | Pond # | 1
| INAC COST (March 2018) | [9 empty] | TMAC Cost (November 2017) | [6 empty] | COST DIFFERENCE |  |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) | % Land | Land Cost | Water Cost | SRK Row Number | Facility Name | Task Description | Units | Quantity | Unit Cost | TMAC Costs (November 2017) |  | Cost Difference (INAC-TMAC) | Notes
CONTROL ACCESS
| Fence |  | m |  | #N/A | 0 | 0 |  | 0 | 0
| Signs |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Berm |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Block roads |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
STABILIZE EMBANKMENT(S)
| Toe buttress, drainage layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Toe buttress, bulk fill |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap |  | m³ |  | RB2 | 17.8 | 0 |  | 0 | 0
| Vegetate |  | ha |  | #N/A | 0 | 0 |  | 0 | 0
| Raise crest |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Flatten slopes |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
COVER TAILINGS
| Grade/shape tailings surface | BM-031 | m² | 72900 | TMAC | 1.23 | 89667 | 50% | 44833.5 | 44833.5 | 1181 | Boston TMA Tailings | regrade top surface for positive drainage | m² | 72900 | 1.2273 | 89473.815 |  | 193.185 |  | 89473.815
| Liner bedding |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Subgrade preparation - compact |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Supply geotextile/geosynthetic |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Supply & Install geotextile/geosynthetic | BM-031 | m² | 202826 | TMAC | 33.85 | 6865660.1 | 50% | 3432830.05 | 3432830.05 | 1182 | Boston TMA Tailings | cover entire dump with hdpe liner, | m² | 202826 | 33.8451 | 6864661.2819 |  | 998.8181 |  | 6864661.2819
| Soil cover |  | m³ |  | SC4L | 9.3 | 0 |  | 0 | 0
| Rock cover | Based on 1000 mm cap | m³ | 202826 | #N/A | 16.35 | 3316205.1 | 50% | 1658102.55 | 1658102.55 | 1185 | Boston TMA Tailings | place 1 m thick liner protection layer of crushed rock & ROQ | m² | 202826 | 16.3529 | 3316788.8294 |  | -583.7294 |  | 3316788.8294
| Other | Rock Crushing | m³ | 60847.8 | TMAC | 4.91 | 298762.698 |  | 0 | 298762.698 | 1184 | Boston TMA Tailings | Produce Crush | m³ | 60847.8 | 4.9062 | 298529.5437 |  | 233.1543 |  | 298529.5437
| Other | Drill and Blast rock for cover BM-031 | m³ | 202826 | TMAC | 23.16 | 4697450.16 | 50% | 2348725.08 | 2348725.08 | 1183 | Boston TMA Tailings | Produce ROQ (quarry drill&blast) | m³ | 202826 | 23.1603 | 4697501.0036 |  | -50.8436 |  | 4697501.0036
BURY PAG ROCK
| Relocate PAG rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Place cover over PAG rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Raise crest of dam |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
STABILIZE DECANT SYSTEM
| Excavate and replace |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Plug/backfill with concrete or clay |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
REMOVE TAILINGS DISCHARGE
| Cyclones |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Pipe |  | m |  | ppls | 57.33 | 0 |  | 0 | 0
| Remove reclaim barge |  | allow |  | #N/A | 0 | 0 |  | 0 | 0
CONSTRUCT DIVERSION DITCHES
| Excavate ditches -soil |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Excavate ditches -rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap in channel base |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
FLOOD TAILINGS
| Doze tailings to final contour |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Raise crest of dam |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
UPGRADE SPILLWAY
| Excavate channel, rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Excavate channel, soil |  | m³ |  | SC3H | 14.2 | 0 |  | 0 | 0
| Concrete |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap |  | m³ |  | RB4H | 30.75 | 0 |  | 0 | 0
| Geotextile |  | m² |  | GSTL | 3.44 | 0 |  | 0 | 0
CONSTRUCT SEEPAGE COLLECTION POND
| Excavate seepage collection pond |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Doze & spread excavated material |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Vegetate spread material |  | ha |  | #N/A | 0 | 0 |  | 0 | 0
| Bedding layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Supply geomembrane |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Install geomembrane |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Erosion protection layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
INSTALL GROUNDWATER COLLECTION SYSTEM
| Excavate/install sumps |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Install pumping wells |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Install pumps/pipelines/power supply |  | LS |  | #N/A | 0 | 0 |  | 0 | 0
SPECIALIZED ITEMS
| Install permanent instrumentation, supply & technican |  | each |  | #N/A | 30000 | 0 |  | 0 | 0
| Install permanent instrumentation, drilling |  | each |  | #N/A | 30000 | 0 |  |  | 0
TREAT SEEPAGE - see "Water Management" and "Water Treatment"
TREAT SUPERNATANT
| Pump water (to pit, U/G) |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Equipment maintenance and parts |  | allow |  | #N/A | 100000 | 0 |  | 0 | 0
| Supply reagents |  | tonne |  | #N/A | 0 | 0 |  | 0 | 0
[6 empty] | Annual treatment costs | 0.0001
| Number of years of treatment |  | years
[6 empty] | Total treatment costs | 0 |  |  | 0
[6 empty] | Total | 15267745.0581 |  | 7484491.18 | 7783253.878 | [5 empty] | Total | 15266954.4736 | Total Difference | 790.5844 |  | 15266954.4736
[6 empty] | % of Total |  |  | 49.02% | 50.98%
* for construction of passive treatment system refer to "Water Management"

## Rock Pile
1 | Rock Pile Name: | Waste Rock and Overburden Dump
| INAC COST (March 2018) | [9 empty] | TMAC Cost (November 2017) | [6 empty] | COST DIFFERENCE |  |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) | % Land | Land Cost | Water Cost | SRK Row Number | Facility Name | Task Description | Units | Quantity | Unit Cost | TMAC Costs (November 2017) |  | Cost Difference (INAC-TMAC) | Notes
STABILIZE SLOPES
| Grade Waste Rock Pile | BM-024 | m³ | 40778 | TMAC | 1.23 | 50156.94 | 50% | 25078.47 | 25078.47 | 40 | Boston Waste Rock Pile | grade for positive drainage | m² | 40778 | 1.2273 | 50048.8783 |  | 108.0617 |  | 50048.8783
| Grade Overburden Pile | BM-026 | m³ | 17860 | TMAC | 1.23 | 21967.8 | 50% | 10983.9 | 10983.9 | 41 | Boston Overburden Pile | grade for positive drainage | m² | 17860 | 1.2273 | 21920.471 |  | 47.329 |  | 21920.471
| Grade Old Camp Ore Pile | BM-040 | m³ | 1512 | TMAC | 1.23 | 1859.76 | 50% | 929.88 | 929.88 | 42 | Boston Old Camp Ore Stockpile | grade for positive drainage | m² | 0 | 1.2273 | 0 |  | 1859.76 | Existing ore stockpiles assumed to be processed, and/or regraded during development of new infrastructure | 0
| Grade Ore Stockpile | BM-001 in BM-036 Bldg & Equip | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Toe buttress, drain mat'l |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Toe buttress, fill mat'l A |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Toe buttress, fill mat'l B |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| COVER ROCK PILE | [17 empty] | 0
| Subgrade preparation - doze surface |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Soil cover - excavate,haul,spread&compact |  | m³ |  | SB1L | 4.3 | 0 |  | 0 | 0 | [8 empty] | 0
| Rock cover - excavate,haul & spread |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Excavate downslope drainage channel & chute |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Rip rap drainage channel and chute |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Vegetate |  | ha |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| VERY LOW PERMEABILITY COVER (in addition to above) | [17 empty] | 0
| Liner subgrade preparation - compact |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Supply geomembrame |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Install geomembrane |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Protective cover - excavate,haul,spread&compact |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Vegetate |  | ha |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Install infiltration/seepage instrumentation |  | allow |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| CONSTRUCT DIVERSION DITCHES | [17 empty] | 0
| Excavate ditches -soil |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Excavate ditches -rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Rip rap in channel base |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| CONSTRUCT SEEPAGE COLLECTION POND | [17 empty] | 0
| Excavate seepage collection pond |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Doze & spread excavated material |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Vegetate spread material |  | ha |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Bedding layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Supply geomembrane |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Install geomembrane |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Erosion protection layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| INSTALL GROUNDWATER COLLECTION SYSTEM | [17 empty] | 0
| Excavate/install sumps |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Install pumping wells |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Install pumps/pipelines/power supply |  | allow |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| RELOCATE DUMPS | [17 empty] | 0
| Load, haul, dump or doze |  | m³ |  | SC3L | 8.9 | 0 |  | 0 | 0 | [8 empty] | 0
| Add lime |  | tonne |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Contour reclaimed area |  | ha |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Other |  | allow |  | #N/A | 20000 | 0 |  | 0 | 0 | [8 empty] | 0
| SPECIALIZED ITEMS | [17 empty] | 0
| Install permanent instrumentation |  | allow |  | Ea | 50000 | 0 |  | 0 | 0 | [8 empty] | 0
| Install permanent instrumentation, drilling |  | each |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| TREAT ROCK PILE SEEPAGE - see "Water Management" | [17 empty] | 0
| HEAP LEACH SEEPAGE TREATMENT - Cyanide Detox | [17 empty] | 0
| Cyanide destruction water treatment pumping |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Reagents |  | tonnes |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Electrician/mechanic to maintain treatment plant |  | allow |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
| Equipment maintenance and parts |  | allow |  | #N/A | 0 | 0 |  | 0 | 0 | [8 empty] | 0
[6 empty] | Annual treatment costs | 0.0001 | [11 empty] | 0.0001
| Number of years of treatment |  | years | [15 empty] | 0
[6 empty] | Total treatment costs | 0 |  |  | 0 | [8 empty] | 0
| HEAP LEACH SEEPAGE TREATMENT - ARD/ML** | [17 empty] | 0
| Upgrade/modify pumping system - report to WTP |  | allow |  | #N/A | 0 | 0 |  |  | 0 | [8 empty] | 0
[6 empty] | Total | 73984.5001 |  | 36992.25 | 36992.25 | [6 empty] | 71969.3493 | Total Difference | 2015.1508 |  | 71969.3493
[6 empty] | % of Total |  |  | 50% | 50%
* For construction of passive treatment system refer to "Water Management". ARD/ML seepage treatment becomes post-closure water treatment cost
**Heap leach ARD/ML seepage treatment becomes post-closure water treatment cost

## Chemicals
1 | Chemicals/Soil Area Name:
| INAC COST (March 2018) | [9 empty] | TMAC Cost (November 2017) | [7 empty] | COST DIFFERENCE |  | Proposed Cost (April 2018)
Note: The procedures, equipment and packaging for clean up and removal of chemicals or contaminated soils are highly dependent on the nature of the chemicals and their existing state of containment. Government guidelines should be consulted on an individual chemical basis. Any estimate made here should be considered very rough unless specific evaluations have been conducted.
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) | % Land | Land Cost | Water Cost | SRK Row Number | Facility Name | Task Description | Quantity | Unit | Unit Cost | Subtotal | TMAC Costs (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Costs
HAZARDOUS MATERIALS AUDIT
| Hazardous materials audit | Not required | allow |  | #N/A | 25000 | 0 |  | 0 | 0 | 271 | Old Boston Soil Treatment Facility | test soils in existing landfarm | 0 | each | 105.7446 | 0 | 0 | 0 |  | 0
BUILDING DECONTAMINATION & CONSOLIDATION OF HAZARDOUS MATERIALS
| Environmental technician/coordinator |  | mandays |  | #N/A | 0 | 0 |  | 0 | 0
| Drain residual fuel from tanks | BM-010 | each | 6 | TMAC | 265 | 1590 | 50% | 795 | 795 | [8 empty] | 1590 | This is accounted for in the buildings and equipment tab (Row 97) | 0
| Clean containment liners | BM-010, BM -013 & BM -030 | m² | 10706 | TMAC | 0.41 | 4389.46 | 50% | 2194.73 | 2194.73 | 204 | Boston Fuel Facility | clean liner | 4406 | m² | 0.41205 | 1815.5006 | 4418.8444 | -29.3844 |  | 4418.8444
[11 empty] | 907 | Boston Land Farm | clean liner | 3800 | m² | 0.41205 | 1565.7972
[11 empty] | 923 | Boston Airstrip De-icing Facility | clean liner | 2500 | m² | 0.41205 | 1030.1297
[11 empty] | 653 | Boston Reagent Storage | clean liner | 18 | m² | 0.41205 | 7.4169
| Decontaminate maintenance shop |  | man days |  | #N/A | 0 | 0 |  | 0 | 0
| Decontaminate sewage treatment plant | BM-015 | LS | 1 | TMAC | 667.63 | 667.63 | 50% | 333.815 | 333.815 | 658 | Boston Sewage Treatment Plant | flush and remove sewage plumbing, collect sewage sludge/waste water in 55 gallon drums | 1 | each | 677.6842 | 677.6842 | 677.6842 | -10.0542 |  | 677.6842
| Decontaminate Water Discharge Line | BM-043 | LS | 1 | TMAC | 667.63 | 667.63 | 50% | 333.815 | 333.815 | 1232 | Boston Water Discharge Line | flush pipeline prior to decommissioning | 1 | Each | 677.6842 | 677.6842 | 677.6842 | -10.0542 |  | 677.6842
| Decontaminate bulk fuel storage | BM-010 | each | 6 | TMAC | 1186.71 | 7120.26 | 50% | 3560.13 | 3560.13 | 195 | Boston Fuel Facility | wash tanks | 6 | each | 1186.7094 | 7120.2566 | 7120.2566 | 0.0034293 |  | 7120.2566
| Decontaminate Process Plant | BM-002 | m³ | 4.16 | TMAC | 2699.56 | 11230.1696 | 50% | 5615.0848 | 5615.0848 | 602 | Boston Process Plant | transport drums to Roberts Bay | 4.16 | m³ | 2.2974 | 9.5571 | 11239.7143 | -9.5447 |  | 11239.7143
[11 empty] | 595 | Boston Process Plant | Drain chemicals and reagents into containers for shipping off site | 4.16 | m3 | 2699.557 | 11230.1572
| Decontaminate offices/warehouse/accom |  | m² |  | BDAL | 25.6 | 0 |  | 0 | 0
| Removal of asbestos siding on buildings |  | m² |  | BDAL | 25.6 | 0 |  | 0 | 0
| Removal of friable asbestos on equipment |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
HAZARDOUS MATERIALS REMOVAL
| Waste oils |  | litre |  | orl | 0.43 | 0 |  | 0 | 0
| Waste fuel | BM-010 | litre | 75000 | orl | 0.43 | 32250 | 50% | 16125 | 16125 | 192 | Boston Fuel Facility | drain residual fuel | 75000 | L | 0.022717 | 1703.8014 | 3435.4579 | 28814.5421 | Memo notes that INAC estimate used rate from previous TMAC estimate, as they felt the current rate was too low. However, Source of $0.43/L cost could not be determined. Carry forward TMAC cost. | 3435.4579
[11 empty] | 193 | Boston Fuel Facility | consolidate fuel in barge at Roberts Bay | 75000 | L | 0.023089 | 1731.6565
| Waste batteries |  | allow |  | AE | 3000 | 0 |  | 0 | 0
| Assay & environmental lab reagents |  | kg |  | #N/A | 25 | 0 |  | 0 | 0
| Machine shop paints, solvents etc |  | litre |  | AE | 10000 | 0 |  | 0 | 0
| Glycol |  | litre |  | AE | 20000 | 0 |  | 0 | 0
| Process reagents | BM-002 | m³ | 5.4 | TMAC | 88.1 | 475.74 | 50% | 237.87 | 237.87 | 650 | Boston Reagent Storage | load contained contaminated soils into megabags for hauling | 5.4 | m³ | 72.731 | 392.7473 | 411.5662 | 64.1738 |  | 411.5662
[11 empty] | 651 | Boston Reagent Storage | haul megabags to Boston underground | 5.4 | m³ | 3.485 | 18.8189
| Nuclear sources |  | allow |  | #N/A | 0 | 0 |  | 0 | 0
| Other hazardous materials |  | allow |  | AE | 20000 | 0 |  | 0 | 0
HAZARDOUS MATERIALS
| Transportation to disposal facility |  | allow |  | ea | 10000 | 0 | 50% | 0 | 0
| Disposal fees |  | allow |  | ea | 20000 | 0 | 50% | 0 | 0
| Other |  | allow |  | ea | 40000 | 0 | 50% | 0 | 0
CONTAMINATED SOILS
| Contam. soil investigation - Phase 1 |  | each | 1 | CS1L | 7500 | 7500 | 50% | 3750 | 3750 | [8 empty] | 7500 | Not included in TMAC estimate. Carry forward INAC cost. | 7500
| Contam. soil investigation - Phase 2 | More money required for INAC to complete an ESA program | allow | 1 | EA | 100000 | 100000 | 50% | 50000 | 50000 | [8 empty] | 100000 | This is already included in the post-closure monitoring and maintenance. Task Monitoring Program: Initial confirmatory program (Row 10). | 0
CONTAMINATED SOIL REMOVAL
| Excavate and transport to Underground | BM-010 & BM-013 | m³ | 3783.6 | TMAC | 72.73 | 275181.228 | 50% | 137590.614 | 137590.614 | 905 | Boston Land Farm | load contained contaminated soils into megabags for shipping off-site | 1140 | m³ | 72.731 | 82913.3093 | 275184.9097 | -3.6817 |  | 275184.9097
[11 empty] | 202 | Boston Fuel Facility | load contained contaminated soils into megabags for hauling | 2643.6 | m³ | 72.731 | 192271.6004
| Place hydrocarbon underground | BM-010 & BM-013 | m³ | 3783.6 | TMAC | 15.37 | 58153.932 | 50% | 29076.966 | 29076.966 | 203 | Boston Fuel Facility | haul megabags to Boston underground | 2643.6 | m³ | 15.367 | 40624.2012 | 44340.4821 | 13813.4499 | INAC estimate used a combined volume from the landfarm and the fuel facility, then the higher of the two unit rates for the transportation. TMAC estimate calculates a unit cost based on distance. TMAC cost carried forward. | 44340.4821
[11 empty] | 906 | Boston Land Farm | haul megabags to Boston underground | 1140 | m³ | 3.2599 | 3716.2809
| Reagents/stabilizing agent | BM-030 de-icier impacted soil to underground (consolidate liner cover, containerize and haul) | m³ | 1505.4 | TMAC | 90.85 | 136765.59 |  | 0 | 136765.59 | 920 | Boston Airstrip De-icing Facility | excavate and stockpile liner protection cover | 1500 | m³ | 2.7487 | 4123.0426 | 118109.3455 | 18656.2445 | INAC estimate used unit rate of $15.37/m³ for placing mega bags underground. | 118109.3455
[11 empty] | 921 | Boston Airstrip De-icing Facility | load contained contaminated soils into megabags for hauling | 1500 | m³ | 72.731 | 109096.4596
[11 empty] | 922 | Boston Airstrip De-icing Facility | haul megabags to Boston underground | 1500 | m³ | 3.2599 | 4889.8432
| Excavate and transport to offsite facility |  | m³ |  | est. | 1000 | 0 | 50% | 0 | 0
| Sludge from Oil/Water Separator |  | m³ | 4 | TMAC | 32.8 | 131.2 | 50% | 65.6 | 65.6 | 196 | Boston Fuel Facility | operate oil/water separator | 3.9354 | m³ | 32.8016 | 129.0879 | 129.0879 | 2.1121 |  | 129.0879
CONTAMINATED SOIL VERY LOW PERMEABILITY COVER
| Supply geomembrame, HDPE, ES3, GCL |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Upper and lower bedding layers |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Install geomembrane, HDPE, ES3, GCL |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Erosion protection layer |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Vegetate |  | m² |  | #N/A | 0 | 0 |  | 0 | 0
| Install infiltration/seepage instrumentation |  | allow |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
OTHER
[5 empty] | #N/A | 0 | 0 |  | 0 | 0
[6 empty] | Total | 636122.8397 |  | 249678.6248 | 386444.2148 | [5 empty] | Total | 465745.0328 | 465745.0328 | 170377.8068 |  | 473245.0328
[6 empty] | % of Total |  |  | 39.25% | 60.75%
[18 empty] | Check | -170377.8069
636122.8396

## Bldgs & Equip
1 | Building / Equip Name: | Boston Mine |  |  |  | Bldg / Equip #: | 1
| INAC COST (March 2018) | [9 empty] | TMAC Cost (November 2017) | [7 empty] | COST DIFFERENCE |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) | % Land | Land Cost | Water Cost | SRK Row Number | Facility Name | Task Description | Quantity | Unit | Unit Cost | Subtotal | TMAC Costs (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Costs
DISPOSE MOBILE EQUIPMENT
| Decontaminate and ship off-site |  | allow |  | #N/A | 0 | 0 |  | 0 | 0
| Decontaminate and dispose on-site |  | manhours |  | mechl | 49 | 0 | 50% | 0 | 0
| Relocate Containers to Roberts Bay | BM-034 (3) | ea | 3 | TMAC | 1345 | 4035 | 50% | 2017.5 | 2017.5 | 1074 | Boston South Apron | disconnect containers and prep for shipping | 3 | each | 1368.9375 | 4106.8125 | 4106.8125 | -71.8125 |  | 4106.8125
| Relocate Trailers to Roberts Bay | BM-034 | m³ | 112 | TMAC | 19.15 | 2144.8 | 50% | 1072.4 | 1072.4 | 1075 | Boston South Apron | haul trailers to Roberts bay for shipping | 111.63 | m³ | 19.1454 | 2137.203 | 2137.203 | 7.597 |  | 2137.203
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
REMOVE BUILDINGS
| Accomodation Complex | BM-018 Demolition | m³ | 14843 | TMAC | 13.12 | 194740.16 | 50% | 97370.08 | 97370.08 | 681 | Boston Accomodation Camp Buildings | demolish accommodation trailers | 13640 | m³ | 13.1207 | 178966.1086 | 194743.7292 | -3.5692 |  | 194743.7292
[11 empty] | 682 | Boston Accomodation Camp Buildings | demolish cribbing, stairs, entryways, etc. | 202.5 | m³ | 13.1207 | 2656.9382
[11 empty] | 683 | Boston Accomodation Camp Buildings | demolish arctic corridor | 1000 | m³ | 13.1207 | 13120.6824
|  | BM-018 elec/mech discommissioning | each | 300 | TMAC | 679.52 | 203856 | 50% | 101928 | 101928 | 680 | Boston Accomodation Camp Buildings | decommission (electrical, mechanical, plumbing) | 300 | each | 679.516 | 203854.7988 | 203854.7988 | 1.2012 |  | 203854.7988
|  | BM-018 - Containerization and disposal | m³ | 24230 | TMAC | 13.49 | 326862.7 | 50% | 163431.35 | 163431.35 | 685 | Boston Accomodation Camp Buildings | load waste into containers | 23329.74 | m³ | 10.2279 | 238614.6366 | 314667.1508 | 12195.5492 | INAC estimate adds 900m3 to TMAC quantity, the source of the additional material is not known. | 314667.1508
[11 empty] | 686 | Boston Accomodation Camp Buildings | haul containers to Boston landfill | 23329.74 | m³ | 3.2599 | 76052.5142
| Process Facilities | BM-002 includes Dismantling and Demolition of Mill, Crusher and Process Plant | LS | 1 | TMAC | 300000 | 300000 | 50% | 150000 | 150000 | 596 | Boston Process Plant | disassemble equipment | 1 | each | 200000 | 200000 | 300000 | 0 |  | 300000
[11 empty] | 594 | Boston Process Plant | decommission crusher, milling, and process plants | 1 | each | 100000 | 100000
|  | BM-020 demolition only | m³ | 198800 | TMAC | 13.12 | 2608256 | 50% | 1304128 | 1304128 | 598 | Boston Process Plant | demolish / dismantle mill building | 198800 | m³ | 13.3199 | 2647993.5459 | 2647993.5459 | -39737.5459 | INAC using lower unit rate. Source of unit rate unknown. Carry forward TMAC unit rate | 2647993.5459
|  | BM-020 office decommissioning | each | 2 | TMAC | 679.52 | 1359.04 | 50% | 679.52 | 679.52 | 616 | Boston Mill Office | decommission (electrical, mechanical, plumbing) | 2 | each | 679.516 | 1359.032 | 1359.032 | 0.0080081 |  | 1359.032
|  | Bm-020 Collect surface debris | m² | 14000 | TMAC | 0.37 | 5180 | 50% | 2590 | 2590 | 599 | Boston Process Plant | Collect Debris | 14000 | m² | 0.37494 | 5249.1386 | 5249.1386 | -69.1386 |  | 5249.1386
|  | BM-020 transfer to landfill | m³ | 207145 | TMAC | 3.26 | 675292.7 | 50% | 337646.35 | 337646.35 | 600 | Boston Process Plant | load waste for transport to Landfill | 8344.8 | m³ | 10.2279 | 85349.919 | 124579.9089 | 550712.7911 | INAC estimate using building volume plus compacted waste volume from buildings, rather than just the compacted waste volume and unit cost for hauling loaded containers to the landfill. Carry forward TMAC cost. | 124579.9089
[11 empty] | 657 | Boston Reagent Storage | haul containers to Boston landfill | 3.668 | m³ | 3.2599 | 11.9573
[11 empty] | 601 | Boston Process Plant | Haul debris to landfill | 8344.8 | m³ | 4.6997 | 39218.0326
| Offices, Repair, Lab, Warehouse | BM-004, BM-005,BM-006, BM-007 demo, load, haul and tip at landfill | m³ | 570 | TMAC | 26.61 | 15167.7 | 50% | 7583.85 | 7583.85 | 629 | Boston Exploration Office | demolish cribbing, stairs, entryways, etc. | 18 | m³ | 13.1207 | 236.1723 | 10742.568 | 4425.132 | Unit cost appears to be created from combining three TMAC tasks (Demolish cribbing stairs etc + collect all debris + haul debris to Boston Landfill), souce of quantity unknown.. Carry forward TMAC estimate. | 10742.568
[11 empty] | 631 | Boston Exploration Office | load waste into containers | 59.688 | m³ | 10.2279 | 610.4839
[11 empty] | 612 | Boston Warehouse | dismantle wood flooring, shelving, and lofts | 9 | m³ | 13.1207 | 118.0861
[11 empty] | 617 | Boston Mill Office | demolish trailers | 90 | m³ | 13.1207 | 1180.8614
[11 empty] | 619 | Boston Mill Office | load waste into containers | 59.688 | m³ | 10.2279 | 610.4839
[11 empty] | 624 | Boston Mine Office | collect all debris | 36 | m² | 0.37494 | 13.4978
[11 empty] | 614 | Boston Warehouse | load debris into containers for transport | 18.14 | m³ | 10.2279 | 185.5344
[11 empty] | 615 | Boston Warehouse | haul debris to Boston landfill | 18.14 | m³ | 3.2599 | 59.1345
[11 empty] | 626 | Boston Mine Office | haul containers to Boston landfill | 59.688 | m³ | 3.2599 | 194.5766
[11 empty] | 632 | Boston Exploration Office | haul containers to Boston landfill | 59.688 | m³ | 3.2599 | 194.5766
[11 empty] | 628 | Boston Exploration Office | demolish trailer | 90 | m³ | 13.1207 | 1180.8614
[11 empty] | 622 | Boston Mine Office | demolish trailer | 90 | m³ | 13.1207 | 1180.8614
[11 empty] | 620 | Boston Mill Office | haul containers to Boston landfill | 59.688 | m³ | 3.2599 | 194.5766
[11 empty] | 623 | Boston Mine Office | demolish cribbing, stairs, entryways, etc. | 18 | m³ | 13.1207 | 236.1723
[11 empty] | 625 | Boston Mine Office | load waste into containers | 59.688 | m³ | 10.2279 | 610.4839
[11 empty] | 611 | Boston Warehouse | demolish tent structure | 300 | m³ | 13.1207 | 3936.2047
|  | decommission equipment | [8 empty] | 621 | Boston Mine Office | decommission (electrical, mechanical, plumbing) | 2 | each | 679.516 | 1359.032 | 2718.064 | 1359.056 |  | 2718.064
|  |  | each | 6 | TMAC | 679.52 | 4077.12 | 50% | 2038.56 | 2038.56 | 627 | Boston Exploration Office | decommission (electrical, mechanical, plumbing) | 2 | each | 679.516 | 1359.032
| Storage Facilites |  | m² |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 0
| Water and Wastewater Treatment Facilities | BM-011 dismantle equipment | ea | 1 | TMAC | 1369 | 1369 | 50% | 684.5 | 684.5 | 645 | Boston Mill Effluent Discharge Water Treatment Plant | disconnect containers and prep for shipping off-site | 1 | each | 1368.9375 | 1368.9375 | 1368.9375 | 0.062494 |  | 1368.9375
|  | BM-011 dismantle and haul to landfill | m³ | 150 | TMAC | 59.95 | 8992.5 | 50% | 4496.25 | 4496.25 | 646 | Boston Mill Effluent Discharge Water Treatment Plant | haul containers to Boston landfill | 150 | m³ | 3.2599 | 488.9843 | 2527.7578 | 6464.7422 | Source of unit rate used in INAC estimate is not clear. Carry forward TMAC cost. | 2527.7578
[11 empty] | 644 | Boston Mill Effluent Discharge Water Treatment Plant | decommission (electrical, mechanical, plumbing) | 3 | each | 679.516 | 2038.548
[11 empty] | 648 | Boston Mill Effluent Discharge Water Treatment Plant | load debris into containers for transport | 0.018 | m³ | 10.2279 | 0.1841
[11 empty] | 649 | Boston Mill Effluent Discharge Water Treatment Plant | haul debris to Boston landfill | 0.018 | m³ | 2.2974 | 0.041353
| Fire Water Tank | BM-017 demolition | m³ | 74.42 | TMAC | 13.12 | 976.3904 | 50% | 488.1952 | 488.1952 | 672 | Boston Fire Water Tank | demolish structure | 74.42 | m³ | 13.1207 | 976.4412 | 976.4412 | -0.050788 |  | 976.4412
|  | BM-017 dismantle into cut for haulage | each | 1 | TMAC | 74212 | 74212 | 50% | 37106 | 37106 | 674 | Boston Fire Water Tank | dismantle tanks and cut into manageable pieces | 1 | each | 74211.7425 | 74211.7425 | 74211.7425 | 0.25747 |  | 74211.7425
|  | BM-017 elec/mech discommissioning | each | 2 | TMAC | 1328 | 2656 | 50% | 1328 | 1328 | 671 | Boston Fire Water Tank | decommission and disconnect electrical and plumbing | 2 | each | 1327.7055 | 2655.411 | 2655.411 | 0.58899 |  | 2655.411
|  | BM-017 consolidate and haul to landfill | m³ | 39.2 | TMAC | 13.49 | 528.808 | 50% | 264.404 | 264.404 | 673 | Boston Fire Water Tank | remove tank insulation | 1 | each | 746.4588 | 746.4588 | 1275.9754 | -747.1674
[11 empty] | 675 | Boston Fire Water Tank | prepare pieces for transportation | 2.2051 | m³ | 10.2279 | 22.5535
[11 empty] | 678 | Boston Fire Water Tank | load debris into containers for transport | 37.0538 | m³ | 10.2279 | 378.9832
[11 empty] | 676 | Boston Fire Water Tank | haul cut metal to Boston landfill | 2.2051 | m³ | 3.2599 | 7.1884
[11 empty] | 679 | Boston Fire Water Tank | haul debris to Boston landfill | 37.0538 | m³ | 3.2599 | 120.7915
| Power Plant | BM-003 includes dismantling/demolition and haulage to Landfill | m³ | 3151 | TMAC | 26.61 | 83848.11 | 50% | 41924.055 | 41924.055 | 609 | Boston Power Plant | load waste into containers | 3150.75 | m³ | 10.2279 | 32225.6084 | 84590.0443 | -741.9343 |  | 84590.0443
[11 empty] | 610 | Boston Power Plant | haul containers to Boston landfill | 3150.75 | m³ | 3.2599 | 10271.1157
[11 empty] | 604 | Boston Power Plant | demolish building | 3125 | m³ | 13.3199 | 41624.647
[11 empty] | 608 | Boston Power Plant | collect all debris | 1250 | m² | 0.37494 | 468.6731
|  | BM-003 dismantle equipment | ea | 4 | TMAC | 784.27 | 3137.08 | 50% | 1568.54 | 1568.54 | 603 | Boston Power Plant | decommission (electrical) | 4 | each | 784.274 | 3137.0961 | 3137.0961 | -0.016135 |  | 3137.0961
|  | BM-003 Prep equipment for offsite shipment | LS | 1 | TMAC | 50000 | 50000 | 50% | 25000 | 25000 | 597 | Boston Process Plant | prepare equipment for shipping off-site | 1 | each | 50000 | 50000 | 50000 | 0 |  | 50000
|  | Dismantle, prep and haul stacks for offsite disposal | lm | 40 | TMAC | 879.54 | 35181.6 | 50% | 17590.8 | 17590.8 | 605 | Boston Power Plant | dismantle stacks | 40 | m | 136.3041 | 5452.1645 | 31083.0717 | 4098.5283 | INAC cost estimate combines several tasks and the resulting task has a higher until rate. Source of the higher unit rate is unclear. Carry forward TMAC cost. | 31083.0717
[11 empty] | 607 | Boston Power Plant | haul stack sections to Boston landfill | 166 | m3 | 3.2599 | 541.1427
[11 empty] | 606 | Boston Power Plant | prep stacks for shipping | 40 | m | 627.2441 | 25089.7645
| Communication Tower |  | m² |  | brs1h | 65 | 0 | 50% | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| U/G Heating Plant |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| Emulsion Plant |  | m² |  | #N/A | 0 | 0 |  | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| AN Storage Facility |  | m² |  | brs1s | 128 | 0 | 50% | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| Warehouse, Shops and Other | BM-009, BM-012 dismantle and transfer to Landfill | m³ | 2400 | TMAC | 26.61 | 63864 | 50% | 31932 | 31932 | 639 | Boston Mobile Equipment Workshop | decommission (electrical, mechanical, plumbing) | 2 | each | 679.516 | 1359.032 | 61455.102 | 2408.898 | INAC unit cost appears to be created from combining three TMAC tasks (Demolish cribbing stairs etc + collect all debris + haul debris to Boston Landfill), but source of volume unknown. TMAC estimate carried forward because it includes a higher level of detail. | 61455.102
[11 empty] | 642 | Boston Mobile Equipment Workshop | load debris into containers for transport | 35.325 | m³ | 10.2279 | 361.3012
[11 empty] | 654 | Boston Reagent Storage | remove and cut liner into manageable pieces | 18 | m² | 0.17038 | 3.0668
[11 empty] | 656 | Boston Reagent Storage | load waste into containers | 3.668 | m³ | 10.2279 | 37.516
[11 empty] | 925 | Boston Airstrip De-icing Facility | load waste into containers | 22.5 | m³ | 10.2279 | 230.1281
[11 empty] | 926 | Boston Airstrip De-icing Facility | haul containers to Boston landfill | 22.5 | m³ | 3.2599 | 73.3476
[11 empty] | 665 | Boston Sewage Treatment Plant | haul debris to Boston landfill | 2.6687 | m³ | 3.2599 | 8.6995
[11 empty] | 661 | Boston Sewage Treatment Plant | disconnect containers and prep for shipping | 1 | each | 1368.9375 | 1368.9375
[11 empty] | 688 | Boston Core Shack | demolish tent structure | 781.25 | m³ | 13.1207 | 10250.5332
[11 empty] | 689 | Boston Core Shack | dismantle wood flooring, shelving, and lofts | 390.625 | m³ | 13.1207 | 5125.2666
[11 empty] | 684 | Boston Accomodation Camp Buildings | collect all debris | 4140 | m² | 0.37494 | 1552.2453
[11 empty] | 687 | Boston Core Shack | decommission (electrical, heating) | 2 | each | 679.516 | 1359.032
[11 empty] | 691 | Boston Core Shack | load debris into containers for transport | 113.5625 | m³ | 10.2279 | 1161.5078
[11 empty] | 640 | Boston Mobile Equipment Workshop | demolish tent structure | 2250 | m³ | 13.1207 | 29521.5355
[11 empty] | 655 | Boston Reagent Storage | demolish tent structure | 36 | m³ | 13.1207 | 472.3446
[11 empty] | 667 | Boston Potable Water Treatment Plant | demolish structure | 105 | m³ | 13.1207 | 1377.6717
[11 empty] | 670 | Boston Potable Water Treatment Plant | haul debris to Boston landfill | 7.5654 | m³ | 3.2599 | 24.6623
[11 empty] | 899 | Boston Laydown Area | decommission vehicle plug system | 10 | each | 679.516 | 6795.16
[11 empty] | 909 | Boston Land Farm | load waste into containers | 36.48 | m³ | 10.2279 | 373.1144
| Laydown area and Core Pad | BM-014 & BM-019 surface clean up | m² | 19300 | TMAC | 0.37 | 7141 | 50% | 3570.5 | 3570.5 | 912 | Boston Core Storage Pad | collect all debris | 10000 | m² | 0.37494 | 3749.3847 | 7236.3126 | -95.3126 |  | 7236.3126
[11 empty] | 901 | Boston Laydown Area | collect all debris | 9300 | m² | 0.37494 | 3486.9278
|  | Post removals | ea | 10 | TMAC | 411.17 | 4111.7 | 50% | 2055.85 | 2055.85 | 900 | Boston Laydown Area | remove cables and posts | 10 | each | 411.1736 | 4111.7362 | 4111.7362 | -0.036223 |  | 4111.7362
|  | BM-019 demolition | m³ | 1000 | TMAC | 13.12 | 13120 | 50% | 6560 | 6560 | 911 | Boston Core Storage Pad | band together core boxes | 500 | each | 11.3587 | 5679.338 | 5679.338 | 7440.662 | INAC unit cost equates this task to demolishing a building, which over estimates the unit cost. Additionally the source of the volume used by INAC is unkonwn. TMAC cost carried forward. | 5679.338
|  | BM-014 & BM-019 debris haul and dispose of at landfill | m³ | 1011.6 | TMAC | 12.59 | 12736.044 | 50% | 6368.022 | 6368.022 | 902 | Boston Laydown Area | load waste into containers | 5.58 | m³ | 10.2279 | 57.0718 | 156.1889 | 12579.8551 | Source of volume and unit cost associated with the INAC cost could not be determined. Carry forward TMAC costs. | 156.1889
[11 empty] | 903 | Boston Laydown Area | haul debris to Boston landfill | 5.58 | m³ | 3.2599 | 18.1902
[11 empty] | 913 | Boston Core Storage Pad | load waste into containers | 6 | m³ | 10.2279 | 61.3675
[11 empty] | 914 | Boston Core Storage Pad | haul debris to Boston landfill | 6 | m³ | 3.2599 | 19.5594
| Fuel tanks | BM-010 | ea | 6 | TMAC | 76000 | 456000 | 50% | 228000 | 228000 | 198 | Boston Fuel Facility | dismantle tanks and cut into manageable pieces | 6 | each | 74211.7425 | 445270.4552 | 450983.2005 | 5016.7995 | Source of INAC unit cost unknown. TMAC cost carried forward. | 450983.2005
[11 empty] | 197 | Boston Fuel Facility | disconnect piping and controls | 6 | each | 476.0621 | 2856.3727
[11 empty] | 194 | Boston Fuel Facility | decommission fuel transfer facilities | 6 | each | 476.0621 | 2856.3727
| Remove containment liner | BM-010, BM-030 & BM-013 | m² | 29001.6 | TMAC | 0.57 | 16530.912 | 50% | 8265.456 | 8265.456 | 908 | Boston Land Farm | remove and cut liner into manageable pieces | 3800 | m² | 0.17038 | 647.4445 | 1824.0898 | 14706.8222 |  | 1824.0898
[11 empty] | 924 | Boston Airstrip De-icing Facility | remove and cut liner into manageable pieces | 2500 | m² | 0.17038 | 425.9504
[11 empty] | 205 | Boston Fuel Facility | remove and cut liner into manageable pieces | 4406 | m² | 0.17038 | 750.6949
| Excavate containment area | BM-010 & BM-013 | m³ | 7567.2 | TMAC | 2.75 | 20809.8 | 50% | 10404.9 | 10404.9 | 201 | Boston Fuel Facility | excavate and stockpile liner protection cover | 5287.2 | m³ | 2.7487 | 14532.9007 | 20799.9255 | 9.8745 |  | 20799.9255
[11 empty] | 904 | Boston Land Farm | excavate and stockpile liner protection cover | 2280 | m³ | 2.7487 | 6267.0248
| Fuel tank piping and containment structure | BM-010 includes load and transport to landfill | m³ | 87.13 | TMAC | 24.31 | 2118.1303 | 50% | 1059.0652 | 1059.0652 | [7 empty] | 1003.4609 | 1114.6694 |  | 1003.4609
[11 empty] | 200 | Boston Fuel Facility | haul cut metal to Boston landfill laydown | 23.7345 | m³ | 4.7346 | 112.3737
[11 empty] | 199 | Boston Fuel Facility | prepare pieces for transportation - load into container | 23.7345 | m³ | 10.2279 | 242.7547
[11 empty] | 206 | Boston Fuel Facility | load waste into containers | 63.3885 | m³ | 10.2279 | 648.3325
| Water Discharge Line | BM-043 | m | 282 | TMAC | 10.79 | 3042.78 | 50% | 1521.39 | 1521.39 | 660 | Boston Sewage Treatment Plant | Decommission sewage pipes | 50 | lm | 119.0155 | 5950.7764 | 5950.7764 | -2907.9964 | Source of INAC costs unknown. | 5950.7764
| Water Discharge Line -electrical | BM-43 | ea | 2 | TMAC | 679.52 | 1359.04 | 50% | 679.52 | 679.52 | 1234 | Boston Water Discharge Line | remove electrical cables and controllers | 2 | each | 679.516 | 1359.032 | 1359.032 | 0.0080081 |  | 1359.032
| Water Discharge | BM-043 demo and landfill | m³ | 13.8 | TMAC | 13.49 | 186.162 | 50% | 93.081 | 93.081 | 1236 | Boston Water Discharge Line | haul containers to Boston landfill | 98.1748 | m³ | 3.2599 | 320.0395 | 320.0395 | -133.8775 |  | 320.0395
| Contact Ponds decommissioning | BM-021, BM-025, BM-027 & BM-032 | m³ | 184 | TMAC | 13.49 | 2482.16 | 50% | 1241.08 | 1241.08 | 769 | Boston Contact Water Pond #2 | load waste into containers | 1.62 | m³ | 10.2279 | 16.5692 | 2480.5551 | 1.6049 |  | 2480.5551
[11 empty] | 770 | Boston Contact Water Pond #2 | haul containers to Boston landfill | 1.62 | m³ | 3.2599 | 5.281
[11 empty] | 774 | Boston Contact Water Pond #1 | load waste into containers | 1.1993 | m³ | 10.2279 | 12.2662
[11 empty] | 775 | Boston Contact Water Pond #1 | haul containers to Boston landfill | 1.1993 | m³ | 3.2599 | 3.9095
[11 empty] | 779 | Boston Overburden Pile Sedimentation Pond | load waste into containers off-site | 1.1993 | m³ | 10.2279 | 12.2662
[11 empty] | 780 | Boston Overburden Pile Sedimentation Pond | haul containers to Boston landfill | 1.1993 | m³ | 3.2599 | 3.9095
[11 empty] | 785 | Boston TMA Contact Water Pond Berms | load waste into containers for hauling to landfill | 179.8923 | m³ | 10.2279 | 1839.9234
[11 empty] | 786 | Boston TMA Contact Water Pond Berms | haul containers to Boston landfill | 179.8923 | m³ | 3.2599 | 586.4301
| Airstrip lighting, navigation, electrician | Tower fixtures | ea | 10 | TMAC | 68.15 | 681.5 | 50% | 340.75 | 340.75 | 694 | Boston Airstrip Lighting | remove floating lighting fixtures (airstrip lighting, approach lights) | 10 | each | 68.1521 | 681.5206 | 681.5206 | -0.020566 |  | 681.5206
| Airstrip lighting, navigation, mechanical | Tower fixtures and equipment | ea | 2 | TMAC | 374.34 | 748.68 | 50% | 374.34 | 374.34 | 1072 | Boston South Apron | decommission electrical, and heating from traffic control tower | 2 | each | 374.3352 | 748.6703 | 748.6703 | 0.0096626 |  | 748.6703
| Break foundation slabs |  | m² |  | brcs | 6 | 0 | 50% | 0 | 0
| Consolidate & dump boneyard debris |  | allow |  | brs1l | 45 | 0 |  | 0 | 0
| Worker Dry | BM-008 Demo, prep and haul waste to landfill | m³ | 682 | TMAC | 26.61 | 18148.02 | 50% | 9074.01 | 9074.01 | 636 | Boston Mine Dry | collect all debris | 198 | m² | 0.37494 | 74.2378 | 29277.3824 | -11129.3624 | Appears as thought the bottom 3 TMAC tasks noted are combined, 682 m³ x ($13.12+$10.23+$3.26), this causes the INAC estimate to over estimate the cost associated with cribbing, stairs, entryways etc.. INAC does not include the top two items in their estimate. Carry forward TMAC cost. | 29277.3824
[11 empty] | 634 | Boston Mine Dry | demolish trailer | 1485 | m³ | 13.3199 | 19780.0323
[11 empty] | 635 | Boston Mine Dry | demolish cribbing, stairs, entryways, etc. | 18 | m³ | 13.1207 | 236.1723
[11 empty] | 637 | Boston Mine Dry | load waste into containers off-site | 681.129 | m³ | 10.2279 | 6966.5307
[11 empty] | 638 | Boston Mine Dry | haul containers to Boston landfill | 681.129 | m³ | 3.2599 | 2220.4094
|  | BM-008 decommission equipment | ea | 3 | TMAC | 679.52 | 2038.56 | 50% | 1019.28 | 1019.28 | 633 | Boston Mine Dry | decommission (electrical, mechanical, plumbing) | 3 | each | 679.516 | 2038.548 | 2038.548 | 0.012012 |  | 2038.548
| Potable WTP & STP | BM-015 & BM-016 Decon electrical | ea | 107 | TMAC | 679.52 | 72708.64 | 50% | 36354.32 | 36354.32 | 659 | Boston Sewage Treatment Plant | decommission (electrical and plumbing) | 2 | each | 679.516 | 1359.032 | 72708.2116 | 0.42843 |  | 72708.2116
[11 empty] | 666 | Boston Potable Water Treatment Plant | decommission (electrical) | 105 | each | 679.516 | 71349.1796
|  | BM-015 & BM -016 demo and landfill | m³ | 82.5 | TMAC | 26.61 | 2195.325 | 50% | 1097.6625 | 1097.6625 | 669 | Boston Potable Water Treatment Plant | load debris into containers for transport | 7.5654 | m³ | 10.2279 | 77.3779 | 348.2683 | 1847.0567 |  | 348.2683
[11 empty] | 662 | Boston Sewage Treatment Plant | haul containers to Boston landfill | 74.725 | m³ | 3.2599 | 243.5957
[11 empty] | 664 | Boston Sewage Treatment Plant | load debris into containers for transport | 2.6687 | m³ | 10.2279 | 27.2948
| WTP Mine Water |  | m² |  | brs1l | 45 | 0 | 50% | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| Water Intake |  | m² |  | brcs | 6 | 0 |  | 0 | 0 | [7 empty] | 0 | 0 |  | 0
| Airstrip/Apron and Helipad | BM-029, BM-030 and BM-034 clean up | m² | 68500 | TMAC | 0.37 | 25345 | 50% | 12672.5 | 12672.5 | 1063 | Boston Heliport | collect debris | 1165 | m² | 0.37494 | 436.8033 | 25542.6836 | -197.6836 |  | 25542.6836
[11 empty] | 1076 | Boston South Apron | collect all debris | 6000 | m² | 0.37494 | 2249.6308
[11 empty] | 1067 | Boston Airstrip | collect all debris | 60960 | m² | 0.37494 | 22856.2494
|  | demo heli shack includes containerization and haul to landfill | m³ | 45 | TMAC | 26.61 | 1197.45 | 50% | 598.725 | 598.725 | 1061 | Boston Heliport | dismantle helicopter pads and walkway | 15 | m³ | 4.1816 | 62.7244 | 1580.268 | -382.818 |  | 1580.268
[11 empty] | 1073 | Boston South Apron | demolish control tower structure (wood shack) | 30.5 | m³ | 13.1207 | 400.1808
[11 empty] | 1064 | Boston Heliport | load debris into containers for transport | 51.519 | m³ | 10.2279 | 526.932
[11 empty] | 1062 | Boston Heliport | demolish helishack | 45 | m³ | 13.1207 | 590.4307
|  | Remove lighting | ea | 70 | TMAC | 42.47 | 2972.9 | 50% | 1486.45 | 1486.45 | 693 | Boston Airstrip Lighting | remove ground lighting fixtures (airstrip lighting, approach lights) | 70 | each | 42.4697 | 2972.8825 | 2972.8825 | 0.017518 |  | 2972.8825
|  | BM-029, BM-030 and BM-034 includes disposal in landfill | m² | 68500 | TMAC | 0.15 | 10275 | 50% | 5137.5 | 5137.5 | 1065 | Boston Heliport | haul debris to Boston landfill | 51.519 | m³ | 3.2599 | 167.9466 | 1011.7441 | 9263.2559 | It appears that INAC estimate used surface area of facilities (rounded up to nearest 500) rather than volume of material. Source of unit cost unknown. Carry forward TMAC cost. | 1011.7441
[11 empty] | 1077 | Boston South Apron | load waste into containers | 25.984 | m³ | 10.2279 | 265.7622
[11 empty] | 1078 | Boston South Apron | haul containers to Boston landfill | 25.984 | m³ | 3.2599 | 84.7051
[11 empty] | 1069 | Boston Airstrip | haul containers to Boston landfill | 36.576 | m³ | 3.2599 | 119.2339
[11 empty] | 1068 | Boston Airstrip | load waste into containers | 36.576 | m³ | 10.2279 | 374.0963
| Other | clean up general areas | m² | 1100 | TMAC | 0.37 | 407 | 50% | 203.5 | 203.5 | 613 | Boston Warehouse | collect debris | 60 | m² | 0.37494 | 22.4963 | 412.2554 | -5.2554 |  | 412.2554
[11 empty] | 618 | Boston Mill Office | collect all debris | 36 | m² | 0.37494 | 13.4978
[11 empty] | 630 | Boston Exploration Office | collect all debris | 36 | m² | 0.37494 | 13.4978
[11 empty] | 641 | Boston Mobile Equipment Workshop | collect debris | 450 | m² | 0.37494 | 168.7223
[11 empty] | 647 | Boston Mill Effluent Discharge Water Treatment Plant | collect debris | 30 | m² | 0.37494 | 11.2482
[11 empty] | 652 | Boston Reagent Storage | collect all debris | 30 | m² | 0.37494 | 11.2482
[11 empty] | 663 | Boston Sewage Treatment Plant | collect debris | 29.89 | m² | 0.37494 | 11.2069
[11 empty] | 668 | Boston Potable Water Treatment Plant | collect debris | 42 | m² | 0.37494 | 15.7474
[11 empty] | 677 | Boston Fire Water Tank | collect debris | 73.1382 | m² | 0.37494 | 27.4223
[11 empty] | 690 | Boston Core Shack | collect debris | 312.5 | m² | 0.37494 | 117.1683
|  | General Area debris haulage and disposal in landfill | m² | 1100 | TMAC | 0.15 | 165 | 50% | 82.5 | 82.5 | 910 | Boston Land Farm | haul containers to Boston landfill | 36.48 | m³ | 3.2599 | 118.921 | 810.9186 | -645.9186 |  | 810.9186
[11 empty] | 692 | Boston Core Shack | haul debris to Boston landfill | 113.5625 | m³ | 3.2599 | 370.2019
[11 empty] | 643 | Boston Mobile Equipment Workshop | haul debris to Boston landfill | 35.325 | m³ | 3.2599 | 115.1558
[11 empty] | 207 | Boston Fuel Facility | haul containers to Boston landfill | 63.3885 | m³ | 3.2599 | 206.64
|  | Seacan landfill placement (double SRK volume) | m³ | 2259 | TMAC | 86.72 | 195900.48 | 50% | 97950.24 | 97950.24 | 1198 | Boston Landfill | empty seacan of debris, place and track pack (all site waste to Boston landfill) | 1129.5028 | each | 86.7233 | 97954.154 | 97954.154 | 97946.326 | INAC estimate doubled the quantity, reason for doubling unknown. Carry forward TMAC cost. | 97954.154
LANDFILL FOR DEMOLITION WASTE
| Place rock cover | BM-038 | m³ | 8112 | TMAC | 16.35 | 132631.2 | 50% | 66315.6 | 66315.6 | 1201 | Boston Landfill | place 0.3 m crushed gravel + 0.7 m ROQ liner protection layer | 8112 | m³ | 16.3529 | 132654.5462 | 132654.5462 | -23.3462 |  | 132654.5462
| Generate rock cover | BM-038 assumes 300 mm cover | m³ | 8112 | TMAC | 24.76 | 200853.12 | 50% | 100426.56 | 100426.56 | 1200 | Boston Landfill | Produce ROQ (quarry drill&blast) | 8112 | m³ | 24.7628 | 200876.1143 | 200876.1143 | -22.9943 |  | 200876.1143
| Final grading of landfill cover | BM-038 | m² | 27040 | TMAC | 1.23 | 33259.2 | 50% | 16629.6 | 16629.6 | 1199 | Boston Landfill | regrade top surface for positive drainage | 27040 | m² | 1.2273 | 33187.544 | 33187.544 | 71.656 |  | 33187.544
| Place soil cover |  | allow |  | #N/A |  | 0 |  | 0 | 0
| Vegetate |  | ha |  | #N/A | 0 | 0 |  | 0 | 0
GRADE AND CONTOUR PADS
| Accomodation Complex |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Process Facilities |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Offices, Repair, Lab, Warehouse |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Storage Facilites |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Water and Wastewater Treatment Facilities |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Power Plant |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Communication Tower |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| U/G Heating Plant |  | m² |  | #N/A | 0 | 0 | 50% | 0 | 0
| Emulsion Plant |  | m² |  | #N/A | 0 | 0 | 50% | 0 | 0
| Warehouse, Shops and Other |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Fuel tanks on site for bulk fuel storage |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Fire Protection pumping station |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Worker Dry |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| WTP & Fresh Water Pumping Station |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| WRSF Pond and Attenuation Pond Pumphouses |  | m² |  | AE | 8.47 | 0 | 50% | 0 | 0
| Other | BM-036 Developed Areas | m² | 122000 | TMAC | 1.23 | 150060 | 50% | 75030 | 75030 | 915 | Boston Developed Areas (for regrading) | regrade for positive drainage | 122000 | m² | 0.0098795 | 1205.3019 | 1205.3019 | 148854.6981 | INAC estimate uses a unit cost associated with large scale regrading using a D7 bulldozer. The TMAC unit cost is associated with a grader, regrading the top surface to fill in small depressions. SRK updated the unit cost for grader regrading. Carry forward updated TMAC cost. | 29280
REMOVE LINED CONTAINMENT STRUCTURES
| Decontaminate/Remove/Dispose of Liner | see Chemicals or Water Treatment | m³ |  | #N/A | 0 | 0 |  | 0 | 0
RECLAIM ROADS
| Remove culverts |  | lm |  | TMAC | 95.76 | 0 |  | 0 | 0
| Remove bridges |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Grade roads | BM-023, BM-037, BM-039 and BM-045 (assumes 4.1 km of road at 10 m width) | ha | 0.41 | TMAC | 12300 | 5043 | 50% | 2521.5 | 2521.5 | 1080 | Boston Landfill Access Road | crown road for positive drainage | 1.261 | km | 866.22 | 1092.3034 | 3645.0538 | 1397.9462 | SRK unit rate updated to $940/km | 3955.52
[11 empty] | 1059 | Boston Mill Haul Road | crown road for positive drainage | 0.293 | km | 866.22 | 253.8025
[11 empty] | 1079 | Boston Airstrip Access Road | crown road for positive drainage | 1.024 | km | 866.22 | 887.0093
[11 empty] | 962 | Boston Water Discharge Access Road | crown road for positive drainage | 0.214 | km | 866.22 | 185.3711
[11 empty] | 963 | Boston Vent Raise Access Road | crown road for positive drainage | 1.17 | km | 866.22 | 1013.4774
[11 empty] | 1081 | Boston Water Intake Access Road | crown road for positive drainage | 0.246 | km | 866.22 | 213.0901
| Grade Helipad, Airstrip and Aprons | BM-029, BM-030 and BM-034 | ha | 6.85 | TMAC | 12300 | 84255 | 50% | 42127.5 | 42127.5 | 1070 | Boston Airstrip | crown airstrip and airstrip expansion for positive drainage | 60960 | m² | 1.2273 | 74819.256 | 82828.5725 | 1426.4275 |  | 82828.5725
[11 empty] | 1071 | Boston South Apron | regrade for positive drainage | 6000 | m² | 1.2273 | 7364.1
[11 empty] | 1066 | Boston Airstrip | decommission airstrip | 2 | Each | 322.6082 | 645.2165
| Scarify ore piles laydown area |  | ha |  | scfyl | 4300 | 0 |  | 0 | 0
| Vegetate |  | allow |  | ea | 20000 | 0 |  | 0 | 0
| Other |  | ha |  | scfyh | 6030 | 0 |  | 0 | 0
SPECIALIZED ITEMS
| Dispose of misc. debris and laydown area refuse |  |  |  | #N/A | 0 | 0 |  | 0 | 0
[6 empty] | Total | 6144259.5118 |  | 3072129.7559 | 3072129.7559 | [6 empty] | 5317822.8266 | 5317822.8266 | 826436.6851 |  | 5344932.0156
[6 empty] | % of Total |  |  | 50% | 50%
| Note: | [16 empty] | Check | 826436.6852
0
Note on C21: Megan Miller: I am assuming that there is a typo here and the work area code referenced is meant to be BM-002
Note on G102: Megan Miller: This unit rate and units are very different, need to confirm that these are refering to the same tasks
Note on G190: Megan Miller: Regrading with D7
Note on R190: Megan Miller: Scarifying with grader

## PostClosure
1 | Post-Closure Monitoring & Maintenance:
| INAC COST (March 2018) | [7 empty] | TMAC Cost (November 2017) | [6 empty] | COST DIFFERENCE
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Costs (March 2018) |  | SRK Row Number | Facility Name | Task Description | Quantity | Unit | Unit Cost | TMAC Costs (November 2017) | Cost Difference (INAC-TMAC) | Notes
MONITORING & INSPECTIONS
| Annual geotechnical inspection | Year 1, 2, 3, 6, 10, 15, 20, & 25 | each | 1 | TMAC | 28000 | 28000 | 8 inspections @$35,000 each = $280,000 | 31 | Annual geotechnical inspection | Annual geotechnical inspection Annual for first 3 years, the years 6 and 10 | 5 | LS | 35000 | 175000 |  | INAC added 3 additional inspections, but they also in the end discounted the costs by 3%
| Cover Monitoirng Inspections | Year 2, 4, 6, 8, 10, 15, 20 &25 | each | 1 | TMAC | 28000 | 28000 | 8 inspections @$35,000 each = $280,000 | 32 | Cover monitoring | Cover monitoring Every 2 years for a 10 year period | 5 | LS | 35000 | 175000 |  | INAC added 3 additional inspections, but they also in the end discounted the costs by 3%
| Surface water sampling | Year 1 - 5, 7, 10, 15, 20 & 25 | each | 1 | TMAC | 60000 | 60000 | 10 insepctions @$60,000 = $600,000 | 34 | Water sampling and testing | Water sampling and testing Annual for 5 consecutive years, they year 7 and 10 | 7 | LS | 60000 | 420000 |  | INAC added 3 additional inspections, but they also in the end discounted the costs by 3%
| Groundwater sampling |  | each |  | wsh | 10000 | 0
| Receiving.downstream water sampling |  | each |  | wsh | 10000 | 0
| Monitoring program | initial confirmatory program | each | 1 | TMAC | 10000 | 10000 | 1 time event prorated for 10 years total = $100,000 | 29 | Confirmatory Sampling and Analysis | Confirmatory Sampling and Analysis | 1 | LS | 100000 | 100000
| Survey inspection |  | each |  | #N/A | 0 | 0
| Regulatory Monitoring* | Year 1 - 10, 15, 20 & 25 | each | 1 | TMAC | 26000 | 26000 | 13 insepctions @$20,000 = $260,000 | 33 | Regulatory costs | Regulatory costs Yearly for 10 years | 10 | LS | 20000 | 200000 |  | INAC added 3 additional inspections, but they also in the end discounted the costs by 3%
| Site water monitoring (AEMP and SNP) |  | each |  | #N/A | 25000 | 0
| - Active closure and flooding |  | each |  | #N/A | 0 | 0
| - Post pit flooding |  | each |  | #N/A | 0 | 0
| Air Quality Monitoring Program (AQMP) |  | each |  | #N/A | 0 | 0
| Wildlife Effects Monitoring Program (WEMP) |  | each |  | #N/A | 0 | 0
| Vegetation Monitoring |  | each |  | #N/A | 0 | 0
| Other | Equipment mechanic for inspections | days | 5 | TMAC | 1157.53 | 5787.65 | approximately 50 days of mechanic time over ten years | 25 | Equipment maintenance support - Mechanic | Equipment maintenance support - Mechanic | 48 | days | 1157.5275 | 55561.3214
COVER MAINTENANCE
| Repair erosion - infill gullies |  | allow |  | #N/A | 0 | 0
| Repair erosion - upgrade diversion ditches |  | allow |  | #N/A | 0 | 0
| Remove problem vegetation |  | allow |  | #N/A | 0 | 0
| Repair animal damage |  | allow |  | #N/A | 0 | 0
| Repair/upgrade access controls |  | allow |  | #N/A | 0 | 0
| Other |  |  |  | #N/A | 0 | 0
SPILLWAY MAINTENANCE
| Repair erosion |  | m³ |  | #N/A | 0 | 0
| Clear spillway |  | each |  | #N/A | 0 | 0
CWTS MAINTENANCE
| Maintain flow, restore vegetation |  | allow |  | #N/A | 0 | 0
POST-CLOSURE WATER TREATMENT
| water treatment - refer to water treatment tab |  |  | 1 | wt tab | 0.0001 | 0.0001
| Subtotal, Annual post-closure costs | [5 empty] | 157787.6502
| Discount rate for calculation of net present value of post-closure cost, % |  |  |  | 3%
| Number of years of post-closure activity |  |  |  | 10 | years
| Present Value of payment stream | [5 empty] | 1345960.6613 | [7 empty] | 1125561.3214 | 220399.3399 | Carry forward TMAC cost
*Regulatory costs - annual reporting, management plans, progress reports etc.

## ICM
1 | Interim Care and Maintenance | [12 empty] | TO DELETE
| INAC COST (March 2018) | [6 empty] | TMAC Cost (November 2017) | [8 empty] | COST DIFFERENCE |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Costs (March 2018) |  | SRK Row Number | Facility Name | Task Description | Quantity | Unit |  | Unit Cost | TMAC Cost (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Costs
INTERIM CARE & MAINTENANCE
| on-site caretaker | supervisor | man months |  | superh | 91.84 | 0
| extra personnel | one skilled labourer | man months |  | lab-sl | 41 | 0
| - electrician | assumes water treatment still required | man months |  | elech | 95 | 0
| - mechanic | assumes water treatment still required | man months |  | mechh | 72.85 | 0
| annual fuel |  | litre |  | fcdh | 1.39 | 0
| misc. supplies |  | allow |  | accmh | 175 | 0
| pick-up truck |  | each |  | #N/A | 0 | 0
| small dozer |  | allow |  | #N/A | 0 | 0
| small excavator |  | allow |  | #N/A | 0 | 0
| snow machine |  | allow |  | #N/A | 0 | 0
| Operation and Maintenance | includes camp operations | allow | 1 | TMAC | 1440000 | 1440000 |  | 1266 | Interim Care and Maintenance - Annual ICM | water management and camp care and maintenance | 1.5 | year | LS | 1439927.5838 | 2159891.3758 |  | Unit cost differences due to rounding | 2159891.3758
| Mobilization of ICM equipment fleet |  | allow | 0.33 | TMAC | 118000 | 38940 |  | 1268 | Interim Care and Maintenance - Annual ICM | mob/demob ICM fleet | 1 | - | LS | 117636 | 117636 |  | Unit cont differences due to rounding | 117636
| communications |  | allow | 1 | ACI | 1500 | 1500 | [10 empty] | Not included in TMAC costs. Carry forward INAC annual cost. | 2250
| SNP/AEMP water sampling & reporting |  | each | 1 | TMAC | 60000 | 60000 |  | 1263 | Closure Compliance | Water Sampling and Testing | 1.3 | each | LS | 60000 | 78000
| Regulatory Reporting |  | each | 1 | TMAC | 20000 | 20000 |  | 1264 | Closure Compliance | Regulatory Costs | 1.3 | each | LS | 20000 | 26000 |  |  | 78000
| geotechnical assessment |  | each | 1 | TMAC | 35000 | 35000 |  | 1262 | Closure Compliance | Annual Geotechical Inspection | 1.3 | each | LS | 35000 | 45500 |  |  | 26000
| interim water treatment |  |  |  | #N/A |  | 0.0001 | [11 empty] | 45500
| other |  | each |  | #N/A | 0 | 0
[6 empty] | Annual Interim C&M Cost | 1595440.0001
| Number of years of ICM |  | years | 3 |  | Total | 4786320.0003 | [7 empty] | Total | 2427027.3758 | 2359292.6245 | Cost difference associated with the different durations of closure, assumed by INAC and TMAC | 2429277.3758

## Mobilization
1 | Mobilization/Demobilization:
| INAC COST (March 2018) | [6 empty] | TMAC Cost (November 2017) | [7 empty] | COST DIFFERENCE |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Cost (March 2018) |  | SRK Row Number | Facility Name | Task Description | Qty | Unit | Subtotal | TMAC Cost (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Cost
MOBILIZE HEAVY EQUIPMENT
| Excavators |  | km |  | mherh | 10.25 | 0
| Dump trucks |  | km |  | mherl | 3.4 | 0
| Dozers |  | km |  | mherh | 10.25 | 0
| Demolition shears |  | km |  | mherh | 10.25 | 0
| Crane |  | km |  | mherh | 10.25 | 0
| Loader |  | km |  | mherh | 10.25 | 0
| Compactor |  | km |  | #N/A | 0 | 0
| Light duty vehicles |  | km |  | mherl | 3.4 | 0
MOBILIZE MISC. EQUIPMENT
| Pump shipping |  | each |  | #N/A | 0 | 0
| Pipe shipping |  | m |  | #N/A | 0 | 0
| Minor tools and equipment |  | allow |  | #N/A | 100000 | 0
| Truck tires |  | allow |  | #N/A | 0 | 0
| Other | Mobilization of equipment and material | allow | 1 | TMAC | 1071125 | 1071125 |  | 14 | Mobilization - all work areas | Mobilization - all work areas Mob/Demob | 1 | each | 1071123.1655 | 1071123.1655 | 1.8345 |  | 1071123.1655
MOBILIZE CAMP
| Maintain Camp Accomodations | Food | man days | 9720 | TMAC | 110 | 1069200 |  | 21 | Groceries | Groceries | 9720.032 | person-day | 110 | 1069203.52 | -3.52 |  | 1069203.52
| Camp Mobilization/Demobilization |  | LS | 1 | TMAC | 170450 | 170450 |  | 19 | Camp Mobilization/Demobilization | Camp Mobilization/Demobilization | 1 | LS | 170437.5 | 170437.5 | 12.5 |  | 170437.5
| Camp Rental |  | year | 1.3 | TMAC | 668250 | 868725 |  | 22 | Camp Rental | Camp Rental | 1.3 | yr | 405000 | 526500 | 342225 | Task names switched between estimates. No overall diffrence. | 526500
| Camp Operations |  | year | 1.3 | TMAC | 405000 | 526500 |  | 18 | Camp Management & Operations | Camp Management & Operations | 1.3 | yr | 668250 | 868725 | -342225 | Task names switched between estimates. No overall diffrence. | 868725
| Reclamation activities |  | allow |  | #N/A | 0 | 0
| Long term reclamation activities (eg pump flooding) |  | allow |  | #N/A | 0 | 0
MOBILIZE WORKERS
| Reclamation activities - transport | air charter only | flights | 34 | TMAC | 10620 | 361080 |  | 20 | Crew charters (by-weekly) | Crew charters (by-weekly) | 34 | each | 10617.5704 | 360997.395 | 82.605 |  | 360997.395
| Reclamation activities - travel time | twenty workers three hours per shift | man hours | 4080 | ACI | 80 | 326400 | [8 empty] | 326400 | This cost is included in the buildup of worker unit rates included in the TMAC estimate. | 0
| Long term reclamation activities (eg pump flooding) - transport |  | each |  | AE | 3500 | 0
| Long term reclamation activities (eg pump flooding) - travel time |  | man hours |  | AE | 80 | 0
| Monitoring Airfare |  | each |  | mwl | 4500 | 0
WORKER ACCOMODATIONS
| Reclamation activities |  | man months |  | #N/A | 2225 | 0
| Long term reclamation activities (eg pump flooding) |  | man months |  | #N/A | 0 | 0
MOBILIZE FUEL
| Fuel freight - reclamation activities | assumes sufficient fuel is on site to complete the work | litre |  | fcdh | 1.39 | 0
| Fuel freight - long term reclamation activities | assumes sufficient fuel is on site to complete the work | litre |  | #N/A | 0 | 0
| Fuel freight accomodations |  | litre |  | #N/A | 0 | 0
WINTER ROAD
| Construction and operation |  | km |  | #N/A | 0 | 0
| Limited winter use |  | km |  | #N/A | 0 | 0
| Winter road tarriff |  | km |  | #N/A | 0 | 0
DEMOBILIZE HEAVY EQUIPMENT
| Excavators | assume two excavators | km |  | mherh | 10.25 | 0
| Dump trucks | assume four dump trucks | km |  | mherl | 3.4 | 0
| Dozers | assume two dozers | km |  | mherh | 10.25 | 0
| Demolition shears | assume one set of shears | km |  | mherh | 10.25 | 0
| Crane | assume one crane | km |  | mherh | 10.25 | 0
| Loader | assume one loader | km |  | mherh | 10.25 | 0
| Compactor |  | each |  | #N/A | 0 | 0
| Light duty vehicles | assume three trucks | km |  | mherl | 3.4 | 0
| Other | Demobilization of equipment and material | allow | 1 | TMAC | 1071125 | 1071125 |  | 15 | Demobilization - all work areas | Demobilization - all work areas Mob/Demob | 1 | each | 1071123.1655 | 1071123.1655 | 1.8345 |  | 1071123.1655
DEMOBILIZE CAMP
|  |  | allow |  | #N/A | 0 | 0
DEMOBILIZE WORKERS
| crew travel time | cost in mobilization of workers. | man days |  | #N/A | 0 | 0
| crew transportation |  | each |  | #N/A | 0 | 0
WINTER ROAD
| Construction and operation |  | km |  | wrcl | 2000 | 0
| Limited winter use |  | km |  | #N/A | 0 | 0
| Winter road tarriff |  | tonnekm |  | wrul | 0.29 | 0
[6 empty] | Total | 5464605.0001 | [6 empty] | Total | 5138109.746 | 326495.254 |  | 5138109.746

## Open Pit
1 | Open Pit Name: |  |  |  |  | Pit # | 1
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | Subtotal | % Land | Land Cost | Water Cost
CONTROL ACCESS
| Fence |  | m |  | #N/A | 0 | 0 |  | 0 | 0
| Signs |  | each |  | SH | 37.08 | 0 |  | 0 | 0
| Berm at crest |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Block roads |  | m³ |  | RB1H | 17.05 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
STABILITY STUDY
| Conduct stability and setback study |  | allow |  | EA | 20000 | 0 |  | 0 | 0
STABILIZE SLOPES
| Off-load crest, soil A |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Off-load crest, soil B |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Doze/trim overburden at crest |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Drill & blast pit crest |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Buttress slope |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
COVER/CONTOUR SLOPES
| Place fill, soil A |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Place fill, soil B |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Vegetate slopes |  | ha |  | #N/A | 0 | 0 |  | 0 | 0
| Vegetate pit floor |  | ha |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
CONSTRUCT DIVERSION DITCHES
| Excavate ditches -soil | covered under Surface Water Mgmt | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Excavate ditches -rock |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap in channel base |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
CONSTRUCT SPILLWAY
| Excavate channel |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Concrete |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Rip rap |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
RECLAIM QUARRIES
| Contour slopes |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Place overburden |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Vegetate |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
FLOOD PIT-Captital
| Remove stationary equipment (sump pumps) |  | Allow |  |  | 10000 | 0 |  | 0 | 0
| Remove dewatering pipeline |  | m |  | #N/A | 0 | 0 |  | 0 | 0
| Remove power lines |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Construct diversion ditches |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| - Ditch, mat'l A |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| - Ditch, mat'l B |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Construct embankment/dam |  | m³ |  | #N/A | 0 | 0 |  | 0 | 0
| Supply/install pump station |  | Allow |  |  | 500000 | 0 |  | 0 | 0
| Supply/install piping system |  | m |  | #N/A | 0 | 0 |  | 0 | 0
| Remove pump post-closure |  | each |  | #N/A | 0 | 0 |  | 0 | 0
| Remove pipeline post-closure |  | m |  | #N/A | 0 | 0 |  | 0 | 0
FLOOD PIT-Annual Cost
| Operate pumps (power) |  | each |  |  | 439359.8 | 0 |  | 0 | 0
| Maintain pump/pipeline |  | allow |  | #N/A | 0 | 0 |  | 0 | 0
| Labour:fuel management, comissioning/decom |  | $/h |  | #N/A | 0 | 0 |  | 0 | 0
| Chemical addition, _____ kg/m³ of water |  | tonne |  | #N/A | 0 | 0 |  | 0 | 0
| Chemicals, purchase and shipping |  | tonne |  | #N/A | 0 | 0 |  | 0 | 0
| Passive/biological additives |  | $/ha |  | #N/A | 0 | 0 |  | 0 | 0
| Passive additives purchase and shipping |  | tonne |  | #N/A | 0 | 0 |  | 0 | 0
| Other |  |  |  | #N/A | 0 | 0 |  | 0 | 0
[6 empty] | Annual pumping costs | 0.0001
| Number of years of pump flooding |  | years | 0
[6 empty] | Total pumping costs | 0 |  | 0 | 0
[6 empty] | Total | 0.0001 |  | 0 | 0
[6 empty] | % of Total |  |  | 0% | 0%

## Water Management
1 | Capital Expenditures and Short Term Water Treatment identified in 'Instructions' worksheet
TO DELETE
| INAC COST (March 2018) | [6 empty] | TMAC Cost (November 2017) | [9 empty] | COST DIFFERENCE |  | Proposed Cost (April 2018)
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | INAC Costs (March 2018) |  | SRK Row Number | Facility Name | Task Description | Qty | Unit |  | Unit Cost | Subtotal | TMAC Costs (November 2017) | Cost Difference (INAC-TMAC) | Notes | Proposed Costs
BREACH DYKE EMBANKMENT
| breach contact ponds | TMA contact water BM-032 | m³ | 2124 | TMAC | 3.26 | 6924.24 |  | 787 | Boston TMA Contact Water Pond Berms | breach contact water containment berm | 1944 | m³ | C.5.05 | 1.2273 | 2385.9684 | 2385.9684 | 4538.2716 | Reason for diffrence in estiamtes unknown. Carry forward TMAC cost. | 2385.9684
| breach contact ponds | Berm 1 and 2 and Overburden pile | m³ | 1944 | TMAC | 1.23 | 2391.12 |  | 771 | Boston Contact Water Pond #2 | breach contact water containment berm | 648 | m³ | C.5.05 | 1.2273 | 795.3228 | 2385.9684 | 5.1516 |  | 2385.9684
[9 empty] | 776 | Boston Contact Water Pond #1 | breach contact water containment berm | 648 | m³ | C.5.05 | 1.2273 | 795.3228
[9 empty] | 781 | Boston Overburden Pile Sedimentation Pond | breach contact water containment berm | 648 | m³ | C.5.05 | 1.2273 | 795.3228
| Remove Liner | all ponds (BM-021, BM-025, BM-027 and BM-032 | m² | 494 | TMAC | 0.47 | 232.18 |  | 772 | Boston Contact Water Pond #2 | remove and cut liner from breach into manageable pieces | 90 | m² | C.3.02 | 0.17038 | 15.3342 | 84.0406 | 148.1394 |  | 84.0406
[9 empty] | 777 | Boston Contact Water Pond #1 | remove and cut liner from breach into manageable pieces | 66.6268 | m² | C.3.02 | 0.17038 | 11.3519
[9 empty] | 782 | Boston Overburden Pile Sedimentation Pond | remove and cut liner from breach into manageable pieces | 66.6268 | m² | C.3.02 | 0.17038 | 11.3519
[9 empty] | 784 | Boston TMA Contact Water Pond Berms | remove and cut liner from breach into manageable pieces | 270 | m² | C.3.02 | 0.17038 | 46.0026
| de-icing containment | BM-030 excavate containment sump | m³ | 17 | TMAC | 16.35 | 277.95 |  | 919 | Boston Airstrip De-icing Facility | backfill sump excavation | 16.9646 | m³ | C.5.02 | 16.3529 | 277.42 | 277.42 | 0.52996 |  | 277.42
| Contour water intake area |  | m³ |  | #N/A | 0 | 0
STABILIZE SEDIMENT PONDS/WATER MANAGEMENT PONDS
| Place soil cover |  | m³ |  | #N/A | 0 | 0
| Doze & spread excavated material |  | m³ |  | #N/A | 0 | 0
| Vegetate spread material |  | ha |  | #N/A | 0 | 0
| Rip rap in channel base |  | each |  | #N/A | 0 | 0
| Remove sediment from WRSF Pond |  | allow |  | AE | 10000 | 0
REDIRECT RUNOFF/CONSTRUCT DIVERSION DITCHES
| Excavate ditches -soil |  | m³ |  | sc3l | 8.9 | 0
| Excavate ditches -rock |  | m³ |  | #N/A | 0 | 0
| Stabilize side slopes |  | m³ |  | #N/A | 0 | 0
| Rip rap in channel base |  | m³ |  | rr2l | 14.2 | 0
BREACH DITCHES
| Excavate breaches |  | m³ |  | #N/A | 0 | 0
| Backfill/recontour |  | m³ |  | SB3l | 5.1 | 0
| Install flow dissipation |  | m³ |  | #N/A | 0 | 0
| Vegetate remainder of ditch |  | m² |  | #N/A | 0 | 0
DECOMISSION FRESH WATER SUPPLY and OTHER EQUIPMENT
| Breach embankment |  | m |  | #N/A | 0 | 0
| Remove pumps | De-icing sump and contact water area pumps | LS | 19 | TMAC | 679.52 | 12910.88 |  | 768 | Boston Contact Water Pond #2 | disconnect piping and electrical wiring, remove sump pumps | 4 | each | C.1.05 | 679.516 | 2718.064 | 15410.8039 | -2499.9239 | INAC cost does not include the Boston airstrio de-icing facility pumps. It appears they should be included here. Carry forward TMAC cost. | 15410.8039
[9 empty] | 773 | Boston Contact Water Pond #1 | disconnect piping and electrical wiring, remove sump pumps | 4 | each | C.1.05 | 679.516 | 2718.064
[9 empty] | 778 | Boston Overburden Pile Sedimentation Pond | disconnect piping and electrical wiring, remove sump pumps | 4 | each | C.1.05 | 679.516 | 2718.064
[9 empty] | 783 | Boston TMA Contact Water Pond Berms | disconnect piping and electrical wiring, remove sump pumps | 6 | each | C.1.05 | 679.516 | 4077.096
[9 empty] | 917 | Boston Airstrip De-icing Facility | decommission sump | 1 | each | C.1.05 | 679.516 | 679.516
[9 empty] | 918 | Boston Airstrip De-icing Facility | remove pumps, pipes, cables, and culverts | 1 | each | X.05 | 2500 | 2500
| Remove pipeline |  | LS |  | AE | 40000 | 0
WATER CONTROL IN RECLAMATION QUARRY
| Install pumping system |  | LS |  | #N/A | 0 | 0
| Remove pumping system |  | LS |  | #N/A | 0 | 0
REMOVE PIPELINES
| Remove pipes | Water discharge line decommission | m | 2000 | TMAC | 11.08 | 22160 |  | 1233 | Boston Water Discharge Line | cut pipelines into manageable pieces and place in containers for hauling to landfill | 2000 | m | C.3.03 | 11.0844 | 22168.895 | 22168.895 | -8.895 |  | 22168.895
|  | Water discharge line load and haul to landfill | m³ | 98 | TMAC | 13.49 | 1322.02 |  | 1235 | Boston Water Discharge Line | load debris into containers for hauling to landfill | 98.1748 | m³ | C.4.01 | 10.2279 | 1004.1234 | 1004.1234 | 317.8966 |  | 1004.1234
| Decomission STP Pipe |  | m | 50 | TMAC | 11.08 | 554 | [10 empty] | 554 |  | 0
| Concrete plug deep pipes |  | m³ |  | #N/A | 0 | 0
| Other |  |  |  | #N/A | 0 | 0
GROUNDWATER COLLECTION SYSTEM
| Excavate/install sumps |  | m³ |  | #N/A | 0 | 0
| Install pumping wells |  | m³ |  | #N/A | 0 | 0
| Install pumps/pipelines/power supply |  | LS |  | #N/A | 0 | 0
CONSTRUCT CONTAMINATED WATER STORAGE POND
| Excavate pond |  | m³ |  | #N/A | 0 | 0
| Doze & spread excavated material |  | m³ |  | #N/A | 0 | 0
| Vegetate spread material |  | ha |  | #N/A | 0 | 0
| Bedding layer |  | m³ |  | #N/A | 0 | 0
| Supply geomembrane |  | m² |  | #N/A | 0 | 0
| Install geomembrane |  | m² |  | #N/A | 0 | 0
| Erosion protection layer |  | m³ |  | #N/A | 0 | 0
CONSTRUCT PASSIVE TREATMENT SYSTEM (e.g. Constructed Wetland)
| Construct access roads |  | km |  | #N/A | 0 | 0
| Install HDPE piping system from collection pond |  | m |  | #N/A | 0 | 0
| Inter-cell flow structures |  | allow |  | #N/A | 0 | 0
| Install liners |  | m² |  | #N/A | 0 | 0
| Install growth media |  | m³ |  | #N/A | 0 | 0
| Wetland vegetation |  | ha |  | #N/A | 0 | 0
CONSTRUCT WATER TREATMENT PLANT
| Build treatment plant |  | LS |  | #N/A | 0 | 0
| Build sludge containment facility |  | LS |  | #N/A | 0 | 0
[6 empty] | Total | 46772.3901 | [8 empty] | 43717.2197 | 43717.2197 | 3055.1703 |  | 43717.2197
For cost of long-term/post-closure water treatment see "WATER TREATMENT" Worksheet"
0
Note on G10: Megan Miller: They are using a different unit rate
Note on J39: Megan Miller: This appears to be in the incorrect spot

## Water Treatment
1 | Post Closure Water Treatment - Identified as long term/post-closure in 'Instructions' worksheet
| ACTIVITY/MATERIAL | Notes | Units | Quantity | Cost Code | Unit Cost | TMAC Costs
ADDITION OF REAGENTS TO WTP
| H2O2 |  | kg |  | #N/A | 0 | 0
| lime |  | kg |  | #N/A | 0 | 0
| ferric sulphate |  | kg |  | #N/A | 0 | 0
| ferrous sulphate |  | kg |  | #N/A | 0 | 0
| flocculents |  | kg |  | #N/A | 0 | 0
| Other |  |  |  | #N/A | 0 | 0
LABOUR AND SUPPLIES
| Annual fuel |  | litres |  | #N/A | 0 | 0
| Annual power |  | kW-h |  | #N/A | 0 | 0
| Electrician/mechanic to maintain treatment plant |  | allow |  | #N/A | 0 | 0
| Equipment maintenance and parts |  | allow |  | #N/A | 0 | 0
| Misc. supplies, hoses, tools |  | allow |  | #N/A | 0 | 0
| Communications |  | allow |  | #N/A | 0 | 0
| Other |  |  |  | #N/A | 0 | 0
WATER MANAGEMENT
| Water Treatment (reagents, equip Op. labour) |  | m³ |  | AE | 0.62 | 0
| Water pumping from sumps and ponds to treatment plant |  | allow |  | AE | 29367.83 | 0
| Annual Treatment Plant Servicing |  | manhours |  | lab-ss | 120 | 0
| Treatment Plant Servicing Travel Allowance |  | visit |  | AE | 4000 | 0
| Other |  |  |  | #N/A | 0 | 0
WTP WATER SAMPLING AND ANALYSES
| Sampling equipment |  | allow |  | #N/A | 0 | 0
| Analyses |  | allow |  | #N/A | 0 | 0
| Shipping to laboratory |  | allow |  | #N/A | 0 | 0
| Reporting |  | allow |  | #N/A | 0 | 0
| Other |  |  |  | #N/A | 0 | 0
SITE ACCESS
| Road maintenance (incl. snow removal) |  | allow |  | AE | 50000 | 0
| Winter road tariff |  | allow |  | #N/A | 0 | 0
| Truck rental |  | allow |  | #N/A | 0 | 0
| Air support |  | allow |  | #N/A | 0 | 0
[6 empty] | Annual water treatment costs | 0.0001
| Number of years of water treatment |  | years | 25
[6 empty] | Total | 0.0025

## Unit_Costs
Unit Cost Table (for refining unit costs see "Estimator" worksheet)
Filter by unit
ITEM | Detail | COST CODE | UNITS | LOW $ | HIGH $ | SPECIFIED $ | COMMENTS
Accomodation
|  | ACCM | manday | 100 | 175
Buildings - Decontaminate
| Asbestos | BDA | m² | 25.6 | 51.2 |  | Low: removal of asbestos siding & flooring; High: removal of insulated pipes, friable asbestos
Buildings - Remove | [6 empty] | Unit costs are based on 3 m high, single storey building. Scale areas accordingly.
| Wood | BRW | m² | 27.5 | 41
| Concrete | BRC | m² | 40 | 65 | 6 | Specified: puncture concrete foundation slabs
| Steel - teardown | BRS1 | m² | 45 | 65
| Steel - for salvage | BRS2 | m² | 67 | 100
Concrete work
| Small pour | CSF | m³ | 426.5 | 639.75 |  | Low: YK; High=1.5xLow
| Large pour | CLF | m³ | 353.5 | 530.25 | 2130 | Specified: concrete crown pillar
Contaminated Soils
| ESA Phase 1 | CS1 | each | 7500 |  |  | Low: small, "clean" site
| ESA Phase 1 | CS2 | each | 50000 |  |  | Low: small, "clean" site
| Remediate on site | CSR | m³ | 47 | 146
Dozing
| doze rock piles | DR | m³ | 1.05 | 2.4 |  | Low cost: doze crest off dump
| doze overburden/soil piles | DS | m³ | 0.95 | 3.8 |  | High cost: push up to 300 m
Excavate Rock; Low Spec's and QA/QC
| drill/blast/load/short haul | RB1 | m³ | 11.4 | 17.05 |  | Low:quarry operations for bulk fill
| drill/blast/load/long haul | RB2 | m³ | 12.05 | 17.8
| RB1 + spread and compact | RB3 | m³ | 12.05 | 17.8
| RB2 + spread and compact | RB4 | m³ | 12.5 | 30.75
| Specified activity | RBS | m³
Excavate Rock; High Spec's and QA/QC | [6 empty] | (e.g. ditch/spillway excavation)
| drill/blast/load/short haul | RC1 | m³ | 12.05 | 17.8 |  | Low:foundation excavation;High:spillway excavation
| drill/blast/load/long haul | RC2 | m³ | 12.7 | 18.4
| RC1 + spread and compact | RC3 | m³ | 12.7 | 18.4 |  | e,g, cover construction
| RC2 + spread and compact | RC4 | m³ | 13.5 | 19.2 |  | e,g, cover construction
| Specified activity | RCS | m³ |  |  | 175 | Specified-drift excavation
Excavate Rip Rap
| drill/blast/load/short haul/place | RR1 | m³ | 13.5 | 17.75 |  | High: quarry & place rip rap in channel
| drill/blast/load/long haul/place | RR2 | m³ | 14.2 | 20.65
| source is waste dump/short haul | RR3 | m³ | 7 |  |  | cost includes sorting
| source is waste dump/long haul | RR4 | m³ | 7.6
| Specified activity | RRS | m³
Excavate Soil; Low Spec's and QA/QC
| clear & grub | SBC | m² | 3.4 | 5
| excavate/load/short haul | SB1 | m³ | 4.3 | 5.9
| excavate/load/long haul | SB2 | m³ | 4.6 | 7.3
| SB1 + spread and compact | SB3 | m³ | 5.1 | 8.9 |  | Low: non-engineered; High:engineered
| SB2 + spread and compact | SB4 | m³ | 5.5 | 11 |  | Low: non-engineered; High:engineered
| Specified activity | SBS | m³ | 3.2 | 6.3 |  | Low: rehandle waste rock dump by dozing; High:rehandle waste rock by hauling
| Tailings | SBT | m³ | 1.35 | 3.7 | 15.5 | High:contour surface - wet or frozen; Specified:haul/place wet infill
Excavate Soil, High Spec's and QA/QC
| excavate/load/short haul | SC1 | m³ | 6.8 | 9.3
| excavate/load/long haul | SC2 | m³ | 7.1 | 11.75
| SC1 + spread and compact | SC3 | m³ | 8.9 | 14.2 |  | Low: non-engineered; High:engineered
| SC2 + spread and compact | SC4 | m³ | 9.3 | 23.2 |  | Low: non-engineered; High:engineered (e.g. complex covers, low volume dam construction)
| Specified activity | SCS | m³ |  |  | 18.8 | Backfill adit with waste rock
Fence
|  | FNC | m | 13.55 | 203
Fuel and Electricity
| Fuel cost - gas | FCG | litre | 1.05 | 1.4
| Fuel cost - diesel | FCD | litre | 0.99 | 1.39
| Fuel mobilization | FCM | litre | 0.22 | 0.42 |  | High: winter road usage
| Electricity | FCE | kW-h | 0.17 | 0.19 | 0.49 | Low and High:Yellowknife; Specified:diesel generator
Geo-Synthetics
| geotextile | GST | m² | 3.44 |  |  | Supply and install
| geogrid | GSG | m² | 5.75
| liner, HDPE | GSHDPE | m² | 7.95 |  |  | Supply and install; large quantity
| liner, ES3 | GSES3 | m² | 20.2 |  |  | FOB Yellowknife
| geosynthetic installation | GSI | m² | 3.16 | 14 |  | Low:geotextile; High:ES3 or HDPE
| bentonite soil ammendment | GSBA | tonne | 308.3 | 348.5 |  | FOB Edmonton, add shipping & mixing
Grouting (/m³ of rock grouted)
|  | grout | m³ | 236.55 | 286.75 |  | High: cement, FOB Yellowknife
Labour & Equipment Rates
| Site manager | sman | $/hr | 125 | 152
| Supervisor | super | $/hr | 52 | 91.84
| Registered engineer | eng | $/hr | 95 | 220
| Environmental coordinator | envco | $/hr | 74.16 | 130
| Evironmental technologist | envtech | $/hr | 36
| Electrician | elec | $/hr | 74 | 95
| Journeyman - various | journey | $/hr | 44 | 71.79
| Labour - skilled | lab-s | $/hr | 41 | 49.6 | 120
| Labour - unskilled | lab-us | $/hr | 31 | 43.98
| Equipment operator | oper | $/hr | 41 | 65
| Heavy duty mechanic | mech | $/hr | 49 | 72.85
| Water treatment plant operator | oper-wt | $/hr | 41 | 59.86
| Security / first aid | safety | $/hr | 36 | 66.97
| Administative staff | admin | $/hr | 38 | 57.89
Equipment rates include operator and fuel
| Loader - 4 cu.yd (3.06m³) | load-s | $/hr | 175
| Loader - 7 cu.yd (5.35m³) | load-l | $/hr | 315
| Excavator - 26.76-30.84 tonnes | exc-s | $/hr | 190
| Excavator - 68.95+tonnes | exc-l | $/hr | 420
| Grader | grad | $/hr | 190
| Dump truck off hwy 30-50 tonnes | truck-s | $/hr | 225
| Dump truck off hwy 55-75 tonnes | truck-l | $/hr | 300
| dozer, small | dozers | $/hr | 205 | 260
| dozer, large | dozerl | $/hr | 490 | 565
| smooth drum compactor | comp | $/hr | 155
| scooptram, 6 yd3 bucket | scoop | $/hr | 170
| flat bed truck with hiab | hiab | $/hr | 155
| fuel truck | ftruck | $/hr | 150
| water truck | wtruck | $/hr | 58 | 150
Mobilize Heavy Equipment
| Road access | MHER | kmtonne | 3.4 | 10.25
| Air access | MHEA | kmtonne | 12 |  |  | cargo rate>500 lb
Mobilize Camp
| Road access | MCR | each | 50000 |  |  | refurbish existing camp
Mobilize Workers
| flight | MW | each | 4500 | 9100 |  | Low:e.g. 8 passenger; High: Dash 7
Oil Removal
| oil removal | OR | litre | 0.43 | 1.2 |  | Low:waste oil heater; High: ship offsite
PCB Removal
| Remove from site | PCBR | litre | 40.2 | 46.9 |  | Low: shipping, handling & disposal from Yellowknife
Pipes, small (<6in dia.)
| remove/dispose on site | PSR | m | 1 | 24 |  | Low: remove/dispose on site; High: remove/re-use
| supply | PSS | m | 6.1 | 11.1 |  | Low:supply; High:supply and ship
| install | PSI | m | 25
Pipes, large (>6in dia.)
| remove/dispose on site | PLR | m | 22 | 72 |  | Low: remove/dispose on site; High: remove/re-use
| supply | PLS | m | 129 | 143 |  | Low:supply; High:supply and ship
| install | PLI | m | 50
Power Lines
| remove/dispose on site | POWR | m | 25.5
Process Chemicals
| Remove from site | PCR | kg | 0.45 | 2.5 |  | Low: shipping, handling & disposal from Yellowknife
Pumps
| Pump capital cost | PC | each | 195000
| Pump shipping | PS | each | 2500
| Pump operating cost | POC | m³ | 0.12 |  |  | pump operating costs should be calculated based on pump capacity, fuel costs, etc.
| Pump maintenance | PM | allow | 25000
Pump sand BackFill
|  | PBF | m³ | 85 | 300
Scarify - road/mine site
|  | SCFY | ha | 4300 | 6030 | 2150
Shaft, Raise & Portal Closures
| Shaft & Raises | SR | m² | 645 | 2132 |  | Low:pre-cast concrete slabs, little site prep. Area=shaft+>1 m all around
| Portals | POR | m³ | 18.8 | 250 | 1200 | Low:unit cost code SCS;High:excavate & backfill collapsed portal;Spec: installed pressure plug
Site Inspection Report
|  | RPT | each | 10000 | 20000
SpillWay - Clear
|  | SW | each | 3000 | 7000
Survey/Instrumentation
|  | SI | each | 1800 | 3600 |  | 2 person crew
Treatment Plant - Construct
| Small (< 1000 m³/d) | TPS | lump sum | 9000000 | 15000000
| Large (> 1000 m³/d) | TPL | lump sum | 15000000 | 46000000
| Constructed Wetland | CWTS | ha | 200000 | 300000
Treatment Plant - Operate
|  | TPO | m³ | 0.35 | 2
Treatment Chemicals
| ferric sulphate | ferric | kg | 1.19
| ferrous sulphate | ferrous | kg | 1.32
| lime | lime | kg | 0.56
| hydrogen peroxide, 35% | hperox | kg | 1.5
| Sodium Metabisulfate | Nametab | kg | 1.18
| Caustic soda, 50% | caustic | kg | 0.74
| Sulfuric acid, 93% | sulfuric | kg | 0.31
| flocculant | flocc | kg | 6
| copper sulphate | copper | kg
| shipping | shipping | kg | 0.2
Vegetation
| Hydroseed, Flat | VHF | ha | 4000
| Hydroseed, Sloped | VHS | ha | 4500
| Veg. blanket/erosion mat | VB | ha | 13000
| Tree planting | VT | ha | 2600 | 6000
| Wetland species | VW | ha |  |  | 47.72 | Specified= /m³, Wetland Growth Media Substrate mixed and installed (sand, biochar and fertilizer, woodchips)
Water Sampling/Analysis/Reporting
|  | WS | each | 7000 | 10000
Winter Road
| Construction | WRC | km | 2000 | 11500
| Usage | WRU | kmtonne | 0.29