## 1-Project Certifcate Requirem
No. | Terms and Condition | Phase of mine development1 | Shear Response | NIRB Comments
Monitoring
1 | Based upon the authority of Article 12.7.1, NIRB will appoint a full time Monitoring Agent for the Tahera project, whose mandate is to monitor the Project as it proceeds and to analyze the success of these Terms and Conditions as the project becomes operational, and beyond, to Abandonment and Restoration. Information gathered by NIRB’s Monitoring Agent is public information that will be shared with the proponent and regulatory authorities. | Construction Operation Closure (COC) | No response required from Shear. | The NIRB has a full time Monitoring Officer assigned for this file: Sophia Granchinho, Technical Advisor, sgranchinho@nirb.ca (867) 793-4633.
2 | The responsibility of the NIRB Monitoring Agent is to give direction to the Proponent on its obligation to compile an annual report for the duration of the mine on major environmental impacts, especially wildlife, fish, and aquatic ecosystems. The Monitoring Agent’s further assignments, and subject to direction from NIRB, include proposing, coordinating and suggesting studies, assessing the study results, undertaking action to follow-up, deciding on site visits, changes to the monitoring program, and recommending to NIRB any changes to the Terms and Conditions as appropriate under section 12.8.2 of the NLCA. | COC | No response required from Shear. | The NIRB will continue to ensure that the responsibilities of the Monitoring Officer are met for this file.
3 | Tahera should work with regulatory authorities to monitor caribou in and around the project area. This caribou monitoring should not duplicate the work underway by other groups and authorities, for example for the Slave Geological Province, but instead will focus on the caribou migrating to the northern portion of the Slave Geological Province. | COC | In 2011 Shear will design a caribou monitoring program with input from, and in collaboration with the Government of Nunavut, the Hunter’s and Trappers Organizations from the communities within the Kitikmeot Region, regional wildlife boards and the Government of the Northwest Territories that will compliment and contribute to the existing monitoring programs and efforts already being conducted in the territories. Shear proposes the development of a caribou monitoring program that will inform the existing larger body of data and not duplicate efforts by government, industry and other organizations. During the care and maintenance period at the Jericho Mine site the monitoring of caribou will be limited to the collection of incidental sightings. Prior to the project entering production, Shear will implement the caribou monitoring program that is developed as described above. | The NIRB requests clarification on the anticipated timing for the submission of a draft caribou monitoring plan for review.
4 | Tahera shall initiate a long term monitoring program regarding the health of fisheries in the Carat Lake systems as far down as the Jericho River, not only to protect this fishery, but also to enhance it. | COC | Tahera conducted baseline studies that described pre-development conditions and developed an aquatic effects monitoring program to monitor the health of the fisheries. Shear submitted a revised AEMP on February 28, 2011 in support of the water licence renewal application. This plan describes the monitoring program Shear proposes to implement at the Jericho Diamond Mine to monitor for potential effects and the overall health of the fisheries. Shear is currently working with DFO to assign the Fisheries Authorization. In July, DFO will travel to site and accompany environment personnel, a fisheries biologist and a geotechnical engineer (contracted by Shear) to verify the construction status of the fish habitat compensation measures and review any alternatives being proposed. The information gathered during the July site visit will be used to develop a revised Fish Habitat Compensation Plan. | The NIRB requests clarification on when the AEMP will begin to be implemented.
5 | The installation of an atmospheric monitoring station to be funded and installed by Tahera, to obtain site-specific meteorological data. This station shall meet the requirements of Environment Canada air quality experts and focus if possible on dust from roads and blasting, and windblown dust from stockpiles. | COC | Shear has purchased, and will be installing, a complete year round atmospheric monitoring station that meets the requirements of Environment Canada. Additionally, Shear has prepared a draft air quality monitoring program (reviewed by Environment Canada) for the period of care and maintenance. The air quality monitoring program will inform Shear as to current conditions and effects as well will provide background information required for the design of an operations level air quality monitoring plan. Plans and policies will also be implemented to monitor the effects of care and maintenance activities on area air quality. | The NIRB requests clarification on when the station will be installed and when Shear will begin to collect data and report on the findings.
6 | Tahera shall implement a site-specific ecosystem based water monitoring program, which it will fund. Tahera will also meet the requirements of regulators including the Nunavut Water Board and take advice from KIA as to site selection of this ecosystem based water quality monitoring program. | COC | Shear submitted an Aquatic Effects Monitoring Plan (AEMP) as part of the care and maintenance plan on January 31, 2011. It is proposed that the AEMP for care and maintenance be implemented for the site until resource evaluation is complete and a decision has been made as to whether Jericho will re-enter operations. Once the decision to re-enter operations has been made, the AEM program will go from care and maintenance to operations. The changes to the AEM program for operations will build on the AEM program for care and maintenance to include the; addition of fisheries monitoring component, and an increased monitoring and sampling frequency. A fisheries monitoring component and an updated frequency schedule to reflect operations will be submitted to the Nunavut Water Board as an addendum by April 30, 2012. The fisheries monitoring and increased frequency will not be implemented until a decision is made to resume operations | The NIRB requests clarification on when the AEMP will begin to be implemented.
7 | Tahera shall re-evaluate data and options for the currently planned diversion, dams, and other hydrologic changes and reconsider mitigation options. This analysis could be made a condition of any federal approvals required by regulatory authorities. | Construction Possibly operation and closure | Tahera constructed a number of water diversion and retention structures to support mining operations. During care and maintenance Shear will conduct annual geotechnical inspections, as well as implement the monitoring programs described in the General Monitoring Plan, Site Water Management Plan and the Aquatic Effects Monitoring Plan. Moving forward the requirement for the retention ponds will be evaluated based on current hydrologic data (being collected in 2011) and the mine plan. | In correspondence March 28, 2011 the NIRB requested a copy of a mine plan from Shear with clarification on how the proposed current exploration activities would be related to the Jericho Mine and any future mining plans. The NIRB is again requesting this mine plan.
Noise
8 | For noise abatement, Tahera shall employ industry best practices to protect people and wildlife from mine activity noise, including vehicles and aircraft. The final noise abatement plan shall be filed with NIRB’s Monitoring Agent. Industry requirements for low-level flying should be maintained. | COC | The noise abatement plan submitted by Tahera addressed measures to be taken for the protection of human health. It did not specifically address measures to protect wildlife from mine activity noise. The measures indicated in the Tahera plan addressed the placement of mine site infrastructure and purchasing of quiet plant and mobile equipment so at to best minimize noise. It is unknown if noise abatement was a criteria for the site selection of infrastructure or a purchasing criteria for equipment. Government of Nunavut, Department of the Environment reviewed the noise abatement plan and specifically requested that the plan address wildlife and cross-reference the relevant sections of the Wildlife Mitigation and Monitoring Plan. Shear will ensure that a noise abatement plan is developed that addresses both the protection of people and wildlife from human induced noise pollution. Shear will incorporate the related areas of the Wildlife Mitigation and Monitoring Plan into the noise abatement plan for operations at the Jericho mine site. The Jericho mine site will be utilized as a base for exploration activities during the period of care and maintenance. Shear will follow criteria and thresholds within the Nunavut General Safety Regulations (Section 30 and 31, Schedule A) and the Nunavut Mine Health and Safety Regulations (Section 9.19-9.26 Schedule 5) for human safety. To minimize the noise disturbance to wildlife Shear will implement an anti-idling policy for noise reduction at site and will require aircraft flying over the Project area to maintain a height of 610 m during point to point travel if safe to do so and 1000 m vertical (1.5 km horizontal) from any observed significant concentrations of wildlife if safe to do and once wildlife has been so identified. If necessary Shear will develop flight corridors to avoid known areas of resident species at risk (i.e. to avoid the Willingham hills- Peregrine nesting). | Noise from blasting, low-level flights, air and truck traffic, drilling, other industrial activities. Are there noise meters installed anywhere around site? The revised noise abatement plan will have to be submitted to the NIRB's Monitoring Officer for review.
Wildlife
9 | Environmental effects of blasting on wildlife shall be kept to a minimum. Blasting cannot occur if it affects in any way migrating caribou and birds or local carnivores. | COC | Shear will develop policies for blasting. Blasting will be prohibited when wildlife are within 500 meters of the blasting area. A survey of the area, by trained personnel, will be conducted prior to blasting to ensure that no wildlife is present. During care and maintenance it is not expected that there will be any blasting activities and there are currently no blasting constituents on site. | The NIRB requests clarification on the anticipated timing for the submission of the blasting policies for review.
10 | Tahera shall develop a plan with the GN to enhance wildlife data and to provide more details on caribou found in the Project area. This work shall begin in 2004 with Tahera taking a lead role. | COC | Shear believes that this term has been addressed in the response provided previously for item #3. If this response is not sufficient, Shear respectfully requests clarification from the NIRB on what this requirement is specifically attempting to address. | This term and condition refers to the development of a wildlife mitigation and monitoring plan in cooperation with the Government of Nunavut. What is the expectations for monitoring wildlife during care and maintenance phase versus operations?
11 | In approving this Project, NIRB encourages all regulatory authorities (i.e. federal, territorial and KIA) to study the cumulative effects of any associated projects (e.g. Bathurst Inlet Port and Road) on regional caribou movements. | Construction Operation | Shear will work with regulatory authorities to address the concerns and potential for cumulative effects. Currently the Lupin Gold Mine remains on care and maintenance. The status of the Izok and Ulu projects is unknown at this time. It is Shear’s understanding that the Bathurst Inlet Port and Road project has been shelved for the time being. Shear welcomes the opportunity to work with proponents of other projects that are being developed from time to time in the region and to contribute to monitoring efforts in a collaborative way with companies and with regulatory authorities. | Cumulative effects concerns not huge at this time.
12 | Tahera shall plan, construct, and operate their mine in such a way that caribou migration paths through the project area are protected. Maps of corridors shall be placed in site offices and upgraded as new information on corridors becomes available. This information shall be sent to NIRB’s Monitoring Agent, GN and KIA. | Construction Operation Closure | It is unknown if caribou migration paths were considered as criteria during the planning and construction of the mine site infrastructure. Shear will place maps of known caribou corridors in site offices. Additionally, the location of any large herds located through the implementation of the caribou alert system will be identified on a map that will be posted within the main corridor at the site. As new information becomes available regarding caribou movements through the Jericho property these maps will be updated to reflect changes. The new information gathered on caribou movements will be sent to NIRB’s Monitoring Agent the GN and the KIA. | Information on Shear's caribou alert system should be submitted. Will it be similar to the alert system described under item 15?
13 | Tahera shall submit plans to regulatory authorities to include measures that will ensure caribou are not harmed, entrapped, or frightened by any project activity. Tahera shall do everything it can to ensure that caribou do not fall into pits, or slip on roads; this includes the requirement that Tahera use whatever means it finds necessary including ramps and crossings to assist in the free movement of caribou and construction of berms or fences where appropriate to prevent accidents involving wildlife. | Construction Operation Closure | Shear is currently developing a draft Wildlife Monitoring and Mitigation Plan. The plan will be developed in 2011 in consultation with the GN, Kitikmeot Inuit Association and the HTO’s to ensure that there is coordination of effort rather than duplication. In the meantime, Shear will implement the measures proposed in the Wildlife Monitoring and Mitigation Plan compiled for Tahera by Golder and Associates, which include mitigation measures to ensure the protection of caribou and other wildlife. During care and maintenance Shear will record wildlife sightings in the field and around the mine site. These sightings will be included in the quarterly reports to be submitted to the NIRB. | The NIRB requests clarification on the anticipated timing for the submission of the draft Wildlife Monitoring and Mitigation Plan for review.
14 | Tahera shall take special care to avoid disturbing nesting sites of any species in the Project lease area. Sites within 500 meters of the Project lease area should be also located, marked, and reported by Tahera to NIRB’s Monitoring Agent. | COC | Shear will avoid disturbing nesting sites of birds in the Project area. General mitigation measures for limiting mine-related disturbance to breeding birds were detailed in Tahera Diamond Corporation, Wildlife Monitoring and Mitigation Plan (May 2007) and in Bearwise (2005) and are presented below. Shear will implement these mitigating measures during the care and maintenance period at the mine site. The mitigating measures will be evaluated and updated if necessary prior to resumption of mining activities. • direct disturbance to the tundra from Project activities will be avoided during the migratory bird breeding season (late May through to September) through the clearing of such areas in the fall or winter; • where meaningful vegetation removal is required during the breeding season a detailed nest survey will be conducted; • active nests found will be avoided, marked and monitored to determine nest success; • if bird collisions (i.e., on windows, transmission lines or other structures) are occurring, then on-site measures will be taken to reduce the likelihood of collisions such as, reducing the mirror effect, wire marking and using silhouettes; • prevent upland birds from nesting on mine infrastructure or areas slated for clearing by using deterrents such as noise guns and eyespot balls (McLennan et. al. 1995); and • any upland bird nest identified within 500 m of the Project footprint will be reported to GNDOE and EC. | The NIRB requests that any bird nest sites identified within 500 m of the Project footprint be report to the NIRB's Monitoring Officer as well.
15 | For the greater protection of wildlife, wildlife must have the right of way, and this principle must be strictly enforced. This means all activity including construction, drilling, blasting, and traffic movements, be stopped in the presence of susceptible raptors, ungulates, and carnivores. | COC | Shear has a strict policy that harassment of wildlife is prohibited. All activities that are undertaken at site will be done in a manner that ensures wildlife are not disturbed or harassed. When wildlife are sited in and around the mine site, their movements will be monitored and the information relayed back to the main site. During care and maintenance, activities at site will be reduced. Shear will rely on visual observations as a first alert that wildlife are present. When wildlife are observed, the alert system will be initiated. The following information will be provided to all personnel; species, number, distance from the mine site and direction of movement. Wildlife policies are introduced and explained within the environment orientation section of the site orientation for all persons on site. These include a clear description of the site-wide speed limit (30km), procedures for proceeding when animals are within the area of roadways and the company requirement that animals must be afforded the right of way in all circumstances. | Will the alert system be modified when the decision has been made to go to operations.
16 | The highest protection shall be given to nesting and flightless birds or vulnerable wildlife including protection of all dens. Further, Tahera must submit a more detailed plan to NIRB’s Monitoring Agent to list specific steps that Tahera will take to study and prevent losses of nests and eggs within the lease boundaries and a buffer zone 500 metres surrounding the lease boundaries. | COC | Shear will include protection measures for nesting and flightless birds and vulnerable wildlife, including dens, in the Wildlife Monitoring and Mitigation Plan being developed in 2011 as described previously in #13. This will include steps that Shear will take to prevent losses of nests and eggs within the site and buffer zone of 500 metres surrounding the lease boundary. This plan, once drafted, will be submitted to the NIRB. | No anticipated timing for submission of the Wildlife Monitoring and Mitigation plan has been supplied.
17 | For safety and other reasons, there shall be no hunting of wildlife in the Project area and 500 metres outside the project lease boundaries. | COC | Personnel are not permitted to hunt wildlife while at the mine site. Additionally Shear Diamonds has a strict no-harassment of wildlife policy. New employees and contractors are informed of the no hunting, no fishing and no harassment policies during the site orientation and prior to commencing any workplace duties. | Acceptable
18 | Problem wildlife shall be reported immediately to the GN and to the NIRB Monitoring Agent. | COC | Shear will report any wildlife incident or problem wildlife to the GN and the NIRB Monitoring agent. A wildlife incident shall be considered any incident involving wildlife that requires management action (i.e. use of deterrents) | Acceptable
Fish and Aquatics
19 | Tahera shall collect pre-construction data for water and sediments, aquatic biota (zooplankton, phytoplankton, and benthic invertebrates) to be submitted to regulatory authorities. The period for ongoing data collection shall be the subject of consultation with regulatory authorities. | Pre-construction; COC | Tahera collected baseline fisheries data prior to development and construction of the mine. A Fish Habitat Compensation/No Net Loss Plan was prepared and submitted as required for the Fisheries Authorization (NU-00-0068). The Aquatic Effects Monitoring Program (AEMP) and on site monitoring programs were conducted last in 2007. The mine site closed and was placed on Care and Maintenance in May 2008. The only sampling and monitoring that was conducted during the Care and Maintenance phase was water sampling for the purpose of discharging from the Processed Kimberlite Containment Area (PKCA). Shear submitted a Care and Maintenance Plan on January 31, 2011. The AEMP was updated and included with the Care and Maintenance Plan. In reviewing the AEMP that Tahera designed and implemented, Shear noted that additional sites were required to adequately monitor for downstream effects and that one of the “Control” sites that had been used was within the zone of influence. Shear has proposed a methodology for selecting a new "control” site. The existing site will continue to be sampled as part of the AEMP. No sites were removed from the program that had been previously approved and implemented by Tahera. Shear will not collect any fish samples in the year of 2011. Prior to resuming mine operations, Shear will conduct the fish sampling as described in the AEMP submitted. | NIRB requests additional information on the methodology for the selection of the new 'control' site and information on when this site will be sampled for baseline data.
20 | Tahera shall ensure mitigation and compensatory measures meet the needs of regulatory authorities for fisheries or habitat losses, included but not limited to, the area of water intakes and outlet areas, Long Lake, and Streams C1 and C3. These programs should be adjusted based on long-term monitoring of fish in the Carat Lake systems, and further site specific studies be undertaken and submitted to the regulatory authorities prior to the final alignment for water crossings or diversions, with the proper development of mitigation measures more specifically detailed. | Pre-construction; COC | Shear is aware, via correspondence from the Department of Fisheries and Oceans (DFO) that the Fisheries Authorization, NU-00-0068, which expired on August 15, 2008, is in non-compliance. At this time, neither Shear nor DFO are fully aware of the extent of the construction activities described in the Fisheries Authorization. Shear has contracted a geotechnical engineer and a fisheries biologist to visit the Jericho Diamond Mine in 2011 to inspect the C1 Diversion channel to establish the status of the construction requirements and to determine the use and function of the channel by fish. Investigations will also include the 01 and 02 lakes, the connecting stream between the aforementioned lakes, and the shoals as described in the Fisheries Authorization. Shear has begun discussions with DFO and has extended DFO an invitation to visit the mine site while the geotechnical engineer and fisheries biologist conduct their investigations. Shear will continue discussions with DFO and once the site visits confirm the extent to which the Fisheries Authorization is non-compliant, Shear will submit a revised Fish Habitat Compensation Plan to DFO. | NIRB requests that the NIRB Monitoring Officer be kept informed on the status regarding the assignment of the Fisheries Act Authorization and copes of the revised Fish Habitat Compensation Plan be forwarded to the NIRB's Monitoring Officer for review.
21 | That Tahera meet the requirements of DFO as it relates to no net loss, further evaluation, and management of the Carat Lake and surrounding fishery. These requirements should be in place before the water license is issued. The Carat Lake causeway must be constructed to minimize disturbance and maximize development of fish habitat including benthic substrate. | Pre-construction; Construction |  | Will this be covered under the new assignment of the Fisheries Act Authorization?
22 | That Tahera conduct a literature review, in consultation with DFO and NIRB’s Monitoring Agent, of the effects of ice road travel, noise and vibration and to fish populations. The results of this review are to be reported to NIRB’s Monitoring Agent. If there are potential problems identified in the review, NIRB’s Monitoring Agent will notify Tahera and the Board of options including a biological study. | Pre-Construction COC |  | What are Shear's plans for using winter road access to the site during the care and maintenance phase and/or exploration phase?
23 | Tahera’s blasting program must meet the needs of regulatory authorities regarding the protection of fisheries. | COC |  | This information should be included in the Fish Habitat Compensation Plan and as part of the blasting policies.
24 | Tahera shall take the greatest caution to prevent any impact on fish and mammal populations, fish eggs, spawning beds, silt loading, offspring, and any wintering areas including carnivore dens and bird nest sites. | COC |  | Plans to prevent impacts to fish, fish habitat and wildlife should be discussed in the Fish Habitat Compensation Plan and the Wildlife Mitigation and Monitoring Plan
Environmental Management
25 | Tahera shall do a cost benefit analysis associated with the various options of water management at the Jericho site, including recycling. This information shall be provided to regulatory authorities. | Pre-construction | Tahera conducted a cost benefit analysis of the various options of water management at the Jericho site. Shear will recycle water to the greatest extent possible. Opportunities to recycle water include, using pit water in the process plant and for exploration purposes (i.e.: drilling), using water from the PKCA in the process plant and using water collected and treated from within the secondary containment berms in the process plant. These alternative water sources are especially attractive during the care and maintenance phase while Shear runs test batches to determine the operational status of the plant. Tahera successfully implemented water recycling in 2007. Pipeline infrastructure remains in place and functional to recycle water from the PKCA Cell B, to the process plant. | Will the cost benefit analysis conducted previously by Tahera be re-evaluated if Shear decides to move to operations?
26 | Site-specific plans for blasting activities must meet federal government standards and blasting crews must be fully trained including being provided a copy of Tahera’s final Project Certificate. | CO | At the present time there are no blasting constituents on site and no plans to bring blasting constituents to site while the project remains on care and maintenance. Once a decision has been made with regard to the need for blasting constituents, Shear will adhere to all federal government standards. Only individuals with the appropriate level of training and certification will be permitted and tasked to handle blasting constituents. | Related to blasting and operations.
27 | All blasting constituents (dynamite, ammonium nitrate, or other components except fuel), and any accelerants, shall be stored in covered and isolated buildings, well marked as being dangerous. Blasting materials buildings shall be protected according to industry standards. Ammonium nitrate that is spilled must be cleaned up immediately. | Construction Operation | There are currently no blasting constituents stored on site. Shear is aware that there were concerns raised over the ammonia nitrate storage practices employed by Tahera. Shear will review the Explosives Management Plan submitted by Tahera, and will update this plan and resubmit it for review and approval prior to bringing blasting constituents to the site. The plan will include; storage, training, standards and spill prevention and response. | Related to blasting and operations.
28 | A blast management plan for Tahera’s operations shall be submitted to the NIRB Monitoring Agent, regarding timing, location, and approximate amounts of blasting agents used on an annual basis or if plans change. | Pre-construction Operation |  | Related to blasting and operations.
29 | Tahera must provide greater detail to regulatory authorities on effluent options, including better information on ammonia and phosphorous levels. | Pre-construction | Shear is unaware of the historical context in which this term was required but allowable levels of ammonia and phosphorous are set out in the Type A Water Licence issued to the Jericho project by the Nunavut Water Board and Shear anticipates that levels will be set out in the renewal of this licence . | Acceptable
30 | Tahera must provide greater detail to regulatory authorities on total dissolved solids (“TDS”) constituents and nutrient concentrations expected to be released to downstream waters. | Pre-construction | Since the provision of this term, Tahera operated the mine for two years and collected water samples at the point of discharge from the PKCA. An Aquatic Effects Monitoring Program was implemented in 2006 and 2007. The monitoring was scaled down during care and maintenance (INAC) with water sampling limited to point of discharge from the PKCA. The water quality data and analyses during operations and care and maintenance indicate that water quality discharge criteria were met. Shear conducted the under ice water sampling component of the AEMP currently under review as part of the Care and Maintenance Plan submitted January 31, 2011. The samples were collected in between April 10 through to the 17th, at locations detailed in the AEMP. Shear will submit the results of this program to regulatory agencies once the samples have been analysed. | NIRB requests an anticipated deadline for the submission of the results from the April sampling program.
31 | Further detailed study by Tahera to ensure that water quality exiting the PKCA meets receiving water standards, including further study on the option of a divider/barrier or dyke in the PKCA to improve water quality. This information is to be provided to NIRB’s Monitoring Agent, DFO, NWB and EC. | Pre-construction | The water quality data on record indicates that Tahera did not have any concerns with regard to meeting discharge criteria. While the project remains on care and maintenance, Shear does not have any reason to believe that water quality exiting the PKCA will not meet the criteria. One of the main ways to ensure that water quality in the PKCA meets discharge criteria is to control the sources that are discharged into the PKCA. Shear is currently investigating a number of options for treating water at the source, i.e. pit water and water that collects in secondary containment structures housing fuel containers. Shear has contracted and been working closely with EBA Engineering on the development of the management plans for operation of the Jericho Mine Site. Shear submitted an updated Processed Kimberlite Containment Area (PKCA) Management Plan on January 31, 2011 as part of the Care and Maintenance Plan. Divider Dyke A was partially completed when the project went on to care and maintenance in 2008. During the geotechnical inspection in late September 2010, Divider Dyke A was inspected and found to be performing well. Divider Dyke A will need to be constructed to the final elevation of 524 m shortly after resuming processing activities. Divider Dyke B has not yet been constructed. It will be required once Cell A nears capacity, once processing activities are resumed. Further information regarding the dykes and dams can be found in the PKCA Management Plan submitted earlier this year, as well as in the 2010 Geotechnical Inspection. | Shear's PKCA Management Plan should be forwarded to the NIRB's Monitoring Officer for review along with any updates regarding anticipated construction timelines for Divider Dyke A and Divider Dyke B, and associated dams.
32 | Any ice or snow road construction, stream or river crossing, in Nunavut be conducted to minimize sedimentation and environmental disruptions, and that DFO, KIA, and the NWB be consulted well in advance of such construction. At a minimum, silt fences must be used where appropriate and all fuel truck drivers must carry spill kits. | Pre-construction | Prior to any ice or snow road construction, stream or river crossing, Shear will consult with DFO, the KIA, and the NWB. Shear will ensure that all vehicles traveling on ice and/or snow roads carry spill kits. Mitigation measures, such as silt fences, will be on-site and available should they be required. | Acceptable
33 | That all movement of goods including hazardous materials across the winter or other roads be subject to a comprehensive materials handling, management, and environmental protection plan. This comprehensive plan shall be in place prior to the initial haul supply of the mine, and shall contain environmental terms at least as stringent as those currently incorporated into the Tibbett-Contwoyto Winter Road agreement, and shall be filed with NIRB’s Monitoring Agent and other regulatory authorities as required. | Pre-construction Construction | Prior to the construction and use of any winter roads, Shear will prepare and submit, to the GN, KIA, NIRB Monitoring Agent and the NWB, a comprehensive plan to include materials handling, management and environmental protection. | Acceptable
34 | All fuel storage areas shall be bermed and meet regulatory requirements | COC | On February 28, 2011 Shear submitted a Fuel Storage Containment Facility Design Plan, which describes the proposed plans for the construction of Phase III of the fuel storage containment facility and the eventual decommissioning of Phase I. Since the issuance of the Project Certificate, INAC has drafted, circulated and implemented the “Draft Recommended Best Practices For the Storage and Handling of Petroleum and Allied Petroleum Products on Federal Crown Lands in Nunavut”. Shear will adhere to all laws, regulations and the aforementioned best practices for the storage of all fuels at Jericho. | Acceptable
35 | Waste management must be controlled in such a way that reduces or eliminates the attraction to carnivores or raptors. Fencing and other suitable deterrents shall be employed in all landfills and waste storage areas. A final waste management plan shall be filed with regulatory authorities including the NWB and NIRB’s Monitoring Agent. | COC | Shear submitted a Waste Management Plan as part of the water licence renewal application on February 28, 2011. Since submitting this plan, Shear has conducted an on-site assessment of the incinerators currently in place at Jericho. Shear also contracted Andy McMullen of BEARWISE to conduct a bear safety audit at the Jericho mine site and to provide Bear Awareness training while on site and in the future on an as needed basis. Shear has ordered parts for the incinerator that was on site. The incinerator is functional but in need of repair to ensure that it operates at full efficiency. Shear is currently in the process of selecting a new incinerator that will address the current and future needs with regards to waste management. Shear is also investigating relocating the incinerator to minimize transport of kitchen food wastes, increase supervision of burns, and reduce wildlife attractants. Once Shear has selected an appropriate incinerator and an appropriate location for the new incinerator, the waste management plan will be updated to include, as an addendum for review, the specifications of the incinerator and the design plan of the new location. | The updated waste management plan should be provided to the NIRB's Monitoring Officer for review once available.
36 | Tahera shall immediately contact the NWB to provide greater detail on the PKCA, West Dam, spillway, settling pond, dumps, waste disposal, stockpiles, and quantities of fresh water needed at the mine site, reclamation plans and any other information needed to assist the NWB in its water license application. | Pre-construction (COC) | Shear is currently in the process of renewing the Type A water licence for the Jericho mine. A number of plans were submitted with the renewal application. These plans, along with the application, are presently out for review and comment. Comments have already been provided by DFO and Environment Canada. Shear will be responding to all comments and information requests. The NWB Technical Meeting and Pre-Hearing Conference have been scheduled for June 20 and 21, 2011. Shear has contracted EBA Engineering to assist with data collection during freshet this spring. A geotechnical engineer and an environmental scientist will be on site with Shear’s environment personnel gathering data that will address information gaps related to site water, associated infrastructure, waste rock design and reclamation. As new information becomes available, Shear will update and append information in the plans that have been submitted to support the water licence renewal application. Shear will provide a written update to the NWB prior to the Technical Meeting. | Acceptable
37 | Tahera shall work with regulatory authorities to combine where appropriate the Hazardous Materials Management Plan, Spill Prevention and Counter-measures Plan and Emergency Response Plan. | Pre-construction (COC) | In accordance with the Type A water licence, Part J, Item 6, Shear submitted a Contingency Management Plan that addresses the Care and Maintenance Phase. From an operations perspective, a document combining the Hazardous Materials Management Plan, the Spill Prevention and Counter-measures Plan and the Emergency Response Plan is cumbersome and impractical. These documents contain important information and measures to be employed in the event of a spill, emergency and while handling hazardous materials. During care and maintenance, Shear will implement the Contingency Management Plan currently being reviewed in support of the water licence renewal application. Hazardous materials management is discussed within the Waste Management Plan submitted on February 28, 2011. Prior to resuming operations, an Emergency Response Plan will need to be developed and submitted that is suitable for an operating mine. | Acceptable. Plans should be forwarded to the NIRB for review.
38 | That Spray Irrigation, it if is incorporated as a project component in the future, is referred back to NIRB with further design detail to be dealt with under NLCA Article 12.4.3 | No stage at this time. | Shear is currently reviewing the option of spray irrigation as a potential measure to mitigate the dispersion, by air, of the fine processed kimberlite from the PKCA to the surrounding area. A mitigation plan is being developed and will be submitted on or before June 10, 2011. The plan will discuss the proposed mitigation measures. If spray irrigation is proposed, a full design and detail would be submitted to the NIRB, NWB, INAC, KIA and EC. | Acceptable
39 | That the outflow Diffuser, it if is incorporated as a project component in the future, be referred back to NIRB with further design detail to be dealt with under NLCA Article 12.4.3. | No stage at this time. | At this time, Shear does not have any plans to install an outflow Diffuser. However, if Shear decides to re-consider use of an outflow Diffuser in the future, detailed design plans will be provided to the NIRB for consideration and approval under Article 12.4.3 of the NLCA. Shear has engaged a geotechnical engineer to be on site during freshet and the start of discharge from the PKCA. The need for erosional controls will be determined at this time. Shear has purchased a number of silt fences, triangle dykes and spring berms to have on site as mitigation measures if required. | Acceptable
Abandonment and Reclamation
40 | Tahera shall enter into written arrangements with its contractors to ensure all site debris is cleaned up off the lands including wind-blown debris. | Pre-construction (COC) | Shear facilitated a site visit by a third party, agreed to by both Shear and the KIA, to conduct an assessment of the infrastructure on site to effectively update costing for reclamation security. Unfortunately, snow cover and bad weather inhibited the ability to fully assess the site. It was agreed that a second site visit would be required once the snow is gone, to assess infrastructure on both Crown and Inuit Owned Lands and complete the updated costing for reclamation security. Shear hopes to have this completed prior to the Technical Meeting, scheduled for June 20, 2011. The updated costing, when complete, will be included in the Interim Closure and Reclamation Plan submitted with the water licence renewal application on February 28, 2011. | Information should be provided to the NIRB on any arrangements with contractors to ensure the land is cleaned up appropriately.
41 | For abandonment and restoration, Tahera must comply with INAC’s policy of full cost restoration and any related NWB requirements such that the Inuit and taxpayers are not liable for any cost associated with clean-up, modification, decommissioning, or abandonment. An updated report on progressive reclamation and the amount of security posted, as required by KIA, INAC or the NWB, shall be filed with NIRB’s Monitoring Agent annually. | Pre-construction (COC) |  | This is an important item from the NIRB's perspective. The NIRB request an update on what reclamation may have occurred since the site went into Care and Maintenance, and full costing of required reclamation moving forward, with assurance that required bonding/securities are in place. The NIRB also request that the updated costing be provided as part of the annual report.
Socio-Economics
42 | Detailed safety requirements shall be met according to all workplace and safety regulatory requirements, including CO monitoring patches worn by all under ground workers. | COC | Shear Diamonds will ensure that all employees and contractors abide by all applicable laws, rules and regulations with respect to workplace health and safety. Currently the project remains on care and maintenance. Shear submitted, to the NWB, a Care and Maintenance Plan on January 31, 2011, for approval. The project will remain on care and maintenance while Shear evaluates the resource and carries out investigations to determine the feasibility of resuming operations of the Jericho Mine. Should Shear determine the project feasible, an Operations Work plan will be submitted to the WSCC for approval. This determination will also trigger notifications to the NWB, INAC, the KitIA, the NIRB and the GN. | Acceptable
43 | Labour recruitment should take place as much as possible in the Kitikmeot communities and also elsewhere in Nunavut. Women should be included as much as possible in the work force. On-the-job training should also be a large part of Tahera’s training program. | COC | Tahera and the KIA entered into an Inuit Impact Benefit Agreement in September of 2004 that addressed preferential hiring of Inuit from the Kitikmeot communities and elsewhere in Nunavut. With the consent of the KIA this IIBA agreement was assigned to Shear in August 2010. Currently due to the care and maintenance status of the project the obligations in the IIBA other than those for employment and contracting, are suspended. While the project remains on care and maintenance, there will be limited opportunities for employment, therefore also limited opportunities for on the job training. Shear will implement the agreed upon provisions of this agreement during operations if mining operations resume. If the project progresses to operations, increased opportunities will exist for on the job training as more positions become available. Prior to resumption of production at Jericho, Shear and the KIA will review the IIBA. | Details on workforce during care and maintenance should be supplied.
44 | Prior to the commencement of operations, a Kitikmeot Socio-Economic Monitoring Committee be formed to supplement, not replace the IIBA. This committee includes GN, INAC, KIA and NIRB’s Monitoring Agent and will involve the preparation of an annual report of the impact of the mine on the closest communities, including Inuit who live near the project area. | Pre-construction | Shear will cooperate with the Kitikmeot Socio-Economic Monitoring Committee. | Acceptable
45 | Tahera shall prepare an orientation program for any non-Inuit workers, to train them to be sensitive to the Inuit culture. KIA shall be consulted on the development of this program. | Pre-construction (COC) | Shear will work with the KIA to develop a cross-cultural awareness program. Once this program has been developed and approved it will become mandatory for all employees and contractors working at the Jericho Diamond Mine. The goal of the cross-cultural training will be to ensure sensitivity for all cultures. This will be a requirement during both care and maintenance and operations. | Acceptable. NIRB requests full details of this program be submitted to the Board for information prior to implementation
46 | Tahera should make best efforts to find management positions for this mine from Nunavut. | Pre-construction (COC) | The project will remain on care and maintenance while Shear determines the feasibility of resuming operations. During this time, limited opportunities for employment will mean limited opportunities for management positions. In determining the feasibility of resuming operations, Shear will rely heavily on highly skilled and trained personnel in the areas of engineering, geology, geophysics, and environment. Wherever and whenever possible, Shear will endeavour to hire these positions from within Nunavut and will work with the Kitikmeot Inuit Association, Nunavut Arctic College and the Government of Nunavut to identify qualified Nunavummiut from the Kitikmeot Region of Nunavut who would qualify for management positions at the Jericho Diamond Mine. | Acceptable
47 | Tahera’s training shall include safety and emergency programs for all personnel. | Pre-construction (COC) | Shear has developed an orientation program for all employees and contractors. The orientation includes three components: • Shear’s policies, general information, site orientation, • Occupational Heath and Safety, and • Environment. All employees and contractors are required to participate in the orientation, and to sign off confirming they have completed the program. Each individual is provided with an Orientation Manual and the required Personal Protective Equipment specific to their tasks. The Orientation Manual outlines the roles and responsibilities of the employee/contractor and the company in upholding the rules and regulations that pertain to operating at the Jericho Diamond Mine. | Acceptable
48 | Tahera shall take steps to ensure that all on-site personnel are drug and alcohol free. | Pre-construction | The Jericho Diamond Mine is drug and alcohol free. This is a term and condition of employment and will be discussed with all employees and contractors during the mandatory orientation. | Discussion of prevention measures for operations may be required
49 | That Tahera work with governmental social and health agencies to determine whether current governmental programs are adequate and can respond to Tahera’s future mine in the West Kitikmeot. Attention should be given to the impacts of Tahera’s Jericho mine in Nunavut and any government studies in this field should be posted in local government offices. | All stages. | Shear will continue to work with local governments and communities to ensure that governmental programs are adequate to respond to the Project’s needs. | Acceptable
Other
50 | Tahera must work proactively with the KIA to meet any requirements of Article 20 of the NLCA. | All stages. | Shear has been working closely with the KIA since the acquisition of the project. Shear has honoured and assigned the water compensation agreement with the KIA. Water compensation payments are current and in good standing. | Acceptable
51 | That any archaeological find that is discovered be immediately and concurrently reported to government agencies, KIA, and NIRB’s Monitoring Agent. This includes grave sites, which if discovered shall be fully protected. | Pre-construction (COC) | All archaeological finds discovered will be reported immediately and concurrently to government agencies, the KIA, and the NIRB. All employees and contractors are instructed to report and avoid any archaeological find. This information is covered during the site orientation that all employees and contractors must undertake when they arrive at site. | Acceptable
52 | Tahera shall meet with respective licensing authorities as soon as possible before construction begins to discuss the posting of adequate performance bonding. Licensing authorities are encouraged to take every measure to require that sufficient security is posted before construction begins. This bonding should not duplicate other amounts of security required (e.g. NWB), but this condition is intended to ensure that firstly, full and complete performance bonding for all aspects of the construction, operation, abandonment/reclamation of Tahera’s mine is a priority for any license or approval that is issued to allow this Project to proceed, and secondly, to fully protect the Inuit and other tax-payers if Tahera for whatever reason fails to perform or fulfill their commitments as promised. | Pre-construction Operation | No response provided by Shear. | This is an important item from the NIRB's perspective.
53 | Any additional mitigation measure proposed by Tahera that is not in conflict with, or covered by these terms and conditions, shall be fully implemented in accordance with regulatory licensing. |  | No response provided by Shear. | It is recognized that Shear has proposed a number of mitigation measures specific to individual management plans which may be above and beyond what is strictly required.
54 | Regulatory authorities shall be entitled to impose additional or stricter licensing requirements if they are necessary or required. |  | No response provided by Shear. | The NIRB will keep itself apprised of the various licensing requirements imposed by other agencies.
Note 1: Phase of mine development from Project Certificate, Appendix C-Status Sheet.

## 2-Outstanding Reports
NIRB Files Contain: | Location | Source
Air Quality Management Plan | NIRB public registry | 040401 submission
Air Quality Management Plan for Care and Maintenance | NIRB public registry | 110612 submission
Ammonium Nitrate Management Plan | NIRB public registry | 050120 submission
Aquatic Effects Management Plan | NIRB public registry | 050322 submission
Borrow Management Plan | NIRB public registry | 050329 submission
C1 Diversion Construction Summary Report | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Care and Maintenance Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Closure and Reclamation Plan + updated plan (080429) | NIRB public registry | 060209 submission
Closure and Reclamation Updated Plan | NIRB public registry | copied from NWB submission
Contingency Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Diversion Construction Update | NIRB public registry | 061006 submission
Drug and Alcohol Policy | NIRB public registry | 050204 submission
Emergency Preparedness and Response Plan for Dam Emergencies | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Explosives Management Plan | NIRB public registry | 060915 submission
Fuel Farm Design | NIRB public registry | 050210 submission
Fuel Storage Containment Facility Design Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Habitat Compensation Monitoring Program | NIRB public registry | 071128 submission
Habitat Monitoring Plan | NIRB public registry | 060503 submission
Interim Closure and Reclamation Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Landfarm Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Landfill Design, Waste and Hazardous Materials Management Plan | NIRB public registry | 070202 submission
Landfill Management Plan | NIRB public registry | 040528 submission
Landfill Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Mine Plan + Revised Plan | NIRB public registry | copied from NWB submission; requested by NIRB on March 28, 2011
Mitigation Monitoring Program for Freshwater Intake | NIRB public registry | 061213 submission
No Net Loss Plan + updated plan (060503) | NIRB public registry | 040401 submission
Noise Abatement Plan | NIRB public registry | 050204 submission
OMS Manual - Jericho Diamond Project | NIRB public registry | copied from NWB ftp site (2011 renewal application)
PKCA Management Plan | NIRB public registry | 060503 submission
2011 Pit Dewatering Plan Addendum to Processed Kimberlite Management Plan | NIRB public registry | revised document received 110611
Preliminary Landfarm Design Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Preliminary Landfill Design Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
QAQC Plan | NIRB public registry | 051005 submission
Spill and Emergency Response Plan + Updated 050322, 060308, 080410 | NIRB public registry | 050118 submission
Waste Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Waste Rock Management Plan | NIRB public registry | 050601 submission
Waste Rock Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Wastewater Treatment Management Plan | NIRB public registry | copied from NWB ftp site (2011 renewal application)
Wildlife Mitigation and Monitoring Plan | NIRB public registry | 070515 submission
Winter Road Emergency Response and Spill Plan | NIRB public registry | 050101 submission
Shear Reports not received by NIRB that were listed as submissions to the NWB: | Posted on NWB ftp | Source
Site Water Management Plan | 2010 NWB Amendment | referenced in 110609 letter to NWB
General Monitoring Plan | 2010 NWB Amendment | referenced in 110609 letter to NWB
Wildlife Effects Management Plan - referenced in Waste Management Plan | none posted | referenced as 2011 Renewal WMP
Shear Reports not received by NIRB that were listed as submission to the NIRB: | Location | Source
September 2010 Monthly Water Use Report, submitted to NWB in accordance with Part K, Item 12 of Water Licence NWB1JER0410 | none | referenced in 110603 letter to NIRB
October 2010 Monthly Water Use Report, submitted to NWB in accordance with Part K, Item 12 of Water Licence NWB1JER0410 | none | referenced in 110603 letter to NIRB
March 2011 Monthly Water Use Report, submitted to NWB in accordance with Part K, Item 12 of Water Licence NWB1JER0410 | none | referenced in 110603 letter to NIRB
April 2011 Monthly Water Use Report, submitted to NWB in accordance with Part K, Item 12 of Water Licence NWB1JER0410 | none | referenced in 110603 letter to NIRB
2010 Geotechnical Inspection Report (EBA), submitted to the NWB | none | referenced in 110603 letter to NIRB
2010 Annual Report as per Appendix D | none | referenced in 110603 letter to NIRB
Quarterly reports (December 2010 and March 2011) as per Appendix D | none | referenced in 110603 letter to NIRB
Note: Items highlighted in red were obtained from other sources or not received by the NIRB

## 3-Other Outstanding Items
Items outstanding from previous NIRB correspondences
Date of request | Item | NIRB Comments
2008-11-25 | Summary of recommendations based on the NIRB's 2007 Annual Monitoring Report for the Jericho Mine: | Many of the items requested for this report previously occurred while the mine was in full operation.
| 1) Prepare future annual reports such that they meet the requirements as outlined in the revised Appendix D of the Project Certificate (issued November 20, 2007). | NIRB request that Shear provide future annual reports such that they meet the requirements of Appendix D
| 2) Include additional items requested by the NIRB in future annual reports. The additional items requested can be found in correspondences from the NIRB to Tahera dated March 15, 2007 and August 7, 2007. | NIRB request that Shear provide additional items requested in future annual reports as outlined in correspondences. In addition, additional items were also requested in correspondence dated December 1, 2008.
| 3) Include incineration management procedures in future reports and provide a discussion on how the Proponent will meet the Canada-wide standards for incinerator emissions. | No response required. See T&C #35.
| 4) Provide a written response to the NIRB’s correspondence dated August 18, 2008 in which the NIRB requested that the Proponent respond to the comments and recommendations on the 2007 Wildlife Summary Report as well as on the status of the mine. | NIRB request information be provided on the 2007 Wildlife Summary Report
| 5) Respond to the NIRB’s correspondence dated August 12, 2008 in which the NIRB requested an update on the status of the Jericho Mine site during the Care and Maintenance period and how the Proponent will meet the requirements of the NIRB’s Project Certificate. | No response required
| 6) Commence monitoring of air quality at the Jericho Mine site based on Tahera’s Air Quality Model report (2007) and Air Quality Management Plan (2004). It is also recommended that the Proponent work with Environment Canada to commence the air quality monitoring program. | No response required. Shear has indicated that atmospheric monitoring station will be installed and that Shear has prepared a draft air quality monitoring plan for the period of care and maintenance. The NIRB request a copy of the plan for review
| 7) Continue monitoring Carat Lake and Lynne Lake for ammonia (as N), and provide mitigative measures if the values exceed the Canadian Council of Ministers of the Environment (CCME) guidelines. | NIRB request that Shear provide the water quality data that were collected for both Carat Lake and Lynne Lake since 2007 for review.
2008-11-25 | Summary of recommendations based on the NIRB's 2008 Site Visit Report: | Many of the items requested for this report previously occurred while the mine was in full operation.
| 1) Tahera to provide information on whether all fuel trucks at the Jericho site have spill kits as outlined in Condition #32 of the Jericho Project Certificate. | No response required.
| 2) Tahera to meet the requirements of Condition #34, in that the fuel storage areas be bermed and meet regulatory requirements. | No response required.
| 3) Tahera to prepare a plan of action on how they will meet Condition #34, especially in regards to the secondary containment unit at the airport that is damaged. In addition, Tahera should ensure that the liners within the bermed areas have not been breached and are in good conditions to prevent contaminated water in the bermed areas from entering the environment. | No response required. Secondary containment unit removed by 2009.
| 4) Contaminated soil was evident in the fuel containment areas (bermed areas) at the airport. A plan of action must be prepared by Tahera on how and when the contaminated soil will be removed. | NIRB request additional information on whether the contaminated soil has been removed.
| 5) Wildlife incidents have resulted from improper or insufficient waste management procedures. Evidence must be provided by Tahera that waste management procedures have been adequately improved to prevent future wildlife incidents. | NIRB request additional information on waste management procedures that have been implemented to prevent wildlife incidences
| 6) Tahera to provide ammonia and phosphorus levels as required by Condition #29. | NIRB request information be provided on any available data for ammonia and phosphorus.
| 7) Tahera to provide the results of total dissolved solids (TDS) and nutrient concentrations released to downstream waters in 2007 as per Condition #30. | NIRB request information be provided
| 8) Tahera to provide further information on whether the reinforcement of the permeable barrier in the PKCA (Processed Kimberlite Containment Area) between East Cell and West Cell is working and that no further seepage have been seen beneath the barrier and no sedimentation have been seen in the West Cell. | No response required.
| 9) Tahera is reminded that it should report wildlife problems/incidents immediately to both the Government of Nunavut and the NIRB as required by Condition #18. | No response required.
2008-12-01 | Recommendations based on summary of findings of NIRB's review of Tahera's 2007 Annual Monitoring Program Report: | Many of the items requested for the 2007 Annual Report previously occurred while the mine was in full operation.
| 1) Tahera mentioned that a Care and Maintenance Plan will be released to regulatory agencies upon completion. The NIRB request a copy of this plan. | No response required.
| 2) Higher sediment deposition rates were observed at the Carat Lake monitoring stations compared to other stations from 2005 to 2007 with rates being lowest in 2006. The NIRB would like the Proponent to continue to monitor Carat Lake to ensure that the increased sediment deposition does not affect the aquatic benthic communities within Carat Lake. The Proponent also indicated in the annual report that the higher sediment deposition rates observed in 2007 versus 2006 were due to the erosion occurring near the causeway and the “effectiveness of the rip-rap will be re-examined once the mine recommences operations. It is recommended that the rip-rap be closely monitored while the mine is in Care and Maintenance. If any significant erosion occurs, in order to properly mitigate the impact, necessary re-assessment of the functionality of the rip-rap should be done prior to any resuming of the mine operations. | The NIRB requests that monitoring results be provided for Carat Lake.
| 3) The Proponent reported that monitoring will be conducted during Care and Maintenance (sections 4.2.6.5, 4.2.6.6, 4.2.6.7, 4.2.6.8). The NIRB is requesting further information on the monitoring proposed during this phase. It should include when the monitoring would begin, how the proponent plans on monitoring and how often. | Where any monitoring conducted during the Care and Maintenance phase since 2008? If so, please provide information.
| 4) The Proponent reported that the University of Alberta was contacted regarding vegetation research at Jericho for 2008 and that discussions were ongoing as to what may be feasible given that Tahera is in Care and Maintenance. The NIRB requests an update on the status of the vegetation research program. | The NIRB requests an update status on the vegetation research program and whether or not it occurred.
| 5) The NIRB requests that the Proponent provide an explanation with supporting evidence for the following: | Please provide the requested information if available.
a. Decrease in dissolved oxygen concentrations with depth for Lake C3 and Jericho Lake compared to other lakes.
b. Higher phytoplankton diversity indices in 2007 versus 2006. What is the reason for this?
c. Increasing trends observed in several water quality parameters (ammonia, nitrate, arsenic, molybdenum and uranium). What are the reasons for this?
| 6) In addition, the NIRB along with INAC would like to know if the Proponent is considering updating or modifying the current aquatics effects monitoring program (AEMP) in order to identify, mitigate and monitor the causes of the increasing trends observed in the water quality parameters. The current AEMP for the Jericho project was developed to monitor sources of effluent to detect unanticipated effects on aquatic biota so that appropriate mitigative actions can be taken. | No response required. The NIRB request a copy of the revised AEMP
| 7) Please verify whether station WQ-16 is within Lynne Lake or Ash Lake. In the 2007 Annual Report, the station was within Lynne Lake, but the 2007 AEM report identifies this location as Ash Lake. | Please provide the requested information if available.
| 8) The NIRB requests an updated schedule on when the remaining fish habitat compensation works will be completed as required by the Fisheries Act authorization (amended on November 28, 2007). | The NIRB requests an update on the remaining fish habitat compensation works once the status of these habitat compensations works have been determined during the July 2011 site visit.
| 9) DFO noted that certain areas of rock shoals LCA03, LCA04 LCA05 and LCA06 have less than two meters water cover (Appendix I – Tahera’s 2007 Fish Habitat Compensation Monitoring Program Report). The Fisheries Act authorization requires that rock shoal be placed in water with a depth of at least two meters below the normal summer water levels. Please provide an explanation on why certain areas of rock shoals have less than the required water cover and if the constructed rock shoals are performing effectively. | Information should be included in the updated Fish Habitat Compensation Plan.
| 10) INAC requested that additional information be provided as part of the annual report. | Please include additional information in future reports.
2009-11-16 | 2009 Site Visit Report Recommendations:
| 1) Berming of the fuel storage areas to meet regulatory requirements, as per Condition #34 of the Project Certificate. | Information should be included in the Fuel Storage Containment Facility Design Plan
| 2) Submission of a plan of action on how Condition #34 will be met, especially in regards to the waste transfer containment area near the airport which was not completely contained during the site visit in July. | NIRB requests additional information whether this waste transfer containment area has been contained or cleaned up.
| 3) Contaminated soil was evident in the fuel containment areas (bermed areas) around site. It is recommended that a plan of action be prepared to address how and when the contaminated soil will be removed. | NIRB request additional information on whether the contaminated soil has been removed.
| 4) Wildlife incidents have resulted from improper or insufficient waste management procedures. Evidence must be provided that waste management procedures have been adequately improved to prevent future wildlife incidents. | NIRB request additional information on waste management procedures that have been implemented to prevent wildlife incidences
| 5) Procedures for reporting wildlife problems/incidents immediately to both the Government of Nunavut and the NIRB as required by Term and Condition #18 | No response required.