## Sheet1
2AM-JER Renewal Application Technical Meeting June 20-21, 2011
List of Commitments (APPENDIX E)
Plan | Commitment made by: | Item # | Description | Proposed due date: | Form:
1 | SHEAR |  | PKCA Mgmt Plan - Priority document for revision prior to the hearing; | Priority Document to be revised prior to the hearing (Aug 15); and further revised following issuance of the licence (if needed) | Full Management Plan
2 |  |  | Pit Dewatering Addendum | Shear has submitted
|  | 10 | Nitrate and TSS Testing methods | 2011-08-15 | TM*
3 | SHEAR |  | Site Water Management Plan
| SHEAR | 12 | Shear will conduct annual geotechnical inspection and the annual seepage survey | 2011-09-15 | Inspection Report
| SHEAR | 13 | Shear will submit an updated site water balance for operations | 2011-08-15 | TM
| INAC | 18 | Clarification on INAC inspections and Geotechnical Inspection for the site in 2009-2010; | 2011-07-15 | Letter/Inspection Report - in addition, information to be provided directly to the NIRB monitoring Officer
| SHEAR | 20 | SWMP to include Appendix A and preliminary design for C4 | 2011-09-15 | TM
| SHEAR | 22 | Results of collector ditches and site grading; Submission of update and annual reporting | Update April 2012; and March 31, 2012 Annual Report | Annual Report, Design Report (if required)
| SHEAR | 25 | Mobile Water Treatment System for HC contaminated soil; Final Design and Specification; WTS to be onsite by July 15, 2011 (testing to occur in advance of any discharge) | 2011-08-15 | Addendum to SWMP.
4 | SHEAR |  | General Monitoring Plan | No proposed changes in advance of the Hearing
5 | SHEAR |  | Preliminary Landfill Management and Design Plan | No proposed changes in advance of the Hearing
| SHEAR | 35 e | Locating of the landfill | 2011-07-31 | TM
6 | SHEAR |  | Preliminary Landfarm Management and Design Plan | No proposed changes in advance of the Hearing
7 |  |  | Waste Rock Management Plan
| SHEAR | 52 | Shear is going to conduct a data review of existing waste rock geochemistry. If necessary Shear will collect additional rock samples to determine leaching characteristics . | 2012-12-31 | TM
8 |  |  | Wastewater Management Plan | No proposed changes in advance of the Hearing
9 |  |  | Waste Management Plan
| SHEAR | 60 | Development of an incineration management plan consistent with the standards outlined in the Technical Document for Batch waste incineration (EC) | 2011-11-01 | Management plan
10 |  |  | Aquatic Effects Monitoring Plan
| SHEAR | 62 - 73 | Summary of proposed changes to the AEMP | 2011-07-15 | TM
| SHEAR | 62 - 73 | Next revision to take into consideration issues and commitments identified by all parties | Following issuance of renewed WL where applicable | Full Management Plan as directed
11 |  |  | Interim Closure and Reclamation Plan
| SHEAR | 81 | Pit in-fill rates reassessment | 2012-04-15 | TM
| SHEAR | N/A | Security Cost re-assessment for the site | 2011-08-15 | TM
12 | SHEAR |  | Contingency Management Plan | immediate update for current onsite operations; administrative revision | Annual Report
13 | SHEAR |  | Emergency Preparedness and Emergency Response Plan for Dam Emergencies | immediate update for current onsite operations; administrative revision | Annual Report
14 | SHEAR |  | Operation, maintenance and Surveillance Manual - PKCA Dams
| EC | 88 a-b | Clarification needed from EC on toxicity testing recommendation/requests | 2011-07-15 | Response letter
General commitments
15 | INAC |  |  | 2011-07-15 | Response letter with revised table
16 | SHEAR |  | Need for detailed ongoing (2 year) implementation schedule for activities and submissions. | 2011-08-15 | Table
| SHEAR |  | Provide a Schedule of monitoring activities | 2011-06-30 | TM
| SHEAR |  | Operational commitment list | 2011-07-15 | TM
| SHEAR |  | Update to the Operational list | With submission to the PH and at the PH | TM
17 | KIA |  | Confirmation of Water Compenstation Status | With submission to the PH and at the PH | intervention statement
| ALL Parties |  | Recommendations on initial proposed discharge criteria for the Project | 2011-07-15 | Response letter
| SHEAR |  | Provide proposed amendments to existing terms and conditions and any proposed discharge criteria for the Project | 2011-08-15 | Response letter
*Note: TM will provide a reference to the changes in the original document.

## Sheet2
POTENTIAL TIMELINES MOVING FORWARD: (Subject to feedback from participatns to PHC and Board determination)
2011-06-20 |  | Technical Meeting PHC
2011-06-24 |  | Board Direction MTG
2011-07-01 |  | Board PHC/TM Decision
Deadline of Information Commitment from the Parties (clarification)
2011-07-14 |  | Proposed Notice of Public Hearing 55(2)
2011-08-03 |  | Deadline Notice of Public Hearing 55(2)
2011-08-15 |  | Deadline for New Information
2011-09-23 |  | Deadline Intervention Submissions (English)
Deadline Intervention Submissions (Inuktituk, Innuinaktun)
2011-10-02 | 2011-10-08 | Public Hearing
2011-10-24 | 2011-11-04 | Board Decision
2011-12-02 | 2012-02-29 | Minister Review Period
2012-03-01 |  | DEADLINE LICENCE EXPIRES