## Submissions
Pending submissions
LEGEND for proposed revised delivery | Proposed Delivery Deadline | Consideration
| As soon as possible | URGENT
| 90 days prior to implementation | Likely significant changes for existing, or new plan
| 60 days prior to implementation | Previous plan with significant or reasonable review previously
| 90 days post construction | No review
Report/Plan | Comment | From recent Shear Plan
PKCA
PKCA MP | 60 days before production currently
Divider Dyke B Design | 60 days before construction currently | 6-9 months pre-production
Divider Dyke B construction report | 90 days post construction currently | 3-6 months pre-production
Perimeter Berm Design | 60 days before construction currently | 6-9 months pre-production
Perimeter Berm construction report | 90 days post construction currently | 3-6 months pre-production
North Dam Design | 60 days before construction currently | 6-9 months pre-production
North Dam Construction report | 90 days post construction currently | 3-6 months pre-production
Settling Pond Dam (potential) | 60 days before construction currently-contingency
Waste Management
Landfill Design Report | 60 days before construction currently | 9-12 mths prior to production
Landfill Construction Report | 90 days post construction currently | 9-12 mths prior to production
Landfarm Design | 60 days before construction currently | 9-12 mths prior to production
Landfarm Construction Report | 90 days post construction currently | 9-12 mths prior to production
Landfarm Mgmt Plan | prior to commissioning currently
WRMP | 60 days before production currently | <3 months pre-production
RECLAIM estimate | To be revised by Shear prior to Hearing
SWMP | Needs revision to go from C&M to comissioning
incl engr design of berms on collection ponds
conceptual in SWMP
Detailed design within 60 days of construction
AEMP | 60 days before production | <3 months pre-production
Needs revision to go from C&M to comissioning
Needs further revision pre-mining
Contingency Management Plan | Very Large Plan | <3 months pre-production
4th version currently
significant review to date
Mine Plan | Potentially significantly modified
Updated Abandonment and Restoration Plan |  | <3 months pre-production
GMP | Needs revision to go from C&M to comissioning
2012-04-29
WMP | 2012-04-29
Explosives Management Plan | 2012-04-29
QA/QC Plan | 2012-04-29