## GN-DOE
No. | Aspect | Technical Comment # | Review Page Reference | Comment/Concern | Intervenor Recommendation | AEM Response
GNDOE-1 | General | n/a | p2 | supporting documents relevant for this technical review are inconsistent with the documents outlined by the applicant in a list (namely Doc. 502 dated Dec. 5, 2007). For example, the Bathymetric Surveys (Doc. 309) and the Incineration Waste Management Plan (Doc. 581) submitted for review, are not currently on the list. Additionally, at the beginning of this review, regulators such as GN-DOE received many documents through electronic mail and regular mail delivery | documents relevant for this review should be clarified
GNDOE-2 |  | n/a | p2 |  | terms and conditions from previoulsy issued Type B water licenses (namely 8BC-TEH, 8BC-MEA, and 3BC-THE respectively), be incorporated into a single enforceable Type A water license that deals with management, mitigation and monitoring of waste and water related issues holistically
GNDOE-3 | A. Water Quality | Issue #1: Acid Rock Drainage and Metal Leaching | p8-10 | It is noted...that analysis for neutralization potential (NP) has been reported as Sobek methodology and that the CaNP, based on CO2 analysis, are comparable (pg 10, Fig 3-4, Doc 425). Although these values are similar, in reviewing the geochemistry data presented to date some samples currently classified as NPAG because of NPR>2, may now be classified as PAG because the NPR<2 if using the CO2 determination for NP. | The applicant should clarify how changing NP determination using on-site analysis (i.e., CaNP test) affects material classification and waste volume calculations. In re-evaluating the ARD/ML potential over the next two years, the applicant should also revisit the existing database and confirm that waste volume calculations are still valid. These revisions should also be reflected in revised water quality predictions.
GNDOE-4 |  |  | p8-10 | applicant suggests that segregation of PAG and NPAG IV may be difficult operationally (pg, 54, Doc 485) and that if it cannot be done then all the material will be managed to minimize ARD potential. | applicant should clarify how IV material will be managed if it cannot be segregated, and when the decision point will be made to segregate NPAG and PAG IV material. If the material cannot affectively be separated, it should all be managed as PAG.
GNDOE-5 |  |  | p8-10 | applicant proposes that over the project life that total metal analysis will be assessed as a tool to indicate metal leaching. It has not been possible to make this correlation to date (pg 10, footnote, Doc 425), however, with on-going work on understanding geochemistry the applicant may be able to establish some useful correlations | In re-evaluating the ARD/ML potential over the next two years, the applicant should include an analysis establishing correlations between metal concentration and leach rates for NPAG material. They should also consider including some PAG material in these programs. Although the intent is to encapsulate the PAG material in order to mitigate leaching potential, the inclusion of these samples in the program may improve correlations by providing additional information with respect to maximum rates possible from material on-site
GNDOE-6 |  |  | p8-10 | applicant has also committed to using NPAG material in road construction (Table 2.1, Doc. 500) | Clarification of what ARD/ML screening criteria will be used for material used to construct site roads, and for exposed outcrop along the road that may be subject to cutting, should be included in the waste and water management plan. Given that work will continue on-site to improve geochemistry this work should be expanded to include access routes as well
GNDOE-7 |  | Issue #2: Water Management & Water Quality | p10-13 | The applicant is proposing to construct the dikes primarily from materials mined on-site with the designs including a downstream rockfill, a filter zone and an upstream impermeable element (pg. 62, Doc. 485). The proposed design includes either a geomembrane liner or compacted till as the impermeable element will depend on the availability of till at the time of construction and the construction costs at that time. Water management also includes a network of ditches and sumps to facilitate site management of contact and non-contact water. The applicant has not provided detailed design or maintenance procedures for these structures, however, they do state commitments to ensure that the challenges presented by ice-rich ground will be considered (pg 65, Doc. 485). | The applicant should provide information with respect to: a) using the liner or till for the dike; and b) design details for the ditch and sump construction before work proceeds
GNDOE-8 |  |  | p10-13 | Discharge to the environment is planned to be from the attenuation pond through a diffuser into Wally Lake in the Vault area throughout operations. In the Portage area discharge to the environment is from the attenuation pond into Third Portage Lake during years 1 to 5, and from the reclaim pond to the open pit from year 5 to closure. Modelling indicates that the discharge complies with MMER at the diffuser discharge point, except during year 6 to closure in the Portage area; there are possible exceedances of cyanide and copper. In reviewing the provided information, GN-DOE notes that at the diffuser, the effluent quality has several parameters that exceed HC DW and CCME FWAL, and the applicant notes that these criteria will potentially be approached within a 30 m radius from the diffuser (pg 70, Doc. 485) | GN-DOE acknowledges that effluent plume modelling from the diffuser must account for effluent discharge, water quality and flow, however, the applicant should clarify at what distance the CCME FWAL criteria are met if it is outside the 30m boundary. As a minimum, the applicant should ensure the effluent discharge to the receiving environment meets the CCME FWAL criteria within a 30 m radius from the Third Portage Lake diffuser.
GNDOE-9 |  |  | p10-13 | the applicant has developed a Water Quality and Flow Monitoring Plan (Doc. 450) to track changes in drainage chemistry. This plan incorporates compliance points (CM), where drainage is discharged to the environment and must meet MMER, and internal monitoring locations (IM) to monitor contact water across the site for operational purposes. | The proposed monitoring plan, and its associated triggers and response mechanisms are sufficient to address water quality issues over the mine life. However, GN-DOE suggests that the applicant confirms the data presented in Appendix C: Table C-1 in the Doc. 450 and clarify if these are the triggers for action for IM locations (i.e., are these 10x predicted "possible poor end"? pg 18, Doc. 450). Further, there is a commitment from the applicant that some locations will meet the HC DW criteria such as the pit lakes and adaptive management may need to reflect a change in applying MMER criteria to HC DW criteria over mine life. This consideration should be reviewed annually with the monitoring program.
GNDOE-10 |  |  |  | the NIRB Project Certificate conditions (#9) include providing water treatment details for process and attenuation pond water. Proposed treatment methods are presented (Doc. 467) to address concentration of TSS, metals and cyanide species. GN-DOE acknowledges that water treatment would be implemented on an "as needed" basis during operation to ensure MMER compliance and implemented at closure to ensure flooded pit water meets HC DW prior to dike breach. A metal that seems to be of concern is arsenic and proposed treatment includes the addition of iron to the drainage prior to pH adjustment with lime (pg 11, Doc. 467). Current water quality predictions indicate that iron concentrations may be above the HC DW and CCME FWAL criteria under the "expected probable" case. Additional treatment for arsenic may introduce additional iron into the drainage, and for iron exceedances, treatment will be implemented by adding lime to precipitate the iron. | GN-DOE acknowledges that even the best models cannot compare with the evaluation of operational monitoring data that allow for refined predictions and management plans. GN-DOE therefore recommends that the applicant refines water quality predictions and management plans (i.e., treatment needs) based on updated monitoring data during operation.
GNDOE-11 |  | Issue #3: Waste Management & Water Quality | p13 | The Mine Waste and Water Management Plan (Doc. 500) indicates that dust-control water (pg 10-5) will be drawn from Portage attenuation pond for use in the Portage Mine Area and drawn from Phaser Lake for use in areas outside the Vault and Portage catchment areas. GN-DOE recognizes that dust suppression will be necessary to minimize contamination of soil and vegetation and will ensure visibility on the road and safe passage for mine traffic. It is anticipated that the road corridors will be part of the site water management system with ditches and sumps directing impacted drainage toward the attenuation ponds. However, there may be areas that fall outside the proposed water management network (e.g., Vault haul road) | GN-DOE recommends that water from the noted areas be used, unless on-going monitoring indicates that it exceeds MMER and will require treatment prior to discharge to the environment. If other dust suppressants are to be used, the applicant is to refer to GN-DOE Guideline for Dust Suppression issued under the Environmental Protection Act.
GNDOE-12 | B. Waste Management | Issue #4: Sewage Treatment & Management | p13-14 | In the submitted documents, the applicant indicates that during mine construction treated sewage will be discharged to a fishless lake, namely Tear Drop Lake; however, it is unclear what the impact will be on the water quality in the lake. Page 10 and 11 of Doc. 355 indicates that a Rotating Biological Contacting (RBC) sewage treatment system will be able to meet a range of effluent quality (i.e., 4 to 40 mg/L for Biochemical Oxygen Demand and Total Suspended Solids). However, there is no further discussion on specific effluent discharge criteria that the applicant intends to meet | To ensure water quality of the Lake is not compromised, GN-DOE recommends as a minimum that the applicant meets Guidelines for the Discharge of Treated Municipal Wastewater in the Northwest Territories, and that monitoring at the lake be conducted to ensure the lake water complies with the Canadian Water Quality Guidelines for the Protection of Aquatic Life.
GNDOE-13 |  |  | p13-14 |  | the applicant should discuss contingency measures in the case of RBC malfunction, and indicate how and where the raw sewage will be handled and placed.
GNDOE-14 |  | Issue #5: Landfill Design Drawings & Management Procedures | p14-15 | The applicant has provided preliminary design drawings for two proposed landfills | given that the project is in licensing stage and construction can be started once a water license is granted, the applicant should have the final design drawings available for review
GNDOE-15 |  |  | p14-15 | Page 11 of Doc. 458 provides a list of materials to be landfilled including asbestos, white goods (i.e., refrigerators), and light bulbs (items of concerns are fluorescent lamp tubes); however, the applicant has not provided detailed landfilling procedures for these items of concern. | The applicant is to refer to GN-DOE guidelines and policy documents regarding landfilling of asbestos, equipment containing ozone depleting substances, and fluorescent lamp tubes.
GNDOE-16 |  | Issue #6: Landfarm Design Drawings & Management Procedures | p15 | The applicant has provided a preliminary design drawing for the proposed landfarm. | However, given the project is in the licensing stage and construction can be started once a water license is granted, the applicant should have the final design drawings available for review.
GNDOE-17 |  |  | p15 | page 5 of the Doc. 564 states “if the soil and snow/ice cells do not have sufficient capacity to accommodate a large spill, a temporary stockpile area could be set up adjacent to the landfarm.” However, the applicant has not provided any further details on management and design of this temporary storage area. For example, how will this area be managed to ensure contaminants do not enter the surrounding environment? Will a liner be installed? What is the capacity of this temporary storage area? | The applicant should provide further design and management details regarding the temporary emergency stockpile area for hydrocarbon contaminated soil
GNDOE-18 |  | Issue #7: Remediation Guidelines for Hydrocarbon Contaminated Soils | p16 | It is unclear which remediation guidelines the applicant intends to use, and what parameter will be measured, for remediation of hydrocarbon contaminated soil. Reuires clarification if intend to use one set of guidelines or the most stringent levels from combination of guidelines | The applicant should clarify the remediation guidelines that will be used for hydrocarbon contaminated soil, how the guidelines will be used, and what parameters will be measured
GNDOE-19 |  | Issue #8: Treatment and Monitoring of Hydrocarbon Contaminated Water | p16-17 | when treating contaminated water by the oil-water separator, it is generally advised to include an additional filtration treatment step such as the use of an activated carbon filter. Further guidance on this can be found in the Government of the Northwest Territories Generic Plans and Operating Procedures of a Remediation Facility for Hydrocarbon Contaminated Materials in the NWT. | The applicant should consider additional treatment beyond the use of an oil-water separator for treatment of hydrocarbon contaminated water
GNDOE-20 | C. Spill Contingency Planning | Issue #9: Spill Contingency Planning | p17-19; p23-25 | GN-DOE believes the Spill Contingency Plan is generally satisfactory; however, we have provided specific comments below for further improvement. Additionally, GN-DOE recognizes the plan cannot be fully completed until the mine and associated infrastructure is in place and operational. Spill plans are evolving documents that must be updated from time to time to adapt to changing circumstances | The applicant is expected to re-visit and revise their spill contingency plan when the mine becomes operational; subsequent to this, the plan should be re-visited and updated yearly.
GNDOE-21 | D. Closure & Reclamation | Issue #10: Closure & Reclamation | p19-21 | The applicant has submitted a Preliminary Closure & Reclamation Plan (Doc. 511) describing how the project site will be restored after closure, and further indicated in page IV of Doc. 511 that a final version of the plan will be submitted. However, the timeline of this submission is unclear, and whether the applicant will seek consultation with relevant regulators such as GN-DOE on the final plan. | The applicant should clarify when the final closure and reclamation plan will be submitted, and should commit to submit this final plan to relevant regulators such as GN-DOE for review
GNDOE-22 |  |  | p19-21 | GN-DOE is concerned about the proposed timeline for monitoring re-vegetation success at disturbed project sites post-closure. | The applicant should clarify when the final closure and reclamation plan will be submitted, and should commit to submit this final plan to relevant regulators such as GN-DOE for review
GNDOE-23 |  |  | p19-21 | GN-DOE is concerned about the proposed methodology to restore disturbed wildlife habitat sites. The applicant indicates on page 11-2 of the Doc. 511 that they will cover the Tailings Storage Facility and Rock Storage Facilities with a layer of coarse grained waste rock, with potential to add another layer of fine till. | The applicant is recommended to cover waste rock piles with finer grain materials and/or to provide corridors through the rock piles to ease wildlife passage
GNDOE-24 |  | Issue #11: Water Quality & Closure | p21-22 | The closure plan incorporates the use of a cover of NPAG material to ensure geochemical stability on the Portage Rock Storage Facility (RSF) and the Tailings Storage Facility (TSF); however, it is proposed that the Vault RSF will not require a cover. It is presented that the decision to cap one but not the other is based on current geochemical understanding and the predicted water quality. The long term geochemical stability of the RSFs and TSF is dependent on assumptions that the establishment and maintenance of frozen conditions will occur, that the proposed classification of waste rock is correct, and that management plans will be appropriately implemented and mitigation measures are successful | The applicant should revise closure plans regarding the TSF and the RSFs as operational information and management plans are revised
GNDOE-25 |  |  |  | The Mine Waste and Water management plan (Doc. 500) suggests that freezing conditions will not be established until 10 to 15 years after operations cease and it is unclear the post-closure monitoring period (pg 14-2, Doc. 511) or if it incorporates thermal monitoring | The applicant should clarify the timing of post-closure monitoring of the TSF thermal conditions; the Mine Waste and Water Management Report (Doc. 500) suggests that freezing conditions will not be established until 10 to 15 years after operations cease and it is unclear the post-closure monitoring period
The applicant should commit to monitor thermal conditions within the Vault and the Portage RSF areas with mitigative measures implemented if predicted thermal response is not realized
GNDOE-26 |  |  |  | The applicant proposes that water quality in the flooded pits will be monitored and predictions indicate that the chemical constituents will comply with MMER criteria and CCME FWAL criteria except for arsenic, cadmium, chromium and manganese | The applicant should ensure the water quality of the flooded pits meets the CCME FWAL criteria (i.e., metals) prior to dike breaching

## INAC
No. | Aspect | Technical Comment # | Review Page Ref | Comment/Concern | Intervenor Recommendation | AEM Response
INAC-1 | General Conditions |  | Sec 2.1 pg.2 and Sec.2.4.1 pg.3 | In a December 10th, 2007 letter from the NWB to AEM, NWB appeared to accept the proposal by AEM that the NWB grant a Water Licence with the condition that AEM provided detailed technical review and expert analysis of the final design of the Goose Island Dike. | This expert review will be required prior to commencement of the Goose Island Dike (at least 12 months).
INAC-2 |  |  | pg.2 | Dr. Norbert R. Morgenstern suggested in a March 30, 2007 draft letter to Cumberland Resources Ltd. that the Proponent form an independent dike safety review board. | This approach has been used at Diavik and other mines and is strongly recommended by INAC and its review team for the Meadowbank Gold Project as a general condition of the Licence
INAC-3 | Design and Construction | 2.3.1 Mitigative Measures For Seepage From Tailings Facility | pg.2 | Rpt 371 appears intended to address the issues identified in Condition #20 and states “Natural freezing of the Central dyke and the Tailings Storage Facility (TSF) resulting permafrost encapsulation (a natural process resulting from climatic conditions at the site)”. However, the thermal analysis (rpt 420) does not appear to have considered the implications of seepage on the development of permafrost in the dyke or TSF. The analysis of seepage may have over-predicted the development of permafrost in the dyke and TSF. | The statement that permafrost in the dyke and TSF is a mitigative measure may be inappropriate.
A coupled seepage and thermal analysis should be carried out as originally noted in NIRB Commitment #65.
INAC-4 |  | 2.3.1 Mitigative Measures For Seepage From Tailings Facility | pg.2 | Reference is made (Rpt 500) to an evaluation of the effect of groundwater flow on tailings freezing using a coupled model for advective groundwater flow and conductive heat transport. | The report infers that this numerical model predicted minimal effects on the timeframe for tailings freezing, although a clear demonstration of these minimal effects on tailings freezing was not presented.
INAC-5 |  | 2.3.2 Final Report, Design Of Dewatering Dykes | pg.3 | Sections 6.4.1 and 6.4.2 note that a turbidity barrier will be put in place prior to placement of materials in the lake and that the two rockfill embankments will be placed by “bulk-heading” with the till subsequently placed between the two rockfill embankments. Figure 6.1 shows the till being placed somewhat behind the advancing fronts of the two rockfill embankments. Since the till contains a significant portion of fine material (on average about 25 percent silt and clay sizes), a considerable amount of sediment may be expected to be released into the water column between the rockfill embankments with only the turbidity barrier to prevent the turbid material from reaching the larger lake environment. | AEM should consider additional methods to limit the potential release of sediments into the environment such as by placing the entire length of the outer rockfill embankment before any till is placed inside do the rockfill will act as a filter for the sediments reduced by the till when it is placed in the water.
The implications of this issue and alternative methods on aquatic resources should also be reviewed.
INAC-6 | Final Design of Dewatering Dikes | 2.4.1 Use of Cement in All Cutoffs | pg.3 | AEM does not commit to using cement in the cutoff wall for the initial construction for the East and Bay Zone Dikes. | If the proposed design approach is to follow an observational approach drawing on experience from design and construction of dikes in water depths of less than 10 m to support (prove) the future design of the same concept for use in water depths of greater than 10 m, then INAC believes that cement should be considered for all initial cutoffs to provide an important link to the rest of the designs, to reduce the possibility of unexpected high water volume management and to reduce the likelihood of internal erosion.
INAC-7 |  | 2.4.1 Use of Cement in All Cutoffs | pg.4 | Dr. Morgenstern highlights that the special considerations of the cutoff wall are: 1. Ability to embed the cutoff wall in the bedrock. 2. Ability to seal the cutoff wall/bedrock interface. 3. Consolidation and resulting properties of the till core. 4. Response of the cutoff wall to lateral loads as a result of deformation of the till core. | Suggest adding internal erosion (piping) at the dike foundation and lakebed contact to list of considerations. If an erosion resistant cutoff is not constructed and if the lakebed is not prepared before placing of the till core, a potential exists for piping failure after dewatering of the pit. AEM should show that piping is not a possibility or AEM should either design for the possibility or piping and/or provide clear direction for an Emergency Response to an erosion pipe developing under the dike.
INAC-8 |  | 2.4.2 Dike Instrumentation: concerns with design of instrumentation program & explanation of instrumentation for initial construction | pg.4 | Specifications call for the use of vibrating wire piezometer model Geokon 4500MLP which is designed to provide intimate contact with the wall of the borehole reducing potential for lag time in monitoring pore water pressure. Literature describing the installation of the 4500MLP references boreholes in cohesive materials which provide wall stability. The core till within the dewatering dike may not exhibit these characteristics and casing may be required to maintain an open hole. | Installation may be cumbersome therefore alternative models of vibrating wire piezometers should be explored as a contingency
INAC-9 |  | 2.4.2 Dike Instrumentation: concerns with design of instrumentation program & explanation of instrumentation for initial construction | pg.4 | The thermistor cable leads and piezometer cable leads are to be extended from the installation location to the data logger sheds in PVC conduit. No allowances have been made to use multi-conductor cable to limit the quantity of cable lead. From each crosssection of the dewatering dikes there will be 13 to 16 cables that have to be extended and bundled through PVC conduit. | This could prove to be a monumental task of managing electrical cables as well as plumbing PVC pipe as each additional cross-section joins up with the trench
INAC-10 |  | 2.4.2 Dike Instrumentation: concerns with design of instrumentation program & explanation of instrumentation for initial construction | pg.4-5 | Specifications for inclinometer casing call for an externally coupled shear wire connection. The anticipated settlements within the core till are 2.5 metres prior to dewatering. | There is no mention of anticipated settlements post pre-loading of the core till and prior to dewatering. There will likely be some settling of the core till however no allowance has been made for collapsible joints in the inclinometer casing. There is a good chance the inclinometer pipe will fail as a result of high vertical deformations due to settlement if it is not allowed to collapse. This would preclude use of the instrument for any longer term evaluations of horizontal deformations;
INAC-11 |  | 2.4.2 Dike Instrumentation: concerns with design of instrumentation program & explanation of instrumentation for initial construction | pg.5 | Slope indicator installations in an uncemented cutoff are expected to be problematic for the dewatering dike cutoffs without adequate strength (typically provided by using cement). | The following questions should be raised: Do Slope indicator need to be installed in the cutoff? Or would SI’s on either side of the cutoff serve the designer’s purpose.
INAC-12 |  | 2.4.2 Dike Instrumentation: concerns with design of instrumentation program & explanation of instrumentation for initial construction | pg.5 |  | What is the expected strength of the soil-cement backfill within the cutoff wall? Will this strength be sufficient to transfer lateral pressures to the inclinometer pipe?
How will the inclinometer pipe be installed within the soil-cement backfill?
What method of drilling is proposed?
What methods are proposed to check the QC of the soil-bentonite and soilcement backfill?
Figure 6000-31, Typical Section A, shows the inclinometer pipe and thermistor cable are installed within the cutoff wall. The section is confusing in that it shows lake bed till - the cutoff wall is to extend to the bedrock therefore no lake bed till. Also, the inclinometer pipe and thermistor cable are positioned 5 metres from centerline piezometer. What is the centerline piezometer?
The report includes a summary table for thermistor cable locations and slope inclinometer locations but not a summary table for piezometer locations.
Drawing Nos. 6000-31, 32 show typical piezometer layout. Twelve piezometers per cross-section and 16 cross sections. 192 piezometers, 32 thermistor cables 488 beads) and 16 slope inclinometers. Document 342 Volume 1 Section 6.5.6 states 56 piezometers and 18 thermistors.
INAC-13 |  | 2.4.3 Central Dike Instrumentation | pg.5-6 | Several instrumentation and constructability and layout questions follow | Shallow piezometers are to be placed upstream of grout curtain under a concrete mat and bituminous liner and, as well, thermistor cables and piezometer cables are to be installed along the slope and crest of the embankment through the bituminous liner. Discussions for these sequences is lacking, including whether the installation may jeopardize the integrity of bituminous liner since access for monitoring purpose during construction to the thermistor cable and piezometer cable locations will require foot traffic on bituminous liner. Little discussion of piezometer installations within the fault zone was found.
Horizontal thermistor bead spacing of 20 metres have 6 beads per cable. AEM does not indicate why only 6 beads installed per cable are proposed when closer spacings would require little extra cost and would permit the failure of a bead without seriously jeopardizing loss of information.
AEM should clarify why, although the thermistor cable installations extend 5 metres into bedrock, none of the cables are planned to extend deeper into bedrock.
INAC-14 | Water Management | 2.6 | pg. 6 | Non-contact water is discussed in the context of the proposed final discharge water quality criteria from the Portage and Vault Attenuation Ponds (Report #515). Noncontact water will be diverted and discharged to the receiving environment throughout mining operations, based on water turbidity as the monitored parameter. | Greater assurance is warranted to demonstrate that non-contact water has not mixed with water exposed to mining activities, so that all non-contact water can only be released to the receiving environment via a surveillance monitoring location.
INAC-15 |  |  | pg. 6 | The top elevation of the shoreline protection system to protect the diffuser pipe from ice action at the shoreline is set at 135.0 masl for Third Portage Lake. | During technical conference calls, AEM agreed to provide the Board with an explanation of how this elevation was determined and an estimate whether this elevation will be exceeded during the lifespan of the project.
INAC-16 | Waste Management Design and Plans | 2.7.1 Incineration Waste Management Plan | pg. 6 | This is a conceptual document. The incinerator (type and size or performance) has not been selected nor has the location of the facility been identified. been selected nor has the location of the facility been identified. One idea is to locate itnear the landfill, although a location nearer to the camp and administration complex may be more appropriate for proximity to electrical power. The document provides only a concept and outline of the proposed incineration plan. All waste materials that may cause odours, are included for incineration (foods, paper/wood, food packaging, sewage sludge, dead animals). A comment on Page 5 says “the incinerator at Meadowbank will be designed for, and achieve, compliance immediately upon attaining normal full scale operation”. This comment could imply that the incinerator may not be in operation or operate effectively for conditions other than full production. | For license approval, the proponent should provide the initial attempt at selecting the incinerator type and size to handle the projected waste stream. In addition, the proponent suggests a bag house may not be needed. Before drawing this conclusion, the proponent must provide the pre-design selection process for the incinerator and performance standards and also allow for provision of a bag house, based on appropriate modeling.
INAC-17 |  | 2.7.1 Incineration Waste Management Plan | cont'd | On Page 7, Sec 3.3 it states that any waste ash above criteria will be buried in the tailings storage facility. This may contravene the regulatory requirements. Section 4.0 suggests that the incinerator has not been selected. On Page 14, the data identified suggest that an incinerator may have been selected but no details are provided. Many sections of this document appear contradictory and need clarification. It also is not clear if the tailings storage facility will be lined to control any unwanted leachate development from materials that cannot go in the landfill. | as above
INAC-18 |  | 2.7.2 Landfill Design and Management Plan | pg.7 | Supplemental information provided on the Portage Rock Storage Facility appears complete. The base of the landfill appears to be on gravel and therefore permeable material. | Any potential leachate developed through the base will need to be monitored.
The landfill monitoring plan should include both a surface water and groundwater monitoring program.
The management plan and the incineration plan allude to waste diversion and purchasing practices to minimize wastes, but details were not provided.
For landfill final closure, the final cover must have a design that will provide long-term care of the site that also minimizes greenhouse gas development.
INAC-19 |  | 2.7.3 Landfarm Design and Management Plan | pg.7 | Document suggests the holding time for hazardous waste material is an open-ended period. | The holding time for hazardous waste material should be per regulation.
|  |  |  | Page 11 indicates that contaminated snow may be removed | Contaminated snow should be handled and treated as contaminated water
INAC-20 |  | 2.7.4 Supplementary Info on STP | pg.7 | The movement and quality of treated effluent is unclear, including transfers to Tear Drop Lake. A model and specification for the proposed sewage treatment plant has been identified (Model L-400, BioDisk Corp., Ontario). The design basis for secondary treatment appears to be sufficient, with waste sludge being sent to the incinerator. | AEM should clarify, in one document, the route for sewage, especially during construction.
INAC-21 |  | 2.7.5 Underground Water Quality | pg.7-8 | Predictions of mine pit water quality are based on a groundwater monitoring well network of seven wells. For the period 2003 to 2007, 13 groundwater samples plus field duplicates, were collected from which baseline groundwater quality values were presented for the main rock types in the mine pits and tailings storage areas (Reports #317 and #548). This dataset was used in the context of the accelerated mine plan (8,500 TPD) to predict mine water quality requiring storage and ultimately treatment (Report #499). Parameter sensitivity analyses indicate significant changes to the predictions of mine pit water quantity and quality will occur if the baseline water quality or hydraulic conductivity of the Bay Zone and Second Portage faults, or other fractured | Continued validation of this mine pit model is warranted using actual mine pit water data when it becomes available, to compare actual to predicted mine water balance and water treatment requirements for demonstrating the underlying reliability of the basis for all operational and post-closure water quality commitments.
INAC-22 |  | 2.7.6 Proposed Water Treatments | pg.8 | The proposed water quality criteria for Portage and Vault Attenuation Ponds (Report #515) describes contact water will be discharged during mine operations, contingent on the water quality complying with the water quality standards specified in the MMER. | Contingencies are provided if reclaim (process) water does not meet release standards,although details of contingencies are not described for the attenuation ponds.
INAC-23 | Contingency Planning | 2.8.1 Spill Contingency Plan | pg.8 | The current spill contingency plan is inadequate to cover all aspects of the project and other spill plans exist. Report #483 does not discuss spill contingencies for the proposed all-weather road or marina, which is included under the B licence. | Before a water licence can be approved, these contingency plans need to be finalized and accepted. As requested by NIRB, a more comprehensive risk assessment of spills is required to include cyanide, hazardous materials and pit/dike/dam failures with mitigation alternatives and consultation with local communities.
INAC-24 |  | 2.8.2 Emergency Response Plan | pg.8 | The currently proposed Emergency Response Plan requires an amendment which will satisfy NIRB’s request for involving the local communities in the Plan. | Amendments should be completed before a water licence is approved.
INAC-25 | Closure and Reclamation | 2.9.1 Disposal of Buildings and Infrastructure | pg.8-9 | If buildings and infrastructure cannot be safely or economically salvaged, the disposal at open pits and/or rock facilities (waste dumps) is only recommended if a strict policy for avoiding placement of toxic or hazardous materials is implemented. | A cleaning and stripping area is recommended to remove oil, grease, fuels, chemicals and any other material which may be harmful to the environment.
After placement of these materials into the open pits or rock facilities, a monitoring and remediation program should be developed and established to report on any long-term impacts on the environment.
INAC-26 |  | 2.9.2 Tailings Cover | pg.9 | A two metre thick cap is proposed for covering tailings during reclamation | A plan to install and monitor this capping is recommended to verify the adequacy of the cap and make adjustments as necessary to protect the environment
INAC-27 |  | 2.10 Closure Plan | pg.9 | The proposed closure plan requires amendment to satisfy reclamation of the port facility, rock quarries for road construction and all-weather road (unless this is to become a permanent feature). | The closure plans included under the water license for the road and the laydown area in Baker Lake should be referenced.

## DFO
No. | Aspect | Technical Comment # | Review Pg Ref | Comment/Concern | Intervenor Recommendation | AEM Response
DFO-1 | Impacts to Fish & Fish Habitat | 3.1..1 Sediment and Water Quality Issues - Construction | pg.4 | Road Construction, Diversion Ditches It is DFO’s position that all materials used for works or undertakings, including fish habitat compensation measures such as dikes, shoals and fish compensation works in or near water, is clean competent rock, non-acid generating (NAG) and non-metal leaching (NML). It is likely that many of these impacts from sediment due to construction activities can be mitigated through best management practices, however specific details are lacking. These need to be addressed specifically in the various management plans. | DFO recommends that all construction, operation, modification, decommissioning, abandonment and restoration plans for all infrastructure works or undertakings in or near water include best management practices for sediment and erosion control that will mitigate potential harmful impacts to fish and fish habitat. Management plans should include specific detail of mitigation measures during and after construction as it relates to ice-rich soils, steep slopes, sedimentation control and bank remediation.
DFO-2 |  | 3.2. Dike Construction Activities | pg.4 | Construction of the dikes is proposed to occur by sequentially adding materials into the lake (p 59-60 of Application) which will cause substrate disturbance and fine sediment disruption which will increase turbidity and TSS levels in the lake. This activity will cause sediment to be suspended in the water column and settle out in other areas of the lake. This could potentially disrupt and limit the ability of fish to locate food sources and feed. Additionally the sediment when it settles out could also smother benthic invertebrates and fish eggs or other biota. It is not certain how far this HADD could potentially reach out into the lakes. Sediment that accumulates at a depth greater than 1 mm will smother and kill biota therefore this impact must be minimized and mitigated to the greatest extent possible. | Details should be provided in regards to the projected sediment plumes and details need to be provided on the extent of this disturbance. Details on mitigative techniques to contain the disturbance and impacts should be provided. The Application document (p.59-60) and the AEMP indicates that a silt curtain will be utilized to contain some of the sediment but specific details on the location have not been presented.
This detailed information needs to be presented in the Plan in relation to background data on lake currents, projected sediment plumes and what measures will be taken to monitor turbidity and sediment accumulation.
DFO-3 |  | 3.3. Dewatering Activities | pg.5 | It is proposed that some of the water to be decanted will be pumped to the natural environment and that some may also be pumped to a number of attenuation ponds or to other lakes. As water levels in the dewatered areas lower, there is potential for sediment to slump and potentially greatly increase TSS and turbidity. The increased levels could potentially harm fish and also result in excess sediment being discharged to some of the lakes. Details are lacking as to threshold values of turbidity and suspended sediment. It is not clear what criteria are to be used to establish threshold limits when alternative areas such as attenuation ponds to allow excess sediment to settle out are to be used. It is also not clear what areas will potentially be used and what the capacity of attenuation ponds will be. | DFO would like clarification and a detailed explanation of the dewatering process and water management during this process to ensure impacts to fish and fish habitat from sediment are fully mitigated. Threshold levels for TSS need to be established for management purposes.
It also proposed that a fish salvage operation will occur in conjunction with dike construction and dewatering activities. Since there is potential that fish could become entrained in pumps, proper screening on intakes will be required. DFO recommends that the company adhere to DFO’s Freshwater End-of-Pipe Fish Screen Guidelines (DFO 1995) for proper screening and submit engineering designs for approval.
DFO-4 |  | 4.1 Fish Salvage Program | pg.5 | Meadowbank has been working on developing a specific fish-out program for the project lakes to submit for approval. | The Fish-Out program should follow the general methods listed in DFO’s Fish-Out Protocol and should include the following: a) Daily electronic reports of the CPUE phase and numbers on total removal phase b) Results of community consultations c) Method of dealing with excess fish d) Phasing of fish out within Second Portage, Third Portage and Vault Lakes.
DFO-5 |  | 5 Aquatics Effects Mgmt Program | pg.6 | It appears that Meadowbank has identified a number of comprehensive monitoring programs; however, many of the Plans are very conceptual. For example in the “Type A Water License Application on page117 in reference to the AEMP, it is stated that; “This program will be developed in detail”. | This detail needs to be provided for the completion of an adequate technical review and before a Type A Water Licence is issued. The review is necessary to determine whether the Monitoring Plans will have the scientific rigour necessary to distinguish project impacts from natural variation.
In addition, monitoring should verify impact predictions.
DFO-6 |  |  | pg.6 | As well, the adequacy of baseline data has not been determined. Meadowbank had also committed during the Environmental Assessment to collect further baseline data during pre operating phases and this information has not been presented. | This information needs to be presented and discussed at the technical sessions in relation to the proposed monitoring plans.
DFO-7 |  |  | pg.6 |  | AEMP needs a detailed table along with mapping or illustrations that identify the specific locations of sample sites, the numbers of samples and each parameter that is proposed for sampling.
DFO-8 |  |  | pg.6 |  | The monitoring schedule for the life of the mine and post closure needs to be developed and presented.
DFO-9 |  |  | pg.6 | Of particular importance to DFO is the monitoring of biological community and the integrity of the aquatic ecosystem | Monitoring needs to be rigorous enough to document that the project does not impact various trophic level organisms such zooplankton that fish such as lake trout or char depend on.
As is mentioned the monitoring program also needs to avoid impacts to fish populations; therefore, sentinels species should be considered when selecting organisms to ascertain metal levels in fish or other biota.
DFO-10 |  |  | pg.7 | A number of targeted monitoring studies are also identified to deal with particular issues. For instance, all dike faces will be constructed from low metal leaching iron formation rock. There is to be a sampling plan to determine metal levels that leach into the water from the dike material but the plan is very conceptual. | Details need to be provided as to methodology, schedule, sampling apparatus and protocols.
DFO-11 |  |  | pg.7 | An additional study mentioned in the AEMP is one to monitor the utilization of spawning habitat by lake trout after dike construction since it is proposed that lake trout will use the dike face. | DFO recommends that details on how the monitoring of the utilization of dike faces as spawning habitat by lake trout after dike construction will be carried out and how success or effectiveness is measured.
DFO-12 |  |  | pg.7 | It is mentioned that the principles of adaptive management will be utilized in monitoring activities. | However, details need to be provided in how this will be carried out. Threshold levels for action need to be an integral part of any adaptive Management Plan and since they have not been provided, the Plans are incomplete.
DFO-13 |  |  | pg.7 | Finally, the requirements for reporting and approving the various monitoring Plans and subsequent monitoring reports needs to be determined and included as conditions of a Type A Water License.
DFO-14 |  | 6. Blasting Plan | pg.7 | A number of outstanding concerns need to be addressed with the blasting Plan to ensure that fish and fish habitat are not impacted during mine blasting operations. | Calculations need to be redone since an Overpressure of 100 kPa was used for calculations when the proponent was advised to use 50 kPa during the EA phase.
DFO-15 |  |  | pg.7 | It is also stated that for portions of dike or shoreline where the 13mm/s guideline is exceeded, modified blast designs can be used or additional fill materials could be placed along the shoreline or dike upstream (lake side) face to increase distance from blast area. This is a concern to DFO since additional fill placed along the shoreline or dike upstream face could result in a HADD if the material is placed in the lake. | Therefore details need to be provided on what will be done for portions that exceed 13 mm/s guideline.
Provide a detailed vibration monitoring program for blasting activities
DFO-16 |  | 7. Closure & Reclamation | pg.7 | The Closure and Reclamation Plan is conceptual in nature but some detail should be provided in regard to processes on refilling the pits and possible effects on the natural lakes. | Management Plans need to include provisions so that excess water withdrawal of natural water bodies will not occur.
DFO-17 |  |  | pg.7 | Since dike breaching will not occur until water quality is acceptable within the pits, contingencies need to be developed in the event that dikes will not be breached. | A requirement for contingency planning should be part of the closure plan.
DFO-18 |  | 8. Habitat Loss, Compensation & NNLP | pg.8 | The NNLP submitted by Meadowbank has been accepted in principle as a result of discussions during the Environmental Assessment phase where it was determined that the habitat losses could likely be compensated. | However it was expected that there would be changes to the design of some of the compensation works and that there may be other suitable areas or projects for compensation.
DFO-19 |  |  |  |  | A chart and schedule should be developed to identify when certain habitat compensation measures are being implemented.
DFO-20 |  |  |  | DFO’s concern is that much of the compensation is delayed until mine closure which will result in an extended loss of productive capacity during the time the compensation is deferred. Much of the compensation is also contingent on acceptable water quality within the pit areas. | Other opportunities should therefore be actively pursued before and during the mine operation period so that the effectiveness of compensation can be determined. There may be many opportunities within the watershed as a whole and these have not been explored to the extent that they should be.
DFO-21 |  |  |  | It will also be very important that effectiveness is determined where compensation has been proposed during operations such as along the face of the dike. This area is supposed to be suitable habitat for spawning and this should be determined during mine operations. Monitoring activities should begin immediately after construction of the dikes to determine if there is a concern due to metal leaching from the rock materials used in dike construction. | Details on monitoring and sampling protocols of the interstitial waters and methods for determining fish use of these areas have not been provided.
In addition threshold levels should be determined so that an adaptive management plan can be utilized in the event that predictions are not realized.
DFO recommends that other fish habitat compensation measures be explored in the watershed. In addition a contingency plan for compensation in the event water quality within the pits is not acceptable must be presented.
DFO-22 |  | 8.2.1 HL from Drawdown And Water Diversions | pg.9 | There is potential loss and impact to fish habitat from many proposed water drawdown and diversion activities that are proposed as a result of infrastructure development. | Controls need to be put in place to ensure that there is no excessive drawdown of the water bodies which could result in fish kills. The water license also needs to contain measures to ensure that drawdowns and diversions do not result in fish habitat losses and impacts from sediment.
DFO-23 |  | 8.2.2 HL from Diversion of Phaser Lake Outflow | pg.9 | Phaser Lake discharge will be redirected to Turn Lake since the natural drainage has been altered. However, no details have been provided to demonstrate that the connecting channel is passable fish. Section 4.2.5 of the NNLP just states that there is no net difference in water balances and therefore that there is no impact to fish habitat, but this is not necessarily true if connecting channels are eliminated or impassable. The text (at least in section 4.2.5) does not indicate that discharge will be pumped, but figures in other reports indicate a dewatering barge will be employed. In addition, erosive conditions that will potentially increase sediment transport and deposition need to be monitored in this location as well as in others. | DFO recommends that details of the diversion channel of Phaser Lake outflow be provided to demonstrate that the connecting channel is passable to fish.
DFO recommends that the NNLP Monitoring include monitoring of the runoff or sedimentation from the diversion channel of Phaser Lake outflow.
DFO-24 |  | 8.2.3 HL from Portage Lakes Connecting Channel | pg.9 | Construction of the dikes will eliminate the westernmost of three channels connecting Secondand Third Portage lakes and it is proposed that the easternmost channel may need to be widened to facilitate flow. It is possible that this enhancement could serve as compensation for fish habitat loss but the detailed engineering survey as suggested in the NNLP (4.2.1) has not been provided. | DFO recommends that the detailed drawings of the proposed modification of the westernmost channel connecting Second and Third Portage Lakes be provided and a hydraulic assessment of the proposed channel modification and the impact on water levels between the two lakes.
DFO-25 |  | 8.2.4 HL from Intake & Effluent Pipes | pg.9 | Three pipelines are to be constructed in the project lakes one of which will be for the intake and two for effluent discharge to a diffuser located in the lakes. | Detailed drawings including the plan, profile and cross-section of the freshwater intake pipe need to be provided as well as the site and design of the fish intake screen. The intake end of the pipe will be screened in accordance with the DFO “Freshwater End-of-Pipe Fish Screen Guidelines
Detailed drawings including the plan, profile and cross-section of the effluent pipes also need to be provided.
DFO-26 |  | 8.2.5 HL from Turn Lake Road Crossing | pg.10 | The access road between the plant site and the Vault development will require two 75 m long, 2.5 m diameter round culverts with a sideslope ratio of 3H:1V. Under freshet conditions discharge velocity will not exceed 0.6 m/s so that fish passage should not be impeded. | Detailed estimates of water velocities and depth of flow during low, medium and high flow events should be provided.
DFO-27 |  |  |  | DFO does not agree with the statement in section 4.2.3 that migratory habitat will not be adversely affected. The NNLP states that fish migration is uncommon and that large boulders are likely preventing the movement of fish between the two lakes. As the culvert installation will result in a HADD of fish habitat, the removal of the fish barrier will provide access between lakes thus providing greater access. This could be considered compensation for the HADD associated with the culvert installation. | DFO recommends that the details of the HADD and fish habitat compensation associated with the Turn Lake Road culvert installation be provided.
DFO-28 |  |  |  | Adequate mitigation to facilitate passage should include embedding the culvert at least 20% with the backfill material in the culvert matching the upstream and downstream gradients. | Monitoring will need to confirm that the installation of the culverts do not block fish migration.
DFO-29 |  |  |  | It is also stated that standard construction practices are to be employed during culvert installation and details should therefore be provided. | Detailed drawings of the plan, profile, and cross-section of the Turn Lake Road culvert crossing will need to be prepared. The construction sequence should be described.

## EC
No. | Aspect | Technical Comment # | Review Page Reference | Comment/Concern | Intervenor Recommendation | AEM Response
EC-1 | Ground Water | 2.1 Baseline Ground Water Quality Data | pg.4 | There are several problems concerning the reporting and use of the total dissolved solids data particularly in the most recent report on the 2007 Baseline Ground Water Quality. * Specific points raised on 2006 & 2007 reports on pg 4-6 * | The reviewer recommends that more robust permanent ground water quality monitoring wells be installed at the Meadowbank site as soon as possible and ground water quality samples be collected and analyzed to establish baseline ground water quality at the permanent sites prior to the start of active mining. The new baseline data should initially be compared to the existing baseline data to determine whether there are any significant variations between the two data sets.
EC-2 |  | 2.2 Revised Predictions of Brackish Water Upwelling | pg.6-9 | In conclusion, the estimates of total flows and average TDS concentrations of brackish ground water predicted in the report dated July 27, 2007 for the accelerated mining rate of 8500 TPD are considered reasonably conservative and may be used in the site water balance model (GoldSim model) to predict overall water balances and water quality for the site. As mining progresses, however, monitoring of the quantity and quality of ground water inflows to the open pits will be needed to verify these predictions and water management plans may need to be reviewed and updated depending on the results of the monitoring. | The reviewer recommends that some updating and rerunning of the model be considered as data become available during the early stages of mining at the site. However, as mining advances, the need for predictive modeling will be replaced by the collection of actual monitoring data from the site.
EC-3 |  | 2.3 Ground Water Monitoring Installations | pg.9 | The high degree of failure of the well installations is disappointing but the reviewer is assured that a better understanding of the baseline groundwater quality has been obtained even though the reliability of the installations has been limited. The installation of the three replacement wells near the sites of the original wells is a required procedure that will allow comparison of the successive sets of ground water quality data even though the sites will eventually be destroyed by the mining development. Subsequent installations, however, should be placed outside areas of direct development such that they can provide a more permanent monitoring capability and, in addition, the design of the new installations needs to be revised, as suggested, to improve their reliability. | The reviewer recommends that more robust permanent ground water quality monitoring wells be installed at the Meadowbank site as soon as possible and ground water quality samples be collected and analyzed to establish baseline ground water quality at the permanent sites prior to the start of active mining.
EC-4 | Water Quality | 3.1 Lake Sediment Removal | pg.10 | Removal of lake bottom sediments will involve handling of saturated materials which are high in several metals (As, Cd, Cr, Cu, Pb, Hg, Ni, and Zn), and having a fine clay/silt particle size. The relatively limited volume to be placed upstream of the tailings dike following excavation of the footing area should not significantly compromise supernatant quality. With respect to the balance of the lake bottom sediments, placement in the footprint of the Portage pit lake may represent a liability when the area is re-watered and may negatively impact water quality during re-watering as a result of suspended solids and metal concentrations. Given the high metals content and fine particle size, it is unlikely that the sediments would be useful for terrestrial reclamation purposes. As the proposed disposal area is shallow (2-8 m maximum), consideration should be given to disposal to the bottom of the Portage pit prior to flooding, or other disposal methods where the materials will be effectively isolated from wind and wave action following rewatering. | Options for disposal of lake bottom sediments should be refined and disposal methods developed that minimize the potential for effects on surface waters. This may simply involve placing materials in deeper areas of the lake floor, and ensuring that a minimum water cover depth will be overlying at closure.
EC-5 |  | 3.2 Dewatering of Lakes | pg.11 | Use of 60% as the proportion of water which can be drawn down untreated is reasonable, based on Diavik’s experience during pool dewatering in the open water season. It is not clear how the balance of potentially turbid water will be treated before discharge. Table 12.1 shows Portage Pit dewatering of 4.57 Mm3 to Third Portage, and 0.39 Mm3 (or 8.5%) being discharged to the attenuation pond. Goose Island Pit will have 1.47 Mm3 dewatered to Third Portage Lake, and 0.007 Mm3 (or 0.5%) pumped to the attenuation pond. Table 12.2 does not show the dewatering volumes expected to go to Wally Lake in Year 4 from Vault Lake. | Dewatering discharges will need to be of sufficient quality and clarity that receiving water bodies are not adversely impacted. EC recommends that there be discussion regarding what would be protective limits to set for this activity, and how the proponent will achieve them. Such limits should be in the order of 15 mg/L TSS, and include total metals parameters.
EC-6 |  | 3.3 Effluent Quality Criteria and Water Treatment | pg.11 | Receiving waters in the project area contain very low concentrations of all parameters, and are ultra-oligotrophic with respect to having low nutrient levels and productivity. Ecosystems are based on very simple food webs, and as such are vulnerable should impacts occur to any compartment of the ecosystem. A very high level of protection is warranted when discharging effluent into such a pristine system, and it must be noted that the MMER discharge criteria provide only a minimum national standard for discharge quality, as these criteria were not developed based on biological impacts. Water treatment will almost certainly be required for reclaim pond discharges, and very possibly for pit lakes and attenuation ponds, depending on water quality. All effluent discharged should pass acute toxicity tests using rainbow trout and Daphnia magna. | It is important that impacts to water quality be avoided (where possible) or minimized through the implementation of mitigation measures, including using best available water treatment practices. Conceptual plans for water treatment have been provided, and MMC should strive to ensure that end of pipe discharge levels are as low as possible prior to discharge. Effluent quality criteria should be set in the water licence which are protective of the receiving environment, and consistent with other mining operations operating in the NWT and NU where experience has not demonstrated unacceptable impacts have resulted.
EC-7 |  | 3.4 Water Quality Predictions – Cyanide Degradation Products | pg.12 | WAD CN does not include the degradation products cyanate (CNO) or thiocyanate (SCN), which will remain in the water column and will degrade to form ammonia. This was seen at the Colomac mine, where an annual progression in the tailings and Zone 2 pit chemistry was observed as SCN and CNO dropped and ammonia and nitrate increased over time. It is not clear whether predictions for ammonia in reclaim water included CNO and SCN breakdown products; if not, ammonia levels may have been significantly underestimated. | MMC should clarify whether ammonia predictions for the reclaim pond included all CN breakdown products, and if not, adjust ammonia predictions to account for these sources. EC asks that the proponent commit to periodic re-calibration of the water quality predictions modeling for parameters of concern.
EC-8 |  | 3.5 Water Quality in Pit Lakes | pg.13 | With respect to the Portage pit post-closure chemocline disappearance, there is uncertainty as to whether the chemocline will erode. ...A deeper chemocline is predicted to develop in Vault pit, and would be less likely to erode given the lack of a talik connection to groundwater. It is unclear why the potential for stratification is not predicted for Goose pit. Ground water discharges to the pits are not included in the GoldSim model during flooding after mine closure, i.e. the ground water taps are turned off at the end of active mining. Modelling of the evolution of pit lake water quality was also done independently of the GoldSim modelling using the model CE-QUAL-W2. It is unclear whether ground water discharge was taken into account in this model. | EC recommends that water quality criteria be set as a prerequisite to be met prior to removal of the dewatering dykes, in order to ensure protection of the receiving environment.
Clarification of the role of groundwater inputs/discharges in the evolution of pit water quality is requested.
EC-9 |  | 3.6 Aquatic Monitoring/EEM Integration | pg.14 | The report notes that either gradient or control-impact study designs will be used, and it should be confirmed that sufficient baseline data has been collected to characterize the full range of natural variability and provide a basis for the study design selected. Other points of discussion would include sediment quality parameters, usefulness of zooplankton monitoring, sampling locations, and capturing seasonal effects. Linkage to the Surveillance Network Program and to adaptive management will be important. | EC recommends that the construction phase SAPs be developed as early as possible, and circulated for review.
With respect to groundwater monitoring, the proponent has developed a general ground water monitoring plan as part of the overall water quality and flow monitoring plan but details on the proposed ground water monitoring installations are scattered through several documents. It would help understand the proposed ground water monitoring if the proponent consolidated these details in a more specific plan that includes a schedule for the phased installation of monitoring wells and a brief discussion of the reason for each installation.
EC-10 | Tailings & Waste Rock Mgmt | 4.1 Design Depth of the Long-term Active Zone | pg.14 | However, the proponent has suggested an upper climate change within the next century in the order of 6 °C. Although the mine site will remain within the zone of continuous permafrost, the thickness of the active layer would likely deepen. .....This would appear to increase the active layer to the current design of 2 meters. Given the crucial function of this cover, the thickness of 2 meters would appear to be a minimum particularly in light of the potential factors such as pile geometry and configuration (i.e. more heating to a south-facing curved pile face resulting in deeper active zone), vegetation (or lack thereof) effects, placement errors and longer term climatic changes that may make the nominal thickness of 2 meters insufficient. | The proponent should confirm the necessary thickness of the capping material to accommodate the active zone in the upper limit climate change simulation to ensure the capping material is effective in the long-term, and, that sufficient benign capping material is available to cover the required facilities
EC-11 |  | 4.2 Viable contingency for waste rock piles if freezing approach insufficient | pg.15 | Although it is appreciated that much effort has gone to establish preferred approach to manage mine rock waste, a contingency should be presented. It should be technically viable and mitigate concern. It may be inferred in the company’s Adaptive Management Approach that contingency would be developed as necessary. | The proponent should develop a contingency that if the preferred approach is inadequate, that it would commit to undertake to address the concern. By way of examples, and not meant to limit or direct the company’s deliberations, such a contingency could be additional thickness of the cover, altering its permeability to air and water, accelerating vegetation, or even relocation or sustainable polishing of problematic drainages so as not to impact nearby fishery waters.
EC-12 |  | 4.3 Environmental characteristics of the till | pg.16 | Sections 2.3.5.3 and 4.1 in the License application appear to be somewhat in conflict. Much of the soil would presumably overlie the ore body. Table 2.17 suggests a substantial portion may be problematic in terms of at least pH. Natural surface waters in the area appear to have low buffering capacity. | The proponent should address if there is in fact a conflict in conclusions. If there is some problematic till, the proponent should describe the effect of any of this material being incorporated in roads, surface toppings or in the core will have bearing on their environmental performance. If this potentially problematic material would have a detrimental effect, the proponent should describe control measures that would be implemented to ensure that this problematic material is not inadvertently incorporated in those environmentally sensitive structures.
EC-13 |  | 4.4 Defining the Plan to effectively segregate site mine rock | pg.16-17 | It is recognized than an Adaptive Management Approach is going to be followed in which techniques and environmental protection measures would be iteratively improved as understanding and experience is accumulated. However, with the excavation commencing soon, the company should be in a position to propose criteria for the metal leaching. Conversely, they should be in a position to substantiate a view that by controlling acid generation, either as measured by sulfur content or neutralizing potential or the ratio, the mine rock will be effectively segregated. As much of the initial excavated material will be incorporated into site infrastructure, these long-term features must be robust and environmentally protective. The purpose of reporting the total neutralizing and acid potential in the rock cells is unclear. Is there a ratio or net magnitude that is a design criterion that has not been expressed in the license application? | Relatively rapid and ‘conservative’ (i.e. ensuring problematic material do not become incorporated into sites where they become a liability) segregation of problematic mine waste is fundamental to environmental protection measures at many mining operations. A credible segregation system should be in place prior to excavation and based on best current understanding. The role of potentially confounding factors should be recognized and accounted for in the segregation system. For example, such factors can include accounting for the presence of siderite (which can potentially overestimate the neutralizing capacity) or high moisture content, which can result in imprecise measures of arsenic using XRE. The system should be audited periodically to affirm it continues to operate effectively and conservatively.
EC-14 | Waste Mgmt | 5.1 Waste Incineration – Compliance w\ CWS for dioxins and furan emissions & mercury emissions. | pg.18 | As our Air Quality Specialist is unavailable before March 17th, we have to defer detailed evaluation of the IWMP, but would anticipate further discussion on aspects such as waste stream management, operator training and ash disposal. | EC would like to confirm that there are no plans for open burning.
EC-15 |  | 5.2 Landfarm Operation - Treatment | pg.18 | EC has some concern that soils and/or ice/snow contaminated with metals, solvents, glycol and heavy oils may find their way into the landfarm facility. | The proponent should provide details on storage and treatment options for these contaminants, noting measures to ensure they remain outside the landfarm facility.
EC-16 |  | 5.3 Landfarm Operation - Containment | pg.19 | Should contaminated soil and/or snow/ice exceed expected volumes, there should be an efficient and workable plan in place for the safe containment of significant volumes regardless of season and location of spill. | Should it be necessary to construct a second landfarm, the proponent should have a contingency plan in place whereby: • Construction time has been considered • There will be adequate personnel and equipment on site to facilitate construction of a second landfarm • Construction materials, e.g., granular materials, HDPE liner etc, will be available.
EC-17 |  | 5.4 Landfarm Operation - Spillway operation | pg.19 | More detail is required describing the design components/specifications of this spillway. | The proponent should specify what the design components of the spillway will be that will prevent the release of PHCs to the environment.
EC-18 |  | 5.5 Landfarm Operation - Potential exceedances in sump volume | pg.19 | Careful monitoring will be required to ensure sump volumes are not exceeded during the snow melt period. | EC recommends regular onsite monitoring in order to ensure trigger points are recognized and excess volumes are transported to the oil-water separator for treatment as needed.
EC-19 |  | 5.6 Landfarm Operation - HDPE liner integrity | pg.20 | It may be difficult to ensure a consistent and minimum depth of 0.3 m over the liner system. Also, during the tilling process, inexperienced operators may inadvertently disrupt or tear through the marker layer and into the liner system. | EC encourages the operators to take steps to prevent damage to the HDPE liner during mechanical operation of the landfarm, e.g., employ experienced operators, ensure an adequate depth of soil, ensure adequate depths of granular material (marker layer) covering the liner etc.
EC-20 | Emergencies | 6.1 Hazardous Material Management Plan | pg.20 | Under the E2 under Part 8 (CEPA), anyone storing or using a listed substance above the specified thresholds or who has a container with a capacity for that substance, will have to notify Environment Canada. Hydrochloric and Hydrofluoric Acids are regulated substances listed in Schedule 1 of the E2 Regulations. The threshold for Hydrochloric Acid in Schedule 1 of the E2 regulations is 6.80 tonnes at a concentration equal to or greater than 30% and for Hydrofluoric Acid the threshold is 0.45 tonnes at a concentration of 50% or more. | 1. Meadowbank must determine whether the maximum quantity of each substance or mixture used or stored at the place is greater than the threshold quantity listed in Schedule 1 of the E2 Regulations. If it is, you must comply with section 200 Regulations for that substance. 2. Spill reporting requirements under Section 201 of CEPA 1999 requires for any of the substances on the list established on Schedule 1, any person who has charge, management or control of the substance shall, as soon as possible, notify a CEPA Enforcement Officer. In addition, this person must abide by a number of other requirements, such as taking all reasonable measures consistent with the protection of the environment and public safety and providing a written report to Environment Canada.
EC-21 |  | 6.2 Revisions required to Spill Contingency Plan | pg.21 | Revisions | Table 5.2 - Environment Canada’s contact is (867) 766-3737 for a 24-hour emergency pager monitored by Emergency and Enforcement Officers. This contact information should be updated in AEM’s other spill contingency plans as well. A section should be added to the spill contingency plan which deals with the handling and disposal of hydrocarbon-contaminated materials that are too large to go to the landfarm. Experience at other northern open pit mines has recorded a high frequency of hydraulic fluid and other spills on rocks, which are difficult to clean up. In the case of both Ekati and Diavik such materials are being segregated inside the waste rock pile. MMC should specify what their intent is for dealing with such materials.
EC-22 | Closure & Reclamation | 7.1 Removal of Dewatering Dykes | pg.21 | The removal of the dykes could impact water quality in the affected lakes. Depending on the removal method chosen, water quality impacts could include increased TSS loadings, increased dissolved metal loadings from oxidization of exposed pit walls, and/or ammonia levels from blast residue (if blasting is used to remove dykes). It is also unclear if these potential impacts have been included in the water quality modelling. MMC will have to ensure that appropriate mitigation is identified and implemented for the chosen method. | EC recommends that further information regarding the method to be used to remove/breach the dewatering dykes be provided. Potential impacts of the chosen method should be discussed and mitigation measures identified.
EC-23 |  | 7.2 Post-closure maintenance of dykes | pg.22 | Will there be ongoing inspections to ensure there has been adequate freezing of the tailings and to ensure the central dike is preventing contaminated drainage into the Portage Pit? Post-closure, is there a maintenance plan in place that will regularly inspect and maintain the dewatering dikes as required? | EC recommends that the C&R Plan outline whether an inspection and maintenance program has been considered for the central Dike and to provide additional details on this program. The final design and construction of all dams/dikes should include provisions for: • the worst possible case environmental events • also recommended that best environmental management practices in Canada and elsewhere for dam design and construction be referenced in order to identify provisions for seepage collection and treatment; and • a dam safety inspection and maintenance program should be prepared for post-closure
EC-24 |  | 7.3 Tailings Storage Facility Closure | pg.22 | Insufficient detail has been provided concerning the environmental protocol describing the discharge water quality and the water management structures for the TSF; there is not enough detail provided on this ‘approved environmental protocol’ to assess the efficacy of this strategy. | EC recommends that more detail be provided on what the ‘environmental protocol’ would involve.
EC-25 |  | 7.4 Monitoring program for the RSF areas. | pg.23 | There is inadequate detail provided and we are therefore unable to evaluate whether objectives of the C&R Plan can be met. | EC recommends that there be discussion presented on what treatment/containment options will be employed should water quality of the drainage water be above guidelines or licence requirements. EC also recommends that testing be continued post-closure to verify expected behaviour of mine rock over the long term. In addition, a verification and field monitoring program for waste rock and the development of a contingency plan to deal with reactive material found in the non-mineralized waste rock storage piles is recommended.
EC-26 |  | 7.5 Water Management Plan to minimize and control contaminated drainage | pg.23 | There is inadequate detail in this section to explain how contaminated drainage will be minimized and controlled. | 1. More detail is required concerning water quality monitoring to be carried out and subsequent treatment options (passive or active).
2. Will the water management plan contain contingencies in the event of high contaminant concentrations and/or high volumes?
3. More detail is required concerning the statement that new surface drainage patterns will be established.
4. The proponent states that the fill rate of the open pits will be based on the maximum acceptable drawdown in each lake. Have these maximum drawdowns been determined?
5. Has consideration been given to the need to inspect and possibly maintain the dewatering dikes until the pit lake water levels achieve static conditions and the water quality is considered acceptable for release to the environment without treatment?
6. Is the proponent aware that water license criteria may be more stringent than MMER and CCME guidelines?
7. EC recommends ongoing modeling and laboratory testing of evolving water quality in the flooded pit, of discharge rates and of the type and length of treatment required
8. EC recommends a strategy to reduce the time that the open pit walls will be exposed before the pit is flooded.
9. Potential seepage pathways between the open pit and local waterbodies could and should be monitored, using strategically placed groundwater monitoring wells, which would give ample warning if contaminants (using suitable threshold levels for contaminants) were migrating through the subsurface/bedrock. MMC would then need to take corrective action, which could presumably include continuing to pump and treat the water in the pit.
EC-27 |  | 7.6 Closure of the Water Treatment Plant (if required) | pg.24 | Details on closure practices for this facility (if required) are lacking | Details on how this facility will be decommissioned (if one is required) should be included in the C & R report.
EC-28 |  | 7.7 Progressively Closing the RSFs | pg.25 | There is inadequate detail provided to evaluate whether objectives of the C&R Plan can be met. | EC recommends that additional information be provided that details what procedures will be modified and how and under what circumstances they will be modified.
EC-29 |  | 7.8 Post-closure monitoring of landfills and other waste management disposal areas | pg.25 | More information is required regarding the nature of post-closure monitoring of the landfills | EC recommends that the proponent develop a post-closure monitoring plan that outlines how the following will be monitored and, if required, mitigated for: • chemical characteristics of any landfill leachate and/or sludge • the ground thermal regime hasn’t been compromised • cover performance is maintained into the long term (e.g., has permafrost aggraded into the landfill etc.) • the cover does not crack or slump over time.

## KIA
No. | Aspect | Technical Comment # | Review Page Ref | Comment/Concern | Intervenor Recommendation | AEM Response
KIA-1 | Dewatering Dike Design | 2.1.1 Lake Bed Sediments | pg.2 (App A) | The data collected on lakebed sediments indicate that they are weak and of limited thickness. It is projected that these sediments will be displaced and/or incorporated into the dike rockfill. However, some of the data from borehole’s indicates a stiff clay layer on the lakebed which may affect rock berm stability on a local basis. MMC’s expert reviewer suggests that during construction there may be a need to flatten the design slopes due to the variability of lakebed conditions. | KIA concurs with MMCs reviewer - additional boreholes be used to more accurately determine the distribution and thickness of this stiff clay layer in order to better determine the extent of change to the dewatering dike design.
KIA-2 |  | 2.2.2 Boulder Distribution | pg.2 (App A) | The boulder distribution within the till below the dewatering dikes is unknown and can only reasonable be determined once excavation and dike construction is undertaken. A higher than planned boulder distribution will affect the construction schedule in that it may take longer to construct certain sections of the cut-off wall. | KIA suggests that a more conservative worst case construction schedule be presented with implications of its cascading effects on other work schedules.
KIA-3 |  | 2.1.3 Till Source & Quality | pg.2 (App A) | The quality and source of the almost 600,000 m3 of till that isrequired for the till cores of the dewatering dikes. In terms of quality the data collected from site confirms that the till is of variable hydraulic conductivity and cannot be relied upon as an impervious layer for cut-off wall construction. This was in evidence for work completed on the runway extension where the near surface soil and till flowed when thawed. The till could have a higher moisture content than is considered optimal. | KIA suggests additional consolidation testing for the wet till is required to determine the magnitude of potential problems with till settlement and consolidation rates. For the source of till it is stated that there will be sufficient till available from the pre-stripping of the North Portage and Third Portage deposits.
KIA would like to see more detail on the location of these till sources, specifically map locations with expected volumes and quality of till, and a quarrying schedule of the various till types to achieved the desired homogenous dyke core quality material
KIA-4 |  | 2.1.4 Dike seepage | pg.3 (App A) | Seepage volumes are predicted to range from 820 m3/day (East Dike) to 1900 m3/day (Goose Island Dike). These volumes can create potential for long term degradation of the seepage controls that are being put in place. A program to delineate and mitigate increased dike seepage over time has been tabled by MMC. | KIA recommends that an independent “dike safety review committee” should be formed to monitor all aspects of dike construction and performance during operational life. Any deficiencies found in design, construction materials, or during operations should be reported to the monitoring committee. This committee would have the authority to recommend changes to rectify deficiencies. The value of this committee is that the members would be able to view the broad issues associated with the dikes without being burdened by day to day operational issues that sometimes mask problems or delay response.
KIA-5 | Central (Tailings) Dike & TIA Design | 2.2 Central Dike & TIA Design | pg.3 | The Central Dike design has been changed such that it does not rely on a processed till core, but on impervious geo-textile materials. This addresses one of the greatest potential concerns from seepage of contaminated water during mine operation and after closure. A potential issue still exists with the Central Dike and with the bottom of the tailings area leaking due to incomplete freezing of the bottom of the tailings area. The dike is being constructed on a known fault the extends through the entire length of the tailings area, and that fault has hydraulic connection to surrounding lakes. During operations this fault could conduct tailings contamination into the pits under the bottom of the tailings dike, and on closure into the rehabilitated lakes eitherthrough the dyke or through the bottom of the tailings due to the higher elevation of the tailings area (147m) in relation to lake level (132m). | KIA suggests that the proposed program by MMC to delineate and mitigate increased dike seepage should include the independent dike safety review committee, again with authority to recommend changes to rectify deficiencies.
KIA also suggests that a “worst case” plan be prepared for implementation if monitoring indicates the possibility of incomplete freezing of the tailings area on closure.
KIA-6 | ARD/ML | 2.3 ARD/ML in Waste Rock, Tailings & WQ Predicitions | pg.4 (App A) | As part of MMC’s plan it will be necessary to closely monitor the thermal characteristics of the mine waste storage areas in order to evaluate the thermal modeling that predicts that the mine waste storage areas will freeze within two (2) years of placement (BGC, 2004). If this thermal modeling is deficient and the waste materials do not freeze then one of the potential consequences may be an inadequate prediction of the water quality. This could result in a negative effect on the perceived impacts and mitigation plans required for ARD/ML in waste rock and the overall water quality during mining operations and post-closure. | KIA suggests that rather than waiting 2 years that monitoring should for ARD, ML and non-metal constituents and re-evaluation of rock disposal practices commence immediately at start of operations.
KIA-7 | Closure & Reclamation | 2.4 C&R | pg.5 (App A) | KIA feels MMC has put together a plausible outline of an abandonment plan based on current knowledge. With that said it is difficult, given the possible “adaptive engineering changes”, to firmly define an abandonment plan at this time. | It is suggested that MMC should provide an annually revised abandonment plan during operational life. This plan would reflect the growing knowledge of the challenges abandonment will face.
These annual plans should then be reviewed by an independent committee, preferably made up of at least some members of the dike reviewing committee, as they will be familiar with the most important issues. This committee would have authority to direct further study into problematic issues and/or offer alternative solutions to these problems.
KIA-8 | Landfill Disposal | Landfill | pg.3 KIA main doc | MMC proposes two (2) landfills for the disposal of non-salvageable, non-hazardous solid waste, plus the option of in-pit disposal for industrial metal waste (primary crusher, ore storage building, mill complex etc.) upon closure. | KIA is in agreement with the landfill disposal techniques for the life of the mine however at this time, KIA does not support the placement of industrial waste (primary crusher, ore storage building, mill complex etc.) in the excavated pits following decommissioning.