## Explo Const Laydown Inventory
| Infrastructure/Asset | Amount | Status | Action | Timeframe | Comments
Regional Exploration | Seacans (salt, core boxes, lumber, equipment) | 49 | In-use | Maintain | NA | Million Dollar Seacan Cleanup
| Core shack | 1 | In-use | Maintain | NA
| Garage | 1 | In-use | Maintain | NA
| Plywood Shacks | 3 | Not in-use | Dismantle/dispose | 2023-2024
| Heli-Pad | 1 | In-use | Dismantle/reconstruct | 2023-2024
Orbit Garant (drilling) | Water seacans | 5 | Not In-use | Dispose | 2023-2024 | Million Dollar Seacan Cleanup
| Water Tanks | 6 | Not In-use | Backhaul | 2023-2024 | Val d'Dor
| Old Mobile Drill Shack | 1 or 2 | Not In-use | Backhaul | 2023-2024 | Assessing 1 or 2, Val d'Dor
| Mobile Pump Shack | 1 | Not In-use | Backhaul | 2023-2024 | Val d'Dor
| Fly Drill Shack | 3 | Not In-use | Dismantle/dispose | 2023-2024 | Scrap Steel
| Fuel Sleighs | 1 | Not In-use | Backhaul | 2023-2024 | Val d'Dor
| Seacan Sleighs | 7 | Not In-use | Backhaul | 2023-2024 | Val d'Dor
| Fly Baskets | 30 | In-use | Maintain | NA
| Fly Drill Floor | 7 | In-use | Maintain | NA
| Fly Drill Base | 7 | In-use | Maintain | NA
| Power Pack/Pressure Pump | 3 | In-use | Maintain | NA
| Fly Core Shack & PVC Tubing (permitting) | 1 | In-use | Maintain | NA
| Seacans (salt, core boxes, lumber, equipment) | 6 | In-use | Maintain | NA
| Mobile Core shack (Permitting) | 1 | In-use | Maintain | NA
| Old Mobile Drilling Units (Storage) | 3 | In-use | Maintain | NA
| Steel Sloop | 1 | Not In-use | Backhaul | 2023-2024 | Val d'Dor
| Wood beams | 15 | Not In-use | Dispose | 2023-2024
Energy and Infrastructure | Old Incinerator | 2 | Not in-use | Backhaul | 2023-2024
| Functional Incinerator | 2 | Not in-use | Store for future use | NA
| Incinerator structures | 3 | Not in-use | Dismantle/dispose | 2023-2024
| Seacans (fuel bladders) | 5 | Not in-use | Backhaul | 2023-2024
| Generator Building (seacans) | 1 | Not in-use | Dismantle/reuse | 2023-2024
| Generator Building (seacans) | 1 | Not in-use | Relocate/reuse | 2023-2024
| Generator Fuel Tank (50k Liter) | 1 | Not in-use | Reuse | 2023-2024 | Needs to be inspected/certified
| Accommodation Complex and auxiliary units (office, kitchen, STP/WTP, dry) | NA | Contingency use | Maintain | N/A
| Helipad | 3 | In-use | Maintain | 2023-2024 | Need to be compliant
| Jet-A Fuel tank | 2 | Not-in -use | Reuse | 2023-2024
| Fresh water intake | 1 | Not-in -use | Stand-By/for emergency 2023/2024 |  | Removed pump from water keep in stand-by
| Water truck Shelter | 1 | Not-in use | Maintain | N/A | N/A
Construction | Culverts (various length/diameters) | 101 | Storage | Reuse | N/A | To be used for AWAR, Discovery, Extension Roadways
| Fuel Tanks | 18 | TBD | Reuse | In-progress | Tanks were inspected in July. Compliant tanks will be reused (4 at West Vent Raise). Non-compliant tanks may be repurposed or will be backhauled 2024.
*Actions and timeframes subject to change based on logistics/resource availability.

## Sheet2
Backhaul
Disposal
In-use
Reuse
Recycle