## Sheet1
Appendix A: List of Relevant Terms and Conditions in the NIRB Mary River Project Report that has Implications for the NWB Licensing Process
Term & Condition # | Category | Description of the term and conditions | Reporting Requirements | Project Phases | Implications for NWB | Implementable under NWB water Licence | Where / How the Terms and Conditions could be met in Licence | Clarification Required | Comments
10 | Air Quality –Dust Management and Monitoring Plan | The Proponent shall update its Dust Management and Monitoring Plan to address and/or include the following additional items: a) Outline the specific plans for monitoring dust along the first few kilometers of the rail corridor leaving the Mary River mine site. b) Identify the specific adaptive management measures to be considered should monitoring indicate that dust deposition from trains transporting along the rail route is greater than initially predicted. | To be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities. | Construction | Yes | Yes | This could be approved as a plan under the terms and conditions within the water licence | No | Why is this condition limited to just the construction phase of the project?
13 | Noise and Vibration-Use of Explosives | The Proponent is encouraged to work with Fisheries and Oceans Canada at the regulatory phase and to take a precautionary approach when selecting the overpressure threshold to be applied to explosives use for the protection of fish and aquatic life | To be developed following approval of the Project by the Minister. | Construction | Potentially | Possibly | This could be addressed as a term and condition a in the water licence | No | Why is this condition limited to the construction phase of the project
16 | Hydrology and Hydrogeology – Water Infrastructure | The Proponent shall ensure that the water related infrastructure or facilities that are designed and constructed, including the modification of culverts, diversion of watercourses, and diversion of runoff into watercourses along the railway, access roads, the Milne Tote Road, and other areas of the Project site, are consistent with those proposed in the FEIS in terms of type, location, and scope and that the requirements of all relevant regulatory authorities are satisfied advance of constructing those facilities. | To be developed following approval of the Project by the Minister. | Construction | Yes | Yes | This could be addressed as a term and condition in the water licence | No | Why is this condition limited to the construction phase of the project
17 | Hydrology and Hydrogeology – Effluent Management | The Proponent shall develop and implement effectives measures to ensure that effluent from project-related facilities and/or activities, including sewage treatment plants, ore stockpiles, and mine pit, satisfies all discharge criteria requirement established by the relevant regulatory agencies prior to being discharged into the receiving environment. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be captured under the AEMP and relevant monitoring requirement included under the water licence | No
18 | Hydrology and Hydrogeology – Pit Lake Monitoring | The Proponent shall carry out continued analyses over time to confirm and update, accordingly, the approximate fill time for the mine pit lake identified in the FEIS. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure/Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be addressed under a term and condition in the water licence | Yes
19 | Hydrology and Hydrogeology – Water Infrastructure Monitoring | The Proponent shall ensure that it develops and implements adequate monitoring and maintenance procedures to ensure that the culverts and other conduits that may be prone to blockage do not significantly hinder or alter the natural flow of water from areas associated with the proposed mine. In addition, the Proponent shall monitor, document and report the withdrawal rates for water removed and utilized for all domestic and industrial purposes. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be addressed under terms and conditions in the water licence | No
20 | Groundwater/Surface Waters - Explosives | The Proponent shall monitor the effects of explosives residue and related by-products from project-related blasting activities as well as develop and implement effective preventative and mitigation measures, including treatment, if necessary, to ensure that the effects associated with the manufacturing, storage, transportation and use of explosives do not negatively impact the Project and surrounding areas. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be addressed as term and condition under the water licence | No
21 | Groundwater/Surface Waters – Aquatic Effects Monitoring Plan | The Proponent shall ensure that the scope of the Aquatic Effects Monitoring Plan (AEMP) includes, at a minimum, monitoring of non-point sources of discharge, selection of appropriate reference sites, measures to ensure the collection of adequate baseline data and the mechanisms proposed to monitor and treat runoff, and sample sediments. | To be developed following approval of the Project by the Minister. | Construction | Yes | Yes | The AEMP will be approved under the terms and conditions in the water licence | No | Why is this condition limited to the construction phase of the project?
22 | Groundwater/Surface Waters – Sediment and Erosion Management Plan | The Proponent shall develop a detailed Sediment and Erosion Management Plan to prevent and/or mitigate sediment loading into surface water within the Project area. | Plan to be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities. | Construction | Yes | Yes | This Plan could be approved under the terms and conditions in the water licence | No | Why is this condition limited to the construction phase of the project?
23 | Groundwater/Surface Waters – Groundwater Monitoring | The Proponent shall develop and implement a Groundwater Monitoring and Management Plan to monitor, prevent and mitigate the potential effects of the Project on groundwater within the Project area. | Plan to be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities. | Construction | Yes | Yes | This Plan could be approved under the term and conditions in the water licence | No | Why is this condition limited to the construction phase of the project?
24 | Groundwater/Surface Waters – Effluent Management | The Proponent shall monitor as required the relevant parameters of the effluent generated from Project activities and facilities and shall carryout treatment if necessary to ensure that discharge conditions are met at all times. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be captured under the AEMP and relevant monitoring requirement including in the water licence | No
25 | Landforms – Additional Geotechnical Investigations | The Proponent shall undertake the additional geotechnical investigations to identify sensitive landforms, modify engineering design for Project infrastructure and develop mitigation and monitoring measures to minimize the impacts of the Project’s activities and infrastructure on sensitive landforms. | Plan to be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities. | Construction | Yes | Yes | This Plan could be approved under the terms and conditions in the water licence | No | Why is this condition limited to the construction phase of the project?
26 | Landforms and Soils – Erosion Management Plan | The Proponent shall develop and implement a comprehensive erosion management plan to prevent or minimize the effects of destabilization and erosion that may occur due to the Project’s construction and operation. | Plan to be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities. | Construction | Yes | Yes | The could be captured under the Sediment Erosion Management Plan in #22 | No | Why is this condition limited to the construction phase of the project?
28 | Construction, Operations, Temporary Closure/Care and Maintenance, Closure and Post-Closure Monitoring | The Proponent shall monitor the effects of the Project on the permafrost along the railway and all other Project affected areas and must implement effective preventative measures to ensure that the integrity of the permafrost is maintained. | To be developed following approval of the Project by the Minister | Construction, Operations, Temporary Closure/Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be capture under a specific terms and condition in the water licence | No
29 | Landforms, Geology and Geomorphology – Design Plans | The Proponent shall provide to the respective regulatory authorities, for review and acceptance, for-construction engineering design and drawings, specifications and engineering analysis to support design in advance of constructing those facilities. Once project facilities are constructed, the Proponent shall provide copies of the as-built drawings and design to the appropriate regulatory authorities. | To be developed following approval of the Project by the Minister | Construction, Operations | Yes | Yes | This could be captured under specific terms and conditions in the water licence | No | Why is condition not capturing the closure phase of the project?
30 | Landforms, Geology and Geomorphology – Quarries | The Proponent shall develop site-specific quarry operation and management plans in advance of the development of any potential quarry site or borrow pit. | Plans to be provided to the NIRB for review and comment at least 30 days prior to commencement of construction activities. | Construction, Operations, Temporary Closure/Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be addressed under terms and conditions in the water licence | No
31 | Vegetation – Construction and Operations | The Proponent shall ensure that Project activities are planned and conducted in such a way as to minimize the Project footprint. | To be developed following approval of the Project by the Minister | Construction, Operations | Yes | Possibly | This could be addressed under terms and conditions in the water licence | No | What about leftover footprint from project activities?
33 | Vegetation - Monitoring | The Proponent shall include relevant Monitoring and Management Plans within its Environmental Management System, Terrestrial Environment Management and Monitoring Plan (TEMMP). | To be included in the Annual Report submitted to the NIRB . | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | These plans could be addressed under specific terms and conditions in water licence | No
34 | Vegetation - Monitoring | The Proponent shall conduct soil sampling to determine metal levels of soils in areas with berry-producing plants near any of the potential development areas, prior to commencing operations. | To be developed following approval of the Project by the Minister | Construction | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence
39 | Vegetation – Reclamation and Vegetation | The Proponent shall develop a progressive vegetation program for disturbed areas that are no longer required for operations, such program to incorporate measures for the use of test plots, reseeding and replanting of native plants as necessary. It is further recommended that this program be directly associated with the management plans for erosion control established for the Project. | To be provided to the NIRB for review and comment at least 60 days prior to commencement of construction activities | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No
40 | Vegetation – Reclamation and Vegetation | The Proponent shall include vegetation strategies in its Site Reclamation Plan that support progressive reclamation and that promote natural vegetation and recovery of disturbed areas compatible with the surrounding natural environment | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No
41 | Freshwater Aquatic Environment – Setbacks | The Proponent shall maintain a minimum 100-metre naturally-vegetated buffer between the high-water mark of any fish-bearing water bodies and any permanent infrastructure. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No | Some flexibility will be required
42 | Freshwater Aquatic Environment – Setbacks | The Proponent shall maintain minimum a 30-metre naturally-vegetated buffer between the mining operation and adjacent water bodies | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No | Some flexibility will be required
43 | Freshwater Aquatic Environment – Drainage | Prior to the start of construction, the Proponent must submit a Site Drainage and Silt Control Plan to the appropriate regulatory authorities for approval. | To be developed following approval of the Project by the Minister. | Construction | Yes | Yes | This could be implement under specific terms and conditions in the water licence | No | Why is this condition limited to the construction phase of the project
44 | Freshwater Aquatic Environment – Explosives | The Proponent shall meet or exceed the guidelines set by Fisheries and Oceans Canada for blasting thresholds and implement practical and effective measures to ensure that residue and by-products of blasting do not negatively affect fish and fish habitat. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be implement under specific terms and conditions in the water licence | No
46 | Freshwater Aquatic Environment – Drainage | The Proponent shall ensure that runoff from fuel storage and maintenance facility areas, sewage and wastewater other facilities responsible for generating liquid effluent and runoff meet discharge requirements. | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Yes | Yes | This could be implement under specific terms and conditions in the water licence | No
47 | Freshwater Aquatic Environment – Watercourses | The Proponent shall ensure that all Project infrastructure in watercourses are designed and constructed in such a manner that they do not unduly prevent and limit the movement of water in fish bearing streams and rivers. | To be developed following approval of the Project by the Minister. | Construction | Yes | Yes | This could be implement under specific terms and conditions in the water licence | Why is this not applicable during the operations and other phases
48 | mitigate impacts to freshwater aquatic habitat. | The Proponent shall engage with Fisheries and Oceans Canada and the Qikiqtani Inuit Association in exploring possible Project specific thresholds for blasting that would exceed the requirements of Fisheries and Oceans Canada’s Guidelines for the Use of Explosives In or Near Canadian Fisheries Waters (D.G. Wright and G.E. Hopky, 1998). | To be developed following approval of the Project by the Minister. | Construction, Operations | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No
64 | Terrestrial Wildlife and Habitat – Waste Management | The Proponent shall ensure that its Environment Protection Plan incorporates waste management provisions to prevent carnivores from being attracted to the Project site(s). Consideration must be given to the following measures: a. installation of an incinerator beside the kitchen that will help to keep the food waste management process simple and will minimize the opportunity for human error (i.e. storage of garbage outside, hauling in a truck (odours remain in truck), hauling some distance to a landfill site, incomplete combustion at landfill, fencing of landfill, etc.) b. installation of solid carnivore-proof skirting on all kitchen and accommodation buildings (i.e., heavy-duty steel mesh that would drop down from the edge of the buildings/trailers and buried about a half meter into the ground to prevent animals from digging under the skirting). | To be developed following approval of the Project by the Minister. | Construction, Operations, Temporary Closure /Care and Maintenance, Closure and Post-Closure Monitoring | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No
179 | Regulatory Capacity | Within 12 months of the issuance of the Project Certificate, all regulatory agencies with a regulatory mandate for the project, land owners and mineral owners are to conduct an internal capacity assessment to identify the monitoring, inspection, enforcement and reporting requirements for the specific regulatory agency, land owner or mineral owner that will be associated with the Project during operations, including taking into account the resource commitments necessary to participate fully in the key Project-specific Working Groups. | To be developed following approval of the Project by the Minister | Pre-Construction | Potentially | Possibly | This could be implement under specific terms and conditions in the water licence | No
180 | Regulatory Capacity | Within 24 months of the issuance of the Project Certificate, and on the basis of the internal capacity assessment, all regulatory agencies with a regulatory mandate for the project, land owners and mineral owners are to develop an implementation plan that identifies the ongoing resource commitments associated with the Project, the gaps in existing capacity and the mechanisms for ensuring there is capacity to meet the required commitments throughout the Project’s lifecycle. | To be developed following approval of the Project by the Minister | Pre-Construction | Potentially | Possibly | NA | No