## Commitments
ID | Recommendation # | Intervener | Party Responsible for Commitment | Commitment | Timeline for Submission | Form of Submission | Commitment Update (February 27, 2025)
1 | CIRNAC R-1 | CIRNAC | Baffinland | Baffinland will include a table providing the status of management plans in the QIA-NWB Annual Report for Operations. | Annually, with the submission of the QIA-NWB Annual Report for Operations | Annual Report | N/A
2 | CIRNAC R-06 | CIRNAC | Baffinland | (a) Baffinland will provide updated figures to reflect the most up to date information for all routine and permitted sampling locations on November 18, 2024 to the Nunavut Water Board and intervenors. | 2024-11-18 |  | Completed.
3 | CIRNAC R-10 | CIRNAC | Baffinland | Baffinland will provide the status of all thermistors, including BH2 and BH3 in the 2024 annual report. | 2025-03-31 | 2024 Annual Report | To be provided in the 2024 Annual Report.
4 | CIRNAC R-11 | CIRNAC | Baffinland | Baffinland will include multiple climate change projections (SSP1, SSP2 and SSP 5) in the next update of the thermal model planned for 2026, as outlined in the Interim Closure and Reclamation Plan Revision 6. | 2026-11-01 | Interim Closure and Reclamation Plan Revision | N/A
5 | CIRNAC R-13 | CIRNAC | Baffinland | Baffinland supports a change in the financial security review process that allows flexibility in timing and duration. Baffinland will continue to engage with CIRNAC and QIA on this specific item and present an agreed upon revision to the relevant WL conditions. | Before the public hearing |  | Baffinland, QIA and CIRNAC have considered Part C and have no revisions to recommend to the NWB at this time. Baffinland is committed to continuing to work with CIRNAC and QIA on an SMA that aligns with the process described in Part C of the Licence. It is anticipated this will occur after issuance of the renewed Licence. Baffinland, CIRNAC and QIA will continue to report to the NWB on the status of this item as discussions progress.
6 | CIRNAC R-22 | CIRNAC | Baffinland | Baffinland will update the Surface Water and Aquatic Ecosystems Monitoring Plan (SWAEMP) with a synthesis of the groundwater activity on site, combined with the groundwater quality analysis and interpretation. It is anticipated the update will include; frequency of upgradient and downgradient monitoring at selected shallow groundwater monitoring locations and identify potential areas and triggers associated with implementation of monitoring at the Project for water quality analytes and the associated monitoring frequencies. | within 1 year following the approval of the WL renewal | Updated Plans | N/A
7 | CIRNAC R-28 | CIRNAC | Baffinland | Baffinland will provide details regarding water bodies that will be withdrawn from and the projected volume of water during the detailed design stage of the Project. This will be submitted to the NWB as part of the design construction reports outlined in Part D, Item 2 of the Water Licence. | 60 days prior to start of water withdrawal for Steensby construction | Design Construction Report(s) | N/A
8 | QIA-TR-4 | QIA | Baffinland | Baffinland will work with QIA as part of the annual security review process to address comments on the thermal model and Interim Closure and Reclamation Plan (ICRP). Baffinland will include multiple climate change projections in the next update of the thermal model planned for 2026 as outlined in the ICRP Revision 6. | 2026-11-01 | Interim Closure and Reclamation Plan Revision | N/A
9 | QIA-TR-7 | QIA | DFO | DFO will provide its analysis of existing and required hydrological datasets associated with the Steensby Component. | 30 days prior to public hearing |  | N/A
10 | QIA-TR-8 | QIA | Baffinland | Baffinland commits to providing details to QIA on the use of the referenced methodology for under-ice water wathdrawals at lakes where no bathymetric information is available. Baffinland will provide the information to QIA for review when it is used. | To be provided when method is used |  | N/A
11 | QIA-TR-10 | QIA | Baffinland | Baffinland will provide aquatic habitat information collected at the proposed water intake sites. These details will be submitted to the Board for review and acceptance at least sixty days prior to construction as outlined in Part D, Item 2 of the Water Licence. | 60 days prior to start of Steensby construction | Design Construction Report(s) | N/A
12 | QIA-TR-20 | QIA | Baffinland | Baffinland will provide updated water sampling and monitoring location figures within the next version of the Surface Water and Aquatic Ecosystems Monitoring Plan (SWAEMP). This update will include updated water monitoring locations and flow directions. | within 1 year following the approval of the WL renewal | Surface Water and Aquatic Ecosystems Monitoring Plan | N/A
13 | QIA-TR-28-38 | QIA | Baffinland | Baffinland and QIA acknowledge there are existing regulatory authorizations (Project Certificate 005 Terms and Conditions and Appendix B Commitments) and bilateral agreements (Mary River IIBA and Water Compensation Agreement) that address the topics raised in QIA technical comments QIA-TR-28 to QIA-TR-38. This includes the integration of IQ into the Mary River Project, waterbodies of heightened importance, updates to Steensby baseline information, the Pond Inlet Freshwater IQ Study, Inuit OITRs, Inuit water rights, Inuit engagement, the Inuit Stewardship Program/Plan and CRLU studies. Many of these initiatives and deliverables are being led directly by QIA. Baffinland and QIA will continue discussions on these important topics and provide an update on the outcomes of those discussions as relevant to the water licence renewal process at least 3 weeks prior to the NWB Final Hearing. In the meantime, Baffinland and QIA agree that the NWB can proceed and schedule a public hearing on the basis of our mutual understanding of the current status of each item as agreed to previously and in other forums between Baffinland and QIA. | 3 weeks prior to the NWB final hearing |  | Baffinland and QIA advanced their discussions regarding QIA-TR-28 to 38, and based on agreed wording proposed in the Water Licence Framework, those comments are considered Resolved.
14 | ECCC #1 | ECCC | Baffinland | A comprehensive follow up report for water quality monitoring at the seep location as well as downstream receiving environment station D1-05 will be provided to ECCC, CIRNAC and QIA in Q4 2024. Baffinland will provide an update on the various infrastructure under the original Mine Site water management plan in subsequent annual reporting. As indicated previously the title may be misleading as this was a planning document and used to permit features under the WL in Modification No. 13. Baffinland will work with ECCC and the various regulators to ensure sufficient information is provided as committed to during ongoing discussions and the WL renewal process. We envision this to include lessons learned, adaptive management implemented to date, ongoing monitoring data, updates on constructed infrastructure with plans to address issues and then ensuring this is incorporated into the new designs or remedial actions for areas that are required. As this information is permitted and built with approval from the NWB then applicable information for how the facility or infrastructure is managed and operated is updated in the applicable WL management plan. Ie. Freshwater, Supply, Wastewater management plan. | by December 31, 2024 within 1 year following the approval of the WL renewal | Applicable Management Plans | A report detailing the seep at the KM 105 dam was provided to ECCC on January 22, 2025. N/A
15 | ECCC #4 | ECCC | Baffinland | Baffinland will include the list of total and dissolved fractions in the next update to the SWAEMP. Timing of plan update to be confirmed before the public hearing. | within 1 year following the approval of the WL renewal | Surface Water and Aquatic Ecosystems Monitoring Plan | N/A
16 | ECCC #5 | ECCC | Baffinland | The abbreviation BTE will be corrected in Section 3.1 of the next revision of the Fresh Water Supply, Sewage, and Wastewater Management Plan, which will be issued with the NWB QIA Annual Report for Operations in 2025 . Timing of plan update to be confirmed before the public hearing. | within 1 year following the approval of the WL renewal | Relevant Management Plan Revisions | N/A
17 | ECCC #6 | ECCC | Baffinland | Baffinland will adopt the below FEQGs as the discharge criteria for benzene, ethylbenzene, toluene and xylene at the Project. Parameter Federal water quality longter+D21m guidelines (mg/L) Benzene 0.59 Toluene 0.03 Ethylbenzene 0.07 Xylene 0.07 | 2024-12-18 | N/A | Baffinland integrated those updates in the Water Licence Framework.
18 | ECCC #7 | ECCC | Baffinland | Baffinland will issue a draft Schedule I with the requested information added on November 18th, 2024 to the NWB for consideration as part of these proceedings. | 2024-11-18 |  | Baffinland submitted a draft Schedule I on November 18, 2024 for review.
19 | ECCC #8 | ECCC | Baffinland | Baffinland will issue a draft Schedule I with this information added on November 18th, 2024 to the Nunavut Water Board for review as part of these proceedings. The most recent revision of the SWAEMP was issued prior to the KM105 Pond being constructed. Water Licence monitoring locations will be updated in the next revision of the SWAEMP. Timing of plan update to be confirmed before the public hearing. Baffinland will make the following updates to the draft Schedule I. 1. Nitrite-N be added to Group 7 in the Water Licence of Table 12 2. Add metals from Group 4 to Group 5 in the Water Licence of Table 12 | 2024-11-18 within 1 year following the approval of the WL renewal 2024-12-18 | Surface Water and Aquatic Ecosystems Monitoring Plan Revisions | Baffinland submitted a draft Schedule I on November 18, 2024 for review.
20 | ECCC #9 | ECCC | Baffinland | Baffinland is committed to incorporating updated industry standard guidelines and utilising them to protect potential receiving environments down gradient of the Project. Baffinland will add the new total Aluminum FEQG to the AEMP pending ongoing analysis of baseline data. Baffinland commits to updating their AEMP benchmark to align with CCME standards in the 2025 AEMP Rev 2 submission for selenium. Timing of plan update to be confirmed before the public hearing. | within 1 year following the approval of the WL renewal | AEMP Revision | N/A
21 | ECCC #11 | ECCC | Baffinland | The requested administrative updates for minor corrections will be made in the next revisions to the referenced plans and management plansfollowing the NWB normal course, of annual reporting, which occurs in parallel with the renewal process. Timing of plan update to be confirmed before the public hearing. | within 1 year following the approval of the WL renewal | Relevant Management Plan | N/A
22 | DFO-TRC-01 | DFO | Baffinland | Baffinland will include a summary table with all proposed watercourse crossings (road and rail culverts and bridges) in the next update to the SWAEMP for crossing locations along the Tote Road. The review of the SWAEMP will occur following the Nunavut Water Board normal course of annual reporting, which occurs in parallel with the renewal process. Timing of plan update to be confirmed before the public hearing. | within 1 year following the approval of the WL renewal | Surface Water and Aquatic Ecosystems Monitoring Plan Revisions | As outlined in response to ECCC #2, Baffinland proposes to update the SWAEMP within 6 months of the approval of this Licence by the Minister.
23 | DFO-TRC-02 | DFO | Baffinland | BIM will implement erosion and sediment control training is required for personnel involved with the planning, installation, and maintenance of erosion and sediment control measures. The addition of Canadian-Certified Inspector of Sediment and Erosion Control (CAN-CISEC) personnel has been valuable in drawing awareness to and understanding of erosion and sediment control requirements, supporting construction activities and daily operations. In-house Erosion and Sediment Control Awareness training is being developed for personnel involved in erosion and sediment control activities and will be rolled-out during winter 2024-25. Topics covered will include: • Legislation that governs erosion and sediment • Types of erosion • Factors that influence erosion • Erosion and Sediment control best management practices • Installation of best management practices | Winter 2024-2025 |  | As of February 20, 2025, the training program is being finalized. The schedule for training delivery is being developed, with plans for roll-out in Q2-2025.
24 | NWB TM-01 | NWB Tech Meeting | Baffinland | Baffinland will provide management plans requiring updates based on Renewal to the NWB within a year following the issuance of the Water Licence renewal. Baffinland will provide a proposed schedule for publication of updated management plans before the public hearings. | within 1 year following the approval of the WL renewal | Management Plans | N/A
25 | NWB TM-02 | NWB Tech Meeting | Baffinland | Baffinland will submit a draft Water Licence Framework to the NWB before the public hearings. | 2024-12-18 | Report: Draft Water Licence Framework | Baffinland submitted a draft Water Licence Framework on December 18, 2024 for review.
26 | ECCC-04 | ECCC | Baffinland | As part of the ongoing ICRP research, Baffinland commits to assessing the potential impacts of pit development on local permafrost and hydrogeological regimes prior to pit development to define closure requirements. The details will be further refined as part of the ICRP Rev 6 review that is ongoing.
27 | ECCC-03 | ECCC | Baffinland | Baffinland will conduct a review of the Tote Road Monitoring Program (TRMP) data to confirm the natural variability in the 150 metre sample area. Baffinland will share this data with ECCC, which will be used to build the trend of the Total Suspended Solid criteria to be implemented.
28 | CIRNAC R-04 | CIRNAC | Baffinland | Baffinland commits to conducting a review of dustfall data and the associated monitoring program to assess the following: • Sample design • Program assumptions • Data Collection • Dustfall relative to baseline predictions. Baffinland commits to conducting the dustfall review described above as part of the 2025 QIA/NWB Annual Report for Operations, to be submitted by March 31, 2026. As required, the outcomes of the dustfall data review will be integrated into relevant management plans. Any plan updates would be completed within 6 months of publication of the dustfall data review, or an alternative date as agreed to between CIRNAC and Baffinland. Furthermore, as outlined in response to QIA-TR-1, Baffinland will develop a memorandum that will assess temporal water quality trends in relation to relevant FEIS predictions. This memorandum, combined with the dustfall review data will inform future updates to relevant management plans. | March 31, 2026 September 30, 2026 | Dustfall Data Review Report Management Plan Updates
29 | CIRNAC-08 | CIRNAC | Baffinland | Baffinland will update the ICRP to include soil or sediments containing site related contaminants that pose a risk to human health and/or the environment. A contaminant is defined as any substance that, when introduced into the air, water, soil or sediment, exceeds an agreed upon end land use or other criteria developed as part of the closure planning process and has the potential to cause adverse effects to human health, the environment or ecological systems. | ICRP Revision | Management Plan Update
30 | CIRNAC-16 | CIRNAC | Baffinland | Baffinland will undertake a pit water quality model update in 2025. This model will include the following: 1. Operational pit water quality predictions for the next 5 years (2025-2029) 2. Water quality predictions for an early closure scenario at the end of 2029, considering three different climate change scenarios for a 100-year period. It should be noted that this model is being completed to provide data requested by CIRNAC and QIA regarding pit water quality predictions to support closure security estimation. As part of this modelling exercise, water quality predictions for the early closure scenario will be compared against closure objectives and criteria, which are outlined in Table 5.1 of Baffinland’s Interim Closure and Reclamation Plan Revision 6. The 5-yr operational water quality predictions will need to be evaluated against FEIS predictions and Type ‘A’ Water Licence Discharge Criteria. The model will be completed by Q4-2025 and is scheduled to be submitted as part of the Annual Security Review process. | Q4-2025 | Report
31 | QIA-TR-1 | QIA | Baffinland | Baffinland commits to the development of a one-time memorandum including the following aquatic monitoring information: • Temporal plots of water quality results from lake and stream CREMP monitoring areas that include results from the baseline (2006 to 2013), construction (2014), and operations (2015 to 2024) periods for specific parameters associated with the mine site ore bodies or with blasting (i.e., aluminum, arsenic, cadmium, chromium, copper, iron, lead, nickel, zinc, nitrate, nitrite, total Kjeldahl nitrogen, and ammonia). Area specific predictions from the Final Environmental Impact Statement (FEIS; Baffinland 2012) will be included on the plots for comparison. • Tabular summaries of seasonal averages • A statement comparing the concentrations to area specific predictions from the FEIS • Weather data will be corelated with sampling to the extent possible to assess the impact of wet versus dry events on observed monitoring values. This memorandum will be submitted within 6 months of the approval of this Licence by the Minister. The memorandum will be submitted to the NWB to allow a review of the study outcomes. Baffinland will provide the memorandum to QIA 30 days before the NWB submission to allow QIA to evaluate the conclusions and provide recommendations of updates into suggested management plans. As required, the outcomes of the memorandum will be integrated into relevant management plans. Any plan updates would be completed within 6 months of publication of the memo, or an alternative date as agreed to between QIA and Baffinland. | within 6 months of the approval of the Water Licence | Memorandum
32 | QIA-TR-2 | QIA | Baffinland | Where professional judgement is applied in relation to TARPs, Baffinland will include supporting rationale. BIMC to further provide a clearer linkage of how exceedances of objective TARP thresholds will result in management actions of project effects pathways. | When used | Annual Report
33 | QIA-TR-2 | QIA | Baffinland | Baffinland will update the AEMP to include event based water quality monitoring informed by the QIA-TR-1 memorandum conclusions, or other relevant data. The AEMP will define how an event is triggered and assessed. | within 6 months of the approval of the Water Licence | Management Plan Update
34 | QIA-TR-6 | QIA | Baffinland | Baffinland will collect supplemental baseline data to support the development of applicable aquatic monitoring programs along the Steensby Railway alignment and at Steensby Port, to cover a full season's data prior to construction commencing in a given location. If the supplemental baseline data deviates by more than 2 standard deviations from the original baseline, Baffinland will engage with QIA to review the findings and collaboratively develop appropriate updates to the construction monitoring programs, if required, to ensure potential environmental changes are effectively captured and addressed. | Prior to Steensby Construction | Report
35 | QIA-TR-7 | QIA | Baffinland | Baffinland is planning to reactivate the four hydrometric monitoring stations (BR11, BR25, BR96-2 and BR137) along the Steensby Railway corridor in 2025 to supplement existing baseline data collected for the 2012 FEIS. These stations will measure streamflow and help characterize natural variation in hydrological conditions. If the supplemental baseline data deviates by more than 2 standard deviations from the original baseline, Baffinland will engage with QIA to review the findings and collaboratively develop appropriate updates to the construction monitoring programs, if required, to ensure potential environmental changes are effectively captured and addressed. | Prior to Steensby Construction | Report
36 | QIA-TR-11/17 | QIA | Baffinland | Baffinland will update the AEMP to provide quantifiable triggers (e.g., exceedances of water quality guidelines or AEMP benchmark values) within the framework. These triggers will lead to specific adaptive management actions to be undertaken in response to exceedances. The management actions for these cases shall be initially investigative following a process defined in the AEMP, and if the investigation determines it, appropriate mitigative actions for the source or the cause of these exceedances will be implemented. Any plan updates would be completed within 6 months following issuance of the renewed water licence, or an alternative date as agreed to between QIA and Baffinland. The AEMP will be revised collaboratively with QIA review and input, specifically with regards to triggers for adaptive management actions. | within 6 months of the issuance of the renewed water licence | Management Plan Update
37 | QIA-TR-14/15 | QIA | Baffinland | Baffinland commits to a one-time submission of usable, sorted data and metadata for statistical analyses by July 31, 2025. The submission will include all the sediment and water quality data collected from Sheardown and Camp catchment (e.g., lake and tributary). QIA's analysis of this data will be completed at their expense. The outcomes of QIA's analysis will be shared with Baffinland in draft for review and to discuss in relation to any further action to be undertaken as part of the adaptive management framework. Following the completion of this process the QIA may publicly disseminate the results of its analysis through the Nunavut Water Board. | 2025-07-31 | Raw Data
38 | QIA-TR-16 | QIA | Baffinland | Baffinland will provide preliminary/interim and final engineering design solutions for the haul road drainage that currently is conveyed through the KM105 dam and eventually into Sheardown tributary into Sheardown Lake for QIA review at a minimum 60 days before the start of construction, in alignment with the Water Licence requirements. Baffinland will provide an initial adaptive design to QIA for review by July 31, 2025. | 2025-07-31 | Engineering Designs
39 | QIA-TR-24 | QIA | Baffinland | Baffinland will collaborate with QIA to incorporate the outcomes of QIA-led data collection into relevant management plans listed in Part B Item 14 of the Water Licence, and will plan to submit any consequential updates to the NWB with the submission of the 2026 Annual Report. The timing of this commitment is contingent on QIA providing Baffinland with available verified QIA program-led data relevant to Project water use and management and/or waste generation and management by the end of September, 2025. | 2025-09-30 | Management Plan Update