## Estimate Details
'Mary River Project - Complete Project Security Assesment - Estimate Breakdown Structure'
Issued on 10 January 2017
[44 empty] | C&M |  | Closure |  |  | Post Closure |  |  |  |  | C&M |  | Closure |  |  | Post Closure
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 0 - % | Year 0+1 - % | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 0- Cost ($) | Year 0+1- Cost ($) | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($)
1000 | Project Wide
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2014 |  | 11767.9113 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 2878.01 | 23854.5782 | 260707.4698 | 261420.0213 | 522127.4911 | 0 | 0 | 100% | 0% | 0% | 100% | 522127.4911 | 0 | 0 | 522127.4911 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 522127.4911 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 |  | 378 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 92.4453 | 766.2388 | 8374.2493 | 8397.1374 | 16771.3867 | 0 | 0 | 100% | 0% | 0% | 100% | 16771.3867 | 0 | 0 | 16771.3867 | Type A 2AM-MRY1325 | Modified | 2015 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 16771.3867 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional Laydown Areas |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2016 |  | 656.3333 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 160.5156 | 1330.4447 | 14540.4735 | 14580.2147 | 29120.6882 | 0 | 0 | 100% | 0% | 0% | 100% | 29120.6882 | 0 | 0 | 29120.6882 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 29120.6882 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables - addition of 49 person camp |  | 49 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 34339.2445 | 0 | 0 | 34339.2445 | 0 | 0 | 100% | 0% | 0% | 100% | 34339.2445 | 0 | 0 | 34339.2445 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 34339.2445 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017 |  | 1192.1667 | ea | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 291.5613 | 2416.6254 | 26411.3781 | 26483.5642 | 52894.9422 | 0 | 0 | 100% | 0% | 0% | 100% | 52894.9422 | 0 | 0 | 52894.9422 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 52894.9422 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C1 & 2018-R |  | 4018.6667 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 982.8221 | 8146.1863 | 89029.9382 | 89273.2699 | 178303.2081 | 0 | 0 | 100% | 0% | 0% | 100% | 178303.2081 | 0 | 0 | 178303.2081 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 178303.2081 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 A |  | 8.0269 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1.9631 | 16.2712 | 177.8281 | 178.3141 | 356.1422 | 0 | 0 | 100% | 0% | 0% | 100% | 356.1422 | 0 | 0 | 356.1422 | Type A 2AM-MRY1325 | Modified | 2015 A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 356.1422 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables |  | 550 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 385440.5 | 0 | 0 | 385440.5 | 0 | 0 | 100% | 0% | 0% | 100% | 385440.5 | 0 | 0 | 385440.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 385440.5 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - Shiploader |  | 5049 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1234.8047 | 10234.7614 | 111856.0446 | 112161.7634 | 224017.808 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 224017.808 | 0 | 224017.808 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 224017.808 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 R |  | 4660.9167 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1139.8934 | 9448.0828 | 103258.4081 | 103540.6283 | 206799.0364 | 0 | 0 | 100% | 0% | 0% | 100% | 206799.0364 | 0 | 0 | 206799.0364 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 206799.0364 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017-A |  | 7146.8933 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1747.8743 | 14487.3733 | 158332.9797 | 158765.7268 | 317098.7065 | 0 | 0 | 100% | 0% | 0% | 100% | 317098.7065 | 0 | 0 | 317098.7065 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 317098.7065 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port
2000 | Milne Port | 2100 | General
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 001 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed - Demolish Building - ISO Shipping Container | 2110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed - Demolish and foundations - Gravel Base - Skidded Building | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 003 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed - Demolish floor finish - Raised Steel or Wooden Floor | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Disturbed Area @ Milne Port (adjacent to Steel Tank Farm) |  | 45000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 571.0446 | 6581.25 | 57104.4642 | 17844.5406 | 81530.2548 | 0 | 0 | 100% | 0% | 0% | 100% | 81530.2548 | 0 | 0 | 81530.2548 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 27176.7516 | 27176.7516 | 27176.7516 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Laydown Area |  | 37375 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 474.2843 | 5466.0938 | 47428.43 | 14820.8823 | 67715.4061 | 0 | 0 | 100% | 0% | 0% | 100% | 67715.4061 | 0 | 0 | 67715.4061 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 22571.802 | 22571.802 | 22571.802 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP3 |  | 131000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1662.3744 | 19158.75 | 166237.4403 | 51947.4403 | 237343.6306 | 0 | 0 | 100% | 0% | 0% | 100% | 237343.6306 | 0 | 0 | 237343.6306 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 79114.5435 | 79114.5435 | 79114.5435 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP5 |  | 65000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 824.8423 | 9506.25 | 82484.2261 | 25775.4475 | 117765.9236 | 0 | 0 | 100% | 0% | 0% | 100% | 117765.9236 | 0 | 0 | 117765.9236 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 39255.3079 | 39255.3079 | 39255.3079 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 32000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 406.0762 | 4680 | 40607.619 | 12689.4511 | 57977.0701 | 0 | 0 | 100% | 0% | 0% | 100% | 57977.0701 | 0 | 0 | 57977.0701 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 19325.69 | 19325.69 | 19325.69 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP7 |  | 21000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 266.4875 | 3071.25 | 26648.75 | 8327.4523 | 38047.4522 | 0 | 0 | 100% | 0% | 0% | 100% | 38047.4522 | 0 | 0 | 38047.4522 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12682.4841 | 12682.4841 | 12682.4841 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | 13000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 164.9685 | 1901.25 | 16496.8452 | 5155.0895 | 23553.1847 | 0 | 0 | 100% | 0% | 0% | 100% | 23553.1847 | 0 | 0 | 23553.1847 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7851.0616 | 7851.0616 | 7851.0616 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP4 |  | 13000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 164.9685 | 1901.25 | 16496.8452 | 5155.0895 | 23553.1847 | 0 | 0 | 100% | 0% | 0% | 100% | 23553.1847 | 0 | 0 | 23553.1847 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7851.0616 | 7851.0616 | 7851.0616 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP6 |  | 7000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 88.8292 | 1023.75 | 8882.9167 | 2775.8174 | 12682.4841 | 0 | 0 | 100% | 0% | 0% | 100% | 12682.4841 | 0 | 0 | 12682.4841 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4227.4947 | 4227.4947 | 4227.4947 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2133 | Materials Handling | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2136 | Milne Port |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 14306 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 181.5414 | 2092.2525 | 18154.1437 | 5672.9777 | 25919.3739 | 0 | 0 | 100% | 0% | 0% | 100% | 25919.3739 | 0 | 0 | 25919.3739 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8639.7913 | 8639.7913 | 8639.7913 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2138 | Quarry Development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 12148.5 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 154.163 | 1776.7181 | 15416.3019 | 4817.4311 | 22010.4511 | 0 | 0 | 100% | 0% | 0% | 100% | 22010.4511 | 0 | 0 | 22010.4511 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7336.817 | 7336.817 | 7336.817 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2134 |  |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad @ Milne Port |  | 66536 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 844.3339 | 9730.89 | 84433.3918 | 26384.5411 | 120548.8229 | 0 | 0 | 100% | 0% | 0% | 100% | 120548.8229 | 0 | 0 | 120548.8229 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 40182.941 | 40182.941 | 40182.941 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 013 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274 W: 2665, H: 2032, 6350 kg | 2140-MO-001 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 014 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-002 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 015 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-003 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 016 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-004 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Mobile Light Plant, Large |  | 5 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 65 | 600 | 6494.3698 | 6000 | 13094.3698 | 96 | 480 | 100% | 0% | 0% | 100% | 13094.3698 | 0 | 0 | 13094.3698 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4364.7899 | 0 | 4364.7899 | 0 | 0 | 0 | 0 | 4364.7899
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Pick-Up Truck |  | 7 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 46.6667 | 175 | 4662.6244 | 1750 | 6587.6244 | 4 | 28 | 100% | 0% | 0% | 100% | 6587.6244 | 0 | 0 | 6587.6244 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2195.8748 | 0 | 2195.8748 | 0 | 0 | 0 | 0 | 2195.8748
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Ford F350 Pickup |  | 6 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 40 | 150 | 3996.5352 | 1500 | 5646.5352 | 4 | 24 | 100% | 0% | 0% | 100% | 5646.5352 | 0 | 0 | 5646.5352 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1882.1784 | 0 | 1882.1784 | 0 | 0 | 0 | 0 | 1882.1784
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Jump Conveyor |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Stockpile Reclaim Loader, 988 |  | 2 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 20 | 90 | 1998.2676 | 900 | 2988.2676 | 24 | 48 | 100% | 0% | 0% | 100% | 2988.2676 | 0 | 0 | 2988.2676 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 996.0892 | 0 | 996.0892 | 0 | 0 | 0 | 0 | 996.0892
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Grove 60 Ton Crane |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 988 Loader |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 345 Excavator |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | John Deere 850 Excavator |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Stockpile Mobile Feeder |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Stockpile Mobile Stacker |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Reclaim Mobile Feeder |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Container Handler |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Gantry Crane |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Ford F550 Mechanics Truck |  | 2 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 13.3333 | 50 | 1332.1784 | 500 | 1882.1784 | 4 | 8 | 100% | 0% | 0% | 100% | 1882.1784 | 0 | 0 | 1882.1784 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 627.3928 | 0 | 627.3928 | 0 | 0 | 0 | 0 | 627.3928
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | FIRE TRUCK |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Freightliner School Bus |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Kenworth Fuel Lube Truck |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | CAT 930 Loader |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Generator 3412-725 KW (Seacan) |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Lunch Rooms |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Man Lift |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Zoom Boom |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Boom Truck |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Passenger Bus |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Integrated Tool Carrier, 938 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | WRECKER TRUCK |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | FREIGHT HAUL TRACTOR , |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | MAINTENANCE FUEL/LUBE TRUCK , |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Skid-steer |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Flat Deck Truck |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Mini-Crane |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Marine Patrol Boat |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | MECHANICS TRUCK, |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 992 Loader |  | 4 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 52 | 480 | 5195.4958 | 4800 | 10475.4958 | 96 | 384 | 100% | 0% | 0% | 100% | 10475.4958 | 0 | 0 | 10475.4958 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3491.8319 | 0 | 3491.8319 | 0 | 0 | 0 | 0 | 3491.8319
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | Pick-Up Truck |  | 6 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 40 | 150 | 3996.5352 | 1500 | 5646.5352 | 4 | 24 | 100% | 0% | 0% | 100% | 5646.5352 | 0 | 0 | 5646.5352 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1882.1784 | 0 | 1882.1784 | 0 | 0 | 0 | 0 | 1882.1784
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | 8 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 341.8 | 4518 | 34150.3936 | 45180 | 83848.3936 | 30 | 240 | 100% | 0% | 0% | 100% | 83848.3936 | 0 | 0 | 83848.3936 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 27949.4645 | 0 | 27949.4645 | 0 | 0 | 0 | 0 | 27949.4645
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | 3 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 128.175 | 1694.25 | 12806.3976 | 16942.5 | 31443.1476 | 30 | 90 | 100% | 0% | 0% | 100% | 31443.1476 | 0 | 0 | 31443.1476 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10481.0492 | 0 | 10481.0492 | 0 | 0 | 0 | 0 | 10481.0492
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 30 | 30 | 100% | 0% | 0% | 100% | 10481.0492 | 0 | 0 | 10481.0492 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3493.6831 | 0 | 3493.6831 | 0 | 0 | 0 | 0 | 3493.6831
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 1 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 30 | 30 | 100% | 0% | 0% | 100% | 10481.0492 | 0 | 0 | 10481.0492 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3493.6831 | 0 | 3493.6831 | 0 | 0 | 0 | 0 | 3493.6831
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 20 | 40 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Passenger Bus |  | 2 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 20 | 90 | 1998.2676 | 900 | 2988.2676 | 24 | 48 | 100% | 0% | 0% | 100% | 2988.2676 | 0 | 0 | 2988.2676 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 996.0892 | 0 | 996.0892 | 0 | 0 | 0 | 0 | 996.0892
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader | JIS00277 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader | JIS00251 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00727 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01304 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01306 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01308 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00734 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00743 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01353 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Telehandler |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Service Truck F250 |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK, DOUBLE WALLED 2494 LITER |  | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1231.2191 | 0 | 1231.2191 | 0 | 0 | 0 | 0 | 1231.2191
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KENWORTH SERVICE TRUCK TOROMONT ML | HTP021 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER VAC TRUCK | HTP026 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL 4400 FUEL TRUCK | FLT012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KALMAR CONTAINER HANDLER | CNH002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | GROVE RT890E CRANE | CRN001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MASABA PORTABLE CONVEYOR | CRURC2 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 320BL EXCAVATOR CATERPILLAR | EXC007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2008 GEHL LIFT TRUCK | FKT008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRI-DRIVE V.I.N. # 5KJRASD18CPBF7663 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRAS013BPAZ8119 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRASD1XBPAZ8117 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK NO: OHT033 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK NO: OHT028 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK OTH027 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRASD14BPAZ8114 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 40' FLATRACK TOLU 897574-0, STC JET FUEL A1 FS II DRUMS 205 L |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN# 5KJRASD16BPA28115 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | M320F WHEELED EXCAVATOR |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2015 FREIGHTLINER SERVICE TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2004 PETERBILT TANKER TRUCK VIN# 2NPNHD8X24M822016 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 60/30 CENTER CAR BODY W BELLY PLATE |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G BODY |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD18GPHD7176 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD18GPHD7175 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR SNOW PLOW | HTP017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR PLOW TRUCK | HTP028 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP031 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512202 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512402 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 4400 GAL STAINLESS STEEL WATER TANK |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | SEWAGE TANK SERAIL # ST111-0716 |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | WATER TANK SERIAL # WT110-0070 |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | OSHKOSH FIRE TRUCK 1998 -T13000 MILNE | EMG001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GMC C8500 FOUNTAIN TIRE | HTP020 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLOAT TRAILER 20 FT - PINTLE HOOK | LBT004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT WATER TRUCK ML 2013 | HTP001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | WATER TRUCK | HTP002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KENWORTH WATER/METHANOL TRUCK | HTP003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KENWORTH T800 W/ KNUCKLE BOOM 2004 | HTP008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT 367 2014 | HTP012 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT 379 2014 | HTP023 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT ROLL OFF TRUCK | HTP027 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT | JLG001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT Z45/25 | JLG003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT Z60/34 | JLG006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT 450 AJ SERIES | JLG009 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ROLLER CP563E | RLR001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TL1255 | TLH001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER GEHL | TLH006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CAT TELEHANDLER TL1055C | TLH007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MINI-CRAWLER CRANE URW-295 (diesel) | CRN005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-350 SILVER PICK-UP , VIN # 1FTWW3BROAEB22478 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | HYDRAULIC PRESS |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-550 WHITE SERVICE TRUCK XLT FEC061335A |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-550 WHITE SERVICE TRUCK XLT FEC061336A |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2008 KENWORTH MECHANICAL TRUCK VIN# 2NKMHN7XX8M212914 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MOBILE OFFICE ON WHEELS SERIAL # 240073498 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES 533C001 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES 133W003 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES UNIT 833X004 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | STEP DECK 3 AXLES UNIT 5334652 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | JOHN DEREE LIGHT TOWER | ALT032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 AMBULANCE 2014 | EMG008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FOUNTAIN TIRE ATLAS COPCO COMPRESSOR | FCM001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR PD7000 | FKT002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR 2ET4000 | FKT003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT MITSUBISHI FB20PNT | FKT004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR DP40K-D | FKT007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT VALLEE | FKT009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HOTSY MOUNTED ON TRAILER | HTY001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP022 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP023 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2008 | LTP037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP039 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP041 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP042 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP048 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP049 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP050 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP051 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP052 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP053 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP054 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP055 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 - 2011 | LTP061 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 | LTP062 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 2012 | LTP064 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 2012 | LTP065 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 2008 | LTP066 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SERVICE TRUCK FOUNTAIN TIRE 2015 | MTP017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 289C ALL TERRAIN | SKD006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 246 ALL TERRAIN | SKD007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CAT SKID STEER 2622C2 | SKD011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 01 | SKJ001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 02 | SKJ002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 04 | SKJ004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 05 | SKJ005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 06 | SKJ006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/MANLIFT | SKJ007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/SCISSOR LIFT | SKJ008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/MANLIFT | SKJ009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | MANLIFT - CROWN WAVE | SKJ011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKI-DOO 2007 | SNM001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKI-DOO 2008 | SNM002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE KUBOTA RTV900 | SXS002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CATERPILLAR 2620 SKID STEER LOADER C/W BUCKET (BOBCAT) S/N 6555GP113734, VIN # CAT0262DVLST00504 |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENSET RADIATOR |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENSET RADIATOR |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SW-95 IRONWORKER |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SW-95 IRONWORKER |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | KNEE MILL |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | KNEE MILL |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BANDSAW |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BANDSAW |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | LATHE |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 213.625 | 2823.75 | 21343.996 | 28237.5 | 52405.246 | 30 | 150 | 100% | 0% | 0% | 100% | 52405.246 | 0 | 0 | 52405.246 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 17468.4153 | 0 | 17468.4153 | 0 | 0 | 0 | 0 | 17468.4153
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 77.5 | 975 | 7743.287 | 9750 | 18468.287 | 20 | 100 | 100% | 0% | 0% | 100% | 18468.287 | 0 | 0 | 18468.287 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 9234.1435 | 9234.1435 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 037 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - SITE MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 038 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - SITE MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 2143-MO-003 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 039 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-004 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 040 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - PETERBILT 348 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-005 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 041 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - SITE MAINTENANCE SMALL LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 2143-MO-006 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 042 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-007 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 043 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 2143-MO-008 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 044 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MINE/TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-009 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 045 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 046 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-012 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 047 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-013 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 048 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 049 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 2143-MO-015 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 050 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 2143-MO-016 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 051 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-017 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 052 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-018 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 053 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-019 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 054 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Compactor | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE COMPACTOR - CAT CS56 L: 5860, W: 2300, H: 3070, 12250 kg | 2143-MO-020 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Compactor | CS56B | M4M00243 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 055 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-021 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 056 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-022 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 057 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170, W: 2410, H: 3320, 18338 kg | 2143-MO-023 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 058 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW295 | 2143-MO-024 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 059 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FD35N L: 2540, W: 1300, H: 2540, 4800 kg | 2143-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 060 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 2143-MO-026 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 061 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT DP50K L: 3305, W: 1460, H: 2400, 7160 kg | 2143-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - FREIGHTLINER |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 018 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-001 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 019 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 020 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-003 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 021 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-004 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 022 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-005 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 023 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-006 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 024 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-009 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 025 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-010 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 026 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 027 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-012 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 028 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-013 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 029 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 030 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-015 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 031 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-016 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 032 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-017 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 033 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-018 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 034 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-019 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 035 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-020 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Front End Loader |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE RECLAIM FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 064 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 2144-MO-001 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 065 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 2144-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 066 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 2144-MO-003 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 067 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 2144-MO-004 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 068 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER DELIVERY TRUCK - PETERBILT 367 TRI-DRIVE | 2144-MO-005 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 069 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-006 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 070 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-007 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 071 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-008 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 072 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-009 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 073 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-010 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 074 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 075 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 2144-MO-012 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 076 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 2144-MO-013 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 077 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-014 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 078 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-015 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 079 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-016 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 080 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-017 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 081 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-018 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 082 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-019 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 083 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 084 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 085 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 086 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 087 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-031 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 088 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-032 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 089 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 090 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 091 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 092 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 093 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 094 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-038 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - FREIGHT HAUL TRACTOR - WeSTERN STAR 4900 |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER, SEMI DUMP |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 740 | MOBILE EQUIPMENT - WATER TRUCK - CAT 740 (8000 GAL) |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2230 | Causeway | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 099 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Dock Office - Demolish and Decontaminate Building - Trailer - Single | 2223-BLD-001 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 100 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Dock Office - Demolish and foundations - Gravel Base - Skidded Building | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 101 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Dock Office - Demolish floor finish - Raised Steel or Wooden Floor | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2221 | Dock Structure (includes ship loader foundations) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2225 | Mooring Buoys | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2240 | Transshipment and Marine Vessels | 2240 | Transshipment and Marine Vessels | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | CONVEYING - RECLAIM CONVEYOR - FAM L: 850000, W: 1524, H: 47000 VERTICAL LIFT SEE REMARKS kg | 2342-CV-001 | 1 | Ea | 5018.4 | 75276 | 501405.311 | 752760 | 1329441.311 | 5018.4 | 75276 | 501405.311 | 752760 | 1329441.311 | 1020 | 1020 | 100% | 0% | 0% | 100% | 1329441.311 | 0 | 0 | 1329441.311 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 443147.1037 | 443147.1037 | 443147.1037 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | [6 empty] | Shiploading E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Shiploading E-House - Demolish and foundations - Gravel Base - Skidded Building | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Shiploading E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 124 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR DISCHARGE CHUTE - FAM | 2342-CH-015 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 125 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-026 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 126 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-027 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 127 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-028 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 128 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-029 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 137 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-002 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 138 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-003 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 139 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-004 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 140 | HP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | sampler bin | HOPPER - SAMPLER BIN - FAM | 2342-HP-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SAMPLER - ORE SAMPLER - FAM L: N/A, W: N/A, H: N/A | 2342-SA-019 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 130 | MT- |  | #N/A |  |  |  |  | RECLAIM CONVEYOR | 2342-MT-001 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 131 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-023 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 132 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-024 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 133 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-025 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 134 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-030 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 135 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-031 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-032 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | 0.16667 | Ea | 5018.4 | 75276 | 501405.311 | 752760 | 1329441.311 | 836.4 | 12546 | 83567.5518 | 125460 | 221573.5518 | 1020 | 170 | 100% | 0% | 0% | 100% | 221573.5518 | 0 | 0 | 221573.5518 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 73857.8506 | 73857.8506 | 73857.8506 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Jump Conveyor |  | 12 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 230.4 | 2556 | 23020.043 | 25560 | 51136.043 | 1 | 12 | 100% | 0% | 0% | 100% | 51136.043 | 0 | 0 | 51136.043 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 17045.3477 | 0 | 17045.3477 | 0 | 0 | 0 | 0 | 17045.3477
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Cone Crusher |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Modified (2017A) | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Feeder (Small) |  | 3 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 57.6 | 639 | 5755.0107 | 6390 | 12784.0107 | 1 | 3 | 100% | 0% | 0% | 100% | 12784.0107 | 0 | 0 | 12784.0107 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4261.3369 | 0 | 4261.3369 | 0 | 0 | 0 | 0 | 4261.3369
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Screener |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - RECLAIM MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT L: 230000, W: 1524 |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - STOCKPILE RECLAIM EXTENSION CONVEYOR |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 2 | ML-PRO-SHL-010-RFL01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 3 | ML-PRO-SHL-010-RFL03 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 4 | ML-PRO-SHL-010-RFL04 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd Party Contractor | Medium Equipment on 2017 Sea Lift |  | 93 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1785.6 | 19809 | 178405.333 | 198090 | 396304.333 | 1 | 93 | 100% | 0% | 0% | 100% | 396304.333 | 0 | 0 | 396304.333 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 132101.4443 | 0 | 132101.4443 | 0 | 0 | 0 | 0 | 132101.4443
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Contractor | Heavy equipment on 2017 Sea Lift |  | 6 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 1008 | 13320 | 100712.688 | 133200 | 247232.688 | 56 | 336 | 100% | 0% | 0% | 100% | 247232.688 | 0 | 0 | 247232.688 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 82410.896 | 0 | 82410.896 | 0 | 0 | 0 | 0 | 82410.896
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | -0.16667 | Ea | 5018.4 | 75276 | 501405.311 | 752760 | 1329441.311 | -836.4 | -12546 | -83567.5518 | -125460 | -221573.5518 | 1020 | -170 | 100% | 0% | 0% | 100% | -221573.5518 | 0 | 0 | -221573.5518 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -73857.8506 | -73857.8506 | -73857.8506 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown |  | 230545.88 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 2925.5998 | 33717.3349 | 292559.9768 | 91421.8957 | 417699.2074 | 0 | 0 | 100% | 0% | 0% | 100% | 417699.2074 | 0 | 0 | 417699.2074 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 139233.0691 | 139233.0691 | 139233.0691 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Footprints |  | 128865.8 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1635.2917 | 18846.6233 | 163529.1659 | 51101.1332 | 233476.9224 | 0 | 0 | 100% | 0% | 0% | 100% | 233476.9224 | 0 | 0 | 233476.9224 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 77825.6408 | 77825.6408 | 77825.6408 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 107 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-001 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 108 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-002 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 109 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-003 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 110 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-004 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 111 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-005 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 112 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-006 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - FINES STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-003 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 115 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-004 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 116 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-005 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 117 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-006 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 118 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-007 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 119 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - FINES STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-008 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion |  | 82000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1040.5702 | 11992.5 | 104057.0237 | 32516.7184 | 148566.242 | 0 | 0 | 100% | 0% | 0% | 100% | 148566.242 | 0 | 0 | 148566.242 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 49522.0807 | 49522.0807 | 49522.0807 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown - Realignment of the shipload conveyor |  | 26000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 329.9369 | 3802.5 | 32993.6904 | 10310.179 | 47106.3694 | 0 | 0 | 100% | 0% | 0% | 100% | 47106.3694 | 0 | 0 | 47106.3694 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15702.1231 | 15702.1231 | 15702.1231 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd party Equipment | Apron Feeder (TK) |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd party Equipment | Hopper (TK) |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional sealift laydown area |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Settling Ponds |  | 11423.76 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 508.2417 | 2034.0005 | 50824.1722 | 8162.7945 | 61020.9672 | 0 | 0 | 100% | 0% | 0% | 100% | 61020.9672 | 0 | 0 | 61020.9672 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20340.3224 | 20340.3224 | 20340.3224 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | VP6 | VENDOR PKG - Ship Loader | VP6 | Packaged Facilities | Ship Loader |  | Shiploader Package | 2351-SL-001 | 0 | Lot | 14448 | 216720 | 1443548.528 | 2167200 | 3827468.528 | 0 | 0 | 0 | 0 | 0 | 30295 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and Decontaminate Building - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and foundations - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish floor finish - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and Decontaminate Building - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and foundations - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish floor finish - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 152 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER PROPORTIONAL GATE - FAM | 2351-CH-003 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 153 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-004 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 154 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-005 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 155 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-006 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 156 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE - FAM | 2351-CH-008 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 157 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-009 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 158 | CV- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CONVEYING - SHIPLOADER LINK CONVEYOR - FAM 212330 kg | 2351-CV-007 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 159 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DRIVE | 2351-MT-007A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 160 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR BRAKE | 2351-MT-007B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 161 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE | 2351-MT-007C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 162 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN | 2351-MT-007D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 163 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR | 2351-MT-007E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 164 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 165 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 166 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM 1960000 kg | 2351-SL-001 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 167 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-001A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 170 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-001B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 171 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-001C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 172 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 173 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 174 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 175 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 176 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-001H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 177 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-001J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 178 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-001K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 179 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE FAN | 2351-MT-001L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 180 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-001M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 181 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-001N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 182 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 183 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 184 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 185 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 186 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 187 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 193 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM | 2351-SL-002 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 194 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-002A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 197 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-002B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 198 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-002C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 199 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 200 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 201 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 202 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 203 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-002H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 204 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-002J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 205 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-002K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 206 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE BRAKE | 2351-MT-002L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 207 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-002M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 208 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-002N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 209 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 210 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 211 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 212 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 213 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 214 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 168 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-001AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 169 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-001AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 188 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-001V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 189 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-001W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 190 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-001X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 191 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-001Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 192 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-001Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 195 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-002AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 196 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-002AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 215 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-002V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 216 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-002W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 217 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-002X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 218 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-002Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 219 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-002Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome
2000 | Milne Port | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2430 | Aerodrome Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2435 | Field Electrical Centre | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 237 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-001 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 240 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-002 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 243 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-003 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 246 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-004 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 238 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BA - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 239 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BA - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 241 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BB - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 242 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BB - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 244 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BC - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 245 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BC - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 247 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BD - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 248 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BD - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Offices, washcars for Laydown R3 62 @ 15m2 3 @ 30m2 3 @ 66m2 |  | 1218 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 273.035 | 4095.525 | 27279.85 | 40955.25 | 72330.625 | 1 | 1218 | 100% | 0% | 0% | 100% | 72330.625 | 0 | 0 | 72330.625 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24110.2083 | 24110.2083 | 24110.2083 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-005 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BE - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BE - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-006 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BF - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BF - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Pre-Cast Concrete Foundations (Mobilized to Site) |  | 8000 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 1000 | 15000 | 99913.381 | 150000 | 264913.381 | 0 | 0 | 100% | 0% | 0% | 100% | 264913.381 | 0 | 0 | 264913.381 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 88304.4603 | 88304.4603 | 88304.4603 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 48.42 | 726.3 | 4837.8059 | 7263 | 12827.1059 | 1 | 216 | 100% | 0% | 0% | 100% | 12827.1059 | 0 | 0 | 12827.1059 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4275.702 | 4275.702 | 4275.702 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 380 person camp at Milne Port |  | 380 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 266304.3455 | 0 | 0 | 266304.3455 | 0 | 0 | 100% | 0% | 0% | 1 | 266304.3455 | 0 | 0 | 266304.3455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 266304.3455 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 380 man temporary hardwall camp at Milne Port inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 10,720 m2) |  | 10720 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 2403.0667 | 36046 | 240098.5153 | 360460 | 636604.5153 | 1 | 10720 | 100% | 0% | 0% | 100% | 636604.5153 | 0 | 0 | 636604.5153 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 212201.5051 | 212201.5051 | 212201.5051 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Offices, washcars (assume 16 units @ 36 m2 per wash car) |  | 576 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 129.12 | 1936.8 | 12900.8157 | 19368 | 34205.6157 | 1 | 576 | 100% | 0% | 0% | 100% | 34205.6157 | 0 | 0 | 34205.6157 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11401.8719 | 11401.8719 | 11401.8719 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2510 | Accommodations Area | 225 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 2510-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2513-BLD-002 | 278.8104 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 43.75 | 656.25 | 4371.2104 | 6562.5 | 11589.9604 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 11589.9604 | 0 | 0 | 11589.9604 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3863.3201 | 3863.3201 | 3863.3201 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 254 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 2513-BLD-002 | 278.8104 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 40.485 | 607.2755 | 4044.9964 | 6072.7548 | 10725.0267 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 10725.0267 | 0 | 0 | 10725.0267 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3575.0089 | 3575.0089 | 3575.0089 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 255 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 2513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 34.8513 | 522.7695 | 3482.1113 | 5227.6952 | 9232.576 | 0 | 0 | 100% | 0% | 0% | 100% | 9232.576 | 0 | 0 | 9232.576 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3077.5253 | 3077.5253 | 3077.5253 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 265 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2513-TK-003 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2513-BLD-001 | 89.2193 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 20 | 300 | 1998.2676 | 3000 | 5298.2676 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 5298.2676 | 0 | 0 | 5298.2676 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1766.0892 | 1766.0892 | 1766.0892 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 267 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 2513-TK-023 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 266 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613, W: 737, H: 1676 | 2513-TK-004 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 251 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 2513-BLD-001 | 89.2193 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 11 | 105 | 699.3937 | 1050 | 1854.3937 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1854.3937 | 0 | 0 | 1854.3937 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 618.1312 | 618.1312 | 618.1312 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 258 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2513-PP-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 259 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2513-MT-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 260 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 261 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 262 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 263 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 264 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 2513-SQ-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 2513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 256 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg | 2513-MO-001 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 257 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Fire Truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH T1500 L: 10540, W: 3100, H: 3810, 16500 kg | 2513-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 227 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 1388.4758 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 311.25 | 4668.75 | 31098.0398 | 46687.5 | 82454.2898 | 1 | 1388.4758 | 100% | 0% | 0% | 100% | 82454.2898 | 0 | 0 | 82454.2898 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 27484.7633 | 27484.7633 | 27484.7633 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 233 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-003 | 423.7918 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 95 | 1425 | 9491.7712 | 14250 | 25166.7712 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 25166.7712 | 0 | 0 | 25166.7712 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8388.9237 | 8388.9237 | 8388.9237 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 230 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-002 | 334.5725 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 75 | 1125 | 7493.5036 | 11250 | 19868.5036 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 19868.5036 | 0 | 0 | 19868.5036 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6622.8345 | 6622.8345 | 6622.8345 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 231 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 232 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 234 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 235 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 228 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 229 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Change Rooms - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-004 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Change Rooms - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Change Rooms - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-005 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-006 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad development (Milne Port) |  | 45000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 571.0446 | 6581.25 | 57104.4642 | 17844.5406 | 81530.2548 | 0 | 0 | 100% | 0% | 0% | 100% | 81530.2548 | 0 | 0 | 81530.2548 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 27176.7516 | 27176.7516 | 27176.7516 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash (Repurposed Warehouse) - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2523-BLD-001 | 0 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash (Repurposed Warehouse) - Demolish and foundations - Precast Footing (Perimeter Beam) | 2523-BLD-001 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash (Repurposed Warehouse) - Demolish floor finish - Gravel | 2523-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | 150000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1903.4821 | 21937.5 | 190348.2141 | 59481.8019 | 271767.5159 | 0 | 0 | 100% | 0% | 0% | 100% | 271767.5159 | 0 | 0 | 271767.5159 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 90589.172 | 90589.172 | 90589.172 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | -150000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | -1903.4821 | -21937.5 | -190348.2141 | -59481.8019 | -271767.5159 | 0 | 0 | 100% | 0% | 0% | 100% | -271767.5159 | 0 | 0 | -271767.5159 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -90589.172 | -90589.172 | -90589.172 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W1 |  | 23100 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 293.1362 | 3378.375 | 29313.625 | 9160.1975 | 41852.1975 | 0 | 0 | 100% | 0% | 0% | 100% | 41852.1975 | 0 | 0 | 41852.1975 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13950.7325 | 13950.7325 | 13950.7325 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W6 |  | 2750 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 34.8972 | 402.1875 | 3489.7173 | 1090.4997 | 4982.4045 | 0 | 0 | 100% | 0% | 0% | 100% | 4982.4045 | 0 | 0 | 4982.4045 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1660.8015 | 1660.8015 | 1660.8015 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W7 |  | 1780 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 22.588 | 260.325 | 2258.7988 | 705.8507 | 3224.9745 | 0 | 0 | 100% | 0% | 0% | 100% | 3224.9745 | 0 | 0 | 3224.9745 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1074.9915 | 1074.9915 | 1074.9915 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W3 |  | 14300 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 181.4653 | 2091.375 | 18146.5297 | 5670.5984 | 25908.5032 | 0 | 0 | 100% | 0% | 0% | 100% | 25908.5032 | 0 | 0 | 25908.5032 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8636.1677 | 8636.1677 | 8636.1677 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W14 |  | 8850 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 112.3054 | 1294.3125 | 11230.5446 | 3509.4263 | 16034.2834 | 0 | 0 | 100% | 0% | 0% | 100% | 16034.2834 | 0 | 0 | 16034.2834 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5344.7611 | 5344.7611 | 5344.7611 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W15 |  | 10950 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 138.9542 | 1601.4375 | 13895.4196 | 4342.1715 | 19839.0287 | 0 | 0 | 100% | 0% | 0% | 100% | 19839.0287 | 0 | 0 | 19839.0287 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6613.0096 | 6613.0096 | 6613.0096 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W10B |  | 12450 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 157.989 | 1820.8125 | 15798.9018 | 4936.9896 | 22556.7038 | 0 | 0 | 100% | 0% | 0% | 100% | 22556.7038 | 0 | 0 | 22556.7038 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7518.9013 | 7518.9013 | 7518.9013 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W11 |  | 7550 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 95.8086 | 1104.1875 | 9580.8601 | 2993.9174 | 13678.965 | 0 | 0 | 100% | 0% | 0% | 100% | 13678.965 | 0 | 0 | 13678.965 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4559.655 | 4559.655 | 4559.655 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 270 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-001 | 892.1933 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 500 | 2100 | 49956.6905 | 75000 | 127056.6905 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 127056.6905 | 0 | 0 | 127056.6905 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 42352.2302 | 42352.2302 | 42352.2302 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 276 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2521-BLD-003 | 267.658 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 150 | 900 | 14987.0071 | 22500 | 38387.0071 | 1 | 267.658 | 100% | 0% | 0% | 100% | 38387.0071 | 0 | 0 | 38387.0071 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12795.669 | 12795.669 | 12795.669 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 271 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-001 | 892.1933 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 129.5521 | 1943.2815 | 12943.9886 | 19432.8154 | 34320.0855 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 34320.0855 | 0 | 0 | 34320.0855 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11440.0285 | 11440.0285 | 11440.0285 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 272 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-001 | 892.1933 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 111.5242 | 1672.8625 | 11142.7562 | 16728.6245 | 29544.2432 | 0 | 0 | 100% | 0% | 0% | 100% | 29544.2432 | 0 | 0 | 29544.2432 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9848.0811 | 9848.0811 | 9848.0811 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 273 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-002 | 148.6989 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 83.3333 | 350 | 8326.1151 | 12500 | 21176.1151 | 1 | 148.6989 | 100% | 0% | 0% | 100% | 21176.1151 | 0 | 0 | 21176.1151 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7058.705 | 7058.705 | 7058.705 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 296 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 2521.5-P | 255 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 63.75 | 956.25 | 6369.478 | 9562.5 | 16888.228 | 0.01 | 2.55 | 100% | 0% | 100% | 0% | 16888.228 | 0 | 16888.228 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5629.4093 | 5629.4093 | 5629.4093 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 295 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2521-TK-053 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 2521-BLD-004 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 294 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803, W: 1245, H: 1346 | 2521-TK-050 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 280 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-004 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 274 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-002 | 148.6989 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 21.592 | 323.8803 | 2157.3314 | 3238.8026 | 5720.0143 | 0.75 | 111.5242 | 100% | 0% | 0% | 100% | 5720.0143 | 0 | 0 | 5720.0143 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1906.6714 | 1906.6714 | 1906.6714 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 277 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-003 | 267.658 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 33 | 315 | 2098.181 | 3150 | 5563.181 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5563.181 | 0 | 0 | 5563.181 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1854.3937 | 1854.3937 | 1854.3937 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 290 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2521-PP-051 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 275 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade | 2521-BLD-002 | 148.6989 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 18.5874 | 278.8104 | 1857.126 | 2788.1041 | 4924.0405 | 0 | 0 | 100% | 0% | 0% | 100% | 4924.0405 | 0 | 0 | 4924.0405 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1641.3468 | 1641.3468 | 1641.3468 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 292 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-005 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 293 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-013 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 281 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 282 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 283 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 284 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 285 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 286 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 287 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 288 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 289 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 291 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2521-MT-051 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 278 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-003 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Anmar Workshop |  | 1670 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 74.2981 | 297.3435 | 7429.8101 | 1193.2907 | 8864.8532 | 0 | 0 | 100% | 0% | 0% | 100% | 8864.8532 | 0 | 0 | 8864.8532 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2954.9511 | 2954.9511 | 2954.9511 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-005 | 0 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-005 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-005 | 0 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-006 | 0 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2- Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-006 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2- Demolish floor finish - Slab on grade | 2521-BLD-006 | 0 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 91.0263 | 364.2903 | 9102.6296 | 1461.9598 | 10928.8797 | 0 | 0 | 100% | 0% | 0% | 100% | 10928.8797 | 0 | 0 | 10928.8797 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3642.9599 | 3642.9599 | 3642.9599 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 301 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 2522-SQ-004 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 306 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 2522-SQ-011 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 313 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-026 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 314 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-027 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 300 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 2522-SQ-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 2522-SQ-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 303 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 2522-SQ-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 304 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-009 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 305 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 307 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 2522-SQ-012 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 308 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 2522-SQ-014 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 309 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 2522-SQ-018 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 310 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 2522-SQ-022 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 311 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-023 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 312 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-025 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 315 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 2522-SQ-028 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 316 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-029 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-029 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 318 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-030 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 319 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-030 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 320 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 2522-SQ-033 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 321 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 2522-SQ-034 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 322 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584, W: 864, H: 1120, 110 kg | 2522-SQ-037 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 323 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-038 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 324 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-039 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 325 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 2522-SQ-040 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Light Plant |  | 10 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 81 | 1065 | 8092.9839 | 10650 | 19807.9839 | 0.5 | 5 | 100% | 0% | 0% | 100% | 19807.9839 | 0 | 0 | 19807.9839 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6602.6613 | 0 | 6602.6613 | 0 | 0 | 0 | 0 | 6602.6613
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Frost Fighter Heater |  | 10 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 81 | 1065 | 8092.9839 | 10650 | 19807.9839 | 0.5 | 5 | 100% | 0% | 0% | 100% | 19807.9839 | 0 | 0 | 19807.9839 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6602.6613 | 0 | 6602.6613 | 0 | 0 | 0 | 0 | 6602.6613
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson extreme cold BT400NEX-D4A |  | 10 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 192 | 2130 | 19183.3691 | 21300 | 42613.3691 | 1 | 10 | 100% | 0% | 0% | 100% | 42613.3691 | 0 | 0 | 42613.3691 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 14204.4564 | 0 | 14204.4564 | 0 | 0 | 0 | 0 | 14204.4564
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | 400,000 BTU Indirect Fired Diesel Heater |  | 18 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 145.8 | 1917 | 14567.3709 | 19170 | 35654.3709 | 0.5 | 9 | 100% | 0% | 0% | 100% | 35654.3709 | 0 | 0 | 35654.3709 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 11884.7903 | 0 | 11884.7903 | 0 | 0 | 0 | 0 | 11884.7903
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Welding machines 400-500 amps |  | 8 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 153.6 | 1704 | 15346.6953 | 17040 | 34090.6953 | 1 | 8 | 100% | 0% | 0% | 100% | 34090.6953 | 0 | 0 | 34090.6953 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 11363.5651 | 0 | 11363.5651 | 0 | 0 | 0 | 0 | 11363.5651
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Power Pack 5/10 gallon per minute |  | 10 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 81 | 1065 | 8092.9839 | 10650 | 19807.9839 | 0.5 | 5 | 100% | 0% | 0% | 100% | 19807.9839 | 0 | 0 | 19807.9839 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6602.6613 | 0 | 6602.6613 | 0 | 0 | 0 | 0 | 6602.6613
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generator +/- 15-20kw |  | 4 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 76.8 | 852 | 7673.3477 | 8520 | 17045.3477 | 1 | 4 | 100% | 0% | 0% | 100% | 17045.3477 | 0 | 0 | 17045.3477 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5681.7826 | 0 | 5681.7826 | 0 | 0 | 0 | 0 | 5681.7826
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson 6700 |  | 4 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 76.8 | 852 | 7673.3477 | 8520 | 17045.3477 | 1 | 4 | 100% | 0% | 0% | 100% | 17045.3477 | 0 | 0 | 17045.3477 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5681.7826 | 0 | 5681.7826 | 0 | 0 | 0 | 0 | 5681.7826
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson 6700 all in one |  | 3 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 57.6 | 639 | 5755.0107 | 6390 | 12784.0107 | 1 | 3 | 100% | 0% | 0% | 100% | 12784.0107 | 0 | 0 | 12784.0107 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4261.3369 | 0 | 4261.3369 | 0 | 0 | 0 | 0 | 4261.3369
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Clipping machine |  | 6 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 48.6 | 639 | 4855.7903 | 6390 | 11884.7903 | 0.5 | 3 | 100% | 0% | 0% | 100% | 11884.7903 | 0 | 0 | 11884.7903 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3961.5968 | 0 | 3961.5968 | 0 | 0 | 0 | 0 | 3961.5968
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson Flagro-1000 trailer mount |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | 55KW Generator |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generators 60+kw |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generators 135kw (shipment 2017) |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Engine System for mobile trolly movement |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Heater (Flagro) |  | 4 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 32.4 | 426 | 3237.1935 | 4260 | 7923.1935 | 0.5 | 2 | 100% | 0% | 0% | 100% | 7923.1935 | 0 | 0 | 7923.1935 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2641.0645 | 0 | 2641.0645 | 0 | 0 | 0 | 0 | 2641.0645
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Air compressor |  | 4 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 32.4 | 426 | 3237.1935 | 4260 | 7923.1935 | 0.5 | 2 | 100% | 0% | 0% | 100% | 7923.1935 | 0 | 0 | 7923.1935 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2641.0645 | 0 | 2641.0645 | 0 | 0 | 0 | 0 | 2641.0645
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Generator 114 kW |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Generator 150 kVA, Generator 250 kVA, Generator 30 kVA, Generator 100 kVA |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | 7m3/min / 250cft/min mobile compressors, set of 50 mm PVC perforated tubes |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Oxy fuel cutting systems, induction heating system, 400A welding generators, welding sets, 7m3/min / 250cft/min mobile compressors |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Heater | Frost Fighter Heater | ML-FAC-POH-010 | 38 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 307.8 | 4047 | 30753.3387 | 40470 | 75270.3387 | 0.5 | 19 | 100% | 0% | 0% | 100% | 75270.3387 | 0 | 0 | 75270.3387 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 25090.1129 | 0 | 25090.1129 | 0 | 0 | 0 | 0 | 25090.1129
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd Party Contractor | Light equipment 2017 Sea Lift |  | 14 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 113.4 | 1491 | 11330.1774 | 14910 | 27731.1774 | 0.5 | 7 | 100% | 0% | 0% | 100% | 27731.1774 | 0 | 0 | 27731.1774 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 9243.7258 | 0 | 9243.7258 | 0 | 0 | 0 | 0 | 9243.7258
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 351 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-009 | 75.2788 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 42.1875 | 253.125 | 4215.0958 | 6328.125 | 10796.3458 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 10796.3458 | 0 | 0 | 10796.3458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3598.7819 | 3598.7819 | 3598.7819 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 354 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-010 | 75.2788 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 42.1875 | 253.125 | 4215.0958 | 6328.125 | 10796.3458 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 10796.3458 | 0 | 0 | 10796.3458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3598.7819 | 3598.7819 | 3598.7819 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 327 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-001 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 330 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-002 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 333 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-003 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 336 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-004 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 339 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-005 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 342 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-006 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 345 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-007 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 348 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-008 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 357 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 2530-BLD-011 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1421.741 | 1421.741 | 1421.741 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 358 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 359 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 328 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 329 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 331 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 332 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 334 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 335 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 337 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 338 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 340 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 341 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 343 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 344 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 346 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 347 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 349 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 350 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 352 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 353 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 355 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 356 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-002 | 56 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 8.7873 | 131.81 | 877.9722 | 1318.1 | 2327.8822 | 1 | 56 | 100% | 0% | 0% | 100% | 2327.8822 | 0 | 0 | 2327.8822 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 775.9607 | 775.9607 | 775.9607 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-002 | 56 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 8.1316 | 121.9733 | 812.451 | 1219.733 | 2154.1574 | 0.75 | 42 | 100% | 0% | 0% | 100% | 2154.1574 | 0 | 0 | 2154.1574 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 718.0525 | 718.0525 | 718.0525 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-001 | 20 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 4.4833 | 67.25 | 447.945 | 672.5 | 1187.695 | 1 | 20 | 100% | 0% | 0% | 100% | 1187.695 | 0 | 0 | 1187.695 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 395.8983 | 395.8983 | 395.8983 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical office - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical office - Demolish floor finish - Gravel | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 2530-BLD-BIM-002 | 56 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 361 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2540-BLD-001 | 446.0967 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 250 | 1050 | 24978.3452 | 37500 | 63528.3452 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 63528.3452 | 0 | 0 | 63528.3452 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 21176.1151 | 21176.1151 | 21176.1151 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 362 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2540-BLD-001 | 446.0967 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 64.7761 | 971.6408 | 6471.9943 | 9716.4077 | 17160.0428 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 17160.0428 | 0 | 0 | 17160.0428 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5720.0143 | 5720.0143 | 5720.0143 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 363 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 2540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 55.7621 | 836.4312 | 5571.3781 | 8364.3123 | 14772.1216 | 0 | 0 | 100% | 0% | 0% | 100% | 14772.1216 | 0 | 0 | 14772.1216 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4924.0405 | 4924.0405 | 4924.0405 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2540-VP-001 | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 9975.9289 | 0 | 0 | 9975.9289 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 364 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 52.0446 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1667 | 175 | 2914.1403 | 4375 | 7464.1403 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 7464.1403 | 0 | 0 | 7464.1403 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2488.0468 | 2488.0468 | 2488.0468 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 374 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2540-TK-003 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 371 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 2540-SQ-002 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 367 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 368 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 369 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 370 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 372 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 2540-SQ-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 373 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG - OHAVX32XW10000X | 2540-SQ-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 365 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 366 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 9975.9289 | 0 | 0 | 9975.9289 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 12933 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 575.3876 | 2302.7206 | 57538.763 | 9241.215 | 69082.6986 | 0 | 0 | 100% | 0% | 0% | 100% | 69082.6986 | 0 | 0 | 69082.6986 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 23027.5662 | 23027.5662 | 23027.5662 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm at Milne Inlet - New waste management building |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Future Hazardous Waste Berm |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Hazardous Waste Berm |  | 0 | m2 | 0.0318 | 0.0318 | 3.18 | 0.318 | 3.498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Snow Dump |  | 3189 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 141.8782 | 567.8014 | 14187.823 | 2278.6851 | 16928.1539 | 0 | 0 | 100% | 0% | 0% | 100% | 16928.1539 | 0 | 0 | 16928.1539 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5642.718 | 5642.718 | 5642.718 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-1 | 2000 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 88.9798 | 356.1 | 8897.9762 | 1429.0907 | 10616.5907 | 0 | 0 | 100% | 0% | 0% | 100% | 10616.5907 | 0 | 0 | 10616.5907 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3538.8636 | 3538.8636 | 3538.8636 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-3 | 678 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 30.1641 | 120.7179 | 3016.4139 | 484.4617 | 3599.0242 | 0 | 0 | 100% | 0% | 0% | 100% | 3599.0242 | 0 | 0 | 3599.0242 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1199.6747 | 1199.6747 | 1199.6747 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-5 | 652 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 29.0074 | 116.0886 | 2900.7402 | 465.8836 | 3461.0086 | 0 | 0 | 100% | 0% | 0% | 100% | 3461.0086 | 0 | 0 | 3461.0086 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1153.6695 | 1153.6695 | 1153.6695 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-4 | 597 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 26.5605 | 106.2958 | 2656.0459 | 426.5836 | 3169.0523 | 0 | 0 | 100% | 0% | 0% | 100% | 3169.0523 | 0 | 0 | 3169.0523 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1056.3508 | 1056.3508 | 1056.3508 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-2 | 272 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 12.1012 | 48.4296 | 1210.1248 | 194.3563 | 1443.8563 | 0 | 0 | 100% | 0% | 0% | 100% | 1443.8563 | 0 | 0 | 1443.8563 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 481.2854 | 481.2854 | 481.2854 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-6 | 34 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 1.5127 | 6.0537 | 151.2656 | 24.2945 | 180.482 | 0 | 0 | 100% | 0% | 0% | 100% | 180.482 | 0 | 0 | 180.482 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 60.1607 | 60.1607 | 60.1607 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 398 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-001 | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 85734.0755 | 85734.0755 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 399 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-002 | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 85734.0755 | 85734.0755 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 400 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-003 | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 85734.0755 | 85734.0755 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 401 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-004 | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 85734.0755 | 85734.0755 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 402 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-005 | 1 | Ea | 418.6 | 5865 | 41823.7413 | 58650 | 106338.7413 | 418.6 | 5865 | 41823.7413 | 58650 | 106338.7413 | 80 | 80 | 100% | 0% | 0% | 100% | 106338.7413 | 0 | 0 | 106338.7413 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 53169.3706 | 53169.3706 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 403 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-006 | 1 | Ea | 418.6 | 5865 | 41823.7413 | 58650 | 106338.7413 | 418.6 | 5865 | 41823.7413 | 58650 | 106338.7413 | 80 | 80 | 100% | 0% | 0% | 100% | 106338.7413 | 0 | 0 | 106338.7413 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 53169.3706 | 53169.3706 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 387 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-014 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2132.6115 | 2132.6115 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 384 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-013 | 14.8699 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 8.3333 | 50 | 832.6115 | 1250 | 2132.6115 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 2132.6115 | 0 | 0 | 2132.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1066.3058 | 1066.3058 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 390 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - EXISTING DIESEL FUEL DISPENSING MODULE | 2613-FD-013 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 391 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 2613-FD-014 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 392 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.1 | 2613-PP-007 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 393 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.2 | 2613-PP-008 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 394 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.3 | 2613-PP-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 395 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.4 | 2613-PP-010 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 396 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.5 | 2613-PP-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 397 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.6 | 2613-PP-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 386 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-013 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 385 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-013 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 389 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-014 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 388 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-014 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 85.45 | 1129.5 | 8537.5984 | 11295 | 20962.0984 | 30 | 60 | 100% | 0% | 0% | 100% | 20962.0984 | 0 | 0 | 20962.0984 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6987.3661 | 0 | 6987.3661 | 0 | 0 | 0 | 0 | 6987.3661
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Diesel Module | Diesel Module | ML-FUM-FDI-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 15ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 57156.0503 | 0 | 57156.0503 | 0 | 0 | 0 | 0 | 57156.0503
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 3ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 679.4 | 9417 | 67881.151 | 94170 | 171468.151 | 160 | 160 | 100% | 0% | 0% | 100% | 171468.151 | 0 | 0 | 171468.151 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 57156.0503 | 0 | 57156.0503 | 0 | 0 | 0 | 0 | 57156.0503
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Farm Berm |  | 25393 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 1129.7315 | 4521.2236 | 112973.1547 | 18144.45 | 135638.8283 | 0 | 0 | 100% | 0% | 0% | 100% | 135638.8283 | 0 | 0 | 135638.8283 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 67819.4141 | 67819.4141 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 413 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-007 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 414 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-008 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 415 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-009 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-010 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 405 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2614-FD-011 | 14.8699 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 8.3333 | 50 | 832.6115 | 1250 | 2132.6115 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 2132.6115 | 0 | 0 | 2132.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1066.3058 | 1066.3058 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 408 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - JET-A1 FUEL DISPENSING MODULE | 2614-FD-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 409 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 410 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 411 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 412 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 407 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Jet-A1 Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2614-FD-011 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 406 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Jet-A1 Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2614-FD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet A1 Module | Jet A1 Module | ML-FUM-FDI-020 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | Additional 750 kL Jet-A Tank at Milne Port |  | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 418 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 17.7083 | 74.375 | 1769.2995 | 2656.25 | 4499.9245 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 4499.9245 | 0 | 0 | 4499.9245 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1499.9748 | 1499.9748 | 1499.9748 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 419 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 17.7083 | 74.375 | 1769.2995 | 2656.25 | 4499.9245 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 4499.9245 | 0 | 0 | 4499.9245 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1499.9748 | 1499.9748 | 1499.9748 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 420 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Marine Manifold Building - Demolish floor finish - Raised Steel or Wooden Floor | 2615-BLD-001 | 31.5985 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 380 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 381 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 422 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 423 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-002 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 424 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 425 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 426 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 427 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 428 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-007 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2616 | Weatherhaven camp |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Weatherhaven genset fuel bladder berm |  | 500 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 22.2449 | 89.025 | 2224.494 | 357.2727 | 2654.1477 | 0 | 0 | 100% | 0% | 0% | 100% | 2654.1477 | 0 | 0 | 2654.1477 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 884.7159 | 884.7159 | 884.7159 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Port Site |  | 3500 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 350 | 5250 | 34969.6833 | 52500 | 92719.6833 | 0.01 | 35 | 100% | 0% | 0% | 100% | 92719.6833 | 0 | 0 | 92719.6833 | Type B Construction 2BC-MRY1416 |  | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 30906.5611 | 30906.5611 | 30906.5611 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | E-House |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
2000 | Milne Port | 2700 | Site Utilities | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 50,000 L Portable Fuel Dispensing Unit |  | 1364 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 60.6842 | 242.8602 | 6068.4198 | 974.6399 | 7285.9198 | 0 | 0 | 100% | 0% | 0% | 100% | 7285.9198 | 0 | 0 | 7285.9198 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2428.6399 | 2428.6399 | 2428.6399 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Water Tank Main Unit |  | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 0 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1074.1647 | 1074.1647 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 431 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2720-BLD-001 | 390.3346 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 61.25 | 918.75 | 6119.6946 | 9187.5 | 16225.9446 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 16225.9446 | 0 | 0 | 16225.9446 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5408.6482 | 5408.6482 | 5408.6482 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 432 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2720-BLD-001 | 390.3346 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 56.679 | 850.1857 | 5662.995 | 8501.8567 | 15015.0374 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 15015.0374 | 0 | 0 | 15015.0374 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5005.0125 | 5005.0125 | 5005.0125 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE VENDOR PACKAGE | 2720-VP-020 | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9975.9289 | 0 | 9975.9289 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 448 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 2720-TK-001 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 449 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 2720-TK-007 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 450 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 2720-TK-008 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 451 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 2720-TK-011 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 452 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2720-TK-033 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 434 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 435 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 436 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 2720-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 437 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 2720-PP-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 438 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 2720-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 439 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 2720-PP-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 440 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 2720-PP-010 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 441 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 2720-PP-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 442 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 2720-PP-013 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 443 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER UNLOADING PUMP - HAYWARD GORDON S-3 | 2720-PP-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 444 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-031 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 445 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-031 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 446 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-032 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 447 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-032 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 433 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 2720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - POTABLE WATER STORAGE TANK (20 m3) |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - RAW WATER TANK (25 m3) |  | 0 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9975.9289 | 0 | 9975.9289 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 4180 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 185.9677 | 744.249 | 18596.7702 | 2986.7995 | 22188.6745 | 0 | 0 | 100% | 0% | 0% | 100% | 22188.6745 | 0 | 0 | 22188.6745 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7396.2248 | 7396.2248 | 7396.2248 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond #3 |  |  | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 4260 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 189.5269 | 758.493 | 18952.6893 | 3043.9632 | 22613.3382 | 0 | 0 | 100% | 0% | 0% | 100% | 22613.3382 | 0 | 0 | 22613.3382 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7537.7794 | 7537.7794 | 7537.7794 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 459 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 178.4387 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 100 | 600 | 9991.3381 | 15000 | 25591.3381 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 25591.3381 | 0 | 0 | 25591.3381 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 12795.669 | 12795.669 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 468 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 2731.2-P | 258 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 64.5 | 967.5 | 6444.4131 | 9675 | 17086.9131 | 0.01 | 2.58 | 100% | 0% | 100% | 0% | 17086.9131 | 0 | 17086.9131 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8543.4565 | 8543.4565 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 2731-VP-005 | 1 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 11035.5824 | 0 | 11035.5824 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5517.7912 | 5517.7912 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 456 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 2731-BLD-001 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2132.6115 | 2132.6115 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 465 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - TREATED EFFLUENT TANK | 2731-TK-002 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Added | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 462 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 2731-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 463 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 2731-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 464 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 2731-SC-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 457 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 458 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 467 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 2731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 460 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 461 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 11035.5824 | 0 | 11035.5824 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5517.7912 | 5517.7912 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 470 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2732-BLD-001 | 55.7621 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 31.25 | 131.25 | 3122.2932 | 4687.5 | 7941.0432 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 7941.0432 | 0 | 0 | 7941.0432 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3970.5216 | 3970.5216 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 477 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2732-TK-003 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 471 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2732-BLD-001 | 55.7621 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 8.097 | 121.4551 | 808.9993 | 1214.551 | 2145.0053 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 2145.0053 | 0 | 0 | 2145.0053 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1072.5027 | 1072.5027 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 473 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 474 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 475 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 476 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 472 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 2732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 480 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to effluent pond and ocean discharge | 2734.1-P | 2595 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 648.75 | 9731.25 | 64818.8059 | 97312.5 | 171862.5559 | 0.01 | 25.95 | 100% | 0% | 100% | 0% | 171862.5559 | 0 | 171862.5559 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 57287.5186 | 57287.5186 | 57287.5186 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 479 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to effluent pond and ocean discharge | 2734.1-E | 1330 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 498 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV - Electrical distribution system from power gen to e-house | 2750.2-E | 6100 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 610 | 9150 | 60947.1624 | 91500 | 161597.1624 | 0.01 | 61 | 100% | 0% | 0% | 100% | 161597.1624 | 0 | 0 | 161597.1624 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53865.7208 | 53865.7208 | 53865.7208 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 2750.3-E | 5000 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 500 | 7500 | 49956.6905 | 75000 | 132456.6905 | 0.01 | 50 | 100% | 0% | 0% | 100% | 132456.6905 | 0 | 0 | 132456.6905 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 44152.2302 | 44152.2302 | 44152.2302 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 483 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-001 | 59.4796 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.3333 | 200 | 1332.1784 | 2000 | 3532.1784 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3532.1784 | 0 | 0 | 3532.1784 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1177.3928 | 1177.3928 | 1177.3928 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 486 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-002 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-003 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 492 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-004 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 495 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-005 | 2.3234 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0.52083 | 7.8125 | 52.0382 | 78.125 | 137.9757 | 1 | 2.3234 | 100% | 0% | 0% | 100% | 137.9757 | 0 | 0 | 137.9757 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68.9879 | 68.9879 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 496 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 497 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 487 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 488 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 490 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 491 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 493 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 494 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 484 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 485 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | Genset modules |  | 4 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 672 | 8880 | 67141.792 | 88800 | 164821.792 | 56 | 224 | 100% | 0% | 0% | 100% | 164821.792 | 0 | 0 | 164821.792 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 54940.5973 | 0 | 54940.5973 | 0 | 0 | 0 | 0 | 54940.5973
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-008 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-009 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road
3000 | Tote Road | 3100 | General
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 3111-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 507 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 3111-BLD-002 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 510 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 3 - Demolish Building - ISO Shipping Container | 3111-BLD-003 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 513 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 4 - Demolish Building - ISO Shipping Container | 3111-BLD-004 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 505 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 506 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 508 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 509 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 511 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 3 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 512 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 514 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 4 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 515 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km88 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km80 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km69 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km49 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km40 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km26 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km7 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 16.8125 | 252.1875 | 1679.7937 | 2521.875 | 4453.8562 | 1 | 150 | 100% | 0% | 0% | 100% | 4453.8562 | 0 | 0 | 4453.8562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1484.6187 | 1484.6187 | 1484.6187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 517 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 5 - Demolish Building - ISO Shipping Container | 3112-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 520 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 6 - Demolish Building - ISO Shipping Container | 3112-BLD-002 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 523 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 7 - Demolish Building - ISO Shipping Container | 3112-BLD-003 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 526 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 8 - Demolish Building - ISO Shipping Container | 3112-BLD-004 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 518 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 5 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 519 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 5 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 521 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 6 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 522 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 6 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 524 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 7 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 525 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 7 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 527 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 8 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 528 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 8 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 530 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 9 - Demolish Building - ISO Shipping Container | 3113-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 533 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 10 - Demolish Building - ISO Shipping Container | 3113-BLD-002 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 536 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 11 - Demolish Building - ISO Shipping Container | 3113-BLD-003 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 531 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 9 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 532 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 9 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 534 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 10 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 535 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 10 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 537 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 11 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 538 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 11 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3114 | Communications Facility No. 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 102 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source |  | 41795 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 530.3736 | 6112.5187 | 53037.3574 | 16573.6127 | 75723.4889 | 0 | 0 | 100% | 0% | 0% | 100% | 75723.4889 | 0 | 0 | 75723.4889 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [7 empty] | 0 |  | 75723.4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2017) |  | 1000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 12.6899 | 146.25 | 1268.9881 | 396.5453 | 1811.7834 | 0 | 0 | 100% | 0% | 0% | 100% | 1811.7834 | 0 | 0 | 1811.7834 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 100% | [7 empty] | 0 |  | 1811.7834 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2018) |  | 1500 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 19.0348 | 219.375 | 1903.4821 | 594.818 | 2717.6752 | 0 | 0 | 100% | 0% | 0% | 100% | 2717.6752 | 0 | 0 | 2717.6752 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 100% | [7 empty] | 0 |  | 2717.6752 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 97/98 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at P1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P1 Borrow Source |  | 75820 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 962.1468 | 11088.675 | 96214.6773 | 30066.0681 | 137369.4204 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 137369.4204 | 0 | 137369.4204 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68684.7102 | 68684.7102 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive magazine pads along Tote Road |  | 760 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 9.6443 | 111.15 | 964.431 | 301.3745 | 1376.9554 | 0 | 0 | 100% | 0% | 0% | 100% | 1376.9554 | 0 | 0 | 1376.9554 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 458.9851 | 458.9851 | 458.9851 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R3 (2017 Carry Over) |  | 25800 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 327.3989 | 3773.25 | 32739.8928 | 10230.8699 | 46705.6199 | 0 | 0 | 100% | 0% | 0% | 100% | 46705.6199 | 0 | 0 | 46705.6199 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15568.54 | 15568.54 | 15568.54 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R1 (2017 Carry Over) |  | 20200 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 256.3356 | 2954.25 | 25633.5595 | 8010.216 | 36567.966 | 0 | 0 | 100% | 0% | 0% | 100% | 36567.966 | 0 | 0 | 36567.966 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12189.322 | 12189.322 | 12189.322 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R2 (2017 Carry Over) |  | 20000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 253.7976 | 2925 | 25379.7619 | 7930.9069 | 36205.9069 | 0 | 0 | 100% | 0% | 0% | 100% | 36205.9069 | 0 | 0 | 36205.9069 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12068.6356 | 12068.6356 | 12068.6356 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown at km 61 |  | 6000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 76.1393 | 877.5 | 7613.9286 | 2379.2721 | 10861.7721 | 0 | 0 | 100% | 0% | 0% | 100% | 10861.7721 | 0 | 0 | 10861.7721 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3620.5907 | 3620.5907 | 3620.5907 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 88 IT Tower Pad |  | 6400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 81.2152 | 936 | 8121.5238 | 2537.8902 | 11585.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 11585.8902 | 0 | 0 | 11585.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3861.9634 | 3861.9634 | 3861.9634 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 80 IT Tower Pad |  | 6400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 81.2152 | 936 | 8121.5238 | 2537.8902 | 11585.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 11585.8902 | 0 | 0 | 11585.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3861.9634 | 3861.9634 | 3861.9634 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 69 IT Tower Pad |  | 5100 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 64.7184 | 745.875 | 6471.8393 | 2022.3813 | 9232.5063 | 0 | 0 | 100% | 0% | 0% | 100% | 9232.5063 | 0 | 0 | 9232.5063 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3077.5021 | 3077.5021 | 3077.5021 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 49 IT Tower Pad |  | 5600 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 71.0633 | 819 | 7106.3333 | 2220.6539 | 10137.6539 | 0 | 0 | 100% | 0% | 0% | 100% | 10137.6539 | 0 | 0 | 10137.6539 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3379.218 | 3379.218 | 3379.218 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 40 IT Tower Pad |  | 2600 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 32.9937 | 380.25 | 3299.369 | 1031.0179 | 4706.7679 | 0 | 0 | 100% | 0% | 0% | 100% | 4706.7679 | 0 | 0 | 4706.7679 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1568.9226 | 1568.9226 | 1568.9226 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 26 IT Tower Pad |  | 4000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 50.7595 | 585 | 5075.9524 | 1586.1814 | 7241.1814 | 0 | 0 | 100% | 0% | 0% | 100% | 7241.1814 | 0 | 0 | 7241.1814 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2413.7271 | 2413.7271 | 2413.7271 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 07 IT Tower Pad |  | 3800 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 48.2215 | 555.75 | 4822.1548 | 1506.8723 | 6879.1223 | 0 | 0 | 100% | 0% | 0% | 100% | 6879.1223 | 0 | 0 | 6879.1223 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2293.0408 | 2293.0408 | 2293.0408 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3136 | Mary River |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 13040 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 165.476 | 1907.1 | 16547.6047 | 5170.9513 | 23625.6561 | 0 | 0 | 100% | 0% | 0% | 100% | 23625.6561 | 0 | 0 | 23625.6561 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7875.2187 | 7875.2187 | 7875.2187 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Q13 Quarry (marginal increase to existing) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 25000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 317.247 | 3656.25 | 31724.7023 | 9913.6336 | 45257.3836 | 0 | 0 | 100% | 0% | 0% | 100% | 45257.3836 | 0 | 0 | 45257.3836 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 22628.6918 | 22628.6918 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P10 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P10 Borrow Source |  | 19344 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 245.4731 | 2829.06 | 24547.3057 | 7670.7732 | 35018.3532 | 0 | 0 | 100% | 0% | 0% | 100% | 35018.3532 | 0 | 0 | 35018.3532 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 17509.1766 | 17509.1766 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P13 Borrow Source |  | 8456 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 107.3056 | 1236.69 | 10730.5633 | 3353.1874 | 15307.8574 | 0 | 0 | 100% | 0% | 0% | 100% | 15307.8574 | 0 | 0 | 15307.8574 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7653.9287 | 7653.9287 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P14 Borrow Source |  | 3160 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 40.1 | 462.15 | 4010.0024 | 1253.0833 | 5720.5333 | 0 | 0 | 100% | 0% | 0% | 100% | 5720.5333 | 0 | 0 | 5720.5333 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2860.2666 | 2860.2666 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P15 Borrow Source |  | 3300 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 41.8766 | 482.625 | 4187.6607 | 1308.5996 | 5973.9746 | 0 | 0 | 100% | 0% | 0% | 100% | 5973.9746 | 0 | 0 | 5973.9746 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2986.9873 | 2986.9873 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Removal of Quarry and Borrow No Longer being Developed (Q9, Q14, Q15, P5, P6, P7, P8, P10, P13, P14, and P15) |  | -102131 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | -1296.0302 | -14936.6587 | -129603.023 | -40499.5727 | -184887.274 | 0 | 0 | 100% | 0% | 0% | 100% | -184887.274 | 0 | 0 | -184887.274 | Type A 2AM-MRY1325 | Removed | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -92443.637 | -92443.637 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P5 Borrow Source |  | 4600 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 58.3735 | 672.75 | 5837.3452 | 1824.1086 | 8327.3586 | 0 | 0 | 100% | 0% | 0% | 100% | 8327.3586 | 0 | 0 | 8327.3586 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4163.6793 | 4163.6793 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P6 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P6 Borrow Source |  | 7500 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 95.1741 | 1096.875 | 9517.4107 | 2974.0901 | 13577.2151 | 0 | 0 | 100% | 0% | 0% | 100% | 13577.2151 | 0 | 0 | 13577.2151 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6788.6075 | 6788.6075 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P7 Borrow Source |  | 8100 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 102.788 | 1184.625 | 10278.8036 | 3212.0173 | 14663.3923 | 0 | 0 | 100% | 0% | 0% | 100% | 14663.3923 | 0 | 0 | 14663.3923 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7331.6962 | 7331.6962 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P8 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P8 Borrow Source |  | 8385 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 106.4047 | 1226.3062 | 10640.4652 | 3325.0327 | 15179.3265 | 0 | 0 | 100% | 0% | 0% | 100% | 15179.3265 | 0 | 0 | 15179.3265 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7589.6632 | 7589.6632 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry |  | 64200 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 814.6904 | 9389.25 | 81469.0356 | 25458.2112 | 116316.4968 | 0 | 0 | 100% | 0% | 0% | 100% | 116316.4968 | 0 | 0 | 116316.4968 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 58158.2484 | 58158.2484 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 76.1393 | 877.5 | 7613.9286 | 2379.2721 | 10870.7006 | 0 | 0 | 100% | 0% | 0% | 100% | 10870.7006 | 0 | 0 | 10870.7006 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5435.3503 | 5435.3503 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 634.494 | 7312.5 | 63449.4047 | 19827.2673 | 90589.172 | 0 | 0 | 100% | 0% | 0% | 100% | 90589.172 | 0 | 0 | 90589.172 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 45294.586 | 45294.586 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing in remainder 2017 - total now reflects area in QMP) |  | 824500 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 10462.8068 | 120583.125 | 1046280.6833 | 326951.6376 | 1493815.4459 | 0 | 0 | 100% | 0% | 0% | 100% | 1493815.4459 | 0 | 0 | 1493815.4459 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 746907.7229 | 746907.7229 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q11 Quarry |  | 50433 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 639.9888 | 7375.8262 | 63998.8765 | 19998.9714 | 91373.6742 | 0 | 0 | 100% | 0% | 0% | 100% | 91373.6742 | 0 | 0 | 91373.6742 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 45686.8371 | 45686.8371 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q18 Quarry |  | 2000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 25.3798 | 292.5 | 2537.9762 | 793.0907 | 3623.5669 | 0 | 0 | 100% | 0% | 0% | 100% | 3623.5669 | 0 | 0 | 3623.5669 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1811.7834 | 1811.7834 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 6350 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 80.5807 | 928.6875 | 8058.0744 | 2518.0629 | 11495.3754 | 0 | 0 | 100% | 0% | 0% | 100% | 11495.3754 | 0 | 0 | 11495.3754 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5747.6877 | 5747.6877 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q14 Quarry |  | 13440 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 170.552 | 1965.6 | 17055.2 | 5329.5694 | 24330.3694 | 0 | 0 | 100% | 0% | 0% | 100% | 24330.3694 | 0 | 0 | 24330.3694 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 12165.1847 | 12165.1847 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q15 Quarry |  | 10680 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 135.5279 | 1561.95 | 13552.7928 | 4235.1043 | 19333.9543 | 0 | 0 | 100% | 0% | 0% | 100% | 19333.9543 | 0 | 0 | 19333.9543 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 9666.9771 | 9666.9771 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q16A |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q16A Quarry |  | 11240 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 142.6343 | 1643.85 | 14263.4262 | 4457.1697 | 20347.7197 | 0 | 0 | 100% | 0% | 0% | 100% | 20347.7197 | 0 | 0 | 20347.7197 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 10173.8598 | 10173.8598 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q19 Quarry |  | 18760 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 238.0622 | 2743.65 | 23806.2166 | 7439.1907 | 33989.0573 | 0 | 0 | 100% | 0% | 0% | 100% | 33989.0573 | 0 | 0 | 33989.0573 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 16994.5287 | 16994.5287 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q9 Quarry |  | 15166 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 192.4547 | 2218.0275 | 19245.4734 | 6014.0067 | 27454.9392 | 0 | 0 | 100% | 0% | 0% | 100% | 27454.9392 | 0 | 0 | 27454.9392 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 13727.4696 | 13727.4696 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry |  | 15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 13588.3758 | 13588.3758 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q7 Quarry |  | 53050 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 673.1982 | 7758.5625 | 67319.8184 | 21036.7306 | 96115.1115 | 0 | 0 | 100% | 0% | 0% | 100% | 96115.1115 | 0 | 0 | 96115.1115 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 48057.5557 | 48057.5557 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Borrow development areas |  | 42080 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 533.9902 | 6154.2 | 53399.019 | 16686.6282 | 76239.8471 | 0 | 0 | 100% | 0% | 0% | 100% | 76239.8471 | 0 | 0 | 76239.8471 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25413.2824 | 25413.2824 | 25413.2824 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3132 | River Crossing at STA 17 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 5000 | 5000 | 0% | 100% | 0% | 100% | 0 | 201838.7664 | 0 | 201838.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 67279.5888 | 67279.5888 | 67279.5888 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3133 | River Crossing at STA 62 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 5000 | 5000 | 100% | 0% | 0% | 100% | 201838.7664 | 0 | 0 | 201838.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 67279.5888 | 67279.5888 | 67279.5888 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3134 | River Crossing at STA 80 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 5000 | 5000 | 100% | 0% | 0% | 100% | 201838.7664 | 0 | 0 | 201838.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 67279.5888 | 67279.5888 | 67279.5888 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3135 | River Crossing at STA 97 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 761.9048 | 11428.5714 | 76124.4807 | 114285.7143 | 201838.7664 | 5000 | 5000 | 100% | 0% | 0% | 100% | 201838.7664 | 0 | 0 | 201838.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 67279.5888 | 67279.5888 | 67279.5888 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 372 | Ea | 6 | 45 | 599.4803 | 450 | 1094.4803 | 2232 | 16740 | 223006.6663 | 167400 | 407146.6663 | 0 | 0 | 100% | 0% | 0% | 100% | 407146.6663 | 0 | 0 | 407146.6663 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 203573.3331 | 203573.3331 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - Crown |  | 11 | Ea | 6 | 45 | 599.4803 | 450 | 1094.4803 | 66 | 495 | 6594.2831 | 4950 | 12039.2831 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 12039.2831 | 0 | 12039.2831 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 6019.6416 | 6019.6416 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mobile Maintenance Depot - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 682 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 382.2042 | 1605.2575 | 38187.3105 | 57330.625 | 97123.193 | 1 | 682 | 0% | 100% | 0% | 100% | 0 | 97123.193 | 0 | 97123.193 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 32374.3977 | 32374.3977 | 32374.3977 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Mobile Maintenance Depot - Demolish floor finish - Slab on grade C/W Drainage |  | 682 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 85.25 | 1278.75 | 8517.6157 | 12787.5 | 22583.8657 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 22583.8657 | 0 | 22583.8657 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7527.9552 | 7527.9552 | 7527.9552 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Mobile Maintenance Depot -Liner Removal |  | 682 | m2 | 0.0318 | 0.0318 | 3.18 | 0.318 | 3.498 | 21.6876 | 21.6876 | 2168.76 | 216.876 | 2385.636 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 2385.636 | 0 | 2385.636 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 795.212 | 795.212 | 795.212 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Mobile Maintenance Depot - Demolish and foundations - Gravel Base - Skidded Building |  | 682 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Out-of-Service Tote Road |  | 266500 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 3381.8533 | 38975.625 | 338185.327 | 105679.3346 | 482443.7096 | 0 | 0 | 100% | 0% | 0% | 100% | 482443.7096 | 0 | 0 | 482443.7096 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 241221.8548 | 241221.8548 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 17 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 62 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 80 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 97 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source |  | 157012 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 2988.6954 | 34444.5075 | 298869.5379 | 93393.5667 | 426707.6121 | 0 | 0 | 100% | 0% | 0% | 100% | 426707.6121 | 0 | 0 | 426707.6121 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 213353.8061 | 213353.8061 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 0 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2017) |  | 1000 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 19.0348 | 219.375 | 1903.4821 | 594.818 | 2717.6752 | 0 | 0 | 100% | 0% | 0% | 100% | 2717.6752 | 0 | 0 | 2717.6752 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1358.8376 | 1358.8376 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2018) |  | 1500 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 28.5522 | 329.0625 | 2855.2232 | 892.227 | 4076.5127 | 0 | 0 | 100% | 0% | 0% | 100% | 4076.5127 | 0 | 0 | 4076.5127 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2038.2564 | 2038.2564 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT -EXCAVATOR - CAT M322D |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 105359 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 2005.4897 | 23113.1306 | 200548.9749 | 62669.4316 | 286096.361 | 0 | 0 | 100% | 0% | 0% | 100% | 286096.361 | 0 | 0 | 286096.361 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 143048.1805 | 143048.1805 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  |  | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  | 697910.1311 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 8856.3965 | 102069.3567 | 885639.6469 | 276753.0143 | 1263423.4622 | 0 | 0 | 100% | 0% | 0% | 100% | 1263423.4622 | 0 | 0 | 1263423.4622 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 631711.7311 | 631711.7311 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 565 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 1 - Demolish Building - ISO Shipping Container | 3160-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 568 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 2 - Demolish Building - ISO Shipping Container | 3160-BLD-002 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 571 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 3 - Demolish Building - ISO Shipping Container | 3160-BLD-003 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 574 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 4 - Demolish Building - ISO Shipping Container | 3160-BLD-004 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 566 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 1 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-001 | 14.8699 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 1.8333 | 17.5 | 116.5656 | 175 | 309.0656 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 309.0656 | 0 | 0 | 309.0656 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 103.0219 | 103.0219 | 103.0219 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 569 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 2 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-002 | 14.8699 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 1.8333 | 17.5 | 116.5656 | 175 | 309.0656 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 309.0656 | 0 | 0 | 309.0656 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 103.0219 | 103.0219 | 103.0219 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 572 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 3 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-003 | 14.8699 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 1.8333 | 17.5 | 116.5656 | 175 | 309.0656 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 309.0656 | 0 | 0 | 309.0656 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 103.0219 | 103.0219 | 103.0219 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 575 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 4 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-004 | 14.8699 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 1.8333 | 17.5 | 116.5656 | 175 | 309.0656 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 309.0656 | 0 | 0 | 309.0656 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 103.0219 | 103.0219 | 103.0219 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 567 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 570 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 573 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 576 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (31m2 x 2) - Demolish and Decontaminate Building - Trailer |  | 62 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 34.7458 | 208.475 | 3471.5737 | 5211.875 | 8891.9237 | 1 | 62 | 100% | 0% | 0% | 100% | 8891.9237 | 0 | 0 | 8891.9237 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2963.9746 | 2963.9746 | 2963.9746 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (15m2 x 3) - Demolish and Decontaminate Building - Trailer |  | 45 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 25.2188 | 151.3125 | 2519.6906 | 3782.8125 | 6453.8156 | 1 | 45 | 100% | 0% | 0% | 100% | 6453.8156 | 0 | 0 | 6453.8156 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2151.2719 | 2151.2719 | 2151.2719 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (22m2) - Demolish and Decontaminate Building - Trailer |  | 22 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 12.3292 | 73.975 | 1231.8487 | 1849.375 | 3155.1987 | 1 | 22 | 100% | 0% | 0% | 100% | 3155.1987 | 0 | 0 | 3155.1987 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1051.7329 | 1051.7329 | 1051.7329 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (12m2) - Demolish and Decontaminate Building - Trailer |  | 12 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 6.725 | 40.35 | 671.9175 | 1008.75 | 1721.0175 | 1 | 12 | 100% | 0% | 0% | 100% | 1721.0175 | 0 | 0 | 1721.0175 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 573.6725 | 573.6725 | 573.6725 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site
4000 | Mine Site | 4100 | General
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 579 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 4110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 582 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 4110-BLD-002 | 14.8699 | m2 | 0.11208 | 1.6812 | 11.1986 | 16.8125 | 29.6924 | 1.6667 | 25 | 166.5223 | 250 | 441.5223 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 441.5223 | 0 | 0 | 441.5223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 147.1741 | 147.1741 | 147.1741 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 580 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 581 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 583 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 584 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Site Development | 4136 | Tote Road |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 223 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 2.8298 | 32.6137 | 282.9843 | 88.4296 | 404.0277 | 0 | 0 | 100% | 0% | 0% | 100% | 404.0277 | 0 | 0 | 404.0277 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 134.6759 | 134.6759 | 134.6759 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | -15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2A |  | 30150 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2B |  | 8700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 1 |  | 5400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction Laydown Area |  | 33576 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 426.0754 | 4910.49 | 42607.5442 | 13314.4065 | 60832.4408 | 0 | 0 | 100% | 0% | 0% | 100% | 60832.4408 | 0 | 0 | 60832.4408 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20277.4803 | 20277.4803 | 20277.4803 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 220.3841 | 2539.912 | 22038.4147 | 6886.7713 | 31465.0981 | 0 | 0 | 100% | 0% | 0% | 100% | 31465.0981 | 0 | 0 | 31465.0981 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10488.366 | 10488.366 | 10488.366 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 220.3841 | 2539.912 | 22038.4147 | 6886.7713 | 31465.0981 | 0 | 0 | 100% | 0% | 0% | 100% | 31465.0981 | 0 | 0 | 31465.0981 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10488.366 | 10488.366 | 10488.366 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development (Nuna services) |  | 11400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 144.6646 | 1667.25 | 14466.4643 | 4520.6169 | 20637.3669 | 0 | 0 | 100% | 0% | 0% | 100% | 20637.3669 | 0 | 0 | 20637.3669 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6879.1223 | 6879.1223 | 6879.1223 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4135 | Explosives Pads | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Explosives Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional laydown next to Hatch old office/carpentry shack |  | 11250 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 142.7612 | 1645.3125 | 14276.1161 | 4461.1351 | 20365.8226 | 0 | 0 | 100% | 0% | 0% | 100% | 20365.8226 | 0 | 0 | 20365.8226 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6788.6075 | 6788.6075 | 6788.6075 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher Pad Expansion |  | 25700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 326.1299 | 3758.625 | 32612.994 | 10191.2154 | 46524.5904 | 0 | 0 | 100% | 0% | 0% | 100% | 46524.5904 | 0 | 0 | 46524.5904 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15508.1968 | 15508.1968 | 15508.1968 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher extension Pad |  | 36180 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 459.1199 | 5291.325 | 45911.9892 | 14347.0106 | 65496.4856 | 0 | 0 | 100% | 0% | 0% | 100% | 65496.4856 | 0 | 0 | 65496.4856 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 21832.1619 | 21832.1619 | 21832.1619 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry |  | 258580 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 3281.3494 | 37817.325 | 328134.9413 | 102538.6955 | 468490.9618 | 0 | 0 | 100% | 0% | 0% | 100% | 468490.9618 | 0 | 0 | 468490.9618 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 234245.4809 | 234245.4809 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q2 Quarry |  | 109807 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1393.4378 | 16059.2737 | 139343.7756 | 43543.4548 | 198946.5041 | 0 | 0 | 100% | 0% | 0% | 100% | 198946.5041 | 0 | 0 | 198946.5041 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 99473.2521 | 99473.2521 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q1 Quarry |  | 66978 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 849.9428 | 9795.5325 | 84994.2845 | 26559.8142 | 121349.6312 | 0 | 0 | 100% | 0% | 0% | 100% | 121349.6312 | 0 | 0 | 121349.6312 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 60674.8156 | 60674.8156 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 76.1393 | 877.5 | 7613.9286 | 2379.2721 | 10870.7006 | 0 | 0 | 100% | 0% | 0% | 100% | 10870.7006 | 0 | 0 | 10870.7006 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5435.3503 | 5435.3503 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour |  |  |  | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 634.494 | 7312.5 | 63449.4047 | 19827.2673 | 90589.172 | 0 | 0 | 100% | 0% | 0% | 100% | 90589.172 | 0 | 0 | 90589.172 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 45294.586 | 45294.586 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -6000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | -76.1393 | -877.5 | -7613.9286 | -2379.2721 | -10870.7006 | 0 | 0 | 100% | 0% | 0% | 100% | -10870.7006 | 0 | 0 | -10870.7006 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -5435.3503 | -5435.3503 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -50000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | -634.494 | -7312.5 | -63449.4047 | -19827.2673 | -90589.172 | 0 | 0 | 100% | 0% | 0% | 100% | -90589.172 | 0 | 0 | -90589.172 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -45294.586 | -45294.586 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Informal Construction Laydown at Mary River |  |  | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Site Roads |  | 80899 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1026.5987 | 11831.4787 | 102659.8678 | 32080.1219 | 146571.4685 | 0 | 0 | 100% | 0% | 0% | 100% | 146571.4685 | 0 | 0 | 146571.4685 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 48857.1562 | 48857.1562 | 48857.1562 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Waste Rock Road |  | 20000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 253.7976 | 2925 | 25379.7619 | 7930.9069 | 36235.6688 | 0 | 0 | 100% | 0% | 0% | 100% | 36235.6688 | 0 | 0 | 36235.6688 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12078.5563 | 12078.5563 | 12078.5563 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 1120 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 14.2127 | 163.8 | 1421.2667 | 444.1308 | 2027.5308 | 0 | 0 | 100% | 0% | 0% | 100% | 2027.5308 | 0 | 0 | 2027.5308 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 675.8436 | 675.8436 | 675.8436 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 599 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-005 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 600 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-006 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 601 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-007 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 602 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 603 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-009 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 604 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-010 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 605 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - MINE SITE LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4141-MO-024 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 606 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 607 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 608 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 609 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 610 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-029 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 611 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 56800 kg | 4141-MO-030 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 612 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg | 4141-MO-031 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 613 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL size | MOBILE EQUIPMENT - SECONDARY DRILL - TAMROCK 800 | 4141-MO-033 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 614 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - DRILL DUST SUPPRESSION WATER/METHANOL TRUCK - KENWORTH T800H | 4141-MO-035 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Mine Haul Truck, 777 |  | 3 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 39 | 360 | 3896.6219 | 3600 | 7856.6219 | 96 | 288 | 100% | 0% | 0% | 100% | 7856.6219 | 0 | 0 | 7856.6219 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2618.874 | 0 | 2618.874 | 0 | 0 | 0 | 0 | 2618.874
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Mobile Light Plant |  | 5 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 50 | 225 | 4995.669 | 2250 | 7470.669 | 24 | 120 | 100% | 0% | 0% | 100% | 7470.669 | 0 | 0 | 7470.669 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2490.223 | 0 | 2490.223 | 0 | 0 | 0 | 0 | 2490.223
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Pick-Up Truck |  | 7 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 46.6667 | 175 | 4662.6244 | 1750 | 6587.6244 | 4 | 28 | 100% | 0% | 0% | 100% | 6587.6244 | 0 | 0 | 6587.6244 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2195.8748 | 0 | 2195.8748 | 0 | 0 | 0 | 0 | 2195.8748
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Truck Wash Facility |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Container Handler |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Gantry Crane |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Single Pass Production Drill |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Ore Haul Truck Workshop |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Boom Truck |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Passenger Bus |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Track Dozer, D9 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Shovel 6030 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Integrated Tool Carrier, 938 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | FREIGHT HAUL TRACTOR , |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | WATER TRUCK |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | MAINTENANCE FUEL/LUBE TRUCK , |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Flat Deck Truck |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Mini-Crane |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | RESCUE UNIT |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | MECHANICS TRUCK, |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Ore Haul Truck |  | 8 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 104 | 960 | 10390.9916 | 9600 | 20950.9916 | 96 | 768 | 100% | 0% | 0% | 100% | 20950.9916 | 0 | 0 | 20950.9916 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6983.6639 | 0 | 6983.6639 | 0 | 0 | 0 | 0 | 6983.6639
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | B-Train Trailer (for Ore Haul Truck) |  | 8 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 80 | 360 | 7993.0705 | 3600 | 11953.0705 | 24 | 192 | 100% | 0% | 0% | 100% | 11953.0705 | 0 | 0 | 11953.0705 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3984.3568 | 0 | 3984.3568 | 0 | 0 | 0 | 0 | 3984.3568
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 3 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 39 | 360 | 3896.6219 | 3600 | 7856.6219 | 96 | 288 | 100% | 0% | 0% | 100% | 7856.6219 | 0 | 0 | 7856.6219 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2618.874 | 0 | 2618.874 | 0 | 0 | 0 | 0 | 2618.874
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick Up | Pick Up Truck |  | 6 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 40 | 150 | 3996.5352 | 1500 | 5646.5352 | 4 | 24 | 100% | 0% | 0% | 100% | 5646.5352 | 0 | 0 | 5646.5352 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1882.1784 | 0 | 1882.1784 | 0 | 0 | 0 | 0 | 1882.1784
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Excavator |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Large Forklift |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Grader |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Haul Truck |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel/ Lube Truck |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Telehandler |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Zoom Boom |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Passenger Bus |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Mechanics Truck (with compressor and crane) |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 78 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 1014 | 9360 | 101312.1683 | 93600 | 204272.1683 | 96 | 7488 | 100% | 0% | 0% | 100% | 204272.1683 | 0 | 0 | 204272.1683 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 68090.7228 | 0 | 68090.7228 | 0 | 0 | 0 | 0 | 68090.7228
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | 128 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 1280 | 5760 | 127889.1276 | 57600 | 191249.1276 | 24 | 3072 | 100% | 0% | 0% | 100% | 191249.1276 | 0 | 0 | 191249.1276 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 63749.7092 | 0 | 63749.7092 | 0 | 0 | 0 | 0 | 63749.7092
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | 188 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 1253.3333 | 4700 | 125224.7708 | 47000 | 176924.7708 | 4 | 752 | 100% | 0% | 0% | 100% | 176924.7708 | 0 | 0 | 176924.7708 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 58974.9236 | 0 | 58974.9236 | 0 | 0 | 0 | 0 | 58974.9236
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992 Loader |  | 4 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 52 | 480 | 5195.4958 | 4800 | 10475.4958 | 96 | 384 | 100% | 0% | 0% | 100% | 10475.4958 | 0 | 0 | 10475.4958 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3491.8319 | 0 | 3491.8319 | 0 | 0 | 0 | 0 | 3491.8319
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 994 Loader |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988 Loader |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793 Haul Truck |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Mobile Primary Crusher Unit |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel/Lube Truck |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - CAT 777 DUMP BOX |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - MINE SITE GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK DX780 |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK SDX800 |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | C 125 JAW CRUSHER |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | SANDVIK NEW QJ341 JAW CRUSHER S/N# QJ34100262 |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT SERVICE TRUCK 2014 | HTP014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER VAC TRUCK | HTP018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER M2 SERVICE TRUCK | HTP022 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2014 MACK JET FUEL TRUCK | FLT003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | SUPER B FUEL TANKER LEAD UNIT | FLT004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRI AXLE FUEL TRAILER | FLT006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | SUPER B FUEL TRAILER PUP UNIT | FLT007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B FUEL/LUBE TRUCK | FLT010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER M2 FUEL TRUCK | FLT011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART020 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING WATER/SAND TRUCK | AWT001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING WATER TRUCK | AWT002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONTAINER HANDLER | CNH001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TEREX RT780 CRANE | CRN002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TEREX RT130 CRANE | CRN003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MANITOWOC CRANE MODEL 2250 | CRN004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE SPYDER CRANE W706 | CRN006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | BOOM CRANE, CONMA, MTP016 | CRN008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TAMROCK RANDER 800-2 HYDRAULIC DRILL 200 | DRL003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MD6290 CAT ROTARY PRODUCTION DRILL | DRL004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MD6290 CAT ROTARY PRODUCTION DRILL | DRL007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | OSHKOSH FIRE TRUCK 1993 -T1500 MR | EMG002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390DL EXCAVATOR CATERPILLAR | EXC001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390DL EXCAVATOR CATERPILLAR | EXC002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | M320F EXCAVATOR CATERPILLAR RUBBER TIRE | EXC009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 16H CATERPILLAR GRADER | GRD001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 16M CATERPILLAR GRADER | GRD002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER | GRD003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER W/WING | GRD004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER | GRD005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER W/WING | GRD006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992K WHEEL LOADER | LDR001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | IT14 LOADER NFLD HARDROCK | LDR019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 906 CATERPILLAR LOADER | LDR020 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | VOLVO L-180 LOADER - W/TIRE MANIPULATOR | LDR021 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT020 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT021 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT022 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT023 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT025 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT026 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT027 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT028 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT029 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT030 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT031 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT032 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT033 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT034 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT035 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT036 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT037 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT038 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT039 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1020 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1021 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1022 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1023 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1025 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1026 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1027 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1028 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1029 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1030 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1031 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1032 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1033 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1034 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1035 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1036 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1037 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1038 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1039 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | LOADER VOLVO-L-180E C/W TIRE HANDLER & 3 CRATES IN CAB |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | HP 400RD PLANT CRUSHER S/N MC-0401/MC2015102 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FORD F650 SERVICE TRUCK VIN# 3FDNF65H13MB00286 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE TRAILER OFF-ROAD MINE MODEL HDT4-38-23 S/N 712379 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK + 10 SPARE TIRES STRAPPED ON TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK (2 PALLETS STRAPPED ON TRUCK) |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK (OHT031) |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2005 WESTERN STAR VIN# 1XKCPBEX85R980272 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2015 CAT 14M GRADER YELLOW VIN# 8814WKR9J88448 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2012 CAT 14M GRADER YELLOW |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WINCH TRUCK |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRAILER DUMP TRUCK TRIAXLE S/N# 2ATE060336A003392 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WETSERN STAR TRUCK VIN: 5KJRASD19GPHD7171 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD14GPHD7174 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD12GPHD7173 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD10GPHD7172 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 824H CATERPILLAR RUBBER TIRED DOZER | DZR011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | FLT005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT ROAD MAINTENANCE 2013 | HTP005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | STERLING BOOM TRUCK W/ MANITEX CRANE | HTP006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | STERLING BOOM TRUCK W/ MANITEX CRANE | HTP007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT 367 TRACTOR 2017 | HTP009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KENWORTH TOW TRUCK | HTP010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT TRACTOR 2014 | HTP011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT TRACTOR 2014 | HTP013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL PLOW TRUCK | HTP016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL BOOM TRUCK KNUCKLE | HTP019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR 4900 2014 (NFLD HARD ROCK) | HTP024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR 4900 2014 (NFLD HARD ROCK) | HTP025 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP029 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP032 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP033 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512109 |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | BRODERSON 16 80 CRANE |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK + BOX PLASTIC FITTINGS |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 716.1098 | 0 | 716.1098 | 0 | 0 | 0 | 0 | 716.1098
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX780 SANDVIK ROCK DRILL | DRL005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2013 K/W FUEL LUBE TRUCK | FLT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2014K/W FUEL LUBE TRUCK | FLT002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2009 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2010 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2011 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2012 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2013 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2014 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2016 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2017 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2018 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2019 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2020 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2021 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2022 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2023 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2024 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2025 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2026 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2027 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2028 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2029 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2030 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2031 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2032 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2033 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2034 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2035 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2036 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2037 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2038 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2039 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SMITHCO SIDE DUMP TRAILER MODEL HDT 4-38-23, S/N 712377 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE SIDE DUMP TRAILER MODEL HDT4-38-23 S/N 712385 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE SIDE-DUMP TRAILER MODEL HDT4-38-23, S/N 712381 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712393 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712387 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712391 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712389 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712395 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2011 KENWORTH S/A MECHANICS SERVICE TRUCK VIN# 2NKHHM6X1BM284136 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL # 712397 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712405 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712378 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712388 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712382 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712392 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712390 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712380 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712398 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL# 712394 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712384 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712402 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712400 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712396 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712406 * damaged by stevedores during receiving (hydraulic fittings in front of trailer) |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712404 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712386 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | END DUMP TRAILER | EDT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HI BOY TRAILER | HBT005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLOAT TRAILER MINI DECK SCHELTENA MD1 | LBT003-01 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F750 DE-ICEING TRUCK BBS-97 | MTP001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MANUAL JIB CRANE MOBILE MAINTENANCE SHOP | CRN007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D5M CATERPILLAR DOZER | DZR009 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D4C CATERPILLAR DOZER LPGIII | DZR010 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TRI AXLE WATER TRUCK | HTP004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT ROLL OFF TRUCK | HTP015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT | JLG007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GENIE BOOM LIFT ZOOM BOOM Z60/34 | JLG008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KUBOTA TRACTOR B7800 | KUB004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | LOWBOY TRAILER DELOUPE | LBT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | LOWBOY TRAILER DELOUPE | LBT002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CS74 SMOOTH ROLLER | RLR002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TL642 | TLH005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TRAILER LIVE BOTTOM | WBT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PC09-1 EXCAVATOR KOMATSU MINI | EXC008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 53' POWER TRAILER |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 FLAT DECK PICK-UP WHITE VIN# 1FDOW5HTOFED33588 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | STEP-DECK TRAILER 3 AXLES UNIT # 533F650 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GMC PICK UP 4WD + TOOL/JOB BOX VIN# 1GTHK39D17E173219 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | UTILITY TRAILERS STACKED 2 HIGH |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL TRAILER (FRONT) SERIAL # 712383 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712399 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712401 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITH SIDE-DUMP TRAILER, SERIAL # 712403 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2007 FREIGHTLINER M2 4X4 VIN# 1FVDCXDC47HX81790 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SANDVIK QA441 SCREENER S/N # QA44100342 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | V SNOW PLOW VIN# 9900-2564 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2006 TRAILER TRIAXLE GREY VIN# LA90735316A003393 * RECEIVED WITH DAMAGE TO HYDROLIC OIL SUPPLY FITTING* |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORKLIFT CATERPILLAR P20000 | FKT001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORKLIFT CATERPILLAR P10000 | FKT005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 SERVICE TRUCK FOUNTAIN TIRE | MTP011 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 SERVICE TRUCK | MTP013 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F650 SERVICE TRUCK 2003 | MTP015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F-550 SERVICE TRUCK FOUNTAIN TIRE | MTP016 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT015 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT021 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT022 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT023 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT038 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT040 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT041 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 AMBULANCE | EMG003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F450 AMBULANCE | EMG004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HAGGLUNDS SNOW RESCUE VEHICLE | EMG007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT/MANLIFT CROWN WAV50-118 | FKT010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GROUND SURFACE HEATER | GTH001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENIE MANLIFT / Z45/25J (BURNED) | JLG004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENIE MANLIFT / Z45/25J | JLG005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | JLG MANLIFT 450AJ | JLG010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLOAT TRAILER SCHELTENA | LBT003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP021 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TOYOTA 4X4 PICK-UP LAND CRUISER | LTP031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TOYOTA 4X4 PICK UP LAND CRUISER | LTP034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2011 | LTP038 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP040 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP043 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP044 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP045 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP046 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP047 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP056 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP057 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2014 | LTP058 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP059 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP060 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 2010- LEVITT SAFETY | LTP063 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 3500 GMC CREW CAB 4X4 2006 | LTP067 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GMC 2500 MOBILE STAIR TRUCK | MST001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 WELDING TRUCK | MTP005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 CUBE VAN | MTP008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 (BLASTERS) | MTP009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2014 | MTP012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2015 | MTP014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PULL- TYPE PNEUMATIC ROLLER | PTR001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PULL-TYPE PNEUMATIC TIRE ROLLER | PTR002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VAC TANK UNIT | PVT001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VACUUM TANK c/w PUMP | PVT002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VAC TANK UNIT | PVT003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP 6" | PWP001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP 4" | PWP003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP - CAT-PAC | PWP004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 277 MULTI TERRAIN | SKD005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 299D | SKD008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 262D Rubber Tire | SKD012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 03 | SKJ003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 10 | SKJ010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKIDOO | SNM003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIK WT 600 | SNM004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIK WT 600 | SNM005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIC ACE 600 SNOWMOBILE | SNM006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIC ACE 600 SNOWMOBILE | SNM007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE CAN AM COMMANDER 800XT | SXS001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT TRACKED | SXS008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TIRE MANIPULATOR | TMN001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER ENCLOSED SNOWMOBILE | TRL001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BOAT TRAILER | TRL002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | STERLING SPILL RESPONSE UNIT 2002 | EMG005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | STERLING SPILL RESPONSE UNIT 2002 | EMG006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CARGO LUGGAGE HANDLER | CNH003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Piling Rig |  | 3 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 39 | 360 | 3896.6219 | 3600 | 7856.6219 | 96 | 288 | 100% | 0% | 0% | 100% | 7856.6219 | 0 | 0 | 7856.6219 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2618.874 | 0 | 2618.874 | 0 | 0 | 0 | 0 | 2618.874
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | Light Vehicles | 4142-MO-033 | 30 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 200 | 750 | 19982.6762 | 7500 | 28232.6762 | 4 | 120 | 100% | 0% | 0% | 100% | 28232.6762 | 0 | 0 | 28232.6762 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 9410.8921 | 0 | 9410.8921 | 0 | 0 | 0 | 0 | 9410.8921
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Dozer |  | 12 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 156 | 1440 | 15586.4874 | 14400 | 31426.4874 | 96 | 1152 | 100% | 0% | 0% | 100% | 31426.4874 | 0 | 0 | 31426.4874 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10475.4958 | 0 | 10475.4958 | 0 | 0 | 0 | 0 | 10475.4958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Front End Loader |  | 12 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 156 | 1440 | 15586.4874 | 14400 | 31426.4874 | 96 | 1152 | 100% | 0% | 0% | 100% | 31426.4874 | 0 | 0 | 31426.4874 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10475.4958 | 0 | 10475.4958 | 0 | 0 | 0 | 0 | 10475.4958
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Excavators |  | 15 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 195 | 1800 | 19483.1093 | 18000 | 39283.1093 | 96 | 1440 | 100% | 0% | 0% | 100% | 39283.1093 | 0 | 0 | 39283.1093 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13094.3698 | 0 | 13094.3698 | 0 | 0 | 0 | 0 | 13094.3698
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | Misc. Support Mobile Equipment (assume medium sized) |  | 40 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 400 | 1800 | 39965.3524 | 18000 | 59765.3524 | 24 | 960 | 100% | 0% | 0% | 100% | 59765.3524 | 0 | 0 | 59765.3524 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 19921.7841 | 0 | 19921.7841 | 0 | 0 | 0 | 0 | 19921.7841
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Haul Truck (40- and 50- ton) |  | 50 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 650 | 6000 | 64943.6976 | 60000 | 130943.6976 | 96 | 4800 | 100% | 0% | 0% | 100% | 130943.6976 | 0 | 0 | 130943.6976 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43647.8992 | 0 | 43647.8992 | 0 | 0 | 0 | 0 | 43647.8992
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 2017 Sea Lift 3rd Party Equipment in addition to addendum numbers |  | 117 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 1170 | 5265 | 116898.6557 | 52650 | 174813.6557 | 24 | 2808 | 100% | 0% | 0% | 100% | 174813.6557 | 0 | 0 | 174813.6557 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 58271.2186 | 0 | 58271.2186 | 0 | 0 | 0 | 0 | 58271.2186
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 2017 Sea Lift 3rd Party Equipment in addition to addendum numbers |  | 34 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 226.6667 | 850 | 22647.033 | 8500 | 31997.033 | 4 | 136 | 100% | 0% | 0% | 100% | 31997.033 | 0 | 0 | 31997.033 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10665.6777 | 0 | 10665.6777 | 0 | 0 | 0 | 0 | 10665.6777
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 2017 - 3rd party contractor equipment from 2017 addendum not mobilized |  | -30 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | -390 | -3600 | -38966.2186 | -36000 | -78566.2186 | 96 | -2880 | 100% | 0% | 0% | 100% | -78566.2186 | 0 | 0 | -78566.2186 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -26188.7395 | 0 | -26188.7395 | 0 | 0 | 0 | 0 | -26188.7395
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 2 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 85.45 | 1129.5 | 8537.5984 | 11295 | 20962.0984 | 30 | 60 | 100% | 0% | 0% | 100% | 20962.0984 | 0 | 0 | 20962.0984 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6987.3661 | 0 | 6987.3661 | 0 | 0 | 0 | 0 | 6987.3661
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 30 | 30 | 100% | 0% | 0% | 100% | 10481.0492 | 0 | 0 | 10481.0492 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3493.6831 | 0 | 3493.6831 | 0 | 0 | 0 | 0 | 3493.6831
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 20 | 40 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 693 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - FORD F550 | 4143-MO-001 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 694 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - PETERBILT 348 | 4143-MO-002 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 695 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 4143-MO-003 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 696 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-004 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 697 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-005 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 698 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Tire Handler | MOBILE EQUIPMENT - TIRE HANDLER - WBM T20P-S 5900 kg | 4143-MO-006 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 699 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FREIGHT HANDLING FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 4143-MO-008 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 700 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - YARD WORK EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 4143-MO-009 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 701 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-010 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 702 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 703 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - CRUSHER MAINTENANCE KNUCKLE CRANE - KENWORTH T800 | 4143-MO-013 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 704 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT780 L: 14630, W: 7920, H: 3990, 42000 kg | 4143-MO-014 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 705 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT130 L: 15240, W: 7920, H: 3970, 60500 kg | 4143-MO-015 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 706 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - WAREHOUSE FORK LIFT - CAT P7000-D L: 2790, W: 1290, H: 2500, 4763 kg | 4143-MO-016 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 707 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - MAINTENANCE FORK LIFT - CAT P20000 L: 4240, W: 2390, H: 2845, 14320 kg | 4143-MO-017 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 708 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 4143-MO-018 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 709 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-019 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 710 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-020 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 711 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-021 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 712 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-022 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 713 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-023 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 714 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - YARD MAINTENANCE PLOW/SAND TRUCK - INTERNATIONAL 7600 | 4143-MO-024 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 715 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg | 4143-MO-025 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 716 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - YARD/TOTE ROAD MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 4143-MO-026 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 717 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 4143-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 718 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG450AJ L: 2500, W: 1170, H: 1970, 6010 kg | 4143-MO-029 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 719 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 4143-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 720 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - ORE HAUL TRUCK RECOVERY TOW TRUCK - KENWORTH T800 | 4143-MO-031 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD CULVERT MAINTENANCE STEAM TRUCK - PETERBILT T/A STEAM TRUCK | 4143-MO-032 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 722 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 723 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 724 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 725 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 726 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 727 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FB20PNT L: 3050, W: 1090, H: 2050, 3500 kg | 4143-MO-038 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW706 | 4143-MO-039 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 729 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 4143-MO-040 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - FLAT DECK TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - LARGE MOBILE LIGHT PLANT - TEREX L: 4623, W: 2007, H: 9000, 925 kg |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - PETERBILT |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 616 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-001A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 617 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 618 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 619 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-002A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 620 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 621 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 622 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-003A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 623 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 624 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 625 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-004A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 626 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 627 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 628 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-005A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 629 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 630 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 631 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-006A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 632 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 633 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 634 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-007A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 635 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 636 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 637 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-008A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 638 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 639 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 640 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-009A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 641 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 642 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 643 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-010A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 644 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 645 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 646 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-011A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 647 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 648 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 649 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-012A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 650 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 651 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 652 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-013A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 653 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 654 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 655 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-014A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 656 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 657 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 658 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-015A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 659 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 660 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 661 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-016A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 662 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 663 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 664 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-017A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 665 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 666 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 667 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-018A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 668 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 669 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 670 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-019A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 671 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 672 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 673 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-020A |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 674 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020B |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 675 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020C |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 676 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 42700 kg | 4142-MO-021 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 677 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg | 4142-MO-022 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 678 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H L: 8716, W: 3556, H: 4102, 46300 kg | 4142-MO-023 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 679 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16H L: 9963, W: 3096, H: 3718, 30400 kg | 4142-MO-024 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 680 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg | 4142-MO-026 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 681 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4142-MO-027 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 682 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 683 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-029 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 684 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 685 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-031 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 686 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-032 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 687 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 688 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 689 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 690 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 691 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHING FRONT END LOADER - CAT 988H, L: 10390, W: 3600, H: 4115, 43400 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - ORE HAUL TRUCK FRONT END LOADER - CAT 988H L: 3277, W: 1676, H: 3810, 3175 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT -TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 731 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 4144-MO-001 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 732 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 4144-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 733 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-003 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 734 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-004 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 735 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 4144-MO-005 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 736 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-006 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 737 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - FREIGHT DELIVERY HIBOY TRAILER L: 14630 W: 2438 | 4144-MO-007 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 738 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - DIESEL FUEL TRAILER TRACTOR - WESTERN STAR 4900FA | 4144-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 739 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - JET-A1 FUEL DELIVERY TRUCK - MACK/INNOCAR GU813 L: 8052, W: 2960, H: 3589 | 4144-MO-009 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 740 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - TREMCAR TC406 SUPER B-TRAIN L: 24384, W: 2590, H: 4013, 33500 kg | 4144-MO-010 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 741 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - MOBILE EQUIPMENT LOWBOY TRAILER - SHELTEMA L: 7620, W: 4572 | 4144-MO-011 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 742 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 4144-MO-012 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 743 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-013 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 744 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-014 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 745 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-015 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 746 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-016 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 747 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-017 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 748 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-018 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 749 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Cat 740 | MOBILE EQUIPMENT - ARTICULATED WATER/SAND TRUCK - CAT 740 | 4144-MO-024 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 750 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - ADVANCE | 4144-MO-025 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 751 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 752 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 753 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-031 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 754 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-032 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 755 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 756 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 757 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 758 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 759 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 760 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-040 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 761 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-041 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 762 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-042 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 763 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-043 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 764 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-044 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 765 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-045 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - COACH PASSENGER TRANSFER BUS |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - FREIGHTLINER |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - INTERNATIONAL |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Trailer | MOBILE EQUIPMENT - Live Bottom Trailer |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Ford Truck | MOBILE EQUIPMENT - MAINTENANCE LUBE TRUCK - Ford |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage vacuum truck | MOBILE EQUIPMENT - SEWAGE VACUUM TRUCK - FREIGHTLINER |  |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT (5400 GAL) |  |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 777 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single | 4213-BLD-001 | 33.4572 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 18.75 | 112.5 | 1873.3759 | 2812.5 | 4798.3759 | 1 | 33.4572 | 100% | 0% | 0% | 100% | 4798.3759 | 0 | 0 | 4798.3759 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1599.4586 | 1599.4586 | 1599.4586 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 778 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Magazines - Demolish and foundations - Gravel Base - Skidded Building | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 779 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Magazines - Demolish floor finish - Raised Steel or Wooden Floor | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 769 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4211-BLD-001 | 342.0074 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 191.6667 | 1150 | 19150.0647 | 28750 | 49050.0647 | 1 | 342.0074 | 100% | 0% | 0% | 100% | 49050.0647 | 0 | 0 | 49050.0647 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 16350.0216 | 16350.0216 | 16350.0216 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 770 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Plant Building - Demolish and foundations - Gravel Base - Skidded Building | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 771 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Plant Building - Demolish floor finish - Raised Steel or Wooden Floor | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4212-BLD-001 | 371.7472 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 208.3333 | 875 | 20815.2877 | 31250 | 52940.2877 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 52940.2877 | 0 | 0 | 52940.2877 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 17646.7626 | 17646.7626 | 17646.7626 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 130 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 72.8542 | 305.9875 | 7279.1061 | 10928.125 | 18513.2186 | 1 | 130 | 100% | 0% | 0% | 100% | 18513.2186 | 0 | 0 | 18513.2186 | Type A 2AM-MRY1325 |  | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6171.0729 | 6171.0729 | 6171.0729 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 775 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Explosives Shop - Demolish floor finish - Slab on grade C/W Drainage | 4212-BLD-001 | 371.7472 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 46.4684 | 697.026 | 4642.8151 | 6970.2602 | 12310.1013 | 0 | 0 | 100% | 0% | 0% | 100% | 12310.1013 | 0 | 0 | 12310.1013 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4103.3671 | 4103.3671 | 4103.3671 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 774 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Shop - Demolish and foundations - Gravel Base - Skidded Building | 4212-BLD-001 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Explosives Facility | 4222 | Explosive pad haul road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive pad haul road |  | 19600 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 248.7217 | 2866.5 | 24872.1666 | 7772.2888 | 35510.9554 | 0 | 0 | 100% | 0% | 0% | 100% | 35510.9554 | 0 | 0 | 35510.9554 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11836.9851 | 11836.9851 | 11836.9851 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Haul Roads | 4221 | Pit 1 Haul Road | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Dump |  | 190000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 2411.0774 | 27787.5 | 241107.7378 | 75343.6157 | 190000 | 0 | 0 | 100% | 0% | 0% | 100% | 190000 | 0 | 0 | 190000 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 63333.3333 | 63333.3333 | 63333.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 6000 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 266.9393 | 1068.3 | 26693.9286 | 4287.2721 | 32049.5006 | 0 | 0 | 100% | 0% | 0% | 100% | 32049.5006 | 0 | 0 | 32049.5006 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10683.1669 | 10683.1669 | 10683.1669 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2008 Bulk Sample Pit |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 2008 bulk sample PWSP |  |  | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 |  | 55000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 697.9435 | 8043.75 | 69794.3452 | 21809.994 | 99648.0892 | 0 | 0 | 100% | 0% | 0% | 100% | 99648.0892 | 0 | 0 | 99648.0892 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 49824.0446 | 49824.0446 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 - Marginal increase |  | 214450 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 2721.345 | 31363.3125 | 272134.4967 | 85039.1494 | 388217.8369 | 0 | 0 | 100% | 0% | 0% | 100% | 388217.8369 | 0 | 0 | 388217.8369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 194108.9185 | 194108.9185 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 6967 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 309.961 | 1240.4743 | 30996.1 | 4978.2374 | 36982.8937 | 0 | 0 | 100% | 0% | 0% | 100% | 36982.8937 | 0 | 0 | 36982.8937 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 36982.8937 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-3 | 6511 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 289.6736 | 1159.2835 | 28967.3615 | 4652.4047 | 34562.311 | 0 | 0 | 100% | 0% | 0% | 100% | 34562.311 | 0 | 0 | 34562.311 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 34562.311 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 3720 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 165.5024 | 662.346 | 16550.2357 | 2658.1087 | 19746.8587 | 0 | 0 | 100% | 0% | 0% | 100% | 19746.8587 | 0 | 0 | 19746.8587 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 19746.8587 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 789 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 44.6097 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 10 | 150 | 999.1338 | 1500 | 2649.1338 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2649.1338 | 0 | 0 | 2649.1338 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 883.0446 | 883.0446 | 883.0446 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 786 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Pit Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4281-BLD-001 | 267.658 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 60 | 900 | 5994.8029 | 9000 | 15894.8029 | 1 | 267.658 | 100% | 0% | 0% | 100% | 15894.8029 | 0 | 0 | 15894.8029 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5298.2676 | 5298.2676 | 5298.2676 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 787 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-001 | 267.658 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 33 | 315 | 2098.181 | 3150 | 5563.181 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5563.181 | 0 | 0 | 5563.181 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1854.3937 | 1854.3937 | 1854.3937 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 790 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Pit Office Washcar - Demolish and foundations - Gravel Base - Skidded Building | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 791 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 788 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Lunchroom Building - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Lunchroom Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-002 | 0 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Lunchroom Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-001 | 72 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 16.14 | 242.1 | 1612.602 | 2421 | 4275.702 | 1 | 72 | 100% | 0% | 0% | 100% | 4275.702 | 0 | 0 | 4275.702 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1425.234 | 1425.234 | 1425.234 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-002 | 54 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 12.105 | 181.575 | 1209.4515 | 1815.75 | 3206.7765 | 1 | 54 | 100% | 0% | 0% | 100% | 3206.7765 | 0 | 0 | 3206.7765 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1068.9255 | 1068.9255 | 1068.9255 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-003 | 36 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.07 | 121.05 | 806.301 | 1210.5 | 2137.851 | 1 | 36 | 100% | 0% | 0% | 100% | 2137.851 | 0 | 0 | 2137.851 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 712.617 | 712.617 | 712.617 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-004 | 25 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 5.6042 | 84.0625 | 559.9312 | 840.625 | 1484.6187 | 1 | 25 | 100% | 0% | 0% | 100% | 1484.6187 | 0 | 0 | 1484.6187 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 494.8729 | 494.8729 | 494.8729 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Ore crushing and Loading Pad, Utility & Accommodation Pads |  | 121021 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 1535.7421 | 17699.3212 | 153574.2081 | 47990.3143 | 219263.8436 | 0 | 0 | 100% | 0% | 0% | 100% | 219263.8436 | 0 | 0 | 219263.8436 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 73087.9479 | 73087.9479 | 73087.9479 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiles |  | 5100.23 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 64.7213 | 745.9086 | 6472.1311 | 2022.4725 | 9240.5123 | 0 | 0 | 100% | 0% | 0% | 100% | 9240.5123 | 0 | 0 | 9240.5123 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3080.1708 | 3080.1708 | 3080.1708 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 795 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-001 | 39.4052 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 22.0833 | 132.5 | 2206.4205 | 3312.5 | 5651.4205 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 5651.4205 | 0 | 0 | 5651.4205 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1883.8068 | 1883.8068 | 1883.8068 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 798 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-002 | 39.4052 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 22.0833 | 132.5 | 2206.4205 | 3312.5 | 5651.4205 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 5651.4205 | 0 | 0 | 5651.4205 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1883.8068 | 1883.8068 | 1883.8068 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 801 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 1 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-001 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 802 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-003 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 803 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-005 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 804 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 2 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-006 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 805 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-008 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 806 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-010 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 815 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 1 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-002 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 816 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 1 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-004 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 817 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 2 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-007 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 818 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 2 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-009 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 796 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 797 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 799 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 800 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 807 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-011 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 808 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-012 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 809 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-013 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 810 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-014 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 811 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-015 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 812 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-016 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 813 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-017 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 814 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-018 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Chain Conveyor | Chain Conveyor (1 for under jaw crusher, 1 for under crusher bin) |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Conveyors |  | 4 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 672 | 8880 | 67141.792 | 88800 | 164821.792 | 56 | 224 | 100% | 0% | 0% | 100% | 164821.792 | 0 | 0 | 164821.792 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 54940.5973 | 0 | 54940.5973 | 0 | 0 | 0 | 0 | 54940.5973
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Electrical sub station |  | 3 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 504 | 6660 | 50356.344 | 66600 | 123616.344 | 56 | 168 | 100% | 0% | 0% | 100% | 123616.344 | 0 | 0 | 123616.344 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 41205.448 | 0 | 41205.448 | 0 | 0 | 0 | 0 | 41205.448
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Genset Trailers |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Screener |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Inclined Screen |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Cone Crusher |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Screener Power Screener |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 3 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | PRIMARY SCREENING PLANT LINE 3 - METSO FS303 |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREENING PLANT LINE 3 - METSO FS 353 L: 3000, W: 6900, 14500 kg |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600 |  | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Jaw Plant | Spread A, Primary Jaw Plant | MR-PRO-CRU-010-PJP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Primary Jaw Plant | Spread B, Primary Jaw Plant | MR-PRO-CRU-020-PJP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Jaw Plant | Spread C, Primary Jaw Plant | MR-PRO-CRU-030-PJP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Secondary Cone Feed | Spread A, Secondary Cone Feed | MR-PRO-CRU-010-PCF01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Screen Plant Discharge | Spread A, Primary Screen Plant Discharge | MR-PRO-CRU-010-PSD01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Screen Plant | Spread A, Primary Screen Plant | MR-PRO-CRU-010-PSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Secondary Cone Plant | Spread A, Secondary Cone Plant | MR-PRO-CRU-010-SCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Tertiary Cone Plant | Spread A, Tertiary Cone Plant | MR-PRO-CRU-010-TCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Twin Screen Plant | Spread A, Twin Screen Plant | MR-PRO-CRU-010-TSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Secondary Cone Feed | Spread B, Secondary Cone Feed | MR-PRO-CRU-020-PCF01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Primary Screen Plant | Spread B, Primary Screen Plant | MR-PRO-CRU-020-PSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Secondary Cone Plant | Spread B, Secondary Cone Plant | MR-PRO-CRU-020-SCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Tertiary Cone Plant | Spread B, Tertiary Cone Plant | MR-PRO-CRU-020-TCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Twin Screen Plant | Spread B, Twin Screen Plant | MR-PRO-CRU-020-TSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Secondary Cone Feed | Spread C, Secondary Cone Feed | MR-PRO-CRU-030-PCF01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Screen Plant Discharge | Spread C, Primary Screen Plant Discharge | MR-PRO-CRU-030-PSD01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Screen Plant | Spread C, Primary Screen Plant | MR-PRO-CRU-030-PSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Secondary Cone Plant | Spread C, Secondary Cone Plant | MR-PRO-CRU-030-SCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Tertiary Cone Plant | Spread C, Tertiary Cone Plant | MR-PRO-CRU-030-TCP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Twin Screen Plant | Spread C, Twin Screen Plant | MR-PRO-CRU-030-TSP01 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | AIM | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Control Room | Spread A, Control Room | MR-PRO-CRU-010-COR01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Fine Discharge | Spread A, Fine Discharge | MR-PRO-CRU-010-FID01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Lumps Discharge | Spread A, Lumps Discharge | MR-PRO-CRU-010-LUD01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | AIM | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Control Room | Spread B, Control Room | MR-PRO-CRU-020-COR01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Fine Discharge | Spread B, Fine Discharge | MR-PRO-CRU-020-FID01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Lumps Discharge | Spread B, Lumps Discharge | MR-PRO-CRU-020-LUD01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Primary Screen Plant Discharge | Spread B, Primary Screen Plant Discharge | MR-PRO-CRU-020-PSD01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread C, Fine Discharge | Spread C, Fine Discharge | MR-PRO-CRU-030-FID01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread C, Lumps Discharge | Spread C, Lumps Discharge | MR-PRO-CRU-030-LUD01 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Drill | Quarry Drills |  | 10 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 192 | 2130 | 19183.3691 | 21300 | 42613.3691 | 1 | 10 | 100% | 0% | 0% | 100% | 42613.3691 | 0 | 0 | 42613.3691 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 21306.6846 | 21306.6846 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | Mobile Crusher/Screener |  | 4 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 672 | 8880 | 67141.792 | 88800 | 164821.792 | 56 | 224 | 100% | 0% | 0% | 100% | 164821.792 | 0 | 0 | 164821.792 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 54940.5973 | 0 | 54940.5973 | 0 | 0 | 0 | 0 | 54940.5973
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 828 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Stockpile Drain Pipe - Piping Installation - Ore stockpile to effluent pond and Mary River | 4385.1-P | 5220 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 1305 | 19575 | 130386.9621 | 195750 | 345711.9621 | 0.01 | 52.2 | 100% | 0% | 100% | 0% | 345711.9621 | 0 | 345711.9621 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 115237.3207 | 115237.3207 | 115237.3207 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Crushing Sedimentation Pond |  | 6428.69 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 286.0117 | 1144.6283 | 28601.1653 | 4593.5905 | 34339.384 | 0 | 0 | 100% | 0% | 0% | 100% | 34339.384 | 0 | 0 | 34339.384 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11446.4613 | 11446.4613 | 11446.4613 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 825 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 826 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 827 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Stockpile Drain Pipe - Heat Trace Installation - Ore stockpile to effluent pond and Mary River | 4385.1-E | 2610 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Crusher Pad Sedimentation Pond 2018 |  | 4500 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 200.2045 | 801.225 | 20020.4464 | 3215.4541 | 24037.1255 | 0 | 0 | 100% | 0% | 0% | 100% | 24037.1255 | 0 | 0 | 24037.1255 | Type A 2AM-MRY1325 | Added | 2018-C3 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8012.3752 | 8012.3752 | 8012.3752 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 820 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4382-BLD-001 | 334.5725 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 187.5 | 787.5 | 18733.7589 | 28125 | 47646.2589 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 47646.2589 | 0 | 0 | 47646.2589 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15882.0863 | 15882.0863 | 15882.0863 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 821 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Weigh Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4382-BLD-001 | 334.5725 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 48.582 | 728.7306 | 4853.9957 | 7287.3058 | 12870.0321 | 0.75 | 250.9294 | 100% | 0% | 0% | 100% | 12870.0321 | 0 | 0 | 12870.0321 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4290.0107 | 4290.0107 | 4290.0107 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 823 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - TRUCK WEIGH SCALE - RICE LAKE OTR-XV L: 36600 W: 3960, H: 1030 | 4382-SC-001 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 822 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Weigh Building - Demolish floor finish - Gravel | 4382-BLD-001 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Truck Weigh Facility disturbed area |  | 13000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 164.9685 | 1901.25 | 16496.8452 | 5155.0895 | 23553.1847 | 0 | 0 | 100% | 0% | 0% | 100% | 23553.1847 | 0 | 0 | 23553.1847 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [7 empty] | 0 |  | 23553.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome
4000 | Mine Site | 4400 | Aerodrome | 4410 | Runway & Apron | 4410 | Runway & Apron | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Heli Pad |  | 5776 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 73.2968 | 844.74 | 7329.6752 | 2290.4459 | 10464.8611 | 0 | 0 | 100% | 0% | 0% | 100% | 10464.8611 | 0 | 0 | 10464.8611 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3488.287 | 3488.287 | 3488.287 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 839 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4431-TK-004 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 833 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 4431-BLD-001 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 838 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4431-TK-001 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 834 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4431-BLD-001 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 836 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 4431-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 837 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4431-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 835 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 4431-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4436 | Airfield Lighting and Visual Aids | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4521-BLD-003 | 1296 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 726.3 | 3050.46 | 72567.0886 | 108945 | 184562.5486 | 1 | 1296 | 100% | 0% | 0% | 100% | 184562.5486 | 0 | 0 | 184562.5486 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 61520.8495 | 61520.8495 | 61520.8495 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4521-BLD-003 | 1296 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 188.1874 | 2822.8108 | 18802.4378 | 28228.1076 | 49853.3562 | 0.75 | 972 | 100% | 0% | 0% | 100% | 49853.3562 | 0 | 0 | 49853.3562 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 16617.7854 | 16617.7854 | 16617.7854 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4521-BLD-003 | 1296 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 162 | 2430 | 16185.9677 | 24300 | 42915.9677 | 0 | 0 | 100% | 0% | 0% | 100% | 42915.9677 | 0 | 0 | 42915.9677 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 14305.3226 | 14305.3226 | 14305.3226 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 850 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4435-BLD-001 | 14.8699 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 8.3333 | 50 | 832.6115 | 1250 | 2132.6115 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 2132.6115 | 0 | 0 | 2132.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 710.8705 | 710.8705 | 710.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 851 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Field Electrical Centre - Demolish and foundations - Gravel Base - Skidded Building | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 852 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Field Electrical Centre - Demolish floor finish - Raised Steel or Wooden Floor | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 845 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | x-ray | AERODROME EQUIPMENT - SECURITY X-RAY MACHINE L: 2282, W: 1030, H: 1467 | 4433-AE-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 846 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT GROUND POWER UNIT | 4433-AE-015 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 847 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT PASSENGER STAIRS L: 9906, W: 2565, H: 3048 | 4433-AE-023 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4434 | Plant & Equipment | 848 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Bus sized | MOBILE EQUIPMENT - AIRPORT MAINTENANCE DE-ICING TRUCK - FORD SUPERIOR | 4434-MO-002 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4439 | Power Generation | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 899 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-001 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 902 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-002 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 905 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-003 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 908 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-004 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 911 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-005 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 914 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-006 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 917 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-007 | 611.803 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.1458 | 2057.1875 | 13702.7039 | 20571.875 | 36331.7664 | 1 | 611.803 | 100% | 0% | 0% | 100% | 36331.7664 | 0 | 0 | 36331.7664 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12110.5888 | 12110.5888 | 12110.5888 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 900 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AA - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 901 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AA - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 903 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AB - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 904 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AB - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 906 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AC - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 907 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AC - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 909 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AD - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 910 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AD - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 912 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AE - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 913 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AE - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 915 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AF - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 916 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AF - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 918 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AG - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 919 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AG - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-008 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AH - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AH - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AI - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-009 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AI - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AI - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AJ - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-010 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AJ - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AJ - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AK - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-011 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AK - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AK - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AL - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-012 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AL - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AL - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AM - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-013 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AM - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AM - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – West side |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – East Side |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 50 units @ 36 m2 per wash car) |  | 1218 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 273.035 | 4095.525 | 27279.85 | 40955.25 | 72330.625 | 1 | 1218 | 100% | 0% | 0% | 100% | 72330.625 | 0 | 0 | 72330.625 | Type B Construction 2BC-MRY1416 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24110.2083 | 24110.2083 | 24110.2083 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 48.42 | 726.3 | 4837.8059 | 7263 | 12827.1059 | 1 | 216 | 100% | 0% | 0% | 100% | 12827.1059 | 0 | 0 | 12827.1059 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4275.702 | 4275.702 | 4275.702 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 50 person camp at Mine Site |  | 50 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 35040.0455 | 0 | 0 | 35040.0455 | 0 | 0 | 100% | 0% | 0% | 100% | 35040.0455 | 0 | 0 | 35040.0455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 35040.0455 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 50- Person Rapid Deploy Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 170.3667 | 2555.5 | 17021.9097 | 25555 | 45132.4097 | 0.5 | 475 | 100% | 0% | 0% | 100% | 45132.4097 | 0 | 0 | 45132.4097 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 45132.4097 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 35- Person 'Norse-man Style' Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 170.3667 | 2555.5 | 17021.9097 | 25555 | 45132.4097 | 0.5 | 475 | 100% | 0% | 0% | 100% | 45132.4097 | 0 | 0 | 45132.4097 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 45132.4097 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 800 person camp at Mine Site |  | 800 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 560640.7273 | 0 | 0 | 560640.7273 | 0 | 0 | 100% | 0% | 0% | 100% | 560640.7273 | 0 | 0 | 560640.7273 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 560640.7273 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4510 | Accommodations Area | 857 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 4510-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 924 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4513-BLD-002 | 278.8104 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 43.75 | 656.25 | 4371.2104 | 6562.5 | 11589.9604 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 11589.9604 | 0 | 0 | 11589.9604 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3863.3201 | 3863.3201 | 3863.3201 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 925 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 4513-BLD-002 | 278.8104 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 40.485 | 607.2755 | 4044.9964 | 6072.7548 | 10725.0267 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 10725.0267 | 0 | 0 | 10725.0267 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3575.0089 | 3575.0089 | 3575.0089 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 926 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 4513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 34.8513 | 522.7695 | 3482.1113 | 5227.6952 | 9232.576 | 0 | 0 | 100% | 0% | 0% | 100% | 9232.576 | 0 | 0 | 9232.576 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3077.5253 | 3077.5253 | 3077.5253 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 937 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4513-TK-004 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 921 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4513-BLD-001 | 89.2193 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 20 | 300 | 1998.2676 | 3000 | 5298.2676 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 5298.2676 | 0 | 0 | 5298.2676 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1766.0892 | 1766.0892 | 1766.0892 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 939 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 4513-TK-023 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 938 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4513-TK-005 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 922 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4513-BLD-001 | 89.2193 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 11 | 105 | 699.3937 | 1050 | 1854.3937 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1854.3937 | 0 | 0 | 1854.3937 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 618.1312 | 618.1312 | 618.1312 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 930 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4513-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 931 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4513-MT-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 932 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 933 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 934 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 935 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 936 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 4513-SQ-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 923 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 4513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 927 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F450 L: 6680, W: 2438, H: 2024, 6350 kg | 4513-MO-001 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 928 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | large fire truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH TI3000 L: 10922 W: 2921, H: 3607, 39000 kg | 4513-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 929 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small tank | MOBILE EQUIPMENT - SNOW RESCUE VEHICLE - HAGGLUND BV206 L: 6900, W: 1870, H: 2400, 6580 kg | 4513-MO-003 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 859 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 1856.8773 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 416.25 | 6243.75 | 41588.9448 | 62437.5 | 110270.1948 | 1 | 1856.8773 | 100% | 0% | 0% | 100% | 110270.1948 | 0 | 0 | 110270.1948 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 36756.7316 | 36756.7316 | 36756.7316 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 862 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-002 | 607.8067 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 136.25 | 2043.75 | 13613.1982 | 20437.5 | 36094.4482 | 1 | 607.8067 | 100% | 0% | 0% | 100% | 36094.4482 | 0 | 0 | 36094.4482 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12031.4827 | 12031.4827 | 12031.4827 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 865 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-003 | 423.7918 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 95 | 1425 | 9491.7712 | 14250 | 25166.7712 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 25166.7712 | 0 | 0 | 25166.7712 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8388.9237 | 8388.9237 | 8388.9237 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 868 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laboratory - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-004 | 312.2677 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 70 | 1050 | 6993.9367 | 10500 | 18543.9367 | 1 | 312.2677 | 100% | 0% | 0% | 100% | 18543.9367 | 0 | 0 | 18543.9367 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6181.3122 | 6181.3122 | 6181.3122 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 871 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 872 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 873 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR DRYER | 4511-LE-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 874 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 875 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 876 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 877 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CARBON/SULFUR ANALYSER | 4511-LE-007 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 878 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CHILLER | 4511-LE-008 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 879 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER | 4511-LE-016 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 880 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER DUST HOOD | 4511-LE-017 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 881 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-018 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 882 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-019 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 883 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DUST COLLECTOR | 4511-LE-020 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 884 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUMEHOOD | 4511-LE-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 885 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUSION SYSTEM | 4511-LE-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 886 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - HOT PLATE | 4511-LE-023 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 887 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MUFFLE FURNACE | 4511-LE-024 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 888 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-027 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 889 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-028 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 890 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER DUST HOOD | 4511-LE-029 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 891 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP | 4511-LE-030 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 892 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP DUST HOOD | 4511-LE-031 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 893 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MAGNETITE ANALYSER | 4511-LE-032 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 894 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - SCRUBBER FAN | 4511-LE-033 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 895 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LABORATORY EQUIPMENT - SCRUBBER RECIRCULATION PUMP | 4511-LE-034 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 896 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - THERMOGRAVIMETRIC ANALYSER | 4511-LE-035 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 897 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - XRF SPECTROMETER | 4511-LE-036 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 869 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laboratory - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 870 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laboratory - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 866 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 867 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 863 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 864 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 860 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 861 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-005 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-006 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 4333 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 629.179 | 9437.6844 | 62863.3974 | 94376.8445 | 166677.9263 | 0.75 | 3249.75 | 100% | 0% | 0% | 100% | 166677.9263 | 0 | 0 | 166677.9263 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 55559.3088 | 55559.3088 | 55559.3088 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 13000 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 2914.1667 | 43712.5 | 291164.2443 | 437125 | 772001.7443 | 1 | 13000 | 100% | 0% | 0% | 100% | 772001.7443 | 0 | 0 | 772001.7443 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 257333.9148 | 257333.9148 | 257333.9148 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 975 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4521-TK-053 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-005 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 942 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-001 | 2416.3569 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 1354.1667 | 5687.5 | 135299.37 | 203125 | 344111.87 | 1 | 2416.3569 | 100% | 0% | 0% | 100% | 344111.87 | 0 | 0 | 344111.87 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 114703.9567 | 114703.9567 | 114703.9567 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 945 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-002 | 892.1933 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 500 | 2100 | 49956.6905 | 75000 | 127056.6905 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 127056.6905 | 0 | 0 | 127056.6905 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 42352.2302 | 42352.2302 | 42352.2302 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 943 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-001 | 2416.3569 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 350.8703 | 5263.0542 | 35056.6357 | 52630.5417 | 92950.2316 | 0.75 | 1812.2677 | 100% | 0% | 0% | 100% | 92950.2316 | 0 | 0 | 92950.2316 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 30983.4105 | 30983.4105 | 30983.4105 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 944 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-001 | 2416.3569 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 302.0446 | 4530.6691 | 30178.2982 | 45306.6914 | 80015.6587 | 0 | 0 | 100% | 0% | 0% | 100% | 80015.6587 | 0 | 0 | 80015.6587 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 26671.8862 | 26671.8862 | 26671.8862 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 948 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-003 | 390.3346 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 218.75 | 918.75 | 21856.0521 | 32812.5 | 55587.3021 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 55587.3021 | 0 | 0 | 55587.3021 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 18529.1007 | 18529.1007 | 18529.1007 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-004 | 267.658 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 150 | 900 | 14987.0071 | 22500 | 38387.0071 | 1 | 267.658 | 100% | 0% | 0% | 100% | 38387.0071 | 0 | 0 | 38387.0071 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12795.669 | 12795.669 | 12795.669 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 946 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-002 | 892.1933 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 129.5521 | 1943.2815 | 12943.9886 | 19432.8154 | 34320.0855 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 34320.0855 | 0 | 0 | 34320.0855 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11440.0285 | 11440.0285 | 11440.0285 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 947 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Warehouse - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-002 | 892.1933 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 111.5242 | 1672.8625 | 11142.7562 | 16728.6245 | 29544.2432 | 0 | 0 | 100% | 0% | 0% | 100% | 29544.2432 | 0 | 0 | 29544.2432 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9848.0811 | 9848.0811 | 9848.0811 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 976 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 4521.5-P | 405 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 101.25 | 1518.75 | 10116.2298 | 15187.5 | 26822.4798 | 0.01 | 4.05 | 100% | 0% | 100% | 0% | 26822.4798 | 0 | 26822.4798 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8940.8266 | 8940.8266 | 8940.8266 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 949 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-003 | 390.3346 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 56.679 | 850.1857 | 5662.995 | 8501.8567 | 15015.0374 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 15015.0374 | 0 | 0 | 15015.0374 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5005.0125 | 5005.0125 | 5005.0125 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 950 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-003 | 390.3346 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 48.7918 | 731.8773 | 4874.9559 | 7318.7732 | 12925.6064 | 0 | 0 | 100% | 0% | 0% | 100% | 12925.6064 | 0 | 0 | 12925.6064 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4308.5355 | 4308.5355 | 4308.5355 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 974 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 4521-TK-050 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 955 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-005 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 952 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-004 | 267.658 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 33 | 315 | 2098.181 | 3150 | 5563.181 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5563.181 | 0 | 0 | 5563.181 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1854.3937 | 1854.3937 | 1854.3937 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 969 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4521-PP-051 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 971 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 4521-TK-005 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 972 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL TANK | 4521-TK-013 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 973 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WAREHOUSE BUILDING DIESEL TANK | 4521-TK-023 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 956 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-005 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 957 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 958 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 959 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 960 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 961 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 962 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 963 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 964 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 965 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 966 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-021 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 967 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 968 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-022 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 970 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4521-MT-051 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 953 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-004 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mine Truck Workshop (2018) |  | 2050 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 1148.8542 | 4825.1875 | 114785.904 | 172328.125 | 291939.2165 | 1 | 2050 | 100% | 0% | 0% | 100% | 291939.2165 | 0 | 0 | 291939.2165 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 97313.0722 | 97313.0722 | 97313.0722 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Rolling Stock Workshop (2018) |  | 2050 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 1148.8542 | 4825.1875 | 114785.904 | 172328.125 | 291939.2165 | 1 | 2050 | 100% | 0% | 0% | 100% | 291939.2165 | 0 | 0 | 291939.2165 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 97313.0722 | 97313.0722 | 97313.0722 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-007 | 0 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-007 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-007 | 0 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Truck Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-008 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Truck Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-008 | 0 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Truck Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Maintenance Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-006 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Maintenance Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-006 | 0 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Maintenance Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-009 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-009 | 0 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER TANK - SIMER JET PUMPS 2205C L: 1803, W: 1245, H: 1346 |  | 0 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK |  | 0 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER PUMP - PLASTIC-MART L: 483, W: 275, H: 267 |  | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 91.0263 | 364.2903 | 9102.6296 | 1461.9598 | 10928.8797 | 0 | 0 | 100% | 0% | 0% | 100% | 10928.8797 | 0 | 0 | 10928.8797 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3642.9599 | 3642.9599 | 3642.9599 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 979 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - KIDNEY LOOP - AG - DYE10MFP240SA10QBV 50 kg | 4522-SQ-002 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 982 | MT- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | LATHE SPINDLE MOTOR | 4522-MT-004A | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 978 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - INDUSTRIAL FREEZER - ONTARIO OVENS 80-12 L: 1525, W: 715, H: 1250, 290 kg | 4522-SQ-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 980 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LARGE SHOP PRESS - AG - OTC1866 L: 1295, W: 1727, H: 3125, 1970 kg | 4522-SQ-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 981 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LATHE - SUMMIT MACHINE TOOL W: 44, H: 64 | 4522-SQ-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 983 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LATHE COOLANT PUMP | 4522-MT-004B | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 984 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MILLING MACHINE - AG | 4522-SQ-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 985 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LINE BORING MACHINE - CLIMAX BB5000 L: 1830 W: 330 H: 280 205 kg | 4522-SQ-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 986 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - IRON WORKER - BAILEIGH INDUSTRIAL 001-99777 L: 1525, W: 915, H: 1985, 2300 kg | 4522-SQ-008 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 987 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HEAVY TRUCK RAMP - ROTARY 60000HDL L: 13360, W: 4980, H: 3990 | 4522-SQ-009 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 988 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LIGHT TRUCK RAMP - ROTARY SM18LO-X H: 6990 | 4522-SQ-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 989 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SIPING MACHINE - AG | 4522-SQ-011 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 990 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - AIR FILTER CLEANER - DIVERSI-TECH L: 1830, W: 1830, H: 2650 | 4522-SQ-012 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 991 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-018 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 992 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-019 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 993 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 4522-SQ-021 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 994 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 4522-SQ-022 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 995 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 4522-SQ-023 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 996 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-026 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 997 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-027 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 998 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 4522-SQ-028 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 999 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 4522-SQ-029 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1000 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 4522-SQ-031 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1001 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 4522-SQ-036 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1002 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG | 4522-SQ-038 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1003 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 4522-SQ-041 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1004 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-042 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1005 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-043 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1006 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 4522-SQ-044 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1007 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - METAL BREAK FLOOR - AG - GGS13W877 580 kg | 4522-SQ-046 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1008 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-047 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1009 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-048 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1010 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-049 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1011 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-050 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1012 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 4522-SQ-051 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1013 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 4522-SQ-052 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1014 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-053 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-053 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1016 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-054 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1017 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-054 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1026 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - INCHING TOOL - AG | 4522-SQ-065 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1027 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-066 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1028 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-067 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1018 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-055 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1019 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-055 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1020 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-056 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1021 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-056 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1022 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 4522-SQ-059 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1023 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 4522-SQ-060 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1024 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG - OTC4240 | 4522-SQ-063 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1025 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584 W: 864 H: 1120 110 kg | 4522-SQ-064 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1029 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 4522-SQ-068 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Tire Shop at Ore Haul Truck Lineup (seacan construction) |  | 500 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 280.2083 | 1681.25 | 27996.562 | 42031.25 | 71709.062 | 1 | 500 | 100% | 0% | 0% | 100% | 71709.062 | 0 | 0 | 71709.062 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 35854.531 | 35854.531 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | Light Plant |  | 10 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 81 | 1065 | 8092.9839 | 10650 | 19807.9839 | 0.5 | 5 | 100% | 0% | 0% | 100% | 19807.9839 | 0 | 0 | 19807.9839 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6602.6613 | 0 | 6602.6613 | 0 | 0 | 0 | 0 | 6602.6613
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | Frost Fighter Heater |  | 10 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 81 | 1065 | 8092.9839 | 10650 | 19807.9839 | 0.5 | 5 | 100% | 0% | 0% | 100% | 19807.9839 | 0 | 0 | 19807.9839 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6602.6613 | 0 | 6602.6613 | 0 | 0 | 0 | 0 | 6602.6613
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Heater | Frost Fighter Heater | MR-FAC-POH-010 | 52 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 421.2 | 5538 | 42083.5161 | 55380 | 103001.5161 | 0.5 | 26 | 100% | 0% | 0% | 100% | 103001.5161 | 0 | 0 | 103001.5161 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 34333.8387 | 0 | 34333.8387 | 0 | 0 | 0 | 0 | 34333.8387
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | HOB | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Hot Box | Hot Box Heater | MR-FAC-POH-020 | 4 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 32.4 | 426 | 3237.1935 | 4260 | 7923.1935 | 0.5 | 2 | 100% | 0% | 0% | 100% | 7923.1935 | 0 | 0 | 7923.1935 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2641.0645 | 0 | 2641.0645 | 0 | 0 | 0 | 0 | 2641.0645
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-001 | 1003.7175 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 562.5 | 2362.5 | 56201.2768 | 84375 | 142938.7768 | 1 | 1003.7175 | 100% | 0% | 0% | 100% | 142938.7768 | 0 | 0 | 142938.7768 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 47646.2589 | 47646.2589 | 47646.2589 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-001 | 1003.7175 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 145.7461 | 2186.1917 | 14561.9872 | 21861.9173 | 38610.0962 | 0.75 | 752.7881 | 100% | 0% | 0% | 100% | 38610.0962 | 0 | 0 | 38610.0962 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12870.0321 | 12870.0321 | 12870.0321 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1038 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - TRUCK WASH BUILDING DIESEL TANK | 4523-TK-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1034 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (DUTY) | 4523-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1035 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1036 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (STANDBY) | 4523-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1037 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1033 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-001 | 1003.7175 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Additional Truck Wash Building |  | 1500 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 840.625 | 3530.625 | 83989.6859 | 126093.75 | 213614.0609 | 1 | 1500 | 100% | 0% | 0% | 100% | 213614.0609 | 0 | 0 | 213614.0609 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 71204.687 | 71204.687 | 71204.687 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Additional Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 1500 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 217.8095 | 3267.1421 | 21762.0808 | 32671.4209 | 57700.6438 | 0.75 | 1125 | 100% | 0% | 0% | 100% | 57700.6438 | 0 | 0 | 57700.6438 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 19233.5479 | 19233.5479 | 19233.5479 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1038 |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Additional Truck Wash Building - Truck Wash System |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Ore Haul Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-002 | 0 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Ore Haul Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-002 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Ore Haul Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical Office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-001 | 20 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 4.4833 | 67.25 | 447.945 | 672.5 | 1187.695 | 1 | 20 | 100% | 0% | 0% | 100% | 1187.695 | 0 | 0 | 1187.695 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 395.8983 | 395.8983 | 395.8983 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Additional Buildings by BIM Site Services slab on grade |  | 180 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 22.5 | 337.5 | 2248.0511 | 3375 | 5960.5511 | 0 | 0 | 100% | 0% | 0% | 100% | 5960.5511 | 0 | 0 | 5960.5511 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1986.8504 | 1986.8504 | 1986.8504 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | Generator for 380-person temporary soft-walled camp |  | 2 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 38.4 | 426 | 3836.6738 | 4260 | 8522.6738 | 1 | 2 | 100% | 0% | 0% | 100% | 8522.6738 | 0 | 0 | 8522.6738 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2840.8913 | 0 | 2840.8913 | 0 | 0 | 0 | 0 | 2840.8913
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1059 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-007 | 66.9145 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 37.5 | 225 | 3746.7518 | 5625 | 9596.7518 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 9596.7518 | 0 | 0 | 9596.7518 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3198.9173 | 3198.9173 | 3198.9173 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1062 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-008 | 66.9145 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 37.5 | 225 | 3746.7518 | 5625 | 9596.7518 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 9596.7518 | 0 | 0 | 9596.7518 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3198.9173 | 3198.9173 | 3198.9173 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1041 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-001 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1044 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-002 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1047 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-003 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1050 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-004 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1053 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-005 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1056 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-006 | 51.9517 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1146 | 174.6875 | 2908.9365 | 4367.1875 | 7450.8115 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 7450.8115 | 0 | 0 | 7450.8115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2483.6038 | 2483.6038 | 2483.6038 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1065 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 4530-BLD-009 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1421.741 | 1421.741 | 1421.741 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1066 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1067 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1042 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1043 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1045 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1046 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1048 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1049 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1051 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1052 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1054 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1055 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1057 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1058 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1060 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1061 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1063 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1064 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-002 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-022 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-023 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #9 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-026 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #9 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #9 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #10 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-027 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #10 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #10 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-029 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-030 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 0 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-002 | 20 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 3.1383 | 47.075 | 313.5615 | 470.75 | 831.3865 | 1 | 20 | 100% | 0% | 0% | 100% | 831.3865 | 0 | 0 | 831.3865 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 277.1288 | 277.1288 | 277.1288 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-002 | 20 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 2.9041 | 43.5619 | 290.1611 | 435.6189 | 769.3419 | 0.75 | 15 | 100% | 0% | 0% | 100% | 769.3419 | 0 | 0 | 769.3419 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 256.4473 | 256.4473 | 256.4473 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Existing Landfill |  | 6245 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1527.3035 | 12659.1573 | 138352.3467 | 138730.4838 | 289741.9877 | 0 | 0 | 100% | 0% | 0% | 100% | 289741.9877 | 0 | 0 | 289741.9877 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 289741.9877 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4540-BLD-001 | 446.0967 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 250 | 1050 | 24978.3452 | 37500 | 63528.3452 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 63528.3452 | 0 | 0 | 63528.3452 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 21176.1151 | 21176.1151 | 21176.1151 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1070 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4540-BLD-001 | 446.0967 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 64.7761 | 971.6408 | 6471.9943 | 9716.4077 | 17160.0428 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 17160.0428 | 0 | 0 | 17160.0428 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5720.0143 | 5720.0143 | 5720.0143 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1071 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 4540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 55.7621 | 836.4312 | 5571.3781 | 8364.3123 | 14772.1216 | 0 | 0 | 100% | 0% | 0% | 100% | 14772.1216 | 0 | 0 | 14772.1216 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4924.0405 | 4924.0405 | 4924.0405 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 4540-VP-001 | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 9975.9289 | 0 | 0 | 9975.9289 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1072 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 52.0446 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.1667 | 175 | 2914.1403 | 4375 | 7464.1403 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 7464.1403 | 0 | 0 | 7464.1403 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2488.0468 | 2488.0468 | 2488.0468 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1082 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4540-TK-007 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2130.6685 | 2130.6685 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1079 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 4540-SQ-002 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1075 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1076 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1077 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1078 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1080 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 4540-SQ-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1081 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG | 4540-SQ-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1073 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1074 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Lined Containment Cell |  | 900 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 40.0409 | 160.245 | 4004.0893 | 643.0908 | 4807.4251 | 0 | 0 | 100% | 0% | 0% | 100% | 4807.4251 | 0 | 0 | 4807.4251 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1602.475 | 1602.475 | 1602.475 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 1 | MS-HWB-XX | 360 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 16.0164 | 64.098 | 1601.6357 | 257.2363 | 1910.9863 | 0 | 0 | 100% | 0% | 0% | 100% | 1910.9863 | 0 | 0 | 1910.9863 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 636.9954 | 636.9954 | 636.9954 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 2 | MS-HWB-XX | 360 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 16.0164 | 64.098 | 1601.6357 | 257.2363 | 1910.9863 | 0 | 0 | 100% | 0% | 0% | 100% | 1910.9863 | 0 | 0 | 1910.9863 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 636.9954 | 636.9954 | 636.9954 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new-by generator) - 3 | MS-HWB-XX | 160 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 7.1184 | 28.488 | 711.8381 | 114.3273 | 849.3273 | 0 | 0 | 100% | 0% | 0% | 100% | 849.3273 | 0 | 0 | 849.3273 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 283.1091 | 283.1091 | 283.1091 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 4475 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 1094.4249 | 9071.2136 | 99139.5919 | 99410.5548 | 198550.1467 | 0 | 0 | 100% | 0% | 0% | 100% | 198550.1467 | 0 | 0 | 198550.1467 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 198550.1467 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 400 | m2 | 0.24456 | 2.0271 | 22.1541 | 22.2146 | 44.3687 | 97.8257 | 810.8347 | 8861.6395 | 8885.8596 | 17747.4991 | 0 | 0 | 100% | 0% | 0% | 100% | 17747.4991 | 0 | 0 | 17747.4991 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 17747.4991 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-2 | 1298 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 57.7479 | 231.1089 | 5774.7865 | 927.4799 | 6890.1674 | 0 | 0 | 100% | 0% | 0% | 100% | 6890.1674 | 0 | 0 | 6890.1674 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2296.7225 | 2296.7225 | 2296.7225 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-1 | 754 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 33.5454 | 134.2497 | 3354.537 | 538.7672 | 4027.5539 | 0 | 0 | 100% | 0% | 0% | 100% | 4027.5539 | 0 | 0 | 4027.5539 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1342.518 | 1342.518 | 1342.518 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-4 | 649 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 28.8739 | 115.5544 | 2887.3933 | 463.7399 | 3445.0837 | 0 | 0 | 100% | 0% | 0% | 100% | 3445.0837 | 0 | 0 | 3445.0837 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1148.3612 | 1148.3612 | 1148.3612 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-3 | 600 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 26.6939 | 106.83 | 2669.3929 | 428.7272 | 3184.9772 | 0 | 0 | 100% | 0% | 0% | 100% | 3184.9772 | 0 | 0 | 3184.9772 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1061.6591 | 1061.6591 | 1061.6591 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-6 | 550 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 24.4694 | 97.9275 | 2446.9435 | 392.9999 | 2919.5624 | 0 | 0 | 100% | 0% | 0% | 100% | 2919.5624 | 0 | 0 | 2919.5624 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 973.1875 | 973.1875 | 973.1875 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-5 | 347 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 15.438 | 61.7833 | 1543.7989 | 247.9472 | 1841.9785 | 0 | 0 | 100% | 0% | 0% | 100% | 1841.9785 | 0 | 0 | 1841.9785 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 613.9928 | 613.9928 | 613.9928 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person camp at Mine Site |  | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 9975.9289 | 0 | 0 | 9975.9289 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-009 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1102 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-010 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1103 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-011 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1104 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-012 | 1 | Ea | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 65.79 | 872.1 | 6573.3013 | 8721 | 16166.4013 | 40 | 40 | 100% | 0% | 0% | 100% | 16166.4013 | 0 | 0 | 16166.4013 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8083.2007 | 8083.2007 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1089 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 4613-FD-013 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2132.6115 | 2132.6115 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1092 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 4613-FD-013 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1093 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1094 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1095 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1096 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1097 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1098 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1099 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-007 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1100 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-008 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1090 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 4613-FD-013 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 85.45 | 1129.5 | 8537.5984 | 11295 | 20962.0984 | 30 | 60 | 100% | 0% | 0% | 100% | 20962.0984 | 0 | 0 | 20962.0984 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 6987.3661 | 0 | 6987.3661 | 0 | 0 | 0 | 0 | 6987.3661
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (North West) |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (South West) |  | 0 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Diesel Module | Diesel Module 1 | MR-FUM-FDI-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | FIR | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Jet A1 Pump Module | Jet A1 Pump Module | MR-FUM-FUS-020-PUM01 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Farm Tank Dike |  | 1911.3 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 85.0335 | 340.307 | 8503.3509 | 1365.7105 | 10209.3684 | 0 | 0 | 100% | 0% | 0% | 100% | 10209.3684 | 0 | 0 | 10209.3684 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5104.6842 | 5104.6842 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 400 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 17.796 | 71.22 | 1779.5952 | 285.8181 | 2136.6334 | 0 | 0 | 100% | 0% | 0% | 100% | 2136.6334 | 0 | 0 | 2136.6334 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1068.3167 | 1068.3167 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1105 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1106 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-002 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1107 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1108 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1109 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1110 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator |  | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - 1.35 MW GENERATOR |  | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4614 | Jet-A System | 416 | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | Tank - Jet-A tanks @ aerodrome apron |  | 0 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4711 | Raw Water Jetty | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1119 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Raw Water Supply Pipe - Piping Installation - Pumphouse to Water Building | 4712.2-P | 8518 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 2129.5 | 31942.5 | 212765.5447 | 319425 | 564133.0447 | 0.01 | 85.18 | 100% | 0% | 100% | 0% | 564133.0447 | 0 | 564133.0447 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 188044.3482 | 188044.3482 | 188044.3482 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1115 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Pumphouse - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4712-BLD-001 | 14.8699 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 3.3333 | 50 | 333.0446 | 500 | 883.0446 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 883.0446 | 0 | 0 | 883.0446 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 294.3482 | 294.3482 | 294.3482 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1116 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Pumphouse - Demolish and foundations - Gravel Base - Skidded Building | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1117 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Pumphouse - Demolish floor finish - Raised Steel or Wooden Floor | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1118 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Raw Water Supply Pipe - Heat Trace Installation - Pumphouse to Water Building | 4712.2-E | 4712 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System |  |  | piping | Piping | Piping | Bulks | Piping |  | Raw Water Intake Pipeline |  |  | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1121 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4720-BLD-001 | 390.3346 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 61.25 | 918.75 | 6119.6946 | 9187.5 | 16225.9446 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 16225.9446 | 0 | 0 | 16225.9446 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5408.6482 | 5408.6482 | 5408.6482 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1122 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4720-BLD-001 | 390.3346 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 56.679 | 850.1857 | 5662.995 | 8501.8567 | 15015.0374 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 15015.0374 | 0 | 0 | 15015.0374 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5005.0125 | 5005.0125 | 5005.0125 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE | 4720-VP-020 | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9975.9289 | 0 | 9975.9289 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1143 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 4720-TK-001 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1144 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 4720-TK-007 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1145 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 4720-TK-009 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1146 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 4720-TK-012 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1147 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - MINE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4720-TK-033 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2130.6685 | 2130.6685 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1124 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1125 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1126 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1127 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1128 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 4720-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1129 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 4720-PP-005 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1130 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 4720-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1131 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-008 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1132 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-008 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1133 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 4720-PP-010 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1134 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 4720-PP-011 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1135 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 4720-PP-013 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1136 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 4720-PP-014 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1137 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-015 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1138 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-015 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1139 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-031 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1140 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-031 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1141 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-032 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1142 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-032 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1123 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 4720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Infill between service and utility pads |  | 20800 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 263.9495 | 3042 | 26394.9523 | 8248.1432 | 37654.1432 | 0 | 0 | 100% | 0% | 0% | 100% | 37654.1432 | 0 | 0 | 37654.1432 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12551.3811 | 12551.3811 | 12551.3811 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK (40 m3) |  | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK (60 m3) |  | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | VENDOR PACKAGE - POTABLE WATER TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 800-person camp at Mine Site |  | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9975.9289 | 0 | 9975.9289 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1154 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 178.4387 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 100 | 600 | 9991.3381 | 15000 | 25591.3381 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 25591.3381 | 0 | 0 | 25591.3381 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 12795.669 | 12795.669 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1163 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 4731.2-P | 247 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 61.75 | 926.25 | 6169.6513 | 9262.5 | 16358.4013 | 0.01 | 2.47 | 100% | 0% | 100% | 0% | 16358.4013 | 0 | 16358.4013 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8179.2006 | 8179.2006 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1161 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 4731-VP-005 | 1 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 11035.5824 | 0 | 11035.5824 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5517.7912 | 5517.7912 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1160 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - TREATED EFFLUENT TANK | 4731-TK-002 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2462.4383 | 2462.4383 | 2462.4383 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1151 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 4731-BLD-001 | 29.7398 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6667 | 100 | 1665.223 | 2500 | 4265.223 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 4265.223 | 0 | 0 | 4265.223 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2132.6115 | 2132.6115 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1157 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 4731-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1158 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 4731-PP-004 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1159 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 4731-SC-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1152 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1153 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1162 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 4731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1155 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 4731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1156 | VP- |  | #N/A |  |  |  |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 4731-VP-005 | 1920 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Realignment of the effluent discharge line around the new crusher pad in 2018 |  | 1500 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 375 | 5625 | 37467.5179 | 56250 | 99342.5179 | 0.01 | 15 | 100% | 0% | 100% | 0% | 99342.5179 | 0 | 99342.5179 | 0 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 49671.2589 | 49671.2589 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 800-person camp at Mine Site |  | 1 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 11035.5824 | 0 | 11035.5824 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5517.7912 | 5517.7912 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1165 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4732-BLD-001 | 55.7621 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 31.25 | 131.25 | 3122.2932 | 4687.5 | 7941.0432 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 7941.0432 | 0 | 0 | 7941.0432 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3970.5216 | 3970.5216 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1172 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4732-TK-003 | 1 | Ea | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 15.5 | 195 | 1548.6574 | 1950 | 3693.6574 | 20 | 20 | 100% | 0% | 0% | 100% | 3693.6574 | 0 | 0 | 3693.6574 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1846.8287 | 1846.8287 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1166 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4732-BLD-001 | 55.7621 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 8.097 | 121.4551 | 808.9993 | 1214.551 | 2145.0053 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 2145.0053 | 0 | 0 | 2145.0053 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1072.5027 | 1072.5027 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1168 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1169 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-001 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1170 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1171 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-002 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1167 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 4732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1178 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to connection with Stockpile Drain Pipe | 4734.1-P | 2125 | m | 0.25 | 3.75 | 24.9783 | 37.5 | 66.2283 | 531.25 | 7968.75 | 53078.9836 | 79687.5 | 140735.2336 | 0.01 | 21.25 | 100% | 0% | 100% | 0% | 140735.2336 | 0 | 140735.2336 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46911.7445 | 46911.7445 | 46911.7445 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1177 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to connection with Stockpile Drain Pipe | 4734.1-E | 2050 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1174 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE | 4733-VM-001 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1175 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE SPARE | 4733-VM-002 | 0 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | FRP Water tanks for 800p camp |  | 4 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 38.6667 | 430 | 3863.3174 | 4300 | 8593.3174 | 1 | 4 | 100% | 0% | 0% | 100% | 8593.3174 | 0 | 0 | 8593.3174 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2864.4391 | 2864.4391 | 2864.4391 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 3 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 93 | 1170 | 9291.9444 | 11700 | 22161.9444 | 2 | 6 | 100% | 0% | 0% | 100% | 22161.9444 | 0 | 0 | 22161.9444 | Type B Construction 2BC-MRY1416 | Confirmed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 11080.9722 | 11080.9722 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1204 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV & Ground Wire - Electrical distribution system from power gen to e-house | 4750.2-E | 11000 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 1100 | 16500 | 109904.719 | 165000 | 291404.719 | 0.01 | 110 | 100% | 0% | 0% | 100% | 291404.719 | 0 | 0 | 291404.719 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 97134.9063 | 97134.9063 | 97134.9063 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 4750.3-E | 5200 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 520 | 7800 | 51954.9581 | 78000 | 137754.9581 | 0.01 | 52 | 100% | 0% | 0% | 100% | 137754.9581 | 0 | 0 | 137754.9581 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 45918.3194 | 45918.3194 | 45918.3194 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1180 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-001 | 59.4796 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.3333 | 200 | 1332.1784 | 2000 | 3532.1784 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3532.1784 | 0 | 0 | 3532.1784 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1177.3928 | 1177.3928 | 1177.3928 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1201 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing & Screening E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 59.4796 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.3333 | 200 | 1332.1784 | 2000 | 3532.1784 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3532.1784 | 0 | 0 | 3532.1784 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1177.3928 | 1177.3928 | 1177.3928 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1183 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-002 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1186 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-003 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1189 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-004 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1192 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-005 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1103.8058 | 1103.8058 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1195 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Aerodrome Area E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-006 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1198 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Supply E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-007 | 37.1747 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3333 | 125 | 832.6115 | 1250 | 2207.6115 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 2207.6115 | 0 | 0 | 2207.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.8705 | 735.8705 | 735.8705 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1184 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1185 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1187 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1188 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1190 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1191 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1193 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1194 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1196 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Area E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1197 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Area E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1199 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Supply E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1200 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Supply E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1181 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1182 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1202 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1203 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Mine Site |  | 3500 | m | 0.1 | 1.5 | 9.9913 | 15 | 26.4913 | 350 | 5250 | 34969.6833 | 52500 | 92719.6833 | 0.01 | 35 | 100% | 0% | 0% | 100% | 92719.6833 | 0 | 0 | 92719.6833 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 30906.5611 | 30906.5611 | 30906.5611 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-012 | 37.1612 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3303 | 124.9546 | 832.3091 | 1249.5459 | 2206.8096 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 2206.8096 | 0 | 0 | 2206.8096 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 735.6032 | 735.6032 | 735.6032 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-010 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-011 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #2- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services
7000 | Construction Facilities & Services | 7100 | Project Wide
7000 | Construction Facilities & Services | 7100 | Project Wide | 7110 | Communications & IT | 7111 | Communications Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7123 | Helicopter Service | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7121 | Jet Service | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7122 | Local Air Charter | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Existing Trailer Camp (Shanco) |  | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | 49-person Hard Wall Trailer Camp (previously at Steensby) |  | 950 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 212.9583 | 3194.375 | 21277.3871 | 31943.75 | 56415.5121 | 1 | 950 | 100% | 0% | 0% | 100% | 56415.5121 | 0 | 0 | 56415.5121 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 56415.5121 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7214 | Off-Spec Effluent Pond(s) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Matrix Camp |  | 5392.34 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 967.0263 | 14505.3946 | 96618.8678 | 145053.946 | 256178.2084 | 0.5 | 2696.17 | 100% | 0% | 0% | 100% | 256178.2084 | 0 | 0 | 256178.2084 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 85392.7361 | 85392.7361 | 85392.7361 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tents |  | 0 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7213 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 0 | ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7238 | Civil Contractor Buildings | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 1252.363 | m2 | 0.58283 | 2.69 | 58.2328 | 87.425 | 148.3478 | 729.9189 | 3368.8565 | 72928.6653 | 109487.8353 | 185785.357 | 0.5 | 626.1815 | 100% | 0% | 0% | 100% | 185785.357 | 0 | 0 | 185785.357 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 61928.4523 | 61928.4523 | 61928.4523 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 878.1618 | m2 | 0.58283 | 2.69 | 58.2328 | 87.425 | 148.3478 | 511.822 | 2362.2552 | 51137.8634 | 76773.2954 | 130273.414 | 0.5 | 439.0809 | 100% | 0% | 0% | 100% | 130273.414 | 0 | 0 | 130273.414 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 43424.4713 | 43424.4713 | 43424.4713 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 250.24 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 140.2387 | 589.0024 | 14011.7193 | 21035.8 | 35636.5217 | 1 | 250.24 | 100% | 0% | 0% | 100% | 35636.5217 | 0 | 0 | 35636.5217 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 35636.5217 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [6 empty] | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [6 empty] | Construction Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish floor finish - Gravel | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [5 empty] | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | 1 | ea | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 100% | 0% | 0% | 100% | 1500000 | 0 | 0 | 1500000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [5 empty] | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | 1 | ea | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 100% | 0% | 0% | 100% | 1500000 | 0 | 0 | 1500000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [5 empty] | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | 1 | ea | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 100% | 0% | 0% | 100% | 1400000 | 0 | 0 | 1400000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 466666.6667 | 466666.6667 | 466666.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [5 empty] | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | 1 | ea | 0 | 0 | 0 | 0 | 2200000 | 0 | 0 | 0 | 0 | 2200000 | 0 | 0 | 100% | 0% | 0% | 100% | 2200000 | 0 | 0 | 2200000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 733333.3333 | 733333.3333 | 733333.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [5 empty] | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | 1 | ea | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 100% | 0% | 0% | 100% | 500000 | 0 | 0 | 500000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 166666.6667 | 166666.6667 | 166666.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.69 | 58.2328 | 87.425 | 148.3478 | 1192.477 | 5503.74 | 119144.4088 | 178871.55 | 303519.6988 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 303519.6988 | 0 | 0 | 303519.6988 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 101173.2329 | 101173.2329 | 101173.2329 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 255.75 | 3836.25 | 25552.8472 | 38362.5 | 67751.5972 | 0 | 0 | 100% | 0% | 0% | 100% | 67751.5972 | 0 | 0 | 67751.5972 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 67751.5972 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1222 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Construction Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 7231-BLD-001 | 267.658 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 60 | 900 | 5994.8029 | 9000 | 15894.8029 | 1 | 267.658 | 100% | 0% | 0% | 100% | 15894.8029 | 0 | 0 | 15894.8029 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5298.2676 | 5298.2676 | 5298.2676 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1230 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7231-TK-001 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1225 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 7231-BLD-002 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1231 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 7231-TK-002 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1226 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1228 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7231-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1229 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7231-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1227 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-002 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1223 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Office - Demolish and foundations - Gravel Base - Skidded Building | 7231-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1224 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Construction Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1415.0943 | 9433.9623 | 14150.9434 | 25000 | 94.3396 | 1415.0943 | 9433.9623 | 14150.9434 | 25000 | 0 | 0 | 100% | 0% | 0% | 100% | 25000 | 0 | 0 | 25000 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1286 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Heated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-002 | 371.7472 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 58.3333 | 875 | 5828.2806 | 8750 | 15453.2806 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 15453.2806 | 0 | 0 | 15453.2806 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5151.0935 | 5151.0935 | 5151.0935 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1289 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-003 | 371.7472 | m2 | 0.15692 | 2.3537 | 15.6781 | 23.5375 | 41.5693 | 58.3333 | 875 | 5828.2806 | 8750 | 15453.2806 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 15453.2806 | 0 | 0 | 15453.2806 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5151.0935 | 5151.0935 | 5151.0935 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1287 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Heated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-002 | 371.7472 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 53.98 | 809.7006 | 5393.3286 | 8097.0064 | 14300.0356 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 14300.0356 | 0 | 0 | 14300.0356 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4766.6785 | 4766.6785 | 4766.6785 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1290 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-003 | 371.7472 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 53.98 | 809.7006 | 5393.3286 | 8097.0064 | 14300.0356 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 14300.0356 | 0 | 0 | 14300.0356 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4766.6785 | 4766.6785 | 4766.6785 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1283 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 32.388 | 485.8204 | 3235.9971 | 4858.2038 | 8580.0214 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 8580.0214 | 0 | 0 | 8580.0214 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2860.0071 | 2860.0071 | 2860.0071 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1284 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 32.388 | 485.8204 | 3235.9971 | 4858.2038 | 8580.0214 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 8580.0214 | 0 | 0 | 8580.0214 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2860.0071 | 2860.0071 | 2860.0071 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1285 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Equipment Building - Demolish floor finish - Gravel | 7235-BLD-001 | 223.0483 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1288 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Heated Warehouse - Demolish floor finish - Gravel | 7235-BLD-002 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1291 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-003 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-004 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-004 | 0 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1271 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-004 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1254 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-009 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1257 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-010 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1272 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-005 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1269 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-001 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1273 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-007 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1074.1647 | 1074.1647 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1274 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-008 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1255 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1258 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1239 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-003 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1248 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-007 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1251 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-008 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1242 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Office - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-005 | 44.6097 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 10 | 150 | 999.1338 | 1500 | 2649.1338 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2649.1338 | 0 | 0 | 2649.1338 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1245 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-006 | 44.6097 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 10 | 150 | 999.1338 | 1500 | 2649.1338 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2649.1338 | 0 | 0 | 2649.1338 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1270 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7232-TK-002 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Washcar - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-002 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Washcar - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Quarry Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1265 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1267 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1260 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7232-BLD-011 | 14.8699 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 8.3333 | 50 | 832.6115 | 1250 | 2132.6115 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 2132.6115 | 0 | 0 | 2132.6115 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 710.8705 | 710.8705 | 710.8705 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1240 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-003 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1249 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-007 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1252 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-008 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-001 | 0 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Quarry Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1256 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-009 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1263 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1264 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1259 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-010 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1266 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1268 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1261 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1262 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1243 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Office - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1244 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Office - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1246 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1247 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1241 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1250 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1253 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1295 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-001 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1296 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-002 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1297 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-003 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1298 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-004 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1299 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-005 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1300 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-006 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1301 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-007 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1302 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-008 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1303 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-009 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1304 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-010 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1305 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1306 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-012 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1307 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-013 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1308 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1309 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7241-MO-024 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1310 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1355 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 3776 kg | 7244-GE-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1350 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Generator | GENERATOR - ACOMMODATIONS AREA GENERATOR - CUMMINS C1600D6R L: 14630, W: 2440, H: 4062, 68320 kg | 7244-GE-001 | 0 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1351 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-002 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1352 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1353 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1354 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1356 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - LOGISTICS TRAILER GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315m 3776 kg | 7244-GE-007 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1357 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-008 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1358 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-009 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1359 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1360 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-002 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1361 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-003 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1362 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7245-MO-004 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1363 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-005 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1364 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-006 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1365 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MAMTEX 26101C | 7245-MO-007 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1366 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - GROVE RT890E 41400 kg | 7245-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1367 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-010 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1368 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-011 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1369 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-012 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7242 | Emergency Response Equipment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1313 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-001 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1314 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1315 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-003 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1316 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-004 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1317 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-005 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1318 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-006 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1319 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-007 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1320 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1321 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-009 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1322 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-010 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1323 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-011 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1324 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-012 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1325 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7243-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1326 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7243-MO-015 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1327 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-016 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1328 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-017 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1329 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-018 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1330 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-019 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1331 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-020 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1332 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7243-MO-021 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1333 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7243-MO-022 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-023 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1335 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-024 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1336 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1337 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1338 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1339 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1340 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-029 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1341 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1342 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-031 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1343 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-032 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1344 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1345 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1346 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1347 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1348 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1349 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7243-MO-046 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1372 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 375 | 1575 | 37467.5179 | 56250 | 95292.5179 | 1 | 669.145 | 100% | 0% | 0% | 100% | 95292.5179 | 0 | 0 | 95292.5179 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 31764.1726 | 31764.1726 | 31764.1726 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1373 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 375 | 1575 | 37467.5179 | 56250 | 95292.5179 | 1 | 669.145 | 100% | 0% | 0% | 100% | 95292.5179 | 0 | 0 | 95292.5179 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 31764.1726 | 31764.1726 | 31764.1726 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Batch Plant Stockpile |  | 5180.44 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 65.7392 | 757.6393 | 6573.9167 | 2054.2794 | 9385.8354 | 0 | 0 | 100% | 0% | 0% | 100% | 9385.8354 | 0 | 0 | 9385.8354 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3128.6118 | 3128.6118 | 3128.6118 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1374 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7251-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  |  | #N/A |  |  |  | Batch Plant Building | Batch Plant Building |  | 3281.62 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7252 | Explosives Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7271 | Camp Operations & Catering | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7275 | Maintenance and Repair | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 43.8377 | 175.4398 | 4383.7659 | 704.0701 | 5263.2758 | 0 | 0 | 100% | 0% | 0% | 100% | 5263.2758 | 0 | 0 | 5263.2758 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1754.4253 | 1754.4253 | 1754.4253 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 43.8377 | 175.4398 | 4383.7659 | 704.0701 | 5263.2758 | 0 | 0 | 100% | 0% | 0% | 100% | 5263.2758 | 0 | 0 | 5263.2758 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1754.4253 | 1754.4253 | 1754.4253 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bladder Farm Decommissioning |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Hazardous Waste Berm |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  |  | #N/A |  |  |  |  | Old STP (RBC) |  | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1386 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-001 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1387 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-002 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1388 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-003 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1389 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 7340-MO-004 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1390 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CS74 L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-014 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1391 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-015 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1392 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-016 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1393 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-017 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Exploration Tent Camp Pad |  | 9432.14 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 1179.0175 | 17685.2625 | 117799.6246 | 176852.625 | 312337.5121 | 0 | 0 | 100% | 0% | 0% | 100% | 312337.5121 | 0 | 0 | 312337.5121 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 312337.5121 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Soft-Wall Camp (Weatherhaven) |  | 6017.14 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 1079.0738 | 16186.1066 | 107813.909 | 161861.066 | 285861.0816 | 0.5 | 3008.57 | 100% | 0% | 0% | 100% | 285861.0816 | 0 | 0 | 285861.0816 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 285861.0816 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tent Camp Tents |  | 2400 | m2 | 0.17933 | 2.69 | 17.9178 | 26.9 | 47.5078 | 430.4 | 6456 | 43002.7192 | 64560 | 114018.7192 | 0.5 | 1200 | 100% | 0% | 0% | 100% | 114018.7192 | 0 | 0 | 114018.7192 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 114018.7192 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Old Incinerator (Medium sized equipment) |  | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  |  | #N/A | VP7 | Packaged Facilities |  |  | Exploration STP |  | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 182.2 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 102.1079 | 428.8532 | 10201.9472 | 15316.1875 | 25946.9879 | 1 | 182.2 | 100% | 0% | 0% | 100% | 25946.9879 | 0 | 0 | 25946.9879 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 25946.9879 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.69 | 58.2328 | 87.425 | 148.3478 | 1192.477 | 5503.74 | 119144.4088 | 178871.55 | 303519.6988 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 303519.6988 | 0 | 0 | 303519.6988 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 101173.2329 | 101173.2329 | 101173.2329 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 255.75 | 3836.25 | 25552.8472 | 38362.5 | 67751.5972 | 0 | 0 | 100% | 0% | 0% | 100% | 67751.5972 | 0 | 0 | 67751.5972 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 67751.5972 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7431 | Office Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7435 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1415.0943 | 9433.9623 | 14150.9434 | 25000 | 94.3396 | 1415.0943 | 9433.9623 | 14150.9434 | 25000 | 0 | 0 | 100% | 0% | 0% | 100% | 25000 | 0 | 0 | 25000 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1435 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-004 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1437 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-007 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1439 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-010 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1407 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-004 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2559.1338 | 2559.1338 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1416 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-007 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1419 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-008 | 35.6877 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 20 | 120 | 1998.2676 | 3000 | 5118.2676 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 5118.2676 | 0 | 0 | 5118.2676 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1706.0892 | 1706.0892 | 1706.0892 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1433 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-001 | 1 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 2 | 2 | 100% | 0% | 0% | 100% | 7387.3148 | 0 | 0 | 7387.3148 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3693.6574 | 3693.6574 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1436 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - FUEL SYSTEMS WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-005 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1074.1647 | 1074.1647 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1438 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-008 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1440 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-011 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1408 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-004 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 370.8787 | 370.8787 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1417 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-007 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1401 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-001 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1404 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-003 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1986.8504 | 1986.8504 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1410 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-005 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1413 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-006 | 66.9145 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 15 | 225 | 1498.7007 | 2250 | 3973.7007 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3973.7007 | 0 | 0 | 3973.7007 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1324.5669 | 1324.5669 | 1324.5669 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1420 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-008 | 35.6877 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.4 | 42 | 279.7575 | 420 | 741.7575 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 741.7575 | 0 | 0 | 741.7575 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 247.2525 | 247.2525 | 247.2525 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1434 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7432-TK-002 | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1422 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7432-BLD-009 | 14.8699 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 8.3333 | 50 | 832.6115 | 1250 | 2132.6115 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 2132.6115 | 0 | 0 | 2132.6115 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 710.8705 | 710.8705 | 710.8705 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1402 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-001 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1405 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Lunchroom - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-003 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 695.3976 | 695.3976 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1411 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-005 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1414 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-006 | 66.9145 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.25 | 78.75 | 524.5453 | 787.5 | 1390.7953 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1390.7953 | 0 | 0 | 1390.7953 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 463.5984 | 463.5984 | 463.5984 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1427 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - FUEL SYSTEMS WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1429 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1431 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1409 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1418 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-007 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1425 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1426 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-003 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1421 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-008 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1428 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-006 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1430 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-009 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1432 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-012 | 0 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | [6 empty] | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1423 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1424 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1403 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1406 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1412 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-005 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1415 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-006 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1446 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader size | MOBILE EQUIPMENT - FUEL/LUBE TRUCK - ARTICULATED - CAT 740 EFLT | 7441-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1447 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7441-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1497 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-009 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1498 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-010 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1499 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-011 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1489 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - ACCOMMODATIONS AREA GENERATOR - CUMMINS C1600D6RG L: 14630, W: 2440, H: 4065, 78220 kg | 7444-GE-001 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1490 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-002 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1491 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-003 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1492 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4496, W: 1905, H: 2085, 6458 kg | 7444-GE-004 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1493 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-005 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1494 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-006 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1495 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-007 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1496 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-008 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1500 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-012 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1501 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-013 | 0 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1502 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-002 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1503 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-003 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1504 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-006 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1505 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-007 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1506 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-008 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1507 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - MANITOWOC 2250 L: 12900, W: 7910, H: 3640, 113000 kg | 7445-MO-009 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1508 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MANITEX 26101C | 7445-MO-012 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1509 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-013 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1510 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1448 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-001 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1449 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-002 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1450 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-003 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1451 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-004 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1452 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-005 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1453 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-006 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1454 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-007 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1455 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-008 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1456 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-009 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1457 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-010 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1458 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-011 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1459 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-012 |  | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1460 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-014 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1461 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Compressor | MOBILE EQUIPMENT - LARGE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-015 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1462 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7443-MO-016 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1463 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-017 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1464 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-018 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1465 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-019 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1466 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-020 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1467 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-021 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1468 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7443-MO-022 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1469 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7443-MO-023 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1470 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-024 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1471 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-025 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1472 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-026 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1473 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-027 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1474 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-028 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1475 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-029 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1476 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-030 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1477 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-031 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1478 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-032 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1479 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-033 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1480 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-034 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1481 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-035 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1482 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-036 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1483 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-037 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1484 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-038 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1485 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7443-MO-051 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1486 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER L: 14630, W: 2438 | 7443-MO-052 |  | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1487 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-053 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1488 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-054 |  | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1513 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 375 | 1575 | 37467.5179 | 56250 | 95292.5179 | 1 | 669.145 | 100% | 0% | 0% | 100% | 95292.5179 | 0 | 0 | 95292.5179 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 31764.1726 | 31764.1726 | 31764.1726 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1514 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 375 | 1575 | 37467.5179 | 56250 | 95292.5179 | 1 | 669.145 | 100% | 0% | 0% | 100% | 95292.5179 | 0 | 0 | 95292.5179 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 31764.1726 | 31764.1726 | 31764.1726 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1515 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7451-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Containment Area - Existing |  | 0 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond (Existing) |  |  | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7471 | Camp Operations & Catering | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7475 | Maintenance and Repair | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bulk Fuel Storage Facility (Bladder Farm) |  | 5787.68 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 257.4932 | 1030.4964 | 25749.3194 | 4135.5598 | 30915.3756 | 0 | 0 | 100% | 0% | 0% | 100% | 30915.3756 | 0 | 0 | 30915.3756 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 15457.6878 | 15457.6878 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Barreled Fuel Line Containment |  | 5411.65 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 240.7637 | 963.5443 | 24076.3664 | 3866.8693 | 28906.78 | 0 | 0 | 100% | 0% | 0% | 100% | 28906.78 | 0 | 0 | 28906.78 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 14453.39 | 14453.39 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7480 | Construction Services | 7484 | Explosives Supply Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7480 | Construction Services | 7482 | Heavy Transport Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | EPCM Services |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 3766032 | 0 | 0 | 98.36% | 1.644% | 0% | 100% | 3704134.3682 | 61897.6318 | 0 | 3766032 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | 22% | 28% | 3.791% | 5.694% | 3.791% | 11.91% | 7.956% | 6.532% | 5.563% | 4.76% | 327580 | 416920 | 56441.1606 | 84780.1561 | 56441.1606 | 177369.3906 | 118466.2215 | 97267.3275 | 82838.0675 | 70870.816
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 1489000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 1454762.8745 | 34237.1255 | 0 | 1489000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 297800 | 297800 | 297800 | 148900 | 148900 | 148900 | 74450 | 74450
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 596000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 582295.9524 | 13704.0476 | 0 | 596000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 238400 | 178800 | 119200 | 59600 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 151000 | 0 | 0 | 100% | 0% | 0% | 100% | 151000 | 0 | 0 | 151000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 30200 | 30200 | 30200 | 15100 | 15100 | 15100 | 7550 | 7550
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 12000 | 9000 | 6000 | 3000 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 55000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 43474.277 | 11525.723 | 0 | 55000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 11000 | 11000 | 11000 | 5500 | 5500 | 5500 | 2750 | 2750
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 23000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 18180.1522 | 4819.8478 | 0 | 23000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 9200 | 6900 | 4600 | 2300 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 125000 | 0 | 0 | 100% | 0% | 0% | 100% | 125000 | 0 | 0 | 125000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 25000 | 25000 | 25000 | 12500 | 12500 | 12500 | 6250 | 6250
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 49000 | 0 | 0 | 100% | 0% | 0% | 100% | 49000 | 0 | 0 | 49000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 19600 | 14700 | 9800 | 4900 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 1206000 | 0 | 0 | 100% | 0% | 0% | 100% | 1206000 | 0 | 0 | 1206000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 241200 | 241200 | 241200 | 120600 | 120600 | 120600 | 60300 | 60300
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 500000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 488503.3158 | 11496.6842 | 0 | 500000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 200000 | 150000 | 100000 | 50000 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 33000 | 0 | 0 | 100% | 0% | 0% | 100% | 33000 | 0 | 0 | 33000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 6600 | 6600 | 6600 | 3300 | 3300 | 3300 | 1650 | 1650
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 14000 | 0 | 0 | 100% | 0% | 0% | 100% | 14000 | 0 | 0 | 14000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 5600 | 4200 | 2800 | 1400 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 543000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 521922.3594 | 21077.6406 | 0 | 543000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 108600 | 108600 | 108600 | 54300 | 54300 | 54300 | 27150 | 27150
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 225000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 216266.171 | 8733.829 | 0 | 225000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 90000 | 67500 | 45000 | 22500 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 514000 | 0 | 0 | 100% | 0% | 0% | 100% | 514000 | 0 | 0 | 514000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 102800 | 102800 | 102800 | 51400 | 51400 | 51400 | 25700 | 25700
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 213000 | 0 | 0 | 100% | 0% | 0% | 100% | 213000 | 0 | 0 | 213000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 85200 | 63900 | 42600 | 21300 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect |  |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect |  |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  |  | Indirect | Indirect |  |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  |  | Indirect | Indirect |  |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive material) | [12 empty] | 2537000 | 0 | 0 | 100% | 0% | 0% | 100% | 2537000 | 0 | 0 | 2537000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 845666.6667 | 845666.6667 | 845666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 234000 | 0 | 0 | 100% | 0% | 0% | 100% | 234000 | 0 | 0 | 234000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 63000 | 0 | 0 | 100% | 0% | 0% | 100% | 63000 | 0 | 0 | 63000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 21000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 5000 | 0 | 0 | 100% | 0% | 0% | 100% | 5000 | 0 | 0 | 5000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 2890000 | 0 | 0 | 100% | 0% | 0% | 100% | 2890000 | 0 | 0 | 2890000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 963333.3333 | 963333.3333 | 963333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 14000 | 0 | 0 | 100% | 0% | 0% | 100% | 14000 | 0 | 0 | 14000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 138000 | 0 | 0 | 100% | 0% | 0% | 100% | 138000 | 0 | 0 | 138000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46000 | 46000 | 46000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 9000 | 0 | 0 | 100% | 0% | 0% | 100% | 9000 | 0 | 0 | 9000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 223000 | 0 | 0 | 100% | 0% | 0% | 100% | 223000 | 0 | 0 | 223000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 74333.3333 | 74333.3333 | 74333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 1213000 | 0 | 0 | 100% | 0% | 0% | 100% | 1213000 | 0 | 0 | 1213000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 404333.3333 | 404333.3333 | 404333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 1528000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 1492866.1331 | 35133.8669 | 0 | 1528000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 305600 | 305600 | 305600 | 152800 | 152800 | 152800 | 76400 | 76400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 652000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 637008.3238 | 14991.6762 | 0 | 652000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 130400 | 130400 | 130400 | 65200 | 65200 | 65200 | 32600 | 32600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 76000 | 0 | 0 | 100% | 0% | 0% | 100% | 76000 | 0 | 0 | 76000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 15200 | 15200 | 15200 | 7600 | 7600 | 7600 | 3800 | 3800
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 46000 | 0 | 0 | 100% | 0% | 0% | 100% | 46000 | 0 | 0 | 46000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 9200 | 9200 | 9200 | 4600 | 4600 | 4600 | 2300 | 2300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 58000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 45845.6012 | 12154.3988 | 0 | 58000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 11600 | 11600 | 11600 | 5800 | 5800 | 5800 | 2900 | 2900
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 29000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 22922.8006 | 6077.1994 | 0 | 29000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 5800 | 5800 | 5800 | 2900 | 2900 | 2900 | 1450 | 1450
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 126000 | 0 | 0 | 100% | 0% | 0% | 100% | 126000 | 0 | 0 | 126000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 25200 | 25200 | 25200 | 12600 | 12600 | 12600 | 6300 | 6300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 43000 | 0 | 0 | 100% | 0% | 0% | 100% | 43000 | 0 | 0 | 43000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 8600 | 8600 | 8600 | 4300 | 4300 | 4300 | 2150 | 2150
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 573000 | 0 | 0 | 100% | 0% | 0% | 100% | 573000 | 0 | 0 | 573000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 114600 | 114600 | 114600 | 57300 | 57300 | 57300 | 28650 | 28650
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 263000 | 0 | 0 | 100% | 0% | 0% | 100% | 263000 | 0 | 0 | 263000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 52600 | 52600 | 52600 | 26300 | 26300 | 26300 | 13150 | 13150
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 35000 | 0 | 0 | 100% | 0% | 0% | 100% | 35000 | 0 | 0 | 35000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 1750 | 1750
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 17000 | 0 | 0 | 100% | 0% | 0% | 100% | 17000 | 0 | 0 | 17000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 3400 | 3400 | 3400 | 1700 | 1700 | 1700 | 850 | 850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 577000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 554602.5808 | 22397.4192 | 0 | 577000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 115400 | 115400 | 115400 | 57700 | 57700 | 57700 | 28850 | 28850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 265000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 254713.4903 | 10286.5097 | 0 | 265000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 53000 | 53000 | 53000 | 26500 | 26500 | 26500 | 13250 | 13250
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 547000 | 0 | 0 | 100% | 0% | 0% | 100% | 547000 | 0 | 0 | 547000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 109400 | 109400 | 109400 | 54700 | 54700 | 54700 | 27350 | 27350
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 172000 | 0 | 0 | 100% | 0% | 0% | 100% | 172000 | 0 | 0 | 172000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 34400 | 34400 | 34400 | 17200 | 17200 | 17200 | 8600 | 8600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 1969000 | 0 | 0 | 100% | 0% | 0% | 100% | 1969000 | 0 | 0 | 1969000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 656333.3333 | 656333.3333 | 656333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 1648000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 1610106.9289 | 37893.0711 | 0 | 1648000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 329600 | 329600 | 329600 | 164800 | 164800 | 164800 | 82400 | 82400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 125194.6519 | 0 | 0 | 100% | 0% | 0% | 100% | 125194.6519 | 0 | 0 | 125194.6519 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 25038.9304 | 25038.9304 | 25038.9304 | 12519.4652 | 12519.4652 | 12519.4652 | 6259.7326 | 6259.7326
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 78000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 61654.4293 | 16345.5707 | 0 | 78000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 15600 | 15600 | 15600 | 7800 | 7800 | 7800 | 3900 | 3900
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 117000 | 0 | 0 | 100% | 0% | 0% | 100% | 117000 | 0 | 0 | 117000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 23400 | 23400 | 23400 | 11700 | 11700 | 11700 | 5850 | 5850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 719000 | 0 | 0 | 100% | 0% | 0% | 100% | 719000 | 0 | 0 | 719000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 143800 | 143800 | 143800 | 71900 | 71900 | 71900 | 35950 | 35950
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 47000 | 0 | 0 | 100% | 0% | 0% | 100% | 47000 | 0 | 0 | 47000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 9400 | 9400 | 9400 | 4700 | 4700 | 4700 | 2350 | 2350
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 727000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 698780.0282 | 28219.9718 | 0 | 727000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 145400 | 145400 | 145400 | 72700 | 72700 | 72700 | 36350 | 36350
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 471000 | 0 | 0 | 100% | 0% | 0% | 100% | 471000 | 0 | 0 | 471000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 94200 | 94200 | 94200 | 47100 | 47100 | 47100 | 23550 | 23550
9000 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts | 9120 | Project Management | 9121 | Owner Accounts - Project Management |  |  |  |  | Indirect | [16 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  |  | Indirect | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 2444000 | 0 | 0 | 97.7% | 2.299% | 0% | 100% | 2387804.2076 | 56195.7924 | 0 | 2444000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 100% | [7 empty] | 0 |  | 2444000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 232000 | 0 | 0 | 100% | 0% | 0% | 100% | 232000 | 0 | 0 | 232000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 100% | [7 empty] | 0 |  | 232000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 93000 | 0 | 0 | 79.04% | 20.96% | 0% | 100% | 73511.0503 | 19488.9497 | 0 | 93000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 100% | [7 empty] | 0 |  | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 202000 | 0 | 0 | 100% | 0% | 0% | 100% | 202000 | 0 | 0 | 202000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 100% | [7 empty] | 0 |  | 202000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 1797785.7244 | 0 | 0 | 97% | 3% | 0% | 100% | 1743852.1527 | 53933.5717 | 0 | 1797785.7244 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 100% | [7 empty] | 0 |  | 1797785.7244 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 100% | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 918000 | 0 | 0 | 96.12% | 3.882% | 0% | 100% | 882365.9778 | 35634.0222 | 0 | 918000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 100% | [7 empty] | 0 |  | 918000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 809000 | 0 | 0 | 100% | 0% | 0% | 100% | 809000 | 0 | 0 | 809000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 100% | [7 empty] | 0 |  | 809000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7146.8333