## Estimate Details
'Mary River Project - Complete Project Security Assesment - Estimate Breakdown Structure'
Updated 22 January 2020
[44 empty] | C&M |  | Closure |  |  | Post Closure |  |  |  |  | C&M |  | Closure |  |  | Post Closure
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 0 - % | Year 0+1 - % | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 0- Cost ($) | Year 0+1- Cost ($) | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($)
1000 | Project Wide
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2014 |  | 11788.2087 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 2973.4415 | 23895.7227 | 195867.8553 | 261870.9208 | 457738.7761 | 0 | 0 | 100% | 0% | 0% | 100% | 457738.7761 | 0 | 0 | 457738.7761 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 457738.7761 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 |  | 378 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 95.3462 | 766.2388 | 6280.687 | 8397.1374 | 14677.8244 | 0 | 0 | 100% | 0% | 0% | 100% | 14677.8244 | 0 | 0 | 14677.8244 | Type A 2AM-MRY1325 | Modified | 2015 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 14677.8244 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional Laydown Areas |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2016 |  | 656.3333 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 165.5526 | 1330.4447 | 10905.3551 | 14580.2147 | 25485.5698 | 0 | 0 | 100% | 0% | 0% | 100% | 25485.5698 | 0 | 0 | 25485.5698 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 25485.5698 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables - addition of 49 person camp |  | 49 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 34339.2445 | 0 | 0 | 34339.2445 | 0 | 0 | 100% | 0% | 0% | 100% | 34339.2445 | 0 | 0 | 34339.2445 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 34339.2445 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017 |  | 1192.1667 | ea | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 300.7105 | 2416.6254 | 19808.5335 | 26483.5642 | 46292.0977 | 0 | 0 | 100% | 0% | 0% | 100% | 46292.0977 | 0 | 0 | 46292.0977 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 46292.0977 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2020 & 2020-R |  | 1558.7947 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 393.1882 | 3159.8122 | 25900.269 | 34628.0777 | 60528.3467 | 0 | 0 | 100% | 0% | 0% | 100% | 60528.3467 | 0 | 0 | 60528.3467 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 60528.3467 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2019 & 2019-R |  | 2722.2197 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 686.649 | 5518.1758 | 45231.2438 | 60473.1565 | 105704.4003 | 0 | 0 | 100% | 0% | 0% | 100% | 105704.4003 | 0 | 0 | 105704.4003 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 105704.4003 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C1 & 2018-R |  | 4018.6667 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1013.6629 | 8146.1863 | 66772.4536 | 89273.2699 | 156045.7236 | 0 | 0 | 100% | 0% | 0% | 100% | 156045.7236 | 0 | 0 | 156045.7236 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 156045.7236 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C2 |  | 121.5447 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 30.6583 | 246.3817 | 2019.5352 | 2700.0732 | 4719.6084 | 0 | 0 | 100% | 0% | 0% | 100% | 4719.6084 | 0 | 0 | 4719.6084 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 4719.6084 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 A |  | 8.0269 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 2.0247 | 16.2712 | 133.371 | 178.3141 | 311.6851 | 0 | 0 | 100% | 0% | 0% | 100% | 311.6851 | 0 | 0 | 311.6851 | Type A 2AM-MRY1325 | Modified | 2015 A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 311.6851 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables |  | 550 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 385440.5 | 0 | 0 | 385440.5 | 0 | 0 | 100% | 0% | 0% | 100% | 385440.5 | 0 | 0 | 385440.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 385440.5 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - Shiploader |  | 5049 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1273.5528 | 10234.7614 | 83892.0334 | 112161.7634 | 196053.7968 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 196053.7968 | 0 | 196053.7968 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 196053.7968 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 R |  | 4660.9167 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1175.6632 | 9448.0828 | 77443.8061 | 103540.6283 | 180984.4344 | 0 | 0 | 100% | 0% | 0% | 100% | 180984.4344 | 0 | 0 | 180984.4344 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 180984.4344 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017-A |  | 7146.8933 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1802.7225 | 14487.3733 | 118749.7348 | 158765.7268 | 277515.4616 | 0 | 0 | 100% | 0% | 0% | 100% | 277515.4616 | 0 | 0 | 277515.4616 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 277515.4616 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port
2000 | Milne Port | 2100 | General
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 001 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed - Demolish Building - ISO Shipping Container | 2110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed - Demolish and foundations - Gravel Base - Skidded Building | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 003 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed - Demolish floor finish - Raised Steel or Wooden Floor | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Disturbed Area @ Milne Port (adjacent to Steel Tank Farm) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 22423.6266 | 22423.6266 | 22423.6266 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Laydown Area |  | 37375 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 474.4697 | 5466.0938 | 35585.2269 | 14820.8823 | 55872.2029 | 0 | 0 | 100% | 0% | 0% | 100% | 55872.2029 | 0 | 0 | 55872.2029 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 18624.0676 | 18624.0676 | 18624.0676 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP3 |  | 131000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1663.0242 | 19158.75 | 124726.8153 | 51947.4403 | 195833.0056 | 0 | 0 | 100% | 0% | 0% | 100% | 195833.0056 | 0 | 0 | 195833.0056 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 65277.6685 | 65277.6685 | 65277.6685 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP5 |  | 65000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 825.1647 | 9506.25 | 61887.3511 | 25775.4475 | 97169.0486 | 0 | 0 | 100% | 0% | 0% | 100% | 97169.0486 | 0 | 0 | 97169.0486 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 32389.6829 | 32389.6829 | 32389.6829 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 32000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 406.2349 | 4680 | 30467.619 | 12689.4511 | 47837.0701 | 0 | 0 | 100% | 0% | 0% | 100% | 47837.0701 | 0 | 0 | 47837.0701 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15945.69 | 15945.69 | 15945.69 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP7 |  | 21000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 266.5917 | 3071.25 | 19994.375 | 8327.4523 | 31393.0772 | 0 | 0 | 100% | 0% | 0% | 100% | 31393.0772 | 0 | 0 | 31393.0772 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10464.3591 | 10464.3591 | 10464.3591 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | -13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -165.0329 | -1901.25 | -12377.4702 | -5155.0895 | -19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | -19433.8097 | 0 | 0 | -19433.8097 | Type A 2AM-MRY1325 | Removed | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -6477.9366 | -6477.9366 | -6477.9366 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 30000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 380.8452 | 4387.5 | 28563.3928 | 11896.3604 | 44847.2532 | 0 | 0 | 100% | 0% | 0% | 100% | 44847.2532 | 0 | 0 | 44847.2532 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 14949.0844 | 14949.0844 | 14949.0844 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6477.9366 | 6477.9366 | 6477.9366 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP4 |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6477.9366 | 6477.9366 | 6477.9366 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP6 |  | 7000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 88.8639 | 1023.75 | 6664.7917 | 2775.8174 | 10464.3591 | 0 | 0 | 100% | 0% | 0% | 100% | 10464.3591 | 0 | 0 | 10464.3591 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3488.1197 | 3488.1197 | 3488.1197 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Module Road 2018 |  | 13300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 168.8414 | 1945.125 | 12663.1041 | 5274.0531 | 19882.2822 | 0 | 0 | 100% | 0% | 0% | 100% | 19882.2822 | 0 | 0 | 19882.2822 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6627.4274 | 6627.4274 | 6627.4274 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Q1 Access Road |  | 1200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 15.2338 | 175.5 | 1142.5357 | 475.8544 | 1793.8901 | 0 | 0 | 100% | 0% | 0% | 100% | 1793.8901 | 0 | 0 | 1793.8901 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 597.9634 | 597.9634 | 597.9634 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Surface Water Management Diversion Berms & Ditching |  | 9500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 120.601 | 1389.375 | 9045.0744 | 3767.1808 | 14201.6302 | 0 | 0 | 100% | 0% | 0% | 100% | 14201.6302 | 0 | 0 | 14201.6302 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4733.8767 | 4733.8767 | 4733.8767 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2133 | Materials Handling | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2136 | Milne Port |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 14306 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 181.6124 | 2092.2525 | 13620.9299 | 5672.9777 | 21386.1601 | 0 | 0 | 100% | 0% | 0% | 100% | 21386.1601 | 0 | 0 | 21386.1601 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7128.72 | 7128.72 | 7128.72 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2138 | Quarry Development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 12148.5 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 154.2233 | 1776.7181 | 11566.7459 | 4817.4311 | 18160.8952 | 0 | 0 | 100% | 0% | 0% | 100% | 18160.8952 | 0 | 0 | 18160.8952 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6053.6317 | 6053.6317 | 6053.6317 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2134 |  |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad @ Milne Port |  | 66536 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 844.664 | 9730.89 | 63349.7968 | 26384.5411 | 99465.2279 | 0 | 0 | 100% | 0% | 0% | 100% | 99465.2279 | 0 | 0 | 99465.2279 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 33155.076 | 33155.076 | 33155.076 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 013 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274 W: 2665, H: 2032, 6350 kg | 2140-MO-001 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 014 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-002 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 015 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-003 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 016 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-004 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Mobile Light Plant, Large |  | 5 | Ea | 13 | 100 | 975 | 1000 | 2075 | 65 | 500 | 4875 | 5000 | 10375 | 96 | 480 | 100% | 0% | 0% | 100% | 10375 | 0 | 0 | 10375 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3458.3333 | 0 | 3458.3333 | 0 | 0 | 0 | 0 | 3458.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Pick-Up Truck |  | 7 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 46.6667 | 145.8333 | 3500 | 1458.3333 | 5104.1667 | 4 | 28 | 100% | 0% | 0% | 100% | 5104.1667 | 0 | 0 | 5104.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1701.3889 | 0 | 1701.3889 | 0 | 0 | 0 | 0 | 1701.3889
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Rescue Boat and Trailer |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Passenger Van |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Ford F350 Pickup |  | 6 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 40 | 125 | 3000 | 1250 | 4375 | 4 | 24 | 100% | 0% | 0% | 100% | 4375 | 0 | 0 | 4375 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1458.3333 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 1458.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Jump Conveyor |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Stockpile Reclaim Loader, 988 |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Grove 60 Ton Crane |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 988 Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 345 Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 30,000 L Fuel Tanker Truck |  | -11 | Ea | 13 | 100 | 975 | 1000 | 2075 | -143 | -1100 | -10725 | -11000 | -22825 | 96 | -1056 | 100% | 0% | 0% | 100% | -22825 | 0 | 0 | -22825 | Type A 2AM-MRY1325 | removed | 2020-r | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -7608.3333 | 0 | -7608.3333 | 0 | 0 | 0 | 0 | -7608.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 30,000 L Fuel Tanker Truck |  | 12 | Ea | 13 | 100 | 975 | 1000 | 2075 | 156 | 1200 | 11700 | 12000 | 24900 | 96 | 1152 | 100% | 0% | 0% | 100% | 24900 | 0 | 0 | 24900 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8300 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 Loader |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950 Loader |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374F Excavator |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2766.6667 | 0 | 2766.6667 | 0 | 0 | 0 | 0 | 2766.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2766.6667 | 0 | 2766.6667 | 0 | 0 | 0 | 0 | 2766.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Duty Shunt Truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Duty Shunt Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Decommissioned Drill |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Feeder Dolly |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Feeder Dolly |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fines Mobile Stacker |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fines Mobile Stacker |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | John Deere 850 Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Stockpile Mobile Feeder |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Stockpile Mobile Stacker |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Reclaim Mobile Feeder |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Container Handler |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | Gantry Crane |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Larue Snow Blower |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 257 Skid steer |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Blaze Cube Frost Fighters |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Ford F550 Mechanics Truck |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | FIRE TRUCK |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Freightliner School Bus |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Kenworth Fuel Lube Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 740B Water Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 14M Grader |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel Tanker |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Jet A Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48p School Bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Track Mounted Drill Rig |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat bed boom truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | CAT 930 Loader |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Generator 3412-725 KW (Seacan) |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Lunch Rooms |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Man Lift |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Zoom Boom |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Boom Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Passenger Bus |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | Integrated Tool Carrier, 938 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | WRECKER TRUCK |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | FREIGHT HAUL TRACTOR , |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd party Equipment | MAINTENANCE FUEL/LUBE TRUCK , |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Skid-steer |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Flat Deck Truck |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Mini-Crane |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | Marine Patrol Boat |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | MECHANICS TRUCK, |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd party Equipment | CAT 992 Loader |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2766.6667 | 0 | 2766.6667 | 0 | 0 | 0 | 0 | 2766.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | Pick-Up Truck |  | 6 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 40 | 125 | 3000 | 1250 | 4375 | 4 | 24 | 100% | 0% | 0% | 100% | 4375 | 0 | 0 | 4375 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1458.3333 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 1458.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | 8 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 341.8 | 3765 | 25635 | 37650 | 67050 | 30 | 240 | 100% | 0% | 0% | 100% | 67050 | 0 | 0 | 67050 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 22350 | 0 | 22350 | 0 | 0 | 0 | 0 | 22350
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | -8 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -341.8 | -3765 | -25635 | -37650 | -67050 | 30 | -240 | 100% | 0% | 0% | 100% | -67050 | 0 | 0 | -67050 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -22350 | 0 | -22350 | 0 | 0 | 0 | 0 | -22350
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | 3 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 128.175 | 1411.875 | 9613.125 | 14118.75 | 25143.75 | 30 | 90 | 100% | 0% | 0% | 100% | 25143.75 | 0 | 0 | 25143.75 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8381.25 | 0 | 8381.25 | 0 | 0 | 0 | 0 | 8381.25
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | -3 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -128.175 | -1411.875 | -9613.125 | -14118.75 | -25143.75 | 30 | -90 | 100% | 0% | 0% | 100% | -25143.75 | 0 | 0 | -25143.75 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -8381.25 | 0 | -8381.25 | 0 | 0 | 0 | 0 | -8381.25
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2793.75 | 0 | 2793.75 | 0 | 0 | 0 | 0 | 2793.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2793.75 | 0 | 2793.75 | 0 | 0 | 0 | 0 | 2793.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -2793.75 | 0 | -2793.75 | 0 | 0 | 0 | 0 | -2793.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | 10,000 Gallon tank (gas and diesel) |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5587.5 | 0 | 5587.5 | 0 | 0 | 0 | 0 | 5587.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 4 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 170.9 | 1882.5 | 12817.5 | 18825 | 33525 | 30 | 120 | 100% | 0% | 0% | 100% | 33525 | 0 | 0 | 33525 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 11175 | 0 | 11175 | 0 | 0 | 0 | 0 | 11175
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2793.75 | 0 | 2793.75 | 0 | 0 | 0 | 0 | 2793.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -2793.75 | 0 | -2793.75 | 0 | 0 | 0 | 0 | -2793.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 1,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -2950 | -2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 9,000L |  | -1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -15.5 | -162.5 | -1162.5 | -1625 | -2950 | 20 | -20 | 100% | 0% | 0% | 100% | -2950 | 0 | 0 | -2950 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -1475 | -1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 5 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 77.5 | 812.5 | 5812.5 | 8125 | 14750 | 20 | 100 | 100% | 0% | 0% | 100% | 14750 | 0 | 0 | 14750 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7375 | 7375 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 31 | 325 | 2325 | 3250 | 5900 | 20 | 40 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -2950 | -2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tower Trailer |  | 3 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 30 | 112.5 | 2250 | 1125 | 3487.5 | 24 | 72 | 100% | 0% | 0% | 100% | 3487.5 | 0 | 0 | 3487.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1162.5 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 1162.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Kalamar DRT450 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D8T Dozer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tri-Trombone flat trailer |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tri-Trombone flat trailer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Freightliner Highway Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 30,000 L Fuel Tanker Trailer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Backhaul deloupe float trailer |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Backhaul Kenworth Unit |  | -2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -20 | -75 | -1500 | -750 | -2325 | 24 | -48 | 100% | 0% | 0% | 100% | -2325 | 0 | 0 | -2325 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -775 | 0 | -775 | 0 | 0 | 0 | 0 | -775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Backhaul Western Star Unit |  | -3 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -30 | -112.5 | -2250 | -1125 | -3487.5 | 24 | -72 | 100% | 0% | 0% | 100% | -3487.5 | 0 | 0 | -3487.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -1162.5 | 0 | -1162.5 | 0 | 0 | 0 | 0 | -1162.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 1988 MACK Service Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Side Dumper Lead or trailer |  | 19 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 190 | 712.5 | 14250 | 7125 | 22087.5 | 24 | 456 | 100% | 0% | 0% | 100% | 22087.5 | 0 | 0 | 22087.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 7362.5 | 0 | 7362.5 | 0 | 0 | 0 | 0 | 7362.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Passenger Bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 775 | 0 | 775 | 0 | 0 | 0 | 0 | 775
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader | JIS00277 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader | JIS00251 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00727 | -5 | Ea | 13 | 100 | 975 | 1000 | 2075 | -65 | -500 | -4875 | -5000 | -10375 | 96 | -480 | 100% | 0% | 0% | 100% | -10375 | 0 | 0 | -10375 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -3458.3333 | 0 | -3458.3333 | 0 | 0 | 0 | 0 | -3458.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00727 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01304 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01306 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01308 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00734 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK00743 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck | TFK01353 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Telehandler |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Kubota RTV-X1100c |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Used Light Plant |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Backhaul Ford Pickup |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -243.0556 | 0 | -243.0556 | 0 | 0 | 0 | 0 | -243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Backhaul GMC Sierra |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -243.0556 | 0 | -243.0556 | 0 | 0 | 0 | 0 | -243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Service Truck F250 |  | 4 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 26.6667 | 83.3333 | 2000 | 833.3333 | 2916.6667 | 4 | 16 | 100% | 0% | 0% | 100% | 2916.6667 | 0 | 0 | 2916.6667 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 972.2222 | 0 | 972.2222 | 0 | 0 | 0 | 0 | 972.2222
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Service Truck F250 |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK, DOUBLE WALLED 2494 LITER |  | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 983.3333 | 0 | 983.3333 | 0 | 0 | 0 | 0 | 983.3333
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KENWORTH SERVICE TRUCK TOROMONT ML | HTP021 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER VAC TRUCK | HTP026 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR016 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR017 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL 4400 FUEL TRUCK | FLT012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KALMAR CONTAINER HANDLER | CNH002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | GROVE RT890E CRANE | CRN001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MASABA PORTABLE CONVEYOR | CRURC2 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 320BL EXCAVATOR CATERPILLAR | EXC007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2008 GEHL LIFT TRUCK | FKT008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRI-DRIVE V.I.N. # 5KJRASD18CPBF7663 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRAS013BPAZ8119 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRASD1XBPAZ8117 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK NO: OHT033 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK NO: OHT028 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK OTH027 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN # 5KJRASD14BPAZ8114 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 40' FLATRACK TOLU 897574-0, STC JET FUEL A1 FS II DRUMS 205 L |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK VIN# 5KJRASD16BPA28115 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | M320F WHEELED EXCAVATOR |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2015 FREIGHTLINER SERVICE TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2004 PETERBILT TANKER TRUCK VIN# 2NPNHD8X24M822016 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINING TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 60/30 CENTER CAR BODY W BELLY PLATE |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G BODY |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD18GPHD7176 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD18GPHD7175 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR SNOW PLOW | HTP017 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR PLOW TRUCK | HTP028 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP031 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512202 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512402 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 4400 GAL STAINLESS STEEL WATER TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | SEWAGE TANK SERAIL # ST111-0716 |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | WATER TANK SERIAL # WT110-0070 |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | OSHKOSH FIRE TRUCK 1998 -T13000 MILNE | EMG001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GMC C8500 FOUNTAIN TIRE | HTP020 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLOAT TRAILER 20 FT - PINTLE HOOK | LBT004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS006 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS007 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT WATER TRUCK ML 2013 | HTP001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | WATER TRUCK | HTP002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KENWORTH WATER/METHANOL TRUCK | HTP003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KENWORTH T800 W/ KNUCKLE BOOM 2004 | HTP008 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT 367 2014 | HTP012 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT 379 2014 | HTP023 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT ROLL OFF TRUCK | HTP027 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT | JLG001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT Z45/25 | JLG003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT Z60/34 | JLG006 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT 450 AJ SERIES | JLG009 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ROLLER CP563E | RLR001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TL1255 | TLH001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER GEHL | TLH006 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CAT TELEHANDLER TL1055C | TLH007 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MINI-CRAWLER CRANE URW-295 (diesel) | CRN005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-350 SILVER PICK-UP , VIN # 1FTWW3BROAEB22478 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | HYDRAULIC PRESS |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-550 WHITE SERVICE TRUCK XLT FEC061335A |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORD F-550 WHITE SERVICE TRUCK XLT FEC061336A |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2008 KENWORTH MECHANICAL TRUCK VIN# 2NKMHN7XX8M212914 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MOBILE OFFICE ON WHEELS SERIAL # 240073498 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES 533C001 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES 133W003 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLATBED 3 AXLES UNIT 833X004 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | STEP DECK 3 AXLES UNIT 5334652 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT031 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | JOHN DEREE LIGHT TOWER | ALT032 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 AMBULANCE 2014 | EMG008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FOUNTAIN TIRE ATLAS COPCO COMPRESSOR | FCM001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR PD7000 | FKT002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR 2ET4000 | FKT003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT MITSUBISHI FB20PNT | FKT004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT CATERPILLAR DP40K-D | FKT007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT VALLEE | FKT009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HOTSY MOUNTED ON TRAILER | HTY001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP022 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP023 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP032 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP035 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP036 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2008 | LTP037 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP039 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP041 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP042 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP048 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP049 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP050 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP051 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP052 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP053 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP054 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP055 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 - 2011 | LTP061 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 | LTP062 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 2012 | LTP064 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 CREW CAB 4X4 2012 | LTP065 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 2008 | LTP066 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SERVICE TRUCK FOUNTAIN TIRE 2015 | MTP017 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 289C ALL TERRAIN | SKD006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 246 ALL TERRAIN | SKD007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CAT SKID STEER 2622C2 | SKD011 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 01 | SKJ001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 02 | SKJ002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 04 | SKJ004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 05 | SKJ005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 06 | SKJ006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/MANLIFT | SKJ007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/SCISSOR LIFT | SKJ008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKYJACK/MANLIFT | SKJ009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | MANLIFT - CROWN WAVE | SKJ011 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKI-DOO 2007 | SNM001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKI-DOO 2008 | SNM002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE KUBOTA RTV900 | SXS002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER TANDEM UTILITY FLAT DECK | TRL006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CATERPILLAR 2620 SKID STEER LOADER C/W BUCKET (BOBCAT) S/N 6555GP113734, VIN # CAT0262DVLST00504 |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENSET RADIATOR |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENSET RADIATOR |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SW-95 IRONWORKER |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SW-95 IRONWORKER |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | KNEE MILL |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | KNEE MILL |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BANDSAW |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BANDSAW |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | LATHE |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 213.625 | 2353.125 | 16021.875 | 23531.25 | 41906.25 | 30 | 150 | 100% | 0% | 0% | 100% | 41906.25 | 0 | 0 | 41906.25 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13968.75 | 0 | 13968.75 | 0 | 0 | 0 | 0 | 13968.75
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 77.5 | 812.5 | 5812.5 | 8125 | 14750 | 20 | 100 | 100% | 0% | 0% | 100% | 14750 | 0 | 0 | 14750 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7375 | 7375 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 037 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - SITE MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 038 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - SITE MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 2143-MO-003 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 039 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-004 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 040 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - PETERBILT 348 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-005 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 041 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - SITE MAINTENANCE SMALL LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 2143-MO-006 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 042 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-007 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 043 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 2143-MO-008 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 044 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MINE/TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-009 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 045 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 046 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-012 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 047 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-013 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 048 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 049 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 2143-MO-015 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 050 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 2143-MO-016 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 051 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-017 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 052 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-018 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 053 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-019 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 054 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Compactor | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE COMPACTOR - CAT CS56 L: 5860, W: 2300, H: 3070, 12250 kg | 2143-MO-020 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Compactor | CS56B | M4M00243 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 055 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-021 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 056 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-022 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 057 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170, W: 2410, H: 3320, 18338 kg | 2143-MO-023 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 058 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW295 | 2143-MO-024 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 059 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FD35N L: 2540, W: 1300, H: 2540, 4800 kg | 2143-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 060 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 2143-MO-026 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 061 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT DP50K L: 3305, W: 1460, H: 2400, 7160 kg | 2143-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - FREIGHTLINER |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 018 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-001 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 019 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 020 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-003 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 021 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-004 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 022 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-005 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 023 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-006 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 024 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-009 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 025 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-010 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 026 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 027 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-012 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 028 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-013 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 029 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 030 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-015 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 031 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-016 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 032 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-017 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 033 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-018 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 034 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-019 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 035 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-020 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Front End Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE RECLAIM FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 064 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 2144-MO-001 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 065 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 2144-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 066 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 2144-MO-003 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 067 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 2144-MO-004 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 068 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER DELIVERY TRUCK - PETERBILT 367 TRI-DRIVE | 2144-MO-005 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 069 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-006 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 070 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-007 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 071 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-008 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 072 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-009 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 073 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-010 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 074 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 075 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 2144-MO-012 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 076 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 2144-MO-013 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 077 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-014 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 078 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-015 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 079 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-016 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 080 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-017 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 081 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-018 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 082 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-019 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 083 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 084 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 085 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 086 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 087 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-031 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 088 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-032 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 089 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 090 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 091 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 092 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 093 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 094 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-038 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - FREIGHT HAUL TRACTOR - WeSTERN STAR 4900 |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER, SEMI DUMP |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 740 | MOBILE EQUIPMENT - WATER TRUCK - CAT 740 (8000 GAL) |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development |  | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 12 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 72 | 450 | 5400 | 4500 | 10350 | 0 | 0 | 100% | 0% | 0% | 100% | 10350 | 0 | 0 | 10350 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 5175 | 5175 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2230 | Causeway | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 099 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Dock Office - Demolish and Decontaminate Building - Trailer - Single | 2223-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 100 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Dock Office - Demolish and foundations - Gravel Base - Skidded Building | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 101 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Dock Office - Demolish floor finish - Raised Steel or Wooden Floor | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2221 | Dock Structure (includes ship loader foundations) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2225 | Mooring Buoys | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 100% | 0% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2240 | Transshipment and Marine Vessels | 2240 | Transshipment and Marine Vessels | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | CONVEYING - RECLAIM CONVEYOR - FAM L: 850000, W: 1524, H: 47000 VERTICAL LIFT SEE REMARKS kg | 2342-CV-001 | 1 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 1020 | 1020 | 100% | 0% | 0% | 100% | 1066410 | 0 | 0 | 1066410 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 355470 | 355470 | 355470 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | [6 empty] | Shiploading E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Shiploading E-House - Demolish and foundations - Gravel Base - Skidded Building | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Shiploading E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 124 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR DISCHARGE CHUTE - FAM | 2342-CH-015 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 125 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-026 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 126 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-027 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 127 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-028 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 128 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-029 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 137 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-002 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 138 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-003 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 139 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-004 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 140 | HP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | sampler bin | HOPPER - SAMPLER BIN - FAM | 2342-HP-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SAMPLER - ORE SAMPLER - FAM L: N/A, W: N/A, H: N/A | 2342-SA-019 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 130 | MT- |  | #N/A |  |  |  |  | RECLAIM CONVEYOR | 2342-MT-001 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 131 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-023 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 132 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-024 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 133 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-025 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 134 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-030 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 135 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-031 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Jump Conveyor |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Jump Conveyor |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Conveyor Feeder |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Conveyor Feeder |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-032 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | 0.16667 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 836.4 | 10455 | 62730 | 104550 | 177735 | 1020 | 170 | 100% | 0% | 0% | 100% | 177735 | 0 | 0 | 177735 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 59245 | 59245 | 59245 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Jump Conveyor |  | 12 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 230.4 | 2130 | 17280 | 21300 | 40710 | 1 | 12 | 100% | 0% | 0% | 100% | 40710 | 0 | 0 | 40710 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 13570 | 0 | 13570 | 0 | 0 | 0 | 0 | 13570
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Feed Convyor |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator 1000 kW |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Conveyors |  | 3 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 504 | 5550 | 37800 | 55500 | 98850 | 56 | 168 | 100% | 0% | 0% | 100% | 98850 | 0 | 0 | 98850 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 32950 | 0 | 32950 | 0 | 0 | 0 | 0 | 32950
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw crusher unit |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screener + Cone crusher unit |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator Sets |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43933.3333 | 0 | 43933.3333 | 0 | 0 | 0 | 0 | 43933.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator Sets |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Bucket Wheel Stacker Reclaimer |  | -2 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -336 | -3700 | -25200 | -37000 | -65900 | 56 | -112 | 100% | 0% | 0% | 100% | -65900 | 0 | 0 | -65900 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -21966.6667 | 0 | -21966.6667 | 0 | 0 | 0 | 0 | -21966.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Bucket Wheel Stacker Reclaimer |  | 2 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 336 | 3700 | 25200 | 37000 | 65900 | 56 | 112 | 100% | 0% | 0% | 100% | 65900 | 0 | 0 | 65900 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 21966.6667 | 0 | 21966.6667 | 0 | 0 | 0 | 0 | 21966.6667
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Cone Crusher |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Feeder (Small) |  | 3 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 57.6 | 532.5 | 4320 | 5325 | 10177.5 | 1 | 3 | 100% | 0% | 0% | 100% | 10177.5 | 0 | 0 | 10177.5 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3392.5 | 0 | 3392.5 | 0 | 0 | 0 | 0 | 3392.5
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Screener |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - RECLAIM MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT L: 230000, W: 1524 |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - STOCKPILE RECLAIM EXTENSION CONVEYOR |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 2 | ML-PRO-SHL-010-RFL01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 3 | ML-PRO-SHL-010-RFL03 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Reclaim Feeding, Line 2 | Reclaim Feeding, Line 4 | ML-PRO-SHL-010-RFL04 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd Party Contractor | Medium Equipment on 2017 Sea Lift |  | 93 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1785.6 | 16507.5 | 133920 | 165075 | 315502.5 | 1 | 93 | 100% | 0% | 0% | 100% | 315502.5 | 0 | 0 | 315502.5 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 105167.5 | 0 | 105167.5 | 0 | 0 | 0 | 0 | 105167.5
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Contractor | Heavy equipment on 2017 Sea Lift |  | 6 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 1008 | 11100 | 75600 | 111000 | 197700 | 56 | 336 | 100% | 0% | 0% | 100% | 197700 | 0 | 0 | 197700 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 65900 | 0 | 65900 | 0 | 0 | 0 | 0 | 65900
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | -0.16667 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | -836.4 | -10455 | -62730 | -104550 | -177735 | 1020 | -170 | 100% | 0% | 0% | 100% | -177735 | 0 | 0 | -177735 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -59245 | -59245 | -59245 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown |  | 230545.88 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2926.7433 | 33717.3349 | 219505.7511 | 91421.8957 | 344644.9817 | 0 | 0 | 100% | 0% | 0% | 100% | 344644.9817 | 0 | 0 | 344644.9817 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 114881.6606 | 114881.6606 | 114881.6606 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Footprints |  | 128865.8 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1635.9309 | 18846.6233 | 122694.8155 | 51101.1332 | 192642.572 | 0 | 0 | 100% | 0% | 0% | 100% | 192642.572 | 0 | 0 | 192642.572 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 64214.1907 | 64214.1907 | 64214.1907 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 107 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-001 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 108 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-002 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 109 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-003 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 110 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-004 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 111 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-005 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 112 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-006 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - FINES STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-003 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 115 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-004 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 116 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-005 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 117 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-006 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 118 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-007 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 119 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - FINES STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-008 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion |  | 82000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1040.977 | 11992.5 | 78073.2737 | 32516.7184 | 122582.492 | 0 | 0 | 100% | 0% | 0% | 100% | 122582.492 | 0 | 0 | 122582.492 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 40860.8307 | 40860.8307 | 40860.8307 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion 2019 |  | 140000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1777.2778 | 20475 | 133295.8331 | 55516.3484 | 209287.1815 | 0 | 0 | 100% | 0% | 0% | 100% | 209287.1815 | 0 | 0 | 209287.1815 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 69762.3938 | 69762.3938 | 69762.3938 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown - Realignment of the shipload conveyor |  | 26000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 330.0659 | 3802.5 | 24754.9404 | 10310.179 | 38867.6194 | 0 | 0 | 100% | 0% | 0% | 100% | 38867.6194 | 0 | 0 | 38867.6194 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12955.8731 | 12955.8731 | 12955.8731 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd party Equipment | Apron Feeder (TK) |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd party Equipment | Hopper (TK) |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional sealift laydown area |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Settling Ponds |  | 11423.76 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 508.2984 | 1943.1816 | 38122.3791 | 7254.6056 | 47320.1663 | 0 | 0 | 100% | 0% | 0% | 100% | 47320.1663 | 0 | 0 | 47320.1663 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15773.3888 | 15773.3888 | 15773.3888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation - New 2019 |  | 15000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 667.4226 | 2551.5 | 50056.6964 | 9525.6802 | 62133.8766 | 0 | 0 | 100% | 0% | 0% | 100% | 62133.8766 | 0 | 0 | 62133.8766 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20711.2922 | 20711.2922 | 20711.2922 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 2a |  | 4400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 195.7773 | 748.44 | 14683.2976 | 2794.1995 | 18225.9371 | 0 | 0 | 100% | 0% | 0% | 100% | 18225.9371 | 0 | 0 | 18225.9371 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6075.3124 | 6075.3124 | 6075.3124 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 1a |  | 5000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 222.4742 | 850.5 | 16685.5655 | 3175.2267 | 20711.2922 | 0 | 0 | 100% | 0% | 0% | 100% | 20711.2922 | 0 | 0 | 20711.2922 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6903.7641 | 6903.7641 | 6903.7641 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | VP6 | VENDOR PKG - Ship Loader | VP6 | Packaged Facilities | Ship Loader |  | Shiploader Package | 2351-SL-001 | 0 | Lot | 14448 | 180600 | 1083600 | 1806000 | 3070200 | 0 | 0 | 0 | 0 | 0 | 30295 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and Decontaminate Building - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and foundations - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish floor finish - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and Decontaminate Building - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and foundations - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish floor finish - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 152 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER PROPORTIONAL GATE - FAM | 2351-CH-003 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 153 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-004 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 154 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-005 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 155 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-006 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 156 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE - FAM | 2351-CH-008 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 157 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-009 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 158 | CV- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CONVEYING - SHIPLOADER LINK CONVEYOR - FAM 212330 kg | 2351-CV-007 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 159 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DRIVE | 2351-MT-007A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 160 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR BRAKE | 2351-MT-007B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 161 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE | 2351-MT-007C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 162 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN | 2351-MT-007D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 163 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR | 2351-MT-007E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 164 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 165 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 166 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM 1960000 kg | 2351-SL-001 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 167 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-001A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 170 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-001B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 171 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-001C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 172 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 173 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 174 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 175 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 176 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-001H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 177 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-001J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 178 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-001K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 179 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE FAN | 2351-MT-001L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 180 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-001M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 181 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-001N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 182 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 183 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 184 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 185 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 186 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 187 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 193 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM | 2351-SL-002 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 194 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-002A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 197 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-002B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 198 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-002C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 199 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 200 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 201 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 202 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 203 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-002H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 204 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-002J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 205 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-002K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 206 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE BRAKE | 2351-MT-002L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 207 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-002M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 208 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-002N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 209 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 210 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 211 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 212 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 213 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 214 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 168 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-001AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 169 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-001AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 188 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-001V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 189 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-001W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 190 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-001X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 191 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-001Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 192 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-001Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 195 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-002AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 196 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-002AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 215 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-002V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 216 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-002W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 217 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-002X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 218 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-002Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 219 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-002Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome
2000 | Milne Port | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2430 | Aerodrome Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2435 | Field Electrical Centre | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 237 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 240 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 243 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 246 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 238 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BA - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 239 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BA - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 241 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BB - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 242 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BB - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 244 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BC - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 245 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BC - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 247 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BD - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 248 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BD - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Offices, washcars for Laydown R3 62 @ 15m2 3 @ 30m2 3 @ 66m2 |  | 1218 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 682.5875 | 3412.9375 | 51194.0625 | 85323.4375 | 139930.4375 | 1 | 1218 | 100% | 0% | 0% | 100% | 139930.4375 | 0 | 0 | 139930.4375 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46643.4792 | 46643.4792 | 46643.4792 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BE - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BE - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BF - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BF - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Pre-Cast Concrete Foundations (Mobilized to Site) |  | 8000 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 1000 | 15000 | 75000 | 150000 | 240000 | 0 | 0 | 100% | 0% | 0% | 100% | 240000 | 0 | 0 | 240000 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 48.42 | 605.25 | 3631.5 | 6052.5 | 10289.25 | 1 | 216 | 100% | 0% | 0% | 100% | 10289.25 | 0 | 0 | 10289.25 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3429.75 | 3429.75 | 3429.75 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 380 person camp at Milne Port |  | 380 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 266304.3455 | 0 | 0 | 266304.3455 | 0 | 0 | 100% | 0% | 0% | 1 | 266304.3455 | 0 | 0 | 266304.3455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 266304.3455 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 380 man temporary hardwall camp at Milne Port inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 10,720 m2) |  | 10720 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 2403.0667 | 30038.3333 | 180230 | 300383.3333 | 510651.6667 | 1 | 10720 | 100% | 0% | 0% | 100% | 510651.6667 | 0 | 0 | 510651.6667 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 170217.2222 | 170217.2222 | 170217.2222 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Offices, washcars (assume 16 units @ 36 m2 per wash car) |  | 576 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 129.12 | 1614 | 9684 | 16140 | 27438 | 1 | 576 | 100% | 0% | 0% | 100% | 27438 | 0 | 0 | 27438 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9146 | 9146 | 9146 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2510 | Accommodations Area | 225 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 2510-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Carpenter Workshop |  | 100 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 15.6917 | 196.1458 | 1176.875 | 1961.4583 | 3334.4792 | 1 | 100 | 100% | 0% | 0% | 100% | 3334.4792 | 0 | 0 | 3334.4792 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1111.4931 | 1111.4931 | 1111.4931 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 43.75 | 546.875 | 3281.25 | 5468.75 | 9296.875 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 9296.875 | 0 | 0 | 9296.875 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3098.9583 | 3098.9583 | 3098.9583 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 254 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 2513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 40.485 | 506.0629 | 3036.3774 | 5060.629 | 8603.0693 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 8603.0693 | 0 | 0 | 8603.0693 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2867.6898 | 2867.6898 | 2867.6898 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 255 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 2513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 34.8513 | 522.7695 | 2613.8476 | 5227.6952 | 8364.3123 | 0 | 0 | 100% | 0% | 0% | 100% | 8364.3123 | 0 | 0 | 8364.3123 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2788.1041 | 2788.1041 | 2788.1041 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 265 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2513-TK-003 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | ff3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) |  |  | Aecon Workshop |  | 1650 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 295.9 | 3698.75 | 22192.5 | 36987.5 | 62878.75 | 0.5 | 825 | 100% | 0% | 0% | 100% | 62878.75 | 0 | 0 | 62878.75 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20959.5833 | 20959.5833 | 20959.5833 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Sana Workshop |  | 500 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 112.0833 | 1401.0417 | 8406.25 | 14010.4167 | 23817.7083 | 1 | 500 | 100% | 0% | 0% | 100% | 23817.7083 | 0 | 0 | 23817.7083 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7939.2361 | 7939.2361 | 7939.2361 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers (2 units at 36 m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Crusher services trailer |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Site Contruction Office |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Offices and Lunchrooms (5 @ 36m2) |  | 180 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 40.35 | 504.375 | 3026.25 | 5043.75 | 8574.375 | 1 | 180 | 100% | 0% | 0% | 100% | 8574.375 | 0 | 0 | 8574.375 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2858.125 | 2858.125 | 2858.125 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 20 | 250 | 1500 | 2500 | 4250 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4250 | 0 | 0 | 4250 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 267 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 2513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 266 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613, W: 737, H: 1676 | 2513-TK-004 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 251 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 2513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 11 | 87.5 | 525 | 875 | 1487.5 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1487.5 | 0 | 0 | 1487.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 495.8333 | 495.8333 | 495.8333 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 258 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2513-PP-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 259 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2513-MT-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 260 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 261 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 262 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 263 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 264 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 2513-SQ-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 2513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 256 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg | 2513-MO-001 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 257 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Fire Truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH T1500 L: 10540, W: 3100, H: 3810, 16500 kg | 2513-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 227 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 1388.4758 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 311.25 | 3890.625 | 23343.75 | 38906.25 | 66140.625 | 1 | 1388.4758 | 100% | 0% | 0% | 100% | 66140.625 | 0 | 0 | 66140.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 22046.875 | 22046.875 | 22046.875 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 233 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 95 | 1187.5 | 7125 | 11875 | 20187.5 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 20187.5 | 0 | 0 | 20187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6729.1667 | 6729.1667 | 6729.1667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 230 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-002 | 334.5725 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 75 | 937.5 | 5625 | 9375 | 15937.5 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 15937.5 | 0 | 0 | 15937.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5312.5 | 5312.5 | 5312.5 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 231 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 232 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 234 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 235 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 228 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 229 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Change Rooms - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Change Rooms - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Change Rooms - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad development (Milne Port) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 22423.6266 | 22423.6266 | 22423.6266 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash (Repurposed Warehouse) - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2523-BLD-001 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash (Repurposed Warehouse) - Demolish and foundations - Precast Footing (Perimeter Beam) | 2523-BLD-001 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash (Repurposed Warehouse) - Demolish floor finish - Gravel | 2523-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | 150000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1904.2262 | 21937.5 | 142816.9641 | 59481.8019 | 224236.2659 | 0 | 0 | 100% | 0% | 0% | 100% | 224236.2659 | 0 | 0 | 224236.2659 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 74745.422 | 74745.422 | 74745.422 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | -150000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -1904.2262 | -21937.5 | -142816.9641 | -59481.8019 | -224236.2659 | 0 | 0 | 100% | 0% | 0% | 100% | -224236.2659 | 0 | 0 | -224236.2659 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -74745.422 | -74745.422 | -74745.422 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W1 |  | 23100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 293.2508 | 3378.375 | 21993.8125 | 9160.1975 | 34532.385 | 0 | 0 | 100% | 0% | 0% | 100% | 34532.385 | 0 | 0 | 34532.385 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 11510.795 | 11510.795 | 11510.795 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W6 |  | 2750 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 34.9108 | 402.1875 | 2618.311 | 1090.4997 | 4110.9982 | 0 | 0 | 100% | 0% | 0% | 100% | 4110.9982 | 0 | 0 | 4110.9982 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1370.3327 | 1370.3327 | 1370.3327 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W7 |  | 1780 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 22.5968 | 260.325 | 1694.7613 | 705.8507 | 2660.937 | 0 | 0 | 100% | 0% | 0% | 100% | 2660.937 | 0 | 0 | 2660.937 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 886.979 | 886.979 | 886.979 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W3 |  | 14300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 181.5362 | 2091.375 | 13615.2172 | 5670.5984 | 21377.1907 | 0 | 0 | 100% | 0% | 0% | 100% | 21377.1907 | 0 | 0 | 21377.1907 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7125.7302 | 7125.7302 | 7125.7302 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W14 |  | 8850 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 112.3493 | 1294.3125 | 8426.2009 | 3509.4263 | 13229.9397 | 0 | 0 | 100% | 0% | 0% | 100% | 13229.9397 | 0 | 0 | 13229.9397 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4409.9799 | 4409.9799 | 4409.9799 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W15 |  | 10950 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 139.0085 | 1601.4375 | 10425.6384 | 4342.1715 | 16369.2474 | 0 | 0 | 100% | 0% | 0% | 100% | 16369.2474 | 0 | 0 | 16369.2474 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5456.4158 | 5456.4158 | 5456.4158 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W10B |  | 12450 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 158.0508 | 1820.8125 | 11853.808 | 4936.9896 | 18611.6101 | 0 | 0 | 100% | 0% | 0% | 100% | 18611.6101 | 0 | 0 | 18611.6101 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6203.87 | 6203.87 | 6203.87 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W11 |  | 7550 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 95.8461 | 1104.1875 | 7188.4539 | 2993.9174 | 11286.5587 | 0 | 0 | 100% | 0% | 0% | 100% | 11286.5587 | 0 | 0 | 11286.5587 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3762.1862 | 3762.1862 | 3762.1862 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 270 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-001 | 892.1933 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 500 | 1750 | 37500 | 62500 | 101750 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 101750 | 0 | 0 | 101750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 33916.6667 | 33916.6667 | 33916.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 276 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2521-BLD-003 | 267.658 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 150 | 750 | 11250 | 18750 | 30750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 30750 | 0 | 0 | 30750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10250 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 271 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-001 | 892.1933 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 129.5521 | 1619.4013 | 9716.4077 | 16194.0128 | 27529.8218 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 27529.8218 | 0 | 0 | 27529.8218 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9176.6073 | 9176.6073 | 9176.6073 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 272 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-001 | 892.1933 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 111.5242 | 1672.8625 | 8364.3123 | 16728.6245 | 26765.7993 | 0 | 0 | 100% | 0% | 0% | 100% | 26765.7993 | 0 | 0 | 26765.7993 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8921.9331 | 8921.9331 | 8921.9331 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 273 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-002 | 148.6989 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 83.3333 | 291.6667 | 6250 | 10416.6667 | 16958.3333 | 1 | 148.6989 | 100% | 0% | 0% | 100% | 16958.3333 | 0 | 0 | 16958.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5652.7778 | 5652.7778 | 5652.7778 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 296 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 2521.5-P | 255 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 63.75 | 796.875 | 4781.25 | 7968.75 | 13546.875 | 0.01 | 2.55 | 100% | 0% | 100% | 0% | 13546.875 | 0 | 13546.875 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4515.625 | 4515.625 | 4515.625 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 295 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2521-TK-053 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 2521-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 294 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803, W: 1245, H: 1346 | 2521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 280 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 274 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-002 | 148.6989 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 21.592 | 269.9002 | 1619.4013 | 2699.0021 | 4588.3036 | 0.75 | 111.5242 | 100% | 0% | 0% | 100% | 4588.3036 | 0 | 0 | 4588.3036 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1529.4345 | 1529.4345 | 1529.4345 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 277 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-003 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 290 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2521-PP-051 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 275 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade | 2521-BLD-002 | 148.6989 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 18.5874 | 278.8104 | 1394.052 | 2788.1041 | 4460.9665 | 0 | 0 | 100% | 0% | 0% | 100% | 4460.9665 | 0 | 0 | 4460.9665 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1486.9888 | 1486.9888 | 1486.9888 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 292 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 293 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 281 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 282 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 283 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 284 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 285 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 286 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 287 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 288 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 289 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 291 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2521-MT-051 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 278 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-003 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Anmar Workshop |  | 1670 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 74.3064 | 284.067 | 5572.9789 | 1060.5257 | 6875.257 | 0 | 0 | 100% | 0% | 0% | 100% | 6875.257 | 0 | 0 | 6875.257 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2291.7523 | 2291.7523 | 2291.7523 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-005 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-005 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-005 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  |  |  | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2- Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-006 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2- Demolish floor finish - Slab on grade | 2521-BLD-006 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 91.0364 | 348.0246 | 6827.7334 | 1299.3028 | 8475.0608 | 0 | 0 | 100% | 0% | 0% | 100% | 8475.0608 | 0 | 0 | 8475.0608 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2825.0203 | 2825.0203 | 2825.0203 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 301 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 2522-SQ-004 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 306 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 2522-SQ-011 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 313 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-026 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 314 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-027 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 600kw Generators |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 60kw Generator |  | 3 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 57.6 | 532.5 | 4320 | 5325 | 10177.5 | 1 | 3 | 100% | 0% | 0% | 100% | 10177.5 | 0 | 0 | 10177.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3392.5 | 0 | 3392.5 | 0 | 0 | 0 | 0 | 3392.5
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Atlas 1000 mVA Transformers |  | 4 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 76.8 | 710 | 5760 | 7100 | 13570 | 1 | 4 | 100% | 0% | 0% | 100% | 13570 | 0 | 0 | 13570 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4523.3333 | 0 | 4523.3333 | 0 | 0 | 0 | 0 | 4523.3333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Generator |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 300 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 2522-SQ-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 2522-SQ-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 303 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 2522-SQ-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 304 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-009 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 305 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 307 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 2522-SQ-012 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 308 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 2522-SQ-014 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 309 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 2522-SQ-018 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 310 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 2522-SQ-022 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 311 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-023 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 312 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-025 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 315 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 2522-SQ-028 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 316 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-029 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-029 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 318 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-030 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 319 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-030 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 320 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 2522-SQ-033 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 321 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 2522-SQ-034 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 322 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584, W: 864, H: 1120, 110 kg | 2522-SQ-037 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 323 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-038 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 324 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-039 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 325 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 2522-SQ-040 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Generator/Air Compressor |  | -1 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | -8.1 | -88.75 | -607.5 | -887.5 | -1583.75 | 0.5 | -0.5 | 100% | 0% | 0% | 100% | -1583.75 | 0 | 0 | -1583.75 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -527.9167 | 0 | -527.9167 | 0 | 0 | 0 | 0 | -527.9167
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Generator/Air Compressor |  | 2 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 16.2 | 177.5 | 1215 | 1775 | 3167.5 | 0.5 | 1 | 100% | 0% | 0% | 100% | 3167.5 | 0 | 0 | 3167.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1055.8333 | 0 | 1055.8333 | 0 | 0 | 0 | 0 | 1055.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Light Plant |  | 27 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 218.7 | 2396.25 | 16402.5 | 23962.5 | 42761.25 | 0.5 | 13.5 | 100% | 0% | 0% | 100% | 42761.25 | 0 | 0 | 42761.25 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 14253.75 | 0 | 14253.75 | 0 | 0 | 0 | 0 | 14253.75
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Light Plant |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Frost Fighter Heater |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson extreme cold BT400NEX-D4A |  | 10 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 192 | 1775 | 14400 | 17750 | 33925 | 1 | 10 | 100% | 0% | 0% | 100% | 33925 | 0 | 0 | 33925 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 11308.3333 | 0 | 11308.3333 | 0 | 0 | 0 | 0 | 11308.3333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | 400,000 BTU Indirect Fired Diesel Heater |  | 18 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 145.8 | 1597.5 | 10935 | 15975 | 28507.5 | 0.5 | 9 | 100% | 0% | 0% | 100% | 28507.5 | 0 | 0 | 28507.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 9502.5 | 0 | 9502.5 | 0 | 0 | 0 | 0 | 9502.5
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Welding machines 400-500 amps |  | 8 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 153.6 | 1420 | 11520 | 14200 | 27140 | 1 | 8 | 100% | 0% | 0% | 100% | 27140 | 0 | 0 | 27140 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 9046.6667 | 0 | 9046.6667 | 0 | 0 | 0 | 0 | 9046.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Power Pack 5/10 gallon per minute |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generator +/- 15-20kw |  | 4 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 76.8 | 710 | 5760 | 7100 | 13570 | 1 | 4 | 100% | 0% | 0% | 100% | 13570 | 0 | 0 | 13570 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4523.3333 | 0 | 4523.3333 | 0 | 0 | 0 | 0 | 4523.3333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson 6700 |  | 4 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 76.8 | 710 | 5760 | 7100 | 13570 | 1 | 4 | 100% | 0% | 0% | 100% | 13570 | 0 | 0 | 13570 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 4523.3333 | 0 | 4523.3333 | 0 | 0 | 0 | 0 | 4523.3333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson 6700 all in one |  | 3 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 57.6 | 532.5 | 4320 | 5325 | 10177.5 | 1 | 3 | 100% | 0% | 0% | 100% | 10177.5 | 0 | 0 | 10177.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3392.5 | 0 | 3392.5 | 0 | 0 | 0 | 0 | 3392.5
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Clipping machine |  | 6 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 48.6 | 532.5 | 3645 | 5325 | 9502.5 | 0.5 | 3 | 100% | 0% | 0% | 100% | 9502.5 | 0 | 0 | 9502.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3167.5 | 0 | 3167.5 | 0 | 0 | 0 | 0 | 3167.5
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Herman Nelson Flagro-1000 trailer mount |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | 55KW Generator |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generators 60+kw |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Diesel Generators 135kw (shipment 2017) |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Engine System for mobile trolly movement |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Heater (Flagro) |  | 4 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 32.4 | 355 | 2430 | 3550 | 6335 | 0.5 | 2 | 100% | 0% | 0% | 100% | 6335 | 0 | 0 | 6335 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2111.6667 | 0 | 2111.6667 | 0 | 0 | 0 | 0 | 2111.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd party Equipment | Air compressor |  | 4 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 32.4 | 355 | 2430 | 3550 | 6335 | 0.5 | 2 | 100% | 0% | 0% | 100% | 6335 | 0 | 0 | 6335 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2111.6667 | 0 | 2111.6667 | 0 | 0 | 0 | 0 | 2111.6667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Generator 114 kW |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Generator 150 kVA, Generator 250 kVA, Generator 30 kVA, Generator 100 kVA |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | 7m3/min / 250cft/min mobile compressors, set of 50 mm PVC perforated tubes |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | 3rd party Equipment | Oxy fuel cutting systems, induction heating system, 400A welding generators, welding sets, 7m3/min / 250cft/min mobile compressors |  | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | -21 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | -170.1 | -1863.75 | -12757.5 | -18637.5 | -33258.75 | 0.5 | -10.5 | 100% | 0% | 0% | 100% | -33258.75 | 0 | 0 | -33258.75 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -11086.25 | 0 | -11086.25 | 0 | 0 | 0 | 0 | -11086.25
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Heater | Frost Fighter Heater | ML-FAC-POH-010 | 38 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 307.8 | 3372.5 | 23085 | 33725 | 60182.5 | 0.5 | 19 | 100% | 0% | 0% | 100% | 60182.5 | 0 | 0 | 60182.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 20060.8333 | 0 | 20060.8333 | 0 | 0 | 0 | 0 | 20060.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | 3rd Party Contractor | Light equipment 2017 Sea Lift |  | 14 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 113.4 | 1242.5 | 8505 | 12425 | 22172.5 | 0.5 | 7 | 100% | 0% | 0% | 100% | 22172.5 | 0 | 0 | 22172.5 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 7390.8333 | 0 | 7390.8333 | 0 | 0 | 0 | 0 | 7390.8333
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 351 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-009 | 75.2788 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 42.1875 | 210.9375 | 3164.0625 | 5273.4375 | 8648.4375 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 8648.4375 | 0 | 0 | 8648.4375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2882.8125 | 2882.8125 | 2882.8125 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 354 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-010 | 75.2788 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 42.1875 | 210.9375 | 3164.0625 | 5273.4375 | 8648.4375 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 8648.4375 | 0 | 0 | 8648.4375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2882.8125 | 2882.8125 | 2882.8125 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 327 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 330 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 333 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 336 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 339 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 342 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 345 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-007 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 348 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-008 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 357 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 2530-BLD-011 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1138.8889 | 1138.8889 | 1138.8889 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 358 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 359 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 328 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 329 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 331 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 332 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 334 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 335 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 337 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 338 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 340 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 341 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 343 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 344 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 346 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 347 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 349 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 350 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 352 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 353 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 355 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 356 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-002 | 56 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 8.7873 | 109.8417 | 659.05 | 1098.4167 | 1867.3083 | 1 | 56 | 100% | 0% | 0% | 100% | 1867.3083 | 0 | 0 | 1867.3083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 622.4361 | 622.4361 | 622.4361 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-002 | 56 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.1316 | 101.6444 | 609.8665 | 1016.4442 | 1727.9551 | 0.75 | 42 | 100% | 0% | 0% | 100% | 1727.9551 | 0 | 0 | 1727.9551 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 575.985 | 575.985 | 575.985 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 4.4833 | 56.0417 | 336.25 | 560.4167 | 952.7083 | 1 | 20 | 100% | 0% | 0% | 100% | 952.7083 | 0 | 0 | 952.7083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 317.5694 | 317.5694 | 317.5694 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical office - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical office - Demolish floor finish - Gravel | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 2530-BLD-BIM-002 | 56 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 361 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 250 | 875 | 18750 | 31250 | 50875 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 50875 | 0 | 0 | 50875 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 16958.3333 | 16958.3333 | 16958.3333 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 362 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 64.7761 | 809.7006 | 4858.2038 | 8097.0064 | 13764.9109 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 13764.9109 | 0 | 0 | 13764.9109 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4588.3036 | 4588.3036 | 4588.3036 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 363 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 2540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 55.7621 | 836.4312 | 4182.1561 | 8364.3123 | 13382.8996 | 0 | 0 | 100% | 0% | 0% | 100% | 13382.8996 | 0 | 0 | 13382.8996 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4460.9665 | 4460.9665 | 4460.9665 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2540-VP-001 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 364 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1667 | 145.8333 | 2187.5 | 3645.8333 | 5979.1667 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 5979.1667 | 0 | 0 | 5979.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1993.0556 | 1993.0556 | 1993.0556 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 374 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2540-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 371 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 2540-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 367 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 368 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 369 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 370 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 372 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 2540-SQ-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 373 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG - OHAVX32XW10000X | 2540-SQ-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 365 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 366 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 12933 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 575.4518 | 2199.9033 | 43158.8836 | 8213.0415 | 53571.8284 | 0 | 0 | 100% | 0% | 0% | 100% | 53571.8284 | 0 | 0 | 53571.8284 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 17857.2761 | 17857.2761 | 17857.2761 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm at Milne Inlet - New waste management building |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Future Hazardous Waste Berm |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Hazardous Waste Berm |  | 0 | m2 | 0.0318 | 0.02385 | 2.385 | 0.2385 | 2.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Snow Dump |  | 3189 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 141.894 | 542.4489 | 10642.0537 | 2025.1596 | 13128.859 | 0 | 0 | 100% | 0% | 0% | 100% | 13128.859 | 0 | 0 | 13128.859 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4376.2863 | 4376.2863 | 4376.2863 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Contaminated Snow dump/oily water containment - new 2019 |  | 2700 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 120.1361 | 459.27 | 9010.2054 | 1714.6224 | 11115.6849 | 0 | 0 | 100% | 0% | 0% | 100% | 11115.6849 | 0 | 0 | 11115.6849 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3705.2283 | 3705.2283 | 3705.2283 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste containment facilities 2020 Port Shop - 72m2 |  | 72 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 3.2036 | 12.2472 | 240.2721 | 45.7233 | 296.4183 | 0 | 0 | 100% | 0% | 0% | 100% | 296.4183 | 0 | 0 | 296.4183 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 98.8061 | 98.8061 | 98.8061 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste Berm 2019 |  | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-1 | 2000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 88.9897 | 340.2 | 6674.2262 | 1270.0907 | 8233.8407 | 0 | 0 | 100% | 0% | 0% | 100% | 8233.8407 | 0 | 0 | 8233.8407 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2744.6136 | 2744.6136 | 2744.6136 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-3 | 678 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 30.1675 | 115.3278 | 2262.5627 | 430.5607 | 2791.272 | 0 | 0 | 100% | 0% | 0% | 100% | 2791.272 | 0 | 0 | 2791.272 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 930.424 | 930.424 | 930.424 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-5 | 652 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 29.0106 | 110.9052 | 2175.7977 | 414.0496 | 2684.2321 | 0 | 0 | 100% | 0% | 0% | 100% | 2684.2321 | 0 | 0 | 2684.2321 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 894.744 | 894.744 | 894.744 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-4 | 597 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 26.5634 | 101.5497 | 1992.2565 | 379.1221 | 2457.8014 | 0 | 0 | 100% | 0% | 0% | 100% | 2457.8014 | 0 | 0 | 2457.8014 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 819.2671 | 819.2671 | 819.2671 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-2 | 272 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 12.1026 | 46.2672 | 907.6948 | 172.7323 | 1119.8023 | 0 | 0 | 100% | 0% | 0% | 100% | 1119.8023 | 0 | 0 | 1119.8023 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 373.2674 | 373.2674 | 373.2674 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-6 | 34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 1.5128 | 5.7834 | 113.4618 | 21.5915 | 139.9753 | 0 | 0 | 100% | 0% | 0% | 100% | 139.9753 | 0 | 0 | 139.9753 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46.6584 | 46.6584 | 46.6584 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 398 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-001 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 399 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-002 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 400 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-003 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 401 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-004 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 402 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-005 | 1 | Ea | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 80 | 80 | 100% | 0% | 0% | 100% | 85157.5 | 0 | 0 | 85157.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 42578.75 | 42578.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 403 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-006 | 1 | Ea | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 80 | 80 | 100% | 0% | 0% | 100% | 85157.5 | 0 | 0 | 85157.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 42578.75 | 42578.75 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 387 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-014 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 384 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-013 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 854.1667 | 854.1667 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 390 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - EXISTING DIESEL FUEL DISPENSING MODULE | 2613-FD-013 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 391 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 2613-FD-014 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 392 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.1 | 2613-PP-007 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 393 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.2 | 2613-PP-008 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 394 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.3 | 2613-PP-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 395 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.4 | 2613-PP-010 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 396 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.5 | 2613-PP-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 397 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.6 | 2613-PP-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 386 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-013 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 385 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-013 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 389 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-014 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 388 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-014 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5587.5 | 0 | 5587.5 | 0 | 0 | 0 | 0 | 5587.5
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Diesel Module | Diesel Module | ML-FUM-FDI-010 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 15ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 45759.1667 | 0 | 45759.1667 | 0 | 0 | 0 | 0 | 45759.1667
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 3ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 45759.1667 | 0 | 45759.1667 | 0 | 0 | 0 | 0 | 45759.1667
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Farm Berm |  | 25393 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 1129.8575 | 4319.3493 | 84739.3128 | 16125.7065 | 105184.3686 | 0 | 0 | 100% | 0% | 0% | 100% | 105184.3686 | 0 | 0 | 105184.3686 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 52592.1843 | 52592.1843 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 413 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-007 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 414 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-008 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 415 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-009 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-010 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 405 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2614-FD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 854.1667 | 854.1667 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 408 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - JET-A1 FUEL DISPENSING MODULE | 2614-FD-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 409 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 410 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 411 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 412 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 407 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Jet-A1 Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2614-FD-011 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 406 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Jet-A1 Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2614-FD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet A1 Module | Jet A1 Module | ML-FUM-FDI-020 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | Additional 750 kL Jet-A Tank at Milne Port |  | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 418 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 17.7083 | 61.9792 | 1328.125 | 2213.5417 | 3603.6458 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 3603.6458 | 0 | 0 | 3603.6458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1201.2153 | 1201.2153 | 1201.2153 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 419 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 17.7083 | 61.9792 | 1328.125 | 2213.5417 | 3603.6458 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 3603.6458 | 0 | 0 | 3603.6458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1201.2153 | 1201.2153 | 1201.2153 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 420 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Marine Manifold Building - Demolish floor finish - Raised Steel or Wooden Floor | 2615-BLD-001 | 31.5985 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 380 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 381 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 422 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 423 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-002 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 424 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 425 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 426 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 427 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 428 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-007 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2616 | Weatherhaven camp |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Weatherhaven genset fuel bladder berm |  | 500 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 22.2474 | 85.05 | 1668.5565 | 317.5227 | 2058.4602 | 0 | 0 | 100% | 0% | 0% | 100% | 2058.4602 | 0 | 0 | 2058.4602 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 686.1534 | 686.1534 | 686.1534 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Port Site |  | 3500 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 350 | 4375 | 26250 | 43750 | 74375 | 0.01 | 35 | 100% | 0% | 0% | 100% | 74375 | 0 | 0 | 74375 | Type B Construction 2BC-MRY1416 |  | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24791.6667 | 24791.6667 | 24791.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | E-House |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
2000 | Milne Port | 2700 | Site Utilities | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 50,000 L Portable Fuel Dispensing Unit |  | 1364 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 60.691 | 232.0164 | 4551.8223 | 866.2019 | 5650.0405 | 0 | 0 | 100% | 0% | 0% | 100% | 5650.0405 | 0 | 0 | 5650.0405 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1883.3468 | 1883.3468 | 1883.3468 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Water Tank Main Unit |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 0 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 431 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 61.25 | 765.625 | 4593.75 | 7656.25 | 13015.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 13015.625 | 0 | 0 | 13015.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4338.5417 | 4338.5417 | 4338.5417 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 432 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | -1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | -47 | -400 | -3525 | -4000 | -7925 | 329.2683 | -329.2683 | 100% | 0% | 100% | 0% | -7925 | 0 | -7925 | 0 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -2641.6667 | -2641.6667 | -2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE VENDOR PACKAGE | 2720-VP-020 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 448 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 2720-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 449 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 2720-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 450 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 2720-TK-008 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 451 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 2720-TK-011 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 452 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2720-TK-033 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 434 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 435 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 436 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 2720-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 437 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 2720-PP-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 438 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 2720-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 439 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 2720-PP-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 440 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 2720-PP-010 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 441 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 2720-PP-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 442 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 2720-PP-013 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 443 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER UNLOADING PUMP - HAYWARD GORDON S-3 | 2720-PP-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 444 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-031 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 445 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-031 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 446 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-032 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 447 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-032 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 433 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 2720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - POTABLE WATER STORAGE TANK (20 m3) |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - RAW WATER TANK (25 m3) |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 4180 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 185.9884 | 711.018 | 13949.1327 | 2654.4895 | 17208.727 | 0 | 0 | 100% | 0% | 0% | 100% | 17208.727 | 0 | 0 | 17208.727 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5736.2423 | 5736.2423 | 5736.2423 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond #3 |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 4260 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 189.548 | 724.626 | 14216.1018 | 2705.2932 | 17538.0807 | 0 | 0 | 100% | 0% | 0% | 100% | 17538.0807 | 0 | 0 | 17538.0807 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5846.0269 | 5846.0269 | 5846.0269 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 459 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 100 | 500 | 7500 | 12500 | 20500 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 20500 | 0 | 0 | 20500 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 468 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 2731.2-P | 258 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 64.5 | 806.25 | 4837.5 | 8062.5 | 13706.25 | 0.01 | 2.58 | 100% | 0% | 100% | 0% | 13706.25 | 0 | 13706.25 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6853.125 | 6853.125 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 2731-VP-005 | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 456 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 2731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 465 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - TREATED EFFLUENT TANK | 2731-TK-002 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type B Construction 2BC-MRY1416 | Added | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 462 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 2731-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 463 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 2731-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 464 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 2731-SC-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 457 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 458 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 467 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 2731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 460 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 461 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 470 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 31.25 | 109.375 | 2343.75 | 3906.25 | 6359.375 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 6359.375 | 0 | 0 | 6359.375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3179.6875 | 3179.6875 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 477 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 471 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.097 | 101.2126 | 607.2755 | 1012.1258 | 1720.6139 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1720.6139 | 0 | 0 | 1720.6139 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 860.3069 | 860.3069 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 473 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 474 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 475 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 476 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 472 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 2732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 480 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to effluent pond and ocean discharge | 2734.1-P | 2595 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 648.75 | 8109.375 | 48656.25 | 81093.75 | 137859.375 | 0.01 | 25.95 | 100% | 0% | 100% | 0% | 137859.375 | 0 | 137859.375 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 45953.125 | 45953.125 | 45953.125 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Sewage System |  | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the Milne Port treated effluent line |  | 750 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 187.5 | 2343.75 | 14062.5 | 23437.5 | 39843.75 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 39843.75 | 0 | 39843.75 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13281.25 | 13281.25 | 13281.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Sewage System |  | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the fuel manifold and piping line |  | 750 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 187.5 | 2343.75 | 14062.5 | 23437.5 | 39843.75 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 39843.75 | 0 | 39843.75 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13281.25 | 13281.25 | 13281.25 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 479 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to effluent pond and ocean discharge | 2734.1-E | 1330 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 498 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV - Electrical distribution system from power gen to e-house | 2750.2-E | 6100 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 610 | 7625 | 45750 | 76250 | 129625 | 0.01 | 61 | 100% | 0% | 0% | 100% | 129625 | 0 | 0 | 129625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 43208.3333 | 43208.3333 | 43208.3333 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 2750.3-E | 5000 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 500 | 6250 | 37500 | 62500 | 106250 | 0.01 | 50 | 100% | 0% | 0% | 100% | 106250 | 0 | 0 | 106250 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 35416.6667 | 35416.6667 | 35416.6667 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 483 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 486 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | e-house |  | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 492 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 495 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-005 | 2.3234 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0.52083 | 6.5104 | 39.0625 | 65.1042 | 110.6771 | 1 | 2.3234 | 100% | 0% | 0% | 100% | 110.6771 | 0 | 0 | 110.6771 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 55.3385 | 55.3385 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 496 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 497 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 487 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 488 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 490 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 491 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 493 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 494 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 484 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 485 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | Genset modules |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43933.3333 | 0 | 43933.3333 | 0 | 0 | 0 | 0 | 43933.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | Genset modules |  | -4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -672 | -7400 | -50400 | -74000 | -131800 | 56 | -224 | 100% | 0% | 0% | 100% | -131800 | 0 | 0 | -131800 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -43933.3333 | 0 | -43933.3333 | 0 | 0 | 0 | 0 | -43933.3333
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road
3000 | Tote Road | 3100 | General
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 3111-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 507 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 3111-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 510 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 3 - Demolish Building - ISO Shipping Container | 3111-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 513 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 4 - Demolish Building - ISO Shipping Container | 3111-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 505 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 506 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 508 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 509 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 511 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 3 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 512 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 514 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 4 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 515 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km88 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km80 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km69 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km49 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km40 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km26 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km7 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 517 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 5 - Demolish Building - ISO Shipping Container | 3112-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 520 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 6 - Demolish Building - ISO Shipping Container | 3112-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 523 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 7 - Demolish Building - ISO Shipping Container | 3112-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 526 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 8 - Demolish Building - ISO Shipping Container | 3112-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 518 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 5 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 519 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 5 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 521 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 6 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 522 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 6 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 524 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 7 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 525 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 7 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 527 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 8 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 528 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 8 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 530 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 9 - Demolish Building - ISO Shipping Container | 3113-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 533 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 10 - Demolish Building - ISO Shipping Container | 3113-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 536 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 11 - Demolish Building - ISO Shipping Container | 3113-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 531 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 9 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 532 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 9 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 534 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 10 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 535 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 10 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 537 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 11 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 538 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 11 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3114 | Communications Facility No. 4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 102 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source |  | 41795 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 530.5809 | 6112.5187 | 39793.5668 | 16573.6127 | 62479.6982 | 0 | 0 | 100% | 0% | 0% | 100% | 62479.6982 | 0 | 0 | 62479.6982 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [7 empty] | 0 |  | 62479.6982 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2017) |  | 1000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 12.6948 | 146.25 | 952.1131 | 396.5453 | 1494.9084 | 0 | 0 | 100% | 0% | 0% | 100% | 1494.9084 | 0 | 0 | 1494.9084 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 100% | [7 empty] | 0 |  | 1494.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2018) |  | 1500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 19.0423 | 219.375 | 1428.1696 | 594.818 | 2242.3627 | 0 | 0 | 100% | 0% | 0% | 100% | 2242.3627 | 0 | 0 | 2242.3627 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 100% | [7 empty] | 0 |  | 2242.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 97/98 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at P1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P1 Borrow Source |  | 75820 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 962.5229 | 11088.675 | 72189.2148 | 30066.0681 | 113343.9579 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 113343.9579 | 0 | 113343.9579 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 56671.9789 | 56671.9789 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive magazine pads along Tote Road |  | 760 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 9.6481 | 111.15 | 723.606 | 301.3745 | 1136.1304 | 0 | 0 | 100% | 0% | 0% | 100% | 1136.1304 | 0 | 0 | 1136.1304 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 378.7101 | 378.7101 | 378.7101 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R3 (2017 Carry Over) |  | 25800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 327.5269 | 3773.25 | 24564.5178 | 10230.8699 | 38530.2449 | 0 | 0 | 100% | 0% | 0% | 100% | 38530.2449 | 0 | 0 | 38530.2449 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12843.415 | 12843.415 | 12843.415 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R1 (2017 Carry Over) |  | 20200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 256.4358 | 2954.25 | 19232.6845 | 8010.216 | 30167.091 | 0 | 0 | 100% | 0% | 0% | 100% | 30167.091 | 0 | 0 | 30167.091 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10055.697 | 10055.697 | 10055.697 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R2 (2017 Carry Over) |  | 20000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 253.8968 | 2925 | 19042.2619 | 7930.9069 | 29868.4069 | 0 | 0 | 100% | 0% | 0% | 100% | 29868.4069 | 0 | 0 | 29868.4069 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9956.1356 | 9956.1356 | 9956.1356 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2 - 2019 |  | 55800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 708.3721 | 8160.75 | 53127.9106 | 22127.2303 | 83332.8553 | 0 | 0 | 100% | 0% | 0% | 100% | 83332.8553 | 0 | 0 | 83332.8553 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 27777.6184 | 27777.6184 | 27777.6184 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 4 - 2019 |  | 66300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 841.668 | 9696.375 | 63125.0981 | 26290.9564 | 99013.7689 | 0 | 0 | 100% | 0% | 0% | 100% | 99013.7689 | 0 | 0 | 99013.7689 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 33004.5896 | 33004.5896 | 33004.5896 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 7 - 2019 |  | 28900 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 366.8809 | 4226.625 | 27516.0684 | 11460.1605 | 43159.848 | 0 | 0 | 100% | 0% | 0% | 100% | 43159.848 | 0 | 0 | 43159.848 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 14386.616 | 14386.616 | 14386.616 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 9 - 2019 |  | 92500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1174.2728 | 13528.125 | 88070.4612 | 36680.4445 | 138141.382 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 138141.382 | 0 | 138141.382 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46047.1273 | 46047.1273 | 46047.1273 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 10 - 2019 |  | 34500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 437.972 | 5045.625 | 32847.9017 | 13680.8144 | 51523.0019 | 0 | 0 | 100% | 0% | 0% | 100% | 51523.0019 | 0 | 0 | 51523.0019 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 17174.334 | 17174.334 | 17174.334 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 13 - 2019 |  | 7000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 88.8639 | 1023.75 | 6664.7917 | 2775.8174 | 10453.9424 | 0 | 0 | 100% | 0% | 0% | 100% | 10453.9424 | 0 | 0 | 10453.9424 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3484.6475 | 3484.6475 | 3484.6475 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown at km 61 |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8960.5221 | 0 | 0 | 100% | 0% | 0% | 100% | 8960.5221 | 0 | 0 | 8960.5221 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2986.8407 | 2986.8407 | 2986.8407 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 88 IT Tower Pad |  | 6400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 81.247 | 936 | 6093.5238 | 2537.8902 | 9557.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 9557.8902 | 0 | 0 | 9557.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3185.9634 | 3185.9634 | 3185.9634 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 80 IT Tower Pad |  | 6400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 81.247 | 936 | 6093.5238 | 2537.8902 | 9557.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 9557.8902 | 0 | 0 | 9557.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3185.9634 | 3185.9634 | 3185.9634 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 69 IT Tower Pad |  | 5100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 64.7437 | 745.875 | 4855.7768 | 2022.3813 | 7616.4438 | 0 | 0 | 100% | 0% | 0% | 100% | 7616.4438 | 0 | 0 | 7616.4438 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2538.8146 | 2538.8146 | 2538.8146 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 49 IT Tower Pad |  | 5600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 71.0911 | 819 | 5331.8333 | 2220.6539 | 8363.1539 | 0 | 0 | 100% | 0% | 0% | 100% | 8363.1539 | 0 | 0 | 8363.1539 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2787.718 | 2787.718 | 2787.718 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 40 IT Tower Pad |  | 2600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 33.0066 | 380.25 | 2475.494 | 1031.0179 | 3882.8929 | 0 | 0 | 100% | 0% | 0% | 100% | 3882.8929 | 0 | 0 | 3882.8929 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1294.2976 | 1294.2976 | 1294.2976 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 26 IT Tower Pad |  | 4000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 50.7794 | 585 | 3808.4524 | 1586.1814 | 5973.6814 | 0 | 0 | 100% | 0% | 0% | 100% | 5973.6814 | 0 | 0 | 5973.6814 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1991.2271 | 1991.2271 | 1991.2271 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 07 IT Tower Pad |  | 3800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 48.2404 | 555.75 | 3618.0298 | 1506.8723 | 5674.9973 | 0 | 0 | 100% | 0% | 0% | 100% | 5674.9973 | 0 | 0 | 5674.9973 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1891.6658 | 1891.6658 | 1891.6658 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3136 | Mary River |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 13040 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.5407 | 1907.1 | 12415.5547 | 5170.9513 | 19493.6061 | 0 | 0 | 100% | 0% | 0% | 100% | 19493.6061 | 0 | 0 | 19493.6061 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6497.8687 | 6497.8687 | 6497.8687 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Q13 Quarry (marginal increase to existing) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 25000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 317.371 | 3656.25 | 23802.8273 | 9913.6336 | 37335.5086 | 0 | 0 | 100% | 0% | 0% | 100% | 37335.5086 | 0 | 0 | 37335.5086 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 18667.7543 | 18667.7543 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P10 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P10 Borrow Source |  | 19344 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 245.569 | 2829.06 | 18417.6757 | 7670.7732 | 28888.7232 | 0 | 0 | 100% | 0% | 0% | 100% | 28888.7232 | 0 | 0 | 28888.7232 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 14444.3616 | 14444.3616 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P13 Borrow Source |  | 8456 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 107.3476 | 1236.69 | 8051.0683 | 3353.1874 | 12628.3624 | 0 | 0 | 100% | 0% | 0% | 100% | 12628.3624 | 0 | 0 | 12628.3624 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6314.1812 | 6314.1812 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P14 Borrow Source |  | 3160 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 40.1157 | 462.15 | 3008.6774 | 1253.0833 | 4719.2083 | 0 | 0 | 100% | 0% | 0% | 100% | 4719.2083 | 0 | 0 | 4719.2083 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2359.6041 | 2359.6041 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P15 Borrow Source |  | 3300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 41.893 | 482.625 | 3141.9732 | 1308.5996 | 4928.2871 | 0 | 0 | 100% | 0% | 0% | 100% | 4928.2871 | 0 | 0 | 4928.2871 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2464.1436 | 2464.1436 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Removal of Quarry and Borrow No Longer being Developed (Q9, Q14, Q15, P5, P6, P7, P8, P10, P13, P14, and P15) |  | -102131 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -1296.5368 | -14936.6587 | -97240.2624 | -40499.5727 | -152524.5133 | 0 | 0 | 100% | 0% | 0% | 100% | -152524.5133 | 0 | 0 | -152524.5133 | Type A 2AM-MRY1325 | Removed | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -76262.2567 | -76262.2567 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P5 Borrow Source |  | 4600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 58.3963 | 672.75 | 4379.7202 | 1824.1086 | 6869.7336 | 0 | 0 | 100% | 0% | 0% | 100% | 6869.7336 | 0 | 0 | 6869.7336 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3434.8668 | 3434.8668 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P6 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P6 Borrow Source |  | 7500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 95.2113 | 1096.875 | 7140.8482 | 2974.0901 | 11200.6526 | 0 | 0 | 100% | 0% | 0% | 100% | 11200.6526 | 0 | 0 | 11200.6526 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 5600.3263 | 5600.3263 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P7 Borrow Source |  | 8100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 102.8282 | 1184.625 | 7712.1161 | 3212.0173 | 12096.7048 | 0 | 0 | 100% | 0% | 0% | 100% | 12096.7048 | 0 | 0 | 12096.7048 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6048.3524 | 6048.3524 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P8 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P8 Borrow Source |  | 8385 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 106.4462 | 1226.3062 | 7983.4683 | 3325.0327 | 12522.3296 | 0 | 0 | 100% | 0% | 0% | 100% | 12522.3296 | 0 | 0 | 12522.3296 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6261.1648 | 6261.1648 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry |  | 64200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 815.0088 | 9389.25 | 61125.6606 | 25458.2112 | 95973.1218 | 0 | 0 | 100% | 0% | 0% | 100% | 95973.1218 | 0 | 0 | 95973.1218 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 47986.5609 | 47986.5609 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2019) |  | 226000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2869.0341 | 33052.5 | 215177.5592 | 89619.2481 | 337849.3073 | 0 | 0 | 100% | 0% | 0% | 100% | 337849.3073 | 0 | 0 | 337849.3073 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 168924.6537 | 168924.6537 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | 8969.4506 | 0 | 0 | 8969.4506 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4484.7253 | 4484.7253 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 634.7421 | 7312.5 | 47605.6547 | 19827.2673 | 74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | 74745.422 | 0 | 0 | 74745.422 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 37372.711 | 37372.711 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing in remainder 2017 - total now reflects area in QMP) |  | 824500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 10466.8966 | 120583.125 | 785017.2458 | 326951.6376 | 1232552.0084 | 0 | 0 | 100% | 0% | 0% | 100% | 1232552.0084 | 0 | 0 | 1232552.0084 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 616276.0042 | 616276.0042 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q11 Quarry |  | 50433 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 640.2389 | 7375.8262 | 48017.9197 | 19998.9714 | 75392.7173 | 0 | 0 | 100% | 0% | 0% | 100% | 75392.7173 | 0 | 0 | 75392.7173 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 37696.3587 | 37696.3587 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q18 Quarry |  | 2000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 25.3897 | 292.5 | 1904.2262 | 793.0907 | 2989.8169 | 0 | 0 | 100% | 0% | 0% | 100% | 2989.8169 | 0 | 0 | 2989.8169 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1494.9084 | 1494.9084 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 6350 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 80.6122 | 928.6875 | 6045.9181 | 2518.0629 | 9483.2192 | 0 | 0 | 100% | 0% | 0% | 100% | 9483.2192 | 0 | 0 | 9483.2192 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4741.6096 | 4741.6096 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q14 Quarry |  | 13440 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 170.6187 | 1965.6 | 12796.4 | 5329.5694 | 20071.5694 | 0 | 0 | 100% | 0% | 0% | 100% | 20071.5694 | 0 | 0 | 20071.5694 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 10035.7847 | 10035.7847 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q15 Quarry |  | 10680 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 135.5809 | 1561.95 | 10168.5678 | 4235.1043 | 15949.7293 | 0 | 0 | 100% | 0% | 0% | 100% | 15949.7293 | 0 | 0 | 15949.7293 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 7974.8646 | 7974.8646 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q16A |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q16A Quarry |  | 11240 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 142.69 | 1643.85 | 10701.7512 | 4457.1697 | 16786.0447 | 0 | 0 | 100% | 0% | 0% | 100% | 16786.0447 | 0 | 0 | 16786.0447 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8393.0223 | 8393.0223 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q19 Quarry |  | 18760 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 238.1552 | 2743.65 | 17861.6416 | 7439.1907 | 28044.4823 | 0 | 0 | 100% | 0% | 0% | 100% | 28044.4823 | 0 | 0 | 28044.4823 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 14022.2412 | 14022.2412 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q9 Quarry |  | 15166 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 192.53 | 2218.0275 | 14439.7472 | 6014.0067 | 22649.213 | 0 | 0 | 100% | 0% | 0% | 100% | 22649.213 | 0 | 0 | 22649.213 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 11324.6065 | 11324.6065 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ2a quarry |  | 345500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 4386.0677 | 50529.375 | 328955.0739 | 137006.417 | 516490.8659 | 0 | 0 | 100% | 0% | 0% | 100% | 516490.8659 | 0 | 0 | 516490.8659 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 258245.4329 | 258245.4329 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ4a quarry |  | 105000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1332.9583 | 15356.25 | 99971.8748 | 41637.2613 | 156965.3862 | 0 | 0 | 100% | 0% | 0% | 100% | 156965.3862 | 0 | 0 | 156965.3862 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 78482.6931 | 78482.6931 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ6a quarry |  | 194000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2462.7992 | 28372.5 | 184709.9402 | 76929.7971 | 290012.2373 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 290012.2373 | 0 | 290012.2373 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 145006.1186 | 145006.1186 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ12a quarry |  | 232200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2947.7421 | 33959.25 | 221080.6604 | 92077.8293 | 347117.7397 | 0 | 0 | 100% | 0% | 0% | 100% | 347117.7397 | 0 | 0 | 347117.7397 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 173558.8698 | 173558.8698 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry Expansion 2019 |  | 1225587 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 15558.6324 | 179242.0987 | 1166897.4302 | 486000.8207 | 1832140.3497 | 0 | 0 | 100% | 0% | 0% | 100% | 1832140.3497 | 0 | 0 | 1832140.3497 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 916070.1748 | 916070.1748 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry |  | 15000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 190.4226 | 2193.75 | 14281.6964 | 5948.1802 | 22423.6266 | 0 | 0 | 100% | 0% | 0% | 100% | 22423.6266 | 0 | 0 | 22423.6266 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 11211.8133 | 11211.8133 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q7 Quarry |  | 53050 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 673.4613 | 7758.5625 | 50509.5996 | 21036.7306 | 79304.8927 | 0 | 0 | 100% | 0% | 0% | 100% | 79304.8927 | 0 | 0 | 79304.8927 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 39652.4464 | 39652.4464 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Borrow development areas |  | 42080 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 534.1989 | 6154.2 | 40064.919 | 16686.6282 | 62905.7471 | 0 | 0 | 100% | 0% | 0% | 100% | 62905.7471 | 0 | 0 | 62905.7471 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20968.5824 | 20968.5824 | 20968.5824 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3132 | River Crossing at STA 17 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 0% | 100% | 0% | 100% | 0 | 161904.7619 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3133 | River Crossing at STA 62 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3134 | River Crossing at STA 80 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3135 | River Crossing at STA 97 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu-m | Culvert Removal per metre | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 2019 Quarries (4 x 20m) |  | 80 | Ea | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 27.824 | 173.9 | 2086.8 | 1739 | 3999.7 | 0 | 0 | 100% | 0% | 0% | 100% | 3999.7 | 0 | 0 | 3999.7 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 1999.85 | 1999.85 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 372 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 2232 | 13950 | 167400 | 139500 | 320850 | 0 | 0 | 100% | 0% | 0% | 100% | 320850 | 0 | 0 | 320850 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 160425 | 160425 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - Crown |  | 11 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 66 | 412.5 | 4950 | 4125 | 9487.5 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 9487.5 | 0 | 9487.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 4743.75 | 4743.75 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mobile Maintenance Depot - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 682 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 382.2042 | 1337.7146 | 28665.3125 | 47775.5208 | 77778.5479 | 1 | 682 | 0% | 100% | 0% | 100% | 0 | 77778.5479 | 0 | 77778.5479 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25926.1826 | 25926.1826 | 25926.1826 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Mobile Maintenance Depot - Demolish floor finish - Slab on grade C/W Drainage |  | 682 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 85.25 | 1278.75 | 6393.75 | 12787.5 | 20460 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 20460 | 0 | 20460 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6820 | 6820 | 6820 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Mobile Maintenance Depot -Liner Removal |  | 682 | m2 | 0.0318 | 0.02385 | 2.385 | 0.2385 | 2.6235 | 21.6876 | 16.2657 | 1626.57 | 162.657 | 1789.227 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 1789.227 | 0 | 1789.227 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 596.409 | 596.409 | 596.409 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Mobile Maintenance Depot - Demolish and foundations - Gravel Base - Skidded Building |  | 682 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Out-of-Service Tote Road |  | 266500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 3383.1752 | 38975.625 | 253738.1395 | 105679.3346 | 397996.5221 | 0 | 0 | 100% | 0% | 0% | 100% | 397996.5221 | 0 | 0 | 397996.5221 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 50% | 50% | [5 empty] | 0 |  | 0 | 198998.2611 | 198998.2611 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 17 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 62 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 80 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | TBD | Sea-can bridge at STA 97 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source |  | 157012 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 2989.8636 | 34444.5075 | 224239.7716 | 93393.5667 | 352077.8459 | 0 | 0 | 100% | 0% | 0% | 100% | 352077.8459 | 0 | 0 | 352077.8459 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 176038.9229 | 176038.9229 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 0 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2017) |  | 1000 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 19.0423 | 219.375 | 1428.1696 | 594.818 | 2242.3627 | 0 | 0 | 100% | 0% | 0% | 100% | 2242.3627 | 0 | 0 | 2242.3627 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1121.1813 | 1121.1813 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2018) |  | 1500 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 28.5634 | 329.0625 | 2142.2545 | 892.227 | 3363.544 | 0 | 0 | 100% | 0% | 0% | 100% | 3363.544 | 0 | 0 | 3363.544 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1681.772 | 1681.772 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT -EXCAVATOR - CAT M322D |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 105359 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 2006.2737 | 23113.1306 | 150470.5252 | 62669.4316 | 236017.9113 | 0 | 0 | 100% | 0% | 0% | 100% | 236017.9113 | 0 | 0 | 236017.9113 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 118008.9557 | 118008.9557 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  |  | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  | 697910.1311 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 8859.8583 | 102069.3567 | 664489.3741 | 276753.0143 | 1042273.1894 | 0 | 0 | 100% | 0% | 0% | 100% | 1042273.1894 | 0 | 0 | 1042273.1894 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 521136.5947 | 521136.5947 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 565 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 1 - Demolish Building - ISO Shipping Container | 3160-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 568 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 2 - Demolish Building - ISO Shipping Container | 3160-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 571 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 3 - Demolish Building - ISO Shipping Container | 3160-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 574 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 4 - Demolish Building - ISO Shipping Container | 3160-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 566 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 1 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-001 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 569 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 2 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-002 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 572 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 3 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-003 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 575 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 4 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-004 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 567 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 570 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 573 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 576 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings ( Not Contaminated) | Single Trailers (modular) |  | Washrooms at KM26 and KM 80 IT Towers |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (31m2 x 2) - Demolish and Decontaminate Building - Trailer |  | 62 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 34.7458 | 173.7292 | 2605.9375 | 4343.2292 | 7122.8958 | 1 | 62 | 100% | 0% | 0% | 100% | 7122.8958 | 0 | 0 | 7122.8958 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2374.2986 | 2374.2986 | 2374.2986 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (15m2 x 3) - Demolish and Decontaminate Building - Trailer |  | 45 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 25.2188 | 126.0938 | 1891.4062 | 3152.3438 | 5169.8438 | 1 | 45 | 100% | 0% | 0% | 100% | 5169.8438 | 0 | 0 | 5169.8438 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1723.2812 | 1723.2812 | 1723.2812 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (22m2) - Demolish and Decontaminate Building - Trailer |  | 22 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 12.3292 | 61.6458 | 924.6875 | 1541.1458 | 2527.4792 | 1 | 22 | 100% | 0% | 0% | 100% | 2527.4792 | 0 | 0 | 2527.4792 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 842.4931 | 842.4931 | 842.4931 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (12m2) - Demolish and Decontaminate Building - Trailer |  | 12 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 6.725 | 33.625 | 504.375 | 840.625 | 1378.625 | 1 | 12 | 100% | 0% | 0% | 100% | 1378.625 | 0 | 0 | 1378.625 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 459.5417 | 459.5417 | 459.5417 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site
4000 | Mine Site | 4100 | General
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 579 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 4110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 582 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 4110-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 580 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 581 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 583 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 584 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Site Development | 4136 | Tote Road |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 223 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2.8309 | 32.6137 | 212.3212 | 88.4296 | 333.3646 | 0 | 0 | 100% | 0% | 0% | 100% | 333.3646 | 0 | 0 | 333.3646 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 111.1215 | 111.1215 | 111.1215 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | -15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2A |  | 30150 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2B |  | 8700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 1 |  | 5400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Warehouse laydown pad expansion |  | 3200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 40.6235 | 468 | 3046.7619 | 1268.9451 | 4783.707 | 0 | 0 | 100% | 0% | 0% | 100% | 4783.707 | 0 | 0 | 4783.707 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1594.569 | 1594.569 | 1594.569 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction Laydown Area |  | 33576 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 426.242 | 4910.49 | 31968.1492 | 13314.4065 | 50193.0458 | 0 | 0 | 100% | 0% | 0% | 100% | 50193.0458 | 0 | 0 | 50193.0458 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 16731.0153 | 16731.0153 | 16731.0153 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of 800p camp laydown |  | 12000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 152.3381 | 1755 | 11425.3571 | 4758.5441 | 17938.9013 | 0 | 0 | 100% | 0% | 0% | 100% | 17938.9013 | 0 | 0 | 17938.9013 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5979.6338 | 5979.6338 | 5979.6338 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | WRF Water Treatment plant laydown 2019 |  | 3500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 44.4319 | 511.875 | 3332.3958 | 1387.9087 | 5232.1795 | 0 | 0 | 100% | 0% | 0% | 100% | 5232.1795 | 0 | 0 | 5232.1795 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1744.0598 | 1744.0598 | 1744.0598 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM107.5 Laydown for haul road parking |  | 91000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1155.2306 | 13308.75 | 86642.2915 | 36085.6265 | 136036.668 | 0 | 0 | 100% | 0% | 0% | 100% | 136036.668 | 0 | 0 | 136036.668 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 45345.556 | 45345.556 | 45345.556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM110.5 Laydown for Mine Ops |  | 180000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2285.0714 | 26325 | 171380.3569 | 71378.1622 | 269083.5191 | 0 | 0 | 100% | 0% | 0% | 100% | 269083.5191 | 0 | 0 | 269083.5191 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 89694.5064 | 89694.5064 | 89694.5064 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km107 Stockpile and access Road |  | 133400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1693.4918 | 19509.75 | 127011.8867 | 52899.1491 | 199420.7858 | 0 | 0 | 100% | 0% | 0% | 100% | 199420.7858 | 0 | 0 | 199420.7858 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 66473.5953 | 66473.5953 | 66473.5953 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 220.4703 | 2539.912 | 16535.2719 | 6886.7713 | 25961.9553 | 0 | 0 | 100% | 0% | 0% | 100% | 25961.9553 | 0 | 0 | 25961.9553 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8653.9851 | 8653.9851 | 8653.9851 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 220.4703 | 2539.912 | 16535.2719 | 6886.7713 | 25961.9553 | 0 | 0 | 100% | 0% | 0% | 100% | 25961.9553 | 0 | 0 | 25961.9553 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8653.9851 | 8653.9851 | 8653.9851 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development (Nuna services) |  | 11400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 144.7212 | 1667.25 | 10854.0893 | 4520.6169 | 17024.9919 | 0 | 0 | 100% | 0% | 0% | 100% | 17024.9919 | 0 | 0 | 17024.9919 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5674.9973 | 5674.9973 | 5674.9973 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Truck Shop (2018) laydown area |  | 25000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 317.371 | 3656.25 | 23802.8273 | 9913.6336 | 37335.5086 | 0 | 0 | 100% | 0% | 0% | 100% | 37335.5086 | 0 | 0 | 37335.5086 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12445.1695 | 12445.1695 | 12445.1695 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4135 | Explosives Pads | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Explosives Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional laydown next to Hatch old office/carpentry shack |  | 11250 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 142.817 | 1645.3125 | 10711.2723 | 4461.1351 | 16800.9789 | 0 | 0 | 100% | 0% | 0% | 100% | 16800.9789 | 0 | 0 | 16800.9789 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5600.3263 | 5600.3263 | 5600.3263 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher Pad Expansion |  | 25700 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 326.2574 | 3758.625 | 24469.3065 | 10191.2154 | 38380.9029 | 0 | 0 | 100% | 0% | 0% | 100% | 38380.9029 | 0 | 0 | 38380.9029 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12793.6343 | 12793.6343 | 12793.6343 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher extension Pad |  | 36180 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 459.2994 | 5291.325 | 34447.4517 | 14347.0106 | 54031.9481 | 0 | 0 | 100% | 0% | 0% | 100% | 54031.9481 | 0 | 0 | 54031.9481 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 18010.6494 | 18010.6494 | 18010.6494 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry |  | 258580 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 3282.6321 | 37817.325 | 246197.4038 | 102538.6955 | 386553.4243 | 0 | 0 | 100% | 0% | 0% | 100% | 386553.4243 | 0 | 0 | 386553.4243 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 193276.7121 | 193276.7121 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q2 Quarry |  | 109807 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1393.9824 | 16059.2737 | 104548.6825 | 43543.4548 | 164151.411 | 0 | 0 | 100% | 0% | 0% | 100% | 164151.411 | 0 | 0 | 164151.411 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 82075.7055 | 82075.7055 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q1 Quarry |  | 66978 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 850.2751 | 9795.5325 | 63770.6308 | 26559.8142 | 100125.9775 | 0 | 0 | 100% | 0% | 0% | 100% | 100125.9775 | 0 | 0 | 100125.9775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 50062.9887 | 50062.9887 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | 8969.4506 | 0 | 0 | 8969.4506 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4484.7253 | 4484.7253 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 33635.4399 | 33635.4399 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 634.7421 | 7312.5 | 47605.6547 | 19827.2673 | 74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | 74745.422 | 0 | 0 | 74745.422 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 37372.711 | 37372.711 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -76.169 | -877.5 | -5712.6786 | -2379.2721 | -8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | -8969.4506 | 0 | 0 | -8969.4506 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -4484.7253 | -4484.7253 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -634.7421 | -7312.5 | -47605.6547 | -19827.2673 | -74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | -74745.422 | 0 | 0 | -74745.422 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -37372.711 | -37372.711 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Informal Construction Laydown at Mary River |  |  | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Site Roads |  | 80899 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1027 | 11831.4787 | 77024.9972 | 32080.1219 | 120936.5978 | 0 | 0 | 100% | 0% | 0% | 100% | 120936.5978 | 0 | 0 | 120936.5978 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 40312.1993 | 40312.1993 | 40312.1993 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Waste Rock Road |  | 20000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 253.8968 | 2925 | 19042.2619 | 7930.9069 | 29898.1688 | 0 | 0 | 100% | 0% | 0% | 100% | 29898.1688 | 0 | 0 | 29898.1688 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9966.0563 | 9966.0563 | 9966.0563 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 1120 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 14.2182 | 163.8 | 1066.3667 | 444.1308 | 1672.6308 | 0 | 0 | 100% | 0% | 0% | 100% | 1672.6308 | 0 | 0 | 1672.6308 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 557.5436 | 557.5436 | 557.5436 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Haul Road Widening and Cross Cut |  | 55900 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 709.6416 | 8175.375 | 53223.1219 | 22166.8848 | 83482.1973 | 0 | 0 | 100% | 0% | 0% | 100% | 83482.1973 | 0 | 0 | 83482.1973 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 27827.3991 | 27827.3991 | 27827.3991 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal per metre | cu-m | Site Works | Culvert Removal per metre |  | Culverts for KM107 Stockpile (3 x 75m) |  | 225 | m | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 78.255 | 489.0938 | 5869.125 | 4890.9375 | 11249.1562 | 0 | 0 | 100% | 0% | 0% | 100% | 11249.1562 | 0 | 0 | 11249.1562 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3749.7188 | 3749.7188 | 3749.7188 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal per metre | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 800p camp discharge line (4 x 15m) |  | 60 | m | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 20.868 | 130.425 | 1565.1 | 1304.25 | 2999.775 | 0 | 0 | 100% | 0% | 0% | 100% | 2999.775 | 0 | 0 | 2999.775 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 999.925 | 999.925 | 999.925 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 14 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 84 | 525 | 6300 | 5250 | 12075 | 0 | 0 | 100% | 0% | 0% | 100% | 12075 | 0 | 0 | 12075 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4025 | 4025 | 4025 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 599 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-005 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 600 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-006 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 601 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-007 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 602 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 603 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-009 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 604 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-010 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 605 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - MINE SITE LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4141-MO-024 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 606 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 607 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 608 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 609 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 610 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-029 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 611 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 56800 kg | 4141-MO-030 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 612 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg | 4141-MO-031 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 613 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL size | MOBILE EQUIPMENT - SECONDARY DRILL - TAMROCK 800 | 4141-MO-033 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 614 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - DRILL DUST SUPPRESSION WATER/METHANOL TRUCK - KENWORTH T800H | 4141-MO-035 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Mine Haul Truck, 777 |  | 3 | Ea | 13 | 100 | 975 | 1000 | 2075 | 39 | 300 | 2925 | 3000 | 6225 | 96 | 288 | 100% | 0% | 0% | 100% | 6225 | 0 | 0 | 6225 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2075 | 0 | 2075 | 0 | 0 | 0 | 0 | 2075
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Mobile Light Plant |  | 5 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 50 | 187.5 | 3750 | 1875 | 5812.5 | 24 | 120 | 100% | 0% | 0% | 100% | 5812.5 | 0 | 0 | 5812.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1937.5 | 0 | 1937.5 | 0 | 0 | 0 | 0 | 1937.5
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light ERT utility vehicle |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -243.0556 | 0 | -243.0556 | 0 | 0 | 0 | 0 | -243.0556
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light ERT utility vehicle |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Off Road Tracked Rescue Vehicle |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Skid Steer, Cat 247B or 275D |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Portable water pump |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -486.1111 | 0 | -486.1111 | 0 | 0 | 0 | 0 | -486.1111
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Portable water pump |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Pickup truck (F350 or similar) |  | -7 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -46.6667 | -145.8333 | -3500 | -1458.3333 | -5104.1667 | 4 | -28 | 100% | 0% | 0% | 100% | -5104.1667 | 0 | 0 | -5104.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -1701.3889 | 0 | -1701.3889 | 0 | 0 | 0 | 0 | -1701.3889
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Pickup truck (F350 or similar) |  | 15 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 100 | 312.5 | 7500 | 3125 | 10937.5 | 4 | 60 | 100% | 0% | 0% | 100% | 10937.5 | 0 | 0 | 10937.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3645.8333 | 0 | 3645.8333 | 0 | 0 | 0 | 0 | 3645.8333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift z60 |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -486.1111 | 0 | -486.1111 | 0 | 0 | 0 | 0 | -486.1111
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift z60 |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 486.1111 | 0 | 486.1111 | 0 | 0 | 0 | 0 | 486.1111
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift s135x |  | -3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -20 | -62.5 | -1500 | -625 | -2187.5 | 4 | -12 | 100% | 0% | 0% | 100% | -2187.5 | 0 | 0 | -2187.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -729.1667 | 0 | -729.1667 | 0 | 0 | 0 | 0 | -729.1667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift s135x |  | 3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 20 | 62.5 | 1500 | 625 | 2187.5 | 4 | 12 | 100% | 0% | 0% | 100% | 2187.5 | 0 | 0 | 2187.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 729.1667 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 729.1667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Pick-Up Truck |  | 7 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 46.6667 | 145.8333 | 3500 | 1458.3333 | 5104.1667 | 4 | 28 | 100% | 0% | 0% | 100% | 5104.1667 | 0 | 0 | 5104.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1701.3889 | 0 | 1701.3889 | 0 | 0 | 0 | 0 | 1701.3889
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Truck Wash Facility |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Container Handler |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Gantry Crane |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Single Pass Production Drill |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Ore Haul Truck Workshop |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Boom Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Passenger Bus |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Track Dozer, D9 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Shovel 6030 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Integrated Tool Carrier, 938 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | FREIGHT HAUL TRACTOR , |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | WATER TRUCK |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | MAINTENANCE FUEL/LUBE TRUCK , |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Flat Deck Truck |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Mini-Crane |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | RESCUE UNIT |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | MECHANICS TRUCK, |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | SKELETON TRAILER, |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Pumper fire truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Pumper fire truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Mobile Primary Crusher Unit |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Excavator - cat 349 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 922K Wheel Loader |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 922K Wheel Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING WATER TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker and tractor |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793 Haul Truck |  | 3 | Ea | 13 | 100 | 975 | 1000 | 2075 | 39 | 300 | 2925 | 3000 | 6225 | 96 | 288 | 100% | 0% | 0% | 100% | 6225 | 0 | 0 | 6225 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2075 | 0 | 2075 | 0 | 0 | 0 | 0 | 2075
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -691.6667 | 0 | -691.6667 | 0 | 0 | 0 | 0 | -691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Ore Haul Truck |  | 8 | Ea | 13 | 100 | 975 | 1000 | 2075 | 104 | 800 | 7800 | 8000 | 16600 | 96 | 768 | 100% | 0% | 0% | 100% | 16600 | 0 | 0 | 16600 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5533.3333 | 0 | 5533.3333 | 0 | 0 | 0 | 0 | 5533.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | B-Train Trailer (for Ore Haul Truck) |  | 8 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 80 | 300 | 6000 | 3000 | 9300 | 24 | 192 | 100% | 0% | 0% | 100% | 9300 | 0 | 0 | 9300 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 3100 | 0 | 3100 | 0 | 0 | 0 | 0 | 3100
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 49 | Ea | 13 | 100 | 975 | 1000 | 2075 | 637 | 4900 | 47775 | 49000 | 101675 | 96 | 4704 | 100% | 0% | 0% | 100% | 101675 | 0 | 0 | 101675 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 33891.6667 | 0 | 33891.6667 | 0 | 0 | 0 | 0 | 33891.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 34 | Ea | 13 | 100 | 975 | 1000 | 2075 | 442 | 3400 | 33150 | 34000 | 70550 | 96 | 3264 | 100% | 0% | 0% | 100% | 70550 | 0 | 0 | 70550 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 23516.6667 | 0 | 23516.6667 | 0 | 0 | 0 | 0 | 23516.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 13 | Ea | 13 | 100 | 975 | 1000 | 2075 | 169 | 1300 | 12675 | 13000 | 26975 | 96 | 1248 | 100% | 0% | 0% | 100% | 26975 | 0 | 0 | 26975 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8991.6667 | 0 | 8991.6667 | 0 | 0 | 0 | 0 | 8991.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 3 | Ea | 13 | 100 | 975 | 1000 | 2075 | 39 | 300 | 2925 | 3000 | 6225 | 96 | 288 | 100% | 0% | 0% | 100% | 6225 | 0 | 0 | 6225 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2075 | 0 | 2075 | 0 | 0 | 0 | 0 | 2075
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick Up | Pick Up Truck |  | 6 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 40 | 125 | 3000 | 1250 | 4375 | 4 | 24 | 100% | 0% | 0% | 100% | 4375 | 0 | 0 | 4375 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1458.3333 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 1458.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Excavator |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Large Forklift |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Grader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Haul Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel/ Lube Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Telehandler |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Zoom Boom |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel/Lube Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Telehandler |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Telehandler |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Zoom Boom 12,000 lbs |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Zoom Boom 12,000 lbs |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Passenger Bus |  | 4 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 40 | 150 | 3000 | 1500 | 4650 | 24 | 96 | 100% | 0% | 0% | 100% | 4650 | 0 | 0 | 4650 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1550 | 0 | 1550 | 0 | 0 | 0 | 0 | 1550
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Boom Truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Boom Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -387.5 | 0 | -387.5 | 0 | 0 | 0 | 0 | -387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Passenger Bus |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Mechanics Truck (with compressor and crane) |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | 78 | Ea | 13 | 100 | 975 | 1000 | 2075 | 1014 | 7800 | 76050 | 78000 | 161850 | 96 | 7488 | 100% | 0% | 0% | 100% | 161850 | 0 | 0 | 161850 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 53950 | 0 | 53950 | 0 | 0 | 0 | 0 | 53950
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 3rd Party Heavy Mobile Equipment (make up for typical fleet) |  | -67 | Ea | 13 | 100 | 975 | 1000 | 2075 | -871 | -6700 | -65325 | -67000 | -139025 | 96 | -6432 | 100% | 0% | 0% | 100% | -139025 | 0 | 0 | -139025 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -46341.6667 | 0 | -46341.6667 | 0 | 0 | 0 | 0 | -46341.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | -33 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -330 | -1237.5 | -24750 | -12375 | -38362.5 | 24 | -792 | 100% | 0% | 0% | 100% | -38362.5 | 0 | 0 | -38362.5 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -12787.5 | 0 | -12787.5 | 0 | 0 | 0 | 0 | -12787.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | 61 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 610 | 2287.5 | 45750 | 22875 | 70912.5 | 24 | 1464 | 100% | 0% | 0% | 100% | 70912.5 | 0 | 0 | 70912.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 23637.5 | 0 | 23637.5 | 0 | 0 | 0 | 0 | 23637.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | 49 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 490 | 1837.5 | 36750 | 18375 | 56962.5 | 24 | 1176 | 100% | 0% | 0% | 100% | 56962.5 | 0 | 0 | 56962.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 18987.5 | 0 | 18987.5 | 0 | 0 | 0 | 0 | 18987.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | 128 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 1280 | 4800 | 96000 | 48000 | 148800 | 24 | 3072 | 100% | 0% | 0% | 100% | 148800 | 0 | 0 | 148800 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 49600 | 0 | 49600 | 0 | 0 | 0 | 0 | 49600
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 3rd Party Medium Mobile Equipment (make up for typical fleet) |  | -59 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -590 | -2212.5 | -44250 | -22125 | -68587.5 | 24 | -1416 | 100% | 0% | 0% | 100% | -68587.5 | 0 | 0 | -68587.5 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -22862.5 | 0 | -22862.5 | 0 | 0 | 0 | 0 | -22862.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | 41 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 273.3333 | 854.1667 | 20500 | 8541.6667 | 29895.8333 | 4 | 164 | 100% | 0% | 0% | 100% | 29895.8333 | 0 | 0 | 29895.8333 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 9965.2778 | 0 | 9965.2778 | 0 | 0 | 0 | 0 | 9965.2778
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | 34 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 226.6667 | 708.3333 | 17000 | 7083.3333 | 24791.6667 | 4 | 136 | 100% | 0% | 0% | 100% | 24791.6667 | 0 | 0 | 24791.6667 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8263.8889 | 0 | 8263.8889 | 0 | 0 | 0 | 0 | 8263.8889
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | 61 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 406.6667 | 1270.8333 | 30500 | 12708.3333 | 44479.1667 | 4 | 244 | 100% | 0% | 0% | 100% | 44479.1667 | 0 | 0 | 44479.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 14826.3889 | 0 | 14826.3889 | 0 | 0 | 0 | 0 | 14826.3889
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | 188 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 1253.3333 | 3916.6667 | 94000 | 39166.6667 | 137083.3333 | 4 | 752 | 100% | 0% | 0% | 100% | 137083.3333 | 0 | 0 | 137083.3333 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 45694.4444 | 0 | 45694.4444 | 0 | 0 | 0 | 0 | 45694.4444
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 3rd Party Light Mobile Equipment (make up for typical fleet) |  | -171 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -1140 | -3562.5 | -85500 | -35625 | -124687.5 | 4 | -684 | 100% | 0% | 0% | 100% | -124687.5 | 0 | 0 | -124687.5 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -41562.5 | 0 | -41562.5 | 0 | 0 | 0 | 0 | -41562.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992 Loader |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2766.6667 | 0 | 2766.6667 | 0 | 0 | 0 | 0 | 2766.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 994 Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988 Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345 D Excavator |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PV-271 Drill |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 1 X D65 ATLAS COPCO DRILL S/N TMG185ED00269 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Cat 793 Mining Truck |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1383.3333 | 0 | 1383.3333 | 0 | 0 | 0 | 0 | 1383.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Western Star Ore Haul TRuck |  | 11 | Ea | 13 | 100 | 975 | 1000 | 2075 | 143 | 1100 | 10725 | 11000 | 22825 | 96 | 1056 | 100% | 0% | 0% | 100% | 22825 | 0 | 0 | 22825 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 7608.3333 | 0 | 7608.3333 | 0 | 0 | 0 | 0 | 7608.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793 Haul Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Mobile Primary Crusher Unit |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel/Lube Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - CAT 777 DUMP BOX |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - MINE SITE GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK DX780 |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK SDX800 |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | C 125 JAW CRUSHER |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | SANDVIK NEW QJ341 JAW CRUSHER S/N# QJ34100262 |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT SERVICE TRUCK 2014 | HTP014 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER VAC TRUCK | HTP018 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER M2 SERVICE TRUCK | HTP022 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950H SNOW REMOVAL LOADER | LDR018 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2014 MACK JET FUEL TRUCK | FLT003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | SUPER B FUEL TANKER LEAD UNIT | FLT004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRI AXLE FUEL TRAILER | FLT006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | SUPER B FUEL TRAILER PUP UNIT | FLT007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B FUEL/LUBE TRUCK | FLT010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FREIGHTLINER M2 FUEL TRUCK | FLT011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART013 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART014 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART015 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART016 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART017 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART018 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART019 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING ROCK TRUCK | ART020 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING WATER/SAND TRUCK | AWT001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740B ARTICULATING WATER TRUCK | AWT002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONTAINER HANDLER | CNH001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TEREX RT780 CRANE | CRN002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TEREX RT130 CRANE | CRN003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MANITOWOC CRANE MODEL 2250 | CRN004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE SPYDER CRANE W706 | CRN006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | BOOM CRANE, CONMA, MTP016 | CRN008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TAMROCK RANDER 800-2 HYDRAULIC DRILL 200 | DRL003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MD6290 CAT ROTARY PRODUCTION DRILL | DRL004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MD6290 CAT ROTARY PRODUCTION DRILL | DRL007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | OSHKOSH FIRE TRUCK 1993 -T1500 MR | EMG002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390DL EXCAVATOR CATERPILLAR | EXC001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390DL EXCAVATOR CATERPILLAR | EXC002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 345DL EXCAVATOR CATERPILLAR | EXC006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | M320F EXCAVATOR CATERPILLAR RUBBER TIRE | EXC009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 16H CATERPILLAR GRADER | GRD001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 16M CATERPILLAR GRADER | GRD002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER | GRD003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER W/WING | GRD004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER | GRD005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M CATERPILLAR GRADER W/WING | GRD006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992K WHEEL LOADER | LDR001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 988H WHEEL LOADER | LDR011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR013 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR014 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 930K WHEEL LOADER | LDR015 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | IT14 LOADER NFLD HARDROCK | LDR019 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 906 CATERPILLAR LOADER | LDR020 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | VOLVO L-180 LOADER - W/TIRE MANIPULATOR | LDR021 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777G MINE HAUL TRUCK | MHT004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT013 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT014 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT015 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT016 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT017 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT018 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT019 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT020 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT021 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT022 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT023 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT024 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT025 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT026 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT027 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT028 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT029 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT030 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT031 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT032 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT033 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT034 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT035 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT036 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT037 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT038 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR ORE HAUL TRUCK | OHT039 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1001 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1002 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1003 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1004 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1008 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1013 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1014 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1015 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1016 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1017 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1018 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1019 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1020 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1021 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1022 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1023 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1024 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1025 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1026 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1027 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1028 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1029 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1030 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1031 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1032 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1033 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1034 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1035 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1036 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1037 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1038 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE HAUL LEAD TRAILER | OHT1039 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | LOADER VOLVO-L-180E C/W TIRE HANDLER & 3 CRATES IN CAB |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | HP 400RD PLANT CRUSHER S/N MC-0401/MC2015102 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | FORD F650 SERVICE TRUCK VIN# 3FDNF65H13MB00286 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | ORE TRAILER OFF-ROAD MINE MODEL HDT4-38-23 S/N 712379 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK + 10 SPARE TIRES STRAPPED ON TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK (2 PALLETS STRAPPED ON TRUCK) |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK (OHT031) |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2005 WESTERN STAR VIN# 1XKCPBEX85R980272 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2015 CAT 14M GRADER YELLOW VIN# 8814WKR9J88448 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2012 CAT 14M GRADER YELLOW |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WINCH TRUCK |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRAILER DUMP TRUCK TRIAXLE S/N# 2ATE060336A003392 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WETSERN STAR TRUCK VIN: 5KJRASD19GPHD7171 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD14GPHD7174 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD12GPHD7173 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 2016 WESTERN STAR TRUCK VIN: 5KJRASD10GPHD7172 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 824H CATERPILLAR RUBBER TIRED DOZER | DZR011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D9T CATERPILLAR DOZER | DZR012 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | FLT005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT ROAD MAINTENANCE 2013 | HTP005 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | STERLING BOOM TRUCK W/ MANITEX CRANE | HTP006 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | STERLING BOOM TRUCK W/ MANITEX CRANE | HTP007 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT 367 TRACTOR 2017 | HTP009 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | KENWORTH TOW TRUCK | HTP010 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT TRACTOR 2014 | HTP011 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | PETERBILT TRACTOR 2014 | HTP013 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL PLOW TRUCK | HTP016 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | INTERNATIONAL BOOM TRUCK KNUCKLE | HTP019 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR 4900 2014 (NFLD HARD ROCK) | HTP024 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR 4900 2014 (NFLD HARD ROCK) | HTP025 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP029 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP032 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | WESTERN STAR TRACTOR | HTP033 | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | TRACTOR FRTL CABOVER UNIT 512109 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | BRODERSON 16 80 CRANE |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 691.6667 | 0 | 691.6667 | 0 | 0 | 0 | 0 | 691.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK + BOX PLASTIC FITTINGS |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 570.1389 | 0 | 570.1389 | 0 | 0 | 0 | 0 | 570.1389
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX780 SANDVIK ROCK DRILL | DRL005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | DX800 SANDVIK ROCK DRILL | DRL006 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2013 K/W FUEL LUBE TRUCK | FLT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2014K/W FUEL LUBE TRUCK | FLT002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2006 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2007 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2008 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2009 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2010 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2011 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2012 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2013 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2014 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2015 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2016 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2017 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2018 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2019 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2020 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2021 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2022 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2023 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2024 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2025 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2026 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2027 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2028 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2029 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2030 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2031 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2032 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2033 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2034 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2035 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2036 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2037 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2038 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL PUP TRAILER | OHT2039 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SMITHCO SIDE DUMP TRAILER MODEL HDT 4-38-23, S/N 712377 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE SIDE DUMP TRAILER MODEL HDT4-38-23 S/N 712385 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE SIDE-DUMP TRAILER MODEL HDT4-38-23, S/N 712381 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712393 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712387 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712391 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712389 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712395 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2011 KENWORTH S/A MECHANICS SERVICE TRUCK VIN# 2NKHHM6X1BM284136 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL # 712397 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712405 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712378 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712388 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712382 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712392 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712390 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712380 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712398 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL# 712394 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712384 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712402 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712400 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712396 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERAIL #712406 * damaged by stevedores during receiving (hydraulic fittings in front of trailer) |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712404 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL #712386 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | END DUMP TRAILER | EDT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HIBOY TRAILER | HBT004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SCONA TRIDEM HI BOY TRAILER | HBT005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FLOAT TRAILER MINI DECK SCHELTENA MD1 | LBT003-01 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F750 DE-ICEING TRUCK BBS-97 | MTP001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 24 PASSENGER BUS | BUS003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 PASSENGER BUS | BUS005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MANUAL JIB CRANE MOBILE MAINTENANCE SHOP | CRN007 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D6T CATERPILLAR DOZER | DZR005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D5M CATERPILLAR DOZER | DZR009 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D4C CATERPILLAR DOZER LPGIII | DZR010 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TRI AXLE WATER TRUCK | HTP004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PETERBILT ROLL OFF TRUCK | HTP015 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | JLG MAN LIFT | JLG007 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GENIE BOOM LIFT ZOOM BOOM Z60/34 | JLG008 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | KUBOTA TRACTOR B7800 | KUB004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | LOWBOY TRAILER DELOUPE | LBT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | LOWBOY TRAILER DELOUPE | LBT002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CS74 SMOOTH ROLLER | RLR002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH002 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH003 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TH514 | TLH004 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TELEHANDLER CAT TL642 | TLH005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | TRAILER LIVE BOTTOM | WBT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | PC09-1 EXCAVATOR KOMATSU MINI | EXC008 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 53' POWER TRAILER |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 FLAT DECK PICK-UP WHITE VIN# 1FDOW5HTOFED33588 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | STEP-DECK TRAILER 3 AXLES UNIT # 533F650 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | GMC PICK UP 4WD + TOOL/JOB BOX VIN# 1GTHK39D17E173219 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | UTILITY TRAILERS STACKED 2 HIGH |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | ORE HAUL TRAILER (FRONT) SERIAL # 712383 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712399 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITHCO SIDE-DUMP TRAILER, SERIAL # 712401 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2015 SMITH SIDE-DUMP TRAILER, SERIAL # 712403 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2007 FREIGHTLINER M2 4X4 VIN# 1FVDCXDC47HX81790 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | SANDVIK QA441 SCREENER S/N # QA44100342 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | V SNOW PLOW VIN# 9900-2564 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 2006 TRAILER TRIAXLE GREY VIN# LA90735316A003393 * RECEIVED WITH DAMAGE TO HYDROLIC OIL SUPPLY FITTING* |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORKLIFT CATERPILLAR P20000 | FKT001 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | FORKLIFT CATERPILLAR P10000 | FKT005 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 SERVICE TRUCK FOUNTAIN TIRE | MTP011 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 SERVICE TRUCK | MTP013 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F650 SERVICE TRUCK 2003 | MTP015 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F-550 SERVICE TRUCK FOUNTAIN TIRE | MTP016 | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 387.5 | 0 | 387.5 | 0 | 0 | 0 | 0 | 387.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT011 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT012 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT013 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT014 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT015 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT016 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT017 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT018 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT019 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT020 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT021 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT022 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT023 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT024 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT025 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT026 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT027 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT028 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT029 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TEREX LIGHT TOWER | ALT030 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT035 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT036 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT037 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT038 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT040 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | INGERSOLL RAND LIGHT TOWER | ALT041 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 AMBULANCE | EMG003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F450 AMBULANCE | EMG004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Decommissioned vehicles |  | -3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -20 | -62.5 | -1500 | -625 | -2187.5 | 4 | -12 | 100% | 0% | 0% | 100% | -2187.5 | 0 | 0 | -2187.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -729.1667 | 0 | -729.1667 | 0 | 0 | 0 | 0 | -729.1667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HAGGLUNDS SNOW RESCUE VEHICLE | EMG007 | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -243.0556 | 0 | -243.0556 | 0 | 0 | 0 | 0 | -243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HAGGLUNDS SNOW RESCUE VEHICLE | EMG007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FORKLIFT/MANLIFT CROWN WAV50-118 | FKT010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLAMELESS SPARKLESS HEATER | FSH004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GROUND SURFACE HEATER | GTH001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENIE MANLIFT / Z45/25J (BURNED) | JLG004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GENIE MANLIFT / Z45/25J | JLG005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | JLG MANLIFT 450AJ | JLG010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | FLOAT TRAILER SCHELTENA | LBT003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2013 | LTP004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP011 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP013 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP014 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP016 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP017 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP020 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP021 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP024 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP025 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP027 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP029 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP030 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TOYOTA 4X4 PICK-UP LAND CRUISER | LTP031 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2008 | LTP033 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TOYOTA 4X4 PICK UP LAND CRUISER | LTP034 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2011 | LTP038 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP040 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2013 | LTP043 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP044 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP045 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP046 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP047 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP056 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP057 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 SD CREW CAB 4X4 2014 | LTP058 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP059 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 SD CREW CAB 4X4 2014 | LTP060 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 CREW CAB 4X4 2010- LEVITT SAFETY | LTP063 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 3500 GMC CREW CAB 4X4 2006 | LTP067 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | GMC 2500 MOBILE STAIR TRUCK | MST001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 DECK TRUCK | MTP004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 WELDING TRUCK | MTP005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 CUBE VAN | MTP008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 (BLASTERS) | MTP009 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2013 | MTP010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2014 | MTP012 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F550 SD CREW CAB 4X4 2015 | MTP014 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PULL- TYPE PNEUMATIC ROLLER | PTR001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PULL-TYPE PNEUMATIC TIRE ROLLER | PTR002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VAC TANK UNIT | PVT001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VACUUM TANK c/w PUMP | PVT002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE VAC TANK UNIT | PVT003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP 6" | PWP001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP | PWP002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP 4" | PWP003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | PORTABLE WATR PUMP - CAT-PAC | PWP004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 277 MULTI TERRAIN | SKD005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 299D | SKD008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 247B | SKD010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER CATERPILLAR 262D Rubber Tire | SKD012 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 03 | SKJ003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SCISSOR LIFT 10 | SKJ010 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TUNDRA SKIDOO | SNM003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIK WT 600 | SNM004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIK WT 600 | SNM005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIC ACE 600 SNOWMOBILE | SNM006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKANDIC ACE 600 SNOWMOBILE | SNM007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE CAN AM COMMANDER 800XT | SXS001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT | SXS007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SIDE BY SIDE BOBCAT TRACKED | SXS008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TIRE MANIPULATOR | TMN001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | TRAILER ENCLOSED SNOWMOBILE | TRL001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | BOAT TRAILER | TRL002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD001 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER MILLER AIR PAK | WLD002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD004 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD007 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | WELDER LINCOLN 300D | WLD008 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | STERLING SPILL RESPONSE UNIT 2002 | EMG005 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | STERLING SPILL RESPONSE UNIT 2002 | EMG006 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | CARGO LUGGAGE HANDLER | CNH003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL002 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SNOW BLOWER VOHL DV4000 | SBL003 | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 243.0556 | 0 | 243.0556 | 0 | 0 | 0 | 0 | 243.0556
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Piling Rig |  | 3 | Ea | 13 | 100 | 975 | 1000 | 2075 | 39 | 300 | 2925 | 3000 | 6225 | 96 | 288 | 100% | 0% | 0% | 100% | 6225 | 0 | 0 | 6225 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2075 | 0 | 2075 | 0 | 0 | 0 | 0 | 2075
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | Light Vehicles | 4142-MO-033 | 30 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 200 | 625 | 15000 | 6250 | 21875 | 4 | 120 | 100% | 0% | 0% | 100% | 21875 | 0 | 0 | 21875 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 7291.6667 | 0 | 7291.6667 | 0 | 0 | 0 | 0 | 7291.6667
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Dozer |  | 12 | Ea | 13 | 100 | 975 | 1000 | 2075 | 156 | 1200 | 11700 | 12000 | 24900 | 96 | 1152 | 100% | 0% | 0% | 100% | 24900 | 0 | 0 | 24900 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8300 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Front End Loader |  | 12 | Ea | 13 | 100 | 975 | 1000 | 2075 | 156 | 1200 | 11700 | 12000 | 24900 | 96 | 1152 | 100% | 0% | 0% | 100% | 24900 | 0 | 0 | 24900 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8300 | 0 | 8300 | 0 | 0 | 0 | 0 | 8300
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Excavators |  | 15 | Ea | 13 | 100 | 975 | 1000 | 2075 | 195 | 1500 | 14625 | 15000 | 31125 | 96 | 1440 | 100% | 0% | 0% | 100% | 31125 | 0 | 0 | 31125 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10375 | 0 | 10375 | 0 | 0 | 0 | 0 | 10375
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | Misc. Support Mobile Equipment (assume medium sized) |  | 40 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 400 | 1500 | 30000 | 15000 | 46500 | 24 | 960 | 100% | 0% | 0% | 100% | 46500 | 0 | 0 | 46500 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 15500 | 0 | 15500 | 0 | 0 | 0 | 0 | 15500
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Haul Truck (40- and 50- ton) |  | 50 | Ea | 13 | 100 | 975 | 1000 | 2075 | 650 | 5000 | 48750 | 50000 | 103750 | 96 | 4800 | 100% | 0% | 0% | 100% | 103750 | 0 | 0 | 103750 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 34583.3333 | 0 | 34583.3333 | 0 | 0 | 0 | 0 | 34583.3333
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | 2017 Sea Lift 3rd Party Equipment in addition to addendum numbers |  | 117 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 1170 | 4387.5 | 87750 | 43875 | 136012.5 | 24 | 2808 | 100% | 0% | 0% | 100% | 136012.5 | 0 | 0 | 136012.5 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 45337.5 | 0 | 45337.5 | 0 | 0 | 0 | 0 | 45337.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | 2017 Sea Lift 3rd Party Equipment in addition to addendum numbers |  | 34 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 226.6667 | 708.3333 | 17000 | 7083.3333 | 24791.6667 | 4 | 136 | 100% | 0% | 0% | 100% | 24791.6667 | 0 | 0 | 24791.6667 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 8263.8889 | 0 | 8263.8889 | 0 | 0 | 0 | 0 | 8263.8889
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | 2017 - 3rd party contractor equipment from 2017 addendum not mobilized |  | -30 | Ea | 13 | 100 | 975 | 1000 | 2075 | -390 | -3000 | -29250 | -30000 | -62250 | 96 | -2880 | 100% | 0% | 0% | 100% | -62250 | 0 | 0 | -62250 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -20750 | 0 | -20750 | 0 | 0 | 0 | 0 | -20750
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5587.5 | 0 | 5587.5 | 0 | 0 | 0 | 0 | 5587.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -85.45 | -941.25 | -6408.75 | -9412.5 | -16762.5 | 30 | -60 | 100% | 0% | 0% | 100% | -16762.5 | 0 | 0 | -16762.5 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -5587.5 | 0 | -5587.5 | 0 | 0 | 0 | 0 | -5587.5
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2793.75 | 0 | 2793.75 | 0 | 0 | 0 | 0 | 2793.75
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -2793.75 | 0 | -2793.75 | 0 | 0 | 0 | 0 | -2793.75
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 31 | 325 | 2325 | 3250 | 5900 | 20 | 40 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -2950 | -2950 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | -1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -15.5 | -162.5 | -1162.5 | -1625 | -2950 | 20 | -20 | 100% | 0% | 0% | 100% | -2950 | 0 | 0 | -2950 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | -1475 | -1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 693 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - FORD F550 | 4143-MO-001 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 694 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - PETERBILT 348 | 4143-MO-002 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 695 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 4143-MO-003 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 696 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-004 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 697 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-005 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 698 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Tire Handler | MOBILE EQUIPMENT - TIRE HANDLER - WBM T20P-S 5900 kg | 4143-MO-006 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 699 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FREIGHT HANDLING FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 4143-MO-008 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 700 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - YARD WORK EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 4143-MO-009 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 701 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-010 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 702 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 703 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - CRUSHER MAINTENANCE KNUCKLE CRANE - KENWORTH T800 | 4143-MO-013 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 704 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT780 L: 14630, W: 7920, H: 3990, 42000 kg | 4143-MO-014 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 705 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT130 L: 15240, W: 7920, H: 3970, 60500 kg | 4143-MO-015 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 706 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - WAREHOUSE FORK LIFT - CAT P7000-D L: 2790, W: 1290, H: 2500, 4763 kg | 4143-MO-016 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 707 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - MAINTENANCE FORK LIFT - CAT P20000 L: 4240, W: 2390, H: 2845, 14320 kg | 4143-MO-017 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 708 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 4143-MO-018 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 709 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-019 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 710 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-020 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 711 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-021 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 712 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-022 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 713 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-023 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 714 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - YARD MAINTENANCE PLOW/SAND TRUCK - INTERNATIONAL 7600 | 4143-MO-024 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 715 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg | 4143-MO-025 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 716 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - YARD/TOTE ROAD MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 4143-MO-026 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 717 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 4143-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 718 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG450AJ L: 2500, W: 1170, H: 1970, 6010 kg | 4143-MO-029 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 719 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 4143-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 720 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - ORE HAUL TRUCK RECOVERY TOW TRUCK - KENWORTH T800 | 4143-MO-031 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD CULVERT MAINTENANCE STEAM TRUCK - PETERBILT T/A STEAM TRUCK | 4143-MO-032 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 722 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 723 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 724 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 725 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 726 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 727 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FB20PNT L: 3050, W: 1090, H: 2050, 3500 kg | 4143-MO-038 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW706 | 4143-MO-039 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 729 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 4143-MO-040 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - FLAT DECK TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - LARGE MOBILE LIGHT PLANT - TEREX L: 4623, W: 2007, H: 9000, 925 kg |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - PETERBILT |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 616 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-001A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 617 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 618 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 619 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-002A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 620 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 621 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 622 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-003A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 623 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 624 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 625 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-004A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 626 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 627 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 628 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-005A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 629 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 630 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 631 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-006A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 632 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 633 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 634 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-007A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 635 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 636 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 637 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-008A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 638 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 639 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 640 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-009A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 641 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 642 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 643 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-010A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 644 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 645 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 646 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-011A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 647 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 648 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 649 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-012A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 650 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 651 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 652 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-013A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 653 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 654 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 655 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-014A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 656 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 657 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 658 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-015A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 659 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 660 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 661 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-016A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 662 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 663 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 664 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-017A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 665 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 666 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 667 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-018A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 668 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 669 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 670 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-019A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 671 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 672 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 673 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-020A |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 674 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020B |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 675 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020C |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 676 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 42700 kg | 4142-MO-021 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 677 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg | 4142-MO-022 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 678 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H L: 8716, W: 3556, H: 4102, 46300 kg | 4142-MO-023 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 679 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16H L: 9963, W: 3096, H: 3718, 30400 kg | 4142-MO-024 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 680 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg | 4142-MO-026 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 681 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4142-MO-027 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 682 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 683 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-029 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 684 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 685 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-031 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 686 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-032 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 687 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 688 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 689 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 690 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 691 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHING FRONT END LOADER - CAT 988H, L: 10390, W: 3600, H: 4115, 43400 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - ORE HAUL TRUCK FRONT END LOADER - CAT 988H L: 3277, W: 1676, H: 3810, 3175 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT -TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 731 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 4144-MO-001 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 732 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 4144-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 733 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-003 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 734 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-004 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 735 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 4144-MO-005 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 736 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-006 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 737 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - FREIGHT DELIVERY HIBOY TRAILER L: 14630 W: 2438 | 4144-MO-007 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 738 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - DIESEL FUEL TRAILER TRACTOR - WESTERN STAR 4900FA | 4144-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 739 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - JET-A1 FUEL DELIVERY TRUCK - MACK/INNOCAR GU813 L: 8052, W: 2960, H: 3589 | 4144-MO-009 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 740 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - TREMCAR TC406 SUPER B-TRAIN L: 24384, W: 2590, H: 4013, 33500 kg | 4144-MO-010 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 741 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - MOBILE EQUIPMENT LOWBOY TRAILER - SHELTEMA L: 7620, W: 4572 | 4144-MO-011 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 742 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 4144-MO-012 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 743 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-013 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 744 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-014 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 745 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-015 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 746 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-016 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 747 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-017 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 748 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-018 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 749 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Cat 740 | MOBILE EQUIPMENT - ARTICULATED WATER/SAND TRUCK - CAT 740 | 4144-MO-024 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 750 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - ADVANCE | 4144-MO-025 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 751 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 752 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 753 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-031 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 754 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-032 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 755 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 756 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 757 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 758 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 759 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 760 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-040 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 761 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-041 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 762 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-042 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 763 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-043 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 764 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-044 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 765 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-045 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - COACH PASSENGER TRANSFER BUS |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - FREIGHTLINER |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - INTERNATIONAL |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Trailer | MOBILE EQUIPMENT - Live Bottom Trailer |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Ford Truck | MOBILE EQUIPMENT - MAINTENANCE LUBE TRUCK - Ford |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage vacuum truck | MOBILE EQUIPMENT - SEWAGE VACUUM TRUCK - FREIGHTLINER |  |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT (5400 GAL) |  |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 777 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single | 4213-BLD-001 | 33.4572 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 18.75 | 93.75 | 1406.25 | 2343.75 | 3843.75 | 1 | 33.4572 | 100% | 0% | 0% | 100% | 3843.75 | 0 | 0 | 3843.75 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1281.25 | 1281.25 | 1281.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 778 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Magazines - Demolish and foundations - Gravel Base - Skidded Building | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 779 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Magazines - Demolish floor finish - Raised Steel or Wooden Floor | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 769 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4211-BLD-001 | 342.0074 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 191.6667 | 958.3333 | 14375 | 23958.3333 | 39291.6667 | 1 | 342.0074 | 100% | 0% | 0% | 100% | 39291.6667 | 0 | 0 | 39291.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13097.2222 | 13097.2222 | 13097.2222 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 770 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Plant Building - Demolish and foundations - Gravel Base - Skidded Building | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 771 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Plant Building - Demolish floor finish - Raised Steel or Wooden Floor | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4212-BLD-001 | 371.7472 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 208.3333 | 729.1667 | 15625 | 26041.6667 | 42395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 42395.8333 | 0 | 0 | 42395.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 14131.9444 | 14131.9444 | 14131.9444 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 130 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 72.8542 | 254.9896 | 5464.0625 | 9106.7708 | 14825.8229 | 1 | 130 | 100% | 0% | 0% | 100% | 14825.8229 | 0 | 0 | 14825.8229 | Type A 2AM-MRY1325 |  | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4941.941 | 4941.941 | 4941.941 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 775 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Explosives Shop - Demolish floor finish - Slab on grade C/W Drainage | 4212-BLD-001 | 371.7472 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 46.4684 | 697.026 | 3485.1301 | 6970.2602 | 11152.4164 | 0 | 0 | 100% | 0% | 0% | 100% | 11152.4164 | 0 | 0 | 11152.4164 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3717.4721 | 3717.4721 | 3717.4721 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 774 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Shop - Demolish and foundations - Gravel Base - Skidded Building | 4212-BLD-001 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Explosives Facility | 4222 | Explosive pad haul road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive pad haul road |  | 19600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 248.8189 | 2866.5 | 18661.4166 | 7772.2888 | 29300.2054 | 0 | 0 | 100% | 0% | 0% | 100% | 29300.2054 | 0 | 0 | 29300.2054 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9766.7351 | 9766.7351 | 9766.7351 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Haul Roads | 4221 | Pit 1 Haul Road | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Dump |  | 190000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2412.0198 | 27787.5 | 180901.4878 | 75343.6157 | 190000 | 0 | 0 | 100% | 0% | 0% | 100% | 190000 | 0 | 0 | 190000 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 63333.3333 | 63333.3333 | 63333.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Facility - Footprint expansion |  | 130000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1650.3294 | 19012.5 | 123774.7022 | 51550.895 | 194338.0971 | 0 | 0 | 100% | 0% | 0% | 100% | 194338.0971 | 0 | 0 | 194338.0971 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 64779.3657 | 64779.3657 | 64779.3657 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Geotube Settling Pond |  | 3000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 133.4845 | 510.3 | 10011.3393 | 1905.136 | 12426.7753 | 0 | 0 | 100% | 0% | 0% | 100% | 12426.7753 | 0 | 0 | 12426.7753 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4142.2584 | 4142.2584 | 4142.2584 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 19000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 845.402 | 3231.9 | 63405.1488 | 12065.8616 | 78702.9104 | 0 | 0 | 100% | 0% | 0% | 100% | 78702.9104 | 0 | 0 | 78702.9104 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 26234.3035 | 26234.3035 | 26234.3035 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 6000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 266.969 | 1020.6 | 20022.6786 | 3810.2721 | 24853.5506 | 0 | 0 | 100% | 0% | 0% | 100% | 24853.5506 | 0 | 0 | 24853.5506 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8284.5169 | 8284.5169 | 8284.5169 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2008 Bulk Sample Pit |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 2008 bulk sample PWSP |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 |  | 55000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 698.2163 | 8043.75 | 52366.2202 | 21809.994 | 82219.9642 | 0 | 0 | 100% | 0% | 0% | 100% | 82219.9642 | 0 | 0 | 82219.9642 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 41109.9821 | 41109.9821 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 - Marginal increase |  | 214450 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2722.4087 | 31363.3125 | 204180.653 | 85039.1494 | 320263.9932 | 0 | 0 | 100% | 0% | 0% | 100% | 320263.9932 | 0 | 0 | 320263.9932 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 160131.9966 | 160131.9966 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New PWSP 2019 |  | 4180 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 185.9884 | 711.018 | 13949.1327 | 2654.4895 | 17208.727 | 0 | 0 | 100% | 0% | 0% | 100% | 17208.727 | 0 | 0 | 17208.727 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 17208.727 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 6967 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 309.9956 | 1185.0867 | 23249.6669 | 4424.3609 | 28682.584 | 0 | 0 | 100% | 0% | 0% | 100% | 28682.584 | 0 | 0 | 28682.584 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 28682.584 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-3 | 6511 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 289.7059 | 1107.5211 | 21727.9434 | 4134.7802 | 26805.2684 | 0 | 0 | 100% | 0% | 0% | 100% | 26805.2684 | 0 | 0 | 26805.2684 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 26805.2684 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 3720 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 165.5208 | 632.772 | 12414.0607 | 2362.3687 | 15314.9437 | 0 | 0 | 100% | 0% | 0% | 100% | 15314.9437 | 0 | 0 | 15314.9437 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 15314.9437 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 789 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 708.3333 | 708.3333 | 708.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 786 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Pit Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4281-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 60 | 750 | 4500 | 7500 | 12750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 787 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 790 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Pit Office Washcar - Demolish and foundations - Gravel Base - Skidded Building | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 791 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 788 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Lunchroom Building - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Lunchroom Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-002 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Lunchroom Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-001 | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-002 | 54 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 12.105 | 151.3125 | 907.875 | 1513.125 | 2572.3125 | 1 | 54 | 100% | 0% | 0% | 100% | 2572.3125 | 0 | 0 | 2572.3125 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 857.4375 | 857.4375 | 857.4375 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-003 | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-004 | 25 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 5.6042 | 70.0521 | 420.3125 | 700.5208 | 1190.8854 | 1 | 25 | 100% | 0% | 0% | 100% | 1190.8854 | 0 | 0 | 1190.8854 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 396.9618 | 396.9618 | 396.9618 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Crusher Pad Expansion 2019 |  | 12000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 152.3381 | 1755 | 11425.3571 | 4758.5441 | 17938.9013 | 0 | 0 | 100% | 0% | 0% | 100% | 17938.9013 | 0 | 0 | 17938.9013 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5979.6338 | 5979.6338 | 5979.6338 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Ore crushing and Loading Pad, Utility & Accommodation Pads |  | 121021 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1536.3424 | 17699.3212 | 115225.6787 | 47990.3143 | 180915.3143 | 0 | 0 | 100% | 0% | 0% | 100% | 180915.3143 | 0 | 0 | 180915.3143 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 60305.1048 | 60305.1048 | 60305.1048 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiles |  | 5100.23 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 64.7466 | 745.9086 | 4855.9958 | 2022.4725 | 7624.3769 | 0 | 0 | 100% | 0% | 0% | 100% | 7624.3769 | 0 | 0 | 7624.3769 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2541.459 | 2541.459 | 2541.459 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 795 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-001 | 39.4052 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 22.0833 | 110.4167 | 1656.25 | 2760.4167 | 4527.0833 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 4527.0833 | 0 | 0 | 4527.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1509.0278 | 1509.0278 | 1509.0278 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 798 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-002 | 39.4052 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 22.0833 | 110.4167 | 1656.25 | 2760.4167 | 4527.0833 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 4527.0833 | 0 | 0 | 4527.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1509.0278 | 1509.0278 | 1509.0278 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 801 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 1 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-001 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 802 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-003 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 803 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-005 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 804 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 2 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-006 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 805 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-008 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 806 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-010 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 815 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 1 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-002 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 816 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 1 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-004 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 817 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 2 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-007 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 818 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 2 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-009 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 796 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 797 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 799 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 800 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 807 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-011 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 808 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-012 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 809 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-013 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 810 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-014 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 811 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-015 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 812 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-016 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 813 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-017 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 814 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-018 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Chain Conveyor | Chain Conveyor (1 for under jaw crusher, 1 for under crusher bin) |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Conveyors |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43933.3333 | 0 | 43933.3333 | 0 | 0 | 0 | 0 | 43933.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Electrical sub station |  | 3 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 504 | 5550 | 37800 | 55500 | 98850 | 56 | 168 | 100% | 0% | 0% | 100% | 98850 | 0 | 0 | 98850 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 32950 | 0 | 32950 | 0 | 0 | 0 | 0 | 32950
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Genset Trailers |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Screener |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Concrete Batch Plant |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Hydraulic Rock Crusher - Tramac |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Used conveyors |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43933.3333 | 0 | 43933.3333 | 0 | 0 | 0 | 0 | 43933.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Grizzly unit 11-0702 |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw Crusher 11-0701 |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screener Unit 10-0701 |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Inclined Screen |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Cone Crusher |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen Metso FS353 |  | -1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -168 | -1850 | -12600 | -18500 | -32950 | 56 | -56 | 100% | 0% | 0% | 100% | -32950 | 0 | 0 | -32950 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -10983.3333 | 0 | -10983.3333 | 0 | 0 | 0 | 0 | -10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen Metso FS353 |  | 2 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 336 | 3700 | 25200 | 37000 | 65900 | 56 | 112 | 100% | 0% | 0% | 100% | 65900 | 0 | 0 | 65900 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 21966.6667 | 0 | 21966.6667 | 0 | 0 | 0 | 0 | 21966.6667
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | 3rd Party Equipment | Screener Power Screener |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 3 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | PRIMARY SCREENING PLANT LINE 3 - METSO FS303 |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREENING PLANT LINE 3 - METSO FS 353 L: 3000, W: 6900, 14500 kg |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600 |  | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Jaw Plant | Spread A, Primary Jaw Plant | MR-PRO-CRU-010-PJP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Primary Jaw Plant | Spread B, Primary Jaw Plant | MR-PRO-CRU-020-PJP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Jaw Plant | Spread C, Primary Jaw Plant | MR-PRO-CRU-030-PJP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Secondary Cone Feed | Spread A, Secondary Cone Feed | MR-PRO-CRU-010-PCF01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Screen Plant Discharge | Spread A, Primary Screen Plant Discharge | MR-PRO-CRU-010-PSD01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Primary Screen Plant | Spread A, Primary Screen Plant | MR-PRO-CRU-010-PSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Secondary Cone Plant | Spread A, Secondary Cone Plant | MR-PRO-CRU-010-SCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Tertiary Cone Plant | Spread A, Tertiary Cone Plant | MR-PRO-CRU-010-TCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread A, Twin Screen Plant | Spread A, Twin Screen Plant | MR-PRO-CRU-010-TSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Secondary Cone Feed | Spread B, Secondary Cone Feed | MR-PRO-CRU-020-PCF01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Primary Screen Plant | Spread B, Primary Screen Plant | MR-PRO-CRU-020-PSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Secondary Cone Plant | Spread B, Secondary Cone Plant | MR-PRO-CRU-020-SCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Tertiary Cone Plant | Spread B, Tertiary Cone Plant | MR-PRO-CRU-020-TCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread B, Twin Screen Plant | Spread B, Twin Screen Plant | MR-PRO-CRU-020-TSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Secondary Cone Feed | Spread C, Secondary Cone Feed | MR-PRO-CRU-030-PCF01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Screen Plant Discharge | Spread C, Primary Screen Plant Discharge | MR-PRO-CRU-030-PSD01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Primary Screen Plant | Spread C, Primary Screen Plant | MR-PRO-CRU-030-PSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Secondary Cone Plant | Spread C, Secondary Cone Plant | MR-PRO-CRU-030-SCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | ADR | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Tertiary Cone Plant | Spread C, Tertiary Cone Plant | MR-PRO-CRU-030-TCP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Spread C, Twin Screen Plant | Spread C, Twin Screen Plant | MR-PRO-CRU-030-TSP01 | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | AIM | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Control Room | Spread A, Control Room | MR-PRO-CRU-010-COR01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Fine Discharge | Spread A, Fine Discharge | MR-PRO-CRU-010-FID01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread A, Lumps Discharge | Spread A, Lumps Discharge | MR-PRO-CRU-010-LUD01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | AIM | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Control Room | Spread B, Control Room | MR-PRO-CRU-020-COR01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Fine Discharge | Spread B, Fine Discharge | MR-PRO-CRU-020-FID01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Lumps Discharge | Spread B, Lumps Discharge | MR-PRO-CRU-020-LUD01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread B, Primary Screen Plant Discharge | Spread B, Primary Screen Plant Discharge | MR-PRO-CRU-020-PSD01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread C, Fine Discharge | Spread C, Fine Discharge | MR-PRO-CRU-030-FID01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | COB | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Spread C, Lumps Discharge | Spread C, Lumps Discharge | MR-PRO-CRU-030-LUD01 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Drill | Quarry Drills |  | 10 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 192 | 1775 | 14400 | 17750 | 33925 | 1 | 10 | 100% | 0% | 0% | 100% | 33925 | 0 | 0 | 33925 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 16962.5 | 16962.5 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | Mobile Crusher/Screener |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 43933.3333 | 0 | 43933.3333 | 0 | 0 | 0 | 0 | 43933.3333
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 828 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Stockpile Drain Pipe - Piping Installation - Ore stockpile to effluent pond and Mary River | 4385.1-P | 5220 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 1305 | 16312.5 | 97875 | 163125 | 277312.5 | 0.01 | 52.2 | 100% | 0% | 100% | 0% | 277312.5 | 0 | 277312.5 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 92437.5 | 92437.5 | 92437.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Mine Haul Road Sedimentation Pond |  | 10000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 444.9484 | 1701 | 33371.1309 | 6350.4535 | 41422.5844 | 0 | 0 | 100% | 0% | 0% | 100% | 41422.5844 | 0 | 0 | 41422.5844 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13807.5281 | 13807.5281 | 13807.5281 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | KM107 Sedimentation Pond |  | 7400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 329.2618 | 1258.74 | 24694.6369 | 4699.3356 | 30652.7125 | 0 | 0 | 100% | 0% | 0% | 100% | 30652.7125 | 0 | 0 | 30652.7125 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10217.5708 | 10217.5708 | 10217.5708 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Crusher Pad Sedimentation Pond 2019 |  | 2000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 88.9897 | 340.2 | 6674.2262 | 1270.0907 | 8284.5169 | 0 | 0 | 100% | 0% | 0% | 100% | 8284.5169 | 0 | 0 | 8284.5169 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2761.5056 | 2761.5056 | 2761.5056 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Crushing Sedimentation Pond |  | 6428.69 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 286.0435 | 1093.5202 | 21453.2656 | 4082.5097 | 26629.2954 | 0 | 0 | 100% | 0% | 0% | 100% | 26629.2954 | 0 | 0 | 26629.2954 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8876.4318 | 8876.4318 | 8876.4318 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 825 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 826 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 827 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Stockpile Drain Pipe - Heat Trace Installation - Ore stockpile to effluent pond and Mary River | 4385.1-E | 2610 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 820 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4382-BLD-001 | 334.5725 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 187.5 | 656.25 | 14062.5 | 23437.5 | 38156.25 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 38156.25 | 0 | 0 | 38156.25 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12718.75 | 12718.75 | 12718.75 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 821 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Weigh Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4382-BLD-001 | 334.5725 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 48.582 | 607.2755 | 3643.6529 | 6072.7548 | 10323.6832 | 0.75 | 250.9294 | 100% | 0% | 0% | 100% | 10323.6832 | 0 | 0 | 10323.6832 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3441.2277 | 3441.2277 | 3441.2277 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 823 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - TRUCK WEIGH SCALE - RICE LAKE OTR-XV L: 36600 W: 3960, H: 1030 | 4382-SC-001 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 822 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Weigh Building - Demolish floor finish - Gravel | 4382-BLD-001 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Truck Weigh Facility disturbed area |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [7 empty] | 0 |  | 19433.8097 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome
4000 | Mine Site | 4400 | Aerodrome | 4410 | Runway & Apron | 4410 | Runway & Apron | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Heli Pad |  | 5776 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 73.3254 | 844.74 | 5499.4052 | 2290.4459 | 8634.5911 | 0 | 0 | 100% | 0% | 0% | 100% | 8634.5911 | 0 | 0 | 8634.5911 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2878.197 | 2878.197 | 2878.197 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 839 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4431-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 833 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 4431-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 838 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4431-TK-001 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 834 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4431-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 836 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 4431-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 837 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4431-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 835 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 4431-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4436 | Airfield Lighting and Visual Aids | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4521-BLD-003 | 1296 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 726.3 | 2542.05 | 54472.5 | 90787.5 | 147802.05 | 1 | 1296 | 100% | 0% | 0% | 100% | 147802.05 | 0 | 0 | 147802.05 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 49267.35 | 49267.35 | 49267.35 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4521-BLD-003 | 1296 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 188.1874 | 2352.3423 | 14114.0538 | 23523.423 | 39989.8192 | 0.75 | 972 | 100% | 0% | 0% | 100% | 39989.8192 | 0 | 0 | 39989.8192 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 13329.9397 | 13329.9397 | 13329.9397 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4521-BLD-003 | 1296 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 162 | 2430 | 12150 | 24300 | 38880 | 0 | 0 | 100% | 0% | 0% | 100% | 38880 | 0 | 0 | 38880 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12960 | 12960 | 12960 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 850 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4435-BLD-001 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 851 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Field Electrical Centre - Demolish and foundations - Gravel Base - Skidded Building | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 852 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Field Electrical Centre - Demolish floor finish - Raised Steel or Wooden Floor | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 845 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | x-ray | AERODROME EQUIPMENT - SECURITY X-RAY MACHINE L: 2282, W: 1030, H: 1467 | 4433-AE-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 846 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT GROUND POWER UNIT | 4433-AE-015 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 847 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT PASSENGER STAIRS L: 9906, W: 2565, H: 3048 | 4433-AE-023 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4434 | Plant & Equipment | 848 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Bus sized | MOBILE EQUIPMENT - AIRPORT MAINTENANCE DE-ICING TRUCK - FORD SUPERIOR | 4434-MO-002 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4439 | Power Generation | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 899 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 902 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 905 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 908 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 911 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-005 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 914 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-006 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 917 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-007 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 900 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AA - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 901 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AA - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 903 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AB - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 904 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AB - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 906 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AC - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 907 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AC - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 909 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AD - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 910 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AD - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 912 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AE - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 913 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AE - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 915 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AF - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 916 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AF - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 918 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AG - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 919 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AG - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AH - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AH - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AI - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AI - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AI - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AJ - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AJ - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AJ - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AK - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AK - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AK - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AL - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-012 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AL - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AL - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AM - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-013 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AM - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AM - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – West side |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – East Side |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Quonset hut |  | 100 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 22.4167 | 280.2083 | 1681.25 | 2802.0833 | 4763.5417 | 1 | 100 | 100% | 0% | 0% | 100% | 4763.5417 | 0 | 0 | 4763.5417 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1587.8472 | 1587.8472 | 1587.8472 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC lunch |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC office |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Rail Operations offices |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (60 x 60) |  | 334 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 74.8717 | 935.8958 | 5615.375 | 9358.9583 | 15910.2292 | 1 | 334 | 100% | 0% | 0% | 100% | 15910.2292 | 0 | 0 | 15910.2292 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 5303.4097 | 5303.4097 | 5303.4097 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (24 x 60) |  | 132 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 29.59 | 369.875 | 2219.25 | 3698.75 | 6287.875 | 1 | 132 | 100% | 0% | 0% | 100% | 6287.875 | 0 | 0 | 6287.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2095.9583 | 2095.9583 | 2095.9583 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (12 x 60) |  | 66 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 14.795 | 184.9375 | 1109.625 | 1849.375 | 3143.9375 | 1 | 66 | 100% | 0% | 0% | 100% | 3143.9375 | 0 | 0 | 3143.9375 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1047.9792 | 1047.9792 | 1047.9792 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Lunchtrailer (44 x 10) |  | 40 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.9667 | 112.0833 | 672.5 | 1120.8333 | 1905.4167 | 1 | 40 | 100% | 0% | 0% | 100% | 1905.4167 | 0 | 0 | 1905.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 635.1389 | 635.1389 | 635.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container w lunchroom |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container Office |  | 144 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 32.28 | 403.5 | 2421 | 4035 | 6859.5 | 1 | 144 | 100% | 0% | 0% | 100% | 6859.5 | 0 | 0 | 6859.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2286.5 | 2286.5 | 2286.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Construction offices, lunchrooms, washcars (assume 50 units @ 36 m2 per wash car) |  | 1218 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 682.5875 | 3412.9375 | 51194.0625 | 85323.4375 | 139930.4375 | 1 | 1218 | 100% | 0% | 0% | 100% | 139930.4375 | 0 | 0 | 139930.4375 | Type B Construction 2BC-MRY1416 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 46643.4792 | 46643.4792 | 46643.4792 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 48.42 | 605.25 | 3631.5 | 6052.5 | 10289.25 | 1 | 216 | 100% | 0% | 0% | 100% | 10289.25 | 0 | 0 | 10289.25 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3429.75 | 3429.75 | 3429.75 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 50 person camp at Mine Site |  | 50 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 35040.0455 | 0 | 0 | 35040.0455 | 0 | 0 | 100% | 0% | 0% | 100% | 35040.0455 | 0 | 0 | 35040.0455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 35040.0455 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 50- Person Rapid Deploy Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 170.3667 | 2129.5833 | 12777.5 | 21295.8333 | 36202.9167 | 0.5 | 475 | 100% | 0% | 0% | 100% | 36202.9167 | 0 | 0 | 36202.9167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 36202.9167 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 35- Person 'Norse-man Style' Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 170.3667 | 2129.5833 | 12777.5 | 21295.8333 | 36202.9167 | 0.5 | 475 | 100% | 0% | 0% | 100% | 36202.9167 | 0 | 0 | 36202.9167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 36202.9167 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 800 person camp at Mine Site |  | 800 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 560640.7273 | 0 | 0 | 560640.7273 | 0 | 0 | 100% | 0% | 0% | 100% | 560640.7273 | 0 | 0 | 560640.7273 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [5 empty] | 0 |  | 0 | 0 | 560640.7273 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4510 | Accommodations Area | 857 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 4510-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 924 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 43.75 | 546.875 | 3281.25 | 5468.75 | 9296.875 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 9296.875 | 0 | 0 | 9296.875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3098.9583 | 3098.9583 | 3098.9583 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 925 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 4513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 40.485 | 506.0629 | 3036.3774 | 5060.629 | 8603.0693 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 8603.0693 | 0 | 0 | 8603.0693 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2867.6898 | 2867.6898 | 2867.6898 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 926 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 4513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 34.8513 | 522.7695 | 2613.8476 | 5227.6952 | 8364.3123 | 0 | 0 | 100% | 0% | 0% | 100% | 8364.3123 | 0 | 0 | 8364.3123 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2788.1041 | 2788.1041 | 2788.1041 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 937 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4513-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 921 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 20 | 250 | 1500 | 2500 | 4250 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4250 | 0 | 0 | 4250 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 939 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 4513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 938 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4513-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 922 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 11 | 87.5 | 525 | 875 | 1487.5 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1487.5 | 0 | 0 | 1487.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 495.8333 | 495.8333 | 495.8333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 930 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4513-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 931 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4513-MT-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 932 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 933 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 934 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 935 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 936 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 4513-SQ-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 923 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 4513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 927 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F450 L: 6680, W: 2438, H: 2024, 6350 kg | 4513-MO-001 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 928 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | large fire truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH TI3000 L: 10922 W: 2921, H: 3607, 39000 kg | 4513-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 929 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small tank | MOBILE EQUIPMENT - SNOW RESCUE VEHICLE - HAGGLUND BV206 L: 6900, W: 1870, H: 2400, 6580 kg | 4513-MO-003 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 859 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 1856.8773 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 416.25 | 5203.125 | 31218.75 | 52031.25 | 88453.125 | 1 | 1856.8773 | 100% | 0% | 0% | 100% | 88453.125 | 0 | 0 | 88453.125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 29484.375 | 29484.375 | 29484.375 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 862 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-002 | 607.8067 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 136.25 | 1703.125 | 10218.75 | 17031.25 | 28953.125 | 1 | 607.8067 | 100% | 0% | 0% | 100% | 28953.125 | 0 | 0 | 28953.125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9651.0417 | 9651.0417 | 9651.0417 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 865 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 95 | 1187.5 | 7125 | 11875 | 20187.5 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 20187.5 | 0 | 0 | 20187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 6729.1667 | 6729.1667 | 6729.1667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 868 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laboratory - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-004 | 312.2677 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 70 | 875 | 5250 | 8750 | 14875 | 1 | 312.2677 | 100% | 0% | 0% | 100% | 14875 | 0 | 0 | 14875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4958.3333 | 4958.3333 | 4958.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 871 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 872 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 873 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR DRYER | 4511-LE-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 874 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 875 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 876 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 877 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CARBON/SULFUR ANALYSER | 4511-LE-007 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 878 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CHILLER | 4511-LE-008 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 879 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER | 4511-LE-016 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 880 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER DUST HOOD | 4511-LE-017 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 881 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-018 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 882 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-019 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 883 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DUST COLLECTOR | 4511-LE-020 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 884 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUMEHOOD | 4511-LE-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 885 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUSION SYSTEM | 4511-LE-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 886 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - HOT PLATE | 4511-LE-023 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 887 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MUFFLE FURNACE | 4511-LE-024 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 888 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-027 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 889 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-028 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 890 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER DUST HOOD | 4511-LE-029 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 891 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP | 4511-LE-030 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 892 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP DUST HOOD | 4511-LE-031 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 893 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MAGNETITE ANALYSER | 4511-LE-032 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 894 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - SCRUBBER FAN | 4511-LE-033 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 895 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LABORATORY EQUIPMENT - SCRUBBER RECIRCULATION PUMP | 4511-LE-034 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 896 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - THERMOGRAVIMETRIC ANALYSER | 4511-LE-035 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 897 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - XRF SPECTROMETER | 4511-LE-036 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 869 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laboratory - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 870 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laboratory - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 866 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 867 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 863 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 864 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 860 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 861 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 4333 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 629.179 | 7864.737 | 47188.4222 | 78647.3704 | 133700.5296 | 0.75 | 3249.75 | 100% | 0% | 0% | 100% | 133700.5296 | 0 | 0 | 133700.5296 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 44566.8432 | 44566.8432 | 44566.8432 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Sailivik (800p) Camp Mine Dry |  | 1200 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 269 | 3362.5 | 20175 | 33625 | 57162.5 | 1 | 1200 | 100% | 0% | 0% | 100% | 57162.5 | 0 | 0 | 57162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 19054.1667 | 19054.1667 | 19054.1667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 13000 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 2914.1667 | 36427.0833 | 218562.5 | 364270.8333 | 619260.4167 | 1 | 13000 | 100% | 0% | 0% | 100% | 619260.4167 | 0 | 0 | 619260.4167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 206420.1389 | 206420.1389 | 206420.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 975 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4521-TK-053 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washroom facility for Tote Road |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-005 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 942 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-001 | 2416.3569 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1354.1667 | 4739.5833 | 101562.5 | 169270.8333 | 275572.9167 | 1 | 2416.3569 | 100% | 0% | 0% | 100% | 275572.9167 | 0 | 0 | 275572.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 91857.6389 | 91857.6389 | 91857.6389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 945 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-002 | 892.1933 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 500 | 1750 | 37500 | 62500 | 101750 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 101750 | 0 | 0 | 101750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 33916.6667 | 33916.6667 | 33916.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 943 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-001 | 2416.3569 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 350.8703 | 4385.8785 | 26315.2708 | 43858.7847 | 74559.9341 | 0.75 | 1812.2677 | 100% | 0% | 0% | 100% | 74559.9341 | 0 | 0 | 74559.9341 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24853.3114 | 24853.3114 | 24853.3114 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 944 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-001 | 2416.3569 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 302.0446 | 4530.6691 | 22653.3457 | 45306.6914 | 72490.7063 | 0 | 0 | 100% | 0% | 0% | 100% | 72490.7063 | 0 | 0 | 72490.7063 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24163.5688 | 24163.5688 | 24163.5688 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 948 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-003 | 390.3346 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 218.75 | 765.625 | 16406.25 | 27343.75 | 44515.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 44515.625 | 0 | 0 | 44515.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 14838.5417 | 14838.5417 | 14838.5417 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Crusher Dry Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Environment Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Lunchroom |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-004 | 267.658 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 150 | 750 | 11250 | 18750 | 30750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 30750 | 0 | 0 | 30750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10250 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 946 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-002 | 892.1933 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 129.5521 | 1619.4013 | 9716.4077 | 16194.0128 | 27529.8218 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 27529.8218 | 0 | 0 | 27529.8218 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9176.6073 | 9176.6073 | 9176.6073 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 947 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Warehouse - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-002 | 892.1933 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 111.5242 | 1672.8625 | 8364.3123 | 16728.6245 | 26765.7993 | 0 | 0 | 100% | 0% | 0% | 100% | 26765.7993 | 0 | 0 | 26765.7993 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 8921.9331 | 8921.9331 | 8921.9331 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 0 | Services Area |  | Waste Rock Facility |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Trasfer line for Deposit 1 to Waste Rock Facility |  | 3500 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 875 | 10937.5 | 65625 | 109375 | 185937.5 | 0.01 | 35 | 100% | 0% | 0% | 100% | 185937.5 | 0 | 0 | 185937.5 | Type A 2AM-MRY1325 | added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 61979.1667 | 61979.1667 | 61979.1667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 0 | Services Area |  | Bulk Fuel Storage |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Fuel Line from new (2019) bulk fuel storage facility to existing bulk fuel storage facility |  | 250 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 62.5 | 781.25 | 4687.5 | 7812.5 | 13281.25 | 0.01 | 2.5 | 100% | 0% | 0% | 100% | 13281.25 | 0 | 0 | 13281.25 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4427.0833 | 4427.0833 | 4427.0833 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 976 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 4521.5-P | 405 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 101.25 | 1265.625 | 7593.75 | 12656.25 | 21515.625 | 0.01 | 4.05 | 100% | 0% | 100% | 0% | 21515.625 | 0 | 21515.625 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7171.875 | 7171.875 | 7171.875 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 949 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-003 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 950 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-003 | 390.3346 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 48.7918 | 731.8773 | 3659.3866 | 7318.7732 | 11710.0372 | 0 | 0 | 100% | 0% | 0% | 100% | 11710.0372 | 0 | 0 | 11710.0372 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3903.3457 | 3903.3457 | 3903.3457 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 974 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 4521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 955 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-005 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 952 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-004 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 969 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4521-PP-051 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 971 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 4521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 972 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL TANK | 4521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 973 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WAREHOUSE BUILDING DIESEL TANK | 4521-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 956 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-005 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 957 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 958 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 959 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 960 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 961 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 962 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 963 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 964 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 965 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 966 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-021 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 967 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 968 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-022 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 970 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4521-MT-051 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 953 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-004 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant building |  | 780 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 437.125 | 1529.9375 | 32784.375 | 54640.625 | 88954.9375 | 1 | 780 | 100% | 0% | 0% | 100% | 88954.9375 | 0 | 0 | 88954.9375 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 29651.6458 | 29651.6458 | 29651.6458 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mine Truck Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1148.8542 | 4020.9896 | 86164.0625 | 143606.7708 | 233791.8229 | 1 | 2050 | 100% | 0% | 0% | 100% | 233791.8229 | 0 | 0 | 233791.8229 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 77930.6076 | 77930.6076 | 77930.6076 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Rolling Stock Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1148.8542 | 4020.9896 | 86164.0625 | 143606.7708 | 233791.8229 | 1 | 2050 | 100% | 0% | 0% | 100% | 233791.8229 | 0 | 0 | 233791.8229 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 77930.6076 | 77930.6076 | 77930.6076 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-007 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-007 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-007 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Truck Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-008 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Truck Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-008 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Truck Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Maintenance Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-006 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Maintenance Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-006 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Maintenance Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-009 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-009 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER TANK - SIMER JET PUMPS 2205C L: 1803, W: 1245, H: 1346 |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER PUMP - PLASTIC-MART L: 483, W: 275, H: 267 |  | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 91.0364 | 348.0246 | 6827.7334 | 1299.3028 | 8475.0608 | 0 | 0 | 100% | 0% | 0% | 100% | 8475.0608 | 0 | 0 | 8475.0608 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2825.0203 | 2825.0203 | 2825.0203 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 979 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - KIDNEY LOOP - AG - DYE10MFP240SA10QBV 50 kg | 4522-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 982 | MT- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | LATHE SPINDLE MOTOR | 4522-MT-004A | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 978 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - INDUSTRIAL FREEZER - ONTARIO OVENS 80-12 L: 1525, W: 715, H: 1250, 290 kg | 4522-SQ-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 980 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LARGE SHOP PRESS - AG - OTC1866 L: 1295, W: 1727, H: 3125, 1970 kg | 4522-SQ-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 981 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LATHE - SUMMIT MACHINE TOOL W: 44, H: 64 | 4522-SQ-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 983 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LATHE COOLANT PUMP | 4522-MT-004B | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 984 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MILLING MACHINE - AG | 4522-SQ-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 985 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LINE BORING MACHINE - CLIMAX BB5000 L: 1830 W: 330 H: 280 205 kg | 4522-SQ-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 986 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - IRON WORKER - BAILEIGH INDUSTRIAL 001-99777 L: 1525, W: 915, H: 1985, 2300 kg | 4522-SQ-008 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 987 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HEAVY TRUCK RAMP - ROTARY 60000HDL L: 13360, W: 4980, H: 3990 | 4522-SQ-009 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 988 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LIGHT TRUCK RAMP - ROTARY SM18LO-X H: 6990 | 4522-SQ-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 989 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SIPING MACHINE - AG | 4522-SQ-011 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 990 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - AIR FILTER CLEANER - DIVERSI-TECH L: 1830, W: 1830, H: 2650 | 4522-SQ-012 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 991 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-018 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 992 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-019 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 993 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 4522-SQ-021 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 994 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 4522-SQ-022 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 995 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 4522-SQ-023 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 996 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-026 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 997 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-027 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 998 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 4522-SQ-028 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 999 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 4522-SQ-029 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1000 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 4522-SQ-031 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1001 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 4522-SQ-036 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1002 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG | 4522-SQ-038 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1003 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 4522-SQ-041 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1004 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-042 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1005 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-043 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1006 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 4522-SQ-044 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1007 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - METAL BREAK FLOOR - AG - GGS13W877 580 kg | 4522-SQ-046 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1008 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-047 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1009 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-048 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1010 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-049 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1011 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-050 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1012 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 4522-SQ-051 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1013 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 4522-SQ-052 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1014 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-053 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-053 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1016 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-054 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1017 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-054 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1026 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - INCHING TOOL - AG | 4522-SQ-065 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1027 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-066 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1028 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-067 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1018 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-055 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1019 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-055 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1020 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-056 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1021 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-056 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1022 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 4522-SQ-059 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1023 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 4522-SQ-060 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1024 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG - OTC4240 | 4522-SQ-063 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1025 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584 W: 864 H: 1120 110 kg | 4522-SQ-064 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1029 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 4522-SQ-068 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Tire Shop at Ore Haul Truck Lineup (seacan construction) |  | 500 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 280.2083 | 1401.0417 | 21015.625 | 35026.0417 | 57442.7083 | 1 | 500 | 100% | 0% | 0% | 100% | 57442.7083 | 0 | 0 | 57442.7083 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 28721.3542 | 28721.3542 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | Light Plant |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | Frost Fighter Heater |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5279.1667 | 0 | 5279.1667 | 0 | 0 | 0 | 0 | 5279.1667
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | FRF | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Heater | Frost Fighter Heater | MR-FAC-POH-010 | 52 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 421.2 | 4615 | 31590 | 46150 | 82355 | 0.5 | 26 | 100% | 0% | 0% | 100% | 82355 | 0 | 0 | 82355 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 27451.6667 | 0 | 27451.6667 | 0 | 0 | 0 | 0 | 27451.6667
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | HOB | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Hot Box | Hot Box Heater | MR-FAC-POH-020 | 4 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 32.4 | 355 | 2430 | 3550 | 6335 | 0.5 | 2 | 100% | 0% | 0% | 100% | 6335 | 0 | 0 | 6335 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2111.6667 | 0 | 2111.6667 | 0 | 0 | 0 | 0 | 2111.6667
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-001 | 1003.7175 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 562.5 | 1968.75 | 42187.5 | 70312.5 | 114468.75 | 1 | 1003.7175 | 100% | 0% | 0% | 100% | 114468.75 | 0 | 0 | 114468.75 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 38156.25 | 38156.25 | 38156.25 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-001 | 1003.7175 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 145.7461 | 1821.8264 | 10930.9587 | 18218.2644 | 30971.0495 | 0.75 | 752.7881 | 100% | 0% | 0% | 100% | 30971.0495 | 0 | 0 | 30971.0495 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10323.6832 | 10323.6832 | 10323.6832 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1038 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - TRUCK WASH BUILDING DIESEL TANK | 4523-TK-004 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1034 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (DUTY) | 4523-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1035 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1036 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (STANDBY) | 4523-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1037 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1033 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-001 | 1003.7175 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Additional Truck Wash Building |  | 1500 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 840.625 | 2942.1875 | 63046.875 | 105078.125 | 171067.1875 | 1 | 1500 | 100% | 0% | 0% | 100% | 171067.1875 | 0 | 0 | 171067.1875 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 57022.3958 | 57022.3958 | 57022.3958 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Additional Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 1500 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 217.8095 | 2722.6184 | 16335.7104 | 27226.1841 | 46284.5129 | 0.75 | 1125 | 100% | 0% | 0% | 100% | 46284.5129 | 0 | 0 | 46284.5129 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 15428.171 | 15428.171 | 15428.171 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1038 |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Additional Truck Wash Building - Truck Wash System |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 10983.3333 | 0 | 10983.3333 | 0 | 0 | 0 | 0 | 10983.3333
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Ore Haul Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-002 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Ore Haul Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-002 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Ore Haul Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical Office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 4.4833 | 56.0417 | 336.25 | 560.4167 | 952.7083 | 1 | 20 | 100% | 0% | 0% | 100% | 952.7083 | 0 | 0 | 952.7083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 317.5694 | 317.5694 | 317.5694 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete Pad for tire maintenance at 110 Laydown |  | 60 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 7.5 | 112.5 | 562.5 | 1125 | 1800 | 0 | 0 | 100% | 0% | 0% | 100% | 1800 | 0 | 0 | 1800 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Additional Buildings by BIM Site Services slab on grade |  | 180 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 22.5 | 337.5 | 1687.5 | 3375 | 5400 | 0 | 0 | 100% | 0% | 0% | 100% | 5400 | 0 | 0 | 5400 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1800 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | Generator for 380-person temporary soft-walled camp |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 2261.6667 | 0 | 2261.6667 | 0 | 0 | 0 | 0 | 2261.6667
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1059 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-007 | 66.9145 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 37.5 | 187.5 | 2812.5 | 4687.5 | 7687.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 7687.5 | 0 | 0 | 7687.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2562.5 | 2562.5 | 2562.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1062 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-008 | 66.9145 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 37.5 | 187.5 | 2812.5 | 4687.5 | 7687.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 7687.5 | 0 | 0 | 7687.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2562.5 | 2562.5 | 2562.5 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1041 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1044 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1047 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1050 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1053 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1056 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1065 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 4530-BLD-009 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1138.8889 | 1138.8889 | 1138.8889 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1066 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1067 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1042 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1043 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1045 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1046 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1048 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1049 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1051 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1052 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1054 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1055 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1057 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1058 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1060 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1061 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1063 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1064 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-002 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-022 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-023 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #9 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-026 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #9 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #9 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #10 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-027 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #10 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #10 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-029 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-030 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-002 | 20 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 3.1383 | 39.2292 | 235.375 | 392.2917 | 666.8958 | 1 | 20 | 100% | 0% | 0% | 100% | 666.8958 | 0 | 0 | 666.8958 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 222.2986 | 222.2986 | 222.2986 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-002 | 20 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 2.9041 | 36.3016 | 217.8095 | 363.0158 | 617.1268 | 0.75 | 15 | 100% | 0% | 0% | 100% | 617.1268 | 0 | 0 | 617.1268 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 205.7089 | 205.7089 | 205.7089 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Existing Landfill |  | 6245 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1575.2302 | 12659.1573 | 103764.26 | 138730.4838 | 255153.901 | 0 | 0 | 100% | 0% | 0% | 100% | 255153.901 | 0 | 0 | 255153.901 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 255153.901 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Heated Maintenance shop for pit equipment at KM110.5 laydown |  | 1500 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 840.625 | 2942.1875 | 63046.875 | 105078.125 | 171067.1875 | 1 | 1500 | 100% | 0% | 0% | 100% | 171067.1875 | 0 | 0 | 171067.1875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 57022.3958 | 57022.3958 | 57022.3958 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 250 | 875 | 18750 | 31250 | 50875 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 50875 | 0 | 0 | 50875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 16958.3333 | 16958.3333 | 16958.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1070 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 64.7761 | 809.7006 | 4858.2038 | 8097.0064 | 13764.9109 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 13764.9109 | 0 | 0 | 13764.9109 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4588.3036 | 4588.3036 | 4588.3036 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1071 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 4540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 55.7621 | 836.4312 | 4182.1561 | 8364.3123 | 13382.8996 | 0 | 0 | 100% | 0% | 0% | 100% | 13382.8996 | 0 | 0 | 13382.8996 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4460.9665 | 4460.9665 | 4460.9665 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 4540-VP-001 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1072 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1667 | 145.8333 | 2187.5 | 3645.8333 | 5979.1667 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 5979.1667 | 0 | 0 | 5979.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1993.0556 | 1993.0556 | 1993.0556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1082 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4540-TK-007 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1696.25 | 1696.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1079 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 4540-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1075 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1076 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1077 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1078 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1080 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 4540-SQ-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1081 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG | 4540-SQ-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1073 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1074 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Lined Containment Cell |  | 900 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 40.0454 | 153.09 | 3003.4018 | 571.5408 | 3728.0326 | 0 | 0 | 100% | 0% | 0% | 100% | 3728.0326 | 0 | 0 | 3728.0326 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1242.6775 | 1242.6775 | 1242.6775 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 9000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 400.4536 | 1530.9 | 30034.0178 | 5715.4081 | 37280.326 | 0 | 0 | 100% | 0% | 0% | 100% | 37280.326 | 0 | 0 | 37280.326 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 12426.7753 | 12426.7753 | 12426.7753 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 1 | MS-HWB-XX | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 2 | MS-HWB-XX | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new-by generator) - 3 | MS-HWB-XX | 160 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 7.1192 | 27.216 | 533.9381 | 101.6073 | 658.7073 | 0 | 0 | 100% | 0% | 0% | 100% | 658.7073 | 0 | 0 | 658.7073 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 219.5691 | 219.5691 | 219.5691 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 4475 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1128.7678 | 9071.2136 | 74354.6939 | 99410.5548 | 173765.2487 | 0 | 0 | 100% | 0% | 0% | 100% | 173765.2487 | 0 | 0 | 173765.2487 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 173765.2487 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 400 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 100.8954 | 810.8347 | 6646.2296 | 8885.8596 | 15532.0893 | 0 | 0 | 100% | 0% | 0% | 100% | 15532.0893 | 0 | 0 | 15532.0893 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 15532.0893 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2018 Landfill Expansion |  | 63000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 799.775 | 9213.75 | 59983.1249 | 24982.3568 | 94085.4818 | 0 | 0 | 100% | 0% | 0% | 100% | 94085.4818 | 0 | 0 | 94085.4818 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 94085.4818 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm Containment Facilities 2020 HD Shop - 72m2, MR Shop - 120 m2, Wash Bay - 120 m2, 110 Laydown - 144 m2 |  | 456 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 20.2896 | 77.5656 | 1521.7236 | 289.5807 | 1877.3157 | 0 | 0 | 100% | 0% | 0% | 100% | 1877.3157 | 0 | 0 | 1877.3157 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 625.7719 | 625.7719 | 625.7719 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - New 2019 |  | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-2 | 1298 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 57.7543 | 220.7898 | 4331.5728 | 824.2889 | 5343.7626 | 0 | 0 | 100% | 0% | 0% | 100% | 5343.7626 | 0 | 0 | 5343.7626 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1781.2542 | 1781.2542 | 1781.2542 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-1 | 754 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 33.5491 | 128.2554 | 2516.1833 | 478.8242 | 3123.2629 | 0 | 0 | 100% | 0% | 0% | 100% | 3123.2629 | 0 | 0 | 3123.2629 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1041.0876 | 1041.0876 | 1041.0876 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-4 | 649 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 28.8772 | 110.3949 | 2165.7864 | 412.1444 | 2671.8813 | 0 | 0 | 100% | 0% | 0% | 100% | 2671.8813 | 0 | 0 | 2671.8813 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 890.6271 | 890.6271 | 890.6271 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-3 | 600 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 26.6969 | 102.06 | 2002.2679 | 381.0272 | 2470.1522 | 0 | 0 | 100% | 0% | 0% | 100% | 2470.1522 | 0 | 0 | 2470.1522 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 823.3841 | 823.3841 | 823.3841 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-6 | 550 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 24.4722 | 93.555 | 1835.4122 | 349.2749 | 2264.3062 | 0 | 0 | 100% | 0% | 0% | 100% | 2264.3062 | 0 | 0 | 2264.3062 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 754.7687 | 754.7687 | 754.7687 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-5 | 347 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 15.4397 | 59.0247 | 1157.9782 | 220.3607 | 1428.5714 | 0 | 0 | 100% | 0% | 0% | 100% | 1428.5714 | 0 | 0 | 1428.5714 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  | VP- | VP1 | VENDOR PKG - Incenerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person camp at Mine Site |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | 15ML Arctic Diesel Tank Mine Site |  | 2 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 1358.8 | 15695 | 101910 | 156950 | 274555 | 160 | 320 | 100% | 0% | 0% | 100% | 274555 | 0 | 0 | 274555 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 137277.5 | 137277.5 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-009 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1102 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-010 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1103 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-011 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1104 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-012 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1089 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 4613-FD-013 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1092 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 4613-FD-013 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1093 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1094 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1095 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1096 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1097 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1098 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1099 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-007 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1100 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-008 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1090 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 4613-FD-013 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 5587.5 | 0 | 5587.5 | 0 | 0 | 0 | 0 | 5587.5
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Site Fuel Tank Farm 2019 Footprint |  | 21620 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 274.4625 | 3161.925 | 20584.6851 | 8573.3104 | 32287.7479 | 0 | 0 | 100% | 0% | 0% | 100% | 32287.7479 | 0 | 0 | 32287.7479 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10762.5826 | 10762.5826 | 10762.5826 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (North West) |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (South West) |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | ENE | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Diesel Module | Diesel Module 1 | MR-FUM-FDI-010 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1130.8333 | 0 | 1130.8333 | 0 | 0 | 0 | 0 | 1130.8333
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | FIR | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Jet A1 Pump Module | Jet A1 Pump Module | MR-FUM-FUS-020-PUM01 | 1 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1583.75 | 0 | 0 | 1583.75 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 527.9167 | 0 | 527.9167 | 0 | 0 | 0 | 0 | 527.9167
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Farm Tank Dike |  | 1911.3 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 85.043 | 325.1121 | 6378.2243 | 1213.7622 | 7917.0986 | 0 | 0 | 100% | 0% | 0% | 100% | 7917.0986 | 0 | 0 | 7917.0986 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3958.5493 | 3958.5493 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 12000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 533.9381 | 2041.2 | 40045.3571 | 7620.5441 | 49707.1013 | 0 | 0 | 100% | 0% | 0% | 100% | 49707.1013 | 0 | 0 | 49707.1013 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 24853.5506 | 24853.5506 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 17.7979 | 68.04 | 1334.8452 | 254.0181 | 1656.9034 | 0 | 0 | 100% | 0% | 0% | 100% | 1656.9034 | 0 | 0 | 1656.9034 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 828.4517 | 828.4517 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1105 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1106 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-002 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1107 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1108 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1109 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator | 1110 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 | Generator |  | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - 1.35 MW GENERATOR |  | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4614 | Jet-A System | 416 | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | Tank - Jet-A tanks @ aerodrome apron |  | 0 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4711 | Raw Water Jetty | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1119 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Raw Water Supply Pipe - Piping Installation - Pumphouse to Water Building | 4712.2-P | 8518 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 2129.5 | 26618.75 | 159712.5 | 266187.5 | 452518.75 | 0.01 | 85.18 | 100% | 0% | 100% | 0% | 452518.75 | 0 | 452518.75 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 150839.5833 | 150839.5833 | 150839.5833 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1115 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Pumphouse - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4712-BLD-001 | 14.8699 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 3.3333 | 41.6667 | 250 | 416.6667 | 708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 708.3333 | 0 | 0 | 708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 236.1111 | 236.1111 | 236.1111 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1116 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Pumphouse - Demolish and foundations - Gravel Base - Skidded Building | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1117 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Pumphouse - Demolish floor finish - Raised Steel or Wooden Floor | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1118 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Raw Water Supply Pipe - Heat Trace Installation - Pumphouse to Water Building | 4712.2-E | 4712 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System |  |  | piping | Piping | Piping | Bulks | Piping |  | Raw Water Intake Pipeline |  |  | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1121 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 61.25 | 765.625 | 4593.75 | 7656.25 | 13015.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 13015.625 | 0 | 0 | 13015.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4338.5417 | 4338.5417 | 4338.5417 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1122 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE | 4720-VP-020 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1143 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 4720-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1144 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 4720-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1145 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 4720-TK-009 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1146 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 4720-TK-012 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1147 | TK- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Tank | TANK - MINE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4720-TK-033 | 1 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 1 | 1 | 100% | 0% | 0% | 100% | 3392.5 | 0 | 0 | 3392.5 | Type A 2AM-MRY1325 | Added | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1696.25 | 1696.25 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1124 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1125 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1126 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1127 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1128 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 4720-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1129 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 4720-PP-005 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1130 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 4720-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1131 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-008 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1132 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-008 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1133 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 4720-PP-010 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1134 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 4720-PP-011 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1135 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 4720-PP-013 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1136 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 4720-PP-014 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1137 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-015 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1138 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-015 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1139 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-031 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1140 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-031 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1141 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-032 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1142 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-032 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1123 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 4720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Infill between service and utility pads |  | 20800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 264.0527 | 3042 | 19803.9523 | 8248.1432 | 31063.1432 | 0 | 0 | 100% | 0% | 0% | 100% | 31063.1432 | 0 | 0 | 31063.1432 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 10354.3811 | 10354.3811 | 10354.3811 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK (40 m3) |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK (60 m3) |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | VENDOR PACKAGE - POTABLE WATER TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP7 | VENDOR PKG - WRF Water Treatment System | VP7 | Packaged Facilities | WRF Water Treatment |  | Water Treatment Plant for the Waste Rock Facility |  | 1 | Ea | 340 | 3625 | 25500 | 36250 | 61750 | 340 | 3625 | 25500 | 36250 | 61750 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 61750 | 0 | 61750 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 20583.3333 | 20583.3333 | 20583.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 800-person camp at Mine Site |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1154 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 100 | 500 | 7500 | 12500 | 20500 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 20500 | 0 | 0 | 20500 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1163 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 4731.2-P | 247 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 61.75 | 771.875 | 4631.25 | 7718.75 | 13121.875 | 0.01 | 2.47 | 100% | 0% | 100% | 0% | 13121.875 | 0 | 13121.875 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 6560.9375 | 6560.9375 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1161 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 4731-VP-005 | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1160 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - TREATED EFFLUENT TANK | 4731-TK-002 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1151 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 4731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1157 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 4731-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1158 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 4731-PP-004 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1159 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 4731-SC-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1152 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1153 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1162 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 4731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1155 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 4731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1156 | VP- |  | #N/A |  |  |  |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 4731-VP-005 | 1920 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - 800p camp to final discharge point |  | 2200 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 550 | 6875 | 41250 | 68750 | 116875 | 0.01 | 22 | 100% | 0% | 100% | 0% | 116875 | 0 | 116875 | 0 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 58437.5 | 58437.5 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 800-person camp at Mine Site |  | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1165 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 31.25 | 109.375 | 2343.75 | 3906.25 | 6359.375 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 6359.375 | 0 | 0 | 6359.375 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 3179.6875 | 3179.6875 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4280 | Mine Support Facilities |  | Water Systems |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Soft Walled Building (tent) Contaminated (480 ft2) |  | Tent Structure for Waste Rock Facility Water Treatment System |  | 726 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 423.137 | 1627.45 | 39033.4257 | 52892.125 | 93553.0007 | 0.5 | 363 | 100% | 0% | 0% | 100% | 93553.0007 | 0 | 0 | 93553.0007 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 46776.5004 | 46776.5004 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1172 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1166 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.097 | 101.2126 | 607.2755 | 1012.1258 | 1720.6139 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1720.6139 | 0 | 0 | 1720.6139 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 860.3069 | 860.3069 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1168 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1169 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-001 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1170 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1171 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-002 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1167 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 4732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1178 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to connection with Stockpile Drain Pipe | 4734.1-P | 2125 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 531.25 | 6640.625 | 39843.75 | 66406.25 | 112890.625 | 0.01 | 21.25 | 100% | 0% | 100% | 0% | 112890.625 | 0 | 112890.625 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 37630.2083 | 37630.2083 | 37630.2083 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1177 | In Meters |  | Inlcuded with Piping | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to connection with Stockpile Drain Pipe | 4734.1-E | 2050 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1174 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE | 4733-VM-001 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1175 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE SPARE | 4733-VM-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | FRP Water tanks for 800p camp |  | 4 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 38.6667 | 358.3333 | 2900 | 3583.3333 | 6841.6667 | 1 | 4 | 100% | 0% | 0% | 100% | 6841.6667 | 0 | 0 | 6841.6667 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2280.5556 | 2280.5556 | 2280.5556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Water Tank 10,000L |  | 4 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 38.6667 | 358.3333 | 2900 | 3583.3333 | 6841.6667 | 1 | 4 | 100% | 0% | 0% | 100% | 6841.6667 | 0 | 0 | 6841.6667 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2280.5556 | 2280.5556 | 2280.5556 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | -3 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -29 | -268.75 | -2175 | -2687.5 | -5131.25 | 1 | -3 | 100% | 0% | 0% | 100% | -5131.25 | 0 | 0 | -5131.25 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -1710.4167 | -1710.4167 | -1710.4167 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 2 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 19.3333 | 179.1667 | 1450 | 1791.6667 | 3420.8333 | 1 | 2 | 100% | 0% | 0% | 100% | 3420.8333 | 0 | 0 | 3420.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1140.2778 | 1140.2778 | 1140.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | 2 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 19.3333 | 179.1667 | 1450 | 1791.6667 | 3420.8333 | 1 | 2 | 100% | 0% | 0% | 100% | 3420.8333 | 0 | 0 | 3420.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1140.2778 | 1140.2778 | 1140.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 3 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 93 | 975 | 6975 | 9750 | 17700 | 2 | 6 | 100% | 0% | 0% | 100% | 17700 | 0 | 0 | 17700 | Type B Construction 2BC-MRY1416 | Confirmed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 8850 | 8850 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1204 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV & Ground Wire - Electrical distribution system from power gen to e-house | 4750.2-E | 11000 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 1100 | 13750 | 82500 | 137500 | 233750 | 0.01 | 110 | 100% | 0% | 0% | 100% | 233750 | 0 | 0 | 233750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 77916.6667 | 77916.6667 | 77916.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 4750.3-E | 5200 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 520 | 6500 | 39000 | 65000 | 110500 | 0.01 | 52 | 100% | 0% | 0% | 100% | 110500 | 0 | 0 | 110500 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 36833.3333 | 36833.3333 | 36833.3333 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1180 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1201 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing & Screening E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1183 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1186 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1189 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1192 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-005 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 885.4167 | 885.4167 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1195 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Aerodrome Area E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-006 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1198 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Supply E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-007 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1184 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1185 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1187 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1188 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1190 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1191 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1193 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1194 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1196 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Area E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1197 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Area E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1199 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Supply E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1200 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Supply E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1181 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1182 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1202 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1203 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Cabling for Lighting at Mine Site Warehouse |  | 600 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 60 | 750 | 4500 | 7500 | 12750 | 0.01 | 6 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Mine Site |  | 3500 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 350 | 4375 | 26250 | 43750 | 74375 | 0.01 | 35 | 100% | 0% | 0% | 100% | 74375 | 0 | 0 | 74375 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 24791.6667 | 24791.6667 | 24791.6667 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-012 | 37.1612 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3303 | 104.1288 | 624.773 | 1041.2883 | 1770.1901 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 1770.1901 | 0 | 0 | 1770.1901 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 590.0634 | 590.0634 | 590.0634 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #2- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services
7000 | Construction Facilities & Services | 7100 | Project Wide
7000 | Construction Facilities & Services | 7100 | Project Wide | 7110 | Communications & IT | 7111 | Communications Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7123 | Helicopter Service | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7121 | Jet Service | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7100 | Project Wide | 7120 | Air Services | 7122 | Local Air Charter | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Existing Trailer Camp (Shanco) |  | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | 49-person Hard Wall Trailer Camp (previously at Steensby) |  | 950 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 212.9583 | 2661.9792 | 15971.875 | 26619.7917 | 45253.6458 | 1 | 950 | 100% | 0% | 0% | 100% | 45253.6458 | 0 | 0 | 45253.6458 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 45253.6458 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7214 | Off-Spec Effluent Pond(s) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Matrix Camp |  | 5392.34 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 967.0263 | 12087.8288 | 72526.973 | 120878.2883 | 205493.0902 | 0.5 | 2696.17 | 100% | 0% | 0% | 100% | 205493.0902 | 0 | 0 | 205493.0902 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 68497.6967 | 68497.6967 | 68497.6967 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tents |  | 0 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7213 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 0 | ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7238 | Civil Contractor Buildings | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 1252.363 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 729.9189 | 2807.3804 | 67333.3583 | 91239.8627 | 161380.6014 | 0.5 | 626.1815 | 100% | 0% | 0% | 100% | 161380.6014 | 0 | 0 | 161380.6014 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 53793.5338 | 53793.5338 | 53793.5338 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 878.1618 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 511.822 | 1968.546 | 47214.4124 | 63977.7461 | 113160.7046 | 0.5 | 439.0809 | 100% | 0% | 0% | 100% | 113160.7046 | 0 | 0 | 113160.7046 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 37720.2349 | 37720.2349 | 37720.2349 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 250.24 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 140.2387 | 490.8353 | 10517.9 | 17529.8333 | 28538.5687 | 1 | 250.24 | 100% | 0% | 0% | 100% | 28538.5687 | 0 | 0 | 28538.5687 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 28538.5687 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [6 empty] | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | [6 empty] | Construction Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish floor finish - Gravel | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 1192.477 | 4586.45 | 110003.2907 | 149059.625 | 263649.3657 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 263649.3657 | 0 | 0 | 263649.3657 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 87883.1219 | 87883.1219 | 87883.1219 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 255.75 | 3836.25 | 19181.25 | 38362.5 | 61380 | 0 | 0 | 100% | 0% | 0% | 100% | 61380 | 0 | 0 | 61380 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 61380 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1222 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Construction Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 7231-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 60 | 750 | 4500 | 7500 | 12750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1230 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7231-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1225 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 7231-BLD-002 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1231 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 7231-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1226 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1228 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7231-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1229 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7231-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1227 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1223 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Office - Demolish and foundations - Gravel Base - Skidded Building | 7231-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1224 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Construction Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 0 | 0 | 100% | 0% | 0% | 100% | 22405.6604 | 0 | 0 | 22405.6604 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7468.5535 | 7468.5535 | 7468.5535 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1286 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Heated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-002 | 371.7472 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 58.3333 | 729.1667 | 4375 | 7291.6667 | 12395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 12395.8333 | 0 | 0 | 12395.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4131.9444 | 4131.9444 | 4131.9444 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1289 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-003 | 371.7472 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 58.3333 | 729.1667 | 4375 | 7291.6667 | 12395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 12395.8333 | 0 | 0 | 12395.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4131.9444 | 4131.9444 | 4131.9444 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1287 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Heated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-002 | 371.7472 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 53.98 | 674.7505 | 4048.5032 | 6747.5053 | 11470.7591 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 11470.7591 | 0 | 0 | 11470.7591 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3823.5864 | 3823.5864 | 3823.5864 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1290 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-003 | 371.7472 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 53.98 | 674.7505 | 4048.5032 | 6747.5053 | 11470.7591 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 11470.7591 | 0 | 0 | 11470.7591 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3823.5864 | 3823.5864 | 3823.5864 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1283 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 32.388 | 404.8503 | 2429.1019 | 4048.5032 | 6882.4555 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 6882.4555 | 0 | 0 | 6882.4555 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2294.1518 | 2294.1518 | 2294.1518 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1284 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 32.388 | 404.8503 | 2429.1019 | 4048.5032 | 6882.4555 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 6882.4555 | 0 | 0 | 6882.4555 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2294.1518 | 2294.1518 | 2294.1518 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1285 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Equipment Building - Demolish floor finish - Gravel | 7235-BLD-001 | 223.0483 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1288 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Heated Warehouse - Demolish floor finish - Gravel | 7235-BLD-002 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1291 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-003 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-004 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1271 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1254 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-009 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1257 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-010 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1272 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1269 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1273 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-007 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1274 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1255 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1258 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1239 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1248 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-007 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1251 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-008 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1242 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Office - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-005 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1245 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-006 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1270 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7232-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Washcar - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Washcar - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Quarry Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1265 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1267 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1260 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7232-BLD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1240 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1249 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-007 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1252 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-008 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Quarry Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-001 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1256 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1263 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1264 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1259 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1266 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1268 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1261 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1262 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1243 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Office - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1244 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Office - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1246 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1247 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1241 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1250 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1253 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1295 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-001 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1296 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-002 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1297 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-003 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1298 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-004 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1299 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-005 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1300 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-006 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1301 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-007 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1302 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-008 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1303 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-009 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1304 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-010 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1305 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1306 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-012 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1307 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-013 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1308 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1309 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7241-MO-024 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1310 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1355 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 3776 kg | 7244-GE-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1350 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Generator | GENERATOR - ACOMMODATIONS AREA GENERATOR - CUMMINS C1600D6R L: 14630, W: 2440, H: 4062, 68320 kg | 7244-GE-001 | 0 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1351 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-002 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1352 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1353 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1354 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1356 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - LOGISTICS TRAILER GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315m 3776 kg | 7244-GE-007 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1357 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-008 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1358 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-009 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1359 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1360 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-002 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1361 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-003 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1362 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7245-MO-004 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1363 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-005 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1364 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-006 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1365 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MAMTEX 26101C | 7245-MO-007 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1366 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - GROVE RT890E 41400 kg | 7245-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1367 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-010 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1368 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-011 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1369 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-012 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7242 | Emergency Response Equipment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1313 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-001 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1314 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1315 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-003 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1316 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-004 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1317 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-005 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1318 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-006 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1319 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-007 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1320 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1321 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-009 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1322 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-010 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1323 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-011 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1324 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-012 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1325 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7243-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1326 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7243-MO-015 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1327 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-016 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1328 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-017 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1329 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-018 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1330 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-019 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1331 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-020 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1332 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7243-MO-021 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1333 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7243-MO-022 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Frost Fighter Heater |  | -6 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -40 | -125 | -3000 | -1250 | -4375 | 4 | -24 | 100% | 0% | 0% | 100% | -4375 | 0 | 0 | -4375 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | -1458.3333 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | -1458.3333
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Frost Fighter Heater |  | 7 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 46.6667 | 145.8333 | 3500 | 1458.3333 | 5104.1667 | 4 | 28 | 100% | 0% | 0% | 100% | 5104.1667 | 0 | 0 | 5104.1667 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 1701.3889 | 0 | 1701.3889 | 0 | 0 | 0 | 0 | 1701.3889
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-023 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1335 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-024 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1336 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1337 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1338 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1339 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1340 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-029 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1341 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1342 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-031 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1343 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-032 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1344 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1345 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1346 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1347 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1348 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1349 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7243-MO-046 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1372 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1373 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Batch Plant Stockpile |  | 5180.44 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 65.7649 | 757.6393 | 4932.3648 | 2054.2794 | 7744.2835 | 0 | 0 | 100% | 0% | 0% | 100% | 7744.2835 | 0 | 0 | 7744.2835 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 2581.4278 | 2581.4278 | 2581.4278 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1374 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7251-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  |  | #N/A |  |  |  | Batch Plant Building | Batch Plant Building |  | 3281.62 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7252 | Explosives Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7271 | Camp Operations & Catering | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7275 | Maintenance and Repair | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 43.8425 | 167.6063 | 3288.191 | 625.7356 | 4081.5329 | 0 | 0 | 100% | 0% | 0% | 100% | 4081.5329 | 0 | 0 | 4081.5329 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1360.511 | 1360.511 | 1360.511 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 43.8425 | 167.6063 | 3288.191 | 625.7356 | 4081.5329 | 0 | 0 | 100% | 0% | 0% | 100% | 4081.5329 | 0 | 0 | 4081.5329 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1360.511 | 1360.511 | 1360.511 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bladder Farm Decommissioning |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Hazardous Waste Berm |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  |  | #N/A |  |  |  |  | Old STP (RBC) |  | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1386 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-001 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1387 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-002 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1388 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-003 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1389 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 7340-MO-004 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1390 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CS74 L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-014 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1391 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-015 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1392 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-016 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1393 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-017 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Exploration Tent Camp Pad |  | 9432.14 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 1179.0175 | 17685.2625 | 88426.3125 | 176852.625 | 282964.2 | 0 | 0 | 100% | 0% | 0% | 100% | 282964.2 | 0 | 0 | 282964.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 282964.2 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Soft-Wall Camp (Weatherhaven) |  | 6017.14 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 1079.0738 | 13488.4222 | 80930.533 | 134884.2217 | 229303.1768 | 0.5 | 3008.57 | 100% | 0% | 0% | 100% | 229303.1768 | 0 | 0 | 229303.1768 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 229303.1768 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Modular Building Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tent Camp Tents |  | 2400 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 430.4 | 5380 | 32280 | 53800 | 91460 | 0.5 | 1200 | 100% | 0% | 0% | 100% | 91460 | 0 | 0 | 91460 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 91460 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Old Incinerator (Medium sized equipment) |  | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  |  | #N/A | VP7 | Packaged Facilities |  |  | Exploration STP |  | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 182.2 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 102.1079 | 357.3777 | 7658.0937 | 12763.4896 | 20778.961 | 1 | 182.2 | 100% | 0% | 0% | 100% | 20778.961 | 0 | 0 | 20778.961 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 20778.961 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF3-c | Modular Building Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 1192.477 | 4586.45 | 110003.2907 | 149059.625 | 263649.3657 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 263649.3657 | 0 | 0 | 263649.3657 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 87883.1219 | 87883.1219 | 87883.1219 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 255.75 | 3836.25 | 19181.25 | 38362.5 | 61380 | 0 | 0 | 100% | 0% | 0% | 100% | 61380 | 0 | 0 | 61380 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [6 empty] | 0 |  | 0 | 61380 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7431 | Office Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7435 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 0 | 0 | 100% | 0% | 0% | 100% | 22405.6604 | 0 | 0 | 22405.6604 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7468.5535 | 7468.5535 | 7468.5535 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1435 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1437 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1439 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-010 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1407 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2050 | 2050 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1416 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-007 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1419 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-008 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1433 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1436 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - FUEL SYSTEMS WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1438 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1440 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-011 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1408 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 297.5 | 297.5 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1417 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-007 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1401 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1404 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 1593.75 | 1593.75 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1410 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-005 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1413 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-006 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1420 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-008 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1434 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7432-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1422 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7432-BLD-009 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1402 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1405 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Lunchroom - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 557.8125 | 557.8125 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1411 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-005 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1414 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-006 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1427 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - FUEL SYSTEMS WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1429 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1431 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1409 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1418 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-007 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1425 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1426 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-003 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1421 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-008 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1428 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-006 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1430 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-009 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1432 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-012 | 0 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | [6 empty] | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1423 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1424 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1403 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1406 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1412 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-005 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1415 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-006 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1446 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader size | MOBILE EQUIPMENT - FUEL/LUBE TRUCK - ARTICULATED - CAT 740 EFLT | 7441-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1447 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7441-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1497 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-009 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1498 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-010 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1499 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-011 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1489 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - ACCOMMODATIONS AREA GENERATOR - CUMMINS C1600D6RG L: 14630, W: 2440, H: 4065, 78220 kg | 7444-GE-001 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1490 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-002 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1491 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-003 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1492 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4496, W: 1905, H: 2085, 6458 kg | 7444-GE-004 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1493 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-005 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1494 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-006 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1495 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-007 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1496 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-008 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1500 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-012 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1501 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-013 | 0 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1502 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-002 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1503 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-003 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1504 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-006 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1505 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-007 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1506 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-008 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1507 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - MANITOWOC 2250 L: 12900, W: 7910, H: 3640, 113000 kg | 7445-MO-009 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1508 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MANITEX 26101C | 7445-MO-012 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1509 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-013 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1510 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1448 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-001 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1449 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-002 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1450 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-003 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1451 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-004 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1452 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-005 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1453 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-006 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1454 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-007 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1455 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-008 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1456 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-009 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1457 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-010 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1458 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-011 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1459 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-012 |  | Ea | 13 | 100 | 975 | 1000 | 2075 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1460 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-014 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1461 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Compressor | MOBILE EQUIPMENT - LARGE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-015 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1462 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7443-MO-016 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1463 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-017 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1464 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-018 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1465 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-019 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1466 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-020 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1467 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-021 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1468 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7443-MO-022 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1469 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7443-MO-023 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1470 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-024 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1471 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-025 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1472 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-026 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1473 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-027 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1474 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-028 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1475 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-029 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1476 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-030 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1477 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-031 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1478 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-032 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1479 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-033 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1480 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-034 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1481 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-035 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1482 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-036 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1483 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-037 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1484 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-038 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1485 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7443-MO-051 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1486 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER L: 14630, W: 2438 | 7443-MO-052 |  | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1487 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-053 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1488 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-054 |  | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1513 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1514 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1515 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7451-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Containment Area - Existing |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond (Existing) |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7471 | Camp Operations & Catering | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7475 | Maintenance and Repair | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bulk Fuel Storage Facility (Bladder Farm) |  | 5787.68 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 257.5219 | 984.4844 | 19314.1427 | 3675.4392 | 23974.0663 | 0 | 0 | 100% | 0% | 0% | 100% | 23974.0663 | 0 | 0 | 23974.0663 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 11987.0332 | 11987.0332 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Barreled Fuel Line Containment |  | 5411.65 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 240.7905 | 920.5217 | 18059.2881 | 3436.6431 | 22416.4529 | 0 | 0 | 100% | 0% | 0% | 100% | 22416.4529 | 0 | 0 | 22416.4529 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [6 empty] | 0 |  | 11208.2264 | 11208.2264 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7480 | Construction Services | 7484 | Explosives Supply Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7480 | Construction Services | 7482 | Heavy Transport Services | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 |  |  | Type A 2AM-MRY1325 |  | 2014 | Direct | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | EPCM Services |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 1712000 | 0 | 0 | 97.29% | 2.709% | 0% | 100% | 1665622.5594 | 46377.4406 | 0 | 1712000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect | 22% | 28% | 3.791% | 5.694% | 3.791% | 11.91% | 7.956% | 6.532% | 5.563% | 4.76% | 22440 | 28560 | 3866.3522 | 5807.64 | 3866.3522 | 12150.2202 | 8115.2146 | 6663.0406 | 5674.6023 | 4854.8175
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | EPCM Services |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 3766032 | 0 | 0 | 97.29% | 2.709% | 0% | 100% | 3664011.5997 | 102020.4003 | 0 | 3766032 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | 22% | 28% | 3.791% | 5.694% | 3.791% | 11.91% | 7.956% | 6.532% | 5.563% | 4.76% | 22440 | 28560 | 3866.3522 | 5807.64 | 3866.3522 | 12150.2202 | 8115.2146 | 6663.0406 | 5674.6023 | 4854.8175
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 1489000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 1454965.899 | 34034.101 | 0 | 1489000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 297800 | 297800 | 297800 | 148900 | 148900 | 148900 | 74450 | 74450
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 486000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 474891.4889 | 11108.5111 | 0 | 486000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 194400 | 145800 | 97200 | 48600 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 142000 | 0 | 0 | 100% | 0% | 0% | 100% | 142000 | 0 | 0 | 142000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 28400 | 28400 | 28400 | 14200 | 14200 | 14200 | 7100 | 7100
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 26000 | 0 | 0 | 100% | 0% | 0% | 100% | 26000 | 0 | 0 | 26000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 10400 | 7800 | 5200 | 2600 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 44000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 34694.0539 | 9305.9461 | 0 | 44000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 8800 | 8800 | 8800 | 4400 | 4400 | 4400 | 2200 | 2200
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 18000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 14193.022 | 3806.978 | 0 | 18000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 7200 | 5400 | 3600 | 1800 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 102000 | 0 | 0 | 100% | 0% | 0% | 100% | 102000 | 0 | 0 | 102000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 20400 | 20400 | 20400 | 10200 | 10200 | 10200 | 5100 | 5100
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 40000 | 0 | 0 | 100% | 0% | 0% | 100% | 40000 | 0 | 0 | 40000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 16000 | 12000 | 8000 | 4000 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 804000 | 0 | 0 | 100% | 0% | 0% | 100% | 804000 | 0 | 0 | 804000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 160800 | 160800 | 160800 | 80400 | 80400 | 80400 | 40200 | 40200
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 87000 | 0 | 0 | 100% | 0% | 0% | 100% | 87000 | 0 | 0 | 87000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 17400 | 17400 | 17400 | 8700 | 8700 | 8700 | 4350 | 4350
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | -58000 | 0 | 0 | 100% | 0% | 0% | 100% | -58000 | 0 | 0 | -58000 | Type A 2AM-MRY1325 | removed | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -11600 | -11600 | -11600 | -5800 | -5800 | -5800 | -2900 | -2900
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 453000 | 0 | 0 | 100% | 0% | 0% | 100% | 453000 | 0 | 0 | 453000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 90600 | 90600 | 90600 | 45300 | 45300 | 45300 | 22650 | 22650
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | -24000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | -23451.4315 | -548.5685 | 0 | -24000 | Type A 2AM-MRY1325 | removed | 2018-MAY | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | -9600 | -7200 | -4800 | -2400 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 188000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 183702.8805 | 4297.1195 | 0 | 188000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 75200 | 56400 | 37600 | 18800 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 28000 | 0 | 0 | 100% | 0% | 0% | 100% | 28000 | 0 | 0 | 28000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 5600 | 5600 | 5600 | 2800 | 2800 | 2800 | 1400 | 1400
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 12000 | 0 | 0 | 100% | 0% | 0% | 100% | 12000 | 0 | 0 | 12000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 4800 | 3600 | 2400 | 1200 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 449000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 430544.4834 | 18455.5166 | 0 | 449000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 89800 | 89800 | 89800 | 44900 | 44900 | 44900 | 22450 | 22450
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 186000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 178354.7303 | 7645.2697 | 0 | 186000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 74400 | 55800 | 37200 | 18600 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 81000 | 0 | 0 | 100% | 0% | 0% | 100% | 81000 | 0 | 0 | 81000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 16200 | 16200 | 16200 | 8100 | 8100 | 8100 | 4050 | 4050
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 446000 | 0 | 0 | 100% | 0% | 0% | 100% | 446000 | 0 | 0 | 446000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 89200 | 89200 | 89200 | 44600 | 44600 | 44600 | 22300 | 22300
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 33000 | 0 | 0 | 100% | 0% | 0% | 100% | 33000 | 0 | 0 | 33000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 13200 | 9900 | 6600 | 3300 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 267000 | 0 | 0 | 100% | 0% | 0% | 100% | 267000 | 0 | 0 | 267000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 106800 | 80100 | 53400 | 26700 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 36000 | 0 | 0 | 100% | 0% | 0% | 100% | 36000 | 0 | 0 | 36000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 14400 | 10800 | 7200 | 3600 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 185000 | 0 | 0 | 100% | 0% | 0% | 100% | 185000 | 0 | 0 | 185000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 40% | 30% | 20% | 10% |  |  |  |  | 0 |  | 74000 | 55500 | 37000 | 18500 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 8000 | 0 | 0 | 100% | 0% | 100% | 0% | 8000 | 0 | 8000 | 0 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 3200 | 2400 | 1600 | 400 | 400
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 40% | 30% | 20% | 5% | 5% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect |  |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect |  |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  |  | Indirect | Indirect |  |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  |  | Indirect | Indirect |  |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect | [5 empty] | 20% | 20% | 20% | 20% | 20% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 2019000 | 0 | 0 | 100% | 0% | 0% | 100% | 2019000 | 0 | 0 | 2019000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 673000 | 673000 | 673000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive material) | [12 empty] | 2537000 | 0 | 0 | 100% | 0% | 0% | 100% | 2537000 | 0 | 0 | 2537000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 845666.6667 | 845666.6667 | 845666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 234000 | 0 | 0 | 100% | 0% | 0% | 100% | 234000 | 0 | 0 | 234000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 63000 | 0 | 0 | 100% | 0% | 0% | 100% | 63000 | 0 | 0 | 63000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 21000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 5000 | 0 | 0 | 100% | 0% | 0% | 100% | 5000 | 0 | 0 | 5000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 2874000 | 0 | 0 | 100% | 0% | 0% | 100% | 2874000 | 0 | 0 | 2874000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 958000 | 958000 | 958000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 29000 | 0 | 0 | 100% | 0% | 0% | 100% | 29000 | 0 | 0 | 29000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9666.6667 | 9666.6667 | 9666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 14000 | 0 | 0 | 100% | 0% | 0% | 100% | 14000 | 0 | 0 | 14000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 4666.6667 | 4666.6667 | 4666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 28000 | 0 | 0 | 100% | 0% | 0% | 100% | 28000 | 0 | 0 | 28000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | -15000 | 0 | 0 | 100% | 0% | 0% | 100% | -15000 | 0 | 0 | -15000 | Type A 2AM-MRY1325 | removed | 2018-MAY | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | -5000 | -5000 | -5000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 136000 | 0 | 0 | 100% | 0% | 0% | 100% | 136000 | 0 | 0 | 136000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 45333.3333 | 45333.3333 | 45333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 21000 | 0 | 0 | 100% | 0% | 0% | 100% | 21000 | 0 | 0 | 21000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 7000 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 237000 | 0 | 0 | 100% | 0% | 0% | 100% | 237000 | 0 | 0 | 237000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 79000 | 79000 | 79000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 76000 | 0 | 0 | 100% | 0% | 0% | 100% | 76000 | 0 | 0 | 76000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 25333.3333 | 25333.3333 | 25333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 9000 | 0 | 0 | 100% | 0% | 0% | 100% | 9000 | 0 | 0 | 9000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 219000 | 0 | 0 | 100% | 0% | 0% | 100% | 219000 | 0 | 0 | 219000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 73000 | 73000 | 73000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 1211000 | 0 | 0 | 100% | 0% | 0% | 100% | 1211000 | 0 | 0 | 1211000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 403666.6667 | 403666.6667 | 403666.6667 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 1246000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 1217520.1546 | 28479.8454 | 0 | 1246000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 249200 | 249200 | 249200 | 124600 | 124600 | 124600 | 62300 | 62300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 652000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 637097.2238 | 14902.7762 | 0 | 652000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 130400 | 130400 | 130400 | 65200 | 65200 | 65200 | 32600 | 32600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 66000 | 0 | 0 | 100% | 0% | 0% | 100% | 66000 | 0 | 0 | 66000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 13200 | 13200 | 13200 | 6600 | 6600 | 6600 | 3300 | 3300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 46000 | 0 | 0 | 100% | 0% | 0% | 100% | 46000 | 0 | 0 | 46000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 9200 | 9200 | 9200 | 4600 | 4600 | 4600 | 2300 | 2300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 47000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 37059.5575 | 9940.4425 | 0 | 47000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 9400 | 9400 | 9400 | 4700 | 4700 | 4700 | 2350 | 2350
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 29000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 22866.5355 | 6133.4645 | 0 | 29000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 5800 | 5800 | 5800 | 2900 | 2900 | 2900 | 1450 | 1450
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | -61637.0833 | 0 | 0 | 100% | 0% | 0% | 100% | -61637.0833 | 0 | 0 | -61637.0833 | Type A 2AM-MRY1325 | Removed | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -12327.4167 | -12327.4167 | -12327.4167 | -6163.7083 | -6163.7083 | -6163.7083 | -3081.8542 | -3081.8542
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 102000 | 0 | 0 | 100% | 0% | 0% | 100% | 102000 | 0 | 0 | 102000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 20400 | 20400 | 20400 | 10200 | 10200 | 10200 | 5100 | 5100
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 42000 | 0 | 0 | 100% | 0% | 0% | 100% | 42000 | 0 | 0 | 42000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 8400 | 8400 | 8400 | 4200 | 4200 | 4200 | 2100 | 2100
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 440000 | 0 | 0 | 100% | 0% | 0% | 100% | 440000 | 0 | 0 | 440000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 88000 | 88000 | 88000 | 44000 | 44000 | 44000 | 22000 | 22000
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 55000 | 0 | 0 | 100% | 0% | 0% | 100% | 55000 | 0 | 0 | 55000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 11000 | 11000 | 11000 | 5500 | 5500 | 5500 | 2750 | 2750
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 43000 | 0 | 0 | 100% | 0% | 0% | 100% | 43000 | 0 | 0 | 43000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 8600 | 8600 | 8600 | 4300 | 4300 | 4300 | 2150 | 2150
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 86000 | 0 | 0 | 100% | 0% | 0% | 100% | 86000 | 0 | 0 | 86000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 17200 | 17200 | 17200 | 8600 | 8600 | 8600 | 4300 | 4300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 684266.7317 | 0 | 0 | 100% | 0% | 0% | 100% | 684266.7317 | 0 | 0 | 684266.7317 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 136853.3463 | 136853.3463 | 136853.3463 | 68426.6732 | 68426.6732 | 68426.6732 | 34213.3366 | 34213.3366
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 92000 | 0 | 0 | 100% | 0% | 0% | 100% | 92000 | 0 | 0 | 92000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 18400 | 18400 | 18400 | 9200 | 9200 | 9200 | 4600 | 4600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 481540.8098 | 0 | 0 | 100% | 0% | 0% | 100% | 481540.8098 | 0 | 0 | 481540.8098 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 96308.162 | 96308.162 | 96308.162 | 48154.081 | 48154.081 | 48154.081 | 24077.0405 | 24077.0405
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2019) |  | 18172 | m3 |  |  |  |  | 68 |  |  |  |  | 1235696 | 0 | 0 | 100% | 0% | 0% | 100% | 1235696 | 0 | 0 | 1235696 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 247139.2 | 247139.2 | 247139.2 | 123569.6 | 123569.6 | 123569.6 | 61784.8 | 61784.8
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2019) |  | 49868 | m3 |  |  |  |  | 68 |  |  |  |  | 3391024 | 0 | 0 | 100% | 0% | 0% | 100% | 3391024 | 0 | 0 | 3391024 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 678204.8 | 678204.8 | 678204.8 | 339102.4 | 339102.4 | 339102.4 | 169551.2 | 169551.2
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2019) |  | 24756 | m3 |  |  |  |  | 68 |  |  |  |  | 1683408 | 0 | 0 | 100% | 0% | 0% | 100% | 1683408 | 0 | 0 | 1683408 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 336681.6 | 336681.6 | 336681.6 | 168340.8 | 168340.8 | 168340.8 | 84170.4 | 84170.4
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2019) |  | 33278 | m3 |  |  |  |  | 68 |  |  |  |  | 2262904 | 0 | 0 | 100% | 0% | 0% | 100% | 2262904 | 0 | 0 | 2262904 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 452580.8 | 452580.8 | 452580.8 | 226290.4 | 226290.4 | 226290.4 | 113145.2 | 113145.2
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Shiploading Module (mobilized in 2019) |  | 81400 | m3 |  |  |  |  | 68 |  |  |  |  | 5535200 | 0 | 0 | 100% | 0% | 0% | 100% | 5535200 | 0 | 0 | 5535200 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 1107040 | 1107040 | 1107040 | 553520 | 553520 | 553520 | 276760 | 276760
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2019) |  | 21815 | m3 |  |  |  |  | 68 |  |  |  |  | 1483420 | 0 | 0 | 100% | 0% | 0% | 100% | 1483420 | 0 | 0 | 1483420 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 296684 | 296684 | 296684 | 148342 | 148342 | 148342 | 74171 | 74171
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | 30500 | m3 |  |  |  |  | 68 |  |  |  |  | 2074000 | 0 | 0 | 100% | 0% | 0% | 100% | 2074000 | 0 | 0 | 2074000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 414800 | 414800 | 414800 | 207400 | 207400 | 207400 | 103700 | 103700
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | -30500 | m3 |  |  |  |  | 68 |  |  |  |  | -2074000 | 0 | 0 | 100% | 0% | 0% | 100% | -2074000 | 0 | 0 | -2074000 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -414800 | -414800 | -414800 | -207400 | -207400 | -207400 | -103700 | -103700
8002 | Other Indirects | 8102 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | 40500 | m3 |  |  |  |  | 68 |  |  |  |  | 2754000 | 0 | 0 | 100% | 0% | 0% | 100% | 2754000 | 0 | 0 | 2754000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 550800 | 550800 | 550800 | 275400 | 275400 | 275400 | 137700 | 137700
8002 | Other Indirects | 8102 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | -40500 | m3 |  |  |  |  | 68 |  |  |  |  | -2754000 | 0 | 0 | 100% | 0% | 0% | 100% | -2754000 | 0 | 0 | -2754000 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -550800 | -550800 | -550800 | -275400 | -275400 | -275400 | -137700 | -137700
8003 | Other Indirects | 8103 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | 24100 | m3 |  |  |  |  | 68 |  |  |  |  | 1638800 | 0 | 0 | 100% | 0% | 0% | 100% | 1638800 | 0 | 0 | 1638800 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 327760 | 327760 | 327760 | 163880 | 163880 | 163880 | 81940 | 81940
8003 | Other Indirects | 8103 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | -24100 | m3 |  |  |  |  | 68 |  |  |  |  | -1638800 | 0 | 0 | 100% | 0% | 0% | 100% | -1638800 | 0 | 0 | -1638800 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -327760 | -327760 | -327760 | -163880 | -163880 | -163880 | -81940 | -81940
8004 | Other Indirects | 8104 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | 41500 | m3 |  |  |  |  | 68 |  |  |  |  | 2822000 | 0 | 0 | 100% | 0% | 0% | 100% | 2822000 | 0 | 0 | 2822000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 564400 | 564400 | 564400 | 282200 | 282200 | 282200 | 141100 | 141100
8004 | Other Indirects | 8104 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | -41500 | m3 |  |  |  |  | 68 |  |  |  |  | -2822000 | 0 | 0 | 100% | 0% | 0% | 100% | -2822000 | 0 | 0 | -2822000 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -564400 | -564400 | -564400 | -282200 | -282200 | -282200 | -141100 | -141100
8005 | Other Indirects | 8105 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | 25100 | m3 |  |  |  |  | 68 |  |  |  |  | 1706800 | 0 | 0 | 100% | 0% | 0% | 100% | 1706800 | 0 | 0 | 1706800 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 341360 | 341360 | 341360 | 170680 | 170680 | 170680 | 85340 | 85340
8005 | Other Indirects | 8105 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | -9926 | m3 |  |  |  |  | 68 |  |  |  |  | -674968 | 0 | 0 | 100% | 0% | 0% | 100% | -674968 | 0 | 0 | -674968 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -134993.6 | -134993.6 | -134993.6 | -67496.8 | -67496.8 | -67496.8 | -33748.4 | -33748.4
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 270000 | 0 | 0 | 100% | 0% | 0% | 100% | 270000 | 0 | 0 | 270000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 54000 | 54000 | 54000 | 27000 | 27000 | 27000 | 13500 | 13500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 6000 | 6000 | 6000 | 3000 | 3000 | 3000 | 1500 | 1500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 18000 | 0 | 0 | 100% | 0% | 0% | 100% | 18000 | 0 | 0 | 18000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 3600 | 3600 | 3600 | 1800 | 1800 | 1800 | 900 | 900
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 477000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 457393.5825 | 19606.4175 | 0 | 477000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 95400 | 95400 | 95400 | 47700 | 47700 | 47700 | 23850 | 23850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 266000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 255066.4423 | 10933.5577 | 0 | 266000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 53200 | 53200 | 53200 | 26600 | 26600 | 26600 | 13300 | 13300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 474000 | 0 | 0 | 100% | 0% | 0% | 100% | 474000 | 0 | 0 | 474000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 94800 | 94800 | 94800 | 47400 | 47400 | 47400 | 23700 | 23700
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | -33000 | 0 | 0 | 100% | 0% | 0% | 100% | -33000 | 0 | 0 | -33000 | Type A 2AM-MRY1325 | removed | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -6600 | -6600 | -6600 | -3300 | -3300 | -3300 | -1650 | -1650
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 177000 | 0 | 0 | 100% | 0% | 0% | 100% | 177000 | 0 | 0 | 177000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 35400 | 35400 | 35400 | 17700 | 17700 | 17700 | 8850 | 8850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 1969000 | 0 | 0 | 100% | 0% | 0% | 100% | 1969000 | 0 | 0 | 1969000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 656333.3333 | 656333.3333 | 656333.3333 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  |  | Indirect | Indirect |  |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | -91000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | -88920.0113 | -2079.9887 | 0 | -91000 | Type A 2AM-MRY1325 | removed | 2018-MAY | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | -18200 | -18200 | -18200 | -9100 | -9100 | -9100 | -4550 | -4550
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 1652000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 1614240.205 | 37759.795 | 0 | 1652000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 330400 | 330400 | 330400 | 165200 | 165200 | 165200 | 82600 | 82600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 125296.655 | 0 | 0 | 100% | 0% | 0% | 100% | 125296.655 | 0 | 0 | 125296.655 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 25059.331 | 25059.331 | 25059.331 | 12529.6655 | 12529.6655 | 12529.6655 | 6264.8327 | 6264.8327
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 78000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 61503.0955 | 16496.9045 | 0 | 78000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 15600 | 15600 | 15600 | 7800 | 7800 | 7800 | 3900 | 3900
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 117000 | 0 | 0 | 100% | 0% | 0% | 100% | 117000 | 0 | 0 | 117000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 23400 | 23400 | 23400 | 11700 | 11700 | 11700 | 5850 | 5850
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 115000 | 0 | 0 | 100% | 0% | 0% | 100% | 115000 | 0 | 0 | 115000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 23000 | 23000 | 23000 | 11500 | 11500 | 11500 | 5750 | 5750
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 1206000 | 0 | 0 | 100% | 0% | 0% | 100% | 1206000 | 0 | 0 | 1206000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 241200 | 241200 | 241200 | 120600 | 120600 | 120600 | 60300 | 60300
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 152000 | 0 | 0 | 100% | 0% | 0% | 100% | 152000 | 0 | 0 | 152000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 30400 | 30400 | 30400 | 15200 | 15200 | 15200 | 7600 | 7600
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 739000 | 0 | 0 | 100% | 0% | 0% | 100% | 739000 | 0 | 0 | 739000 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 147800 | 147800 | 147800 | 73900 | 73900 | 73900 | 36950 | 36950
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 48000 | 0 | 0 | 100% | 0% | 0% | 100% | 48000 | 0 | 0 | 48000 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 9600 | 9600 | 9600 | 4800 | 4800 | 4800 | 2400 | 2400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 728000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 698076.5788 | 29923.4212 | 0 | 728000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 145600 | 145600 | 145600 | 72800 | 72800 | 72800 | 36400 | 36400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 485000 | 0 | 0 | 100% | 0% | 0% | 100% | 485000 | 0 | 0 | 485000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 20% | 20% | 20% | 10% | 10% | 10% | 5% | 5% | 0 |  | 97000 | 97000 | 97000 | 48500 | 48500 | 48500 | 24250 | 24250
9000 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts | 9120 | Project Management | 9121 | Owner Accounts - Project Management |  |  |  |  | Indirect | [16 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  |  | Indirect | [10 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 2444000 | 0 | 0 | 97.71% | 2.286% | 0% | 100% | 2388137.4461 | 55862.5539 | 0 | 2444000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 100% | [7 empty] | 0 |  | 2444000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 218000 | 0 | 0 | 100% | 0% | 0% | 100% | 218000 | 0 | 0 | 218000 | Type A 2AM-MRY1325 |  | 2015 | Indirect |  |  | 100% | [7 empty] | 0 |  | 218000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 78000 | 0 | 0 | 78.85% | 21.15% | 0% | 100% | 61503.0955 | 16496.9045 | 0 | 78000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 100% | [7 empty] | 0 |  | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 168000 | 0 | 0 | 100% | 0% | 0% | 100% | 168000 | 0 | 0 | 168000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 100% | [7 empty] | 0 |  | 168000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 137000 | 0 | 0 | 93.32% | 6.68% | 0% | 100% | 127848.1359 | 9151.8641 | 0 | 137000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 100% | [7 empty] | 0 |  | 137000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 3310000 | 0 | 0 | 93.32% | 6.68% | 0% | 100% | 3088885.6192 | 221114.3808 | 0 | 3310000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [7 empty] | 0 |  | 3310000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 153000 | 0 | 0 | 100% | 0% | 0% | 100% | 153000 | 0 | 0 | 153000 | Type A 2AM-MRY1325 | Added | 2018-C2 | Indirect |  |  | 100% | [7 empty] | 0 |  | 153000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | -1346000 | 0 | 0 | 100% | 0% | 0% | 100% | -1346000 | 0 | 0 | -1346000 | Type A 2AM-MRY1325 | Removed | 2018-MAY | Indirect |  |  | 100% | [7 empty] | 0 |  | -1346000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 2162635.1051 | 0 | 0 | 100% | 0% | 0% | 100% | 2162635.1051 | 0 | 0 | 2162635.1051 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 100% | [7 empty] | 0 |  | 2162635.1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 49501.3617 | 0 | 0 | 100% | 0% | 0% | 100% | 49501.3617 | 0 | 0 | 49501.3617 | Type A 2AM-MRY1325 |  | 2015 A | Indirect |  |  | 100% | [7 empty] | 0 |  | 49501.3617 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 781000 | 0 | 0 | 95.89% | 4.11% | 0% | 100% | 748898.088 | 32101.912 | 0 | 781000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 100% | [7 empty] | 0 |  | 781000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 846000 | 0 | 0 | 100% | 0% | 0% | 100% | 846000 | 0 | 0 | 846000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 100% | [7 empty] | 0 |  | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0