## Estimate Details
'Mary River Project - Complete Project Security Assesment - Estimate Breakdown Structure'
Updated November 6, 2020
[44 empty] | C&M |  | Closure |  |  | Post Closure | [7 empty] | C&M |  | Closure |  |  | Post Closure
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 0 - % | Year 0+1 - % | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 16 - % | Year 17 - % | Year 18 - % | Year 0- Cost ($) | Year 0+1- Cost ($) | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Year 16 - Cost ($) | Year 17 - Cost ($) | Year 18 - Cost ($)
1000 | Project Wide
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2014 |  | 11787.5421 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 2973.2734 | 23894.3714 | 195856.7782 | 261856.1111 | 457712.8893 | 0 | 0 | 100% | 0% | 0% | 100% | 457712.8893 | 0 | 0 | 457712.8893 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 457712.8893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 |  | 378 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 95.3462 | 766.2388 | 6280.687 | 8397.1374 | 14677.8244 | 0 | 0 | 100% | 0% | 0% | 100% | 14677.8244 | 0 | 0 | 14677.8244 | Type A 2AM-MRY1325 | Modified | 2015 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 14677.8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2016 |  | 133.6667 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 33.7159 | 270.9539 | 2220.9484 | 2969.3581 | 5190.3065 | 0 | 0 | 100% | 0% | 0% | 100% | 5190.3065 | 0 | 0 | 5190.3065 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 5190.3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables - addition of 49 person camp |  | 49 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 34339.2445 | 0 | 0 | 34339.2445 | 0 | 0 | 100% | 0% | 0% | 100% | 34339.2445 | 0 | 0 | 34339.2445 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 34339.2445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017 |  | 719.1667 | ea | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 181.4016 | 1457.8133 | 11949.367 | 15976.0352 | 27925.4022 | 0 | 0 | 100% | 0% | 0% | 100% | 27925.4022 | 0 | 0 | 27925.4022 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 27925.4022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2021 & 2021-R |  | 1292.274 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 325.9614 | 2619.5515 | 21471.8737 | 28707.4126 | 50179.2863 | 0 | 0 | 100% | 0% | 0% | 100% | 50179.2863 | 0 | 0 | 50179.2863 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 50179.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2020-AR |  | -1050.6667 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | -265.0187 | -2129.7926 | -17457.4298 | -23340.1913 | -40797.6212 | 0 | 0 | 100% | 0% | 0% | 100% | -40797.6212 | 0 | 0 | -40797.6212 | Type A 2AM-MRY1325 | Added | 2020-AR | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | -40797.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2020 & 2020-R |  | 508.128 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 128.1695 | 1030.0197 | 8442.8392 | 11287.8863 | 19730.7255 | 0 | 0 | 100% | 0% | 0% | 100% | 19730.7255 | 0 | 0 | 19730.7255 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 19730.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2019 & 2019-R |  | 8036.4697 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 2027.1081 | 16290.622 | 133530.5582 | 178527.3556 | 312057.9138 | 0 | 0 | 100% | 0% | 0% | 100% | 312057.9138 | 0 | 0 | 312057.9138 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 312057.9138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C1 & 2018-R |  | 1517.3333 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 382.7301 | 3075.7664 | 25211.3644 | 33707.0276 | 58918.392 | 0 | 0 | 100% | 0% | 0% | 100% | 58918.392 | 0 | 0 | 58918.392 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 58918.392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C2 |  | 121.5447 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 30.6583 | 246.3817 | 2019.5352 | 2700.0732 | 4719.6084 | 0 | 0 | 100% | 0% | 0% | 100% | 4719.6084 | 0 | 0 | 4719.6084 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 4719.6084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 A |  | 8.0269 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 2.0247 | 16.2712 | 133.371 | 178.3141 | 311.6851 | 0 | 0 | 100% | 0% | 0% | 100% | 311.6851 | 0 | 0 | 311.6851 | Type A 2AM-MRY1325 | Modified | 2015 A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 311.6851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables |  | 550 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 385440.5 | 0 | 0 | 385440.5 | 0 | 0 | 100% | 0% | 0% | 100% | 385440.5 | 0 | 0 | 385440.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 385440.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - Shiploader |  | 5049 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1273.5528 | 10234.7614 | 83892.0334 | 112161.7634 | 196053.7968 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 196053.7968 | 0 | 196053.7968 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 196053.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 R |  | 64.3333 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 16.2274 | 130.4093 | 1068.9353 | 1429.1424 | 2498.0777 | 0 | 0 | 100% | 0% | 0% | 100% | 2498.0777 | 0 | 0 | 2498.0777 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2498.0777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017-A |  | 5455.56 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1376.1029 | 11058.8938 | 90647.2605 | 121193.3503 | 211840.6108 | 0 | 0 | 100% | 0% | 0% | 100% | 211840.6108 | 0 | 0 | 211840.6108 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 211840.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port
2000 | Milne Port | 2100 | General
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 001 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed - Demolish Building - ISO Shipping Container | 2110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed - Demolish and foundations - Gravel Base - Skidded Building | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 003 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed - Demolish floor finish - Raised Steel or Wooden Floor | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Disturbed Area @ Milne Port (adjacent to Steel Tank Farm) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 22423.6266 | 22423.6266 | 22423.6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Laydown Area |  | 37375 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 474.4697 | 5466.0938 | 35585.2269 | 14820.8823 | 55872.2029 | 0 | 0 | 100% | 0% | 0% | 100% | 55872.2029 | 0 | 0 | 55872.2029 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 18624.0676 | 18624.0676 | 18624.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP3 |  | 131000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1663.0242 | 19158.75 | 124726.8153 | 51947.4403 | 195833.0056 | 0 | 0 | 100% | 0% | 0% | 100% | 195833.0056 | 0 | 0 | 195833.0056 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 65277.6685 | 65277.6685 | 65277.6685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP5 |  | 65000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 825.1647 | 9506.25 | 61887.3511 | 25775.4475 | 97169.0486 | 0 | 0 | 100% | 0% | 0% | 100% | 97169.0486 | 0 | 0 | 97169.0486 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 32389.6829 | 32389.6829 | 32389.6829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 32000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 406.2349 | 4680 | 30467.619 | 12689.4511 | 47837.0701 | 0 | 0 | 100% | 0% | 0% | 100% | 47837.0701 | 0 | 0 | 47837.0701 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15945.69 | 15945.69 | 15945.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP7 |  | 21000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 266.5917 | 3071.25 | 19994.375 | 8327.4523 | 31393.0772 | 0 | 0 | 100% | 0% | 0% | 100% | 31393.0772 | 0 | 0 | 31393.0772 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10464.3591 | 10464.3591 | 10464.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | -13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -165.0329 | -1901.25 | -12377.4702 | -5155.0895 | -19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | -19433.8097 | 0 | 0 | -19433.8097 | Type A 2AM-MRY1325 | Removed | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -6477.9366 | -6477.9366 | -6477.9366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 30000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 380.8452 | 4387.5 | 28563.3928 | 11896.3604 | 44847.2532 | 0 | 0 | 100% | 0% | 0% | 100% | 44847.2532 | 0 | 0 | 44847.2532 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14949.0844 | 14949.0844 | 14949.0844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6477.9366 | 6477.9366 | 6477.9366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP4 |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6477.9366 | 6477.9366 | 6477.9366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP6 |  | 7000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 88.8639 | 1023.75 | 6664.7917 | 2775.8174 | 10464.3591 | 0 | 0 | 100% | 0% | 0% | 100% | 10464.3591 | 0 | 0 | 10464.3591 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3488.1197 | 3488.1197 | 3488.1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Module Road 2018 |  | 13300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 168.8414 | 1945.125 | 12663.1041 | 5274.0531 | 19882.2822 | 0 | 0 | 100% | 0% | 0% | 100% | 19882.2822 | 0 | 0 | 19882.2822 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6627.4274 | 6627.4274 | 6627.4274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Q1 Access Road |  | 1200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 15.2338 | 175.5 | 1142.5357 | 475.8544 | 1793.8901 | 0 | 0 | 100% | 0% | 0% | 100% | 1793.8901 | 0 | 0 | 1793.8901 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 597.9634 | 597.9634 | 597.9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Surface Water Management Diversion Berms & Ditching |  | 9500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 120.601 | 1389.375 | 9045.0744 | 3767.1808 | 14201.6302 | 0 | 0 | 100% | 0% | 0% | 100% | 14201.6302 | 0 | 0 | 14201.6302 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4733.8767 | 4733.8767 | 4733.8767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2136 | Milne Port |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 14306 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 181.6124 | 2092.2525 | 13620.9299 | 5672.9777 | 21386.1601 | 0 | 0 | 100% | 0% | 0% | 100% | 21386.1601 | 0 | 0 | 21386.1601 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7128.72 | 7128.72 | 7128.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 12148.5 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 154.2233 | 1776.7181 | 11566.7459 | 4817.4311 | 18160.8952 | 0 | 0 | 100% | 0% | 0% | 100% | 18160.8952 | 0 | 0 | 18160.8952 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6053.6317 | 6053.6317 | 6053.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2134 |  |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad @ Milne Port |  | 66536 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 844.664 | 9730.89 | 63349.7968 | 26384.5411 | 99465.2279 | 0 | 0 | 100% | 0% | 0% | 100% | 99465.2279 | 0 | 0 | 99465.2279 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33155.076 | 33155.076 | 33155.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | 8 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 341.8 | 3765 | 25635 | 37650 | 67050 | 30 | 240 | 100% | 0% | 0% | 100% | 67050 | 0 | 0 | 67050 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 22350 | 22350 | 22350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | -8 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -341.8 | -3765 | -25635 | -37650 | -67050 | 30 | -240 | 100% | 0% | 0% | 100% | -67050 | 0 | 0 | -67050 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -22350 | -22350 | -22350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | 3 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 128.175 | 1411.875 | 9613.125 | 14118.75 | 25143.75 | 30 | 90 | 100% | 0% | 0% | 100% | 25143.75 | 0 | 0 | 25143.75 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8381.25 | 8381.25 | 8381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | -3 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -128.175 | -1411.875 | -9613.125 | -14118.75 | -25143.75 | 30 | -90 | 100% | 0% | 0% | 100% | -25143.75 | 0 | 0 | -25143.75 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -8381.25 | -8381.25 | -8381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2793.75 | 2793.75 | 2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2793.75 | 2793.75 | 2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2793.75 | -2793.75 | -2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | 10,000 Gallon tank (gas and diesel) |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5587.5 | 5587.5 | 5587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 4 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 170.9 | 1882.5 | 12817.5 | 18825 | 33525 | 30 | 120 | 100% | 0% | 0% | 100% | 33525 | 0 | 0 | 33525 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11175 | 11175 | 11175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2793.75 | 2793.75 | 2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2793.75 | -2793.75 | -2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 1,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | [10 empty] | 0 | 0 | -2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 9,000L |  | -1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -15.5 | -162.5 | -1162.5 | -1625 | -2950 | 20 | -20 | 100% | 0% | 0% | 100% | -2950 | 0 | 0 | -2950 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | [10 empty] | 0 | 0 | -1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 5 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 77.5 | 812.5 | 5812.5 | 8125 | 14750 | 20 | 100 | 100% | 0% | 0% | 100% | 14750 | 0 | 0 | 14750 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | [10 empty] | 0 | 0 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 31 | 325 | 2325 | 3250 | 5900 | 20 | 40 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | [10 empty] | 0 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | [10 empty] | 0 | 0 | -2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK, DOUBLE WALLED 2494 LITER |  | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 983.3333 | 983.3333 | 983.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 4400 GAL STAINLESS STEEL WATER TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | SEWAGE TANK SERAIL # ST111-0716 |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | WATER TANK SERIAL # WT110-0070 |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 213.625 | 2353.125 | 16021.875 | 23531.25 | 41906.25 | 30 | 150 | 100% | 0% | 0% | 100% | 41906.25 | 0 | 0 | 41906.25 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13968.75 | 13968.75 | 13968.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 77.5 | 812.5 | 5812.5 | 8125 | 14750 | 20 | 100 | 100% | 0% | 0% | 100% | 14750 | 0 | 0 | 14750 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7375 | 7375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development |  | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 12 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 72 | 450 | 5400 | 4500 | 10350 | 0 | 0 | 100% | 0% | 0% | 100% | 10350 | 0 | 0 | 10350 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 5175 | 5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 099 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Dock Office - Demolish and Decontaminate Building - Trailer - Single | 2223-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 100 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Dock Office - Demolish and foundations - Gravel Base - Skidded Building | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 101 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Dock Office - Demolish floor finish - Raised Steel or Wooden Floor | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | CONVEYING - RECLAIM CONVEYOR - FAM L: 850000, W: 1524, H: 47000 VERTICAL LIFT SEE REMARKS kg | 2342-CV-001 | 1 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 1020 | 1020 | 100% | 0% | 0% | 100% | 1066410 | 0 | 0 | 1066410 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 355470 | 355470 | 355470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A |  |  |  |  | Shiploading E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Shiploading E-House - Demolish and foundations - Gravel Base - Skidded Building | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Shiploading E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 130 | MT- |  | #N/A |  |  |  |  | RECLAIM CONVEYOR | 2342-MT-001 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | 0.16667 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | 836.4 | 10455 | 62730 | 104550 | 177735 | 1020 | 170 | 100% | 0% | 0% | 100% | 177735 | 0 | 0 | 177735 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 59245 | 59245 | 59245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | -0.16667 | Ea | 5018.4 | 62730 | 376380 | 627300 | 1066410 | -836.4 | -10455 | -62730 | -104550 | -177735 | 1020 | -170 | 100% | 0% | 0% | 100% | -177735 | 0 | 0 | -177735 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -59245 | -59245 | -59245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown |  | 230545.88 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2926.7433 | 33717.3349 | 219505.7511 | 91421.8957 | 344644.9817 | 0 | 0 | 100% | 0% | 0% | 100% | 344644.9817 | 0 | 0 | 344644.9817 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 114881.6606 | 114881.6606 | 114881.6606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Footprints |  | 128865.8 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1635.9309 | 18846.6233 | 122694.8155 | 51101.1332 | 192642.572 | 0 | 0 | 100% | 0% | 0% | 100% | 192642.572 | 0 | 0 | 192642.572 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 64214.1907 | 64214.1907 | 64214.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion |  | 82000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1040.977 | 11992.5 | 78073.2737 | 32516.7184 | 122582.492 | 0 | 0 | 100% | 0% | 0% | 100% | 122582.492 | 0 | 0 | 122582.492 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 40860.8307 | 40860.8307 | 40860.8307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion 2019 |  | 140000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1777.2778 | 20475 | 133295.8331 | 55516.3484 | 209287.1815 | 0 | 0 | 100% | 0% | 0% | 100% | 209287.1815 | 0 | 0 | 209287.1815 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 69762.3938 | 69762.3938 | 69762.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown - Realignment of the shipload conveyor |  | 26000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 330.0659 | 3802.5 | 24754.9404 | 10310.179 | 38867.6194 | 0 | 0 | 100% | 0% | 0% | 100% | 38867.6194 | 0 | 0 | 38867.6194 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12955.8731 | 12955.8731 | 12955.8731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional sealift laydown area |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Settling Ponds |  | 11423.76 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 508.2984 | 1943.1816 | 38122.3791 | 7254.6056 | 47320.1663 | 0 | 0 | 100% | 0% | 0% | 100% | 47320.1663 | 0 | 0 | 47320.1663 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15773.3888 | 15773.3888 | 15773.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation - New 2019 |  | 15000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 667.4226 | 2551.5 | 50056.6964 | 9525.6802 | 62133.8766 | 0 | 0 | 100% | 0% | 0% | 100% | 62133.8766 | 0 | 0 | 62133.8766 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20711.2922 | 20711.2922 | 20711.2922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 2a |  | 4400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 195.7773 | 748.44 | 14683.2976 | 2794.1995 | 18225.9371 | 0 | 0 | 100% | 0% | 0% | 100% | 18225.9371 | 0 | 0 | 18225.9371 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6075.3124 | 6075.3124 | 6075.3124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 1a |  | 5000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 222.4742 | 850.5 | 16685.5655 | 3175.2267 | 20711.2922 | 0 | 0 | 100% | 0% | 0% | 100% | 20711.2922 | 0 | 0 | 20711.2922 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6903.7641 | 6903.7641 | 6903.7641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | VP6 | VENDOR PKG - Ship Loader | VP6 | Packaged Facilities | Ship Loader |  | Shiploader Package | 2351-SL-001 | 0 | Lot | 14448 | 180600 | 1083600 | 1806000 | 3070200 | 0 | 0 | 0 | 0 | 0 | 30295 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and Decontaminate Building - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and foundations - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish floor finish - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and Decontaminate Building - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and foundations - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish floor finish - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 152 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER PROPORTIONAL GATE - FAM | 2351-CH-003 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 153 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-004 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 154 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-005 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 155 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-006 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 156 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE - FAM | 2351-CH-008 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 157 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-009 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 158 | CV- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CONVEYING - SHIPLOADER LINK CONVEYOR - FAM 212330 kg | 2351-CV-007 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 159 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DRIVE | 2351-MT-007A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 160 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR BRAKE | 2351-MT-007B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 161 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE | 2351-MT-007C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 162 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN | 2351-MT-007D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 163 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR | 2351-MT-007E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 164 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 165 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 166 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM 1960000 kg | 2351-SL-001 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 167 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-001A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 170 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-001B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 171 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-001C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 172 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 173 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 174 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 175 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 176 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-001H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 177 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-001J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 178 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-001K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 179 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE FAN | 2351-MT-001L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 180 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-001M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 181 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-001N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 182 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 183 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 184 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 185 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 186 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 187 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 193 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM | 2351-SL-002 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 194 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-002A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 197 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-002B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 198 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-002C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 199 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 200 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 201 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 202 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 203 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-002H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 204 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-002J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 205 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-002K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 206 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE BRAKE | 2351-MT-002L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 207 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-002M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 208 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-002N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 209 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 210 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 211 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 212 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 213 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 214 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 168 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-001AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 169 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-001AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 188 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-001V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 189 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-001W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 190 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-001X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 191 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-001Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 192 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-001Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 195 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-002AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 196 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-002AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 215 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-002V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 216 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-002W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 217 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-002X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 218 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-002Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 219 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-002Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome
2000 | Milne Port | 2500 | Non Process Facilities
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 237 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 240 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 243 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 246 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 238 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BA - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 239 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BA - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 241 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BB - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 242 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BB - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 244 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BC - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 245 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BC - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 247 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BD - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 248 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BD - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Offices, washcars for Laydown R3 62 @ 15m2 3 @ 30m2 3 @ 66m2 |  | 1218 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 682.5875 | 3412.9375 | 51194.0625 | 85323.4375 | 139930.4375 | 1 | 1218 | 100% | 0% | 0% | 100% | 139930.4375 | 0 | 0 | 139930.4375 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 46643.4792 | 46643.4792 | 46643.4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BE - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BE - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BF - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BF - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 1 | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Pre-Cast Concrete Foundations (Mobilized to Site) |  | 8000 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 1000 | 15000 | 75000 | 150000 | 240000 | 0 | 0 | 100% | 0% | 0% | 100% | 240000 | 0 | 0 | 240000 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 80000 | 80000 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 48.42 | 605.25 | 3631.5 | 6052.5 | 10289.25 | 1 | 216 | 100% | 0% | 0% | 100% | 10289.25 | 0 | 0 | 10289.25 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3429.75 | 3429.75 | 3429.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 380 person camp at Milne Port |  | 380 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 266304.3455 | 0 | 0 | 266304.3455 | 0 | 0 | 100% | 0% | 0% | 1 | 266304.3455 | 0 | 0 | 266304.3455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 266304.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 380 man temporary hardwall camp at Milne Port inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 10,720 m2) |  | 10720 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 2403.0667 | 30038.3333 | 180230 | 300383.3333 | 510651.6667 | 1 | 10720 | 100% | 0% | 0% | 100% | 510651.6667 | 0 | 0 | 510651.6667 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 170217.2222 | 170217.2222 | 170217.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Offices, washcars (assume 16 units @ 36 m2 per wash car) |  | 576 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 129.12 | 1614 | 9684 | 16140 | 27438 | 1 | 576 | 100% | 0% | 0% | 100% | 27438 | 0 | 0 | 27438 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9146 | 9146 | 9146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Carpenter Workshop |  | 100 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 15.6917 | 196.1458 | 1176.875 | 1961.4583 | 3334.4792 | 1 | 100 | 100% | 0% | 0% | 100% | 3334.4792 | 0 | 0 | 3334.4792 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1111.4931 | 1111.4931 | 1111.4931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 43.75 | 546.875 | 3281.25 | 5468.75 | 9296.875 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 9296.875 | 0 | 0 | 9296.875 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3098.9583 | 3098.9583 | 3098.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 254 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 2513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 40.485 | 506.0629 | 3036.3774 | 5060.629 | 8603.0693 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 8603.0693 | 0 | 0 | 8603.0693 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2867.6898 | 2867.6898 | 2867.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 255 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 2513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 34.8513 | 522.7695 | 2613.8476 | 5227.6952 | 8364.3123 | 0 | 0 | 100% | 0% | 0% | 100% | 8364.3123 | 0 | 0 | 8364.3123 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2788.1041 | 2788.1041 | 2788.1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 265 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2513-TK-003 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | ff3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) |  |  | Aecon Workshop |  | 1650 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 295.9 | 3698.75 | 22192.5 | 36987.5 | 62878.75 | 0.5 | 825 | 100% | 0% | 0% | 100% | 62878.75 | 0 | 0 | 62878.75 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20959.5833 | 20959.5833 | 20959.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Sana Workshop |  | 500 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 112.0833 | 1401.0417 | 8406.25 | 14010.4167 | 23817.7083 | 1 | 500 | 100% | 0% | 0% | 100% | 23817.7083 | 0 | 0 | 23817.7083 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7939.2361 | 7939.2361 | 7939.2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers (2 units at 36 m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Crusher services trailer |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Site Contruction Office |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Offices and Lunchrooms (5 @ 36m2) |  | 180 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 40.35 | 504.375 | 3026.25 | 5043.75 | 8574.375 | 1 | 180 | 100% | 0% | 0% | 100% | 8574.375 | 0 | 0 | 8574.375 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2858.125 | 2858.125 | 2858.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 20 | 250 | 1500 | 2500 | 4250 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4250 | 0 | 0 | 4250 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 267 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 2513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 266 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613, W: 737, H: 1676 | 2513-TK-004 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 251 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 2513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 11 | 87.5 | 525 | 875 | 1487.5 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1487.5 | 0 | 0 | 1487.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 495.8333 | 495.8333 | 495.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 2513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 227 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 1388.4758 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 311.25 | 3890.625 | 23343.75 | 38906.25 | 66140.625 | 1 | 1388.4758 | 100% | 0% | 0% | 100% | 66140.625 | 0 | 0 | 66140.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 22046.875 | 22046.875 | 22046.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 233 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 95 | 1187.5 | 7125 | 11875 | 20187.5 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 20187.5 | 0 | 0 | 20187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6729.1667 | 6729.1667 | 6729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 230 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-002 | 334.5725 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 75 | 937.5 | 5625 | 9375 | 15937.5 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 15937.5 | 0 | 0 | 15937.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5312.5 | 5312.5 | 5312.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 231 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 232 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 234 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 235 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 228 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 229 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Change Rooms - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Change Rooms - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Change Rooms - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Camp Pad development (Milne Port) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 22423.6266 | 22423.6266 | 22423.6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash (Repurposed Warehouse) - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2523-BLD-001 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash (Repurposed Warehouse) - Demolish and foundations - Precast Footing (Perimeter Beam) | 2523-BLD-001 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash (Repurposed Warehouse) - Demolish floor finish - Gravel | 2523-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | 150000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1904.2262 | 21937.5 | 142816.9641 | 59481.8019 | 224236.2659 | 0 | 0 | 100% | 0% | 0% | 100% | 224236.2659 | 0 | 0 | 224236.2659 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 74745.422 | 74745.422 | 74745.422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | -150000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -1904.2262 | -21937.5 | -142816.9641 | -59481.8019 | -224236.2659 | 0 | 0 | 100% | 0% | 0% | 100% | -224236.2659 | 0 | 0 | -224236.2659 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -74745.422 | -74745.422 | -74745.422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W1 |  | 23100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 293.2508 | 3378.375 | 21993.8125 | 9160.1975 | 34532.385 | 0 | 0 | 100% | 0% | 0% | 100% | 34532.385 | 0 | 0 | 34532.385 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11510.795 | 11510.795 | 11510.795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W6 |  | 2750 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 34.9108 | 402.1875 | 2618.311 | 1090.4997 | 4110.9982 | 0 | 0 | 100% | 0% | 0% | 100% | 4110.9982 | 0 | 0 | 4110.9982 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1370.3327 | 1370.3327 | 1370.3327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W7 |  | 1780 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 22.5968 | 260.325 | 1694.7613 | 705.8507 | 2660.937 | 0 | 0 | 100% | 0% | 0% | 100% | 2660.937 | 0 | 0 | 2660.937 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 886.979 | 886.979 | 886.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W3 |  | 14300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 181.5362 | 2091.375 | 13615.2172 | 5670.5984 | 21377.1907 | 0 | 0 | 100% | 0% | 0% | 100% | 21377.1907 | 0 | 0 | 21377.1907 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7125.7302 | 7125.7302 | 7125.7302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W14 |  | 8850 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 112.3493 | 1294.3125 | 8426.2009 | 3509.4263 | 13229.9397 | 0 | 0 | 100% | 0% | 0% | 100% | 13229.9397 | 0 | 0 | 13229.9397 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4409.9799 | 4409.9799 | 4409.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W15 |  | 10950 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 139.0085 | 1601.4375 | 10425.6384 | 4342.1715 | 16369.2474 | 0 | 0 | 100% | 0% | 0% | 100% | 16369.2474 | 0 | 0 | 16369.2474 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5456.4158 | 5456.4158 | 5456.4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W10B |  | 12450 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 158.0508 | 1820.8125 | 11853.808 | 4936.9896 | 18611.6101 | 0 | 0 | 100% | 0% | 0% | 100% | 18611.6101 | 0 | 0 | 18611.6101 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6203.87 | 6203.87 | 6203.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W11 |  | 7550 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 95.8461 | 1104.1875 | 7188.4539 | 2993.9174 | 11286.5587 | 0 | 0 | 100% | 0% | 0% | 100% | 11286.5587 | 0 | 0 | 11286.5587 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3762.1862 | 3762.1862 | 3762.1862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 270 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-001 | 892.1933 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 500 | 1750 | 37500 | 62500 | 101750 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 101750 | 0 | 0 | 101750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33916.6667 | 33916.6667 | 33916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 276 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2521-BLD-003 | 267.658 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 150 | 750 | 11250 | 18750 | 30750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 30750 | 0 | 0 | 30750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10250 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 271 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-001 | 892.1933 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 129.5521 | 1619.4013 | 9716.4077 | 16194.0128 | 27529.8218 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 27529.8218 | 0 | 0 | 27529.8218 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9176.6073 | 9176.6073 | 9176.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 272 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-001 | 892.1933 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 111.5242 | 1672.8625 | 8364.3123 | 16728.6245 | 26765.7993 | 0 | 0 | 100% | 0% | 0% | 100% | 26765.7993 | 0 | 0 | 26765.7993 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8921.9331 | 8921.9331 | 8921.9331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 273 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-002 | 148.6989 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 83.3333 | 291.6667 | 6250 | 10416.6667 | 16958.3333 | 1 | 148.6989 | 100% | 0% | 0% | 100% | 16958.3333 | 0 | 0 | 16958.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5652.7778 | 5652.7778 | 5652.7778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 296 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 2521.5-P | 255 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 63.75 | 796.875 | 4781.25 | 7968.75 | 13546.875 | 0.01 | 2.55 | 100% | 0% | 100% | 0% | 13546.875 | 0 | 13546.875 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4515.625 | 4515.625 | 4515.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 295 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2521-TK-053 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar for Ore Pad |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 2521-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 294 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803, W: 1245, H: 1346 | 2521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 280 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 274 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-002 | 148.6989 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 21.592 | 269.9002 | 1619.4013 | 2699.0021 | 4588.3036 | 0.75 | 111.5242 | 100% | 0% | 0% | 100% | 4588.3036 | 0 | 0 | 4588.3036 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1529.4345 | 1529.4345 | 1529.4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 277 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-003 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 275 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade | 2521-BLD-002 | 148.6989 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 18.5874 | 278.8104 | 1394.052 | 2788.1041 | 4460.9665 | 0 | 0 | 100% | 0% | 0% | 100% | 4460.9665 | 0 | 0 | 4460.9665 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1486.9888 | 1486.9888 | 1486.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 292 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 293 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 281 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 278 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-003 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Anmar Workshop |  | 1670 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 74.3064 | 284.067 | 5572.9789 | 1060.5257 | 6875.257 | 0 | 0 | 100% | 0% | 0% | 100% | 6875.257 | 0 | 0 | 6875.257 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2291.7523 | 2291.7523 | 2291.7523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-005 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-005 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-005 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2- Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-006 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2- Demolish floor finish - Slab on grade | 2521-BLD-006 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 91.0364 | 348.0246 | 6827.7334 | 1299.3028 | 8475.0608 | 0 | 0 | 100% | 0% | 0% | 100% | 8475.0608 | 0 | 0 | 8475.0608 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2825.0203 | 2825.0203 | 2825.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 301 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 2522-SQ-004 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 306 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 2522-SQ-011 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 313 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-026 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 314 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-027 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 351 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-009 | 75.2788 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 42.1875 | 210.9375 | 3164.0625 | 5273.4375 | 8648.4375 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 8648.4375 | 0 | 0 | 8648.4375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2882.8125 | 2882.8125 | 2882.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 354 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-010 | 75.2788 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 42.1875 | 210.9375 | 3164.0625 | 5273.4375 | 8648.4375 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 8648.4375 | 0 | 0 | 8648.4375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2882.8125 | 2882.8125 | 2882.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 327 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 330 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 333 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 336 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 339 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 342 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 345 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-007 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 348 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-008 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 357 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 2530-BLD-011 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1138.8889 | 1138.8889 | 1138.8889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 358 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 359 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 328 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 329 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 331 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 332 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 334 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 335 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 337 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 338 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 340 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 341 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 343 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 344 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 346 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 347 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 349 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 350 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 352 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 353 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 355 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 356 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-002 | 56 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 8.7873 | 109.8417 | 659.05 | 1098.4167 | 1867.3083 | 1 | 56 | 100% | 0% | 0% | 100% | 1867.3083 | 0 | 0 | 1867.3083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 622.4361 | 622.4361 | 622.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-002 | 56 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.1316 | 101.6444 | 609.8665 | 1016.4442 | 1727.9551 | 0.75 | 42 | 100% | 0% | 0% | 100% | 1727.9551 | 0 | 0 | 1727.9551 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 575.985 | 575.985 | 575.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 4.4833 | 56.0417 | 336.25 | 560.4167 | 952.7083 | 1 | 20 | 100% | 0% | 0% | 100% | 952.7083 | 0 | 0 | 952.7083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 317.5694 | 317.5694 | 317.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical office - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical office - Demolish floor finish - Gravel | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 2530-BLD-BIM-002 | 56 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 361 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 250 | 875 | 18750 | 31250 | 50875 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 50875 | 0 | 0 | 50875 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16958.3333 | 16958.3333 | 16958.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 362 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 64.7761 | 809.7006 | 4858.2038 | 8097.0064 | 13764.9109 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 13764.9109 | 0 | 0 | 13764.9109 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4588.3036 | 4588.3036 | 4588.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 363 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 2540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 55.7621 | 836.4312 | 4182.1561 | 8364.3123 | 13382.8996 | 0 | 0 | 100% | 0% | 0% | 100% | 13382.8996 | 0 | 0 | 13382.8996 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4460.9665 | 4460.9665 | 4460.9665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2540-VP-001 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 364 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1667 | 145.8333 | 2187.5 | 3645.8333 | 5979.1667 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 5979.1667 | 0 | 0 | 5979.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1993.0556 | 1993.0556 | 1993.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 374 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2540-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 371 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 2540-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 365 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 366 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 12933 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 575.4518 | 2199.9033 | 43158.8836 | 8213.0415 | 53571.8284 | 0 | 0 | 100% | 0% | 0% | 100% | 53571.8284 | 0 | 0 | 53571.8284 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 17857.2761 | 17857.2761 | 17857.2761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm at Milne Inlet - New waste management building |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Future Hazardous Waste Berm |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Hazardous Waste Berm |  | 0 | m2 | 0.0318 | 0.02385 | 2.385 | 0.2385 | 2.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Snow Dump |  | 3189 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 141.894 | 542.4489 | 10642.0537 | 2025.1596 | 13128.859 | 0 | 0 | 100% | 0% | 0% | 100% | 13128.859 | 0 | 0 | 13128.859 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4376.2863 | 4376.2863 | 4376.2863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Contaminated Snow dump/oily water containment - new 2019 |  | 2700 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 120.1361 | 459.27 | 9010.2054 | 1714.6224 | 11115.6849 | 0 | 0 | 100% | 0% | 0% | 100% | 11115.6849 | 0 | 0 | 11115.6849 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3705.2283 | 3705.2283 | 3705.2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste containment facilities 2020 Port Shop - 72m2 |  | 72 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 3.2036 | 12.2472 | 240.2721 | 45.7233 | 296.4183 | 0 | 0 | 100% | 0% | 0% | 100% | 296.4183 | 0 | 0 | 296.4183 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 98.8061 | 98.8061 | 98.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste Berm 2019 |  | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-1 | 2000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 88.9897 | 340.2 | 6674.2262 | 1270.0907 | 8233.8407 | 0 | 0 | 100% | 0% | 0% | 100% | 8233.8407 | 0 | 0 | 8233.8407 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2744.6136 | 2744.6136 | 2744.6136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-3 | 678 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 30.1675 | 115.3278 | 2262.5627 | 430.5607 | 2791.272 | 0 | 0 | 100% | 0% | 0% | 100% | 2791.272 | 0 | 0 | 2791.272 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 930.424 | 930.424 | 930.424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-5 | 652 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 29.0106 | 110.9052 | 2175.7977 | 414.0496 | 2684.2321 | 0 | 0 | 100% | 0% | 0% | 100% | 2684.2321 | 0 | 0 | 2684.2321 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 894.744 | 894.744 | 894.744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-4 | 597 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 26.5634 | 101.5497 | 1992.2565 | 379.1221 | 2457.8014 | 0 | 0 | 100% | 0% | 0% | 100% | 2457.8014 | 0 | 0 | 2457.8014 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 819.2671 | 819.2671 | 819.2671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-2 | 272 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 12.1026 | 46.2672 | 907.6948 | 172.7323 | 1119.8023 | 0 | 0 | 100% | 0% | 0% | 100% | 1119.8023 | 0 | 0 | 1119.8023 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 373.2674 | 373.2674 | 373.2674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-6 | 34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 1.5128 | 5.7834 | 113.4618 | 21.5915 | 139.9753 | 0 | 0 | 100% | 0% | 0% | 100% | 139.9753 | 0 | 0 | 139.9753 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 46.6584 | 46.6584 | 46.6584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 398 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-001 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 399 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-002 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 400 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-003 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 401 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-004 | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 68638.75 | 68638.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 402 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-005 | 1 | Ea | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 80 | 80 | 100% | 0% | 0% | 100% | 85157.5 | 0 | 0 | 85157.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 42578.75 | 42578.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 403 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-006 | 1 | Ea | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 418.6 | 4887.5 | 31395 | 48875 | 85157.5 | 80 | 80 | 100% | 0% | 0% | 100% | 85157.5 | 0 | 0 | 85157.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 42578.75 | 42578.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 387 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-014 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 384 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-013 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 854.1667 | 854.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 386 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-013 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 385 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-013 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 389 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-014 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 388 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-014 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5587.5 | 5587.5 | 5587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 15ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 45759.1667 | 45759.1667 | 45759.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 3ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 160 | 160 | 100% | 0% | 0% | 100% | 137277.5 | 0 | 0 | 137277.5 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 45759.1667 | 45759.1667 | 45759.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Farm Berm |  | 25393 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 1129.8575 | 4319.3493 | 84739.3128 | 16125.7065 | 105184.3686 | 0 | 0 | 100% | 0% | 0% | 100% | 105184.3686 | 0 | 0 | 105184.3686 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 52592.1843 | 52592.1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 413 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-007 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 414 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-008 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 415 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-009 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-010 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 405 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2614-FD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 854.1667 | 854.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 407 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Jet-A1 Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2614-FD-011 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 406 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Jet-A1 Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2614-FD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | Additional 750 kL Jet-A Tank at Milne Port |  | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 418 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 17.7083 | 61.9792 | 1328.125 | 2213.5417 | 3603.6458 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 3603.6458 | 0 | 0 | 3603.6458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1201.2153 | 1201.2153 | 1201.2153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 419 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 17.7083 | 61.9792 | 1328.125 | 2213.5417 | 3603.6458 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 3603.6458 | 0 | 0 | 3603.6458 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1201.2153 | 1201.2153 | 1201.2153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 420 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Marine Manifold Building - Demolish floor finish - Raised Steel or Wooden Floor | 2615-BLD-001 | 31.5985 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2616 | Weatherhaven camp |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Weatherhaven genset fuel bladder berm |  | 500 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 22.2474 | 85.05 | 1668.5565 | 317.5227 | 2058.4602 | 0 | 0 | 100% | 0% | 0% | 100% | 2058.4602 | 0 | 0 | 2058.4602 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 686.1534 | 686.1534 | 686.1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Port Site |  | 3500 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 350 | 4375 | 26250 | 43750 | 74375 | 0.01 | 35 | 100% | 0% | 0% | 100% | 74375 | 0 | 0 | 74375 | Type B Construction 2BC-MRY1416 |  | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24791.6667 | 24791.6667 | 24791.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 50,000 L Portable Fuel Dispensing Unit |  | 1364 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 60.691 | 232.0164 | 4551.8223 | 866.2019 | 5650.0405 | 0 | 0 | 100% | 0% | 0% | 100% | 5650.0405 | 0 | 0 | 5650.0405 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1883.3468 | 1883.3468 | 1883.3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Water Tank Main Unit |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 0 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 431 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 61.25 | 765.625 | 4593.75 | 7656.25 | 13015.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 13015.625 | 0 | 0 | 13015.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4338.5417 | 4338.5417 | 4338.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 432 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | -1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | -47 | -400 | -3525 | -4000 | -7925 | 329.2683 | -329.2683 | 100% | 0% | 100% | 0% | -7925 | 0 | -7925 | 0 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2641.6667 | -2641.6667 | -2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE VENDOR PACKAGE | 2720-VP-020 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 448 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 2720-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 449 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 2720-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 450 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 2720-TK-008 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 451 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 2720-TK-011 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 452 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2720-TK-033 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 433 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 2720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - POTABLE WATER STORAGE TANK (20 m3) |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - RAW WATER TANK (25 m3) |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 4180 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 185.9884 | 711.018 | 13949.1327 | 2654.4895 | 17208.727 | 0 | 0 | 100% | 0% | 0% | 100% | 17208.727 | 0 | 0 | 17208.727 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5736.2423 | 5736.2423 | 5736.2423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond #3 |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 4260 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 189.548 | 724.626 | 14216.1018 | 2705.2932 | 17538.0807 | 0 | 0 | 100% | 0% | 0% | 100% | 17538.0807 | 0 | 0 | 17538.0807 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5846.0269 | 5846.0269 | 5846.0269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 459 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 100 | 500 | 7500 | 12500 | 20500 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 20500 | 0 | 0 | 20500 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 468 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 2731.2-P | 258 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 64.5 | 806.25 | 4837.5 | 8062.5 | 13706.25 | 0.01 | 2.58 | 100% | 0% | 100% | 0% | 13706.25 | 0 | 13706.25 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6853.125 | 6853.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 2731-VP-005 | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 456 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 2731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 457 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 458 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 467 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 2731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 460 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 461 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 380-person temporary soft-walled camp at Milne Port |  | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 470 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 31.25 | 109.375 | 2343.75 | 3906.25 | 6359.375 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 6359.375 | 0 | 0 | 6359.375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3179.6875 | 3179.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 477 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 471 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.097 | 101.2126 | 607.2755 | 1012.1258 | 1720.6139 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1720.6139 | 0 | 0 | 1720.6139 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 860.3069 | 860.3069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 472 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 2732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 480 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to effluent pond and ocean discharge | 2734.1-P | 2595 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 648.75 | 8109.375 | 48656.25 | 81093.75 | 137859.375 | 0.01 | 25.95 | 100% | 0% | 100% | 0% | 137859.375 | 0 | 137859.375 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 45953.125 | 45953.125 | 45953.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Sewage System |  | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the Milne Port treated effluent line |  | 750 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 187.5 | 2343.75 | 14062.5 | 23437.5 | 39843.75 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 39843.75 | 0 | 39843.75 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13281.25 | 13281.25 | 13281.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Sewage System |  | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the fuel manifold and piping line |  | 750 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 187.5 | 2343.75 | 14062.5 | 23437.5 | 39843.75 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 39843.75 | 0 | 39843.75 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13281.25 | 13281.25 | 13281.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 479 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to effluent pond and ocean discharge | 2734.1-E | 1330 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 498 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV - Electrical distribution system from power gen to e-house | 2750.2-E | 6100 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 610 | 7625 | 45750 | 76250 | 129625 | 0.01 | 61 | 100% | 0% | 0% | 100% | 129625 | 0 | 0 | 129625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 43208.3333 | 43208.3333 | 43208.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 2750.3-E | 5000 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 500 | 6250 | 37500 | 62500 | 106250 | 0.01 | 50 | 100% | 0% | 0% | 100% | 106250 | 0 | 0 | 106250 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 35416.6667 | 35416.6667 | 35416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation - Milne Port 'Steensby Camp' power line (100 m) | 2750.3-E | 100 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 10 | 125 | 750 | 1250 | 2125 | 0.01 | 1 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type B Construction 2BC-MRY1416 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 708.3333 | 708.3333 | 708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 483 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 486 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | e-house |  | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 492 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 495 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-005 | 2.3234 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0.52083 | 6.5104 | 39.0625 | 65.1042 | 110.6771 | 1 | 2.3234 | 100% | 0% | 0% | 100% | 110.6771 | 0 | 0 | 110.6771 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 55.3385 | 55.3385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 496 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 497 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 487 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 488 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 490 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 491 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 493 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 494 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 484 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 485 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road
3000 | Tote Road | 3100 | General
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 3111-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 507 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 3111-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 510 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 3 - Demolish Building - ISO Shipping Container | 3111-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 513 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 4 - Demolish Building - ISO Shipping Container | 3111-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 505 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 506 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 508 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 509 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 511 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 3 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 512 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 514 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 4 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 515 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km88 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km80 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km69 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km49 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km40 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km26 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km7 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 16.8125 | 210.1562 | 1260.9375 | 2101.5625 | 3572.6562 | 1 | 150 | 100% | 0% | 0% | 100% | 3572.6562 | 0 | 0 | 3572.6562 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1190.8854 | 1190.8854 | 1190.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 517 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 5 - Demolish Building - ISO Shipping Container | 3112-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 520 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 6 - Demolish Building - ISO Shipping Container | 3112-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 523 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 7 - Demolish Building - ISO Shipping Container | 3112-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 526 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 8 - Demolish Building - ISO Shipping Container | 3112-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 518 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 5 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 519 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 5 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 521 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 6 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 522 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 6 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 524 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 7 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 525 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 7 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 527 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 8 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 528 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 8 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 530 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 9 - Demolish Building - ISO Shipping Container | 3113-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 533 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 10 - Demolish Building - ISO Shipping Container | 3113-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 536 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 11 - Demolish Building - ISO Shipping Container | 3113-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 531 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 9 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 532 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 9 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 534 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 10 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 535 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 10 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 537 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 11 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 538 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 11 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source |  | 41795 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 530.5809 | 6112.5187 | 39793.5668 | 16573.6127 | 62479.6982 | 0 | 0 | 100% | 0% | 0% | 100% | 62479.6982 | 0 | 0 | 62479.6982 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 62479.6982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2017) |  | 1000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 12.6948 | 146.25 | 952.1131 | 396.5453 | 1494.9084 | 0 | 0 | 100% | 0% | 0% | 100% | 1494.9084 | 0 | 0 | 1494.9084 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1494.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2018) |  | 1500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 19.0423 | 219.375 | 1428.1696 | 594.818 | 2242.3627 | 0 | 0 | 100% | 0% | 0% | 100% | 2242.3627 | 0 | 0 | 2242.3627 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2242.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at P1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P1 Borrow Source |  | 75820 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 962.5229 | 11088.675 | 72189.2148 | 30066.0681 | 113343.9579 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 113343.9579 | 0 | 113343.9579 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 56671.9789 | 56671.9789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive magazine pads along Tote Road |  | 760 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 9.6481 | 111.15 | 723.606 | 301.3745 | 1136.1304 | 0 | 0 | 100% | 0% | 0% | 100% | 1136.1304 | 0 | 0 | 1136.1304 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 378.7101 | 378.7101 | 378.7101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R3 (2017 Carry Over) |  | 25800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 327.5269 | 3773.25 | 24564.5178 | 10230.8699 | 38530.2449 | 0 | 0 | 100% | 0% | 0% | 100% | 38530.2449 | 0 | 0 | 38530.2449 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12843.415 | 12843.415 | 12843.415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R1 (2017 Carry Over) |  | 20200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 256.4358 | 2954.25 | 19232.6845 | 8010.216 | 30167.091 | 0 | 0 | 100% | 0% | 0% | 100% | 30167.091 | 0 | 0 | 30167.091 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10055.697 | 10055.697 | 10055.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R2 (2017 Carry Over) |  | 20000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 253.8968 | 2925 | 19042.2619 | 7930.9069 | 29868.4069 | 0 | 0 | 100% | 0% | 0% | 100% | 29868.4069 | 0 | 0 | 29868.4069 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9956.1356 | 9956.1356 | 9956.1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2 - 2019 |  | 55800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 708.3721 | 8160.75 | 53127.9106 | 22127.2303 | 83332.8553 | 0 | 0 | 100% | 0% | 0% | 100% | 83332.8553 | 0 | 0 | 83332.8553 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 27777.6184 | 27777.6184 | 27777.6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 4 - 2019 |  | 66300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 841.668 | 9696.375 | 63125.0981 | 26290.9564 | 99013.7689 | 0 | 0 | 100% | 0% | 0% | 100% | 99013.7689 | 0 | 0 | 99013.7689 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33004.5896 | 33004.5896 | 33004.5896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 7 - 2019 |  | 28900 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 366.8809 | 4226.625 | 27516.0684 | 11460.1605 | 43159.848 | 0 | 0 | 100% | 0% | 0% | 100% | 43159.848 | 0 | 0 | 43159.848 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14386.616 | 14386.616 | 14386.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 9 - 2019 |  | 92500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1174.2728 | 13528.125 | 88070.4612 | 36680.4445 | 138141.382 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 138141.382 | 0 | 138141.382 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 46047.1273 | 46047.1273 | 46047.1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 10 - 2019 |  | 34500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 437.972 | 5045.625 | 32847.9017 | 13680.8144 | 51523.0019 | 0 | 0 | 100% | 0% | 0% | 100% | 51523.0019 | 0 | 0 | 51523.0019 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 17174.334 | 17174.334 | 17174.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 13 - 2019 |  | 7000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 88.8639 | 1023.75 | 6664.7917 | 2775.8174 | 10453.9424 | 0 | 0 | 100% | 0% | 0% | 100% | 10453.9424 | 0 | 0 | 10453.9424 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3484.6475 | 3484.6475 | 3484.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown at km 61 |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8960.5221 | 0 | 0 | 100% | 0% | 0% | 100% | 8960.5221 | 0 | 0 | 8960.5221 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2986.8407 | 2986.8407 | 2986.8407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 88 IT Tower Pad |  | 6400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 81.247 | 936 | 6093.5238 | 2537.8902 | 9557.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 9557.8902 | 0 | 0 | 9557.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3185.9634 | 3185.9634 | 3185.9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 80 IT Tower Pad |  | 6400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 81.247 | 936 | 6093.5238 | 2537.8902 | 9557.8902 | 0 | 0 | 100% | 0% | 0% | 100% | 9557.8902 | 0 | 0 | 9557.8902 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3185.9634 | 3185.9634 | 3185.9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 69 IT Tower Pad |  | 5100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 64.7437 | 745.875 | 4855.7768 | 2022.3813 | 7616.4438 | 0 | 0 | 100% | 0% | 0% | 100% | 7616.4438 | 0 | 0 | 7616.4438 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2538.8146 | 2538.8146 | 2538.8146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 49 IT Tower Pad |  | 5600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 71.0911 | 819 | 5331.8333 | 2220.6539 | 8363.1539 | 0 | 0 | 100% | 0% | 0% | 100% | 8363.1539 | 0 | 0 | 8363.1539 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2787.718 | 2787.718 | 2787.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 40 IT Tower Pad |  | 2600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 33.0066 | 380.25 | 2475.494 | 1031.0179 | 3882.8929 | 0 | 0 | 100% | 0% | 0% | 100% | 3882.8929 | 0 | 0 | 3882.8929 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1294.2976 | 1294.2976 | 1294.2976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 26 IT Tower Pad |  | 4000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 50.7794 | 585 | 3808.4524 | 1586.1814 | 5973.6814 | 0 | 0 | 100% | 0% | 0% | 100% | 5973.6814 | 0 | 0 | 5973.6814 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1991.2271 | 1991.2271 | 1991.2271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 07 IT Tower Pad |  | 3800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 48.2404 | 555.75 | 3618.0298 | 1506.8723 | 5674.9973 | 0 | 0 | 100% | 0% | 0% | 100% | 5674.9973 | 0 | 0 | 5674.9973 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1891.6658 | 1891.6658 | 1891.6658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3136 | Mary River |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 13040 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.5407 | 1907.1 | 12415.5547 | 5170.9513 | 19493.6061 | 0 | 0 | 100% | 0% | 0% | 100% | 19493.6061 | 0 | 0 | 19493.6061 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6497.8687 | 6497.8687 | 6497.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Q13 Quarry (marginal increase to existing) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 25000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 317.371 | 3656.25 | 23802.8273 | 9913.6336 | 37335.5086 | 0 | 0 | 100% | 0% | 0% | 100% | 37335.5086 | 0 | 0 | 37335.5086 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 18667.7543 | 18667.7543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P10 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P10 Borrow Source |  | 19344 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 245.569 | 2829.06 | 18417.6757 | 7670.7732 | 28888.7232 | 0 | 0 | 100% | 0% | 0% | 100% | 28888.7232 | 0 | 0 | 28888.7232 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 14444.3616 | 14444.3616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P13 Borrow Source |  | 8456 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 107.3476 | 1236.69 | 8051.0683 | 3353.1874 | 12628.3624 | 0 | 0 | 100% | 0% | 0% | 100% | 12628.3624 | 0 | 0 | 12628.3624 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6314.1812 | 6314.1812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P14 Borrow Source |  | 3160 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 40.1157 | 462.15 | 3008.6774 | 1253.0833 | 4719.2083 | 0 | 0 | 100% | 0% | 0% | 100% | 4719.2083 | 0 | 0 | 4719.2083 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2359.6041 | 2359.6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P15 Borrow Source |  | 3300 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 41.893 | 482.625 | 3141.9732 | 1308.5996 | 4928.2871 | 0 | 0 | 100% | 0% | 0% | 100% | 4928.2871 | 0 | 0 | 4928.2871 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2464.1436 | 2464.1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Removal of Quarry and Borrow No Longer being Developed (Q9, Q14, Q15, P5, P6, P7, P8, P10, P13, P14, and P15) |  | -102131 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -1296.5368 | -14936.6587 | -97240.2624 | -40499.5727 | -152524.5133 | 0 | 0 | 100% | 0% | 0% | 100% | -152524.5133 | 0 | 0 | -152524.5133 | Type A 2AM-MRY1325 | Removed | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -76262.2567 | -76262.2567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P5 Borrow Source |  | 4600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 58.3963 | 672.75 | 4379.7202 | 1824.1086 | 6869.7336 | 0 | 0 | 100% | 0% | 0% | 100% | 6869.7336 | 0 | 0 | 6869.7336 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3434.8668 | 3434.8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P6 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P6 Borrow Source |  | 7500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 95.2113 | 1096.875 | 7140.8482 | 2974.0901 | 11200.6526 | 0 | 0 | 100% | 0% | 0% | 100% | 11200.6526 | 0 | 0 | 11200.6526 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 5600.3263 | 5600.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P7 Borrow Source |  | 8100 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 102.8282 | 1184.625 | 7712.1161 | 3212.0173 | 12096.7048 | 0 | 0 | 100% | 0% | 0% | 100% | 12096.7048 | 0 | 0 | 12096.7048 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6048.3524 | 6048.3524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P8 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P8 Borrow Source |  | 8385 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 106.4462 | 1226.3062 | 7983.4683 | 3325.0327 | 12522.3296 | 0 | 0 | 100% | 0% | 0% | 100% | 12522.3296 | 0 | 0 | 12522.3296 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6261.1648 | 6261.1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry |  | 64200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 815.0088 | 9389.25 | 61125.6606 | 25458.2112 | 95973.1218 | 0 | 0 | 100% | 0% | 0% | 100% | 95973.1218 | 0 | 0 | 95973.1218 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 47986.5609 | 47986.5609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2019) |  | 226000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2869.0341 | 33052.5 | 215177.5592 | 89619.2481 | 337849.3073 | 0 | 0 | 100% | 0% | 0% | 100% | 337849.3073 | 0 | 0 | 337849.3073 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 168924.6537 | 168924.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | 8969.4506 | 0 | 0 | 8969.4506 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4484.7253 | 4484.7253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 634.7421 | 7312.5 | 47605.6547 | 19827.2673 | 74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | 74745.422 | 0 | 0 | 74745.422 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 37372.711 | 37372.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing in remainder 2017 - total now reflects area in QMP) |  | 824500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 10466.8966 | 120583.125 | 785017.2458 | 326951.6376 | 1232552.0084 | 0 | 0 | 100% | 0% | 0% | 100% | 1232552.0084 | 0 | 0 | 1232552.0084 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 616276.0042 | 616276.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q11 Quarry |  | 50433 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 640.2389 | 7375.8262 | 48017.9197 | 19998.9714 | 75392.7173 | 0 | 0 | 100% | 0% | 0% | 100% | 75392.7173 | 0 | 0 | 75392.7173 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 37696.3587 | 37696.3587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q18 Quarry |  | 2000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 25.3897 | 292.5 | 1904.2262 | 793.0907 | 2989.8169 | 0 | 0 | 100% | 0% | 0% | 100% | 2989.8169 | 0 | 0 | 2989.8169 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1494.9084 | 1494.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 6350 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 80.6122 | 928.6875 | 6045.9181 | 2518.0629 | 9483.2192 | 0 | 0 | 100% | 0% | 0% | 100% | 9483.2192 | 0 | 0 | 9483.2192 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4741.6096 | 4741.6096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q14 Quarry |  | 13440 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 170.6187 | 1965.6 | 12796.4 | 5329.5694 | 20071.5694 | 0 | 0 | 100% | 0% | 0% | 100% | 20071.5694 | 0 | 0 | 20071.5694 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 10035.7847 | 10035.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q15 Quarry |  | 10680 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 135.5809 | 1561.95 | 10168.5678 | 4235.1043 | 15949.7293 | 0 | 0 | 100% | 0% | 0% | 100% | 15949.7293 | 0 | 0 | 15949.7293 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7974.8646 | 7974.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q16A |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q16A Quarry |  | 11240 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 142.69 | 1643.85 | 10701.7512 | 4457.1697 | 16786.0447 | 0 | 0 | 100% | 0% | 0% | 100% | 16786.0447 | 0 | 0 | 16786.0447 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 8393.0223 | 8393.0223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q19 Quarry |  | 18760 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 238.1552 | 2743.65 | 17861.6416 | 7439.1907 | 28044.4823 | 0 | 0 | 100% | 0% | 0% | 100% | 28044.4823 | 0 | 0 | 28044.4823 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 14022.2412 | 14022.2412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q9 Quarry |  | 15166 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 192.53 | 2218.0275 | 14439.7472 | 6014.0067 | 22649.213 | 0 | 0 | 100% | 0% | 0% | 100% | 22649.213 | 0 | 0 | 22649.213 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11324.6065 | 11324.6065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ2a quarry |  | 345500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 4386.0677 | 50529.375 | 328955.0739 | 137006.417 | 516490.8659 | 0 | 0 | 100% | 0% | 0% | 100% | 516490.8659 | 0 | 0 | 516490.8659 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 258245.4329 | 258245.4329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ4a quarry |  | 105000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1332.9583 | 15356.25 | 99971.8748 | 41637.2613 | 156965.3862 | 0 | 0 | 100% | 0% | 0% | 100% | 156965.3862 | 0 | 0 | 156965.3862 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 78482.6931 | 78482.6931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ6a quarry |  | 194000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2462.7992 | 28372.5 | 184709.9402 | 76929.7971 | 290012.2373 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 290012.2373 | 0 | 290012.2373 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 145006.1186 | 145006.1186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ12a quarry |  | 232200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2947.7421 | 33959.25 | 221080.6604 | 92077.8293 | 347117.7397 | 0 | 0 | 100% | 0% | 0% | 100% | 347117.7397 | 0 | 0 | 347117.7397 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 173558.8698 | 173558.8698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry Expansion 2019 |  | 1225587 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 15558.6324 | 179242.0987 | 1166897.4302 | 486000.8207 | 1832140.3497 | 0 | 0 | 100% | 0% | 0% | 100% | 1832140.3497 | 0 | 0 | 1832140.3497 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 916070.1748 | 916070.1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry |  | 15000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 190.4226 | 2193.75 | 14281.6964 | 5948.1802 | 22423.6266 | 0 | 0 | 100% | 0% | 0% | 100% | 22423.6266 | 0 | 0 | 22423.6266 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11211.8133 | 11211.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q7 Quarry |  | 53050 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 673.4613 | 7758.5625 | 50509.5996 | 21036.7306 | 79304.8927 | 0 | 0 | 100% | 0% | 0% | 100% | 79304.8927 | 0 | 0 | 79304.8927 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 39652.4464 | 39652.4464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Borrow development areas |  | 42080 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 534.1989 | 6154.2 | 40064.919 | 16686.6282 | 62905.7471 | 0 | 0 | 100% | 0% | 0% | 100% | 62905.7471 | 0 | 0 | 62905.7471 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20968.5824 | 20968.5824 | 20968.5824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3132 | River Crossing at STA 17 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 0% | 100% | 0% | 100% | 0 | 161904.7619 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3133 | River Crossing at STA 62 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3134 | River Crossing at STA 80 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3135 | River Crossing at STA 97 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Ea | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 761.9048 | 9523.8095 | 57142.8571 | 95238.0952 | 161904.7619 | 5000 | 5000 | 100% | 0% | 0% | 100% | 161904.7619 | 0 | 0 | 161904.7619 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53968.254 | 53968.254 | 53968.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 2019 Quarries (4 x 20m) |  | 80 | Ea | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 27.824 | 173.9 | 2086.8 | 1739 | 3999.7 | 0 | 0 | 100% | 0% | 0% | 100% | 3999.7 | 0 | 0 | 3999.7 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 1999.85 | 1999.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 372 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 2232 | 13950 | 167400 | 139500 | 320850 | 0 | 0 | 100% | 0% | 0% | 100% | 320850 | 0 | 0 | 320850 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 160425 | 160425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - Crown |  | 11 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 66 | 412.5 | 4950 | 4125 | 9487.5 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 9487.5 | 0 | 9487.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 4743.75 | 4743.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mobile Maintenance Depot - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 682 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 382.2042 | 1337.7146 | 28665.3125 | 47775.5208 | 77778.5479 | 1 | 682 | 0% | 100% | 0% | 100% | 0 | 77778.5479 | 0 | 77778.5479 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25926.1826 | 25926.1826 | 25926.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Mobile Maintenance Depot - Demolish floor finish - Slab on grade C/W Drainage |  | 682 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 85.25 | 1278.75 | 6393.75 | 12787.5 | 20460 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 20460 | 0 | 20460 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6820 | 6820 | 6820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Mobile Maintenance Depot -Liner Removal |  | 682 | m2 | 0.0318 | 0.02385 | 2.385 | 0.2385 | 2.6235 | 21.6876 | 16.2657 | 1626.57 | 162.657 | 1789.227 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 1789.227 | 0 | 1789.227 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 596.409 | 596.409 | 596.409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Mobile Maintenance Depot - Demolish and foundations - Gravel Base - Skidded Building |  | 682 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Out-of-Service Tote Road |  | 266500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 3383.1752 | 38975.625 | 253738.1395 | 105679.3346 | 397996.5221 | 0 | 0 | 100% | 0% | 0% | 100% | 397996.5221 | 0 | 0 | 397996.5221 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 198998.2611 | 198998.2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source |  | 157012 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 2989.8636 | 34444.5075 | 224239.7716 | 93393.5667 | 352077.8459 | 0 | 0 | 100% | 0% | 0% | 100% | 352077.8459 | 0 | 0 | 352077.8459 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 176038.9229 | 176038.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 0 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2017) |  | 1000 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 19.0423 | 219.375 | 1428.1696 | 594.818 | 2242.3627 | 0 | 0 | 100% | 0% | 0% | 100% | 2242.3627 | 0 | 0 | 2242.3627 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1121.1813 | 1121.1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2018) |  | 1500 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 28.5634 | 329.0625 | 2142.2545 | 892.227 | 3363.544 | 0 | 0 | 100% | 0% | 0% | 100% | 3363.544 | 0 | 0 | 3363.544 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1681.772 | 1681.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 105359 | m2 | 0.019042 | 0.21937 | 1.4282 | 0.59482 | 2.2401 | 2006.2737 | 23113.1306 | 150470.5252 | 62669.4316 | 236017.9113 | 0 | 0 | 100% | 0% | 0% | 100% | 236017.9113 | 0 | 0 | 236017.9113 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 118008.9557 | 118008.9557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  |  | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  | 697910.1311 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 8859.8583 | 102069.3567 | 664489.3741 | 276753.0143 | 1042273.1894 | 0 | 0 | 100% | 0% | 0% | 100% | 1042273.1894 | 0 | 0 | 1042273.1894 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 521136.5947 | 521136.5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 565 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 1 - Demolish Building - ISO Shipping Container | 3160-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 568 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 2 - Demolish Building - ISO Shipping Container | 3160-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 571 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 3 - Demolish Building - ISO Shipping Container | 3160-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 574 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 4 - Demolish Building - ISO Shipping Container | 3160-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 566 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 1 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-001 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 569 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 2 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-002 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 572 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 3 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-003 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 575 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 4 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-004 | 14.8699 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 1.8333 | 14.5833 | 87.5 | 145.8333 | 247.9167 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 247.9167 | 0 | 0 | 247.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 82.6389 | 82.6389 | 82.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 567 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 570 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 573 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 576 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings ( Not Contaminated) | Single Trailers (modular) |  | Washrooms at KM26 and KM 80 IT Towers |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (31m2 x 2) - Demolish and Decontaminate Building - Trailer |  | 62 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 34.7458 | 173.7292 | 2605.9375 | 4343.2292 | 7122.8958 | 1 | 62 | 100% | 0% | 0% | 100% | 7122.8958 | 0 | 0 | 7122.8958 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2374.2986 | 2374.2986 | 2374.2986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (15m2 x 3) - Demolish and Decontaminate Building - Trailer |  | 45 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 25.2188 | 126.0938 | 1891.4062 | 3152.3438 | 5169.8438 | 1 | 45 | 100% | 0% | 0% | 100% | 5169.8438 | 0 | 0 | 5169.8438 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1723.2812 | 1723.2812 | 1723.2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (22m2) - Demolish and Decontaminate Building - Trailer |  | 22 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 12.3292 | 61.6458 | 924.6875 | 1541.1458 | 2527.4792 | 1 | 22 | 100% | 0% | 0% | 100% | 2527.4792 | 0 | 0 | 2527.4792 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 842.4931 | 842.4931 | 842.4931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (12m2) - Demolish and Decontaminate Building - Trailer |  | 12 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 6.725 | 33.625 | 504.375 | 840.625 | 1378.625 | 1 | 12 | 100% | 0% | 0% | 100% | 1378.625 | 0 | 0 | 1378.625 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 459.5417 | 459.5417 | 459.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site
4000 | Mine Site | 4100 | General
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 579 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 4110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 582 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 4110-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 8.4062 | 14.0104 | 23.8177 | 1.6667 | 20.8333 | 125 | 208.3333 | 354.1667 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 354.1667 | 0 | 0 | 354.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 118.0556 | 118.0556 | 118.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 580 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 581 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 583 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 584 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Site Development | 4136 | Tote Road |  |  | A3 | Grade & Re-Contour | A9 | Site Works | Grade and Re-Contour Building Footprints |  | Grade and Re-Contour Building Footprints |  | 223 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2.8309 | 32.6137 | 212.3212 | 88.4296 | 333.3646 | 0 | 0 | 100% | 0% | 0% | 100% | 333.3646 | 0 | 0 | 333.3646 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 111.1215 | 111.1215 | 111.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | -15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2A |  | 30150 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2B |  | 8700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 1 |  | 5400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Warehouse laydown pad expansion |  | 3200 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 40.6235 | 468 | 3046.7619 | 1268.9451 | 4783.707 | 0 | 0 | 100% | 0% | 0% | 100% | 4783.707 | 0 | 0 | 4783.707 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1594.569 | 1594.569 | 1594.569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction Laydown Area |  | 33576 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 426.242 | 4910.49 | 31968.1492 | 13314.4065 | 50193.0458 | 0 | 0 | 100% | 0% | 0% | 100% | 50193.0458 | 0 | 0 | 50193.0458 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16731.0153 | 16731.0153 | 16731.0153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of the area east of the Mine Site workshops and crushing area for improved traffic management |  | 37732 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 479.0018 | 5518.305 | 35925.1313 | 14962.449 | 56405.8852 | 0 | 0 | 100% | 0% | 0% | 100% | 56405.8852 | 0 | 0 | 56405.8852 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 18801.9617 | 18801.9617 | 18801.9617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of MSC laydown for vehicle parking |  | 5243 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 66.5591 | 766.7887 | 4991.929 | 2079.0872 | 7837.8049 | 0 | 0 | 100% | 0% | 0% | 100% | 7837.8049 | 0 | 0 | 7837.8049 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2612.6016 | 2612.6016 | 2612.6016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of three (3) laydown areas for road aggregate storage on the mine haul road Km 106, Km 107 and Km 108 |  | 10705 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 135.8983 | 1565.6062 | 10192.3707 | 4245.0179 | 16002.9948 | 0 | 0 | 100% | 0% | 0% | 100% | 16002.9948 | 0 | 0 | 16002.9948 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5334.3316 | 5334.3316 | 5334.3316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Explosives plant secondary storage location |  | 20000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 253.8968 | 2925 | 19042.2619 | 7930.9069 | 29898.1688 | 0 | 0 | 100% | 0% | 0% | 100% | 29898.1688 | 0 | 0 | 29898.1688 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9966.0563 | 9966.0563 | 9966.0563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of 800p camp laydown |  | 12000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 152.3381 | 1755 | 11425.3571 | 4758.5441 | 17938.9013 | 0 | 0 | 100% | 0% | 0% | 100% | 17938.9013 | 0 | 0 | 17938.9013 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5979.6338 | 5979.6338 | 5979.6338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | WRF Water Treatment plant laydown 2019 |  | 3500 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 44.4319 | 511.875 | 3332.3958 | 1387.9087 | 5232.1795 | 0 | 0 | 100% | 0% | 0% | 100% | 5232.1795 | 0 | 0 | 5232.1795 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1744.0598 | 1744.0598 | 1744.0598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM107.5 Laydown for haul road parking |  | 91000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1155.2306 | 13308.75 | 86642.2915 | 36085.6265 | 136036.668 | 0 | 0 | 100% | 0% | 0% | 100% | 136036.668 | 0 | 0 | 136036.668 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 45345.556 | 45345.556 | 45345.556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM110.5 Laydown for Mine Ops |  | 180000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2285.0714 | 26325 | 171380.3569 | 71378.1622 | 269083.5191 | 0 | 0 | 100% | 0% | 0% | 100% | 269083.5191 | 0 | 0 | 269083.5191 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 89694.5064 | 89694.5064 | 89694.5064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km107 Stockpile and access Road |  | 133400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1693.4918 | 19509.75 | 127011.8867 | 52899.1491 | 199420.7858 | 0 | 0 | 100% | 0% | 0% | 100% | 199420.7858 | 0 | 0 | 199420.7858 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 66473.5953 | 66473.5953 | 66473.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 220.4703 | 2539.912 | 16535.2719 | 6886.7713 | 25961.9553 | 0 | 0 | 100% | 0% | 0% | 100% | 25961.9553 | 0 | 0 | 25961.9553 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8653.9851 | 8653.9851 | 8653.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 220.4703 | 2539.912 | 16535.2719 | 6886.7713 | 25961.9553 | 0 | 0 | 100% | 0% | 0% | 100% | 25961.9553 | 0 | 0 | 25961.9553 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8653.9851 | 8653.9851 | 8653.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development (Nuna services) |  | 11400 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 144.7212 | 1667.25 | 10854.0893 | 4520.6169 | 17024.9919 | 0 | 0 | 100% | 0% | 0% | 100% | 17024.9919 | 0 | 0 | 17024.9919 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5674.9973 | 5674.9973 | 5674.9973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Truck Shop (2018) laydown area |  | 25000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 317.371 | 3656.25 | 23802.8273 | 9913.6336 | 37335.5086 | 0 | 0 | 100% | 0% | 0% | 100% | 37335.5086 | 0 | 0 | 37335.5086 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12445.1695 | 12445.1695 | 12445.1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional laydown next to Hatch old office/carpentry shack |  | 11250 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 142.817 | 1645.3125 | 10711.2723 | 4461.1351 | 16800.9789 | 0 | 0 | 100% | 0% | 0% | 100% | 16800.9789 | 0 | 0 | 16800.9789 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5600.3263 | 5600.3263 | 5600.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher Pad Expansion |  | 25700 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 326.2574 | 3758.625 | 24469.3065 | 10191.2154 | 38380.9029 | 0 | 0 | 100% | 0% | 0% | 100% | 38380.9029 | 0 | 0 | 38380.9029 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12793.6343 | 12793.6343 | 12793.6343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher extension Pad |  | 36180 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 459.2994 | 5291.325 | 34447.4517 | 14347.0106 | 54031.9481 | 0 | 0 | 100% | 0% | 0% | 100% | 54031.9481 | 0 | 0 | 54031.9481 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 18010.6494 | 18010.6494 | 18010.6494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry |  | 258580 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 3282.6321 | 37817.325 | 246197.4038 | 102538.6955 | 386553.4243 | 0 | 0 | 100% | 0% | 0% | 100% | 386553.4243 | 0 | 0 | 386553.4243 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 193276.7121 | 193276.7121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q2 Quarry |  | 109807 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1393.9824 | 16059.2737 | 104548.6825 | 43543.4548 | 164151.411 | 0 | 0 | 100% | 0% | 0% | 100% | 164151.411 | 0 | 0 | 164151.411 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 82075.7055 | 82075.7055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q1 Quarry |  | 66978 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 850.2751 | 9795.5325 | 63770.6308 | 26559.8142 | 100125.9775 | 0 | 0 | 100% | 0% | 0% | 100% | 100125.9775 | 0 | 0 | 100125.9775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 50062.9887 | 50062.9887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 76.169 | 877.5 | 5712.6786 | 2379.2721 | 8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | 8969.4506 | 0 | 0 | 8969.4506 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4484.7253 | 4484.7253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 45000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 571.2679 | 6581.25 | 42845.0892 | 17844.5406 | 67270.8798 | 0 | 0 | 100% | 0% | 0% | 100% | 67270.8798 | 0 | 0 | 67270.8798 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 33635.4399 | 33635.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 634.7421 | 7312.5 | 47605.6547 | 19827.2673 | 74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | 74745.422 | 0 | 0 | 74745.422 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 37372.711 | 37372.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -6000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -76.169 | -877.5 | -5712.6786 | -2379.2721 | -8969.4506 | 0 | 0 | 100% | 0% | 0% | 100% | -8969.4506 | 0 | 0 | -8969.4506 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -4484.7253 | -4484.7253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -50000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -634.7421 | -7312.5 | -47605.6547 | -19827.2673 | -74745.422 | 0 | 0 | 100% | 0% | 0% | 100% | -74745.422 | 0 | 0 | -74745.422 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -37372.711 | -37372.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Informal Construction Laydown at Mary River |  |  | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Site Roads |  | 80899 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1027 | 11831.4787 | 77024.9972 | 32080.1219 | 120936.5978 | 0 | 0 | 100% | 0% | 0% | 100% | 120936.5978 | 0 | 0 | 120936.5978 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 40312.1993 | 40312.1993 | 40312.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Waste Rock Road |  | 20000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 253.8968 | 2925 | 19042.2619 | 7930.9069 | 29898.1688 | 0 | 0 | 100% | 0% | 0% | 100% | 29898.1688 | 0 | 0 | 29898.1688 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9966.0563 | 9966.0563 | 9966.0563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 1120 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 14.2182 | 163.8 | 1066.3667 | 444.1308 | 1672.6308 | 0 | 0 | 100% | 0% | 0% | 100% | 1672.6308 | 0 | 0 | 1672.6308 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 557.5436 | 557.5436 | 557.5436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Haul Road Widening and Cross Cut |  | 55900 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 709.6416 | 8175.375 | 53223.1219 | 22166.8848 | 83482.1973 | 0 | 0 | 100% | 0% | 0% | 100% | 83482.1973 | 0 | 0 | 83482.1973 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 27827.3991 | 27827.3991 | 27827.3991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for KM107 Stockpile (3 x 75m) |  | 225 | m | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 78.255 | 489.0938 | 5869.125 | 4890.9375 | 11249.1562 | 0 | 0 | 100% | 0% | 0% | 100% | 11249.1562 | 0 | 0 | 11249.1562 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3749.7188 | 3749.7188 | 3749.7188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 800p camp discharge line (4 x 15m) |  | 60 | m | 0.3478 | 2.1738 | 26.085 | 21.7375 | 50 | 20.868 | 130.425 | 1565.1 | 1304.25 | 2999.775 | 0 | 0 | 100% | 0% | 0% | 100% | 2999.775 | 0 | 0 | 2999.775 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 999.925 | 999.925 | 999.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 14 | Ea | 6 | 37.5 | 450 | 375 | 862.5 | 84 | 525 | 6300 | 5250 | 12075 | 0 | 0 | 100% | 0% | 0% | 100% | 12075 | 0 | 0 | 12075 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4025 | 4025 | 4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK + BOX PLASTIC FITTINGS |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5587.5 | 5587.5 | 5587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -85.45 | -941.25 | -6408.75 | -9412.5 | -16762.5 | 30 | -60 | 100% | 0% | 0% | 100% | -16762.5 | 0 | 0 | -16762.5 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -5587.5 | -5587.5 | -5587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 30 | 30 | 100% | 0% | 0% | 100% | 8381.25 | 0 | 0 | 8381.25 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2793.75 | 2793.75 | 2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | -42.725 | -470.625 | -3204.375 | -4706.25 | -8381.25 | 30 | -30 | 100% | 0% | 0% | 100% | -8381.25 | 0 | 0 | -8381.25 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2793.75 | -2793.75 | -2793.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 31 | 325 | 2325 | 3250 | 5900 | 20 | 40 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -31 | -325 | -2325 | -3250 | -5900 | 20 | -40 | 100% | 0% | 0% | 100% | -5900 | 0 | 0 | -5900 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -2950 | -2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | -1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | -15.5 | -162.5 | -1162.5 | -1625 | -2950 | 20 | -20 | 100% | 0% | 0% | 100% | -2950 | 0 | 0 | -2950 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -1475 | -1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 777 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single | 4213-BLD-001 | 33.4572 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 18.75 | 93.75 | 1406.25 | 2343.75 | 3843.75 | 1 | 33.4572 | 100% | 0% | 0% | 100% | 3843.75 | 0 | 0 | 3843.75 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1281.25 | 1281.25 | 1281.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 778 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Magazines - Demolish and foundations - Gravel Base - Skidded Building | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 779 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Magazines - Demolish floor finish - Raised Steel or Wooden Floor | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 769 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4211-BLD-001 | 342.0074 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 191.6667 | 958.3333 | 14375 | 23958.3333 | 39291.6667 | 1 | 342.0074 | 100% | 0% | 0% | 100% | 39291.6667 | 0 | 0 | 39291.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13097.2222 | 13097.2222 | 13097.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 770 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Plant Building - Demolish and foundations - Gravel Base - Skidded Building | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 771 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Plant Building - Demolish floor finish - Raised Steel or Wooden Floor | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4212-BLD-001 | 371.7472 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 208.3333 | 729.1667 | 15625 | 26041.6667 | 42395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 42395.8333 | 0 | 0 | 42395.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14131.9444 | 14131.9444 | 14131.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 130 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 72.8542 | 254.9896 | 5464.0625 | 9106.7708 | 14825.8229 | 1 | 130 | 100% | 0% | 0% | 100% | 14825.8229 | 0 | 0 | 14825.8229 | Type A 2AM-MRY1325 |  | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4941.941 | 4941.941 | 4941.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 775 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Explosives Shop - Demolish floor finish - Slab on grade C/W Drainage | 4212-BLD-001 | 371.7472 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 46.4684 | 697.026 | 3485.1301 | 6970.2602 | 11152.4164 | 0 | 0 | 100% | 0% | 0% | 100% | 11152.4164 | 0 | 0 | 11152.4164 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3717.4721 | 3717.4721 | 3717.4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 774 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Shop - Demolish and foundations - Gravel Base - Skidded Building | 4212-BLD-001 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Explosives Facility | 4222 | Explosive pad haul road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Explosive pad haul road |  | 19600 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 248.8189 | 2866.5 | 18661.4166 | 7772.2888 | 29300.2054 | 0 | 0 | 100% | 0% | 0% | 100% | 29300.2054 | 0 | 0 | 29300.2054 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9766.7351 | 9766.7351 | 9766.7351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Dump |  | 190000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2412.0198 | 27787.5 | 180901.4878 | 75343.6157 | 190000 | 0 | 0 | 100% | 0% | 0% | 100% | 190000 | 0 | 0 | 190000 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 63333.3333 | 63333.3333 | 63333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Facility - Footprint expansion |  | 130000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1650.3294 | 19012.5 | 123774.7022 | 51550.895 | 194338.0971 | 0 | 0 | 100% | 0% | 0% | 100% | 194338.0971 | 0 | 0 | 194338.0971 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 64779.3657 | 64779.3657 | 64779.3657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Facility - Expansion to approved footprint |  | 265000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 3364.1329 | 38756.25 | 252309.9698 | 105084.5166 | 396150.7365 | 0 | 0 | 100% | 0% | 0% | 100% | 396150.7365 | 0 | 0 | 396150.7365 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132050.2455 | 132050.2455 | 132050.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Geotube Settling Pond |  | 3000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 133.4845 | 510.3 | 10011.3393 | 1905.136 | 12426.7753 | 0 | 0 | 100% | 0% | 0% | 100% | 12426.7753 | 0 | 0 | 12426.7753 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4142.2584 | 4142.2584 | 4142.2584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 19000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 845.402 | 3231.9 | 63405.1488 | 12065.8616 | 78702.9104 | 0 | 0 | 100% | 0% | 0% | 100% | 78702.9104 | 0 | 0 | 78702.9104 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 26234.3035 | 26234.3035 | 26234.3035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 6000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 266.969 | 1020.6 | 20022.6786 | 3810.2721 | 24853.5506 | 0 | 0 | 100% | 0% | 0% | 100% | 24853.5506 | 0 | 0 | 24853.5506 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8284.5169 | 8284.5169 | 8284.5169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2008 Bulk Sample Pit |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 2008 bulk sample PWSP |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 |  | 55000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 698.2163 | 8043.75 | 52366.2202 | 21809.994 | 82219.9642 | 0 | 0 | 100% | 0% | 0% | 100% | 82219.9642 | 0 | 0 | 82219.9642 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 41109.9821 | 41109.9821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 - Marginal increase |  | 214450 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 2722.4087 | 31363.3125 | 204180.653 | 85039.1494 | 320263.9932 | 0 | 0 | 100% | 0% | 0% | 100% | 320263.9932 | 0 | 0 | 320263.9932 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 160131.9966 | 160131.9966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New PWSP 2019 |  | 4180 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 185.9884 | 711.018 | 13949.1327 | 2654.4895 | 17208.727 | 0 | 0 | 100% | 0% | 0% | 100% | 17208.727 | 0 | 0 | 17208.727 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 17208.727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 6967 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 309.9956 | 1185.0867 | 23249.6669 | 4424.3609 | 28682.584 | 0 | 0 | 100% | 0% | 0% | 100% | 28682.584 | 0 | 0 | 28682.584 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 28682.584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-3 | 6511 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 289.7059 | 1107.5211 | 21727.9434 | 4134.7802 | 26805.2684 | 0 | 0 | 100% | 0% | 0% | 100% | 26805.2684 | 0 | 0 | 26805.2684 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 26805.2684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 3720 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 165.5208 | 632.772 | 12414.0607 | 2362.3687 | 15314.9437 | 0 | 0 | 100% | 0% | 0% | 100% | 15314.9437 | 0 | 0 | 15314.9437 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 15314.9437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 789 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 708.3333 | 708.3333 | 708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 786 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Pit Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4281-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 60 | 750 | 4500 | 7500 | 12750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 787 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 790 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Pit Office Washcar - Demolish and foundations - Gravel Base - Skidded Building | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 791 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 788 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Lunchroom Building - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Lunchroom Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-002 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Lunchroom Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-001 | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-002 | 54 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 12.105 | 151.3125 | 907.875 | 1513.125 | 2572.3125 | 1 | 54 | 100% | 0% | 0% | 100% | 2572.3125 | 0 | 0 | 2572.3125 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 857.4375 | 857.4375 | 857.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-003 | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-004 | 25 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 5.6042 | 70.0521 | 420.3125 | 700.5208 | 1190.8854 | 1 | 25 | 100% | 0% | 0% | 100% | 1190.8854 | 0 | 0 | 1190.8854 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 396.9618 | 396.9618 | 396.9618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Crusher Pad Expansion 2019 |  | 12000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 152.3381 | 1755 | 11425.3571 | 4758.5441 | 17938.9013 | 0 | 0 | 100% | 0% | 0% | 100% | 17938.9013 | 0 | 0 | 17938.9013 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5979.6338 | 5979.6338 | 5979.6338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Ore crushing and Loading Pad, Utility & Accommodation Pads |  | 121021 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1536.3424 | 17699.3212 | 115225.6787 | 47990.3143 | 180915.3143 | 0 | 0 | 100% | 0% | 0% | 100% | 180915.3143 | 0 | 0 | 180915.3143 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 60305.1048 | 60305.1048 | 60305.1048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiles |  | 5100.23 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 64.7466 | 745.9086 | 4855.9958 | 2022.4725 | 7624.3769 | 0 | 0 | 100% | 0% | 0% | 100% | 7624.3769 | 0 | 0 | 7624.3769 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2541.459 | 2541.459 | 2541.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 795 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-001 | 39.4052 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 22.0833 | 110.4167 | 1656.25 | 2760.4167 | 4527.0833 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 4527.0833 | 0 | 0 | 4527.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1509.0278 | 1509.0278 | 1509.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 798 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-002 | 39.4052 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 22.0833 | 110.4167 | 1656.25 | 2760.4167 | 4527.0833 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 4527.0833 | 0 | 0 | 4527.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1509.0278 | 1509.0278 | 1509.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 796 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 797 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 799 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 800 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 828 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Stockpile Drain Pipe - Piping Installation - Ore stockpile to effluent pond and Mary River | 4385.1-P | 5220 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 1305 | 16312.5 | 97875 | 163125 | 277312.5 | 0.01 | 52.2 | 100% | 0% | 100% | 0% | 277312.5 | 0 | 277312.5 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 92437.5 | 92437.5 | 92437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Mine Haul Road Sedimentation Pond |  | 10000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 444.9484 | 1701 | 33371.1309 | 6350.4535 | 41422.5844 | 0 | 0 | 100% | 0% | 0% | 100% | 41422.5844 | 0 | 0 | 41422.5844 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13807.5281 | 13807.5281 | 13807.5281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | KM107 Sedimentation Pond |  | 7400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 329.2618 | 1258.74 | 24694.6369 | 4699.3356 | 30652.7125 | 0 | 0 | 100% | 0% | 0% | 100% | 30652.7125 | 0 | 0 | 30652.7125 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10217.5708 | 10217.5708 | 10217.5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Crusher Pad Sedimentation Pond 2019 |  | 2000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 88.9897 | 340.2 | 6674.2262 | 1270.0907 | 8284.5169 | 0 | 0 | 100% | 0% | 0% | 100% | 8284.5169 | 0 | 0 | 8284.5169 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2761.5056 | 2761.5056 | 2761.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Crushing Sedimentation Pond |  | 6428.69 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 286.0435 | 1093.5202 | 21453.2656 | 4082.5097 | 26629.2954 | 0 | 0 | 100% | 0% | 0% | 100% | 26629.2954 | 0 | 0 | 26629.2954 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8876.4318 | 8876.4318 | 8876.4318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 827 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Stockpile Drain Pipe - Heat Trace Installation - Ore stockpile to effluent pond and Mary River | 4385.1-E | 2610 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 820 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4382-BLD-001 | 334.5725 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 187.5 | 656.25 | 14062.5 | 23437.5 | 38156.25 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 38156.25 | 0 | 0 | 38156.25 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12718.75 | 12718.75 | 12718.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 821 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Weigh Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4382-BLD-001 | 334.5725 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 48.582 | 607.2755 | 3643.6529 | 6072.7548 | 10323.6832 | 0.75 | 250.9294 | 100% | 0% | 0% | 100% | 10323.6832 | 0 | 0 | 10323.6832 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3441.2277 | 3441.2277 | 3441.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 822 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Weigh Building - Demolish floor finish - Gravel | 4382-BLD-001 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Truck Weigh Facility disturbed area |  | 13000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 165.0329 | 1901.25 | 12377.4702 | 5155.0895 | 19433.8097 | 0 | 0 | 100% | 0% | 0% | 100% | 19433.8097 | 0 | 0 | 19433.8097 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 19433.8097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour |  | Heli Pad |  | 5776 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 73.3254 | 844.74 | 5499.4052 | 2290.4459 | 8634.5911 | 0 | 0 | 100% | 0% | 0% | 100% | 8634.5911 | 0 | 0 | 8634.5911 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2878.197 | 2878.197 | 2878.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 839 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4431-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 833 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 4431-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 838 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4431-TK-001 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 834 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4431-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 835 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 4431-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4521-BLD-003 | 1296 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 726.3 | 2542.05 | 54472.5 | 90787.5 | 147802.05 | 1 | 1296 | 100% | 0% | 0% | 100% | 147802.05 | 0 | 0 | 147802.05 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 49267.35 | 49267.35 | 49267.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4521-BLD-003 | 1296 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 188.1874 | 2352.3423 | 14114.0538 | 23523.423 | 39989.8192 | 0.75 | 972 | 100% | 0% | 0% | 100% | 39989.8192 | 0 | 0 | 39989.8192 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13329.9397 | 13329.9397 | 13329.9397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4521-BLD-003 | 1296 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 162 | 2430 | 12150 | 24300 | 38880 | 0 | 0 | 100% | 0% | 0% | 100% | 38880 | 0 | 0 | 38880 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12960 | 12960 | 12960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 850 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4435-BLD-001 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 851 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Field Electrical Centre - Demolish and foundations - Gravel Base - Skidded Building | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 852 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Field Electrical Centre - Demolish floor finish - Raised Steel or Wooden Floor | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 899 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 902 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 905 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 908 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 911 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-005 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 914 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-006 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 917 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-007 | 611.803 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 137.1458 | 1714.3229 | 10285.9375 | 17143.2292 | 29143.4896 | 1 | 611.803 | 100% | 0% | 0% | 100% | 29143.4896 | 0 | 0 | 29143.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9714.4965 | 9714.4965 | 9714.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 900 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AA - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 901 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AA - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 903 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AB - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 904 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AB - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 906 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AC - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 907 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AC - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 909 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AD - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 910 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AD - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 912 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AE - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 913 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AE - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 915 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AF - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 916 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AF - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 918 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AG - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 919 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AG - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AH - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AH - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AI - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AI - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AI - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AJ - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AJ - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AJ - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AK - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AK - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AK - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AL - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-012 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AL - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AL - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AM - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-013 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AM - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AM - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – West side |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – East Side |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Quonset hut |  | 100 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 22.4167 | 280.2083 | 1681.25 | 2802.0833 | 4763.5417 | 1 | 100 | 100% | 0% | 0% | 100% | 4763.5417 | 0 | 0 | 4763.5417 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1587.8472 | 1587.8472 | 1587.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at Milne Port Firehall |  | 100 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 22.4167 | 280.2083 | 1681.25 | 2802.0833 | 4763.5417 | 1 | 100 | 100% | 0% | 0% | 100% | 4763.5417 | 0 | 0 | 4763.5417 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1587.8472 | 1587.8472 | 1587.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at the Aerodrome |  | 100 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 22.4167 | 280.2083 | 1681.25 | 2802.0833 | 4763.5417 | 1 | 100 | 100% | 0% | 0% | 100% | 4763.5417 | 0 | 0 | 4763.5417 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1587.8472 | 1587.8472 | 1587.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC lunch |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC office |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Construction of new offices and trailers at the OHT Laydown, and expansion of the OHT laydown |  | 400 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 89.6667 | 1120.8333 | 6725 | 11208.3333 | 19054.1667 | 1 | 400 | 100% | 0% | 0% | 100% | 19054.1667 | 0 | 0 | 19054.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6351.3889 | 6351.3889 | 6351.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Rail Operations offices |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (60 x 60) |  | 334 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 74.8717 | 935.8958 | 5615.375 | 9358.9583 | 15910.2292 | 1 | 334 | 100% | 0% | 0% | 100% | 15910.2292 | 0 | 0 | 15910.2292 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5303.4097 | 5303.4097 | 5303.4097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (24 x 60) |  | 132 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 29.59 | 369.875 | 2219.25 | 3698.75 | 6287.875 | 1 | 132 | 100% | 0% | 0% | 100% | 6287.875 | 0 | 0 | 6287.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2095.9583 | 2095.9583 | 2095.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (12 x 60) |  | 66 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 14.795 | 184.9375 | 1109.625 | 1849.375 | 3143.9375 | 1 | 66 | 100% | 0% | 0% | 100% | 3143.9375 | 0 | 0 | 3143.9375 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1047.9792 | 1047.9792 | 1047.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Lunchtrailer (44 x 10) |  | 40 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.9667 | 112.0833 | 672.5 | 1120.8333 | 1905.4167 | 1 | 40 | 100% | 0% | 0% | 100% | 1905.4167 | 0 | 0 | 1905.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 635.1389 | 635.1389 | 635.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container w lunchroom |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container Office |  | 144 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 32.28 | 403.5 | 2421 | 4035 | 6859.5 | 1 | 144 | 100% | 0% | 0% | 100% | 6859.5 | 0 | 0 | 6859.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2286.5 | 2286.5 | 2286.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Construction offices, lunchrooms, washcars (assume 50 units @ 36 m2 per wash car) |  | 1218 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 682.5875 | 3412.9375 | 51194.0625 | 85323.4375 | 139930.4375 | 1 | 1218 | 100% | 0% | 0% | 100% | 139930.4375 | 0 | 0 | 139930.4375 | Type B Construction 2BC-MRY1416 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 46643.4792 | 46643.4792 | 46643.4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 48.42 | 605.25 | 3631.5 | 6052.5 | 10289.25 | 1 | 216 | 100% | 0% | 0% | 100% | 10289.25 | 0 | 0 | 10289.25 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3429.75 | 3429.75 | 3429.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 50 person camp at Mine Site |  | 50 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 35040.0455 | 0 | 0 | 35040.0455 | 0 | 0 | 100% | 0% | 0% | 100% | 35040.0455 | 0 | 0 | 35040.0455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 35040.0455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 50- Person Rapid Deploy Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 170.3667 | 2129.5833 | 12777.5 | 21295.8333 | 36202.9167 | 0.5 | 475 | 100% | 0% | 0% | 100% | 36202.9167 | 0 | 0 | 36202.9167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 36202.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 35- Person 'Norse-man Style' Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 170.3667 | 2129.5833 | 12777.5 | 21295.8333 | 36202.9167 | 0.5 | 475 | 100% | 0% | 0% | 100% | 36202.9167 | 0 | 0 | 36202.9167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 36202.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 800 person camp at Mine Site |  | 800 | Bed Space | 0 | 700.8009 | 0 | 0 | 700.8009 | 0 | 560640.7273 | 0 | 0 | 560640.7273 | 0 | 0 | 100% | 0% | 0% | 100% | 560640.7273 | 0 | 0 | 560640.7273 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 560640.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 924 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 43.75 | 546.875 | 3281.25 | 5468.75 | 9296.875 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 9296.875 | 0 | 0 | 9296.875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3098.9583 | 3098.9583 | 3098.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 925 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 4513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 40.485 | 506.0629 | 3036.3774 | 5060.629 | 8603.0693 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 8603.0693 | 0 | 0 | 8603.0693 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2867.6898 | 2867.6898 | 2867.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 926 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 4513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 34.8513 | 522.7695 | 2613.8476 | 5227.6952 | 8364.3123 | 0 | 0 | 100% | 0% | 0% | 100% | 8364.3123 | 0 | 0 | 8364.3123 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2788.1041 | 2788.1041 | 2788.1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 937 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4513-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 921 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 20 | 250 | 1500 | 2500 | 4250 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4250 | 0 | 0 | 4250 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1416.6667 | 1416.6667 | 1416.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 939 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 4513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 938 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4513-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 922 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 11 | 87.5 | 525 | 875 | 1487.5 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1487.5 | 0 | 0 | 1487.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 495.8333 | 495.8333 | 495.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 923 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 4513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 859 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 1856.8773 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 416.25 | 5203.125 | 31218.75 | 52031.25 | 88453.125 | 1 | 1856.8773 | 100% | 0% | 0% | 100% | 88453.125 | 0 | 0 | 88453.125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 29484.375 | 29484.375 | 29484.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 862 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-002 | 607.8067 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 136.25 | 1703.125 | 10218.75 | 17031.25 | 28953.125 | 1 | 607.8067 | 100% | 0% | 0% | 100% | 28953.125 | 0 | 0 | 28953.125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9651.0417 | 9651.0417 | 9651.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 865 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 95 | 1187.5 | 7125 | 11875 | 20187.5 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 20187.5 | 0 | 0 | 20187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6729.1667 | 6729.1667 | 6729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 868 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laboratory - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-004 | 312.2677 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 70 | 875 | 5250 | 8750 | 14875 | 1 | 312.2677 | 100% | 0% | 0% | 100% | 14875 | 0 | 0 | 14875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4958.3333 | 4958.3333 | 4958.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 869 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laboratory - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 870 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laboratory - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 866 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 867 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 863 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 864 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 860 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 861 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 4333 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 629.179 | 7864.737 | 47188.4222 | 78647.3704 | 133700.5296 | 0.75 | 3249.75 | 100% | 0% | 0% | 100% | 133700.5296 | 0 | 0 | 133700.5296 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 44566.8432 | 44566.8432 | 44566.8432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Sailivik (800p) Camp Mine Dry |  | 1200 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 269 | 3362.5 | 20175 | 33625 | 57162.5 | 1 | 1200 | 100% | 0% | 0% | 100% | 57162.5 | 0 | 0 | 57162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 19054.1667 | 19054.1667 | 19054.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 13000 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 2914.1667 | 36427.0833 | 218562.5 | 364270.8333 | 619260.4167 | 1 | 13000 | 100% | 0% | 0% | 100% | 619260.4167 | 0 | 0 | 619260.4167 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 206420.1389 | 206420.1389 | 206420.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 975 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4521-TK-053 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washroom facility for Tote Road |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar |  | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-005 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 942 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-001 | 2416.3569 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1354.1667 | 4739.5833 | 101562.5 | 169270.8333 | 275572.9167 | 1 | 2416.3569 | 100% | 0% | 0% | 100% | 275572.9167 | 0 | 0 | 275572.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 91857.6389 | 91857.6389 | 91857.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 945 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-002 | 892.1933 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 500 | 1750 | 37500 | 62500 | 101750 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 101750 | 0 | 0 | 101750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33916.6667 | 33916.6667 | 33916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 943 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-001 | 2416.3569 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 350.8703 | 4385.8785 | 26315.2708 | 43858.7847 | 74559.9341 | 0.75 | 1812.2677 | 100% | 0% | 0% | 100% | 74559.9341 | 0 | 0 | 74559.9341 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24853.3114 | 24853.3114 | 24853.3114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 944 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-001 | 2416.3569 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 302.0446 | 4530.6691 | 22653.3457 | 45306.6914 | 72490.7063 | 0 | 0 | 100% | 0% | 0% | 100% | 72490.7063 | 0 | 0 | 72490.7063 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24163.5688 | 24163.5688 | 24163.5688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 948 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-003 | 390.3346 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 218.75 | 765.625 | 16406.25 | 27343.75 | 44515.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 44515.625 | 0 | 0 | 44515.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14838.5417 | 14838.5417 | 14838.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Crusher Dry Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Environment Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 16.14 | 201.75 | 1210.5 | 2017.5 | 3429.75 | 1 | 72 | 100% | 0% | 0% | 100% | 3429.75 | 0 | 0 | 3429.75 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1143.25 | 1143.25 | 1143.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Lunchroom |  | 36 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.07 | 100.875 | 605.25 | 1008.75 | 1714.875 | 1 | 36 | 100% | 0% | 0% | 100% | 1714.875 | 0 | 0 | 1714.875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 571.625 | 571.625 | 571.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-004 | 267.658 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 150 | 750 | 11250 | 18750 | 30750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 30750 | 0 | 0 | 30750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10250 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 946 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-002 | 892.1933 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 129.5521 | 1619.4013 | 9716.4077 | 16194.0128 | 27529.8218 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 27529.8218 | 0 | 0 | 27529.8218 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9176.6073 | 9176.6073 | 9176.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 947 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Warehouse - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-002 | 892.1933 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 111.5242 | 1672.8625 | 8364.3123 | 16728.6245 | 26765.7993 | 0 | 0 | 100% | 0% | 0% | 100% | 26765.7993 | 0 | 0 | 26765.7993 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8921.9331 | 8921.9331 | 8921.9331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 0 | Services Area |  | Waste Rock Facility |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Trasfer line for Deposit 1 to Waste Rock Facility |  | 3500 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 875 | 10937.5 | 65625 | 109375 | 185937.5 | 0.01 | 35 | 100% | 0% | 0% | 100% | 185937.5 | 0 | 0 | 185937.5 | Type A 2AM-MRY1325 | added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 61979.1667 | 61979.1667 | 61979.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 0 | Services Area |  | Bulk Fuel Storage |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Fuel Line from new (2019) bulk fuel storage facility to existing bulk fuel storage facility |  | 250 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 62.5 | 781.25 | 4687.5 | 7812.5 | 13281.25 | 0.01 | 2.5 | 100% | 0% | 0% | 100% | 13281.25 | 0 | 0 | 13281.25 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4427.0833 | 4427.0833 | 4427.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 976 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 4521.5-P | 405 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 101.25 | 1265.625 | 7593.75 | 12656.25 | 21515.625 | 0.01 | 4.05 | 100% | 0% | 100% | 0% | 21515.625 | 0 | 21515.625 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7171.875 | 7171.875 | 7171.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 949 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-003 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 950 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-003 | 390.3346 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 48.7918 | 731.8773 | 3659.3866 | 7318.7732 | 11710.0372 | 0 | 0 | 100% | 0% | 0% | 100% | 11710.0372 | 0 | 0 | 11710.0372 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3903.3457 | 3903.3457 | 3903.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 974 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 4521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 955 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-005 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 952 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-004 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 971 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 4521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 972 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL TANK | 4521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 973 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WAREHOUSE BUILDING DIESEL TANK | 4521-TK-023 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 956 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-005 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 953 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-004 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant building |  | 780 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 437.125 | 1529.9375 | 32784.375 | 54640.625 | 88954.9375 | 1 | 780 | 100% | 0% | 0% | 100% | 88954.9375 | 0 | 0 | 88954.9375 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 29651.6458 | 29651.6458 | 29651.6458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mine Truck Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1148.8542 | 4020.9896 | 86164.0625 | 143606.7708 | 233791.8229 | 1 | 2050 | 100% | 0% | 0% | 100% | 233791.8229 | 0 | 0 | 233791.8229 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 77930.6076 | 77930.6076 | 77930.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Rolling Stock Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 1148.8542 | 4020.9896 | 86164.0625 | 143606.7708 | 233791.8229 | 1 | 2050 | 100% | 0% | 0% | 100% | 233791.8229 | 0 | 0 | 233791.8229 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 77930.6076 | 77930.6076 | 77930.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-007 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-007 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-007 | 0 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Truck Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-008 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Truck Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-008 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Truck Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Maintenance Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-006 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Maintenance Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-006 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Maintenance Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-009 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-009 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER TANK - SIMER JET PUMPS 2205C L: 1803, W: 1245, H: 1346 |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 91.0364 | 348.0246 | 6827.7334 | 1299.3028 | 8475.0608 | 0 | 0 | 100% | 0% | 0% | 100% | 8475.0608 | 0 | 0 | 8475.0608 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2825.0203 | 2825.0203 | 2825.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 979 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - KIDNEY LOOP - AG - DYE10MFP240SA10QBV 50 kg | 4522-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 982 | MT- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | LATHE SPINDLE MOTOR | 4522-MT-004A | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1026 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - INCHING TOOL - AG | 4522-SQ-065 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1027 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-066 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1028 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-067 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Tire Shop at Ore Haul Truck Lineup (seacan construction) |  | 500 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 280.2083 | 1401.0417 | 21015.625 | 35026.0417 | 57442.7083 | 1 | 500 | 100% | 0% | 0% | 100% | 57442.7083 | 0 | 0 | 57442.7083 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 28721.3542 | 28721.3542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of seacan tent structure at the aerodrome for freight and equipment sorting |  | 1127 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 631.5896 | 3157.9479 | 47369.2188 | 78948.6979 | 129475.8646 | 1 | 1127 | 100% | 0% | 0% | 100% | 129475.8646 | 0 | 0 | 129475.8646 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 64737.9323 | 64737.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of new warehouse facility (seacan tent structure) on laydown LP2 |  | 1127 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 631.5896 | 3157.9479 | 47369.2188 | 78948.6979 | 129475.8646 | 1 | 1127 | 100% | 0% | 0% | 100% | 129475.8646 | 0 | 0 | 129475.8646 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 64737.9323 | 64737.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of warehouse parts/staging area (seacan tent structure) |  | 540 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 302.625 | 1513.125 | 22696.875 | 37828.125 | 62038.125 | 1 | 540 | 100% | 0% | 0% | 100% | 62038.125 | 0 | 0 | 62038.125 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 31019.0625 | 31019.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of offices and workshops at the stockpile and shiploader (seacan structure) |  | 208 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 116.5667 | 582.8333 | 8742.5 | 14570.8333 | 23896.1667 | 1 | 208 | 100% | 0% | 0% | 100% | 23896.1667 | 0 | 0 | 23896.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11948.0833 | 11948.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-001 | 1003.7175 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 562.5 | 1968.75 | 42187.5 | 70312.5 | 114468.75 | 1 | 1003.7175 | 100% | 0% | 0% | 100% | 114468.75 | 0 | 0 | 114468.75 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 38156.25 | 38156.25 | 38156.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-001 | 1003.7175 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 145.7461 | 1821.8264 | 10930.9587 | 18218.2644 | 30971.0495 | 0.75 | 752.7881 | 100% | 0% | 0% | 100% | 30971.0495 | 0 | 0 | 30971.0495 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10323.6832 | 10323.6832 | 10323.6832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1033 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-001 | 1003.7175 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Additional Truck Wash Building |  | 1500 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 840.625 | 2942.1875 | 63046.875 | 105078.125 | 171067.1875 | 1 | 1500 | 100% | 0% | 0% | 100% | 171067.1875 | 0 | 0 | 171067.1875 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 57022.3958 | 57022.3958 | 57022.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | New thaw and wash bay facilitiy for maintenance |  | 1250 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 700.5208 | 2451.8229 | 52539.0625 | 87565.1042 | 142555.9896 | 1 | 1250 | 100% | 0% | 0% | 100% | 142555.9896 | 0 | 0 | 142555.9896 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 47518.6632 | 47518.6632 | 47518.6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Additional Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 1500 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 217.8095 | 2722.6184 | 16335.7104 | 27226.1841 | 46284.5129 | 0.75 | 1125 | 100% | 0% | 0% | 100% | 46284.5129 | 0 | 0 | 46284.5129 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15428.171 | 15428.171 | 15428.171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Ore Haul Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-002 | 0 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Ore Haul Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-002 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Ore Haul Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical Office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 4.4833 | 56.0417 | 336.25 | 560.4167 | 952.7083 | 1 | 20 | 100% | 0% | 0% | 100% | 952.7083 | 0 | 0 | 952.7083 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 317.5694 | 317.5694 | 317.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | #REF! | 4500 | Non Process Facilities | 4530 | #REF! | 4530 | #REF! |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete Pad for tire maintenance at 110 Laydown |  | 60 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 7.5 | 112.5 | 562.5 | 1125 | 1800 | 0 | 0 | 100% | 0% | 0% | 100% | 1800 | 0 | 0 | 1800 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete pad apron for exterior of HD Shop |  | 1020 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 127.5 | 1912.5 | 9562.5 | 19125 | 30600 | 0 | 0 | 100% | 0% | 0% | 100% | 30600 | 0 | 0 | 30600 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10200 | 10200 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete Pad for tire maintenance and welding shop at 110 Laydown |  | 600 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 75 | 1125 | 5625 | 11250 | 18000 | 0 | 0 | 100% | 0% | 0% | 100% | 18000 | 0 | 0 | 18000 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Additional Buildings by BIM Site Services slab on grade |  | 180 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 22.5 | 337.5 | 1687.5 | 3375 | 5400 | 0 | 0 | 100% | 0% | 0% | 100% | 5400 | 0 | 0 | 5400 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1800 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1059 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-007 | 66.9145 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 37.5 | 187.5 | 2812.5 | 4687.5 | 7687.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 7687.5 | 0 | 0 | 7687.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2562.5 | 2562.5 | 2562.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1062 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-008 | 66.9145 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 37.5 | 187.5 | 2812.5 | 4687.5 | 7687.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 7687.5 | 0 | 0 | 7687.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2562.5 | 2562.5 | 2562.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1041 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1044 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1047 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1050 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1053 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1056 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1146 | 145.5729 | 2183.5938 | 3639.3229 | 5968.4896 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 5968.4896 | 0 | 0 | 5968.4896 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1989.4965 | 1989.4965 | 1989.4965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1065 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 4530-BLD-009 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1138.8889 | 1138.8889 | 1138.8889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1066 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1067 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1042 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1043 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1045 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1046 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1048 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1049 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1051 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1052 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1054 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1055 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1057 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1058 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1060 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1061 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1063 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1064 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-002 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-022 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-023 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #9 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-026 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #9 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #9 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #10 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-027 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #10 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #10 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-029 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-030 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 0 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-002 | 20 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 3.1383 | 39.2292 | 235.375 | 392.2917 | 666.8958 | 1 | 20 | 100% | 0% | 0% | 100% | 666.8958 | 0 | 0 | 666.8958 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.2986 | 222.2986 | 222.2986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-002 | 20 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 2.9041 | 36.3016 | 217.8095 | 363.0158 | 617.1268 | 0.75 | 15 | 100% | 0% | 0% | 100% | 617.1268 | 0 | 0 | 617.1268 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 205.7089 | 205.7089 | 205.7089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Existing Landfill |  | 6245 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1575.2302 | 12659.1573 | 103764.26 | 138730.4838 | 255153.901 | 0 | 0 | 100% | 0% | 0% | 100% | 255153.901 | 0 | 0 | 255153.901 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 255153.901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Heated Maintenance shop for pit equipment at KM110.5 laydown |  | 1500 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 840.625 | 2942.1875 | 63046.875 | 105078.125 | 171067.1875 | 1 | 1500 | 100% | 0% | 0% | 100% | 171067.1875 | 0 | 0 | 171067.1875 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 57022.3958 | 57022.3958 | 57022.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Heated Maintenance shops (2) for pit equipment at KM110.5 laydown |  | 180 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 100.875 | 353.0625 | 7565.625 | 12609.375 | 20528.0625 | 1 | 180 | 100% | 0% | 0% | 100% | 20528.0625 | 0 | 0 | 20528.0625 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6842.6875 | 6842.6875 | 6842.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 250 | 875 | 18750 | 31250 | 50875 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 50875 | 0 | 0 | 50875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16958.3333 | 16958.3333 | 16958.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1070 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 64.7761 | 809.7006 | 4858.2038 | 8097.0064 | 13764.9109 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 13764.9109 | 0 | 0 | 13764.9109 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4588.3036 | 4588.3036 | 4588.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1071 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 4540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 55.7621 | 836.4312 | 4182.1561 | 8364.3123 | 13382.8996 | 0 | 0 | 100% | 0% | 0% | 100% | 13382.8996 | 0 | 0 | 13382.8996 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4460.9665 | 4460.9665 | 4460.9665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 4540-VP-001 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1072 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 29.1667 | 145.8333 | 2187.5 | 3645.8333 | 5979.1667 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 5979.1667 | 0 | 0 | 5979.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1993.0556 | 1993.0556 | 1993.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1079 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 4540-SQ-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1073 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1074 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Lined Containment Cell |  | 900 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 40.0454 | 153.09 | 3003.4018 | 571.5408 | 3728.0326 | 0 | 0 | 100% | 0% | 0% | 100% | 3728.0326 | 0 | 0 | 3728.0326 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1242.6775 | 1242.6775 | 1242.6775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 9000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 400.4536 | 1530.9 | 30034.0178 | 5715.4081 | 37280.326 | 0 | 0 | 100% | 0% | 0% | 100% | 37280.326 | 0 | 0 | 37280.326 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12426.7753 | 12426.7753 | 12426.7753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 1 | MS-HWB-XX | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 2 | MS-HWB-XX | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new-by generator) - 3 | MS-HWB-XX | 160 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 7.1192 | 27.216 | 533.9381 | 101.6073 | 658.7073 | 0 | 0 | 100% | 0% | 0% | 100% | 658.7073 | 0 | 0 | 658.7073 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 219.5691 | 219.5691 | 219.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 4475 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 1128.7678 | 9071.2136 | 74354.6939 | 99410.5548 | 173765.2487 | 0 | 0 | 100% | 0% | 0% | 100% | 173765.2487 | 0 | 0 | 173765.2487 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 173765.2487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 400 | m2 | 0.25224 | 2.0271 | 16.6156 | 22.2146 | 38.8302 | 100.8954 | 810.8347 | 6646.2296 | 8885.8596 | 15532.0893 | 0 | 0 | 100% | 0% | 0% | 100% | 15532.0893 | 0 | 0 | 15532.0893 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 15532.0893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2018 Landfill Expansion |  | 63000 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 799.775 | 9213.75 | 59983.1249 | 24982.3568 | 94085.4818 | 0 | 0 | 100% | 0% | 0% | 100% | 94085.4818 | 0 | 0 | 94085.4818 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 94085.4818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm Containment Facilities 2020 HD Shop - 72m2, MR Shop - 120 m2, Wash Bay - 120 m2, 110 Laydown - 144 m2 |  | 456 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 20.2896 | 77.5656 | 1521.7236 | 289.5807 | 1877.3157 | 0 | 0 | 100% | 0% | 0% | 100% | 1877.3157 | 0 | 0 | 1877.3157 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 625.7719 | 625.7719 | 625.7719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - New 2019 |  | 360 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 16.0181 | 61.236 | 1201.3607 | 228.6163 | 1482.0913 | 0 | 0 | 100% | 0% | 0% | 100% | 1482.0913 | 0 | 0 | 1482.0913 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 494.0304 | 494.0304 | 494.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-2 | 1298 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 57.7543 | 220.7898 | 4331.5728 | 824.2889 | 5343.7626 | 0 | 0 | 100% | 0% | 0% | 100% | 5343.7626 | 0 | 0 | 5343.7626 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1781.2542 | 1781.2542 | 1781.2542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-1 | 754 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 33.5491 | 128.2554 | 2516.1833 | 478.8242 | 3123.2629 | 0 | 0 | 100% | 0% | 0% | 100% | 3123.2629 | 0 | 0 | 3123.2629 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1041.0876 | 1041.0876 | 1041.0876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-4 | 649 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 28.8772 | 110.3949 | 2165.7864 | 412.1444 | 2671.8813 | 0 | 0 | 100% | 0% | 0% | 100% | 2671.8813 | 0 | 0 | 2671.8813 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 890.6271 | 890.6271 | 890.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-3 | 600 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 26.6969 | 102.06 | 2002.2679 | 381.0272 | 2470.1522 | 0 | 0 | 100% | 0% | 0% | 100% | 2470.1522 | 0 | 0 | 2470.1522 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 823.3841 | 823.3841 | 823.3841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-6 | 550 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 24.4722 | 93.555 | 1835.4122 | 349.2749 | 2264.3062 | 0 | 0 | 100% | 0% | 0% | 100% | 2264.3062 | 0 | 0 | 2264.3062 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 754.7687 | 754.7687 | 754.7687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-5 | 347 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 15.4397 | 59.0247 | 1157.9782 | 220.3607 | 1428.5714 | 0 | 0 | 100% | 0% | 0% | 100% | 1428.5714 | 0 | 0 | 1428.5714 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 476.1905 | 476.1905 | 476.1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person camp at Mine Site |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 7925 | 0 | 0 | 7925 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | 15ML Arctic Diesel Tank Mine Site |  | 2 | Ea | 679.4 | 7847.5 | 50955 | 78475 | 137277.5 | 1358.8 | 15695 | 101910 | 156950 | 274555 | 160 | 320 | 100% | 0% | 0% | 100% | 274555 | 0 | 0 | 274555 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 137277.5 | 137277.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-009 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1102 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-010 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1103 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-011 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1104 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-012 | 1 | Ea | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 65.79 | 726.75 | 4934.25 | 7267.5 | 12928.5 | 40 | 40 | 100% | 0% | 0% | 100% | 12928.5 | 0 | 0 | 12928.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6464.25 | 6464.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1089 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 4613-FD-013 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1090 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 4613-FD-013 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 85.45 | 941.25 | 6408.75 | 9412.5 | 16762.5 | 30 | 60 | 100% | 0% | 0% | 100% | 16762.5 | 0 | 0 | 16762.5 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5587.5 | 5587.5 | 5587.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Site Fuel Tank Farm 2019 Footprint |  | 21620 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 274.4625 | 3161.925 | 20584.6851 | 8573.3104 | 32287.7479 | 0 | 0 | 100% | 0% | 0% | 100% | 32287.7479 | 0 | 0 | 32287.7479 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10762.5826 | 10762.5826 | 10762.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (North West) |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (South West) |  | 0 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Farm Tank Dike |  | 1911.3 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 85.043 | 325.1121 | 6378.2243 | 1213.7622 | 7917.0986 | 0 | 0 | 100% | 0% | 0% | 100% | 7917.0986 | 0 | 0 | 7917.0986 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3958.5493 | 3958.5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 12000 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 533.9381 | 2041.2 | 40045.3571 | 7620.5441 | 49707.1013 | 0 | 0 | 100% | 0% | 0% | 100% | 49707.1013 | 0 | 0 | 49707.1013 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 24853.5506 | 24853.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 400 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 17.7979 | 68.04 | 1334.8452 | 254.0181 | 1656.9034 | 0 | 0 | 100% | 0% | 0% | 100% | 1656.9034 | 0 | 0 | 1656.9034 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 828.4517 | 828.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4614 | Jet-A System | 416 | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | Tank - Jet-A tanks @ aerodrome apron |  | 0 | Ea | 42.725 | 470.625 | 3204.375 | 4706.25 | 8381.25 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1119 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Raw Water Supply Pipe - Piping Installation - Pumphouse to Water Building | 4712.2-P | 8518 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 2129.5 | 26618.75 | 159712.5 | 266187.5 | 452518.75 | 0.01 | 85.18 | 100% | 0% | 100% | 0% | 452518.75 | 0 | 452518.75 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 150839.5833 | 150839.5833 | 150839.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1115 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Pumphouse - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4712-BLD-001 | 14.8699 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 3.3333 | 41.6667 | 250 | 416.6667 | 708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 708.3333 | 0 | 0 | 708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 236.1111 | 236.1111 | 236.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1116 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Pumphouse - Demolish and foundations - Gravel Base - Skidded Building | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1117 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Pumphouse - Demolish floor finish - Raised Steel or Wooden Floor | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1118 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Raw Water Supply Pipe - Heat Trace Installation - Pumphouse to Water Building | 4712.2-E | 4712 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System |  |  | piping | Piping | Piping | Bulks | Piping |  | Raw Water Intake Pipeline |  |  | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1121 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 61.25 | 765.625 | 4593.75 | 7656.25 | 13015.625 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 13015.625 | 0 | 0 | 13015.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4338.5417 | 4338.5417 | 4338.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1122 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 56.679 | 708.4881 | 4250.9284 | 7084.8806 | 12044.297 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 12044.297 | 0 | 0 | 12044.297 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4014.7657 | 4014.7657 | 4014.7657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE | 4720-VP-020 | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1143 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 4720-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1144 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 4720-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1145 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 4720-TK-009 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1146 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 4720-TK-012 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1123 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 4720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Infill between service and utility pads |  | 20800 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 264.0527 | 3042 | 19803.9523 | 8248.1432 | 31063.1432 | 0 | 0 | 100% | 0% | 0% | 100% | 31063.1432 | 0 | 0 | 31063.1432 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10354.3811 | 10354.3811 | 10354.3811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK (40 m3) |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK (60 m3) |  | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | VENDOR PACKAGE - POTABLE WATER TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP7 | VENDOR PKG - WRF Water Treatment System | VP7 | Packaged Facilities | WRF Water Treatment |  | Water Treatment Plant for the Waste Rock Facility |  | 1 | Ea | 340 | 3625 | 25500 | 36250 | 61750 | 340 | 3625 | 25500 | 36250 | 61750 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 61750 | 0 | 61750 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20583.3333 | 20583.3333 | 20583.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 800-person camp at Mine Site |  | 1 | Ea | 47 | 400 | 3525 | 4000 | 7925 | 47 | 400 | 3525 | 4000 | 7925 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 7925 | 0 | 7925 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2641.6667 | 2641.6667 | 2641.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1154 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 100 | 500 | 7500 | 12500 | 20500 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 20500 | 0 | 0 | 20500 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 10250 | 10250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1163 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 4731.2-P | 247 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 61.75 | 771.875 | 4631.25 | 7718.75 | 13121.875 | 0.01 | 2.47 | 100% | 0% | 100% | 0% | 13121.875 | 0 | 13121.875 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6560.9375 | 6560.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1161 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 4731-VP-005 | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1160 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - TREATED EFFLUENT TANK | 4731-TK-002 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1966.6667 | 1966.6667 | 1966.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1151 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 4731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 16.6667 | 83.3333 | 1250 | 2083.3333 | 3416.6667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3416.6667 | 0 | 0 | 3416.6667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1708.3333 | 1708.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1152 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1153 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1162 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 4731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1155 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 4731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1156 | VP- |  | #N/A |  |  |  |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 4731-VP-005 | 1920 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - 800p camp to final discharge point |  | 2200 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 550 | 6875 | 41250 | 68750 | 116875 | 0.01 | 22 | 100% | 0% | 100% | 0% | 116875 | 0 | 116875 | 0 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 58437.5 | 58437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE |  | 0 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 800-person camp at Mine Site |  | 1 | Ea | 51 | 450 | 3825 | 4500 | 8775 | 51 | 450 | 3825 | 4500 | 8775 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8775 | 0 | 8775 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4387.5 | 4387.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1165 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 31.25 | 109.375 | 2343.75 | 3906.25 | 6359.375 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 6359.375 | 0 | 0 | 6359.375 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3179.6875 | 3179.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4280 | Mine Support Facilities |  | Water Systems |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Soft Walled Building (tent) Contaminated (480 ft2) |  | Tent Structure for Waste Rock Facility Water Treatment System |  | 726 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 423.137 | 1627.45 | 39033.4257 | 52892.125 | 93553.0007 | 0.5 | 363 | 100% | 0% | 0% | 100% | 93553.0007 | 0 | 0 | 93553.0007 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 46776.5004 | 46776.5004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1172 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 15.5 | 162.5 | 1162.5 | 1625 | 2950 | 20 | 20 | 100% | 0% | 0% | 100% | 2950 | 0 | 0 | 2950 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1475 | 1475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1166 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 8.097 | 101.2126 | 607.2755 | 1012.1258 | 1720.6139 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1720.6139 | 0 | 0 | 1720.6139 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 860.3069 | 860.3069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1167 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 4732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1178 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to connection with Stockpile Drain Pipe | 4734.1-P | 2125 | m | 0.25 | 3.125 | 18.75 | 31.25 | 53.125 | 531.25 | 6640.625 | 39843.75 | 66406.25 | 112890.625 | 0.01 | 21.25 | 100% | 0% | 100% | 0% | 112890.625 | 0 | 112890.625 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 37630.2083 | 37630.2083 | 37630.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1177 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to connection with Stockpile Drain Pipe | 4734.1-E | 2050 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1174 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE | 4733-VM-001 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1175 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE SPARE | 4733-VM-002 | 0 | Ea | 2 | 25 | 150 | 250 | 425 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | FRP Water tanks for 800p camp |  | 4 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 38.6667 | 358.3333 | 2900 | 3583.3333 | 6841.6667 | 1 | 4 | 100% | 0% | 0% | 100% | 6841.6667 | 0 | 0 | 6841.6667 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2280.5556 | 2280.5556 | 2280.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Water Tank 10,000L |  | 4 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 38.6667 | 358.3333 | 2900 | 3583.3333 | 6841.6667 | 1 | 4 | 100% | 0% | 0% | 100% | 6841.6667 | 0 | 0 | 6841.6667 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2280.5556 | 2280.5556 | 2280.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | -3 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -29 | -268.75 | -2175 | -2687.5 | -5131.25 | 1 | -3 | 100% | 0% | 0% | 100% | -5131.25 | 0 | 0 | -5131.25 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1710.4167 | -1710.4167 | -1710.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 2 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 19.3333 | 179.1667 | 1450 | 1791.6667 | 3420.8333 | 1 | 2 | 100% | 0% | 0% | 100% | 3420.8333 | 0 | 0 | 3420.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1140.2778 | 1140.2778 | 1140.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | 2 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 19.3333 | 179.1667 | 1450 | 1791.6667 | 3420.8333 | 1 | 2 | 100% | 0% | 0% | 100% | 3420.8333 | 0 | 0 | 3420.8333 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1140.2778 | 1140.2778 | 1140.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | -1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | -9.6667 | -89.5833 | -725 | -895.8333 | -1710.4167 | 1 | -1 | 100% | 0% | 0% | 100% | -1710.4167 | 0 | 0 | -1710.4167 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -570.1389 | -570.1389 | -570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 3 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 93 | 975 | 6975 | 9750 | 17700 | 2 | 6 | 100% | 0% | 0% | 100% | 17700 | 0 | 0 | 17700 | Type B Construction 2BC-MRY1416 | Confirmed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 8850 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1204 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV & Ground Wire - Electrical distribution system from power gen to e-house | 4750.2-E | 11000 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 1100 | 13750 | 82500 | 137500 | 233750 | 0.01 | 110 | 100% | 0% | 0% | 100% | 233750 | 0 | 0 | 233750 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 77916.6667 | 77916.6667 | 77916.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 4750.3-E | 5200 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 520 | 6500 | 39000 | 65000 | 110500 | 0.01 | 52 | 100% | 0% | 0% | 100% | 110500 | 0 | 0 | 110500 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 36833.3333 | 36833.3333 | 36833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation - Mary River Powerhouse to Dyno Nobel explosives facility (500 m), and Mary River E-House 3 to KM 104 laydown (300 m) |  | 800 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 80 | 1000 | 6000 | 10000 | 17000 | 0.01 | 8 | 100% | 0% | 0% | 100% | 17000 | 0 | 0 | 17000 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5666.6667 | 5666.6667 | 5666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1180 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1201 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing & Screening E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 59.4796 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 13.3333 | 166.6667 | 1000 | 1666.6667 | 2833.3333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 2833.3333 | 0 | 0 | 2833.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 944.4444 | 944.4444 | 944.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1183 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1186 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1189 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1192 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-005 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 885.4167 | 885.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1195 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Aerodrome Area E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-006 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1198 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Supply E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-007 | 37.1747 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3333 | 104.1667 | 625 | 1041.6667 | 1770.8333 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1770.8333 | 0 | 0 | 1770.8333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.2778 | 590.2778 | 590.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1184 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1185 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1187 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1188 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1190 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1191 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1193 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1194 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1196 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Area E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1197 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Area E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1199 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Supply E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1200 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Supply E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1181 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1182 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1202 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1203 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Cabling for Lighting at Mine Site Warehouse |  | 600 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 60 | 750 | 4500 | 7500 | 12750 | 0.01 | 6 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Mine Site |  | 3500 | m | 0.1 | 1.25 | 7.5 | 12.5 | 21.25 | 350 | 4375 | 26250 | 43750 | 74375 | 0.01 | 35 | 100% | 0% | 0% | 100% | 74375 | 0 | 0 | 74375 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24791.6667 | 24791.6667 | 24791.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-012 | 37.1612 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 8.3303 | 104.1288 | 624.773 | 1041.2883 | 1770.1901 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 1770.1901 | 0 | 0 | 1770.1901 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 590.0634 | 590.0634 | 590.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #2- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment
5000 | Baffinland Owned Equipment | 5100 | Project Wide
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 74 | m2 | 168 | 1850 | 12600 | 18500 | 32950 | 12432 | 136900 | 932400 | 1369000 | 2438300 | 56 | 4144 | 100% | 0% | 0% | 100% | 2438300 | 0 | 0 | 2438300 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2438300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 183 | m2 | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 3513.6 | 32482.5 | 263520 | 324825 | 620827.5 | 1 | 183 | 100% | 0% | 0% | 100% | 620827.5 | 0 | 0 | 620827.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 620827.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 220 | m2 | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 1782 | 19525 | 133650 | 195250 | 348425 | 0.5 | 110 | 100% | 0% | 0% | 100% | 348425 | 0 | 0 | 348425 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 348425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 312 | m2 | 13 | 100 | 975 | 1000 | 2075 | 4056 | 31200 | 304200 | 312000 | 647400 | 96 | 29952 | 100% | 0% | 0% | 100% | 647400 | 0 | 0 | 647400 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 647400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 326 | m2 | 10 | 37.5 | 750 | 375 | 1162.5 | 3260 | 12225 | 244500 | 122250 | 378975 | 24 | 7824 | 100% | 0% | 0% | 100% | 378975 | 0 | 0 | 378975 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 378975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 297 | m2 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 1980 | 6187.5 | 148500 | 61875 | 216562.5 | 4 | 1188 | 100% | 0% | 0% | 100% | 216562.5 | 0 | 0 | 216562.5 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 216562.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Arbitration Reconciliation for 2020 Work Plan |  | -49 | m2 | 13 | 100 | 975 | 1000 | 2075 | -637 | -4900 | -47775 | -49000 | -101675 | 96 | -4704 | 100% | 0% | 0% | 100% | -101675 | 0 | 0 | -101675 | Type A 2AM-MRY1325 | Removed | 2020-AR | Direct |  |  | 100% | [10 empty] | 0 | 0 | -101675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Arbitration Reconciliation for 2020 Work Plan |  | -61 | m2 | 10 | 37.5 | 750 | 375 | 1162.5 | -610 | -2287.5 | -45750 | -22875 | -70912.5 | 24 | -1464 | 100% | 0% | 0% | 100% | -70912.5 | 0 | 0 | -70912.5 | Type A 2AM-MRY1325 | Removed | 2020-AR | Direct |  |  | 100% | [10 empty] | 0 | 0 | -70912.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Arbitration Reconciliation for 2020 Work Plan |  | -34 | m2 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -226.6667 | -708.3333 | -17000 | -7083.3333 | -24791.6667 | 4 | -136 | 100% | 0% | 0% | 100% | -24791.6667 | 0 | 0 | -24791.6667 | Type A 2AM-MRY1325 | Removed | 2020-AR | Direct |  |  | 100% | [10 empty] | 0 | 0 | -24791.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 317 | MT- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Generator/Air Compressor |  | -1 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | -8.1 | -88.75 | -607.5 | -887.5 | -1583.75 | 0.5 | -0.5 | 100% | 0% | 0% | 100% | -1583.75 | 0 | 0 | -1583.75 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1583.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | -21 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | -170.1 | -1863.75 | -12757.5 | -18637.5 | -33258.75 | 0.5 | -10.5 | 100% | 0% | 0% | 100% | -33258.75 | 0 | 0 | -33258.75 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -33258.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | -7 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | -56.7 | -621.25 | -4252.5 | -6212.5 | -11086.25 | 0.5 | -3.5 | 100% | 0% | 0% | 100% | -11086.25 | 0 | 0 | -11086.25 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -11086.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | 10 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 81 | 887.5 | 6075 | 8875 | 15837.5 | 0.5 | 5 | 100% | 0% | 0% | 100% | 15837.5 | 0 | 0 | 15837.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 15837.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1263 | PP- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Water Jet - Ceramic Cutting |  | 1 | Ea | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 8.1 | 88.75 | 607.5 | 887.5 | 1583.75 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1583.75 | 0 | 0 | 1583.75 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1583.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Rescue Boat and Trailer |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Ford F350 Pickup |  | 3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 20 | 62.5 | 1500 | 625 | 2187.5 | 4 | 12 | 100% | 0% | 0% | 100% | 2187.5 | 0 | 0 | 2187.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Welding Shop Crane |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 30,000 L Fuel Tanker Truck |  | -11 | Ea | 13 | 100 | 975 | 1000 | 2075 | -143 | -1100 | -10725 | -11000 | -22825 | 96 | -1056 | 100% | 0% | 0% | 100% | -22825 | 0 | 0 | -22825 | Type A 2AM-MRY1325 | removed | 2020-r | Direct |  |  | 100% | [10 empty] | 0 | 0 | -22825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | USED TANDEM DRIVE WESTERN STAR WINCH TRUCK UNIT# 587 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | USED WINCH TRUCK WESTERN STAR UNIT# 586 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740 Articulated Truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Western Star Haul Truck |  | -2 | Ea | 13 | 100 | 975 | 1000 | 2075 | -26 | -200 | -1950 | -2000 | -4150 | 96 | -192 | 100% | 0% | 0% | 100% | -4150 | 0 | 0 | -4150 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 Loader |  | -2 | Ea | 13 | 100 | 975 | 1000 | 2075 | -26 | -200 | -1950 | -2000 | -4150 | 96 | -192 | 100% | 0% | 0% | 100% | -4150 | 0 | 0 | -4150 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 Loader |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950 Loader |  | -2 | Ea | 13 | 100 | 975 | 1000 | 2075 | -26 | -200 | -1950 | -2000 | -4150 | 96 | -192 | 100% | 0% | 0% | 100% | -4150 | 0 | 0 | -4150 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950 Loader |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374F Excavator |  | -4 | Ea | 13 | 100 | 975 | 1000 | 2075 | -52 | -400 | -3900 | -4000 | -8300 | 96 | -384 | 100% | 0% | 0% | 100% | -8300 | 0 | 0 | -8300 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374F Excavator |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 CAT Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck |  | 4 | Ea | 13 | 100 | 975 | 1000 | 2075 | 52 | 400 | 3900 | 4000 | 8300 | 96 | 384 | 100% | 0% | 0% | 100% | 8300 | 0 | 0 | 8300 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 8300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Duty Shunt Truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Decommissioned Drill |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Feeder Dolly |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fines Mobile Stacker |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Boat Trailer |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Tire Changer |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Argo Vehicle |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Larue Snow Blower |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Larue Snow Blower |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 257 Skid steer |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 257 Skid steer |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Blaze Cube Frost Fighters |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Blaze Cube Frost Fighters |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 Fire Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 740B Water Truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 14M Grader |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel Tanker |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Jet A Truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | -2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -20 | -75 | -1500 | -750 | -2325 | 24 | -48 | 100% | 0% | 0% | 100% | -2325 | 0 | 0 | -2325 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Track Mounted Drill Rig |  | -2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -20 | -75 | -1500 | -750 | -2325 | 24 | -48 | 100% | 0% | 0% | 100% | -2325 | 0 | 0 | -2325 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -20 | -75 | -1500 | -750 | -2325 | 24 | -48 | 100% | 0% | 0% | 100% | -2325 | 0 | 0 | -2325 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 740B Water Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 14M Grader |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel Tanker |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Jet A Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Bus |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48p School Bus |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48p School Bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Track Mounted Drill Rig |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 15 passenger crew van |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Deckover Trailer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat bed boom truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat bed boom truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Duel Engine Marine Response Boat |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tower Trailer |  | 3 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 30 | 112.5 | 2250 | 1125 | 3487.5 | 24 | 72 | 100% | 0% | 0% | 100% | 3487.5 | 0 | 0 | 3487.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Kalamar DRT450 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D8T Dozer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tri-Trombone flat trailer |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 349 Cat Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 320 Track Cat Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | HPS 185 Spray Unit for Stockpile Dust suppression |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Jump Conveyor |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Conveyor Feeder |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Stacker |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 131800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen |  | 4 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 672 | 7400 | 50400 | 74000 | 131800 | 56 | 224 | 100% | 0% | 0% | 100% | 131800 | 0 | 0 | 131800 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 131800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Feed Conveyor |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator 1000 kW |  | -1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -168 | -1850 | -12600 | -18500 | -32950 | 56 | -56 | 100% | 0% | 0% | 100% | -32950 | 0 | 0 | -32950 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator 1000 kW |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Conveyors |  | 3 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 504 | 5550 | 37800 | 55500 | 98850 | 56 | 168 | 100% | 0% | 0% | 100% | 98850 | 0 | 0 | 98850 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 98850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw crusher unit |  | -1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -168 | -1850 | -12600 | -18500 | -32950 | 56 | -56 | 100% | 0% | 0% | 100% | -32950 | 0 | 0 | -32950 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw crusher unit |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screener + Cone crusher unit |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator Sets |  | 1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | 168 | 1850 | 12600 | 18500 | 32950 | 56 | 56 | 100% | 0% | 0% | 100% | 32950 | 0 | 0 | 32950 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Bucket Wheel Stacker Reclaimer |  | -2 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -336 | -3700 | -25200 | -37000 | -65900 | 56 | -112 | 100% | 0% | 0% | 100% | -65900 | 0 | 0 | -65900 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -65900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 600kw Generators |  | -2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | -38.4 | -355 | -2880 | -3550 | -6785 | 1 | -2 | 100% | 0% | 0% | 100% | -6785 | 0 | 0 | -6785 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 60kw Generator |  | -3 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | -57.6 | -532.5 | -4320 | -5325 | -10177.5 | 1 | -3 | 100% | 0% | 0% | 100% | -10177.5 | 0 | 0 | -10177.5 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -10177.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Atlas 1000 mVA Transformers |  | -4 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | -76.8 | -710 | -5760 | -7100 | -13570 | 1 | -4 | 100% | 0% | 0% | 100% | -13570 | 0 | 0 | -13570 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -13570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 600kw Generators |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 60kw Generator |  | 3 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 57.6 | 532.5 | 4320 | 5325 | 10177.5 | 1 | 3 | 100% | 0% | 0% | 100% | 10177.5 | 0 | 0 | 10177.5 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 10177.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Atlas 1000 mVA Transformers |  | 4 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 76.8 | 710 | 5760 | 7100 | 13570 | 1 | 4 | 100% | 0% | 0% | 100% | 13570 | 0 | 0 | 13570 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 13570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light ERT utility vehicle |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Portable water pump |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Pickup truck (F350 or similar) |  | -7 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -46.6667 | -145.8333 | -3500 | -1458.3333 | -5104.1667 | 4 | -28 | 100% | 0% | 0% | 100% | -5104.1667 | 0 | 0 | -5104.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -5104.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F-350 Pickup |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F-350 Pickup |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift z60 |  | -2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -13.3333 | -41.6667 | -1000 | -416.6667 | -1458.3333 | 4 | -8 | 100% | 0% | 0% | 100% | -1458.3333 | 0 | 0 | -1458.3333 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift s135x |  | -3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -20 | -62.5 | -1500 | -625 | -2187.5 | 4 | -12 | 100% | 0% | 0% | 100% | -2187.5 | 0 | 0 | -2187.5 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Shovel 6060 |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Heated Water Truck - Drill Water System |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Pumper fire truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 922K Wheel Loader |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390 Excavator |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793F Haul Truck |  | 3 | Ea | 13 | 100 | 975 | 1000 | 2075 | 39 | 300 | 2925 | 3000 | 6225 | 96 | 288 | 100% | 0% | 0% | 100% | 6225 | 0 | 0 | 6225 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -1 | Ea | 13 | 100 | 975 | 1000 | 2075 | -13 | -100 | -975 | -1000 | -2075 | 96 | -96 | 100% | 0% | 0% | 100% | -2075 | 0 | 0 | -2075 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Tripper Car |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Water Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Zoom Boom 12,000 lbs |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Boom Truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat Bed Boom Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | -1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | -10 | -37.5 | -750 | -375 | -1162.5 | 24 | -24 | 100% | 0% | 0% | 100% | -1162.5 | 0 | 0 | -1162.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 Person School Bus |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | 2 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 20 | 75 | 1500 | 750 | 2325 | 24 | 48 | 100% | 0% | 0% | 100% | 2325 | 0 | 0 | 2325 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Spreader Box |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Spare 793 Box |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Vac Truck |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740 Water Truck |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M Grader |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 CATERPILLAR LOADER |  | 2 | Ea | 13 | 100 | 975 | 1000 | 2075 | 26 | 200 | 1950 | 2000 | 4150 | 96 | 192 | 100% | 0% | 0% | 100% | 4150 | 0 | 0 | 4150 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Epiroc D65 Drill |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 Service/Fuel Truck |  | 4 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 40 | 150 | 3000 | 1500 | 4650 | 24 | 96 | 100% | 0% | 0% | 100% | 4650 | 0 | 0 | 4650 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Service Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Decommissioned vehicles |  | -3 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -20 | -62.5 | -1500 | -625 | -2187.5 | 4 | -12 | 100% | 0% | 0% | 100% | -2187.5 | 0 | 0 | -2187.5 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HAGGLUNDS SNOW RESCUE VEHICLE |  | -1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -6.6667 | -20.8333 | -500 | -208.3333 | -729.1667 | 4 | -4 | 100% | 0% | 0% | 100% | -729.1667 | 0 | 0 | -729.1667 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Land Cruiser Service Truck |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light Vehicle |  | 8 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 53.3333 | 166.6667 | 4000 | 1666.6667 | 5833.3333 | 4 | 32 | 100% | 0% | 0% | 100% | 5833.3333 | 0 | 0 | 5833.3333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 5833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER |  | 2 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 13.3333 | 41.6667 | 1000 | 416.6667 | 1458.3333 | 4 | 8 | 100% | 0% | 0% | 100% | 1458.3333 | 0 | 0 | 1458.3333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1458.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER - 257D |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 4 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 705 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | Welding Shop Crane |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | Steam Truck |  | 1 | Ea | 10 | 37.5 | 750 | 375 | 1162.5 | 10 | 37.5 | 750 | 375 | 1162.5 | 24 | 24 | 100% | 0% | 0% | 100% | 1162.5 | 0 | 0 | 1162.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1162.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | SPYDER CRANE URW295 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | SPYDER CRANE URW706 |  | 1 | Ea | 13 | 100 | 975 | 1000 | 2075 | 13 | 100 | 975 | 1000 | 2075 | 96 | 96 | 100% | 0% | 0% | 100% | 2075 | 0 | 0 | 2075 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen Metso FS353 |  | -1 | Ea | 168 | 1850 | 12600 | 18500 | 32950 | -168 | -1850 | -12600 | -18500 | -32950 | 56 | -56 | 100% | 0% | 0% | 100% | -32950 | 0 | 0 | -32950 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -32950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 1500 kW Alternators |  | 2 | Ea | 19.2 | 177.5 | 1440 | 1775 | 3392.5 | 38.4 | 355 | 2880 | 3550 | 6785 | 1 | 2 | 100% | 0% | 0% | 100% | 6785 | 0 | 0 | 6785 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Power plant generators | Gensets/compressors for field maintenance |  | 1 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | 4 | 2 | 100% | 0% | 0% | 100% | 729.1667 | 0 | 0 | 729.1667 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 729.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Frost Fighter Heater |  | -6 | Ea | 6.6667 | 20.8333 | 500 | 208.3333 | 729.1667 | -40 | -125 | -3000 | -1250 | -4375 | 4 | -24 | 100% | 0% | 0% | 100% | -4375 | 0 | 0 | -4375 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas
6000 | Disturbed Areas | 6100 | Project Wide
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area Reconciliation - 2020 Satellite Image - IOL |  | 5078123 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 64465.9653 | 742675.4887 | 4834947.4 | 2013706.0409 | 7591328.9296 | 0 | 0 | 100% | 0% | 0% | 100% | 7591328.9296 | 0 | 0 | 7591328.9296 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2530442.9765 | 2530442.9765 | 2530442.9765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area Reconciliation - 2021 Work Plan and Prior - IOL |  | 3160642 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 40123.8484 | 462243.8925 | 3009288.6329 | 1253337.8748 | 4724870.4001 | 0 | 0 | 100% | 0% | 0% | 100% | 4724870.4001 | 0 | 0 | 4724870.4001 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1574956.8 | 1574956.8 | 1574956.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2021 - IOL |  | -8355237 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -106068.4073 | -1221953.4112 | -7955130.5491 | -3313230.3452 | -12490314.3055 | 0 | 0 | 100% | 0% | 0% | 100% | -12490314.3055 | 0 | 0 | -12490314.3055 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -4163438.1018 | -4163438.1018 | -4163438.1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2021 - Crown |  | -362320 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | -4599.5949 | -52989.3 | -344969.6161 | -143676.3097 | -541635.2258 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -541635.2258 | 0 | -541635.2258 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -180545.0753 | -180545.0753 | -180545.0753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area - 2020 Satellite Image - Crown Land |  | 143305 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 1819.2342 | 20958.3562 | 136442.5669 | 56826.9308 | 214227.8539 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 214227.8539 | 0 | 214227.8539 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 71409.2846 | 71409.2846 | 71409.2846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area - 2021 Work Plan and Prior - Crown Land |  | 332244 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 4217.7848 | 48590.685 | 316333.8627 | 131749.8119 | 496674.3596 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 496674.3596 | 0 | 496674.3596 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 165558.1199 | 165558.1199 | 165558.1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Lined Disturbed Area - 2020 Satellite Image - IOL |  | 114884 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 5111.7453 | 19541.7684 | 383380.9007 | 72956.5495 | 475879.2186 | 0 | 0 | 100% | 0% | 0% | 100% | 475879.2186 | 0 | 0 | 475879.2186 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 158626.4062 | 158626.4062 | 158626.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Lined Disturbed Area - 2021 Work Plan and Prior - IOL |  | 15714 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 699.1919 | 2672.9514 | 52439.3952 | 9979.1026 | 65091.4491 | 0 | 0 | 100% | 0% | 0% | 100% | 65091.4491 | 0 | 0 | 65091.4491 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 21697.1497 | 21697.1497 | 21697.1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2021 - Lined - IOL |  | -219252 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | -9755.5829 | -37294.7652 | -731668.72 | -139234.9622 | -908198.4474 | 0 | 0 | 100% | 0% | 0% | 100% | -908198.4474 | 0 | 0 | -908198.4474 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -302732.8158 | -302732.8158 | -302732.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services
7000 | Construction Facilities & Services | 7200 | Milne Port
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Existing Trailer Camp (Shanco) |  | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | 49-person Hard Wall Trailer Camp (previously at Steensby) |  | 950 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 212.9583 | 2661.9792 | 15971.875 | 26619.7917 | 45253.6458 | 1 | 950 | 100% | 0% | 0% | 100% | 45253.6458 | 0 | 0 | 45253.6458 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 45253.6458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Matrix Camp |  | 5392.34 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 967.0263 | 12087.8288 | 72526.973 | 120878.2883 | 205493.0902 | 0.5 | 2696.17 | 100% | 0% | 0% | 100% | 205493.0902 | 0 | 0 | 205493.0902 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 68497.6967 | 68497.6967 | 68497.6967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tents |  | 0 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 1252.363 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 729.9189 | 2807.3804 | 67333.3583 | 91239.8627 | 161380.6014 | 0.5 | 626.1815 | 100% | 0% | 0% | 100% | 161380.6014 | 0 | 0 | 161380.6014 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53793.5338 | 53793.5338 | 53793.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 878.1618 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 511.822 | 1968.546 | 47214.4124 | 63977.7461 | 113160.7046 | 0.5 | 439.0809 | 100% | 0% | 0% | 100% | 113160.7046 | 0 | 0 | 113160.7046 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 37720.2349 | 37720.2349 | 37720.2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 250.24 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 140.2387 | 490.8353 | 10517.9 | 17529.8333 | 28538.5687 | 1 | 250.24 | 100% | 0% | 0% | 100% | 28538.5687 | 0 | 0 | 28538.5687 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 28538.5687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD |  | #N/A |  |  |  |  | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD |  | #N/A |  |  |  |  | Construction Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish floor finish - Gravel | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 1192.477 | 4586.45 | 110003.2907 | 149059.625 | 263649.3657 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 263649.3657 | 0 | 0 | 263649.3657 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87883.1219 | 87883.1219 | 87883.1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 255.75 | 3836.25 | 19181.25 | 38362.5 | 61380 | 0 | 0 | 100% | 0% | 0% | 100% | 61380 | 0 | 0 | 61380 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 61380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1222 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Construction Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 7231-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 60 | 750 | 4500 | 7500 | 12750 | 1 | 267.658 | 100% | 0% | 0% | 100% | 12750 | 0 | 0 | 12750 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4250 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1230 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7231-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1225 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 7231-BLD-002 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1231 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 7231-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1226 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1227 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1223 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Office - Demolish and foundations - Gravel Base - Skidded Building | 7231-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1224 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Construction Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 33 | 262.5 | 1575 | 2625 | 4462.5 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 4462.5 | 0 | 0 | 4462.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1487.5 | 1487.5 | 1487.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 0 | 0 | 100% | 0% | 0% | 100% | 22405.6604 | 0 | 0 | 22405.6604 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7468.5535 | 7468.5535 | 7468.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1286 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Heated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-002 | 371.7472 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 58.3333 | 729.1667 | 4375 | 7291.6667 | 12395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 12395.8333 | 0 | 0 | 12395.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4131.9444 | 4131.9444 | 4131.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1289 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-003 | 371.7472 | m2 | 0.15692 | 1.9615 | 11.7687 | 19.6146 | 33.3448 | 58.3333 | 729.1667 | 4375 | 7291.6667 | 12395.8333 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 12395.8333 | 0 | 0 | 12395.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4131.9444 | 4131.9444 | 4131.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1287 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Heated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-002 | 371.7472 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 53.98 | 674.7505 | 4048.5032 | 6747.5053 | 11470.7591 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 11470.7591 | 0 | 0 | 11470.7591 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3823.5864 | 3823.5864 | 3823.5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1290 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-003 | 371.7472 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 53.98 | 674.7505 | 4048.5032 | 6747.5053 | 11470.7591 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 11470.7591 | 0 | 0 | 11470.7591 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3823.5864 | 3823.5864 | 3823.5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1283 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 32.388 | 404.8503 | 2429.1019 | 4048.5032 | 6882.4555 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 6882.4555 | 0 | 0 | 6882.4555 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2294.1518 | 2294.1518 | 2294.1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1284 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 32.388 | 404.8503 | 2429.1019 | 4048.5032 | 6882.4555 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 6882.4555 | 0 | 0 | 6882.4555 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2294.1518 | 2294.1518 | 2294.1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1285 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Equipment Building - Demolish floor finish - Gravel | 7235-BLD-001 | 223.0483 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1288 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Heated Warehouse - Demolish floor finish - Gravel | 7235-BLD-002 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1291 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-003 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-004 | 0 | m2 | 0.14521 | 1.8151 | 10.8905 | 18.1508 | 30.8563 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1271 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1254 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-009 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1257 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-010 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1272 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1269 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1273 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-007 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1274 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1255 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1258 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1239 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1248 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-007 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1251 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-008 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1242 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Office - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-005 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1245 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-006 | 44.6097 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 10 | 125 | 750 | 1250 | 2125 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2125 | 0 | 0 | 2125 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1270 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7232-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Washcar - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Washcar - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Quarry Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1260 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7232-BLD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1240 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1249 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-007 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1252 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-008 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Quarry Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-001 | 0 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1256 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1259 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1261 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1262 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1243 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Office - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1244 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Office - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1246 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1247 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1241 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1250 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1253 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1372 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1373 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Batch Plant Stockpile |  | 5180.44 | m2 | 0.012695 | 0.14625 | 0.95211 | 0.39655 | 1.4934 | 65.7649 | 757.6393 | 4932.3648 | 2054.2794 | 7744.2835 | 0 | 0 | 100% | 0% | 0% | 100% | 7744.2835 | 0 | 0 | 7744.2835 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2581.4278 | 2581.4278 | 2581.4278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1374 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7251-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  |  | #N/A |  |  |  | Batch Plant Building | Batch Plant Building |  | 3281.62 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 43.8425 | 167.6063 | 3288.191 | 625.7356 | 4081.5329 | 0 | 0 | 100% | 0% | 0% | 100% | 4081.5329 | 0 | 0 | 4081.5329 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1360.511 | 1360.511 | 1360.511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 43.8425 | 167.6063 | 3288.191 | 625.7356 | 4081.5329 | 0 | 0 | 100% | 0% | 0% | 100% | 4081.5329 | 0 | 0 | 4081.5329 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1360.511 | 1360.511 | 1360.511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bladder Farm Decommissioning |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Hazardous Waste Berm |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  |  | #N/A |  |  |  |  | Old STP (RBC) |  | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road
7000 | Construction Facilities & Services | 7400 | Mine Site
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Exploration Tent Camp Pad |  | 9432.14 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 1179.0175 | 17685.2625 | 88426.3125 | 176852.625 | 282964.2 | 0 | 0 | 100% | 0% | 0% | 100% | 282964.2 | 0 | 0 | 282964.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 282964.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Soft-Wall Camp (Weatherhaven) |  | 6017.14 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 1079.0738 | 13488.4222 | 80930.533 | 134884.2217 | 229303.1768 | 0.5 | 3008.57 | 100% | 0% | 0% | 100% | 229303.1768 | 0 | 0 | 229303.1768 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 229303.1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tent Camp Tents |  | 2400 | m2 | 0.17933 | 2.2417 | 13.45 | 22.4167 | 38.1083 | 430.4 | 5380 | 32280 | 53800 | 91460 | 0.5 | 1200 | 100% | 0% | 0% | 100% | 91460 | 0 | 0 | 91460 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 91460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  |  | #N/A | VP7 | Packaged Facilities |  |  | Exploration STP |  | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 182.2 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 102.1079 | 357.3777 | 7658.0937 | 12763.4896 | 20778.961 | 1 | 182.2 | 100% | 0% | 0% | 100% | 20778.961 | 0 | 0 | 20778.961 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 20778.961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 53.765 | 72.8542 | 128.8609 | 1192.477 | 4586.45 | 110003.2907 | 149059.625 | 263649.3657 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 263649.3657 | 0 | 0 | 263649.3657 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87883.1219 | 87883.1219 | 87883.1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 9.375 | 18.75 | 30 | 255.75 | 3836.25 | 19181.25 | 38362.5 | 61380 | 0 | 0 | 100% | 0% | 0% | 100% | 61380 | 0 | 0 | 61380 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 61380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7435 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 94.3396 | 1179.2453 | 9433.9623 | 11792.4528 | 22405.6604 | 0 | 0 | 100% | 0% | 0% | 100% | 22405.6604 | 0 | 0 | 22405.6604 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7468.5535 | 7468.5535 | 7468.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1435 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-004 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1437 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-007 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1439 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-010 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1407 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2050 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1416 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-007 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1419 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-008 | 35.6877 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 20 | 100 | 1500 | 2500 | 4100 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4100 | 0 | 0 | 4100 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1366.6667 | 1366.6667 | 1366.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1433 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-001 | 1 | Ea | 31 | 325 | 2325 | 3250 | 5900 | 31 | 325 | 2325 | 3250 | 5900 | 2 | 2 | 100% | 0% | 0% | 100% | 5900 | 0 | 0 | 5900 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2950 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1436 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - FUEL SYSTEMS WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 855.2083 | 855.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1438 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1440 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-011 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1408 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 297.5 | 297.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1417 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-007 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1401 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1404 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1593.75 | 1593.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1410 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-005 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1413 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-006 | 66.9145 | m2 | 0.22417 | 2.8021 | 16.8125 | 28.0208 | 47.6354 | 15 | 187.5 | 1125 | 1875 | 3187.5 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3187.5 | 0 | 0 | 3187.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1062.5 | 1062.5 | 1062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1420 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-008 | 35.6877 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 4.4 | 35 | 210 | 350 | 595 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 595 | 0 | 0 | 595 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 198.3333 | 198.3333 | 198.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1434 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7432-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 9.6667 | 89.5833 | 725 | 895.8333 | 1710.4167 | 1 | 1 | 100% | 0% | 0% | 100% | 1710.4167 | 0 | 0 | 1710.4167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 570.1389 | 570.1389 | 570.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1422 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7432-BLD-009 | 14.8699 | m2 | 0.56042 | 2.8021 | 42.0312 | 70.0521 | 114.8854 | 8.3333 | 41.6667 | 625 | 1041.6667 | 1708.3333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1708.3333 | 0 | 0 | 1708.3333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.4444 | 569.4444 | 569.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1402 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1405 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Lunchroom - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 557.8125 | 557.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1411 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-005 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1414 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-006 | 66.9145 | m2 | 0.12329 | 0.98073 | 5.8844 | 9.8073 | 16.6724 | 8.25 | 65.625 | 393.75 | 656.25 | 1115.625 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1115.625 | 0 | 0 | 1115.625 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 371.875 | 371.875 | 371.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1409 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1418 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-007 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1421 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-008 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD |  | #N/A |  |  |  |  | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1423 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1424 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1403 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1406 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1412 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-005 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1415 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-006 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1513 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1514 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 42.0312 | 70.0521 | 114.0448 | 375 | 1312.5 | 28125 | 46875 | 76312.5 | 1 | 669.145 | 100% | 0% | 0% | 100% | 76312.5 | 0 | 0 | 76312.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25437.5 | 25437.5 | 25437.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1515 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7451-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Containment Area - Existing |  | 0 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond (Existing) |  |  | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bulk Fuel Storage Facility (Bladder Farm) |  | 5787.68 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 257.5219 | 984.4844 | 19314.1427 | 3675.4392 | 23974.0663 | 0 | 0 | 100% | 0% | 0% | 100% | 23974.0663 | 0 | 0 | 23974.0663 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11987.0332 | 11987.0332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Barreled Fuel Line Containment |  | 5411.65 | m2 | 0.044495 | 0.1701 | 3.3371 | 0.63505 | 4.1169 | 240.7905 | 920.5217 | 18059.2881 | 3436.6431 | 22416.4529 | 0 | 0 | 100% | 0% | 0% | 100% | 22416.4529 | 0 | 0 | 22416.4529 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11208.2264 | 11208.2264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 1712000 | 0 | 0 | 96.83% | 3.169% | 0% | 100% | 1657745.6732 | 54254.3268 | 0 | 1712000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 342400 | 428000 | 64894.0678 | 97477.2514 | 64894.0678 | 154080 | 119840 | 111834.5633 | 95244.3059 | 81484.7797 | 34240 | 34240 | 85600
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 3766032 | 0 | 0 | 96.83% | 3.169% | 0% | 100% | 3646684.1433 | 119347.8567 | 0 | 3766032 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 753206.4 | 941508 | 142753 | 214429 | 142753 | 338942.88 | 263622.24 | 246012 | 209517 | 179249 | 75320.64 | 75320.64 | 188301.6
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting - Arbitration Award 2019 (Regulatory Fees) | [12 empty] | 2300000 | 0 | 0 | 96.79% | 3.209% | 0% | 100% | 2226203.0856 | 73796.9144 | 0 | 2300000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 460000 | 575000 | 87182.4509 | 130956.5877 | 87182.4509 | 207000 | 161000 | 150245.0324 | 127956.7194 | 109471.3746 | 46000 | 46000 | 115000
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 40000 | 0 | 0 | 100% | 0% | 0% | 100% | 40000 | 0 | 0 | 40000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 16000 | 12000 | 8000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 24000 | 0 | 0 | 100% | 0% | 0% | 100% | 24000 | 0 | 0 | 24000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 9600 | 7200 | 4800 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees - 2019 Arbitration outcome | [12 empty] | 1431000 | 0 | 0 | 100% | 0% | 0% | 100% | 1431000 | 0 | 0 | 1431000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 572400 | 429300 | 286200 | 143100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration - 2019 Arbitration Outcome | [12 empty] | 4197000 | 0 | 0 | 100% | 0% | 0% | 100% | 4197000 | 0 | 0 | 4197000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 755460 | 755460 | 755460 | 419700 | 419700 | 293790 | 209850 | 209850 | 83940 | 83940 | 209850
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 97000 | 0 | 0 | 100% | 0% | 0% | 100% | 97000 | 0 | 0 | 97000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 17460 | 17460 | 17460 | 9700 | 9700 | 6790 | 4850 | 4850 | 1940 | 1940 | 4850
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 58000 | 0 | 0 | 100% | 0% | 0% | 100% | 58000 | 0 | 0 | 58000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 10440 | 10440 | 10440 | 5800 | 5800 | 4060 | 2900 | 2900 | 1160 | 1160 | 2900
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 2019000 | 0 | 0 | 100% | 0% | 0% | 100% | 2019000 | 0 | 0 | 2019000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 673000 | 673000 | 673000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive material) | [12 empty] | 2537000 | 0 | 0 | 100% | 0% | 0% | 100% | 2537000 | 0 | 0 | 2537000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 845666.6667 | 845666.6667 | 845666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 234000 | 0 | 0 | 100% | 0% | 0% | 100% | 234000 | 0 | 0 | 234000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 63000 | 0 | 0 | 100% | 0% | 0% | 100% | 63000 | 0 | 0 | 63000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 21000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect |  |  | Contaminated Soil Treatment | [12 empty] | 5000 | 0 | 0 | 100% | 0% | 0% | 100% | 5000 | 0 | 0 | 5000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 49000 | 0 | 0 | 100% | 0% | 0% | 100% | 49000 | 0 | 0 | 49000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16333.3333 | 16333.3333 | 16333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel - 2019 Arbitration Outcome | [12 empty] | 7383000 | 0 | 0 | 100% | 0% | 0% | 100% | 7383000 | 0 | 0 | 7383000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2461000 | 2461000 | 2461000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 40000 | 0 | 0 | 100% | 0% | 0% | 100% | 40000 | 0 | 0 | 40000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 7200 | 7200 | 7200 | 4000 | 4000 | 2800 | 2000 | 2000 | 800 | 800 | 2000
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 28000 | 0 | 0 | 100% | 0% | 0% | 100% | 28000 | 0 | 0 | 28000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 5040 | 5040 | 5040 | 2800 | 2800 | 1960 | 1400 | 1400 | 560 | 560 | 1400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation - 2019 Arbitration Outcome | [12 empty] | 1910000 | 0 | 0 | 100% | 0% | 0% | 100% | 1910000 | 0 | 0 | 1910000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 343800 | 343800 | 343800 | 191000 | 191000 | 133700 | 95500 | 95500 | 38200 | 38200 | 95500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 103000 | 0 | 0 | 100% | 0% | 0% | 100% | 103000 | 0 | 0 | 103000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 18540 | 18540 | 18540 | 10300 | 10300 | 7210 | 5150 | 5150 | 2060 | 2060 | 5150
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 62000 | 0 | 0 | 100% | 0% | 0% | 100% | 62000 | 0 | 0 | 62000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 11160 | 11160 | 11160 | 6200 | 6200 | 4340 | 3100 | 3100 | 1240 | 1240 | 3100
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift - 2019 Arbitrtion Outcome | [12 empty] | 3668270 | 0 | 0 | 100% | 0% | 0% | 100% | 3668270 | 0 | 0 | 3668270 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 660288.6 | 660288.6 | 660288.6 | 366827 | 366827 | 256778.9 | 183413.5 | 183413.5 | 73365.4 | 73365.4 | 183413.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2019) |  | 18172 | m3 |  |  |  |  | 103.02 |  |  |  |  | 1872079.44 | 0 | 0 | 100% | 0% | 0% | 100% | 1872079.44 | 0 | 0 | 1872079.44 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 336974.2992 | 336974.2992 | 336974.2992 | 187207.944 | 187207.944 | 131045.5608 | 93603.972 | 93603.972 | 37441.5888 | 37441.5888 | 93603.972
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2019) |  | 49868 | m3 |  |  |  |  | 103.02 |  |  |  |  | 5137401.36 | 0 | 0 | 100% | 0% | 0% | 100% | 5137401.36 | 0 | 0 | 5137401.36 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 924732.2448 | 924732.2448 | 924732.2448 | 513740.136 | 513740.136 | 359618.0952 | 256870.068 | 256870.068 | 102748.0272 | 102748.0272 | 256870.068
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2019) |  | 24756 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2550363.12 | 0 | 0 | 100% | 0% | 0% | 100% | 2550363.12 | 0 | 0 | 2550363.12 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 459065.3616 | 459065.3616 | 459065.3616 | 255036.312 | 255036.312 | 178525.4184 | 127518.156 | 127518.156 | 51007.2624 | 51007.2624 | 127518.156
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2019) |  | 33278 | m3 |  |  |  |  | 103.02 |  |  |  |  | 3428299.56 | 0 | 0 | 100% | 0% | 0% | 100% | 3428299.56 | 0 | 0 | 3428299.56 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 617093.9208 | 617093.9208 | 617093.9208 | 342829.956 | 342829.956 | 239980.9692 | 171414.978 | 171414.978 | 68565.9912 | 68565.9912 | 171414.978
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Shiploading Module (mobilized in 2019) |  | 81400 | m3 |  |  |  |  | 103.02 |  |  |  |  | 8385828 | 0 | 0 | 100% | 0% | 0% | 100% | 8385828 | 0 | 0 | 8385828 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 1509449.04 | 1509449.04 | 1509449.04 | 838582.8 | 838582.8 | 587007.96 | 419291.4 | 419291.4 | 167716.56 | 167716.56 | 419291.4
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2019) |  | 21815 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2247381.3 | 0 | 0 | 100% | 0% | 0% | 100% | 2247381.3 | 0 | 0 | 2247381.3 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 404528.634 | 404528.634 | 404528.634 | 224738.13 | 224738.13 | 157316.691 | 112369.065 | 112369.065 | 44947.626 | 44947.626 | 112369.065
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | 30500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 3142110 | 0 | 0 | 100% | 0% | 0% | 100% | 3142110 | 0 | 0 | 3142110 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 565579.8 | 565579.8 | 565579.8 | 314211 | 314211 | 219947.7 | 157105.5 | 157105.5 | 62842.2 | 62842.2 | 157105.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | -30500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -3142110 | 0 | 0 | 100% | 0% | 0% | 100% | -3142110 | 0 | 0 | -3142110 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -565579.8 | -565579.8 | -565579.8 | -314211 | -314211 | -219947.7 | -157105.5 | -157105.5 | -62842.2 | -62842.2 | -157105.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | 40500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 4172310 | 0 | 0 | 100% | 0% | 0% | 100% | 4172310 | 0 | 0 | 4172310 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 751015.8 | 751015.8 | 751015.8 | 417231 | 417231 | 292061.7 | 208615.5 | 208615.5 | 83446.2 | 83446.2 | 208615.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | -40500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -4172310 | 0 | 0 | 100% | 0% | 0% | 100% | -4172310 | 0 | 0 | -4172310 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -751015.8 | -751015.8 | -751015.8 | -417231 | -417231 | -292061.7 | -208615.5 | -208615.5 | -83446.2 | -83446.2 | -208615.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | 24100 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2482782 | 0 | 0 | 100% | 0% | 0% | 100% | 2482782 | 0 | 0 | 2482782 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 446900.76 | 446900.76 | 446900.76 | 248278.2 | 248278.2 | 173794.74 | 124139.1 | 124139.1 | 49655.64 | 49655.64 | 124139.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | -24100 | m3 |  |  |  |  | 103.02 |  |  |  |  | -2482782 | 0 | 0 | 100% | 0% | 0% | 100% | -2482782 | 0 | 0 | -2482782 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -446900.76 | -446900.76 | -446900.76 | -248278.2 | -248278.2 | -173794.74 | -124139.1 | -124139.1 | -49655.64 | -49655.64 | -124139.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | 41500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 4275330 | 0 | 0 | 100% | 0% | 0% | 100% | 4275330 | 0 | 0 | 4275330 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 769559.4 | 769559.4 | 769559.4 | 427533 | 427533 | 299273.1 | 213766.5 | 213766.5 | 85506.6 | 85506.6 | 213766.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | -41500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -4275330 | 0 | 0 | 100% | 0% | 0% | 100% | -4275330 | 0 | 0 | -4275330 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -769559.4 | -769559.4 | -769559.4 | -427533 | -427533 | -299273.1 | -213766.5 | -213766.5 | -85506.6 | -85506.6 | -213766.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | 25100 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2585802 | 0 | 0 | 100% | 0% | 0% | 100% | 2585802 | 0 | 0 | 2585802 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 465444.36 | 465444.36 | 465444.36 | 258580.2 | 258580.2 | 181006.14 | 129290.1 | 129290.1 | 51716.04 | 51716.04 | 129290.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | -9926 | m3 |  |  |  |  | 103.02 |  |  |  |  | -1022576.52 | 0 | 0 | 100% | 0% | 0% | 100% | -1022576.52 | 0 | 0 | -1022576.52 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -184063.7736 | -184063.7736 | -184063.7736 | -102257.652 | -102257.652 | -71580.3564 | -51128.826 | -51128.826 | -20451.5304 | -20451.5304 | -51128.826
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - Arbitration Reconciliation |  | 188 | Ea |  |  |  |  | 15964.53 |  |  |  |  | 3001331.64 | 0 | 0 | 100% | 0% | 0% | 100% | 3001331.64 | 0 | 0 | 3001331.64 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 3001331.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Medium 3rd Party Equipment Demob - Arbitration Reconciliation |  | 156 | Ea |  |  |  |  | 8202.67 |  |  |  |  | 1279616.52 | 0 | 0 | 100% | 0% | 0% | 100% | 1279616.52 | 0 | 0 | 1279616.52 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 1279616.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - Arbitration Reconciliation |  | 183 | Ea |  |  |  |  | 2785.99 |  |  |  |  | 509836.17 | 0 | 0 | 100% | 0% | 0% | 100% | 509836.17 | 0 | 0 | 509836.17 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 509836.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2020-R |  | 49 | Ea |  |  |  |  | 15964.53 |  |  |  |  | 782261.97 | 0 | 0 | 100% | 0% | 0% | 100% | 782261.97 | 0 | 0 | 782261.97 | Type A 2AM-MRY1325 | Added | 2020-AR | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 782261.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2020-R |  | 61 | Ea |  |  |  |  | 8202.67 |  |  |  |  | 500362.87 | 0 | 0 | 100% | 0% | 0% | 100% | 500362.87 | 0 | 0 | 500362.87 | Type A 2AM-MRY1325 | Added | 2020-AR | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 500362.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2020-R |  | 34 | Ea |  |  |  |  | 2785.99 |  |  |  |  | 94723.66 | 0 | 0 | 100% | 0% | 0% | 100% | 94723.66 | 0 | 0 | 94723.66 | Type A 2AM-MRY1325 | Added | 2020-AR | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 94723.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2021 |  | 5 | ea |  |  |  |  | 8202.67 |  |  |  |  | 41013.35 | 0 | 0 | 100% | 0% | 0% | 100% | 41013.35 | 0 | 0 | 41013.35 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 41013.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2021 |  | 13 | ea |  |  |  |  | 2785.99 |  |  |  |  | 36217.87 | 0 | 0 | 100% | 0% | 0% | 100% | 36217.87 | 0 | 0 | 36217.87 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 36217.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2021-R |  | -6 | ea |  |  |  |  | 15964.53 |  |  |  |  | -95787.18 | 0 | 0 | 100% | 0% | 0% | 100% | -95787.18 | 0 | 0 | -95787.18 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -95787.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2021-R |  | -17 | ea |  |  |  |  | 8202.67 |  |  |  |  | -139445.39 | 0 | 0 | 100% | 0% | 0% | 100% | -139445.39 | 0 | 0 | -139445.39 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -139445.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2021-R |  | -26 | ea |  |  |  |  | 2785.99 |  |  |  |  | -72435.74 | 0 | 0 | 100% | 0% | 0% | 100% | -72435.74 | 0 | 0 | -72435.74 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -72435.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 1969000 | 0 | 0 | 100% | 0% | 0% | 100% | 1969000 | 0 | 0 | 1969000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 1969000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 110000 | 0 | 0 | 100% | 0% | 0% | 100% | 110000 | 0 | 0 | 110000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 19800 | 19800 | 19800 | 11000 | 11000 | 7700 | 5500 | 5500 | 2200 | 2200 | 5500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 76000 | 0 | 0 | 100% | 0% | 0% | 100% | 76000 | 0 | 0 | 76000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 13680 | 13680 | 13680 | 7600 | 7600 | 5320 | 3800 | 3800 | 1520 | 1520 | 3800
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation - 2019 Arbitration Outcome | [12 empty] | 5233000 | 0 | 0 | 100% | 0% | 0% | 100% | 5233000 | 0 | 0 | 5233000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 941940 | 941940 | 941940 | 523300 | 523300 | 366310 | 261650 | 261650 | 104660 | 104660 | 261650
9000 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 124000 | 0 | 0 | 95.99% | 4.011% | 0% | 100% | 119025.9384 | 4974.0616 | 0 | 124000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 124000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 210000 | 0 | 0 | 95.99% | 4.011% | 0% | 100% | 201576.1861 | 8423.8139 | 0 | 210000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency - 2019 Arbitration Outcome | [12 empty] | 8929000 | 0 | 0 | 95.99% | 4.011% | 0% | 100% | 8570827.4539 | 358172.5461 | 0 | 8929000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 8929000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0