## Estimate Details
Mary River Project - Complete Project Security Assesment - Estimate Breakdown Structure'
Updated December 15, 2022
[44 empty] | C&M |  | Closure |  |  | Post Closure | [7 empty] | C&M |  | Closure |  |  | Post Closure
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 0 - % | Year 0+1 - % | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 16 - % | Year 17 - % | Year 18 - % | Year 0- Cost ($) | Year 0+1- Cost ($) | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Year 16 - Cost ($) | Year 17 - Cost ($) | Year 18 - Cost ($)
1000 | Project Wide
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2014 |  | 11787.5421 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 2930.505 | 23894.3714 | 195856.7782 | 266836.6301 | 497007.5159 | 0 | 0 | 100% | 0% | 0% | 100% | 497007.5159 | 0 | 0 | 497007.5159 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 497007.5159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 |  | 378 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 93.9747 | 766.2388 | 6280.687 | 8556.8514 | 15937.9148 | 0 | 0 | 100% | 0% | 0% | 100% | 15937.9148 | 0 | 0 | 15937.9148 | Type A 2AM-MRY1325 | Modified | 2015 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 15937.9148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2016 |  | 20 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 4.9722 | 40.5417 | 332.3115 | 452.7435 | 843.2759 | 0 | 0 | 100% | 0% | 0% | 100% | 843.2759 | 0 | 0 | 843.2759 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 843.2759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables - addition of 49 person camp |  | 49 | Bed space | 0 | 700.8009 | 0 | 0 | 790.3008 | 0 | 34339.2445 | 0 | 0 | 34339.2445 | 0 | 0 | 100% | 0% | 0% | 100% | 34339.2445 | 0 | 0 | 34339.2445 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 34339.2445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017 |  | 719.1667 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 178.7923 | 1457.8133 | 11949.367 | 16279.9003 | 30322.7964 | 0 | 0 | 100% | 0% | 0% | 100% | 30322.7964 | 0 | 0 | 30322.7964 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 30322.7964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2021-D |  | -224.0833 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | -55.7094 | -454.2364 | -3723.2732 | -5072.6132 | -9448.2039 | 0 | 0 | 100% | 0% | 0% | 100% | -9448.2039 | 0 | 0 | -9448.2039 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | -9448.2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2021 & 2021-R |  | 1244.274 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 309.3394 | 2522.2514 | 20674.3261 | 28166.845 | 52463.3131 | 0 | 0 | 100% | 0% | 0% | 100% | 52463.3131 | 0 | 0 | 52463.3131 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 52463.3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2020-AR |  | 0 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2020 & 2020-R |  | 508.128 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 126.3259 | 1030.0197 | 8442.8392 | 11502.5826 | 21424.6073 | 0 | 0 | 100% | 0% | 0% | 100% | 21424.6073 | 0 | 0 | 21424.6073 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 21424.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2019 & 2019-R |  | 8036.4697 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1997.9496 | 16290.622 | 133530.5582 | 181922.9567 | 338848.0687 | 0 | 0 | 100% | 0% | 0% | 100% | 338848.0687 | 0 | 0 | 338848.0687 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 338848.0687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C1 & 2018-R |  | 1517.3333 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 377.2248 | 3075.7664 | 25211.3644 | 34348.1373 | 63976.5327 | 0 | 0 | 100% | 0% | 0% | 100% | 63976.5327 | 0 | 0 | 63976.5327 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 63976.5327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2018-C2 |  | 120.2947 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 29.9065 | 243.8478 | 1998.7658 | 2723.1323 | 5072.0818 | 0 | 0 | 100% | 0% | 0% | 100% | 5072.0818 | 0 | 0 | 5072.0818 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 5072.0818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 A |  | 8.0269 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1.9956 | 16.2712 | 133.371 | 181.7056 | 338.4433 | 0 | 0 | 100% | 0% | 0% | 100% | 338.4433 | 0 | 0 | 338.4433 | Type A 2AM-MRY1325 | Modified | 2015 A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 338.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | CON | Consumables | CON |  | Consumables |  | Consumables |  | 550 | Bed space | 0 | 700.8009 | 0 | 0 | 790.3008 | 0 | 385440.5 | 0 | 0 | 385440.5 | 0 | 0 | 100% | 0% | 0% | 100% | 385440.5 | 0 | 0 | 385440.5 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 385440.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - Shiploader |  | 5049 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1255.2337 | 10234.7614 | 83892.0334 | 114295.0869 | 212885.0046 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 212885.0046 | 0 | 212885.0046 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 212885.0046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2015 R |  | 64.3333 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 15.9939 | 130.4093 | 1068.9353 | 1456.3248 | 2712.5375 | 0 | 0 | 100% | 0% | 0% | 100% | 2712.5375 | 0 | 0 | 2712.5375 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2712.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2017-A |  | 5455.56 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1356.3087 | 11058.8938 | 90647.2605 | 123498.4551 | 230027.1157 | 0 | 0 | 100% | 0% | 0% | 100% | 230027.1157 | 0 | 0 | 230027.1157 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 230027.1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2022 |  | 527.2454 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 131.0787 | 1068.7721 | 8760.4845 | 11935.3447 | 22230.666 | 0 | 0 | 100% | 0% | 0% | 100% | 22230.666 | 0 | 0 | 22230.666 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 22230.666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2022-R |  | -833.5833 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | -207.2374 | -1689.7458 | -13850.4656 | -18869.9702 | -35147.0374 | 0 | 0 | 100% | 0% | 0% | 100% | -35147.0374 | 0 | 0 | -35147.0374 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | -35147.0374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2023 |  | 59.9614 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 14.907 | 121.5469 | 996.2928 | 1357.3562 | 2528.1995 | 0 | 0 | 100% | 0% | 0% | 100% | 2528.1995 | 0 | 0 | 2528.1995 | Type A 2AM-MRY1325 | Added | 2023 | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 2528.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A2 | Fill Application | Fill | Site Works | Fill Application | Fill Application | Fill Application - 2023-R |  | -1187.4076 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | -295.2018 | -2406.9782 | -19729.4584 | -26879.5506 | -50065.6101 | 0 | 0 | 100% | 0% | 0% | 100% | -50065.6101 | 0 | 0 | -50065.6101 | Type A 2AM-MRY1325 | Added | 2023-R | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | -50065.6101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port
2000 | Milne Port | 2100 | General
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 001 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed - Demolish Building - ISO Shipping Container | 2110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 2110-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed - Demolish and foundations - Gravel Base - Skidded Building | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure | 003 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed - Demolish floor finish - Raised Steel or Wooden Floor | 2110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Disturbed Area @ Milne Port (adjacent to Steel Tank Farm) |  | 45000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 571.1347 | 6581.25 | 50339.8167 | 18068.3031 | 74989.3698 | 0 | 0 | 100% | 0% | 0% | 100% | 74989.3698 | 0 | 0 | 74989.3698 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24996.4566 | 24996.4566 | 24996.4566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Laydown Area |  | 37375 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 474.3591 | 5466.0938 | 41810.0144 | 15006.7295 | 62282.8377 | 0 | 0 | 100% | 0% | 0% | 100% | 62282.8377 | 0 | 0 | 62282.8377 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20760.9459 | 20760.9459 | 20760.9459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP3 |  | 131000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1662.6367 | 19158.75 | 146544.7998 | 52598.8378 | 218302.3876 | 0 | 0 | 100% | 0% | 0% | 100% | 218302.3876 | 0 | 0 | 218302.3876 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 72767.4625 | 72767.4625 | 72767.4625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of berm and linear steel support structure on laydown LP3 | 2019-7 | 6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 76.1513 | 877.5 | 6711.9756 | 2409.1071 | 9998.5826 | 0 | 0 | 100% | 0% | 0% | 100% | 9998.5826 | 0 | 0 | 9998.5826 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3332.8609 | 3332.8609 | 3332.8609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of berm and linear steel support structure on laydown LP3 | 2019-7 | -6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -76.1513 | -877.5 | -6711.9756 | -2409.1071 | -9998.5826 | 0 | 0 | 100% | 0% | 0% | 100% | -9998.5826 | 0 | 0 | -9998.5826 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3332.8609 | -3332.8609 | -3332.8609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP5 |  | 65000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 824.9724 | 9506.25 | 72713.0686 | 26098.66 | 108317.9786 | 0 | 0 | 100% | 0% | 0% | 100% | 108317.9786 | 0 | 0 | 108317.9786 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 36105.9929 | 36105.9929 | 36105.9929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 32000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 406.1403 | 4680 | 35797.203 | 12848.5711 | 53325.7741 | 0 | 0 | 100% | 0% | 0% | 100% | 53325.7741 | 0 | 0 | 53325.7741 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 17775.258 | 17775.258 | 17775.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP7 |  | 21000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 266.5295 | 3071.25 | 23491.9145 | 8431.8748 | 34995.0392 | 0 | 0 | 100% | 0% | 0% | 100% | 34995.0392 | 0 | 0 | 34995.0392 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11665.0131 | 11665.0131 | 11665.0131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | -13000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -164.9945 | -1901.25 | -14542.6137 | -5219.732 | -21663.5957 | 0 | 0 | 100% | 0% | 0% | 100% | -21663.5957 | 0 | 0 | -21663.5957 | Type A 2AM-MRY1325 | Removed | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -7221.1986 | -7221.1986 | -7221.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP2 |  | 30000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 380.7565 | 4387.5 | 33559.8778 | 12045.5354 | 49992.9132 | 0 | 0 | 100% | 0% | 0% | 100% | 49992.9132 | 0 | 0 | 49992.9132 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16664.3044 | 16664.3044 | 16664.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP1 |  | 13000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 164.9945 | 1901.25 | 14542.6137 | 5219.732 | 21663.5957 | 0 | 0 | 100% | 0% | 0% | 100% | 21663.5957 | 0 | 0 | 21663.5957 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7221.1986 | 7221.1986 | 7221.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP4 |  | 13000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 164.9945 | 1901.25 | 14542.6137 | 5219.732 | 21663.5957 | 0 | 0 | 100% | 0% | 0% | 100% | 21663.5957 | 0 | 0 | 21663.5957 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7221.1986 | 7221.1986 | 7221.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown LP6 |  | 7000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 88.8432 | 1023.75 | 7830.6382 | 2810.6249 | 11665.0131 | 0 | 0 | 100% | 0% | 0% | 100% | 11665.0131 | 0 | 0 | 11665.0131 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3888.3377 | 3888.3377 | 3888.3377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Module Road 2018 |  | 13300 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 168.802 | 1945.125 | 14878.2125 | 5340.1873 | 22163.5248 | 0 | 0 | 100% | 0% | 0% | 100% | 22163.5248 | 0 | 0 | 22163.5248 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7387.8416 | 7387.8416 | 7387.8416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Q1 Access Road |  | 1200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 15.2303 | 175.5 | 1342.3951 | 481.8214 | 1999.7165 | 0 | 0 | 100% | 0% | 0% | 100% | 1999.7165 | 0 | 0 | 1999.7165 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 666.5722 | 666.5722 | 666.5722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2131 | Construction Laydown |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Milne Port Surface Water Management Diversion Berms & Ditching | 2020-7 | 9500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 120.5729 | 1389.375 | 10627.2946 | 3814.4195 | 15831.0892 | 0 | 0 | 100% | 0% | 0% | 100% | 15831.0892 | 0 | 0 | 15831.0892 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5277.0297 | 5277.0297 | 5277.0297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2136 | Milne Port |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Grade and Re-Contour Building Footprints |  | 14306 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 181.5701 | 2092.2525 | 16003.5871 | 5744.1143 | 23839.9539 | 0 | 0 | 100% | 0% | 0% | 100% | 23839.9539 | 0 | 0 | 23839.9539 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7946.6513 | 7946.6513 | 7946.6513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 12148.5 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 154.1873 | 1776.7181 | 13590.0725 | 4877.8395 | 20244.6302 | 0 | 0 | 100% | 0% | 0% | 100% | 20244.6302 | 0 | 0 | 20244.6302 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6748.2101 | 6748.2101 | 6748.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development | 2134 |  |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Camp Pad @ Milne Port |  | 66536 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 844.4671 | 9730.89 | 74431.3343 | 26715.3914 | 110877.6157 | 0 | 0 | 100% | 0% | 0% | 100% | 110877.6157 | 0 | 0 | 110877.6157 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 36959.2052 | 36959.2052 | 36959.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | 8 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 341.8 | 3765 | 30126.252 | 41526.444 | 75417.696 | 30 | 240 | 100% | 0% | 0% | 100% | 75417.696 | 0 | 0 | 75417.696 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25139.232 | 25139.232 | 25139.232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Portable Fuel Tank |  | -8 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -341.8 | -3765 | -30126.252 | -41526.444 | -75417.696 | 30 | -240 | 100% | 0% | 0% | 100% | -75417.696 | 0 | 0 | -75417.696 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -25139.232 | -25139.232 | -25139.232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | 3 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 128.175 | 1411.875 | 11297.3445 | 15572.4165 | 28281.636 | 30 | 90 | 100% | 0% | 0% | 100% | 28281.636 | 0 | 0 | 28281.636 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9427.212 | 9427.212 | 9427.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | TK Large Fuel Tank for Generators (22,500L) |  | -3 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -128.175 | -1411.875 | -11297.3445 | -15572.4165 | -28281.636 | 30 | -90 | 100% | 0% | 0% | 100% | -28281.636 | 0 | 0 | -28281.636 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -9427.212 | -9427.212 | -9427.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3142.404 | 3142.404 | 3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3142.404 | 3142.404 | 3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -42.725 | -470.625 | -3765.7815 | -5190.8055 | -9427.212 | 30 | -30 | 100% | 0% | 0% | 100% | -9427.212 | 0 | 0 | -9427.212 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3142.404 | -3142.404 | -3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | 10,000 Gallon tank (gas and diesel) |  | 2 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 85.45 | 941.25 | 7531.563 | 10381.611 | 18854.424 | 30 | 60 | 100% | 0% | 0% | 100% | 18854.424 | 0 | 0 | 18854.424 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6284.808 | 6284.808 | 6284.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 4 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 170.9 | 1882.5 | 15063.126 | 20763.222 | 37708.848 | 30 | 120 | 100% | 0% | 0% | 100% | 37708.848 | 0 | 0 | 37708.848 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12569.616 | 12569.616 | 12569.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3142.404 | 3142.404 | 3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -42.725 | -470.625 | -3765.7815 | -5190.8055 | -9427.212 | 30 | -30 | 100% | 0% | 0% | 100% | -9427.212 | 0 | 0 | -9427.212 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3142.404 | -3142.404 | -3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 1,000L |  | -2 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | -31 | -325 | -2732.34 | -3584.62 | -6641.96 | 20 | -40 | 100% | 0% | 0% | 100% | -6641.96 | 0 | 0 | -6641.96 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | [10 empty] | 0 | 0 | -3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 9,000L |  | -1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | -15.5 | -162.5 | -1366.17 | -1792.31 | -3320.98 | 20 | -20 | 100% | 0% | 0% | 100% | -3320.98 | 0 | 0 | -3320.98 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 50% | [10 empty] | 0 | 0 | -1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 5 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 77.5 | 812.5 | 6830.85 | 8961.55 | 16604.9 | 20 | 100 | 100% | 0% | 0% | 100% | 16604.9 | 0 | 0 | 16604.9 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | [10 empty] | 0 | 0 | 8302.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 20 | 40 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | [10 empty] | 0 | 0 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | -31 | -325 | -2732.34 | -3584.62 | -6641.96 | 20 | -40 | 100% | 0% | 0% | 100% | -6641.96 | 0 | 0 | -6641.96 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | [10 empty] | 0 | 0 | -3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK, DOUBLE WALLED 2494 LITER |  | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1106.9933 | 1106.9933 | 1106.9933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 4400 GAL STAINLESS STEEL WATER TANK |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | SEWAGE TANK SERAIL # ST111-0716 |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | WATER TANK SERIAL # WT110-0070 |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 213.625 | 2353.125 | 18828.9075 | 25954.0275 | 47136.06 | 30 | 150 | 100% | 0% | 0% | 100% | 47136.06 | 0 | 0 | 47136.06 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15712.02 | 15712.02 | 15712.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | 2017 - Diesel tanks on sea lift |  | 5 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 77.5 | 812.5 | 6830.85 | 8961.55 | 16604.9 | 20 | 100 | 100% | 0% | 0% | 100% | 16604.9 | 0 | 0 | 16604.9 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 8302.45 | 8302.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | General | 2130 | Site Development |  | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 12 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | 72 | 450 | 6346.08 | 4963.32 | 11759.4 | 0 | 0 | 100% | 0% | 0% | 100% | 11759.4 | 0 | 0 | 11759.4 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 5879.7 | 5879.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 099 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Dock Office - Demolish and Decontaminate Building - Trailer - Single | 2223-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 100 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Dock Office - Demolish and foundations - Gravel Base - Skidded Building | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 101 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Dock Office - Demolish floor finish - Raised Steel or Wooden Floor | 2223-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | CONVEYING - RECLAIM CONVEYOR - FAM L: 850000, W: 1524, H: 47000 VERTICAL LIFT SEE REMARKS kg | 2342-CV-001 | 1 | Ea | 5018.4 | 62730 | 442321.776 | 691886.808 | 1196938.584 | 5018.4 | 62730 | 442321.776 | 691886.808 | 1196938.584 | 1020 | 1020 | 100% | 0% | 0% | 100% | 1196938.584 | 0 | 0 | 1196938.584 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 398979.528 | 398979.528 | 398979.528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A |  |  |  |  | Shiploading E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Shiploading E-House - Demolish and foundations - Gravel Base - Skidded Building | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Shiploading E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2342-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 130 | MT- |  | #N/A |  |  |  |  | RECLAIM CONVEYOR | 2342-MT-001 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | 0.16667 | Ea | 5018.4 | 62730 | 442321.776 | 691886.808 | 1196938.584 | 836.4 | 10455 | 73720.296 | 115314.468 | 199489.764 | 1020 | 170 | 100% | 0% | 0% | 100% | 199489.764 | 0 | 0 | 199489.764 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 66496.588 | 66496.588 | 66496.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 129 | CV- | CV | Reclaim Conveyor | CV | Mechanical Equipment | Reclaim Conveyor |  | Cross' Conveyor at Ore Stockpile Pad (assume 1/6 length of existing shiploader conveyor) |  | -0.16667 | Ea | 5018.4 | 62730 | 442321.776 | 691886.808 | 1196938.584 | -836.4 | -10455 | -73720.296 | -115314.468 | -199489.764 | 1020 | -170 | 100% | 0% | 0% | 100% | -199489.764 | 0 | 0 | -199489.764 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -66496.588 | -66496.588 | -66496.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown |  | 230545.88 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2926.0614 | 33717.3349 | 257903.0521 | 92568.2851 | 384188.6721 | 0 | 0 | 100% | 0% | 0% | 100% | 384188.6721 | 0 | 0 | 384188.6721 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 128062.8907 | 128062.8907 | 128062.8907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Footprints |  | 128865.8 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1635.5497 | 18846.6233 | 144157.3501 | 51741.9184 | 214745.8917 | 0 | 0 | 100% | 0% | 0% | 100% | 214745.8917 | 0 | 0 | 214745.8917 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 71581.9639 | 71581.9639 | 71581.9639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion |  | 82000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1040.7344 | 11992.5 | 91730.3327 | 32924.4634 | 136647.296 | 0 | 0 | 100% | 0% | 0% | 100% | 136647.296 | 0 | 0 | 136647.296 | Type B Construction 2BC-MRY1416 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 45549.0987 | 45549.0987 | 45549.0987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion 2019 | 2019-6 | 140000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1776.8637 | 20475 | 156612.7631 | 56212.4984 | 233300.2615 | 0 | 0 | 100% | 0% | 0% | 100% | 233300.2615 | 0 | 0 | 233300.2615 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 77766.7538 | 77766.7538 | 77766.7538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Pad Expansion 2019 | 2019-6 | -140000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1776.8637 | -20475 | -156612.7631 | -56212.4984 | -233300.2615 | 0 | 0 | 100% | 0% | 0% | 100% | -233300.2615 | 0 | 0 | -233300.2615 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -77766.7538 | -77766.7538 | -77766.7538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpile Laydown - Realignment of the shipload conveyor |  | 26000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 329.989 | 3802.5 | 29085.2274 | 10439.464 | 43327.1914 | 0 | 0 | 100% | 0% | 0% | 100% | 43327.1914 | 0 | 0 | 43327.1914 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14442.3971 | 14442.3971 | 14442.3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional sealift laydown area |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Settling Ponds |  | 11423.76 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 508.2646 | 1943.1816 | 44798.4416 | 7788.7544 | 54530.3775 | 0 | 0 | 100% | 0% | 0% | 100% | 54530.3775 | 0 | 0 | 54530.3775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 18176.7925 | 18176.7925 | 18176.7925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation - New 2019 | 2019-6 | 15000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 667.3782 | 2551.5 | 58822.7189 | 10227.0457 | 71601.2646 | 0 | 0 | 100% | 0% | 0% | 100% | 71601.2646 | 0 | 0 | 71601.2646 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 23867.0882 | 23867.0882 | 23867.0882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation - New 2019 | 2019-6 | -15000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -667.3782 | -2551.5 | -58822.7189 | -10227.0457 | -71601.2646 | 0 | 0 | 100% | 0% | 0% | 100% | -71601.2646 | 0 | 0 | -71601.2646 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -23867.0882 | -23867.0882 | -23867.0882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 2a | 2019-25 | 4400 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 195.7643 | 748.44 | 17254.6642 | 2999.9334 | 21003.0376 | 0 | 0 | 100% | 0% | 0% | 100% | 21003.0376 | 0 | 0 | 21003.0376 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7001.0125 | 7001.0125 | 7001.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 2a | 2019-25 | -4400 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -195.7643 | -748.44 | -17254.6642 | -2999.9334 | -21003.0376 | 0 | 0 | 100% | 0% | 0% | 100% | -21003.0376 | 0 | 0 | -21003.0376 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -7001.0125 | -7001.0125 | -7001.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Stockpile Sedimentation Pond 1a |  | 5000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 222.4594 | 850.5 | 19607.573 | 3409.0152 | 23867.0882 | 0 | 0 | 100% | 0% | 0% | 100% | 23867.0882 | 0 | 0 | 23867.0882 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7955.6961 | 7955.6961 | 7955.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | VP6 | VENDOR PKG - Ship Loader | VP6 | Packaged Facilities | Ship Loader |  | Shiploader Package | 2351-SL-001 | 0 | Lot | 14448 | 180600 | 1273446.72 | 1991945.76 | 3445992.48 | 0 | 0 | 0 | 0 | 0 | 30295 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and Decontaminate Building - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and foundations - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish floor finish - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and Decontaminate Building - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and foundations - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish floor finish - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 152 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER PROPORTIONAL GATE - FAM | 2351-CH-003 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 153 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-004 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 154 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-005 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 155 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-006 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 156 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE - FAM | 2351-CH-008 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 157 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-009 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 158 | CV- |  | Ship Loader | Ship Loader | Mechanical Equipment | Ship Loader |  | CONVEYING - SHIPLOADER LINK CONVEYOR - FAM 212330 kg | 2351-CV-007 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 159 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DRIVE | 2351-MT-007A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 160 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR BRAKE | 2351-MT-007B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 161 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE | 2351-MT-007C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 162 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN | 2351-MT-007D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 163 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR | 2351-MT-007E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 164 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 165 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 166 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM 1960000 kg | 2351-SL-001 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 167 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-001A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 170 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-001B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 171 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-001C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 172 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 173 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 174 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 175 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 176 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-001H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 177 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-001J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 178 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-001K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 179 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE FAN | 2351-MT-001L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 180 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-001M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 181 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-001N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 182 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 183 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 184 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 185 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 186 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 187 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 193 | SL- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER - SHIPLOADER - FAM | 2351-SL-002 | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 194 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-002A | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 197 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-002B | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 198 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-002C | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 199 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002D | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 200 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002E | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 201 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002F | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 202 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002G | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 203 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-002H | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 204 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-002J | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 205 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-002K | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 206 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE BRAKE | 2351-MT-002L | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 207 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-002M | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 208 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-002N | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 209 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002P | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 210 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002Q | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 211 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002R | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 212 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002S | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 213 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002T | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 214 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002U | 0 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 168 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-001AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 169 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-001AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 188 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-001V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 189 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-001W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 190 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-001X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 191 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-001Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 192 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-001Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 195 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SPOT | 2351-MT-002AA | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 196 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | FEEDER CABIN | 2351-MT-002AB | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 215 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | AIR CONDITIONER E-HOUSE | 2351-MT-002V | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 216 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER E-HOUSE | 2351-MT-002W | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 217 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | DUST COLLECTOR E-HOUSE | 2351-MT-002X | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 218 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | WELDING RECEPTACLE | 2351-MT-002Y | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 219 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR | 2351-MT-002Z | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2400 | Aerodrome
2000 | Milne Port | 2500 | Non Process Facilities
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 237 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 240 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 243 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 246 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 238 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BA - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 239 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BA - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 241 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BB - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 242 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BB - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 244 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BC - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 245 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BC - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 247 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BD - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 248 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BD - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Offices, washcars for Laydown R3 62 @ 15m2 3 @ 30m2 3 @ 66m2 |  | 1218 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 682.5875 | 3412.9375 | 60163.2622 | 94108.3386 | 157684.5384 | 1 | 1218 | 100% | 0% | 0% | 100% | 157684.5384 | 0 | 0 | 157684.5384 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 52561.5128 | 52561.5128 | 52561.5128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BE - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BE - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BF - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BF - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Pre-Cast Concrete Foundations (Mobilized to Site) |  | 8000 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 1000 | 15000 | 88140 | 150000 | 253140 | 0 | 0 | 100% | 0% | 0% | 100% | 253140 | 0 | 0 | 253140 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 84380 | 84380 | 84380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 48.42 | 605.25 | 4267.7388 | 6675.6654 | 11548.6542 | 1 | 216 | 100% | 0% | 0% | 100% | 11548.6542 | 0 | 0 | 11548.6542 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3849.5514 | 3849.5514 | 3849.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 380 person camp at Milne Port |  | 380 | Bed space | 0 | 700.8009 | 0 | 0 | 790.3008 | 0 | 266304.3455 | 0 | 0 | 266304.3455 | 0 | 0 | 100% | 0% | 0% | 100% | 266304.3455 | 0 | 0 | 266304.3455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 266304.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 380 man temporary hardwall camp at Milne Port inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 10,720 m2) |  | 10720 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 2403.0667 | 30038.3333 | 211806.296 | 331310.8013 | 573155.4307 | 1 | 10720 | 100% | 0% | 0% | 100% | 573155.4307 | 0 | 0 | 573155.4307 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 191051.8102 | 191051.8102 | 191051.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Offices, washcars (assume 16 units @ 36 m2 per wash car) |  | 576 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 129.12 | 1614 | 11380.6368 | 17801.7744 | 30796.4112 | 1 | 576 | 100% | 0% | 0% | 100% | 30796.4112 | 0 | 0 | 30796.4112 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10265.4704 | 10265.4704 | 10265.4704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Carpenter Workshop |  | 100 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 15.6917 | 196.1458 | 1383.0635 | 2163.4101 | 3742.6194 | 1 | 100 | 100% | 0% | 0% | 100% | 3742.6194 | 0 | 0 | 3742.6194 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1247.5398 | 1247.5398 | 1247.5398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 253 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 43.75 | 546.875 | 3856.125 | 6031.8125 | 10434.8125 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 10434.8125 | 0 | 0 | 10434.8125 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3478.2708 | 3478.2708 | 3478.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 254 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 2513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 40.485 | 506.0629 | 3568.3507 | 5581.6714 | 9656.085 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 9656.085 | 0 | 0 | 9656.085 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3218.695 | 3218.695 | 3218.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 255 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 2513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 34.8513 | 522.7695 | 3071.7937 | 5227.6952 | 8822.2584 | 0 | 0 | 100% | 0% | 0% | 100% | 8822.2584 | 0 | 0 | 8822.2584 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2940.7528 | 2940.7528 | 2940.7528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 265 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2513-TK-003 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | ff3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) |  |  | Aecon Workshop |  | 1650 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 295.9 | 3698.75 | 26080.626 | 40795.733 | 70575.109 | 0.5 | 825 | 100% | 0% | 0% | 100% | 70575.109 | 0 | 0 | 70575.109 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 23525.0363 | 23525.0363 | 23525.0363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Sana Workshop | 2019-17 | 500 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 112.0833 | 1401.0417 | 9879.025 | 15452.9292 | 26732.9958 | 1 | 500 | 100% | 0% | 0% | 100% | 26732.9958 | 0 | 0 | 26732.9958 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8910.9986 | 8910.9986 | 8910.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Workshop | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Sana Workshop | 2019-17 | -500 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -112.0833 | -1401.0417 | -9879.025 | -15452.9292 | -26732.9958 | 1 | -500 | 100% | 0% | 0% | 100% | -26732.9958 | 0 | 0 | -26732.9958 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -8910.9986 | -8910.9986 | -8910.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers (2 units at 36 m2) |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Office trailers |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Crusher services trailer |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Site Contruction Office |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Offices and Lunchrooms (5 @ 36m2) |  | 180 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 40.35 | 504.375 | 3556.449 | 5563.0545 | 9623.8785 | 1 | 180 | 100% | 0% | 0% | 100% | 9623.8785 | 0 | 0 | 9623.8785 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3207.9595 | 3207.9595 | 3207.9595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 250 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 20 | 250 | 1762.8 | 2757.4 | 4770.2 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4770.2 | 0 | 0 | 4770.2 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1590.0667 | 1590.0667 | 1590.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 267 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 2513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 266 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613, W: 737, H: 1676 | 2513-TK-004 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 251 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 2513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 11 | 87.5 | 616.98 | 965.09 | 1669.57 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1669.57 | 0 | 0 | 1669.57 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 556.5233 | 556.5233 | 556.5233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 2513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Enhancement of training grounds for the Emergency Response Team with fire retardent infrastructure and secondary spill containment | 2022-17 | 59.4579 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 6.6642 | 83.303 | 587.3863 | 918.799 | 1589.4883 | 1 | 59.4579 | 100% | 0% | 0% | 100% | 1589.4883 | 0 | 0 | 1589.4883 | Type B Construction 2BC-MRY1416 | Addedd | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 529.8294 | 529.8294 | 529.8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 252 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Enhancement of training grounds for the Emergency Response Team with fire retardent infrastructure and secondary spill containment | 2022-17 | -59.4579 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -6.6642 | -83.303 | -587.3863 | -918.799 | -1589.4883 | 1 | -59.4579 | 100% | 0% | 0% | 100% | -1589.4883 | 0 | 0 | -1589.4883 | Type B Construction 2BC-MRY1416 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -529.8294 | -529.8294 | -529.8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 227 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 1388.4758 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 311.25 | 3890.625 | 27433.575 | 42912.0375 | 74236.2375 | 1 | 1388.4758 | 100% | 0% | 0% | 100% | 74236.2375 | 0 | 0 | 74236.2375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24745.4125 | 24745.4125 | 24745.4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 233 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 95 | 1187.5 | 8373.3 | 13097.65 | 22658.45 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 22658.45 | 0 | 0 | 22658.45 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7552.8167 | 7552.8167 | 7552.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 230 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-002 | 334.5725 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 75 | 937.5 | 6610.5 | 10340.25 | 17888.25 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 17888.25 | 0 | 0 | 17888.25 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5962.75 | 5962.75 | 5962.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 231 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 232 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-002 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 234 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 235 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 228 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 229 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 1388.4758 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Change Rooms - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Change Rooms - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Change Rooms - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Camp Pad development (Milne Port) |  | 45000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 571.1347 | 6581.25 | 50339.8167 | 18068.3031 | 74989.3698 | 0 | 0 | 100% | 0% | 0% | 100% | 74989.3698 | 0 | 0 | 74989.3698 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 24996.4566 | 24996.4566 | 24996.4566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash (Repurposed Warehouse) - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2523-BLD-001 | 0 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash (Repurposed Warehouse) - Demolish and foundations - Precast Footing (Perimeter Beam) | 2523-BLD-001 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash (Repurposed Warehouse) - Demolish floor finish - Gravel | 2523-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | 150000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1903.7825 | 21937.5 | 167799.3891 | 60227.6769 | 249964.5659 | 0 | 0 | 100% | 0% | 0% | 100% | 249964.5659 | 0 | 0 | 249964.5659 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 83321.522 | 83321.522 | 83321.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Milne Port) |  | -150000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1903.7825 | -21937.5 | -167799.3891 | -60227.6769 | -249964.5659 | 0 | 0 | 100% | 0% | 0% | 100% | -249964.5659 | 0 | 0 | -249964.5659 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -83321.522 | -83321.522 | -83321.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W1 |  | 23100 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 293.1825 | 3378.375 | 25841.1059 | 9275.0622 | 38494.5432 | 0 | 0 | 100% | 0% | 0% | 100% | 38494.5432 | 0 | 0 | 38494.5432 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 12831.5144 | 12831.5144 | 12831.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W6 |  | 2750 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 34.9027 | 402.1875 | 3076.3221 | 1104.1741 | 4582.6837 | 0 | 0 | 100% | 0% | 0% | 100% | 4582.6837 | 0 | 0 | 4582.6837 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1527.5612 | 1527.5612 | 1527.5612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W7 |  | 1780 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 22.5916 | 260.325 | 1991.2194 | 714.7018 | 2966.2462 | 0 | 0 | 100% | 0% | 0% | 100% | 2966.2462 | 0 | 0 | 2966.2462 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 988.7487 | 988.7487 | 988.7487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W3 |  | 14300 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 181.4939 | 2091.375 | 15996.8751 | 5741.7052 | 23829.9553 | 0 | 0 | 100% | 0% | 0% | 100% | 23829.9553 | 0 | 0 | 23829.9553 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7943.3184 | 7943.3184 | 7943.3184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W14 |  | 8850 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 112.3232 | 1294.3125 | 9900.164 | 3553.4329 | 14747.9094 | 0 | 0 | 100% | 0% | 0% | 100% | 14747.9094 | 0 | 0 | 14747.9094 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4915.9698 | 4915.9698 | 4915.9698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W15 |  | 10950 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 138.9761 | 1601.4375 | 12249.3554 | 4396.6204 | 18247.4133 | 0 | 0 | 100% | 0% | 0% | 100% | 18247.4133 | 0 | 0 | 18247.4133 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6082.4711 | 6082.4711 | 6082.4711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W10B |  | 12450 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 158.0139 | 1820.8125 | 13927.3493 | 4998.8972 | 20747.059 | 0 | 0 | 100% | 0% | 0% | 100% | 20747.059 | 0 | 0 | 20747.059 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6915.6863 | 6915.6863 | 6915.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown W11 |  | 7550 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 95.8237 | 1104.1875 | 8445.9026 | 3031.4597 | 12581.5498 | 0 | 0 | 100% | 0% | 0% | 100% | 12581.5498 | 0 | 0 | 12581.5498 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4193.8499 | 4193.8499 | 4193.8499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 270 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-001 | 892.1933 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 500 | 1750 | 44070 | 68935 | 114755 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 114755 | 0 | 0 | 114755 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 38251.6667 | 38251.6667 | 38251.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 276 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2521-BLD-003 | 267.658 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 150 | 750 | 13221 | 20680.5 | 34651.5 | 1 | 267.658 | 100% | 0% | 0% | 100% | 34651.5 | 0 | 0 | 34651.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11550.5 | 11550.5 | 11550.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 271 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-001 | 892.1933 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 129.5521 | 1619.4013 | 11418.7223 | 17861.3484 | 30899.472 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 30899.472 | 0 | 0 | 30899.472 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10299.824 | 10299.824 | 10299.824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 272 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-001 | 892.1933 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 111.5242 | 1672.8625 | 9829.7398 | 16728.6245 | 28231.2268 | 0 | 0 | 100% | 0% | 0% | 100% | 28231.2268 | 0 | 0 | 28231.2268 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9410.4089 | 9410.4089 | 9410.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 273 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-002 | 148.6989 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 83.3333 | 291.6667 | 7345 | 11489.1667 | 19125.8333 | 1 | 148.6989 | 100% | 0% | 0% | 100% | 19125.8333 | 0 | 0 | 19125.8333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6375.2778 | 6375.2778 | 6375.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 296 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 2521.5-P | 255 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 63.75 | 796.875 | 5618.925 | 8789.2125 | 15205.0125 | 0.01 | 2.55 | 100% | 0% | 100% | 0% | 15205.0125 | 0 | 15205.0125 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5068.3375 | 5068.3375 | 5068.3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 295 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791, W: 1829, H: 610 | 2521-TK-053 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar for Ore Pad |  | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type B Construction 2BC-MRY1416 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 279 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 2521-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 294 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803, W: 1245, H: 1346 | 2521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 280 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 274 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-002 | 148.6989 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 21.592 | 269.9002 | 1903.1204 | 2976.8914 | 5149.912 | 0.75 | 111.5242 | 100% | 0% | 0% | 100% | 5149.912 | 0 | 0 | 5149.912 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1716.6373 | 1716.6373 | 1716.6373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 277 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 2521-BLD-003 | 267.658 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 33 | 262.5 | 1850.94 | 2895.27 | 5008.71 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5008.71 | 0 | 0 | 5008.71 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1669.57 | 1669.57 | 1669.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 275 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade | 2521-BLD-002 | 148.6989 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 18.5874 | 278.8104 | 1638.29 | 2788.1041 | 4705.2045 | 0 | 0 | 100% | 0% | 0% | 100% | 4705.2045 | 0 | 0 | 4705.2045 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1568.4015 | 1568.4015 | 1568.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 292 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 293 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 281 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 278 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 2521-BLD-003 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Anmar Workshop |  | 1670 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 74.3014 | 284.067 | 6548.9294 | 1138.6111 | 7929.2928 | 0 | 0 | 100% | 0% | 0% | 100% | 7929.2928 | 0 | 0 | 7929.2928 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2643.0976 | 2643.0976 | 2643.0976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-005 | 0 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-005 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-005 | 0 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2- Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-006 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2- Demolish floor finish - Slab on grade | 2521-BLD-006 | 0 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 91.0304 | 348.0246 | 8023.4189 | 1394.969 | 9766.4125 | 0 | 0 | 100% | 0% | 0% | 100% | 9766.4125 | 0 | 0 | 9766.4125 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3255.4708 | 3255.4708 | 3255.4708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Addition of offices/ trailers at the Environment Department work areas | 2022-18 | 55.7418 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 6.2477 | 78.0966 | 550.6746 | 861.3741 | 1490.1453 | 1 | 55.7418 | 100% | 0% | 0% | 100% | 1490.1453 | 0 | 0 | 1490.1453 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 496.7151 | 496.7151 | 496.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Addition of offices/ trailers at the Environment Department work areas | 2022-18 | -55.7418 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -6.2477 | -78.0966 | -550.6746 | -861.3741 | -1490.1453 | 1 | -55.7418 | 100% | 0% | 0% | 100% | -1490.1453 | 0 | 0 | -1490.1453 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -496.7151 | -496.7151 | -496.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 301 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 2522-SQ-004 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 306 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 2522-SQ-011 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 313 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-026 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 314 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-027 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 351 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-009 | 75.2788 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 42.1875 | 210.9375 | 3718.4063 | 5816.3906 | 9745.7344 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 9745.7344 | 0 | 0 | 9745.7344 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3248.5781 | 3248.5781 | 3248.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 354 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-010 | 75.2788 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 42.1875 | 210.9375 | 3718.4063 | 5816.3906 | 9745.7344 | 1 | 75.2788 | 100% | 0% | 0% | 100% | 9745.7344 | 0 | 0 | 9745.7344 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3248.5781 | 3248.5781 | 3248.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 327 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 330 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 333 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 336 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 339 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 342 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 345 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-007 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 348 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2530-BLD-008 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 357 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 2530-BLD-011 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.3889 | 1283.3889 | 1283.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 358 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 359 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-011 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 328 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 329 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 331 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 332 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 334 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 335 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 337 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 338 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 340 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 341 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 343 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 344 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 346 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 347 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-007 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 349 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 350 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-008 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 352 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 353 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-009 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 355 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation | 356 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2530-BLD-010 | 75.2788 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-002 | 56 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 8.7873 | 109.8417 | 774.5156 | 1211.5096 | 2095.8669 | 1 | 56 | 100% | 0% | 0% | 100% | 2095.8669 | 0 | 0 | 2095.8669 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 698.6223 | 698.6223 | 698.6223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-002 | 56 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 8.1316 | 101.6444 | 716.7151 | 1121.0973 | 1939.4569 | 0.75 | 42 | 100% | 0% | 0% | 100% | 1939.4569 | 0 | 0 | 1939.4569 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 646.4856 | 646.4856 | 646.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 4.4833 | 56.0417 | 395.161 | 618.1172 | 1069.3198 | 1 | 20 | 100% | 0% | 0% | 100% | 1069.3198 | 0 | 0 | 1069.3198 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 356.4399 | 356.4399 | 356.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical office - Demolish and foundations - Precast Footing (Perimeter Beam) | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical office - Demolish floor finish - Gravel | 2530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2530 | Power Generation | 2530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 2530-BLD-BIM-002 | 56 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 361 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 250 | 875 | 22035 | 34467.5 | 57377.5 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 57377.5 | 0 | 0 | 57377.5 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 19125.8333 | 19125.8333 | 19125.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 362 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 64.7761 | 809.7006 | 5709.3612 | 8930.6742 | 15449.736 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 15449.736 | 0 | 0 | 15449.736 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5149.912 | 5149.912 | 5149.912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 363 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 2540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 55.7621 | 836.4312 | 4914.8699 | 8364.3123 | 14115.6134 | 0 | 0 | 100% | 0% | 0% | 100% | 14115.6134 | 0 | 0 | 14115.6134 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4705.2045 | 4705.2045 | 4705.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2020-3 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2020-3 | -1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | -47 | -400 | -4142.58 | -4411.84 | -8954.42 | 329.2683 | -329.2683 | 100% | 0% | 0% | 100% | -8954.42 | 0 | 0 | -8954.42 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2984.8067 | -2984.8067 | -2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2540-VP-001 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 364 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1667 | 145.8333 | 2570.75 | 4021.2083 | 6737.7917 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 6737.7917 | 0 | 0 | 6737.7917 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2245.9306 | 2245.9306 | 2245.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 374 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2540-TK-003 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 371 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 2540-SQ-002 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 365 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 366 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 2540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 375 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person temporary soft-walled camp at Milne Port |  | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 12933 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 575.4135 | 2199.9033 | 50716.9482 | 8817.7588 | 61734.6103 | 0 | 0 | 100% | 0% | 0% | 100% | 61734.6103 | 0 | 0 | 61734.6103 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20578.2034 | 20578.2034 | 20578.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm at Milne Inlet - New waste management building |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Future Hazardous Waste Berm |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Hazardous Waste Berm |  | 0 | m2 | 0.0318 | 0.02385 | 2.8029 | 0.28029 | 3.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Snow Dump |  | 3189 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 141.8846 | 542.4489 | 12505.71 | 2174.2699 | 15141.6257 | 0 | 0 | 100% | 0% | 0% | 100% | 15141.6257 | 0 | 0 | 15141.6257 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5047.2086 | 5047.2086 | 5047.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Contaminated Snow dump/oily water containment - new 2019 | 2019-9 | 2700 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 120.1281 | 459.27 | 10588.0894 | 1840.8682 | 12819.8148 | 0 | 0 | 100% | 0% | 0% | 100% | 12819.8148 | 0 | 0 | 12819.8148 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4273.2716 | 4273.2716 | 4273.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste containment facilities 2020 Port Shop - 72m2 |  | 72 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 3.2034 | 12.2472 | 282.3491 | 49.0898 | 341.8617 | 0 | 0 | 100% | 0% | 0% | 100% | 341.8617 | 0 | 0 | 341.8617 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 113.9539 | 113.9539 | 113.9539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New Hazardous Waste Berm 2019 | 2019-11 | 360 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 16.0171 | 61.236 | 1411.7453 | 245.4491 | 1709.3086 | 0 | 0 | 100% | 0% | 0% | 100% | 1709.3086 | 0 | 0 | 1709.3086 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.7695 | 569.7695 | 569.7695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-1 | 2000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 88.9838 | 340.2 | 7843.0292 | 1363.6061 | 9496.1591 | 0 | 0 | 100% | 0% | 0% | 100% | 9496.1591 | 0 | 0 | 9496.1591 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3165.3864 | 3165.3864 | 3165.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-3 | 678 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 30.1655 | 115.3278 | 2658.7869 | 462.2625 | 3219.1979 | 0 | 0 | 100% | 0% | 0% | 100% | 3219.1979 | 0 | 0 | 3219.1979 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1073.066 | 1073.066 | 1073.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-5 | 652 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 29.0087 | 110.9052 | 2556.8275 | 444.5356 | 3095.7479 | 0 | 0 | 100% | 0% | 0% | 100% | 3095.7479 | 0 | 0 | 3095.7479 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1031.916 | 1031.916 | 1031.916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-4 | 597 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 26.5617 | 101.5497 | 2341.1442 | 407.0364 | 2834.6035 | 0 | 0 | 100% | 0% | 0% | 100% | 2834.6035 | 0 | 0 | 2834.6035 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 944.8678 | 944.8678 | 944.8678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-2 | 272 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 12.1018 | 46.2672 | 1066.652 | 185.4504 | 1291.4776 | 0 | 0 | 100% | 0% | 0% | 100% | 1291.4776 | 0 | 0 | 1291.4776 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 430.4925 | 430.4925 | 430.4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MP-HWB-6 | 34 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 1.5127 | 5.7834 | 133.3315 | 23.1813 | 161.4347 | 0 | 0 | 100% | 0% | 0% | 100% | 161.4347 | 0 | 0 | 161.4347 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53.8116 | 53.8116 | 53.8116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 398 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-001 | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 77142.301 | 77142.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 399 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-002 | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 77142.301 | 77142.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 400 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-003 | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 77142.301 | 77142.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 401 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 | 2613-TK-004 | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 77142.301 | 77142.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 402 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-005 | 1 | Ea | 418.6 | 4887.5 | 36895.404 | 53907.17 | 95690.074 | 418.6 | 4887.5 | 36895.404 | 53907.17 | 95690.074 | 80 | 80 | 100% | 0% | 0% | 100% | 95690.074 | 0 | 0 | 95690.074 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 47845.037 | 47845.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 403 | TK- | MT3-d | Large Diesel Tanks Load and Transport (5M L) | MT3-d | Mechanical Equipment | Large Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 25600 DI H: 9760 | 2613-TK-006 | 1 | Ea | 418.6 | 4887.5 | 36895.404 | 53907.17 | 95690.074 | 418.6 | 4887.5 | 36895.404 | 53907.17 | 95690.074 | 80 | 80 | 100% | 0% | 0% | 100% | 95690.074 | 0 | 0 | 95690.074 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 47845.037 | 47845.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 387 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-014 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1925.0833 | 1925.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 384 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-013 | 14.8699 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 8.3333 | 41.6667 | 734.5 | 1148.9167 | 1925.0833 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1925.0833 | 0 | 0 | 1925.0833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 962.5417 | 962.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 386 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-013 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 385 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-013 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 389 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-014 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 388 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-014 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 85.45 | 941.25 | 7531.563 | 10381.611 | 18854.424 | 30 | 60 | 100% | 0% | 0% | 100% | 18854.424 | 0 | 0 | 18854.424 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6284.808 | 6284.808 | 6284.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 15ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 51428.2007 | 51428.2007 | 51428.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | Additional 3ML Arctic Diesel Tank at Milne Port |  | 1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 160 | 160 | 100% | 0% | 0% | 100% | 154284.602 | 0 | 0 | 154284.602 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 51428.2007 | 51428.2007 | 51428.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Farm Berm |  | 25393 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 1129.7824 | 4319.3493 | 99579.0201 | 17313.0247 | 121211.3941 | 0 | 0 | 100% | 0% | 0% | 100% | 121211.3941 | 0 | 0 | 121211.3941 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 60605.6971 | 60605.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 413 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-007 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 414 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-008 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 415 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-009 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - JET-A1 TANK W: 10250 DI H: 9140 | 2614-TK-010 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 405 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2614-FD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 8.3333 | 41.6667 | 734.5 | 1148.9167 | 1925.0833 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1925.0833 | 0 | 0 | 1925.0833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 962.5417 | 962.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 407 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Jet-A1 Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2614-FD-011 | 14.8645 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 406 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Jet-A1 Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2614-FD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 416 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | Additional 750 kL Jet-A Tank at Milne Port |  | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 418 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 17.7083 | 61.9792 | 1560.8125 | 2441.4479 | 4064.2396 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 4064.2396 | 0 | 0 | 4064.2396 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1354.7465 | 1354.7465 | 1354.7465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 419 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2615-BLD-001 | 31.5985 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 17.7083 | 61.9792 | 1560.8125 | 2441.4479 | 4064.2396 | 1 | 31.5985 | 100% | 0% | 0% | 100% | 4064.2396 | 0 | 0 | 4064.2396 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1354.7465 | 1354.7465 | 1354.7465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2615 | Marine Pipeline | 420 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Marine Manifold Building - Demolish floor finish - Raised Steel or Wooden Floor | 2615-BLD-001 | 31.5985 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2616 | Weatherhaven camp |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Weatherhaven genset fuel bladder berm |  | 500 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 22.2459 | 85.05 | 1960.7573 | 340.9015 | 2374.0398 | 0 | 0 | 100% | 0% | 0% | 100% | 2374.0398 | 0 | 0 | 2374.0398 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 791.3466 | 791.3466 | 791.3466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities
2000 | Milne Port | 2700 | Site Utilities | 0 | Power Distribution System |  | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Port Site |  | 3500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 350 | 4375 | 30849 | 48254.5 | 83478.5 | 0.01 | 35 | 100% | 0% | 0% | 100% | 83478.5 | 0 | 0 | 83478.5 | Type B Construction 2BC-MRY1416 |  | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 27826.1667 | 27826.1667 | 27826.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 50,000 L Portable Fuel Dispensing Unit |  | 1364 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 60.6869 | 232.0164 | 5348.9459 | 929.9794 | 6510.9417 | 0 | 0 | 100% | 0% | 0% | 100% | 6510.9417 | 0 | 0 | 6510.9417 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2170.3139 | 2170.3139 | 2170.3139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Water Tank Main Unit |  | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 0 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 2017 -Water tanks on Sea Lift |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 964.8358 | 964.8358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 431 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 61.25 | 765.625 | 5398.575 | 8444.5375 | 14608.7375 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 14608.7375 | 0 | 0 | 14608.7375 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4869.5792 | 4869.5792 | 4869.5792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 432 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 56.679 | 708.4881 | 4995.691 | 7814.3399 | 13518.519 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 13518.519 | 0 | 0 | 13518.519 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4506.173 | 4506.173 | 4506.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | -1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | -47 | -400 | -4142.58 | -4411.84 | -8954.42 | 329.2683 | -329.2683 | 100% | 0% | 100% | 0% | -8954.42 | 0 | -8954.42 | 0 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2984.8067 | -2984.8067 | -2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant |  | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant | 2021-13 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Desalination Plant | 2021-13 | -1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | -47 | -400 | -4142.58 | -4411.84 | -8954.42 | 329.2683 | -329.2683 | 100% | 0% | 100% | 0% | -8954.42 | 0 | -8954.42 | 0 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2984.8067 | -2984.8067 | -2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE VENDOR PACKAGE | 2720-VP-020 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 448 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 2720-TK-001 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 449 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 2720-TK-007 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 450 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 2720-TK-008 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 451 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 2720-TK-011 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 452 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE WATER BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2720-TK-033 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 433 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 2720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - POTABLE WATER STORAGE TANK (20 m3) |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - RAW WATER TANK (25 m3) |  | 0 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 453 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 380-person temporary soft-walled camp at Milne Port |  | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 4180 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 185.9761 | 711.018 | 16391.931 | 2849.9367 | 19846.9725 | 0 | 0 | 100% | 0% | 0% | 100% | 19846.9725 | 0 | 0 | 19846.9725 | Type B Construction 2BC-MRY1416 | Modified | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6615.6575 | 6615.6575 | 6615.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond #3 |  |  | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 4260 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 189.5354 | 724.626 | 16705.6522 | 2904.481 | 20226.8189 | 0 | 0 | 100% | 0% | 0% | 100% | 20226.8189 | 0 | 0 | 20226.8189 | Type B Construction 2BC-MRY1416 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6742.273 | 6742.273 | 6742.273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 459 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 100 | 500 | 8814 | 13787 | 23101 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 23101 | 0 | 0 | 23101 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11550.5 | 11550.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 468 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 2731.2-P | 258 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 64.5 | 806.25 | 5685.03 | 8892.615 | 15383.895 | 0.01 | 2.58 | 100% | 0% | 100% | 0% | 15383.895 | 0 | 15383.895 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7691.9475 | 7691.9475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 2731-VP-005 | 1 | Lot | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9908.46 | 0 | 9908.46 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4954.23 | 4954.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 456 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 2731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1925.0833 | 1925.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 457 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 458 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 2731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 467 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 2731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 460 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 461 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 2731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 466 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 380-person temporary soft-walled camp at Milne Port |  | 1 | Lot | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9908.46 | 0 | 9908.46 | 0 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4954.23 | 4954.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 470 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 31.25 | 109.375 | 2754.375 | 4308.4375 | 7172.1875 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 7172.1875 | 0 | 0 | 7172.1875 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3586.0938 | 3586.0938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 477 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MILNE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 2732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 471 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 2732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 8.097 | 101.2126 | 713.6701 | 1116.3343 | 1931.217 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1931.217 | 0 | 0 | 1931.217 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 965.6085 | 965.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 472 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 2732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 480 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to effluent pond and ocean discharge | 2734.1-P | 2595 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 648.75 | 8109.375 | 57180.825 | 89443.1625 | 154733.3625 | 0.01 | 25.95 | 100% | 0% | 100% | 0% | 154733.3625 | 0 | 154733.3625 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 51577.7875 | 51577.7875 | 51577.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 0 | Sewage System |  | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the Milne Port treated effluent line |  | 750 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 187.5 | 2343.75 | 16526.25 | 25850.625 | 44720.625 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 44720.625 | 0 | 44720.625 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14906.875 | 14906.875 | 14906.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2010 | Sewage System | 2018 | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the fuel manifold and piping line | 2018-28 | 750 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 187.5 | 2343.75 | 16526.25 | 25850.625 | 44720.625 | 0.01 | 7.5 | 100% | 0% | 100% | 0% | 44720.625 | 0 | 44720.625 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14906.875 | 14906.875 | 14906.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2010 | Sewage System | 2018 | Treated Effluent Discharge |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Realignment of the fuel manifold and piping line | 2018-28 | -750 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | -187.5 | -2343.75 | -16526.25 | -25850.625 | -44720.625 | 0.01 | -7.5 | 100% | 0% | 100% | 0% | -44720.625 | 0 | -44720.625 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -14906.875 | -14906.875 | -14906.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2734 | Treated Effluent Discharge | 479 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to effluent pond and ocean discharge | 2734.1-E | 1330 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 498 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV - Electrical distribution system from power gen to e-house | 2750.2-E | 6100 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 610 | 7625 | 53765.4 | 84100.7 | 145491.1 | 0.01 | 61 | 100% | 0% | 0% | 100% | 145491.1 | 0 | 0 | 145491.1 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 48497.0333 | 48497.0333 | 48497.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 2750.3-E | 5000 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 500 | 6250 | 44070 | 68935 | 119255 | 0.01 | 50 | 100% | 0% | 0% | 100% | 119255 | 0 | 0 | 119255 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 39751.6667 | 39751.6667 | 39751.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 499 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation - Milne Port 'Steensby Camp' power line (100 m) | 2750.3-E | 100 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 10 | 125 | 881.4 | 1378.7 | 2385.1 | 0.01 | 1 | 100% | 0% | 0% | 100% | 2385.1 | 0 | 0 | 2385.1 | Type B Construction 2BC-MRY1416 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 795.0333 | 795.0333 | 795.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 483 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 13.3333 | 166.6667 | 1175.2 | 1838.2667 | 3180.1333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3180.1333 | 0 | 0 | 3180.1333 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1060.0444 | 1060.0444 | 1060.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 486 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | e-house |  | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 489 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 492 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 495 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-005 | 2.3234 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0.52083 | 6.5104 | 45.9062 | 71.8073 | 124.224 | 1 | 2.3234 | 100% | 0% | 0% | 100% | 124.224 | 0 | 0 | 124.224 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 62.112 | 62.112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 496 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 497 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-005 | 2.3234 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 487 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 488 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 490 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 491 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 493 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 494 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 484 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 485 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road
3000 | Tote Road | 3100 | General
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 3111-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 507 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 3111-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 510 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 3 - Demolish Building - ISO Shipping Container | 3111-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 513 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 4 - Demolish Building - ISO Shipping Container | 3111-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 505 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 506 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 508 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 509 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 511 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 3 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 512 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 514 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 4 - Demolish and foundations - Gravel Base - Skidded Building | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 515 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3111-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km88 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km80 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km69 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km49 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km40 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km26 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1 | 504 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | IT Towers Communication Sheds - km7 (10 units at 15m2 ea) |  | 150 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 16.8125 | 210.1562 | 1481.8537 | 2317.9394 | 4009.9494 | 1 | 150 | 100% | 0% | 0% | 100% | 4009.9494 | 0 | 0 | 4009.9494 | Type A 2AM-MRY1325 | added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1336.6498 | 1336.6498 | 1336.6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 517 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 5 - Demolish Building - ISO Shipping Container | 3112-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 520 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 6 - Demolish Building - ISO Shipping Container | 3112-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 523 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 7 - Demolish Building - ISO Shipping Container | 3112-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 526 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 8 - Demolish Building - ISO Shipping Container | 3112-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 518 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 5 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 519 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 5 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 521 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 6 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 522 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 6 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 524 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 7 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 525 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 7 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 527 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 8 - Demolish and foundations - Gravel Base - Skidded Building | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3112 | Communications Facility No. 2 | 528 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 8 - Demolish floor finish - Raised Steel or Wooden Floor | 3112-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 530 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 9 - Demolish Building - ISO Shipping Container | 3113-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 533 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 10 - Demolish Building - ISO Shipping Container | 3113-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 536 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 11 - Demolish Building - ISO Shipping Container | 3113-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 531 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 9 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 532 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 9 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 534 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 10 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 535 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 10 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 537 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 11 - Demolish and foundations - Gravel Base - Skidded Building | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3110 | Communication and IT Infrastructure | 3113 | Communications Facility No. 3 | 538 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 11 - Demolish floor finish - Raised Steel or Wooden Floor | 3113-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source |  | 41795 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 530.4573 | 6112.5187 | 46754.5031 | 16781.4384 | 69648.4602 | 0 | 0 | 100% | 0% | 0% | 100% | 69648.4602 | 0 | 0 | 69648.4602 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 69648.4602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2017) |  | 1000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 12.6919 | 146.25 | 1118.6626 | 401.5178 | 1666.4304 | 0 | 0 | 100% | 0% | 0% | 100% | 1666.4304 | 0 | 0 | 1666.4304 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1666.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at Km 2 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km 2 Borrow source (marginal increase in 2018) |  | 1500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 19.0378 | 219.375 | 1677.9939 | 602.2768 | 2499.6457 | 0 | 0 | 100% | 0% | 0% | 100% | 2499.6457 | 0 | 0 | 2499.6457 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2499.6457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Borrow Source at P1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P1 Borrow Source |  | 75820 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 962.2986 | 11088.675 | 84816.9979 | 30443.0831 | 126348.7559 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 126348.7559 | 0 | 126348.7559 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 63174.378 | 63174.378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Explosive magazine pads along Tote Road |  | 760 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 9.6458 | 111.15 | 850.1836 | 305.1536 | 1266.4871 | 0 | 0 | 100% | 0% | 0% | 100% | 1266.4871 | 0 | 0 | 1266.4871 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 422.1624 | 422.1624 | 422.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R3 (2017 Carry Over) |  | 25800 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 327.4506 | 3773.25 | 28861.4949 | 10359.1604 | 42955.5125 | 0 | 0 | 100% | 0% | 0% | 100% | 42955.5125 | 0 | 0 | 42955.5125 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14318.5042 | 14318.5042 | 14318.5042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R1 (2017 Carry Over) |  | 20200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 256.376 | 2954.25 | 22596.9844 | 8110.6605 | 33631.8354 | 0 | 0 | 100% | 0% | 0% | 100% | 33631.8354 | 0 | 0 | 33631.8354 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11210.6118 | 11210.6118 | 11210.6118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown R2 (2017 Carry Over) |  | 20000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 253.8377 | 2925 | 22373.2519 | 8030.3569 | 33298.8469 | 0 | 0 | 100% | 0% | 0% | 100% | 33298.8469 | 0 | 0 | 33298.8469 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11099.6156 | 11099.6156 | 11099.6156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2 - 2019 |  | 55800 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 708.2071 | 8160.75 | 62421.3727 | 22404.6958 | 92903.7829 | 0 | 0 | 100% | 0% | 0% | 100% | 92903.7829 | 0 | 0 | 92903.7829 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 30967.9276 | 30967.9276 | 30967.9276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 4 - 2019 |  | -66300 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -841.4719 | -9696.375 | -74167.33 | -26620.6332 | -110385.6775 | 0 | 0 | 100% | 0% | 0% | 100% | -110385.6775 | 0 | 0 | -110385.6775 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -36795.2258 | -36795.2258 | -36795.2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 4 - 2019 |  | 66300 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 841.4719 | 9696.375 | 74167.33 | 26620.6332 | 110385.6775 | 0 | 0 | 100% | 0% | 0% | 100% | 110385.6775 | 0 | 0 | 110385.6775 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 36795.2258 | 36795.2258 | 36795.2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 7 - 2019 |  | -28900 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -366.7954 | -4226.625 | -32329.349 | -11603.8657 | -48116.8338 | 0 | 0 | 100% | 0% | 0% | 100% | -48116.8338 | 0 | 0 | -48116.8338 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -16038.9446 | -16038.9446 | -16038.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 7 - 2019 |  | 28900 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 366.7954 | 4226.625 | 32329.349 | 11603.8657 | 48116.8338 | 0 | 0 | 100% | 0% | 0% | 100% | 48116.8338 | 0 | 0 | 48116.8338 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16038.9446 | 16038.9446 | 16038.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 9 - 2019 | 2019-2-C | 92500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1173.9992 | 13528.125 | 103476.2899 | 37140.4007 | 154007.167 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 154007.167 | 0 | 154007.167 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 51335.7223 | 51335.7223 | 51335.7223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 9 - 2019 | 2019-2-C | -92500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1173.9992 | -13528.125 | -103476.2899 | -37140.4007 | -154007.167 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -154007.167 | 0 | -154007.167 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -51335.7223 | -51335.7223 | -51335.7223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 10 - 2019 |  | -34500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -437.87 | -5045.625 | -38593.8595 | -13852.3657 | -57440.5109 | 0 | 0 | 100% | 0% | 0% | 100% | -57440.5109 | 0 | 0 | -57440.5109 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -19146.837 | -19146.837 | -19146.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 10 - 2019 |  | 34500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 437.87 | 5045.625 | 38593.8595 | 13852.3657 | 57440.5109 | 0 | 0 | 100% | 0% | 0% | 100% | 57440.5109 | 0 | 0 | 57440.5109 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 19146.837 | 19146.837 | 19146.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 13 - 2019 |  | -7000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -88.8432 | -1023.75 | -7830.6382 | -2810.6249 | -11654.5964 | 0 | 0 | 100% | 0% | 0% | 100% | -11654.5964 | 0 | 0 | -11654.5964 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3884.8655 | -3884.8655 | -3884.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 13 - 2019 |  | 7000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 88.8432 | 1023.75 | 7830.6382 | 2810.6249 | 11654.5964 | 0 | 0 | 100% | 0% | 0% | 100% | 11654.5964 | 0 | 0 | 11654.5964 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3884.8655 | 3884.8655 | 3884.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown at km 61 |  | 6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 76.1513 | 877.5 | 6711.9756 | 2409.1071 | 9989.6541 | 0 | 0 | 100% | 0% | 0% | 100% | 9989.6541 | 0 | 0 | 9989.6541 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3329.8847 | 3329.8847 | 3329.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 88 IT Tower Pad |  | 6400 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 81.2281 | 936 | 7159.4406 | 2569.7142 | 10655.631 | 0 | 0 | 100% | 0% | 0% | 100% | 10655.631 | 0 | 0 | 10655.631 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3551.877 | 3551.877 | 3551.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 80 IT Tower Pad |  | 6400 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 81.2281 | 936 | 7159.4406 | 2569.7142 | 10655.631 | 0 | 0 | 100% | 0% | 0% | 100% | 10655.631 | 0 | 0 | 10655.631 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3551.877 | 3551.877 | 3551.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 69 IT Tower Pad |  | 5100 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 64.7286 | 745.875 | 5705.1792 | 2047.741 | 8491.206 | 0 | 0 | 100% | 0% | 0% | 100% | 8491.206 | 0 | 0 | 8491.206 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2830.402 | 2830.402 | 2830.402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 49 IT Tower Pad |  | 5600 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 71.0745 | 819 | 6264.5105 | 2248.4999 | 9323.6771 | 0 | 0 | 100% | 0% | 0% | 100% | 9323.6771 | 0 | 0 | 9323.6771 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3107.8924 | 3107.8924 | 3107.8924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 40 IT Tower Pad |  | 2600 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 32.9989 | 380.25 | 2908.5227 | 1043.9464 | 4328.8501 | 0 | 0 | 100% | 0% | 0% | 100% | 4328.8501 | 0 | 0 | 4328.8501 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1442.95 | 1442.95 | 1442.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 26 IT Tower Pad |  | 4000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 50.7675 | 585 | 4474.6504 | 1606.0714 | 6659.7694 | 0 | 0 | 100% | 0% | 0% | 100% | 6659.7694 | 0 | 0 | 6659.7694 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2219.9231 | 2219.9231 | 2219.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3139 | Infrastructure Pads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development - Km 07 IT Tower Pad |  | 3800 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 48.2292 | 555.75 | 4250.9179 | 1525.7678 | 6326.7809 | 0 | 0 | 100% | 0% | 0% | 100% | 6326.7809 | 0 | 0 | 6326.7809 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2108.927 | 2108.927 | 2108.927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3136 | Mary River |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour Building Footprints | Grade and Contour | Grade and Re-Contour Building Footprints |  | 13040 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 165.5022 | 1907.1 | 14587.3602 | 5235.7927 | 21730.2529 | 0 | 0 | 100% | 0% | 0% | 100% | 21730.2529 | 0 | 0 | 21730.2529 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7243.4176 | 7243.4176 | 7243.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Q13 Quarry (marginal increase to existing) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 25000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 317.2971 | 3656.25 | 27966.5648 | 10037.9461 | 41623.5586 | 0 | 0 | 100% | 0% | 0% | 100% | 41623.5586 | 0 | 0 | 41623.5586 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 20811.7793 | 20811.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P10 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P10 Borrow Source |  | 19344 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 245.5118 | 2829.06 | 21639.4092 | 7766.9612 | 32206.6447 | 0 | 0 | 100% | 0% | 0% | 100% | 32206.6447 | 0 | 0 | 32206.6447 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 16103.3224 | 16103.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P13 Borrow Source |  | 8456 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 107.3226 | 1236.69 | 9459.4109 | 3395.2349 | 14078.7525 | 0 | 0 | 100% | 0% | 0% | 100% | 14078.7525 | 0 | 0 | 14078.7525 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7039.3762 | 7039.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P14 Borrow Source |  | 3160 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 40.1064 | 462.15 | 3534.9738 | 1268.7964 | 5261.2178 | 0 | 0 | 100% | 0% | 0% | 100% | 5261.2178 | 0 | 0 | 5261.2178 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2630.6089 | 2630.6089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P15 Borrow Source |  | 3300 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 41.8832 | 482.625 | 3691.5866 | 1325.0089 | 5494.3097 | 0 | 0 | 100% | 0% | 0% | 100% | 5494.3097 | 0 | 0 | 5494.3097 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2747.1549 | 2747.1549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Removal of Quarry and Borrow No Longer being Developed (Q9, Q14, Q15, P5, P6, P7, P8, P10, P13, P14, and P15) |  | -102131 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1296.2347 | -14936.6587 | -114250.1294 | -41007.4191 | -170042.2267 | 0 | 0 | 100% | 0% | 0% | 100% | -170042.2267 | 0 | 0 | -170042.2267 | Type A 2AM-MRY1325 | Removed | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -85021.1134 | -85021.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P5 Borrow Source |  | 4600 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 58.3827 | 672.75 | 5145.8479 | 1846.9821 | 7658.7348 | 0 | 0 | 100% | 0% | 0% | 100% | 7658.7348 | 0 | 0 | 7658.7348 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3829.3674 | 3829.3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P6 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P6 Borrow Source |  | 7500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 95.1891 | 1096.875 | 8389.9695 | 3011.3838 | 12487.0676 | 0 | 0 | 100% | 0% | 0% | 100% | 12487.0676 | 0 | 0 | 12487.0676 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6243.5338 | 6243.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P7 Borrow Source |  | 8100 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 102.8043 | 1184.625 | 9061.167 | 3252.2946 | 13486.033 | 0 | 0 | 100% | 0% | 0% | 100% | 13486.033 | 0 | 0 | 13486.033 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6743.0165 | 6743.0165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at P8 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | P8 Borrow Source |  | 8385 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 106.4214 | 1226.3062 | 9379.9858 | 3366.7271 | 13960.5416 | 0 | 0 | 100% | 0% | 0% | 100% | 13960.5416 | 0 | 0 | 13960.5416 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 6980.2708 | 6980.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry |  | 64200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 814.8189 | 9389.25 | 71818.1385 | 25777.4457 | 106984.8342 | 0 | 0 | 100% | 0% | 0% | 100% | 106984.8342 | 0 | 0 | 106984.8342 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 53492.4171 | 53492.4171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2019) | 2019-1-A | 226000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2868.3656 | 33052.5 | 252817.7462 | 90743.0331 | 376613.2793 | 0 | 0 | 100% | 0% | 0% | 100% | 376613.2793 | 0 | 0 | 376613.2793 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 188306.6397 | 188306.6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2019) | 2019-1-A | -226000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -2868.3656 | -33052.5 | -252817.7462 | -90743.0331 | -376613.2793 | 0 | 0 | 100% | 0% | 0% | 100% | -376613.2793 | 0 | 0 | -376613.2793 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -188306.6397 | -188306.6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 76.1513 | 877.5 | 6711.9756 | 2409.1071 | 9998.5826 | 0 | 0 | 100% | 0% | 0% | 100% | 9998.5826 | 0 | 0 | 9998.5826 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4999.2913 | 4999.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 634.5942 | 7312.5 | 55933.1297 | 20075.8923 | 83321.522 | 0 | 0 | 100% | 0% | 0% | 100% | 83321.522 | 0 | 0 | 83321.522 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 41660.761 | 41660.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (revised to PDA boundary) |  | -651406 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -8267.5689 | -95268.1275 | -728703.5255 | -261551.1338 | -1085522.7869 | 0 | 0 | 100% | 0% | 0% | 100% | -1085522.7869 | 0 | 0 | -1085522.7869 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -542761.3934 | -542761.3934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q1 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q1 Quarry (marginal increase to existing in remainder 2017 - total now reflects area in QMP) |  | 824500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 10464.4578 | 120583.125 | 922337.3085 | 331051.4638 | 1373971.8974 | 0 | 0 | 100% | 0% | 0% | 100% | 1373971.8974 | 0 | 0 | 1373971.8974 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 686985.9487 | 686985.9487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q11 Quarry |  | 50433 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 640.0898 | 7375.8262 | 56417.5106 | 20249.7495 | 84043.0864 | 0 | 0 | 100% | 0% | 0% | 100% | 84043.0864 | 0 | 0 | 84043.0864 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 42021.5432 | 42021.5432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q11 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q18 Quarry |  | 2000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 25.3838 | 292.5 | 2237.3252 | 803.0357 | 3332.8609 | 0 | 0 | 100% | 0% | 0% | 100% | 3332.8609 | 0 | 0 | 3332.8609 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1666.4304 | 1666.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q13 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q13 Quarry |  | 6350 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 80.5935 | 928.6875 | 7103.5075 | 2549.6383 | 10572.3839 | 0 | 0 | 100% | 0% | 0% | 100% | 10572.3839 | 0 | 0 | 10572.3839 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 5286.1919 | 5286.1919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q14 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q14 Quarry |  | 13440 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 170.5789 | 1965.6 | 15034.8253 | 5396.3998 | 22376.8251 | 0 | 0 | 100% | 0% | 0% | 100% | 22376.8251 | 0 | 0 | 22376.8251 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11188.4126 | 11188.4126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q15 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q15 Quarry |  | 10680 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 135.5493 | 1561.95 | 11947.3165 | 4288.2106 | 17781.5843 | 0 | 0 | 100% | 0% | 0% | 100% | 17781.5843 | 0 | 0 | 17781.5843 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 8890.7921 | 8890.7921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q16A |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q16A Quarry |  | 11240 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 142.6568 | 1643.85 | 12573.7676 | 4513.0606 | 18713.952 | 0 | 0 | 100% | 0% | 0% | 100% | 18713.952 | 0 | 0 | 18713.952 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 9356.976 | 9356.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q19 Quarry |  | 18760 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 238.0997 | 2743.65 | 20986.1103 | 7532.4748 | 31262.235 | 0 | 0 | 100% | 0% | 0% | 100% | 31262.235 | 0 | 0 | 31262.235 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 15631.1175 | 15631.1175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q19 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q9 Quarry |  | 15166 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 192.4851 | 2218.0275 | 16965.6369 | 6089.4196 | 25250.5156 | 0 | 0 | 100% | 0% | 0% | 100% | 25250.5156 | 0 | 0 | 25250.5156 | Type A 2AM-MRY1325 | Removed (2017) | 2016 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 12625.2578 | 12625.2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ2a quarry |  | -345500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -4385.0457 | -50529.375 | -386497.9261 | -138724.4157 | -575751.7169 | 0 | 0 | 100% | 0% | 0% | 100% | -575751.7169 | 0 | 0 | -575751.7169 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -287875.8584 | -287875.8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ2a quarry |  | 345500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 4385.0457 | 50529.375 | 386497.9261 | 138724.4157 | 575751.7169 | 0 | 0 | 100% | 0% | 0% | 100% | 575751.7169 | 0 | 0 | 575751.7169 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 287875.8584 | 287875.8584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ4a quarry |  | -105000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1332.6477 | -15356.25 | -117459.5723 | -42159.3738 | -174975.1962 | 0 | 0 | 100% | 0% | 0% | 100% | -174975.1962 | 0 | 0 | -174975.1962 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -87487.5981 | -87487.5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ4a quarry |  | 105000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1332.6477 | 15356.25 | 117459.5723 | 42159.3738 | 174975.1962 | 0 | 0 | 100% | 0% | 0% | 100% | 174975.1962 | 0 | 0 | 174975.1962 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 87487.5981 | 87487.5981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ6a quarry | 2019-1-E | 194000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2462.2254 | 28372.5 | 217020.5432 | 77894.4621 | 323287.5053 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 323287.5053 | 0 | 323287.5053 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 161643.7526 | 161643.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ6a quarry | 2019-1-E | -194000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -2462.2254 | -28372.5 | -217020.5432 | -77894.4621 | -323287.5053 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -323287.5053 | 0 | -323287.5053 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -161643.7526 | -161643.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ12a quarry |  | -232200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -2947.0553 | -33959.25 | -259753.4543 | -93232.4438 | -386945.1481 | 0 | 0 | 100% | 0% | 0% | 100% | -386945.1481 | 0 | 0 | -386945.1481 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -193472.574 | -193472.574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | PQ12a quarry |  | 232200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2947.0553 | 33959.25 | 259753.4543 | 93232.4438 | 386945.1481 | 0 | 0 | 100% | 0% | 0% | 100% | 386945.1481 | 0 | 0 | 386945.1481 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 193472.574 | 193472.574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry Expansion 2019 |  | -1225587 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -15555.0072 | -179242.0987 | -1371018.3323 | -492095.0521 | -2042355.4831 | 0 | 0 | 100% | 0% | 0% | 100% | -2042355.4831 | 0 | 0 | -2042355.4831 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -1021177.7415 | -1021177.7415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry Expansion 2019 |  | 1225587 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 15555.0072 | 179242.0987 | 1371018.3323 | 492095.0521 | 2042355.4831 | 0 | 0 | 100% | 0% | 0% | 100% | 2042355.4831 | 0 | 0 | 2042355.4831 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1021177.7415 | 1021177.7415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry |  | -15000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -190.3782 | -2193.75 | -16779.9389 | -6022.7677 | -24996.4566 | 0 | 0 | 100% | 0% | 0% | 100% | -24996.4566 | 0 | 0 | -24996.4566 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -12498.2283 | -12498.2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q5 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q5 Quarry |  | 15000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 190.3782 | 2193.75 | 16779.9389 | 6022.7677 | 24996.4566 | 0 | 0 | 100% | 0% | 0% | 100% | 24996.4566 | 0 | 0 | 24996.4566 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 12498.2283 | 12498.2283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry at Q7 |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Q7 Quarry |  | 53050 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 673.3044 | 7758.5625 | 59345.0506 | 21300.5217 | 88404.1348 | 0 | 0 | 100% | 0% | 0% | 100% | 88404.1348 | 0 | 0 | 88404.1348 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 44202.0674 | 44202.0674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Borrow development areas |  | 42080 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 534.0744 | 6154.2 | 47073.3219 | 16895.871 | 70123.3929 | 0 | 0 | 100% | 0% | 0% | 100% | 70123.3929 | 0 | 0 | 70123.3929 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 23374.4643 | 23374.4643 | 23374.4643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3132 | River Crossing at STA 17 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Lot | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 5000 | 5000 | 0% | 100% | 0% | 100% | 0 | 181721.9048 | 0 | 181721.9048 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 60573.9683 | 60573.9683 | 60573.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3133 | River Crossing at STA 62 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Lot | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 5000 | 5000 | 100% | 0% | 0% | 100% | 181721.9048 | 0 | 0 | 181721.9048 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 60573.9683 | 60573.9683 | 60573.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3134 | River Crossing at STA 80 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Lot | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 5000 | 5000 | 100% | 0% | 0% | 100% | 181721.9048 | 0 | 0 | 181721.9048 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 60573.9683 | 60573.9683 | 60573.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3135 | River Crossing at STA 97 |  |  | Br | Bridge Removal | Br | Site Works | Bridge Removal |  | Bridge Removal |  | 1 | Lot | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 761.9048 | 9523.8095 | 67154.2857 | 105043.8095 | 181721.9048 | 5000 | 5000 | 100% | 0% | 0% | 100% | 181721.9048 | 0 | 0 | 181721.9048 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 60573.9683 | 60573.9683 | 60573.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 2019 Quarries (4 x 20m) |  | 80 | m | 0.3478 | 2.1738 | 30.6551 | 23.9756 | 56.8044 | 27.824 | 173.9 | 2452.4074 | 1918.0474 | 4544.3548 | 0 | 0 | 100% | 0% | 0% | 100% | 4544.3548 | 0 | 0 | 4544.3548 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 2272.1774 | 2272.1774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 372 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | 2232 | 13950 | 196728.48 | 153862.92 | 364541.4 | 0 | 0 | 100% | 0% | 0% | 100% | 364541.4 | 0 | 0 | 364541.4 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 182270.7 | 182270.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culvert upgrades - IOL | 2023-4 | 1419 | m | 0.3478 | 2.1738 | 30.6551 | 23.9756 | 56.8044 | 493.5282 | 3084.5512 | 43499.5755 | 34021.3665 | 80605.4933 | 0 | 0 | 100% | 0% | 0% | 100% | 80605.4933 | 0 | 0 | 80605.4933 | Type A 2AM-MRY1325 | added | 2023 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 40302.7466 | 40302.7466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL | 2023-4 | -46 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | -276 | -1725 | -24326.64 | -19026.06 | -45077.7 | 0 | 0 | 100% | 0% | 0% | 100% | -45077.7 | 0 | 0 | -45077.7 | Type A 2AM-MRY1325 | removed | 2023 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | -22538.85 | -22538.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - Crown |  | 11 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | 66 | 412.5 | 5817.24 | 4549.71 | 10779.45 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 10779.45 | 0 | 10779.45 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 5389.725 | 5389.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culvert upgrades - Crown | 2023-4 | 182 | m | 0.3478 | 2.1738 | 30.6551 | 23.9756 | 56.8044 | 63.2996 | 395.6225 | 5579.2267 | 4363.5579 | 10338.4072 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 10338.4072 | 0 | 10338.4072 | Type A 2AM-MRY1325 | added | 2023 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 5169.2036 | 5169.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - Crown | 2023-4 | -6 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | -36 | -225 | -3173.04 | -2481.66 | -5879.7 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -5879.7 | 0 | -5879.7 | Type A 2AM-MRY1325 | removed | 2023 | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | -2939.85 | -2939.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Mobile Maintenance Depot - Demolish floor finish - Slab on grade C/W Drainage |  | 682 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 85.25 | 1278.75 | 7513.935 | 12787.5 | 21580.185 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 21580.185 | 0 | 21580.185 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7193.395 | 7193.395 | 7193.395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Mobile Maintenance Depot -Liner Removal |  | 682 | m2 | 0.0318 | 0.02385 | 2.8029 | 0.28029 | 3.0831 | 21.6876 | 16.2657 | 1911.5451 | 191.1545 | 2102.6996 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 2102.6996 | 0 | 2102.6996 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 700.8999 | 700.8999 | 700.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Mobile Maintenance Depot - Demolish and foundations - Gravel Base - Skidded Building |  | 682 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3131 | Road Upgrade |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Out-of-Service Tote Road |  | 266500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 3382.3869 | 38975.625 | 298123.5812 | 107004.5059 | 443707.1351 | 0 | 0 | 100% | 0% | 0% | 100% | 443707.1351 | 0 | 0 | 443707.1351 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 50% | 50% | [8 empty] | 0 | 0 | 0 | 221853.5676 | 221853.5676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source |  | 157012 | m2 | 0.019038 | 0.21937 | 1.678 | 0.60228 | 2.4974 | 2989.167 | 34444.5075 | 263465.1768 | 94564.68 | 392474.3643 | 0 | 0 | 100% | 0% | 0% | 100% | 392474.3643 | 0 | 0 | 392474.3643 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 196237.1821 | 196237.1821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 0 | m2 | 0.019038 | 0.21937 | 1.678 | 0.60228 | 2.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2017) |  | 1000 | m2 | 0.019038 | 0.21937 | 1.678 | 0.60228 | 2.4974 | 19.0378 | 219.375 | 1677.9939 | 602.2768 | 2499.6457 | 0 | 0 | 100% | 0% | 0% | 100% | 2499.6457 | 0 | 0 | 2499.6457 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1249.8228 | 1249.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | KM 97 Borrow Source (marginal increase in 2018) |  | 1500 | m2 | 0.019038 | 0.21937 | 1.678 | 0.60228 | 2.4974 | 28.5567 | 329.0625 | 2516.9908 | 903.4152 | 3749.4685 | 0 | 0 | 100% | 0% | 0% | 100% | 3749.4685 | 0 | 0 | 3749.4685 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1874.7342 | 1874.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 105359 | m2 | 0.019038 | 0.21937 | 1.678 | 0.60228 | 2.4974 | 2005.8062 | 23113.1306 | 176791.7583 | 63455.2781 | 263124.9909 | 0 | 0 | 100% | 0% | 0% | 100% | 263124.9909 | 0 | 0 | 263124.9909 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 131562.4955 | 131562.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  |  | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  | 697910.1311 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 8857.7939 | 102069.3567 | 780725.9575 | 280223.3724 | 1161980.1309 | 0 | 0 | 100% | 0% | 0% | 100% | 1161980.1309 | 0 | 0 | 1161980.1309 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 580990.0654 | 580990.0654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 565 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 1 - Demolish Building - ISO Shipping Container | 3160-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 568 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 2 - Demolish Building - ISO Shipping Container | 3160-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 571 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 3 - Demolish Building - ISO Shipping Container | 3160-BLD-003 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 574 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Emergency Shelter No. 4 - Demolish Building - ISO Shipping Container | 3160-BLD-004 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 566 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 1 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-001 | 14.8699 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 1.8333 | 14.5833 | 102.83 | 160.8483 | 278.2617 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 278.2617 | 0 | 0 | 278.2617 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 92.7539 | 92.7539 | 92.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 569 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 2 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-002 | 14.8699 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 1.8333 | 14.5833 | 102.83 | 160.8483 | 278.2617 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 278.2617 | 0 | 0 | 278.2617 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 92.7539 | 92.7539 | 92.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 572 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 3 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-003 | 14.8699 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 1.8333 | 14.5833 | 102.83 | 160.8483 | 278.2617 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 278.2617 | 0 | 0 | 278.2617 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 92.7539 | 92.7539 | 92.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 575 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Shelter No. 4 - Demolish and foundations - Timber Cribbing to Elevate Building | 3160-BLD-004 | 14.8699 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 1.8333 | 14.5833 | 102.83 | 160.8483 | 278.2617 | 0.3 | 4.461 | 100% | 0% | 0% | 100% | 278.2617 | 0 | 0 | 278.2617 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 92.7539 | 92.7539 | 92.7539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 567 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 570 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 573 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 3 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-003 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3160 | Emergency Shelters | 3160 | Emergency Shelters | 576 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Shelter No. 4 - Demolish floor finish - Raised Steel or Wooden Floor | 3160-BLD-004 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Emergency Shelters | 3213 | Explosives Magazines |  |  | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings ( Not Contaminated) | Single Trailers (modular) |  | Washrooms at KM26 and KM 80 IT Towers | 2020-14 | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Emergency Shelters | 3213 | Explosives Magazines |  |  | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings ( Not Contaminated) | Single Trailers (modular) |  | Washrooms at KM26 and KM 80 IT Towers | 2020-14 | -72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -16.14 | -201.75 | -1422.5796 | -2225.2218 | -3849.5514 | 1 | -72 | 100% | 0% | 0% | 100% | -3849.5514 | 0 | 0 | -3849.5514 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1283.1838 | -1283.1838 | -1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (31m2 x 2) - Demolish and Decontaminate Building - Trailer |  | 62 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 34.7458 | 173.7292 | 3062.4977 | 4790.408 | 8026.635 | 1 | 62 | 100% | 0% | 0% | 100% | 8026.635 | 0 | 0 | 8026.635 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2675.545 | 2675.545 | 2675.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines (15m2 x 3) - Demolish and Decontaminate Building - Trailer |  | 45 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 25.2188 | 126.0938 | 2222.7806 | 3476.9091 | 5825.7834 | 1 | 45 | 100% | 0% | 0% | 100% | 5825.7834 | 0 | 0 | 5825.7834 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1941.9278 | 1941.9278 | 1941.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (22m2) - Demolish and Decontaminate Building - Trailer |  | 22 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 12.3292 | 61.6458 | 1086.6927 | 1699.8222 | 2848.1608 | 1 | 22 | 100% | 0% | 0% | 100% | 2848.1608 | 0 | 0 | 2848.1608 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 949.3869 | 949.3869 | 949.3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3200 | General | 3210 | Explosives Facility | 3213 | Explosives Magazines |  |  | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazine (12m2) - Demolish and Decontaminate Building - Trailer |  | 12 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 6.725 | 33.625 | 592.7415 | 927.1757 | 1553.5422 | 1 | 12 | 100% | 0% | 0% | 100% | 1553.5422 | 0 | 0 | 1553.5422 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 517.8474 | 517.8474 | 517.8474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site
4000 | Mine Site | 4100 | General
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 579 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 1 - Demolish Building - ISO Shipping Container | 4110-BLD-001 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 582 | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Communication Shed No. 2 - Demolish Building - ISO Shipping Container | 4110-BLD-002 | 14.8699 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 1.6667 | 20.8333 | 146.9 | 229.7833 | 397.5167 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 397.5167 | 0 | 0 | 397.5167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 132.5056 | 132.5056 | 132.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and Decontaminate Building - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish and foundations - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure |  | BLD | [6 empty] | Satellite Dish Sea Can - Demolish floor finish - Undefined | 4110-BLD-003 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 580 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 1 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 581 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 1 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 583 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Communication Shed No. 2 - Demolish and foundations - Gravel Base - Skidded Building | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure | 584 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Communication Shed No. 2 - Demolish floor finish - Raised Steel or Wooden Floor | 4110-BLD-002 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4110 | Site Development | 4136 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour Building Footprints | Grade and Contour | Grade and Re-Contour Building Footprints |  | 223 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2.8303 | 32.6137 | 249.4618 | 89.5385 | 371.614 | 0 | 0 | 100% | 0% | 0% | 100% | 371.614 | 0 | 0 | 371.614 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 123.8713 | 123.8713 | 123.8713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | -15000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Removed | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2A |  | 30150 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 2B |  | 8700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Tote Road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown 1 |  | 5400 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 190.3482 | 2193.75 | 19034.8214 | 5948.1802 | 27176.7516 | 0 | 0 | 100% | 0% | 0% | 100% | 27176.7516 | 0 | 0 | 27176.7516 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9058.9172 | 9058.9172 | 9058.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Warehouse laydown pad expansion | 2020-10 | 3200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 40.614 | 468 | 3579.7203 | 1284.8571 | 5332.5774 | 0 | 0 | 100% | 0% | 0% | 100% | 5332.5774 | 0 | 0 | 5332.5774 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1777.5258 | 1777.5258 | 1777.5258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Warehouse laydown pad expansion | 2020-10 | -3200 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -40.614 | -468 | -3579.7203 | -1284.8571 | -5332.5774 | 0 | 0 | 100% | 0% | 0% | 100% | -5332.5774 | 0 | 0 | -5332.5774 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1777.5258 | -1777.5258 | -1777.5258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction Laydown Area |  | 33576 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 426.1427 | 4910.49 | 37560.2152 | 13481.3632 | 55952.0684 | 0 | 0 | 100% | 0% | 0% | 100% | 55952.0684 | 0 | 0 | 55952.0684 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 18650.6895 | 18650.6895 | 18650.6895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of the area east of the Mine Site workshops and crushing area for improved traffic management | 2021-15 | 37732 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 478.8901 | 5518.305 | 42209.377 | 15150.0714 | 62877.7533 | 0 | 0 | 100% | 0% | 0% | 100% | 62877.7533 | 0 | 0 | 62877.7533 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20959.2511 | 20959.2511 | 20959.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of MSC laydown for vehicle parking | 2021-16 | 5243 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 66.5435 | 766.7887 | 5865.148 | 2105.1581 | 8737.0948 | 0 | 0 | 100% | 0% | 0% | 100% | 8737.0948 | 0 | 0 | 8737.0948 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2912.3649 | 2912.3649 | 2912.3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of MSC laydown for vehicle parking | 2021-16 | -5243 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -66.5435 | -766.7887 | -5865.148 | -2105.1581 | -8737.0948 | 0 | 0 | 100% | 0% | 0% | 100% | -8737.0948 | 0 | 0 | -8737.0948 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2912.3649 | -2912.3649 | -2912.3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of three (3) laydown areas for road aggregate storage on the mine haul road Km 106, Km 107 and Km 108 | 2021-17 | 10705 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 135.8666 | 1565.6062 | 11975.2831 | 4298.2485 | 17839.1379 | 0 | 0 | 100% | 0% | 0% | 100% | 17839.1379 | 0 | 0 | 17839.1379 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5946.3793 | 5946.3793 | 5946.3793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of three (3) laydown areas for road aggregate storage on the mine haul road Km 106, Km 107 and Km 108 | 2021-17 | -10705 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -135.8666 | -1565.6062 | -11975.2831 | -4298.2485 | -17839.1379 | 0 | 0 | 100% | 0% | 0% | 100% | -17839.1379 | 0 | 0 | -17839.1379 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -5946.3793 | -5946.3793 | -5946.3793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of KM 106 stockpile pad to increase road width to accommodate water truck loading area | 2023-2 | 2000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 25.3838 | 292.5 | 2237.3252 | 803.0357 | 3332.8609 | 0 | 0 | 100% | 0% | 0% | 100% | 3332.8609 | 0 | 0 | 3332.8609 | Type A 2AM-MRY1325 | Added | 2023 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1110.9536 | 1110.9536 | 1110.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Explosives plant secondary storage location | 2021-19 | 20000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 253.8377 | 2925 | 22373.2519 | 8030.3569 | 33328.6088 | 0 | 0 | 100% | 0% | 0% | 100% | 33328.6088 | 0 | 0 | 33328.6088 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11109.5363 | 11109.5363 | 11109.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of 800p camp laydown | 2019-16 | 12000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 152.3026 | 1755 | 13423.9511 | 4818.2141 | 19997.1653 | 0 | 0 | 100% | 0% | 0% | 100% | 19997.1653 | 0 | 0 | 19997.1653 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6665.7218 | 6665.7218 | 6665.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion of 800p camp laydown | 2019-16 | -12000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -152.3026 | -1755 | -13423.9511 | -4818.2141 | -19997.1653 | 0 | 0 | 100% | 0% | 0% | 100% | -19997.1653 | 0 | 0 | -19997.1653 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -6665.7218 | -6665.7218 | -6665.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | WRF Water Treatment plant laydown 2019 |  | 3500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 44.4216 | 511.875 | 3915.3191 | 1405.3125 | 5832.5065 | 0 | 0 | 100% | 0% | 0% | 100% | 5832.5065 | 0 | 0 | 5832.5065 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1944.1688 | 1944.1688 | 1944.1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM107.5 Laydown for haul road parking | 2019-12 | 91000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1154.9614 | 13308.75 | 101798.296 | 36538.124 | 151645.17 | 0 | 0 | 100% | 0% | 0% | 100% | 151645.17 | 0 | 0 | 151645.17 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 50548.39 | 50548.39 | 50548.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM107.5 Laydown for haul road parking | 2019-12 | -91000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1154.9614 | -13308.75 | -101798.296 | -36538.124 | -151645.17 | 0 | 0 | 100% | 0% | 0% | 100% | -151645.17 | 0 | 0 | -151645.17 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -50548.39 | -50548.39 | -50548.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM110.5 Laydown for Mine Ops | 2019-13 | 180000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2284.539 | 26325 | 201359.2669 | 72273.2122 | 299957.4791 | 0 | 0 | 100% | 0% | 0% | 100% | 299957.4791 | 0 | 0 | 299957.4791 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 99985.8264 | 99985.8264 | 99985.8264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | KM110.5 Laydown for Mine Ops | 2019-13 | -58689 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -744.8739 | -8583.2662 | -65653.189 | -23564.6809 | -97801.1361 | 0 | 0 | 100% | 0% | 0% | 100% | -97801.1361 | 0 | 0 | -97801.1361 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -32600.3787 | -32600.3787 | -32600.3787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km107 Stockpile and access Road | 2019-23 | 133400 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1693.0972 | 19509.75 | 149229.59 | 53562.4806 | 222301.8206 | 0 | 0 | 100% | 0% | 0% | 100% | 222301.8206 | 0 | 0 | 222301.8206 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 74100.6069 | 74100.6069 | 74100.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Km107 Stockpile and access Road | 2019-23 | -56800 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -720.899 | -8307 | -63540.0353 | -22806.2136 | -94653.249 | 0 | 0 | 100% | 0% | 0% | 100% | -94653.249 | 0 | 0 | -94653.249 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -31551.083 | -31551.083 | -31551.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiling area at KM 105.5 | 2022-2 | 114847 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1457.6247 | 16796.3737 | 128475.0429 | 46113.12 | 191384.5367 | 0 | 0 | 100% | 0% | 0% | 100% | 191384.5367 | 0 | 0 | 191384.5367 | Type A 2AM-MRY1325 | added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 63794.8456 | 63794.8456 | 63794.8456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiling area at KM 105.5 | 2022-2 | -114847 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -1457.6247 | -16796.3737 | -128475.0429 | -46113.12 | -191384.5367 | 0 | 0 | 100% | 0% | 0% | 100% | -191384.5367 | 0 | 0 | -191384.5367 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -63794.8456 | -63794.8456 | -63794.8456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 220.4189 | 2539.912 | 19427.7238 | 6973.1283 | 28940.7641 | 0 | 0 | 100% | 0% | 0% | 100% | 28940.7641 | 0 | 0 | 28940.7641 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9646.9214 | 9646.9214 | 9646.9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Existing Laydown Area |  | 17366.92 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 220.4189 | 2539.912 | 19427.7238 | 6973.1283 | 28940.7641 | 0 | 0 | 100% | 0% | 0% | 100% | 28940.7641 | 0 | 0 | 28940.7641 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9646.9214 | 9646.9214 | 9646.9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad Development (Nuna services) |  | 11400 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 144.6875 | 1667.25 | 12752.7536 | 4577.3034 | 18980.3427 | 0 | 0 | 100% | 0% | 0% | 100% | 18980.3427 | 0 | 0 | 18980.3427 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6326.7809 | 6326.7809 | 6326.7809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Truck Shop (2018) laydown area |  | 25000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 317.2971 | 3656.25 | 27966.5648 | 10037.9461 | 41623.5586 | 0 | 0 | 100% | 0% | 0% | 100% | 41623.5586 | 0 | 0 | 41623.5586 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13874.5195 | 13874.5195 | 13874.5195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional laydown next to Hatch old office/carpentry shack |  | 11250 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 142.7837 | 1645.3125 | 12584.9542 | 4517.0758 | 18730.6014 | 0 | 0 | 100% | 0% | 0% | 100% | 18730.6014 | 0 | 0 | 18730.6014 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6243.5338 | 6243.5338 | 6243.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to KM 105 Equipment Laydown east | 2022-3 | 27509 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 349.141 | 4023.1912 | 30773.2893 | 11045.3544 | 45800.899 | 0 | 0 | 100% | 0% | 0% | 100% | 45800.899 | 0 | 0 | 45800.899 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15266.9663 | 15266.9663 | 15266.9663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to KM 105 Equipment Laydown west | 2022-3 | 36332 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 461.1215 | 5313.555 | 40643.2494 | 14587.9464 | 60490.6853 | 0 | 0 | 100% | 0% | 0% | 100% | 60490.6853 | 0 | 0 | 60490.6853 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20163.5618 | 20163.5618 | 20163.5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to KM 105 Equipment Laydown east | 2022-3 | -27509 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -349.141 | -4023.1912 | -30773.2893 | -11045.3544 | -45800.899 | 0 | 0 | 100% | 0% | 0% | 100% | -45800.899 | 0 | 0 | -45800.899 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -15266.9663 | -15266.9663 | -15266.9663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to KM 105 Equipment Laydown west | 2022-3 | -36332 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -461.1215 | -5313.555 | -40643.2494 | -14587.9464 | -60490.6853 | 0 | 0 | 100% | 0% | 0% | 100% | -60490.6853 | 0 | 0 | -60490.6853 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -20163.5618 | -20163.5618 | -20163.5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | D&B | Drill and Blast | A2 | Site Works | Drill and Blast | Drill and Blast | KM 105 Pond wall | 2022-3 | 60 | m3 | 0.074457 | 0.64331 | 6.5627 | 7.1862 | 13.5382 | 4.4674 | 38.5984 | 393.7593 | 431.1708 | 812.2895 | 0 | 0 | 100% | 0% | 0% | 100% | 812.2895 | 0 | 0 | 812.2895 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 270.7632 | 270.7632 | 270.7632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | MCS - 1 | Excavate, Load & Haul - 1 km | A2 | Site Works | Excavate, Load & Haul - 1 km | Excavate, Load & Haul - 1 km | KM 105 Pond wall | 2022-3 | 58800 | m3 | 0.025932 | 0.30016 | 2.2856 | 2.1245 | 4.3155 | 1524.7845 | 17649.3581 | 134394.5059 | 124919.2292 | 253751.2457 | 0 | 0 | 100% | 0% | 0% | 100% | 253751.2457 | 0 | 0 | 253751.2457 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 84583.7486 | 84583.7486 | 84583.7486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mobile equipment laydown and tire facility | 2022-4 | 14108 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 179.0571 | 2063.295 | 15782.0919 | 5664.6138 | 23489.0066 | 0 | 0 | 100% | 0% | 0% | 100% | 23489.0066 | 0 | 0 | 23489.0066 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7829.6689 | 7829.6689 | 7829.6689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher Pad Expansion |  | 25700 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 326.1814 | 3758.625 | 28749.6287 | 10319.0086 | 42789.0183 | 0 | 0 | 100% | 0% | 0% | 100% | 42789.0183 | 0 | 0 | 42789.0183 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14263.0061 | 14263.0061 | 14263.0061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4133 | Ore Crushing and Loading |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher extension Pad |  | 36180 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 459.1923 | 5291.325 | 40473.2126 | 14526.9157 | 60237.6141 | 0 | 0 | 100% | 0% | 0% | 100% | 60237.6141 | 0 | 0 | 60237.6141 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 20079.2047 | 20079.2047 | 20079.2047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry |  | 258580 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 3281.8672 | 37817.325 | 289263.7735 | 103824.4846 | 430905.5831 | 0 | 0 | 100% | 0% | 0% | 100% | 430905.5831 | 0 | 0 | 430905.5831 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 215452.7915 | 215452.7915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q2 Quarry |  | 109807 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1393.6576 | 16059.2737 | 122836.9834 | 44089.4701 | 182985.7273 | 0 | 0 | 100% | 0% | 0% | 100% | 182985.7273 | 0 | 0 | 182985.7273 | Type A 2AM-MRY1325 | Check | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 91492.8636 | 91492.8636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | D1Q1 Quarry |  | 66978 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 850.077 | 9795.5325 | 74925.7832 | 26892.8623 | 111614.178 | 0 | 0 | 100% | 0% | 0% | 100% | 111614.178 | 0 | 0 | 111614.178 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 55807.089 | 55807.089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (additional marginal increase in 2017) |  | 6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 76.1513 | 877.5 | 6711.9756 | 2409.1071 | 9998.5826 | 0 | 0 | 100% | 0% | 0% | 100% | 9998.5826 | 0 | 0 | 9998.5826 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4999.2913 | 4999.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Laydown Pad development (Mine Site) |  | 45000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 571.1347 | 6581.25 | 50339.8167 | 18068.3031 | 74989.3698 | 0 | 0 | 100% | 0% | 0% | 100% | 74989.3698 | 0 | 0 | 74989.3698 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 37494.6849 | 37494.6849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal increase to existing) |  | 50000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 634.5942 | 7312.5 | 55933.1297 | 20075.8923 | 83321.522 | 0 | 0 | 100% | 0% | 0% | 100% | 83321.522 | 0 | 0 | 83321.522 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 41660.761 | 41660.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -6000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -76.1513 | -877.5 | -6711.9756 | -2409.1071 | -9998.5826 | 0 | 0 | 100% | 0% | 0% | 100% | -9998.5826 | 0 | 0 | -9998.5826 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -4999.2913 | -4999.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4138 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | QMR2 Quarry (marginal decrease, area not used in 2017) |  | -50000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -634.5942 | -7312.5 | -55933.1297 | -20075.8923 | -83321.522 | 0 | 0 | 100% | 0% | 0% | 100% | -83321.522 | 0 | 0 | -83321.522 | Type A 2AM-MRY1325 | Added | 2018-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -41660.761 | -41660.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Quarry Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Informal Construction Laydown at Mary River |  |  | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 80899 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1026.7607 | 11831.4787 | 90498.6852 | 32482.3922 | 134812.5561 | 0 | 0 | 100% | 0% | 0% | 100% | 134812.5561 | 0 | 0 | 134812.5561 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 44937.5187 | 44937.5187 | 44937.5187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Road |  | 20000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 253.8377 | 2925 | 22373.2519 | 8030.3569 | 33328.6088 | 0 | 0 | 100% | 0% | 0% | 100% | 33328.6088 | 0 | 0 | 33328.6088 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11109.5363 | 11109.5363 | 11109.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Site Roads |  | 1120 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 14.2149 | 163.8 | 1252.9021 | 449.7 | 1864.7354 | 0 | 0 | 100% | 0% | 0% | 100% | 1864.7354 | 0 | 0 | 1864.7354 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 621.5785 | 621.5785 | 621.5785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Haul Road Widening and Cross Cut |  | 55900 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 709.4763 | 8175.375 | 62533.239 | 22444.8476 | 93070.2771 | 0 | 0 | 100% | 0% | 0% | 100% | 93070.2771 | 0 | 0 | 93070.2771 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 31023.4257 | 31023.4257 | 31023.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of a West perimeter road to bypass pit | 2022-6 | 74577 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 946.5226 | 10906.8862 | 83426.5003 | 29943.9964 | 124166.4053 | 0 | 0 | 100% | 0% | 0% | 100% | 124166.4053 | 0 | 0 | 124166.4053 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 41388.8018 | 41388.8018 | 41388.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 510 Hillside Road | 2022-6 | 11423 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 144.9794 | 1670.6137 | 12778.4828 | 4586.5384 | 19018.6364 | 0 | 0 | 100% | 0% | 0% | 100% | 19018.6364 | 0 | 0 | 19018.6364 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6339.5455 | 6339.5455 | 6339.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 470 Hillside Road | 2022-6 | 2429 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 30.8286 | 355.2412 | 2717.2314 | 975.2868 | 4044.145 | 0 | 0 | 100% | 0% | 0% | 100% | 4044.145 | 0 | 0 | 4044.145 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1348.0483 | 1348.0483 | 1348.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Bypass road from cross-cut road towards waste dump | 2022-6 | 24534 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 311.3827 | 3588.0975 | 27445.2681 | 9850.8388 | 40847.6955 | 0 | 0 | 100% | 0% | 0% | 100% | 40847.6955 | 0 | 0 | 40847.6955 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13615.8985 | 13615.8985 | 13615.8985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of a West perimeter road to bypass pit | 2022-6 | -74577 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -946.5226 | -10906.8862 | -83426.5003 | -29943.9964 | -124166.4053 | 0 | 0 | 100% | 0% | 0% | 100% | -124166.4053 | 0 | 0 | -124166.4053 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -41388.8018 | -41388.8018 | -41388.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 510 Hillside Road | 2022-6 | -11423 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -144.9794 | -1670.6137 | -12778.4828 | -4586.5384 | -19018.6364 | 0 | 0 | 100% | 0% | 0% | 100% | -19018.6364 | 0 | 0 | -19018.6364 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -6339.5455 | -6339.5455 | -6339.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 470 Hillside Road | 2022-6 | -2429 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -30.8286 | -355.2412 | -2717.2314 | -975.2868 | -4044.145 | 0 | 0 | 100% | 0% | 0% | 100% | -4044.145 | 0 | 0 | -4044.145 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1348.0483 | -1348.0483 | -1348.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Bypass road from cross-cut road towards waste dump | 2022-6 | -24534 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -311.3827 | -3588.0975 | -27445.2681 | -9850.8388 | -40847.6955 | 0 | 0 | 100% | 0% | 0% | 100% | -40847.6955 | 0 | 0 | -40847.6955 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -13615.8985 | -13615.8985 | -13615.8985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for KM107 Stockpile (3 x 75m) |  | 225 | m | 0.3478 | 2.1738 | 30.6551 | 23.9756 | 56.8044 | 78.255 | 489.0938 | 6897.3957 | 5394.5084 | 12780.9979 | 0 | 0 | 100% | 0% | 0% | 100% | 12780.9979 | 0 | 0 | 12780.9979 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4260.3326 | 4260.3326 | 4260.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu-m | Culvert Removal | cu-m | Site Works | Culvert Removal per metre |  | Culverts for 800p camp discharge line (4 x 15m) |  | 60 | m | 0.3478 | 2.1738 | 30.6551 | 23.9756 | 56.8044 | 20.868 | 130.425 | 1839.3055 | 1438.5356 | 3408.2661 | 0 | 0 | 100% | 0% | 0% | 100% | 3408.2661 | 0 | 0 | 3408.2661 | Type A 2AM-MRY1325 | added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1136.0887 | 1136.0887 | 1136.0887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4139 | Site Roads |  |  | Cu | Culvert Removal | cu | Site Works | Culvert Removal |  | Culverts - IOL |  | 14 | Ea | 6 | 37.5 | 528.84 | 413.61 | 979.95 | 84 | 525 | 7403.76 | 5790.54 | 13719.3 | 0 | 0 | 100% | 0% | 0% | 100% | 13719.3 | 0 | 0 | 13719.3 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4573.1 | 4573.1 | 4573.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | Fuel System | 4130 | Site Development | 4616 | Weatherhaven camp |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Lined containment berm and 15,000 L Jet A Tank at the weatherhaven. | 2023-3 | 146 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 6.4958 | 24.8346 | 572.5411 | 99.5432 | 693.2196 | 0 | 0 | 100% | 0% | 0% | 100% | 693.2196 | 0 | 0 | 693.2196 | Type A 2AM-MRY1325 | Added | 2023 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 231.0732 | 231.0732 | 231.0732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | 1650 GAL. VERTICAL STORAGE TANK + BOX PLASTIC FITTINGS |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | 2 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 85.45 | 941.25 | 7531.563 | 10381.611 | 18854.424 | 30 | 60 | 100% | 0% | 0% | 100% | 18854.424 | 0 | 0 | 18854.424 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6284.808 | 6284.808 | 6284.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Gas Tank 50,000L |  | -2 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -85.45 | -941.25 | -7531.563 | -10381.611 | -18854.424 | 30 | -60 | 100% | 0% | 0% | 100% | -18854.424 | 0 | 0 | -18854.424 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -6284.808 | -6284.808 | -6284.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3142.404 | 3142.404 | 3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | 3rd Party Contractor | Diesel Tank 22,500 L |  | -1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -42.725 | -470.625 | -3765.7815 | -5190.8055 | -9427.212 | 30 | -30 | 100% | 0% | 0% | 100% | -9427.212 | 0 | 0 | -9427.212 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3142.404 | -3142.404 | -3142.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | 2 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 20 | 40 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Diesel Tank 10,000L |  | -2 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | -31 | -325 | -2732.34 | -3584.62 | -6641.96 | 20 | -40 | 100% | 0% | 0% | 100% | -6641.96 | 0 | 0 | -6641.96 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -3320.98 | -3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4140 | Mobile Equipment |  | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks | 3rd Party Equipment | Gas Tank 10,000L |  | -1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | -15.5 | -162.5 | -1366.17 | -1792.31 | -3320.98 | 20 | -20 | 100% | 0% | 0% | 100% | -3320.98 | 0 | 0 | -3320.98 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -1660.49 | -1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 777 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single | 4213-BLD-001 | 33.4572 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 18.75 | 93.75 | 1652.625 | 2585.0625 | 4331.4375 | 1 | 33.4572 | 100% | 0% | 0% | 100% | 4331.4375 | 0 | 0 | 4331.4375 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1443.8125 | 1443.8125 | 1443.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 778 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Magazines - Demolish and foundations - Gravel Base - Skidded Building | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4213 | Explosives Magazines | 779 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Magazines - Demolish floor finish - Raised Steel or Wooden Floor | 4213-BLD-001 | 33.4572 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 769 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4211-BLD-001 | 342.0074 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 191.6667 | 958.3333 | 16893.5 | 26425.0833 | 44276.9167 | 1 | 342.0074 | 100% | 0% | 0% | 100% | 44276.9167 | 0 | 0 | 44276.9167 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14758.9722 | 14758.9722 | 14758.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 770 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Plant Building - Demolish and foundations - Gravel Base - Skidded Building | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building | 771 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Explosives Plant Building - Demolish floor finish - Raised Steel or Wooden Floor | 4211-BLD-001 | 342.0074 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4212-BLD-001 | 371.7472 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 208.3333 | 729.1667 | 18362.5 | 28722.9167 | 47814.5833 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 47814.5833 | 0 | 0 | 47814.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15938.1944 | 15938.1944 | 15938.1944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 773 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 130 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 72.8542 | 254.9896 | 6421.3663 | 10044.404 | 16720.7598 | 1 | 130 | 100% | 0% | 0% | 100% | 16720.7598 | 0 | 0 | 16720.7598 | Type A 2AM-MRY1325 |  | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5573.5866 | 5573.5866 | 5573.5866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 775 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Explosives Shop - Demolish floor finish - Slab on grade C/W Drainage | 4212-BLD-001 | 371.7472 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 46.4684 | 697.026 | 4095.7249 | 6970.2602 | 11763.0112 | 0 | 0 | 100% | 0% | 0% | 100% | 11763.0112 | 0 | 0 | 11763.0112 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3921.0037 | 3921.0037 | 3921.0037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4210 | Explosives Facility | 4212 | Explosives Shop | 774 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Explosives Shop - Demolish and foundations - Gravel Base - Skidded Building | 4212-BLD-001 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4220 | Explosives Facility | 4222 | Explosive pad haul road |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Explosive pad haul road |  | 19600 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 248.7609 | 2866.5 | 21925.7868 | 7869.7498 | 32662.0366 | 0 | 0 | 100% | 0% | 0% | 100% | 32662.0366 | 0 | 0 | 32662.0366 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10887.3455 | 10887.3455 | 10887.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Dump |  | 190000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2411.4578 | 27787.5 | 212545.8928 | 76288.3907 | 190000 | 0 | 0 | 100% | 0% | 0% | 100% | 190000 | 0 | 0 | 190000 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 63333.3333 | 63333.3333 | 63333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Facility - Footprint expansion |  | 130000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1649.9448 | 19012.5 | 145426.1372 | 52197.32 | 216635.9571 | 0 | 0 | 100% | 0% | 0% | 100% | 216635.9571 | 0 | 0 | 216635.9571 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 72211.9857 | 72211.9857 | 72211.9857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Waste Rock Facility - Expansion to approved footprint | 2021-18 | 265000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 3363.3491 | 38756.25 | 296445.5873 | 106402.2291 | 441604.0665 | 0 | 0 | 100% | 0% | 0% | 100% | 441604.0665 | 0 | 0 | 441604.0665 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 147201.3555 | 147201.3555 | 147201.3555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Geotube Settling Pond | 2020-4 | 3000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 133.4756 | 510.3 | 11764.5438 | 2045.4091 | 14320.2529 | 0 | 0 | 100% | 0% | 0% | 100% | 14320.2529 | 0 | 0 | 14320.2529 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4773.4176 | 4773.4176 | 4773.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 19000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 845.3458 | 3231.9 | 74508.7773 | 12954.2579 | 90694.9352 | 0 | 0 | 100% | 0% | 0% | 100% | 90694.9352 | 0 | 0 | 90694.9352 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 30231.6451 | 30231.6451 | 30231.6451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4230 | Waste Rock Pond | 4230 | Waste Rock Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Waste Rock Pond |  | 6000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 266.9513 | 1020.6 | 23529.0876 | 4090.8183 | 28640.5058 | 0 | 0 | 100% | 0% | 0% | 100% | 28640.5058 | 0 | 0 | 28640.5058 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9546.8353 | 9546.8353 | 9546.8353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2008 Bulk Sample Pit |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 2008 bulk sample PWSP |  |  | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 |  | 55000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 698.0536 | 8043.75 | 61526.4427 | 22083.4815 | 91653.6742 | 0 | 0 | 100% | 0% | 0% | 100% | 91653.6742 | 0 | 0 | 91653.6742 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 45826.8371 | 45826.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Pit 1 - Marginal increase |  | 214450 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 2721.7744 | 31363.3125 | 239897.1932 | 86105.502 | 357046.8861 | 0 | 0 | 100% | 0% | 0% | 100% | 357046.8861 | 0 | 0 | 357046.8861 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 178523.443 | 178523.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | DC | Drainage Channel | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Deposit 1 -Drainage Channel |  | 600 | m3 | 0.074457 | 0.64331 | 6.5627 | 7.1862 | 13.5382 | 44.6743 | 385.9841 | 3937.5934 | 4311.7075 | 8122.8949 | 0 | 0 | 100% | 0% | 0% | 100% | 8122.8949 | 0 | 0 | 8122.8949 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4061.4474 | 4061.4474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | New PWSP 2019 |  | 4180 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 185.9761 | 711.018 | 16391.931 | 2849.9367 | 19846.9725 | 0 | 0 | 100% | 0% | 0% | 100% | 19846.9725 | 0 | 0 | 19846.9725 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 19846.9725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-2 | 6967 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 309.975 | 1185.0867 | 27321.1922 | 4750.1218 | 33079.8702 | 0 | 0 | 100% | 0% | 0% | 100% | 33079.8702 | 0 | 0 | 33079.8702 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 33079.8702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-3 | 6511 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 289.6867 | 1107.5211 | 25532.9815 | 4439.2196 | 30914.7459 | 0 | 0 | 100% | 0% | 0% | 100% | 30914.7459 | 0 | 0 | 30914.7459 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 30914.7459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | PWSP | PWSP-1 | 3720 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 165.5098 | 632.772 | 14588.0343 | 2536.3073 | 17662.8559 | 0 | 0 | 100% | 0% | 0% | 100% | 17662.8559 | 0 | 0 | 17662.8559 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 17662.8559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 789 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 44.6097 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 10 | 125 | 881.4 | 1378.7 | 2385.1 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2385.1 | 0 | 0 | 2385.1 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 795.0333 | 795.0333 | 795.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 786 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Pit Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4281-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 60 | 750 | 5288.4 | 8272.2 | 14310.6 | 1 | 267.658 | 100% | 0% | 0% | 100% | 14310.6 | 0 | 0 | 14310.6 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4770.2 | 4770.2 | 4770.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 787 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 33 | 262.5 | 1850.94 | 2895.27 | 5008.71 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5008.71 | 0 | 0 | 5008.71 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1669.57 | 1669.57 | 1669.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 790 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Pit Office Washcar - Demolish and foundations - Gravel Base - Skidded Building | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 791 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 788 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Lunchroom Building - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Lunchroom Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-002 | 0 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Lunchroom Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-001 | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-002 | 54 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 12.105 | 151.3125 | 1066.9347 | 1668.9163 | 2887.1635 | 1 | 54 | 100% | 0% | 0% | 100% | 2887.1635 | 0 | 0 | 2887.1635 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 962.3878 | 962.3878 | 962.3878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-003 | 36 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.07 | 100.875 | 711.2898 | 1112.6109 | 1924.7757 | 1 | 36 | 100% | 0% | 0% | 100% | 1924.7757 | 0 | 0 | 1924.7757 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.5919 | 641.5919 | 641.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Geology ‘core’ building - Demolish and Decontaminate Building - Trailer - Single | 4000-BLD-GEO-004 | 25 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 5.6042 | 70.0521 | 493.9512 | 772.6465 | 1336.6498 | 1 | 25 | 100% | 0% | 0% | 100% | 1336.6498 | 0 | 0 | 1336.6498 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 445.5499 | 445.5499 | 445.5499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-004 | 25 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-003 | 36 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-002 | 54 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Geology ‘core’ building - Demolish and foundations - Gravel Base - Skidded Building | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Geology ‘core’ building - Demolish floor finish - Raised Steel or Wooden Floor | 4000-BLD-GEO-001 | 72 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Crusher Pad Expansion 2019 |  | 12000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 152.3026 | 1755 | 13423.9511 | 4818.2141 | 19997.1653 | 0 | 0 | 100% | 0% | 0% | 100% | 19997.1653 | 0 | 0 | 19997.1653 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6665.7218 | 6665.7218 | 6665.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore crushing and Loading Pad, Utility & Accommodation Pads |  | 121021 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1535.9844 | 17699.3212 | 135381.6658 | 48592.0912 | 201673.0782 | 0 | 0 | 100% | 0% | 0% | 100% | 201673.0782 | 0 | 0 | 201673.0782 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 67224.3594 | 67224.3594 | 67224.3594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Ore Stockpiles |  | 5100.23 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 64.7315 | 745.9086 | 5705.4365 | 2047.8334 | 8499.1785 | 0 | 0 | 100% | 0% | 0% | 100% | 8499.1785 | 0 | 0 | 8499.1785 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2833.0595 | 2833.0595 | 2833.0595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 795 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-001 | 39.4052 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 22.0833 | 110.4167 | 1946.425 | 3044.6292 | 5101.4708 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 5101.4708 | 0 | 0 | 5101.4708 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1700.4903 | 1700.4903 | 1700.4903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 798 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4381-BLD-002 | 39.4052 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 22.0833 | 110.4167 | 1946.425 | 3044.6292 | 5101.4708 | 1 | 39.4052 | 100% | 0% | 0% | 100% | 5101.4708 | 0 | 0 | 5101.4708 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1700.4903 | 1700.4903 | 1700.4903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 796 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 797 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-001 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 799 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening Electrical Trailer - Demolish and foundations - Gravel Base - Skidded Building | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 800 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening Electrical Trailer - Demolish floor finish - Raised Steel or Wooden Floor | 4381-BLD-002 | 39.4052 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 828 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Stockpile Drain Pipe - Piping Installation - Ore stockpile to effluent pond and Mary River | 4385.1-P | 5220 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 1305 | 16312.5 | 115022.7 | 179920.35 | 311255.55 | 0.01 | 52.2 | 100% | 0% | 100% | 0% | 311255.55 | 0 | 311255.55 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 103751.85 | 103751.85 | 103751.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Mine Haul Road Sedimentation Pond | 2020-6 | 10000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 444.9188 | 1701 | 39215.1459 | 6818.0305 | 47734.1764 | 0 | 0 | 100% | 0% | 0% | 100% | 47734.1764 | 0 | 0 | 47734.1764 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15911.3921 | 15911.3921 | 15911.3921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | KM107 Sedimentation Pond | 2019-23 | 7400 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 329.2399 | 1258.74 | 29019.208 | 5045.3425 | 35323.2905 | 0 | 0 | 100% | 0% | 0% | 100% | 35323.2905 | 0 | 0 | 35323.2905 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11774.4302 | 11774.4302 | 11774.4302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3 | Grade & Re-Contour | A3 | Site Works | Grade and Re-Contour |  | KM107 Sedimentation Pond | 2019-23 | 10600 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 134.534 | 1550.25 | 11857.8235 | 4256.0892 | 17664.1627 | 0 | 0 | 100% | 0% | 0% | 100% | 17664.1627 | 0 | 0 | 17664.1627 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5888.0542 | 5888.0542 | 5888.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Crusher Pad Sedimentation Pond 2019 |  | 2000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 88.9838 | 340.2 | 7843.0292 | 1363.6061 | 9546.8353 | 0 | 0 | 100% | 0% | 0% | 100% | 9546.8353 | 0 | 0 | 9546.8353 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3182.2784 | 3182.2784 | 3182.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Ore Crushing Sedimentation Pond |  | 6428.69 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 286.0245 | 1093.5202 | 25210.2017 | 4383.1004 | 30686.8222 | 0 | 0 | 100% | 0% | 0% | 100% | 30686.8222 | 0 | 0 | 30686.8222 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10228.9407 | 10228.9407 | 10228.9407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to the sedimentation pond at KM 105 to manage surface water runoff | 2022-7 | 19238 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 244.1665 | 2813.5575 | 21520.831 | 7724.4003 | 32058.7888 | 0 | 0 | 100% | 0% | 0% | 100% | 32058.7888 | 0 | 0 | 32058.7888 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10686.2629 | 10686.2629 | 10686.2629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Expansion to the sedimentation pond at KM 105 to manage surface water runoff | 2022-7 | 6687 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 297.5172 | 1137.4587 | 26223.1681 | 4559.217 | 31919.8438 | 0 | 0 | 100% | 0% | 0% | 100% | 31919.8438 | 0 | 0 | 31919.8438 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10639.9479 | 10639.9479 | 10639.9479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Construction of new Sedimentation Pond SDLT-1 | 2022-12 | 58324 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 740.2414 | 8529.885 | 65244.8771 | 23418.1268 | 97192.889 | 0 | 0 | 100% | 0% | 0% | 100% | 97192.889 | 0 | 0 | 97192.889 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 32397.6297 | 32397.6297 | 32397.6297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Construction of new Sedimentation Pond SDLT-1 | 2022-12 | 20678 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 920.0032 | 3517.3278 | 81089.0788 | 14098.3234 | 98704.73 | 0 | 0 | 100% | 0% | 0% | 100% | 98704.73 | 0 | 0 | 98704.73 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 32901.5767 | 32901.5767 | 32901.5767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Construction of new Sedimentation Pond Camp Lake | 2022-20 | 10000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 444.9188 | 1701 | 39215.1459 | 6818.0305 | 47734.1764 | 0 | 0 | 100% | 0% | 0% | 100% | 47734.1764 | 0 | 0 | 47734.1764 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 15911.3921 | 15911.3921 | 15911.3921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 827 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Stockpile Drain Pipe - Heat Trace Installation - Ore stockpile to effluent pond and Mary River | 4385.1-E | 2610 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 820 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4382-BLD-001 | 334.5725 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 187.5 | 656.25 | 16526.25 | 25850.625 | 43033.125 | 1 | 334.5725 | 100% | 0% | 0% | 100% | 43033.125 | 0 | 0 | 43033.125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14344.375 | 14344.375 | 14344.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 821 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Weigh Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4382-BLD-001 | 334.5725 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 48.582 | 607.2755 | 4282.0209 | 6698.0056 | 11587.302 | 0.75 | 250.9294 | 100% | 0% | 0% | 100% | 11587.302 | 0 | 0 | 11587.302 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3862.434 | 3862.434 | 3862.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 822 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Weigh Building - Demolish floor finish - Gravel | 4382-BLD-001 | 334.5725 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Truck Weigh Facility disturbed area |  | 13000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 164.9945 | 1901.25 | 14542.6137 | 5219.732 | 21663.5957 | 0 | 0 | 100% | 0% | 0% | 100% | 21663.5957 | 0 | 0 | 21663.5957 | Type A 2AM-MRY1325 | Check | 2015 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 21663.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Heli Pad |  | 5776 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 73.3083 | 844.74 | 6461.3951 | 2319.1671 | 9625.3022 | 0 | 0 | 100% | 0% | 0% | 100% | 9625.3022 | 0 | 0 | 9625.3022 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3208.4341 | 3208.4341 | 3208.4341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 839 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4431-TK-004 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 833 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 4431-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 838 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4431-TK-001 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 834 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4431-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 835 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 4431-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | [6 empty] | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4432-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Aerodrome Equipment Building - Demolish and Decontaminate Building - Undefined | 4521-BLD-003 | 1296 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 726.3 | 2542.05 | 64016.082 | 100134.981 | 166693.113 | 1 | 1296 | 100% | 0% | 0% | 100% | 166693.113 | 0 | 0 | 166693.113 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 55564.371 | 55564.371 | 55564.371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Aerodrome Equipment Building - Demolish and foundations - Undefined | 4521-BLD-003 | 1296 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 188.1874 | 2352.3423 | 16586.8361 | 25945.3947 | 44884.573 | 0.75 | 972 | 100% | 0% | 0% | 100% | 44884.573 | 0 | 0 | 44884.573 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14961.5243 | 14961.5243 | 14961.5243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Aerodrome Equipment Building - Demolish floor finish - Undefined | 4521-BLD-003 | 1296 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 162 | 2430 | 14278.68 | 24300 | 41008.68 | 0 | 0 | 100% | 0% | 0% | 100% | 41008.68 | 0 | 0 | 41008.68 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 13669.56 | 13669.56 | 13669.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 850 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4435-BLD-001 | 14.8699 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 8.3333 | 41.6667 | 734.5 | 1148.9167 | 1925.0833 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1925.0833 | 0 | 0 | 1925.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.6944 | 641.6944 | 641.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 851 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Field Electrical Centre - Demolish and foundations - Gravel Base - Skidded Building | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4435 | Field Electrical Centre | 852 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Field Electrical Centre - Demolish floor finish - Raised Steel or Wooden Floor | 4435-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 899 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AA - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-001 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 902 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AB - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-002 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 905 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AC - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-003 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 908 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AD - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-004 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 911 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-005 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 914 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-006 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 917 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-007 | 611.803 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 137.1458 | 1714.3229 | 12088.0337 | 18908.296 | 32710.6527 | 1 | 611.803 | 100% | 0% | 0% | 100% | 32710.6527 | 0 | 0 | 32710.6527 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10903.5509 | 10903.5509 | 10903.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 900 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AA - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 901 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AA - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-001 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 903 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AB - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 904 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AB - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-002 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 906 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AC - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 907 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AC - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-003 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 909 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AD - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 910 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AD - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-004 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 912 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AE - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 913 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AE - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-005 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 915 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AF - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 916 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AF - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-006 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 918 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AG - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 919 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AG - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-007 | 611.803 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AH - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AH - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AI - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-009 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AI - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AI - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AJ - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AJ - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AJ - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AK - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AK - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AK - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AL - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-012 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AL - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AL - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-012 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AM - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-013 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Wing AM - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AM - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-013 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – West side |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – East Side |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Quonset hut |  | 100 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 22.4167 | 280.2083 | 1975.805 | 3090.5858 | 5346.5992 | 1 | 100 | 100% | 0% | 0% | 100% | 5346.5992 | 0 | 0 | 5346.5992 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1782.1997 | 1782.1997 | 1782.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at Milne Port Firehall | 2021-5 | 100 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 22.4167 | 280.2083 | 1975.805 | 3090.5858 | 5346.5992 | 1 | 100 | 100% | 0% | 0% | 100% | 5346.5992 | 0 | 0 | 5346.5992 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1782.1997 | 1782.1997 | 1782.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at the Aerodrome | 2021-5 | 100 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 22.4167 | 280.2083 | 1975.805 | 3090.5858 | 5346.5992 | 1 | 100 | 100% | 0% | 0% | 100% | 5346.5992 | 0 | 0 | 5346.5992 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1782.1997 | 1782.1997 | 1782.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at Milne Port Firehall | 2021-5 | -100 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -22.4167 | -280.2083 | -1975.805 | -3090.5858 | -5346.5992 | 1 | -100 | 100% | 0% | 0% | 100% | -5346.5992 | 0 | 0 | -5346.5992 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1782.1997 | -1782.1997 | -1782.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quonset hut structure at the Aerodrome | 2021-5 | -100 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -22.4167 | -280.2083 | -1975.805 | -3090.5858 | -5346.5992 | 1 | -100 | 100% | 0% | 0% | 100% | -5346.5992 | 0 | 0 | -5346.5992 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1782.1997 | -1782.1997 | -1782.1997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC lunch |  | 36 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.07 | 100.875 | 711.2898 | 1112.6109 | 1924.7757 | 1 | 36 | 100% | 0% | 0% | 100% | 1924.7757 | 0 | 0 | 1924.7757 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.5919 | 641.5919 | 641.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | EBC office |  | 36 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.07 | 100.875 | 711.2898 | 1112.6109 | 1924.7757 | 1 | 36 | 100% | 0% | 0% | 100% | 1924.7757 | 0 | 0 | 1924.7757 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.5919 | 641.5919 | 641.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) |  | Construction of new offices and trailers at the OHT Laydown, and expansion of the OHT laydown |  | 400 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 89.6667 | 1120.8333 | 7903.22 | 12362.3433 | 21386.3967 | 1 | 400 | 100% | 0% | 0% | 100% | 21386.3967 | 0 | 0 | 21386.3967 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7128.7989 | 7128.7989 | 7128.7989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Rail Operations offices |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (60 x 60) |  | 334 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 74.8717 | 935.8958 | 6599.1887 | 10322.5567 | 17857.6412 | 1 | 334 | 100% | 0% | 0% | 100% | 17857.6412 | 0 | 0 | 17857.6412 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5952.5471 | 5952.5471 | 5952.5471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (24 x 60) |  | 132 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 29.59 | 369.875 | 2608.0626 | 4079.5733 | 7057.5109 | 1 | 132 | 100% | 0% | 0% | 100% | 7057.5109 | 0 | 0 | 7057.5109 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2352.5036 | 2352.5036 | 2352.5036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Office Trailer (12 x 60) |  | 66 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 14.795 | 184.9375 | 1304.0313 | 2039.7867 | 3528.7554 | 1 | 66 | 100% | 0% | 0% | 100% | 3528.7554 | 0 | 0 | 3528.7554 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1176.2518 | 1176.2518 | 1176.2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Lunchtrailer (44 x 10) |  | 40 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.9667 | 112.0833 | 790.322 | 1236.2343 | 2138.6397 | 1 | 40 | 100% | 0% | 0% | 100% | 2138.6397 | 0 | 0 | 2138.6397 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 712.8799 | 712.8799 | 712.8799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container w lunchroom |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Single Trailers (modular) | 3rd Party Contractor | Container Office |  | 144 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 32.28 | 403.5 | 2845.1592 | 4450.4436 | 7699.1028 | 1 | 144 | 100% | 0% | 0% | 100% | 7699.1028 | 0 | 0 | 7699.1028 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2566.3676 | 2566.3676 | 2566.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Construction offices, lunchrooms, washcars (assume 50 units @ 36 m2 per wash car) |  | 1218 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 682.5875 | 3412.9375 | 60163.2622 | 94108.3386 | 157684.5384 | 1 | 1218 | 100% | 0% | 0% | 100% | 157684.5384 | 0 | 0 | 157684.5384 | Type B Construction 2BC-MRY1416 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 52561.5128 | 52561.5128 | 52561.5128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Construction offices, lunchrooms, washcars (assume 6 units @ 36 m2 per wash car) |  | 216 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 48.42 | 605.25 | 4267.7388 | 6675.6654 | 11548.6542 | 1 | 216 | 100% | 0% | 0% | 100% | 11548.6542 | 0 | 0 | 11548.6542 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3849.5514 | 3849.5514 | 3849.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 50 person camp at Mine Site |  | 50 | Bed space | 0 | 700.8009 | 0 | 0 | 790.3008 | 0 | 35040.0455 | 0 | 0 | 35040.0455 | 0 | 0 | 100% | 0% | 0% | 100% | 35040.0455 | 0 | 0 | 35040.0455 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 35040.0455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 50- Person Rapid Deploy Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 170.3667 | 2129.5833 | 15016.118 | 23488.4523 | 40634.1537 | 0.5 | 475 | 100% | 0% | 0% | 100% | 40634.1537 | 0 | 0 | 40634.1537 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 40634.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | 35- Person 'Norse-man Style' Camp (assume same footprint as former Shanco Trailer Camp) |  | 950 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 170.3667 | 2129.5833 | 15016.118 | 23488.4523 | 40634.1537 | 0.5 | 475 | 100% | 0% | 0% | 100% | 40634.1537 | 0 | 0 | 40634.1537 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 40634.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | CON | Consumables | CON |  | Consumables |  | Addition of 800 person camp at Mine Site |  | 800 | Bed space | 0 | 700.8009 | 0 | 0 | 790.3008 | 0 | 560640.7273 | 0 | 0 | 560640.7273 | 0 | 0 | 100% | 0% | 0% | 100% | 560640.7273 | 0 | 0 | 560640.7273 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  |  | 100% | [8 empty] | 0 | 0 | 0 | 0 | 560640.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 924 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4513-BLD-002 | 278.8104 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 43.75 | 546.875 | 3856.125 | 6031.8125 | 10434.8125 | 1 | 278.8104 | 100% | 0% | 0% | 100% | 10434.8125 | 0 | 0 | 10434.8125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3478.2708 | 3478.2708 | 3478.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 925 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Emergency Response Garage - Demolish and foundations - Precast Footing (Perimeter Beam) | 4513-BLD-002 | 278.8104 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 40.485 | 506.0629 | 3568.3507 | 5581.6714 | 9656.085 | 0.75 | 209.1078 | 100% | 0% | 0% | 100% | 9656.085 | 0 | 0 | 9656.085 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3218.695 | 3218.695 | 3218.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 926 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Emergency Response Garage - Demolish floor finish - Slab on grade C/W Drainage | 4513-BLD-002 | 278.8104 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 34.8513 | 522.7695 | 3071.7937 | 5227.6952 | 8822.2584 | 0 | 0 | 100% | 0% | 0% | 100% | 8822.2584 | 0 | 0 | 8822.2584 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2940.7528 | 2940.7528 | 2940.7528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 937 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4513-TK-004 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 921 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4513-BLD-001 | 89.2193 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 20 | 250 | 1762.8 | 2757.4 | 4770.2 | 1 | 89.2193 | 100% | 0% | 0% | 100% | 4770.2 | 0 | 0 | 4770.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1590.0667 | 1590.0667 | 1590.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 939 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK - DTE ULC601-07 | 4513-TK-023 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 938 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 4513-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Enhancement of training grounds for the Emergency Response Team with fire retardent infrastructure and secondary spill containment | 2022-17 | 59.4579 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 6.6642 | 83.303 | 587.3863 | 918.799 | 1589.4883 | 1 | 59.4579 | 100% | 0% | 0% | 100% | 1589.4883 | 0 | 0 | 1589.4883 | Type B Construction 2BC-MRY1416 | Addedd | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 529.8294 | 529.8294 | 529.8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Enhancement of training grounds for the Emergency Response Team with fire retardent infrastructure and secondary spill containment | 2022-17 | -59.4579 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -6.6642 | -83.303 | -587.3863 | -918.799 | -1589.4883 | 1 | -59.4579 | 100% | 0% | 0% | 100% | -1589.4883 | 0 | 0 | -1589.4883 | Type B Construction 2BC-MRY1416 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -529.8294 | -529.8294 | -529.8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 922 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Emergency Response Office - Demolish and foundations - Timber Cribbing to Elevate Building | 4513-BLD-001 | 89.2193 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 11 | 87.5 | 616.98 | 965.09 | 1669.57 | 0.3 | 26.7658 | 100% | 0% | 0% | 100% | 1669.57 | 0 | 0 | 1669.57 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 556.5233 | 556.5233 | 556.5233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 923 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Emergency Response Office - Demolish floor finish - Raised Steel or Wooden Floor | 4513-BLD-001 | 89.2193 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Construction of a new COVID-19 PCR testing lab building at the Mine Site | 2022-14 | 53.5121 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 5.9978 | 74.9727 | 528.6477 | 826.9191 | 1430.5395 | 1 | 53.5121 | 100% | 0% | 0% | 100% | 1430.5395 | 0 | 0 | 1430.5395 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 476.8465 | 476.8465 | 476.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Construction of a new COVID-19 PCR testing lab building at the Mine Site | 2022-14 | -53.5121 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -5.9978 | -74.9727 | -528.6477 | -826.9191 | -1430.5395 | 1 | -53.5121 | 100% | 0% | 0% | 100% | -1430.5395 | 0 | 0 | -1430.5395 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -476.8465 | -476.8465 | -476.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 859 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 1856.8773 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 416.25 | 5203.125 | 36688.275 | 57388.3875 | 99279.7875 | 1 | 1856.8773 | 100% | 0% | 0% | 100% | 99279.7875 | 0 | 0 | 99279.7875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33093.2625 | 33093.2625 | 33093.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 862 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-002 | 607.8067 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 136.25 | 1703.125 | 12009.075 | 18784.7875 | 32496.9875 | 1 | 607.8067 | 100% | 0% | 0% | 100% | 32496.9875 | 0 | 0 | 32496.9875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10832.3292 | 10832.3292 | 10832.3292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 865 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-003 | 423.7918 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 95 | 1187.5 | 8373.3 | 13097.65 | 22658.45 | 1 | 423.7918 | 100% | 0% | 0% | 100% | 22658.45 | 0 | 0 | 22658.45 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7552.8167 | 7552.8167 | 7552.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 868 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Laboratory - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-004 | 312.2677 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 70 | 875 | 6169.8 | 9650.9 | 16695.7 | 1 | 312.2677 | 100% | 0% | 0% | 100% | 16695.7 | 0 | 0 | 16695.7 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5565.2333 | 5565.2333 | 5565.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 869 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laboratory - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 870 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laboratory - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-004 | 312.2677 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 866 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Laundry - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 867 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Laundry - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-003 | 423.7918 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 863 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Office - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 864 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Office - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-002 | 607.8067 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 860 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 861 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 1856.8773 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-005 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-005 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-006 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 4333 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 629.179 | 7864.737 | 55455.8338 | 86744.9036 | 150065.4745 | 0.75 | 3249.75 | 100% | 0% | 0% | 100% | 150065.4745 | 0 | 0 | 150065.4745 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 50021.8248 | 50021.8248 | 50021.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Sailivik (800p) Camp Mine Dry facility | 2020-2 | 1200 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 269 | 3362.5 | 23709.66 | 37087.03 | 64159.19 | 1 | 1200 | 100% | 0% | 0% | 100% | 64159.19 | 0 | 0 | 64159.19 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 21386.3967 | 21386.3967 | 21386.3967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Sailivik (800p) Camp Mine Dry facility | 2020-2 | -1200 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -269 | -3362.5 | -23709.66 | -37087.03 | -64159.19 | 1 | -1200 | 100% | 0% | 0% | 100% | -64159.19 | 0 | 0 | -64159.19 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -21386.3967 | -21386.3967 | -21386.3967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Addition of offices/trailers/buildings at the 800p Camp, including a new fire hall and emergency response building. | 2019-17 | 925 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 207.3542 | 2591.9271 | 18276.1962 | 28587.919 | 49456.0423 | 1 | 925 | 100% | 0% | 0% | 100% | 49456.0423 | 0 | 0 | 49456.0423 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16485.3474 | 16485.3474 | 16485.3474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Addition of offices/trailers/buildings at the 800p Camp, including a new fire hall and emergency response building. | 2019-17 | -925 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | -207.3542 | -2591.9271 | -18276.1962 | -28587.919 | -49456.0423 | 1 | -925 | 100% | 0% | 0% | 100% | -49456.0423 | 0 | 0 | -49456.0423 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -16485.3474 | -16485.3474 | -16485.3474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | 800 man temporary hard-walled camp at Mine Site inclusive of kitchen, dining, locker, recreational and washroom (assume footprint of 13,000 m2) |  | 13000 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 2914.1667 | 36427.0833 | 256854.65 | 401776.1583 | 695057.8917 | 1 | 13000 | 100% | 0% | 0% | 100% | 695057.8917 | 0 | 0 | 695057.8917 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 231685.9639 | 231685.9639 | 231685.9639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 975 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 4521-TK-053 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washroom facility for Tote Road |  | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar |  | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Washcar |  | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) | Small Building | Washcar (bathroom) | E-10 | 36 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20.175 | 100.875 | 1778.2245 | 2781.5273 | 4660.6268 | 1 | 36 | 100% | 0% | 0% | 100% | 4660.6268 | 0 | 0 | 4660.6268 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1553.5422 | 1553.5422 | 1553.5422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 954 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-005 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 942 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-001 | 2416.3569 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 1354.1667 | 4739.5833 | 119356.25 | 186698.9583 | 310794.7917 | 1 | 2416.3569 | 100% | 0% | 0% | 100% | 310794.7917 | 0 | 0 | 310794.7917 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 103598.2639 | 103598.2639 | 103598.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 945 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-002 | 892.1933 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 500 | 1750 | 44070 | 68935 | 114755 | 1 | 892.1933 | 100% | 0% | 0% | 100% | 114755 | 0 | 0 | 114755 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 38251.6667 | 38251.6667 | 38251.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 943 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-001 | 2416.3569 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 350.8703 | 4385.8785 | 30925.7063 | 48374.4852 | 83686.07 | 0.75 | 1812.2677 | 100% | 0% | 0% | 100% | 83686.07 | 0 | 0 | 83686.07 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 27895.3567 | 27895.3567 | 27895.3567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 944 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-001 | 2416.3569 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 302.0446 | 4530.6691 | 26622.2119 | 45306.6914 | 76459.5725 | 0 | 0 | 100% | 0% | 0% | 100% | 76459.5725 | 0 | 0 | 76459.5725 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25486.5242 | 25486.5242 | 25486.5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 948 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-003 | 390.3346 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 218.75 | 765.625 | 19280.625 | 30159.0625 | 50205.3125 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 50205.3125 | 0 | 0 | 50205.3125 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 16735.1042 | 16735.1042 | 16735.1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Crusher Dry Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Environment Trailers (2 x 36m2) |  | 72 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 16.14 | 201.75 | 1422.5796 | 2225.2218 | 3849.5514 | 1 | 72 | 100% | 0% | 0% | 100% | 3849.5514 | 0 | 0 | 3849.5514 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.1838 | 1283.1838 | 1283.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Lunchroom |  | 36 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.07 | 100.875 | 711.2898 | 1112.6109 | 1924.7757 | 1 | 36 | 100% | 0% | 0% | 100% | 1924.7757 | 0 | 0 | 1924.7757 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.5919 | 641.5919 | 641.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-004 | 267.658 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 150 | 750 | 13221 | 20680.5 | 34651.5 | 1 | 267.658 | 100% | 0% | 0% | 100% | 34651.5 | 0 | 0 | 34651.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11550.5 | 11550.5 | 11550.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 946 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-002 | 892.1933 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 129.5521 | 1619.4013 | 11418.7223 | 17861.3484 | 30899.472 | 0.75 | 669.145 | 100% | 0% | 0% | 100% | 30899.472 | 0 | 0 | 30899.472 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10299.824 | 10299.824 | 10299.824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 947 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Warehouse - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-002 | 892.1933 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 111.5242 | 1672.8625 | 9829.7398 | 16728.6245 | 28231.2268 | 0 | 0 | 100% | 0% | 0% | 100% | 28231.2268 | 0 | 0 | 28231.2268 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 9410.4089 | 9410.4089 | 9410.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 0 | Services Area |  | Waste Rock Facility |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Trasfer line for Deposit 1 to Waste Rock Facility |  | 3500 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 875 | 10937.5 | 77122.5 | 120636.25 | 208696.25 | 0.01 | 35 | 100% | 0% | 0% | 100% | 208696.25 | 0 | 0 | 208696.25 | Type A 2AM-MRY1325 | added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 69565.4167 | 69565.4167 | 69565.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 2020 | Services Area |  | Bulk Fuel Storage |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Fuel Line from new (2019) bulk fuel storage facility to existing bulk fuel storage facility | 2020-1 | 250 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 62.5 | 781.25 | 5508.75 | 8616.875 | 14906.875 | 0.01 | 2.5 | 100% | 0% | 0% | 100% | 14906.875 | 0 | 0 | 14906.875 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4968.9583 | 4968.9583 | 4968.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 2020 | Services Area |  | Bulk Fuel Storage |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Fuel Line from new (2019) bulk fuel storage facility to existing bulk fuel storage facility | 2020-1 | -250 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | -62.5 | -781.25 | -5508.75 | -8616.875 | -14906.875 | 0.01 | -2.5 | 100% | 0% | 0% | 100% | -14906.875 | 0 | 0 | -14906.875 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -4968.9583 | -4968.9583 | -4968.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 976 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Maintenance Building Utility Piping - Piping Installation - Water, air and lube piping inside building | 4521.5-P | 405 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 101.25 | 1265.625 | 8924.175 | 13959.3375 | 24149.1375 | 0.01 | 4.05 | 100% | 0% | 100% | 0% | 24149.1375 | 0 | 24149.1375 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 8049.7125 | 8049.7125 | 8049.7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 949 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-003 | 390.3346 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 56.679 | 708.4881 | 4995.691 | 7814.3399 | 13518.519 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 13518.519 | 0 | 0 | 13518.519 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4506.173 | 4506.173 | 4506.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 950 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-003 | 390.3346 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 48.7918 | 731.8773 | 4300.5112 | 7318.7732 | 12351.1617 | 0 | 0 | 100% | 0% | 0% | 100% | 12351.1617 | 0 | 0 | 12351.1617 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4117.0539 | 4117.0539 | 4117.0539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 974 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 4521-TK-050 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 955 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-005 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 952 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-004 | 267.658 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 33 | 262.5 | 1850.94 | 2895.27 | 5008.71 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5008.71 | 0 | 0 | 5008.71 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1669.57 | 1669.57 | 1669.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 971 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WELDING SHOP DIESEL FUEL TANK - DTE ULC601-07 | 4521-TK-005 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 972 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MAINTENANCE BUILDING DIESEL TANK | 4521-TK-013 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 973 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - WAREHOUSE BUILDING DIESEL TANK | 4521-TK-023 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 956 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-005 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 953 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-004 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant building |  | 780 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 437.125 | 1529.9375 | 38528.1975 | 60266.4238 | 100324.5587 | 1 | 780 | 100% | 0% | 0% | 100% | 100324.5587 | 0 | 0 | 100324.5587 | Type A 2AM-MRY1325 | Added | 2019-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 33441.5196 | 33441.5196 | 33441.5196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Mine Truck Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 1148.8542 | 4020.9896 | 101260.0063 | 158392.524 | 263673.5198 | 1 | 2050 | 100% | 0% | 0% | 100% | 263673.5198 | 0 | 0 | 263673.5198 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87891.1733 | 87891.1733 | 87891.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 951 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Rolling Stock Workshop (2018) |  | 2050 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 1148.8542 | 4020.9896 | 101260.0063 | 158392.524 | 263673.5198 | 1 | 2050 | 100% | 0% | 0% | 100% | 263673.5198 | 0 | 0 | 263673.5198 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87891.1733 | 87891.1733 | 87891.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-007 | 0 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-007 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-007 | 0 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Truck Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-008 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Truck Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-008 | 0 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Truck Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Maintenance Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-006 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Maintenance Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-006 | 0 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Maintenance Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-006 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-009 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-009 | 0 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-009 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER TANK - SIMER JET PUMPS 2205C L: 1803, W: 1245, H: 1346 |  | 0 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK |  | 0 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Liner Removal for Soft Wall Maintenance Garage (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 91.0304 | 348.0246 | 8023.4189 | 1394.969 | 9766.4125 | 0 | 0 | 100% | 0% | 0% | 100% | 9766.4125 | 0 | 0 | 9766.4125 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3255.4708 | 3255.4708 | 3255.4708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Bit shack (container building) | 2022-9/ 2021-R | 29.729 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 3.3321 | 41.6515 | 293.6931 | 459.3995 | 794.7442 | 1 | 29.729 | 100% | 0% | 0% | 100% | 794.7442 | 0 | 0 | 794.7442 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 264.9147 | 264.9147 | 264.9147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Addition of offices/ trailers at the Environment Department work areas | 2022-18 | 55.7418 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 6.2477 | 78.0966 | 550.6746 | 861.3741 | 1490.1453 | 1 | 55.7418 | 100% | 0% | 0% | 100% | 1490.1453 | 0 | 0 | 1490.1453 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 496.7151 | 496.7151 | 496.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Addition of offices/ trailers at the Environment Department work areas | 2022-18 | -55.7418 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -6.2477 | -78.0966 | -550.6746 | -861.3741 | -1490.1453 | 1 | -55.7418 | 100% | 0% | 0% | 100% | -1490.1453 | 0 | 0 | -1490.1453 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -496.7151 | -496.7151 | -496.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Communication tower KM 108 | 2022-13 | 1 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1781.561 | 0 | 0 | 1781.561 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 593.8537 | 593.8537 | 593.8537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 979 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - KIDNEY LOOP - AG - DYE10MFP240SA10QBV 50 kg | 4522-SQ-002 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 982 | MT- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | LATHE SPINDLE MOTOR | 4522-MT-004A | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1026 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - INCHING TOOL - AG | 4522-SQ-065 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1027 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-066 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1028 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-067 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Tire Shop at Ore Haul Truck Lineup (seacan construction) |  | 500 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 280.2083 | 1401.0417 | 24697.5625 | 38632.3229 | 64730.9271 | 1 | 500 | 100% | 0% | 0% | 100% | 64730.9271 | 0 | 0 | 64730.9271 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 32365.4635 | 32365.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of seacan tent structure at the aerodrome for freight and equipment sorting |  | 1127 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 631.5896 | 3157.9479 | 55668.3059 | 87077.2559 | 145903.5096 | 1 | 1127 | 100% | 0% | 0% | 100% | 145903.5096 | 0 | 0 | 145903.5096 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 72951.7548 | 72951.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of new warehouse facility (seacan tent structure) on laydown LP2 | 2021-2 | 1127 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 631.5896 | 3157.9479 | 55668.3059 | 87077.2559 | 145903.5096 | 1 | 1127 | 100% | 0% | 0% | 100% | 145903.5096 | 0 | 0 | 145903.5096 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 72951.7548 | 72951.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of new warehouse facility (seacan tent structure) on laydown LP2 | 2021-2 | -1127 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | -631.5896 | -3157.9479 | -55668.3059 | -87077.2559 | -145903.5096 | 1 | -1127 | 100% | 0% | 0% | 100% | -145903.5096 | 0 | 0 | -145903.5096 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -72951.7548 | -72951.7548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of warehouse parts/staging area (seacan tent structure) |  | 540 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 302.625 | 1513.125 | 26673.3675 | 41722.9088 | 69909.4012 | 1 | 540 | 100% | 0% | 0% | 100% | 69909.4012 | 0 | 0 | 69909.4012 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 34954.7006 | 34954.7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of offices and workshops at the stockpile and shiploader (seacan structure) | 2021-3 | 208 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 116.5667 | 582.8333 | 10274.186 | 16071.0463 | 26928.0657 | 1 | 208 | 100% | 0% | 0% | 100% | 26928.0657 | 0 | 0 | 26928.0657 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 13464.0328 | 13464.0328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment |  | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Construction of offices and workshops at the stockpile and shiploader (seacan structure) | 2021-3 | -208 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | -116.5667 | -582.8333 | -10274.186 | -16071.0463 | -26928.0657 | 1 | -208 | 100% | 0% | 0% | 100% | -26928.0657 | 0 | 0 | -26928.0657 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -13464.0328 | -13464.0328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-001 | 1003.7175 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 562.5 | 1968.75 | 49578.75 | 77551.875 | 129099.375 | 1 | 1003.7175 | 100% | 0% | 0% | 100% | 129099.375 | 0 | 0 | 129099.375 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 43033.125 | 43033.125 | 43033.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-001 | 1003.7175 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 145.7461 | 1821.8264 | 12846.0626 | 20094.0169 | 34761.906 | 0.75 | 752.7881 | 100% | 0% | 0% | 100% | 34761.906 | 0 | 0 | 34761.906 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11587.302 | 11587.302 | 11587.302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1033 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-001 | 1003.7175 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Additional Truck Wash Building |  | 1500 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 840.625 | 2942.1875 | 74092.6875 | 115896.9688 | 192931.8438 | 1 | 1500 | 100% | 0% | 0% | 100% | 192931.8438 | 0 | 0 | 192931.8438 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 64310.6146 | 64310.6146 | 64310.6146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2100 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1031 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | New thaw and wash bay facilitiy for maintenance | 2021-8 | 1250 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 700.5208 | 2451.8229 | 61743.9062 | 96580.8073 | 160776.5365 | 1 | 1250 | 100% | 0% | 0% | 100% | 160776.5365 | 0 | 0 | 160776.5365 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 53592.1788 | 53592.1788 | 53592.1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1032 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Additional Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 1500 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 217.8095 | 2722.6184 | 19197.7269 | 30029.392 | 51949.7373 | 0.75 | 1125 | 100% | 0% | 0% | 100% | 51949.7373 | 0 | 0 | 51949.7373 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 17316.5791 | 17316.5791 | 17316.5791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Ore Haul Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-002 | 0 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Ore Haul Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-002 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Ore Haul Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Electrical Office - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-001 | 20 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 4.4833 | 56.0417 | 395.161 | 618.1172 | 1069.3198 | 1 | 20 | 100% | 0% | 0% | 100% | 1069.3198 | 0 | 0 | 1069.3198 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 356.4399 | 356.4399 | 356.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete Pad for tire maintenance at 110 Laydown |  | 60 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 7.5 | 112.5 | 661.05 | 1125 | 1898.55 | 0 | 0 | 100% | 0% | 0% | 100% | 1898.55 | 0 | 0 | 1898.55 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 632.85 | 632.85 | 632.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete pad apron for exterior of HD Shop |  | 1020 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 127.5 | 1912.5 | 11237.85 | 19125 | 32275.35 | 0 | 0 | 100% | 0% | 0% | 100% | 32275.35 | 0 | 0 | 32275.35 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10758.45 | 10758.45 | 10758.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Concrete Pad for tire maintenance and welding shop at 110 Laydown |  | 600 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 75 | 1125 | 6610.5 | 11250 | 18985.5 | 0 | 0 | 100% | 0% | 0% | 100% | 18985.5 | 0 | 0 | 18985.5 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6328.5 | 6328.5 | 6328.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Services Area | 4530 | Services Area |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Additional Buildings by BIM Site Services slab on grade |  | 180 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 22.5 | 337.5 | 1983.15 | 3375 | 5695.65 | 0 | 0 | 100% | 0% | 0% | 100% | 5695.65 | 0 | 0 | 5695.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1898.55 | 1898.55 | 1898.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1059 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-007 | 66.9145 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 37.5 | 187.5 | 3305.25 | 5170.125 | 8662.875 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 8662.875 | 0 | 0 | 8662.875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2887.625 | 2887.625 | 2887.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1062 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-008 | 66.9145 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 37.5 | 187.5 | 3305.25 | 5170.125 | 8662.875 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 8662.875 | 0 | 0 | 8662.875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2887.625 | 2887.625 | 2887.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1041 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-001 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1044 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-002 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1047 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-003 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1050 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-004 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1053 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-005 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1056 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-006 | 51.9517 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1146 | 145.5729 | 2566.1594 | 4014.0276 | 6725.7599 | 1 | 51.9517 | 100% | 0% | 0% | 100% | 6725.7599 | 0 | 0 | 6725.7599 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2241.92 | 2241.92 | 2241.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1065 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 4530-BLD-009 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1283.3889 | 1283.3889 | 1283.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1066 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1067 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-009 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1042 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1043 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-001 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1045 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1046 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-002 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1048 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1049 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-003 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1051 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1052 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-004 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1054 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #5 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1055 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #5 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-005 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1057 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #6 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1058 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #6 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-006 | 51.9517 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1060 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1061 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1063 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 1064 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-001 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Electrical Shop - Demolish floor finish - Gravel | 4530-BLD-BIM-002 | 20 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-022 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-022 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-023 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-023 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #9 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-026 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #9 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #9 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-026 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #10 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-027 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Module #10 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #10 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-027 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-029 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-029 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-030 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation E-House #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-030 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 0 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Power Generation Stores #2 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-031 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Electrical Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4530-BLD-BIM-002 | 20 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 3.1383 | 39.2292 | 276.6127 | 432.682 | 748.5239 | 1 | 20 | 100% | 0% | 0% | 100% | 748.5239 | 0 | 0 | 748.5239 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 249.508 | 249.508 | 249.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation |  | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Electrical Shop - Demolish and foundations - Precast Footing (Perimeter Beam) | 4530-BLD-BIM-002 | 20 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 2.9041 | 36.3016 | 255.9697 | 400.3919 | 692.6632 | 0.75 | 15 | 100% | 0% | 0% | 100% | 692.6632 | 0 | 0 | 692.6632 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 230.8877 | 230.8877 | 230.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Existing Landfill |  | 6245 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1552.5717 | 12659.1573 | 103764.26 | 141369.146 | 257792.5632 | 0 | 0 | 100% | 0% | 0% | 100% | 257792.5632 | 0 | 0 | 257792.5632 | Type A 2AM-MRY1325 | Modified | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 257792.5632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Heated Maintenance shop for pit equipment at KM110.5 laydown | 2019-14 | 1500 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 840.625 | 2942.1875 | 74092.6875 | 115896.9688 | 192931.8438 | 1 | 1500 | 100% | 0% | 0% | 100% | 192931.8438 | 0 | 0 | 192931.8438 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 64310.6146 | 64310.6146 | 64310.6146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | New building and expansion of Mary River HD Maintenance Shop | 2022-15 | 878 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 492.0458 | 1722.1604 | 43368.9198 | 67838.359 | 112929.4392 | 1 | 878 | 100% | 0% | 0% | 100% | 112929.4392 | 0 | 0 | 112929.4392 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 37643.1464 | 37643.1464 | 37643.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Heated Maintenance shops (2) for pit equipment at KM110.5 laydown |  | 180 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 100.875 | 353.0625 | 8891.1225 | 13907.6362 | 23151.8213 | 1 | 180 | 100% | 0% | 0% | 100% | 23151.8213 | 0 | 0 | 23151.8213 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7717.2738 | 7717.2738 | 7717.2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1069 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4540-BLD-001 | 446.0967 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 250 | 875 | 22035 | 34467.5 | 57377.5 | 1 | 446.0967 | 100% | 0% | 0% | 100% | 57377.5 | 0 | 0 | 57377.5 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 19125.8333 | 19125.8333 | 19125.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1070 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Waste Management Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4540-BLD-001 | 446.0967 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 64.7761 | 809.7006 | 5709.3612 | 8930.6742 | 15449.736 | 0.75 | 334.5725 | 100% | 0% | 0% | 100% | 15449.736 | 0 | 0 | 15449.736 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5149.912 | 5149.912 | 5149.912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1071 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Waste Management Building - Demolish floor finish - Slab on grade C/W Drainage | 4540-BLD-001 | 446.0967 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 55.7621 | 836.4312 | 4914.8699 | 8364.3123 | 14115.6134 | 0 | 0 | 100% | 0% | 0% | 100% | 14115.6134 | 0 | 0 | 14115.6134 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4705.2045 | 4705.2045 | 4705.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2020-3 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type A 2AM-MRY1325 |  | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 2020-3 | -1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | -47 | -400 | -4142.58 | -4411.84 | -8954.42 | 329.2683 | -329.2683 | 100% | 0% | 0% | 100% | -8954.42 | 0 | 0 | -8954.42 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2984.8067 | -2984.8067 | -2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1083 | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | WASTE INCINERATOR VENDOR PACKAGE | 4540-VP-001 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1072 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 52.0446 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 29.1667 | 145.8333 | 2570.75 | 4021.2083 | 6737.7917 | 1 | 52.0446 | 100% | 0% | 0% | 100% | 6737.7917 | 0 | 0 | 6737.7917 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2245.9306 | 2245.9306 | 2245.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1079 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 4540-SQ-002 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1073 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1074 | VP- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 4540-VP-001 | 52.0446 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Lined Containment Cell |  | 900 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 40.0427 | 153.09 | 3529.3631 | 613.6227 | 4296.0759 | 0 | 0 | 100% | 0% | 0% | 100% | 4296.0759 | 0 | 0 | 4296.0759 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1432.0253 | 1432.0253 | 1432.0253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm | 2019-18 | 9000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 400.4269 | 1530.9 | 35293.6313 | 6136.2274 | 42960.7588 | 0 | 0 | 100% | 0% | 0% | 100% | 42960.7588 | 0 | 0 | 42960.7588 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14320.2529 | 14320.2529 | 14320.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Expansion of Landfarm Cell 3 | 2022-1 | 1288 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 57.3055 | 219.0888 | 5050.9108 | 878.1623 | 6148.1619 | 0 | 0 | 100% | 0% | 0% | 100% | 6148.1619 | 0 | 0 | 6148.1619 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2049.3873 | 2049.3873 | 2049.3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Construction of Landfarm Cell 4 | 2022-1 | 4611 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 205.1521 | 784.3311 | 18082.1038 | 3143.7938 | 22010.2287 | 0 | 0 | 100% | 0% | 0% | 100% | 22010.2287 | 0 | 0 | 22010.2287 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7336.7429 | 7336.7429 | 7336.7429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 1 | MS-HWB-XX | 360 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 16.0171 | 61.236 | 1411.7453 | 245.4491 | 1709.3086 | 0 | 0 | 100% | 0% | 0% | 100% | 1709.3086 | 0 | 0 | 1709.3086 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.7695 | 569.7695 | 569.7695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new) - 2 | MS-HWB-XX | 360 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 16.0171 | 61.236 | 1411.7453 | 245.4491 | 1709.3086 | 0 | 0 | 100% | 0% | 0% | 100% | 1709.3086 | 0 | 0 | 1709.3086 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.7695 | 569.7695 | 569.7695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - 2016 (new-by generator) - 3 | MS-HWB-XX | 160 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 7.1187 | 27.216 | 627.4423 | 109.0885 | 759.6927 | 0 | 0 | 100% | 0% | 0% | 100% | 759.6927 | 0 | 0 | 759.6927 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 253.2309 | 253.2309 | 253.2309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 4475 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 1112.5313 | 9071.2136 | 74354.6939 | 101301.3496 | 188682.9859 | 0 | 0 | 100% | 0% | 0% | 100% | 188682.9859 | 0 | 0 | 188682.9859 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 188682.9859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A2 | Fill Application - Assumed average Depth of 1.50 m3 | Fill | Site Works | Fill Application | Fill Application | Landfill Expansion |  | 400 | m2 | 0.24861 | 2.0271 | 16.6156 | 22.6372 | 42.1638 | 99.4441 | 810.8347 | 6646.2296 | 9054.8692 | 16865.5183 | 0 | 0 | 100% | 0% | 0% | 100% | 16865.5183 | 0 | 0 | 16865.5183 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 16865.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | 2018 Landfill Expansion |  | 63000 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 799.5886 | 9213.75 | 70475.7434 | 25295.6243 | 104891.3678 | 0 | 0 | 100% | 0% | 0% | 100% | 104891.3678 | 0 | 0 | 104891.3678 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 104891.3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm Containment Facilities 2020 HD Shop - 72m2, MR Shop - 120 m2, Wash Bay - 120 m2, 110 Laydown - 144 m2 | 2020-8 | 456 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 20.2883 | 77.5656 | 1788.2107 | 310.9022 | 2165.1243 | 0 | 0 | 100% | 0% | 0% | 100% | 2165.1243 | 0 | 0 | 2165.1243 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 721.7081 | 721.7081 | 721.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - New 2019 | 2019-11 | 360 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 16.0171 | 61.236 | 1411.7453 | 245.4491 | 1709.3086 | 0 | 0 | 100% | 0% | 0% | 100% | 1709.3086 | 0 | 0 | 1709.3086 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 569.7695 | 569.7695 | 569.7695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm - New 2019 | 2019-11 | -360 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -16.0171 | -61.236 | -1411.7453 | -245.4491 | -1709.3086 | 0 | 0 | 100% | 0% | 0% | 100% | -1709.3086 | 0 | 0 | -1709.3086 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -569.7695 | -569.7695 | -569.7695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3 | Grade & Re-Contour | A3 | Site Works | Grade and Re-Contour |  | Mine Site Hazardous Waste Berm | 2019-11 | 1820 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 23.0992 | 266.175 | 2035.9659 | 730.7625 | 3030.1951 | 0 | 0 | 100% | 0% | 0% | 100% | 3030.1951 | 0 | 0 | 3030.1951 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1010.065 | 1010.065 | 1010.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Mine Site Hazardous Waste Berm | 2019-11 | 2700 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 120.1281 | 459.27 | 10588.0894 | 1840.8682 | 12819.8148 | 0 | 0 | 100% | 0% | 0% | 100% | 12819.8148 | 0 | 0 | 12819.8148 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4273.2716 | 4273.2716 | 4273.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-2 | 1298 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 57.7505 | 220.7898 | 5090.1259 | 884.9804 | 6163.0073 | 0 | 0 | 100% | 0% | 0% | 100% | 6163.0073 | 0 | 0 | 6163.0073 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2054.3358 | 2054.3358 | 2054.3358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-1 | 754 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 33.5469 | 128.2554 | 2956.822 | 514.0795 | 3599.1569 | 0 | 0 | 100% | 0% | 0% | 100% | 3599.1569 | 0 | 0 | 3599.1569 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1199.719 | 1199.719 | 1199.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-4 | 649 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 28.8752 | 110.3949 | 2545.063 | 442.4902 | 3081.5036 | 0 | 0 | 100% | 0% | 0% | 100% | 3081.5036 | 0 | 0 | 3081.5036 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1027.1679 | 1027.1679 | 1027.1679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-3 | 600 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 26.6951 | 102.06 | 2352.9088 | 409.0818 | 2848.8477 | 0 | 0 | 100% | 0% | 0% | 100% | 2848.8477 | 0 | 0 | 2848.8477 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 949.6159 | 949.6159 | 949.6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-6 | 550 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 24.4705 | 93.555 | 2156.833 | 374.9917 | 2611.4438 | 0 | 0 | 100% | 0% | 0% | 100% | 2611.4438 | 0 | 0 | 2611.4438 | Type A 2AM-MRY1325 | Added | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 870.4813 | 870.4813 | 870.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm | MS-HWB-5 | 347 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 15.4387 | 59.0247 | 1360.7656 | 236.5857 | 1647.5836 | 0 | 0 | 100% | 0% | 0% | 100% | 1647.5836 | 0 | 0 | 1647.5836 | Type A 2AM-MRY1325 | Modified | 2015 R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 549.1945 | 549.1945 | 549.1945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management |  | VP- | VP1 | VENDOR PKG - Incinerator | VP1 | Packaged Facilities | Incinerator |  | Incinerator for 380-person camp at Mine Site |  | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 0% | 100% | 8954.42 | 0 | 0 | 8954.42 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | 15ML Arctic Diesel Tank Mine Site | 2019-20 | 2 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | 1358.8 | 15695 | 119764.632 | 173109.572 | 308569.204 | 160 | 320 | 100% | 0% | 0% | 100% | 308569.204 | 0 | 0 | 308569.204 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 154284.602 | 154284.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT4-d | Largest Diesel Tanks (10M L to 12M L) | MT4-d | Mechanical Equipment | Largest Diesel Tanks |  | 15ML Arctic Diesel Tank Mine Site | 2019-20 | -1 | Ea | 679.4 | 7847.5 | 59882.316 | 86554.786 | 154284.602 | -679.4 | -7847.5 | -59882.316 | -86554.786 | -154284.602 | 160 | -160 | 100% | 0% | 0% | 100% | -154284.602 | 0 | 0 | -154284.602 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -77142.301 | -77142.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1101 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-009 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1102 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-010 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1103 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-011 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1104 | TK- | MT2-d | Medium Diesel Tanks (500k L to 750k L) | MT2-d | Mechanical Equipment | Medium Diesel Tanks |  | TANK - ARCTIC DIESEL TANK W: 8350 DIA H: 9140 | 4613-TK-012 | 1 | Ea | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 65.79 | 726.75 | 5798.7306 | 8015.7618 | 14541.2424 | 40 | 40 | 100% | 0% | 0% | 100% | 14541.2424 | 0 | 0 | 14541.2424 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7270.6212 | 7270.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1089 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 4613-FD-013 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1925.0833 | 1925.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1091 | FD- |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1090 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 4613-FD-013 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | 50,000 L Portable Fuel Dispensing Unit |  | 2 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 85.45 | 941.25 | 7531.563 | 10381.611 | 18854.424 | 30 | 60 | 100% | 0% | 0% | 100% | 18854.424 | 0 | 0 | 18854.424 | Type A 2AM-MRY1325 | Added | 2016 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6284.808 | 6284.808 | 6284.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Mine Site Fuel Tank Farm 2019 Footprint |  | 21620 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 274.3985 | 3161.925 | 24185.4853 | 8680.8158 | 35996.0535 | 0 | 0 | 100% | 0% | 0% | 100% | 35996.0535 | 0 | 0 | 35996.0535 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11998.6845 | 11998.6845 | 11998.6845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (North West) |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (South West) |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | Fuel tank | 250,000 liter Fuel tank | 2022-5 E-17 | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -8381.25 | -8381.25 | -8381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | Fuel tank | 250,000 liter Fuel tank | 2022-5 E-17 | -1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | -42.725 | -470.625 | -3765.7815 | -5190.8055 | -9427.212 | 30 | -30 | 100% | 0% | 0% | 100% | -9427.212 | 0 | 0 | -9427.212 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -8381.25 | -8381.25 | -8381.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Farm Tank Dike |  | 1911.3 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 85.0373 | 325.1121 | 7495.1908 | 1303.1302 | 9123.4331 | 0 | 0 | 100% | 0% | 0% | 100% | 9123.4331 | 0 | 0 | 9123.4331 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4561.7166 | 4561.7166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 12000 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 533.9026 | 2041.2 | 47058.1751 | 8181.6365 | 57281.0117 | 0 | 0 | 100% | 0% | 0% | 100% | 57281.0117 | 0 | 0 | 57281.0117 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 28640.5058 | 28640.5058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Fuel Tank Containment Area |  | 400 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 17.7968 | 68.04 | 1568.6058 | 272.7212 | 1909.3671 | 0 | 0 | 100% | 0% | 0% | 100% | 1909.3671 | 0 | 0 | 1909.3671 | Type A 2AM-MRY1325 |  | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 954.6835 | 954.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4614 | Jet-A System | 416 | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | Tank - Jet-A tanks @ aerodrome apron |  | 0 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1119 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Raw Water Supply Pipe - Piping Installation - Pumphouse to Water Building | 4712.2-P | 8518 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 2129.5 | 26618.75 | 187694.13 | 293594.165 | 507907.045 | 0.01 | 85.18 | 100% | 0% | 100% | 0% | 507907.045 | 0 | 507907.045 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 169302.3483 | 169302.3483 | 169302.3483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1115 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Pumphouse - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4712-BLD-001 | 14.8699 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 3.3333 | 41.6667 | 293.8 | 459.5667 | 795.0333 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 795.0333 | 0 | 0 | 795.0333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 265.0111 | 265.0111 | 265.0111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1116 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Pumphouse - Demolish and foundations - Gravel Base - Skidded Building | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1117 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Pumphouse - Demolish floor finish - Raised Steel or Wooden Floor | 4712-BLD-001 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System | 1118 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Raw Water Supply Pipe - Heat Trace Installation - Pumphouse to Water Building | 4712.2-E | 4712 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4710 | Raw Water Intake | 4712 | Raw Water System |  |  | piping | Piping | Piping | Bulks | Piping |  | Raw Water Intake Pipeline |  |  | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1121 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4720-BLD-001 | 390.3346 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 61.25 | 765.625 | 5398.575 | 8444.5375 | 14608.7375 | 1 | 390.3346 | 100% | 0% | 0% | 100% | 14608.7375 | 0 | 0 | 14608.7375 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4869.5792 | 4869.5792 | 4869.5792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1122 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Water Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4720-BLD-001 | 390.3346 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 56.679 | 708.4881 | 4995.691 | 7814.3399 | 13518.519 | 0.75 | 292.7509 | 100% | 0% | 0% | 100% | 13518.519 | 0 | 0 | 13518.519 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4506.173 | 4506.173 | 4506.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE | 4720-VP-020 | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1143 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK | 4720-TK-001 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1144 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FIRE WATER TANK | 4720-TK-007 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1145 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK | 4720-TK-009 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1146 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BACKWASH SETTLING TANK | 4720-TK-012 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1123 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Water Building - Demolish floor finish - Gravel | 4720-BLD-001 | 390.3346 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Infill between service and utility pads |  | 20800 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 263.9912 | 3042 | 23268.1819 | 8351.5712 | 34630.8008 | 0 | 0 | 100% | 0% | 0% | 100% | 34630.8008 | 0 | 0 | 34630.8008 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 11543.6003 | 11543.6003 | 11543.6003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - POTABLE WATER STORAGE TANK (40 m3) |  | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - RAW WATER TANK (60 m3) |  | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 | Confirmed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | VENDOR PACKAGE - POTABLE WATER TREATMENT PLANT VENDOR PACKAGE |  | 0 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP7 | VENDOR PKG - WRF Water Treatment System | VP7 | Packaged Facilities | WRF Water Treatment |  | Water Treatment Plant for the Waste Rock Facility |  | 1 | Lot | 340 | 3625 | 29967.6 | 39982.3 | 69949.9 | 340 | 3625 | 29967.6 | 39982.3 | 69949.9 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 69949.9 | 0 | 69949.9 | 0 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 23316.6333 | 23316.6333 | 23316.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP7 | VENDOR PKG - WRF Water Treatment System | VP7 | Packaged Facilities | WRF Water Treatment |  | Water Treatment Plant for km 105 Sedimentation Pond | 2023 | 1 | Lot | 340 | 3625 | 29967.6 | 39982.3 | 69949.9 | 340 | 3625 | 29967.6 | 39982.3 | 69949.9 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 69949.9 | 0 | 69949.9 | 0 | Type A 2AM-MRY1325 |  | 2023 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 23316.6333 | 23316.6333 | 23316.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1148 | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | Potable Water System for 800-person camp at Mine Site |  | 1 | Lot | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 47 | 400 | 4142.58 | 4411.84 | 8954.42 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 8954.42 | 0 | 8954.42 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2984.8067 | 2984.8067 | 2984.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | BLD | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers |  | Replacement of inflatable building with rigid building | 2022-8 | 208.1027 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 23.3248 | 291.5606 | 2055.852 | 3215.7966 | 5563.2091 | 1 | 208.1027 | 100% | 0% | 0% | 100% | 5563.2091 | 0 | 0 | 5563.2091 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1854.403 | 1854.403 | 1854.403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to the Water Treatment Plant Pad | 2022-16 | 10500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 133.2648 | 1535.625 | 11745.9572 | 4215.9374 | 17497.5196 | 0 | 0 | 100% | 0% | 0% | 100% | 17497.5196 | 0 | 0 | 17497.5196 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 5832.5065 | 5832.5065 | 5832.5065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Expansion to the Water Treatment Plant Pad | 2022-16 | -10500 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -133.2648 | -1535.625 | -11745.9572 | -4215.9374 | -17497.5196 | 0 | 0 | 100% | 0% | 0% | 100% | -17497.5196 | 0 | 0 | -17497.5196 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -5832.5065 | -5832.5065 | -5832.5065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1154 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 178.4387 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 100 | 500 | 8814 | 13787 | 23101 | 1 | 178.4387 | 100% | 0% | 0% | 100% | 23101 | 0 | 0 | 23101 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 11550.5 | 11550.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1163 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - Sewage truck bldg to STP | 4731.2-P | 247 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 61.75 | 771.875 | 5442.645 | 8513.4725 | 14727.9925 | 0.01 | 2.47 | 100% | 0% | 100% | 0% | 14727.9925 | 0 | 14727.9925 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 7363.9963 | 7363.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1161 | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | SEWAGE TREATMENT PLANT VENDOR PACKAGE | 4731-VP-005 | 1 | Lot | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9908.46 | 0 | 9908.46 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4954.23 | 4954.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1160 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - TREATED EFFLUENT TANK | 4731-TK-002 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2213.9867 | 2213.9867 | 2213.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1151 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 4731-BLD-001 | 29.7398 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 16.6667 | 83.3333 | 1469 | 2297.8333 | 3850.1667 | 1 | 29.7398 | 100% | 0% | 0% | 100% | 3850.1667 | 0 | 0 | 3850.1667 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1925.0833 | 1925.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1152 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Chemical Storage Container - Demolish and foundations - Gravel Base - Skidded Building | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1153 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Sewage Chemical Storage Container - Demolish floor finish - Raised Steel or Wooden Floor | 4731-BLD-001 | 29.7398 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1162 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Sewage Treatment Piping - Heat Trace Installation - Sewage truck bldg to STP | 4731.2-E | 128 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1155 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 4731-VP-005 | 178.4387 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1156 | VP- |  | #N/A |  |  |  |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 4731-VP-005 | 1920 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | In Meters | piping | Piping | Piping | Bulks | Piping |  | Sewage Treatment Piping - Piping Installation - 800p camp to final discharge point |  | 2200 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 550 | 6875 | 48477 | 75828.5 | 131180.5 | 0.01 | 22 | 100% | 0% | 100% | 0% | 131180.5 | 0 | 131180.5 | 0 | Type A 2AM-MRY1325 | Added | 2018-C2 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 65590.25 | 65590.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE |  | 0 | Lot | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 0 | 0 | 0 | 0 | 0 | 329.2683 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | Sewage Treatment Plant for 800-person camp at Mine Site |  | 1 | Lot | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 51 | 450 | 4495.14 | 4963.32 | 9908.46 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9908.46 | 0 | 9908.46 | 0 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4954.23 | 4954.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1165 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4732-BLD-001 | 55.7621 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 31.25 | 109.375 | 2754.375 | 4308.4375 | 7172.1875 | 1 | 55.7621 | 100% | 0% | 0% | 100% | 7172.1875 | 0 | 0 | 7172.1875 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3586.0938 | 3586.0938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4280 | Mine Support Facilities |  | Water Systems |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Soft Walled Building (tent) Contaminated (480 ft2) |  | Tent Structure for Waste Rock Facility Water Treatment System |  | 726 | m2 | 0.58283 | 2.2417 | 56.1215 | 80.3552 | 138.7184 | 423.137 | 1627.45 | 40744.2012 | 58337.8982 | 100709.5494 | 0.5 | 363 | 100% | 0% | 0% | 100% | 100709.5494 | 0 | 0 | 100709.5494 | Type A 2AM-MRY1325 |  | 2018-C2 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 50354.7747 | 50354.7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1172 | TK- | MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | MT1-d | Mechanical Equipment | Light Diesel Tanks |  | TANK - MINE SEWAGE TRUCK BUILDING DIESEL FUEL TANK - DTE ULC601-07 | 4732-TK-003 | 1 | Ea | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 15.5 | 162.5 | 1366.17 | 1792.31 | 3320.98 | 20 | 20 | 100% | 0% | 0% | 100% | 3320.98 | 0 | 0 | 3320.98 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1660.49 | 1660.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1166 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Sewage Truck Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4732-BLD-001 | 55.7621 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 8.097 | 101.2126 | 713.6701 | 1116.3343 | 1931.217 | 0.75 | 41.8216 | 100% | 0% | 0% | 100% | 1931.217 | 0 | 0 | 1931.217 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 965.6085 | 965.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1167 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Sewage Truck Building - Demolish floor finish - Gravel | 4732-BLD-001 | 55.7621 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1178 | In Meters | piping | Piping | Piping | Bulks | Piping |  | Treated Effluent Piping - Piping Installation - STP to connection with Stockpile Drain Pipe | 4734.1-P | 2125 | m | 0.25 | 3.125 | 22.035 | 34.4675 | 59.6275 | 531.25 | 6640.625 | 46824.375 | 73243.4375 | 126708.4375 | 0.01 | 21.25 | 100% | 0% | 100% | 0% | 126708.4375 | 0 | 126708.4375 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 42236.1458 | 42236.1458 | 42236.1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4734 | Treated Effluent Discharge | 1177 | In Meters |  | #N/A | Piping - Heat Tracing | Bulks | Piping - Heat Tracing |  | Treated Effluent Piping - Heat Trace Installation - STP to connection with Stockpile Drain Pipe | 4734.1-E | 2050 | m | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1174 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE | 4733-VM-001 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1175 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE SPARE | 4733-VM-002 | 0 | Ea | 2 | 25 | 176.28 | 275.74 | 477.02 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | FRP Water tanks for 800p camp |  | 4 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 38.6667 | 358.3333 | 3408.08 | 3952.2733 | 7718.6867 | 1 | 4 | 100% | 0% | 0% | 100% | 7718.6867 | 0 | 0 | 7718.6867 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2572.8956 | 2572.8956 | 2572.8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | -1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | -9.6667 | -89.5833 | -852.02 | -988.0683 | -1929.6717 | 1 | -1 | 100% | 0% | 0% | 100% | -1929.6717 | 0 | 0 | -1929.6717 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -643.2239 | -643.2239 | -643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Water Tank 10,000L |  | 4 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 38.6667 | 358.3333 | 3408.08 | 3952.2733 | 7718.6867 | 1 | 4 | 100% | 0% | 0% | 100% | 7718.6867 | 0 | 0 | 7718.6867 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2572.8956 | 2572.8956 | 2572.8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | -3 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | -29 | -268.75 | -2556.06 | -2964.205 | -5789.015 | 1 | -3 | 100% | 0% | 0% | 100% | -5789.015 | 0 | 0 | -5789.015 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -1929.6717 | -1929.6717 | -1929.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 2 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 19.3333 | 179.1667 | 1704.04 | 1976.1367 | 3859.3433 | 1 | 2 | 100% | 0% | 0% | 100% | 3859.3433 | 0 | 0 | 3859.3433 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1286.4478 | 1286.4478 | 1286.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 50,000L |  | -1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | -9.6667 | -89.5833 | -852.02 | -988.0683 | -1929.6717 | 1 | -1 | 100% | 0% | 0% | 100% | -1929.6717 | 0 | 0 | -1929.6717 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -643.2239 | -643.2239 | -643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 1,000L |  | 2 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 19.3333 | 179.1667 | 1704.04 | 1976.1367 | 3859.3433 | 1 | 2 | 100% | 0% | 0% | 100% | 3859.3433 | 0 | 0 | 3859.3433 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1286.4478 | 1286.4478 | 1286.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 15,000L |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 | Added | 2018-C1 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks | 3rd Party Contractor | Water Tank 10,000L |  | -1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | -9.6667 | -89.5833 | -852.02 | -988.0683 | -1929.6717 | 1 | -1 | 100% | 0% | 0% | 100% | -1929.6717 | 0 | 0 | -1929.6717 | Type A 2AM-MRY1325 | Added | 2018-MAY | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -643.2239 | -643.2239 | -643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 3 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 93 | 975 | 8197.02 | 10753.86 | 19925.88 | 2 | 6 | 100% | 0% | 0% | 100% | 19925.88 | 0 | 0 | 19925.88 | Type B Construction 2BC-MRY1416 | Confirmed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 9962.94 | 9962.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 0 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | Fuel tank | 15,000 L Bulk diesel storage at Weatherhaven | 2022-10 E-33 | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4713.606 | 4713.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks | Fuel tank | 15,000 L Bulk Jet A storage | E-3 | 1 | Ea | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 42.725 | 470.625 | 3765.7815 | 5190.8055 | 9427.212 | 30 | 30 | 100% | 0% | 0% | 100% | 9427.212 | 0 | 0 | 9427.212 | Type A 2AM-MRY1325 | Added | 2023 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 4713.606 | 4713.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1204 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 5kV & Ground Wire - Electrical distribution system from power gen to e-house | 4750.2-E | 11000 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 1100 | 13750 | 96954 | 151657 | 262361 | 0.01 | 110 | 100% | 0% | 0% | 100% | 262361 | 0 | 0 | 262361 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87453.6667 | 87453.6667 | 87453.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation 600V - Connections from e-house to facilities | 4750.3-E | 5200 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 520 | 6500 | 45832.8 | 71692.4 | 124025.2 | 0.01 | 52 | 100% | 0% | 0% | 100% | 124025.2 | 0 | 0 | 124025.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 41341.7333 | 41341.7333 | 41341.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution System - Electrical Cable Installation - Mary River Powerhouse to Dyno Nobel explosives facility (500 m), and Mary River E-House 3 to KM 104 laydown (300 m) |  | 800 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 80 | 1000 | 7051.2 | 11029.6 | 19080.8 | 0.01 | 8 | 100% | 0% | 0% | 100% | 19080.8 | 0 | 0 | 19080.8 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6360.2667 | 6360.2667 | 6360.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling from the new KM110 building to the Mine water treatment facility | 2022-11 | 500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 50 | 625 | 4407 | 6893.5 | 11925.5 | 0.01 | 5 | 100% | 0% | 0% | 100% | 11925.5 | 0 | 0 | 11925.5 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3975.1667 | 3975.1667 | 3975.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling from the new KM110 building to the Mine water treatment facility | 2022-11 | -500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | -50 | -625 | -4407 | -6893.5 | -11925.5 | 0.01 | -5 | 100% | 0% | 0% | 100% | -11925.5 | 0 | 0 | -11925.5 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3975.1667 | -3975.1667 | -3975.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling and distribution equipment for a new service from the Port Power house area to CV-001 on the shiploader | 2022-19 | 800 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 80 | 1000 | 7051.2 | 11029.6 | 19080.8 | 0.01 | 8 | 100% | 0% | 0% | 100% | 19080.8 | 0 | 0 | 19080.8 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 6360.2667 | 6360.2667 | 6360.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling and distribution equipment for a new service from the Port Power house area to CV-001 on the shiploader | 2022-19 | -800 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | -80 | -1000 | -7051.2 | -11029.6 | -19080.8 | 0.01 | -8 | 100% | 0% | 0% | 100% | -19080.8 | 0 | 0 | -19080.8 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -6360.2667 | -6360.2667 | -6360.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling (from the Powerhouse to Dyno Nobel explosives facility) | 2021-1 | 500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 50 | 625 | 4407 | 6893.5 | 11925.5 | 0.01 | 5 | 100% | 0% | 0% | 100% | 11925.5 | 0 | 0 | 11925.5 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3975.1667 | 3975.1667 | 3975.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling (from E-House 3 to KM 104 laydown) | 2021-1 | 300 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 30 | 375 | 2644.2 | 4136.1 | 7155.3 | 0.01 | 3 | 100% | 0% | 0% | 100% | 7155.3 | 0 | 0 | 7155.3 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2385.1 | 2385.1 | 2385.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling (from the Powerhouse to Dyno Nobel explosives facility) | 2021-1 | -500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | -50 | -625 | -4407 | -6893.5 | -11925.5 | 0.01 | -5 | 100% | 0% | 0% | 100% | -11925.5 | 0 | 0 | -11925.5 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3975.1667 | -3975.1667 | -3975.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Power Distribution cabling (from E-House 3 to KM 104 laydown) | 2021-1 | -300 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | -30 | -375 | -2644.2 | -4136.1 | -7155.3 | 0.01 | -3 | 100% | 0% | 0% | 100% | -7155.3 | 0 | 0 | -7155.3 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -2385.1 | -2385.1 | -2385.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1180 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-001 | 59.4796 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 13.3333 | 166.6667 | 1175.2 | 1838.2667 | 3180.1333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3180.1333 | 0 | 0 | 3180.1333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1060.0444 | 1060.0444 | 1060.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1201 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing & Screening E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 59.4796 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 13.3333 | 166.6667 | 1175.2 | 1838.2667 | 3180.1333 | 1 | 59.4796 | 100% | 0% | 0% | 100% | 3180.1333 | 0 | 0 | 3180.1333 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1060.0444 | 1060.0444 | 1060.0444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1183 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-002 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1186 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-003 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1189 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-004 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1192 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-005 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 993.7917 | 993.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1195 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Aerodrome Area E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-006 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1198 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Raw Water Supply E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-007 | 37.1747 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3333 | 104.1667 | 734.5 | 1148.9167 | 1987.5833 | 1 | 37.1747 | 100% | 0% | 0% | 100% | 1987.5833 | 0 | 0 | 1987.5833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.5278 | 662.5278 | 662.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1184 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1185 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-002 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1187 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1188 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-003 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1190 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #2 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1191 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-004 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1193 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Tank Farm E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1194 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Tank Farm E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-005 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1196 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Aerodrome Area E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1197 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Area E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-006 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1199 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Raw Water Supply E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1200 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Raw Water Supply E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-007 | 37.1747 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1181 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1182 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-001 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1202 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing & Screening E-House - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1203 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing & Screening E-House - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 59.4796 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Cabling for Lighting at Mine Site Warehouse | 2020-11 | 600 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 60 | 750 | 5288.4 | 8272.2 | 14310.6 | 0.01 | 6 | 100% | 0% | 0% | 100% | 14310.6 | 0 | 0 | 14310.6 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4770.2 | 4770.2 | 4770.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 1205 | In Meters | cable | Cable | Cable | Bulks | Cable |  | Additional outdoor lighting for safety (with cables) at Mine Site |  | 3500 | m | 0.1 | 1.25 | 8.814 | 13.787 | 23.851 | 350 | 4375 | 30849 | 48254.5 | 83478.5 | 0.01 | 35 | 100% | 0% | 0% | 100% | 83478.5 | 0 | 0 | 83478.5 | Type A 2AM-MRY1325 | Added | 2017 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 27826.1667 | 27826.1667 | 27826.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-012 | 37.1612 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 8.3303 | 104.1288 | 734.2332 | 1148.4993 | 1986.8613 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 1986.8613 | 0 | 0 | 1986.8613 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 662.2871 | 662.2871 | 662.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-010 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-010 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-011 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #2- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-011 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Services Area E-House #3- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-012 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Crushing and Screening E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment
5000 | Baffinland Owned Equipment | 5100 | Project Wide
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 74 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 12432 | 136900 | 1095756.48 | 1509952.24 | 2742608.72 | 56 | 4144 | 100% | 0% | 0% | 100% | 2742608.72 | 0 | 0 | 2742608.72 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2742608.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 183 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 3513.6 | 32482.5 | 309688.704 | 358268.982 | 700440.186 | 1 | 183 | 100% | 0% | 0% | 100% | 700440.186 | 0 | 0 | 700440.186 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 700440.186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 220 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 1782 | 19525 | 157065.48 | 215352.94 | 391943.42 | 0.5 | 110 | 100% | 0% | 0% | 100% | 391943.42 | 0 | 0 | 391943.42 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 391943.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 312 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 4056 | 31200 | 357495.84 | 344123.52 | 732819.36 | 96 | 29952 | 100% | 0% | 0% | 100% | 732819.36 | 0 | 0 | 732819.36 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 732819.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 326 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 3260 | 12225 | 287336.4 | 134836.86 | 434398.26 | 24 | 7824 | 100% | 0% | 0% | 100% | 434398.26 | 0 | 0 | 434398.26 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 434398.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Global Estimate for Equipment - Arbitration Reconciliation |  | 297 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 1980 | 6187.5 | 174517.2 | 68245.65 | 248950.35 | 4 | 1188 | 100% | 0% | 0% | 100% | 248950.35 | 0 | 0 | 248950.35 | Type A 2AM-MRY1325 | Added | 2019 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 248950.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Heavy 3rd Party Equipment Demob |  | 49 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 637 | 4900 | 56145.18 | 54045.04 | 115090.22 | 96 | 4704 | 100% | 0% | 0% | 100% | 115090.22 | 0 | 0 | 115090.22 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 115090.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Med 3rd Party Equipment Demob |  | 61 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 610 | 2287.5 | 53765.4 | 25230.21 | 81283.11 | 24 | 1464 | 100% | 0% | 0% | 100% | 81283.11 | 0 | 0 | 81283.11 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 81283.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Light 3rd Party Equipment Demob |  | 34 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 226.6667 | 708.3333 | 19978.4 | 7812.6333 | 28499.3667 | 4 | 136 | 100% | 0% | 0% | 100% | 28499.3667 | 0 | 0 | 28499.3667 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 28499.3667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 3rd Party Equipment | Heavy - Arbitration Reconciliation for 2020 Work Plan |  | -49 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -637 | -4900 | -56145.18 | -54045.04 | -115090.22 | 96 | -4704 | 100% | 0% | 0% | 100% | -115090.22 | 0 | 0 | -115090.22 | Type A 2AM-MRY1325 | Removed | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | -115090.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | 3rd Party Equipment | Med - Arbitration Reconciliation for 2020 Work Plan |  | -61 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -610 | -2287.5 | -53765.4 | -25230.21 | -81283.11 | 24 | -1464 | 100% | 0% | 0% | 100% | -81283.11 | 0 | 0 | -81283.11 | Type A 2AM-MRY1325 | Removed | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | -81283.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | 3rd Party Equipment | Light - Arbitration Reconciliation for 2020 Work Plan |  | -34 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -226.6667 | -708.3333 | -19978.4 | -7812.6333 | -28499.3667 | 4 | -136 | 100% | 0% | 0% | 100% | -28499.3667 | 0 | 0 | -28499.3667 | Type A 2AM-MRY1325 | Removed | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | -28499.3667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 317 | MT- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Generator/Air Compressor |  | -1 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -8.1 | -88.75 | -713.934 | -978.877 | -1781.561 | 0.5 | -0.5 | 100% | 0% | 0% | 100% | -1781.561 | 0 | 0 | -1781.561 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1781.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | -21 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -170.1 | -1863.75 | -14992.614 | -20556.417 | -37412.781 | 0.5 | -10.5 | 100% | 0% | 0% | 100% | -37412.781 | 0 | 0 | -37412.781 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -37412.781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | -7 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -56.7 | -621.25 | -4997.538 | -6852.139 | -12470.927 | 0.5 | -3.5 | 100% | 0% | 0% | 100% | -12470.927 | 0 | 0 | -12470.927 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -12470.927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | FRF | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Plants |  | 10 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 81 | 887.5 | 7139.34 | 9788.77 | 17815.61 | 0.5 | 5 | 100% | 0% | 0% | 100% | 17815.61 | 0 | 0 | 17815.61 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 17815.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1263 | PP- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Water Jet - Ceramic Cutting | 2021-11 | -1 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -8.1 | -88.75 | -713.934 | -978.877 | -1781.561 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | -1781.561 | 0 | 0 | -1781.561 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1781.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1263 | PP- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Water Jet - Ceramic Cutting | 2021-11 | 1 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1781.561 | 0 | 0 | 1781.561 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1781.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Rescue Boat and Trailer |  | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Ford F350 Pickup | 2021-10 | -3 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -20 | -62.5 | -1762.8 | -689.35 | -2514.65 | 4 | 12 | 100% | 0% | 0% | 100% | -2514.65 | 0 | 0 | -2514.65 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2514.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Ford F350 Pickup | 2021-10 | 3 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 20 | 62.5 | 1762.8 | 689.35 | 2514.65 | 4 | 12 | 100% | 0% | 0% | 100% | 2514.65 | 0 | 0 | 2514.65 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2514.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Welding Shop Crane | 2021-22 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 30,000 L Fuel Tanker Truck |  | -11 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -143 | -1100 | -12604.02 | -12132.56 | -25836.58 | 96 | -1056 | 100% | 0% | 0% | 100% | -25836.58 | 0 | 0 | -25836.58 | Type A 2AM-MRY1325 | removed | 2020-r | Direct |  |  | 100% | [10 empty] | 0 | 0 | -25836.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | USED TANDEM DRIVE WESTERN STAR WINCH TRUCK UNIT# 587 |  | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | USED WINCH TRUCK WESTERN STAR UNIT# 586 |  | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740 Articulated Truck |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Western Star Haul Truck |  | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | -192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 Loader | 2021-2 | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | -192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 Loader | 2021-2 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950 Loader |  | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | -192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950 Loader |  | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374F Excavator |  | -4 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -52 | -400 | -4583.28 | -4411.84 | -9395.12 | 96 | -384 | 100% | 0% | 0% | 100% | -9395.12 | 0 | 0 | -9395.12 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -9395.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374F Excavator |  | 4 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 52 | 400 | 4583.28 | 4411.84 | 9395.12 | 96 | 384 | 100% | 0% | 0% | 100% | 9395.12 | 0 | 0 | 9395.12 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 9395.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 CAT Excavator | 2021-6 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 CAT Excavator | 2021-6 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 745C Rock Truck |  | 4 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 52 | 400 | 4583.28 | 4411.84 | 9395.12 | 96 | 384 | 100% | 0% | 0% | 100% | 9395.12 | 0 | 0 | 9395.12 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 9395.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 950M Loader |  | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Duty Shunt Truck |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Decommissioned Drill |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Feeder Dolly |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fines Mobile Stacker |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Boat Trailer |  | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Tire Changer |  | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Argo Vehicle |  | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Larue Snow Blower |  | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Larue Snow Blower |  | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 257 Skid steer |  | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | 257 Skid steer |  | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Blaze Cube Frost Fighters |  | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Blaze Cube Frost Fighters |  | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 Fire Truck | 2021-13 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 740B Water Truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 14M Grader | 2021-31 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel Tanker | 2021-32 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Jet A Truck | 2021-33 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | -48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Track Mounted Drill Rig |  | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | -48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | -48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 740B Water Truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 14M Grader | 2021-31 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Fuel Tanker | 2021-32 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Jet A Truck | 2021-33 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck |  | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Bus |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48p School Bus |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48p School Bus |  | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Track Mounted Drill Rig |  | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 15 passenger crew van | 2021-12 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 15 passenger crew van | 2021-12 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Deckover Trailer |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat bed boom truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat bed boom truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer | 2021-29 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck | 2021-21 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 96 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure Washing Truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Dual Engine Marine Response Boat | 2021-18 | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Dual Engine Marine Response Boat | 2021-18 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tower Trailer |  | 3 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 30 | 112.5 | 2644.2 | 1240.83 | 3997.53 | 24 | 72 | 100% | 0% | 0% | 100% | 3997.53 | 0 | 0 | 3997.53 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3997.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Kalamar DRT450 |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | D8T Dozer |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Tri-Trombone flat trailer |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle | 2021-17 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 349 Cat Excavator | 2021-7 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 349 Cat Excavator | 2021-7 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 320 Track Cat Excavator | 2021-8 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 320 Track Cat Excavator | 2021-8 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | HPS 185 Spray Unit for Stockpile Dust suppression | 2021-5 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Jump Conveyor |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - Conveyor Feeder |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Stacker |  | 4 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 672 | 7400 | 59230.08 | 81619.04 | 148249.12 | 56 | 224 | 100% | 0% | 0% | 100% | 148249.12 | 0 | 0 | 148249.12 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 148249.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen |  | 4 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 672 | 7400 | 59230.08 | 81619.04 | 148249.12 | 56 | 224 | 100% | 0% | 0% | 100% | 148249.12 | 0 | 0 | 148249.12 | Type A 2AM-MRY1325 | Added | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 148249.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Feed Conveyor |  | 1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 56 | 56 | 100% | 0% | 0% | 100% | 37062.28 | 0 | 0 | 37062.28 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator 1000 kW |  | -1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | -168 | -1850 | -14807.52 | -20404.76 | -37062.28 | 56 | -56 | 100% | 0% | 0% | 100% | -37062.28 | 0 | 0 | -37062.28 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator 1000 kW |  | 1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 56 | 56 | 100% | 0% | 0% | 100% | 37062.28 | 0 | 0 | 37062.28 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Conveyors |  | 3 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 504 | 5550 | 44422.56 | 61214.28 | 111186.84 | 56 | 168 | 100% | 0% | 0% | 100% | 111186.84 | 0 | 0 | 111186.84 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 111186.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw crusher unit |  | -1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | -168 | -1850 | -14807.52 | -20404.76 | -37062.28 | 56 | -56 | 100% | 0% | 0% | 100% | -37062.28 | 0 | 0 | -37062.28 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Jaw crusher unit |  | 1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 56 | 56 | 100% | 0% | 0% | 100% | 37062.28 | 0 | 0 | 37062.28 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screener + Cone crusher unit |  | 1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 56 | 56 | 100% | 0% | 0% | 100% | 37062.28 | 0 | 0 | 37062.28 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Generator Sets |  | 1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 56 | 56 | 100% | 0% | 0% | 100% | 37062.28 | 0 | 0 | 37062.28 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 141 | SA- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Bucket Wheel Stacker Reclaimer |  | -2 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | -336 | -3700 | -29615.04 | -40809.52 | -74124.56 | 56 | -112 | 100% | 0% | 0% | 100% | -74124.56 | 0 | 0 | -74124.56 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -74124.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 600kw Generators |  | -2 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | -38.4 | -355 | -3384.576 | -3915.508 | -7655.084 | 1 | -2 | 100% | 0% | 0% | 100% | -7655.084 | 0 | 0 | -7655.084 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -7655.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 60kw Generator |  | -3 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | -57.6 | -532.5 | -5076.864 | -5873.262 | -11482.626 | 1 | -3 | 100% | 0% | 0% | 100% | -11482.626 | 0 | 0 | -11482.626 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -11482.626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Atlas 1000 mVA Transformers |  | -4 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | -76.8 | -710 | -6769.152 | -7831.016 | -15310.168 | 1 | -4 | 100% | 0% | 0% | 100% | -15310.168 | 0 | 0 | -15310.168 | Type A 2AM-MRY1325 | Removed | 2021-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -15310.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 600kw Generators |  | 2 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 38.4 | 355 | 3384.576 | 3915.508 | 7655.084 | 1 | 2 | 100% | 0% | 0% | 100% | 7655.084 | 0 | 0 | 7655.084 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7655.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 60kw Generator |  | 3 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 57.6 | 532.5 | 5076.864 | 5873.262 | 11482.626 | 1 | 3 | 100% | 0% | 0% | 100% | 11482.626 | 0 | 0 | 11482.626 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 11482.626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Atlas 1000 mVA Transformers |  | 4 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 76.8 | 710 | 6769.152 | 7831.016 | 15310.168 | 1 | 4 | 100% | 0% | 0% | 100% | 15310.168 | 0 | 0 | 15310.168 | Type A 2AM-MRY1325 | Added | 2020 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 15310.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light ERT utility vehicle |  | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Portable water pump |  | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Pickup truck (F350 or similar) |  | -7 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -46.6667 | -145.8333 | -4113.2 | -1608.4833 | -5867.5167 | 4 | -28 | 100% | 0% | 0% | 100% | -5867.5167 | 0 | 0 | -5867.5167 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -5867.5167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F-350 Pickup | 2021-3 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F-350 Pickup | 2021-14 2021-15 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F-350 Pickup | 2021-26 2021-55 | 4 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 26.6667 | 83.3333 | 2350.4 | 919.1333 | 3352.8667 | 4 | 8 | 100% | 0% | 0% | 100% | 3352.8667 | 0 | 0 | 3352.8667 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3352.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift z60 |  | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Manlift s135x |  | -3 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -20 | -62.5 | -1762.8 | -689.35 | -2514.65 | 4 | -12 | 100% | 0% | 0% | 100% | -2514.65 | 0 | 0 | -2514.65 | Type A 2AM-MRY1325 | Added | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2514.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Shovel 6060 | 2021-39 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Heated Water Truck - Drill Water System | 2021-50 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Pumper fire truck |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 922K Wheel Loader |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator | 2021-41 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator | 2021-41 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390 Excavator | 2021-44 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 390 Excavator | 2021-44 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker | 2021-32 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker | 2021-32 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck | 2021-33 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A Truck | 2021-33 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793F Haul Truck | 2021-42 | 3 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 39 | 300 | 3437.46 | 3308.88 | 7046.34 | 96 | 288 | 100% | 0% | 0% | 100% | 7046.34 | 0 | 0 | 7046.34 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7046.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 793F Haul Truck | 2021-42 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer |  | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer | 2021-40 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Tripper Car | 2021-51 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Water Truck | 2021-47 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Zoom Boom 12,000 lbs |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus |  | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 4x4 hotseating bus | 2021-49 | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Boom Truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Flat Bed Boom Truck | 2021-19 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Pressure washing truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 Person School Bus | 2021-35 | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | 48 Person School Bus | 2021-35 | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube truck | 2021-34 | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Spreader Box | 2021-46 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Spare 793 Box | 2021-43 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Spare 793 Box | 2021-43 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Vac Truck | 2021-38 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740 Water Truck | 2021-30 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 740 Water Truck | 2021-30 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M Grader | 2021-31 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 14M Grader | 2021-31 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 CATERPILLAR LOADER | 2021-2 | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 908 CATERPILLAR LOADER | 2021-2 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Epiroc D65 Drill | 2021-45 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | F550 Service/Fuel Truck | 2021-37 | 4 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 40 | 150 | 3525.6 | 1654.44 | 5330.04 | 24 | 96 | 100% | 0% | 0% | 100% | 5330.04 | 0 | 0 | 5330.04 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 5330.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Service Truck |  | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Service Truck |  | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | CCM200E Concrete Mixer | 2021-29 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Decommissioned vehicles |  | -3 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -20 | -62.5 | -1762.8 | -689.35 | -2514.65 | 4 | -12 | 100% | 0% | 0% | 100% | -2514.65 | 0 | 0 | -2514.65 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2514.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | HAGGLUNDS SNOW RESCUE VEHICLE |  | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Land Cruiser Service Truck | 2021-28 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle | 2021-17 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle | 2021-17 | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light Vehicles | 2021-48 | 8 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 53.3333 | 166.6667 | 4700.8 | 1838.2667 | 6705.7333 | 4 | 32 | 100% | 0% | 0% | 100% | 6705.7333 | 0 | 0 | 6705.7333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 6705.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER | 2021-4 | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Removed | 2021-D | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER | 2021-4 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | SKID STEER - 257D | 2021-27 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Case TV-380 Skidsteer | 2021-54 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 705 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | Welding Shop Crane | 2021-23 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | Steam Truck | 2021-36 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2021-d | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | Steam Truck | 2021-36 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | SPYDER CRANE URW295 | 2021-25 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | SPYDER CRANE URW706 | 2021-24 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | BAE | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Screen Metso FS353 |  | -1 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | -168 | -1850 | -14807.52 | -20404.76 | -37062.28 | 56 | -56 | 100% | 0% | 0% | 100% | -37062.28 | 0 | 0 | -37062.28 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -37062.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | 1500 kW Alternators | 2021-1 | 2 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 38.4 | 355 | 3384.576 | 3915.508 | 7655.084 | 1 | 2 | 100% | 0% | 0% | 100% | 7655.084 | 0 | 0 | 7655.084 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7655.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Power plant generators | Gensets/compressors for field maintenance | 2021-16 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 2 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2021 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Frost Fighter Heater |  | -6 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -40 | -125 | -3525.6 | -1378.7 | -5029.3 | 4 | -24 | 100% | 0% | 0% | 100% | -5029.3 | 0 | 0 | -5029.3 | Type A 2AM-MRY1325 | Removed | 2020-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -5029.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Frost Fighter Heater | 2021-59 | 9 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 60 | 187.5 | 5288.4 | 2068.05 | 7543.95 | 4 | 36 | 100% | 0% | 0% | 100% | 7543.95 | 0 | 0 | 7543.95 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7543.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A truck | E-1 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker | E-2 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Jet A truck | E-1 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Fuel Tanker | E-2 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube Truck | E-3 | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Cube Truck | E-3 | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | -48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Bus | E-4 | 2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 20 | 75 | 1762.8 | 827.22 | 2665.02 | 24 | 48 | 100% | 0% | 0% | 100% | 2665.02 | 0 | 0 | 2665.02 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Bus | E-4 | -2 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -20 | -75 | -1762.8 | -827.22 | -2665.02 | 24 | -48 | 100% | 0% | 0% | 100% | -2665.02 | 0 | 0 | -2665.02 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2665.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 18M Graders | E-7 | 3 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 39 | 300 | 3437.46 | 3308.88 | 7046.34 | 96 | 288 | 100% | 0% | 0% | 100% | 7046.34 | 0 | 0 | 7046.34 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7046.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 18M Graders | E-7 | -3 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -39 | -300 | -3437.46 | -3308.88 | -7046.34 | 96 | -288 | 100% | 0% | 0% | 100% | -7046.34 | 0 | 0 | -7046.34 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -7046.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light Vehicles (F-250 or similar) | E-8 | 9 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 60 | 187.5 | 5288.4 | 2068.05 | 7543.95 | 4 | 36 | 100% | 0% | 0% | 100% | 7543.95 | 0 | 0 | 7543.95 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 7543.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Dewatering Pumps | E-9 | 3 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 24.3 | 266.25 | 2141.802 | 2936.631 | 5344.683 | 0.5 | 1.5 | 100% | 0% | 0% | 100% | 5344.683 | 0 | 0 | 5344.683 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 5344.683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Dewatering Pumps | E-9 | -3 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -24.3 | -266.25 | -2141.802 | -2936.631 | -5344.683 | 0.5 | -1.5 | 100% | 0% | 0% | 100% | -5344.683 | 0 | 0 | -5344.683 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -5344.683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Production Drill | E-11 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Production Drill | E-11 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992 Loader | E-12 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 992 Loader | E-12 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator | E-13 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 374 Excavator | E-13 | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | -192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer | E-14 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | D10 Dozer | E-14 | -1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -13 | -100 | -1145.82 | -1102.96 | -2348.78 | 96 | -96 | 100% | 0% | 0% | 100% | -2348.78 | 0 | 0 | -2348.78 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam Truck | E-15 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Steam Truck | E-15 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Lowboy Float | E-16 | 1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 24 | 24 | 100% | 0% | 0% | 100% | 1332.51 | 0 | 0 | 1332.51 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Lowboy Float | E-16 | -1 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -10 | -37.5 | -881.4 | -413.61 | -1332.51 | 24 | -24 | 100% | 0% | 0% | 100% | -1332.51 | 0 | 0 | -1332.51 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1332.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers | Container | Lube / Def Container | E-18 | 29.729 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | 3.3321 | 41.6515 | 293.6931 | 459.3995 | 794.7442 | 1 | 29.729 | 100% | 0% | 0% | 100% | 794.7442 | 0 | 0 | 794.7442 | Type A 2AM-MRY1325 |  | 2022 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 397.3721 | 397.3721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | FF4 | ISO Container | FC | Buildings (Not Contaminated) | ISO Shipping Containers | Container | Lube / Def Container | E-18 | -29.729 | m2 | 0.11208 | 1.401 | 9.879 | 15.4529 | 26.733 | -3.3321 | -41.6515 | -293.6931 | -459.3995 | -794.7442 | 1 | -29.729 | 100% | 0% | 0% | 100% | -794.7442 | 0 | 0 | -794.7442 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | -397.3721 | -397.3721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Hydraulic Ripper | E-19 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Hydraulic Ripper | E-19 | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Ford 15 Passenger Vans (or similar) | E-20 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Ford 15 Passenger Vans (or similar) | E-20 | -2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -13.3333 | -41.6667 | -1175.2 | -459.5667 | -1676.4333 | 4 | -8 | 100% | 0% | 0% | 100% | -1676.4333 | 0 | 0 | -1676.4333 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | All Terrain Vehicle (Prinoth or similar) | E-21 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | All Terrain Vehicle (Prinoth or similar) | E-21 | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Skid steer (for drilling support) | E-22 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Large Water Pump | E-23 | 2 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 16.2 | 177.5 | 1427.868 | 1957.754 | 3563.122 | 0.5 | 1 | 100% | 0% | 0% | 100% | 3563.122 | 0 | 0 | 3563.122 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3563.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Commissioning of small mobile gensets ranging in size from 20kW - 60kW | E-24 | 10 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 66.6667 | 208.3333 | 5876 | 2297.8333 | 8382.1667 | 4 | 40 | 100% | 0% | 0% | 100% | 8382.1667 | 0 | 0 | 8382.1667 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 8382.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Type 1 E-House | E-25 | 1 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 1 | 1 | 100% | 0% | 0% | 100% | 3827.542 | 0 | 0 | 3827.542 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3827.542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Type 3 E-House | E-26 | 1 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 1 | 1 | 100% | 0% | 0% | 100% | 3827.542 | 0 | 0 | 3827.542 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3827.542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Hydraulic Hammer (7 tonnes) | E-27 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | 777 Fuel & Lube body | E-28 | 1 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 96 | 96 | 100% | 0% | 0% | 100% | 2348.78 | 0 | 0 | 2348.78 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2348.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Snowmobile | E-29 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle | E-32 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Snowmobile | E-30 | 2 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 13.3333 | 41.6667 | 1175.2 | 459.5667 | 1676.4333 | 4 | 8 | 100% | 0% | 0% | 100% | 1676.4333 | 0 | 0 | 1676.4333 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1676.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Side by Side | E-31 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Side by Side | E-31 | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Service Truck | E-5 | 4 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 40 | 150 | 3525.6 | 1654.44 | 5330.04 | 24 | 96 | 100% | 0% | 0% | 100% | 5330.04 | 0 | 0 | 5330.04 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 5330.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Service Truck | E-5 | -4 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -40 | -150 | -3525.6 | -1654.44 | -5330.04 | 24 | -96 | 100% | 0% | 0% | 100% | -5330.04 | 0 | 0 | -5330.04 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -5330.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Vac Truck | E-6 | 2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 26 | 200 | 2291.64 | 2205.92 | 4697.56 | 96 | 192 | 100% | 0% | 0% | 100% | 4697.56 | 0 | 0 | 4697.56 | Type A 2AM-MRY1325 | Added | 2022 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Vac Truck | E-6 | -2 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -26 | -200 | -2291.64 | -2205.92 | -4697.56 | 96 | -192 | 100% | 0% | 0% | 100% | -4697.56 | 0 | 0 | -4697.56 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -4697.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F350 Pickup backhauled off site |  | -1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -6.6667 | -20.8333 | -587.6 | -229.7833 | -838.2167 | 4 | -4 | 100% | 0% | 0% | 100% | -838.2167 | 0 | 0 | -838.2167 | Type A 2AM-MRY1325 | Removed | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | F250 Light Vehicle |  | 10 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 66.6667 | 208.3333 | 5876 | 2297.8333 | 8382.1667 | 4 | 40 | 100% | 0% | 0% | 100% | 8382.1667 | 0 | 0 | 8382.1667 | Type A 2AM-MRY1325 | Added | 2023-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 8382.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Runway traffic control gate arms | E-1 | 1 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1781.561 | 0 | 0 | 1781.561 | Type A 2AM-MRY1325 | Added | 2023 | Direct |  |  | 100% | [10 empty] | 0 | 0 | 1781.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Zinex A5 Diamond Drills | 2021-52 | 5 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 40.5 | 443.75 | 3569.67 | 4894.385 | 8907.805 | 0.5 | 2.5 | 100% | 0% | 0% | 100% | 8907.805 | 0 | 0 | 8907.805 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 8907.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Bean model 435 Water Pumps | 2021-53 | 10 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 81 | 887.5 | 7139.34 | 9788.77 | 17815.61 | 0.5 | 5 | 100% | 0% | 0% | 100% | 17815.61 | 0 | 0 | 17815.61 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 17815.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie Skylift Z-135 | 2021-56 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie S85 | 2021-57 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Genie S125 | 2021-58 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Yukon 14ft Boat | 2021-60 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Boat Trailer | 2021-61 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Trailer | 2021-62 | 1 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 4 | 4 | 100% | 0% | 0% | 100% | 838.2167 | 0 | 0 | 838.2167 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 838.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Equipment (2021 Equipment Audit) |  | -216 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | -1749.6 | -19170 | -154209.744 | -211437.432 | -384817.176 | 0.5 | -108 | 100% | 0% | 0% | 100% | -384817.176 | 0 | 0 | -384817.176 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -384817.176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Medium Equipment (2021 Equipment Audit) |  | -185 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | -3552 | -32837.5 | -313073.28 | -362184.49 | -708095.27 | 1 | -185 | 100% | 0% | 0% | 100% | -708095.27 | 0 | 0 | -708095.27 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -708095.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Heavy Equipment (2021 Equipment Audit) |  | -85 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | -14280 | -157250 | -1258639.2 | -1734404.6 | -3150293.8 | 56 | -4760 | 100% | 0% | 0% | 100% | -3150293.8 | 0 | 0 | -3150293.8 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -3150293.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light Mobile Equipment (2021 Equipment Audit) |  | -308 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | -2053.3333 | -6416.6667 | -180980.8 | -70773.2667 | -258170.7333 | 4 | -1232 | 100% | 0% | 0% | 100% | -258170.7333 | 0 | 0 | -258170.7333 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -258170.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Medium Mobile Equipment (2021 Equipment Audit) |  | -344 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | -3440 | -12900 | -303201.6 | -142281.84 | -458383.44 | 24 | -8256 | 100% | 0% | 0% | 100% | -458383.44 | 0 | 0 | -458383.44 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -458383.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Mobile Equipment (2021 Equipment Audit) |  | -308 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | -4004 | -30800 | -352912.56 | -339711.68 | -723424.24 | 96 | -29568 | 100% | 0% | 0% | 100% | -723424.24 | 0 | 0 | -723424.24 | Type A 2AM-MRY1325 | Removed | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | -723424.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | MM1 | Light Equipment | MM1 | Mechanical Equipment | Light Equipment |  | Light Equipment (2021 Equipment Audit) |  | 238 | Ea | 8.1 | 88.75 | 713.934 | 978.877 | 1781.561 | 1927.8 | 21122.5 | 169916.292 | 232972.726 | 424011.518 | 0.5 | 119 | 100% | 0% | 0% | 100% | 424011.518 | 0 | 0 | 424011.518 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 424011.518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Medium Equipment (2021 Equipment Audit) |  | 552 | Ea | 19.2 | 177.5 | 1692.288 | 1957.754 | 3827.542 | 10598.4 | 97980 | 934142.976 | 1080680.208 | 2112803.184 | 1 | 552 | 100% | 0% | 0% | 100% | 2112803.184 | 0 | 0 | 2112803.184 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 2112803.184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment |  | Heavy Equipment (2021 Equipment Audit) |  | 97 | Ea | 168 | 1850 | 14807.52 | 20404.76 | 37062.28 | 16296 | 179450 | 1436329.44 | 1979261.72 | 3595041.16 | 56 | 5432 | 100% | 0% | 0% | 100% | 3595041.16 | 0 | 0 | 3595041.16 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 3595041.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment |  | Light Mobile Equipment (2021 Equipment Audit) |  | 291 | Ea | 6.6667 | 20.8333 | 587.6 | 229.7833 | 838.2167 | 1940 | 6062.5 | 170991.6 | 66866.95 | 243921.05 | 4 | 1164 | 100% | 0% | 0% | 100% | 243921.05 | 0 | 0 | 243921.05 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 243921.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | Medium Mobile Equipment (2021 Equipment Audit) |  | 329 | Ea | 10 | 37.5 | 881.4 | 413.61 | 1332.51 | 3290 | 12337.5 | 289980.6 | 136077.69 | 438395.79 | 24 | 7896 | 100% | 0% | 0% | 100% | 438395.79 | 0 | 0 | 438395.79 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 438395.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | Baffinland Owned Equipment | 5100 | Project Wide | 5140 | Mobile Equipment | 5140 | Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | Heavy Mobile Equipment (2021 Equipment Audit) |  | 237 | Ea | 13 | 100 | 1145.82 | 1102.96 | 2348.78 | 3081 | 23700 | 271559.34 | 261401.52 | 556660.86 | 96 | 22752 | 100% | 0% | 0% | 100% | 556660.86 | 0 | 0 | 556660.86 | Type A 2AM-MRY1325 | Added | 2022-R | Direct |  |  | 100% | [10 empty] | 0 | 0 | 556660.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas
6000 | Disturbed Areas | 6100 | Project Wide
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area Reconciliation - 2022 Satellite Image - IOL |  | 5754373.2321 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 73033.8335 | 841577.0852 | 6437202.0852 | 2310483.5439 | 9589262.7144 | 0 | 0 | 100% | 0% | 0% | 100% | 9589262.7144 | 0 | 0 | 9589262.7144 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3196420.9048 | 3196420.9048 | 3196420.9048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area Reconciliation - 2023 Work Plan Satellite Image - IOL |  | 639477.6601 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 8116.1758 | 93523.6078 | 715359.7378 | 256761.6925 | 1065645.0381 | 0 | 0 | 100% | 0% | 0% | 100% | 1065645.0381 | 0 | 0 | 1065645.0381 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 355215.0127 | 355215.0127 | 355215.0127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2023 - IOL |  | -6019626 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -76400.3907 | -880370.3025 | -6733930.4346 | -2416987.2639 | -10031288.001 | 0 | 0 | 100% | 0% | 0% | 100% | -10031288.001 | 0 | 0 | -10031288.001 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3343762.667 | -3343762.667 | -3343762.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Actual Lined Disturbed Area - 2022 Satellite Image - IOL |  | 147217.4467 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 6549.9815 | 25041.6877 | 577315.3656 | 100373.3035 | 702730.3569 | 0 | 0 | 100% | 0% | 0% | 100% | 702730.3569 | 0 | 0 | 702730.3569 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 234243.4523 | 234243.4523 | 234243.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Proposed Lined Disturbed Area - 2023 Work Plan and Prior - Sat Image - IOL |  | 55011.3256 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 2447.5575 | 9357.4265 | 215727.7163 | 37506.8894 | 262592.0321 | 0 | 0 | 100% | 0% | 0% | 100% | 262592.0321 | 0 | 0 | 262592.0321 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 87530.6774 | 87530.6774 | 87530.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Reconciled EBS Input 2014-2023 - Lined - IOL |  | -165480 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -7362.5168 | -28148.148 | -648932.235 | -112824.768 | -789905.151 | 0 | 0 | 100% | 0% | 0% | 100% | -789905.151 | 0 | 0 | -789905.151 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -263301.717 | -263301.717 | -263301.717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area - 2022 Satellite Image - Crown Land |  | 145183.0283 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1842.6461 | 21233.0179 | 162410.823 | 58293.5768 | 241937.4176 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 241937.4176 | 0 | 241937.4176 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 80645.8059 | 80645.8059 | 80645.8059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area - 2023 Work Plan and Prior Sat Image - Crown Land |  | 0 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2023 - Crown |  | -190345 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -2415.8365 | -27837.9562 | -212931.8314 | -76426.9144 | -317196.702 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -317196.702 | 0 | -317196.702 | Type A 2AM-MRY1325 | added | 2023-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -105732.234 | -105732.234 | -105732.234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area Reconciliation - 2021 Satellite Image - IOL |  | 5581347.4768 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 70837.8108 | 816272.0685 | 6243644.645 | 2241010.6154 | 9300927.3289 | 0 | 0 | 100% | 0% | 0% | 100% | 9300927.3289 | 0 | 0 | 9300927.3289 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 3100309.1096 | 3100309.1096 | 3100309.1096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area Reconciliation - 2022 Work Plan and Prior - IOL |  | 1230757 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 15620.6242 | 179998.2112 | 1376801.8179 | 494170.8993 | 2050970.9285 | 0 | 0 | 100% | 0% | 0% | 100% | 2050970.9285 | 0 | 0 | 2050970.9285 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 683656.9762 | 683656.9762 | 683656.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2022 - IOL |  | -6051446.44 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -76804.252 | -885024.0419 | -6769526.7705 | -2429763.7384 | -10084314.5508 | 0 | 0 | 100% | 0% | 0% | 100% | -10084314.5508 | 0 | 0 | -10084314.5508 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -3361438.1836 | -3361438.1836 | -3361438.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Actual Lined Disturbed Area - 2021 Satellite Image - IOL |  | 149711 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 6660.9243 | 25465.8411 | 587093.8713 | 102073.4158 | 714633.1282 | 0 | 0 | 100% | 0% | 0% | 100% | 714633.1282 | 0 | 0 | 714633.1282 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 238211.0427 | 238211.0427 | 238211.0427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Proposed Lined Disturbed Area - 2022 Work Plan and Prior - IOL |  | 32683 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 1454.1282 | 5559.3783 | 128166.8615 | 22283.3689 | 156009.6087 | 0 | 0 | 100% | 0% | 0% | 100% | 156009.6087 | 0 | 0 | 156009.6087 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 52003.2029 | 52003.2029 | 52003.2029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Reconciled EBS Input 2014-2022 - Lined - IOL |  | -173862 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -7735.4478 | -29573.9262 | -681802.3703 | -118539.6411 | -829915.9376 | 0 | 0 | 100% | 0% | 0% | 100% | -829915.9376 | 0 | 0 | -829915.9376 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -276638.6459 | -276638.6459 | -276638.6459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area - 2021 Satellite Image - Crown Land |  | 144600.0164 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1835.2465 | 21147.7524 | 161758.6294 | 58059.4871 | 240965.8689 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 240965.8689 | 0 | 240965.8689 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 80321.9563 | 80321.9563 | 80321.9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area - 2022 Work Plan and Prior - Crown Land |  | 332245 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 4216.8148 | 48590.8312 | 371670.0535 | 133402.2967 | 553663.1814 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 553663.1814 | 0 | 553663.1814 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 184554.3938 | 184554.3938 | 184554.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2022 - Crown |  | -475549 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -6035.6124 | -69549.0412 | -531978.8778 | -190941.41 | -792469.3291 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -792469.3291 | 0 | -792469.3291 | Type A 2AM-MRY1325 | added | 2022-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -264156.443 | -264156.443 | -264156.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area Reconciliation - 2020 Satellite Image - IOL |  | 5307266 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 67359.2007 | 776187.6525 | 5937039.9493 | 2130962.0113 | 8844189.6131 | 0 | 0 | 100% | 0% | 0% | 100% | 8844189.6131 | 0 | 0 | 8844189.6131 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2948063.2044 | 2948063.2044 | 2948063.2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area Reconciliation - 2021 Work Plan and Prior - IOL |  | 3160642 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 40114.4994 | 462243.8925 | 3535691.9776 | 1269054.1671 | 5266990.0372 | 0 | 0 | 100% | 0% | 0% | 100% | 5266990.0372 | 0 | 0 | 5266990.0372 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1755663.3457 | 1755663.3457 | 1755663.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2021 - IOL |  | -8355237 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -106043.6929 | -1221953.4112 | -9346691.0938 | -3354776.7612 | -13923421.2662 | 0 | 0 | 100% | 0% | 0% | 100% | -13923421.2662 | 0 | 0 | -13923421.2662 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -4641140.4221 | -4641140.4221 | -4641140.4221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Reconciled EBS Input 2014-2021 - Crown |  | -362320 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | -4598.5232 | -52989.3 | -405313.831 | -145477.9459 | -603781.0768 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | -603781.0768 | 0 | -603781.0768 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -201260.3589 | -201260.3589 | -201260.3589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Actual Disturbed Area - 2020 Satellite Image - Crown Land |  | 143305 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 1818.8103 | 20958.3562 | 160309.943 | 57539.5149 | 238807.8141 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 238807.8141 | 0 | 238807.8141 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 79602.6047 | 79602.6047 | 79602.6047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Proposed Disturbed Area - 2021 Work Plan and Prior - Crown Land |  | 332244 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 4216.8021 | 48590.685 | 371668.9348 | 133401.8952 | 553661.5149 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 553661.5149 | 0 | 553661.5149 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 184553.8383 | 184553.8383 | 184553.8383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6110 | Actual Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Actual Lined Disturbed Area - 2020 Satellite Image - IOL |  | 114884 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 5111.4055 | 19541.7684 | 450519.2826 | 78328.2611 | 548389.3121 | 0 | 0 | 100% | 0% | 0% | 100% | 548389.3121 | 0 | 0 | 548389.3121 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 182796.4374 | 182796.4374 | 182796.4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Proposed Lined Disturbed Area - 2021 Work Plan and Prior - IOL |  | 15714 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 699.1455 | 2672.9514 | 61622.6803 | 10713.8531 | 75009.4848 | 0 | 0 | 100% | 0% | 0% | 100% | 75009.4848 | 0 | 0 | 75009.4848 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25003.1616 | 25003.1616 | 25003.1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | Disturbed Areas | 6100 | Project Wide | 6110 | Site Development | 6120 | Proposed Disturbed Area |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner | Grade and Contour | Reconciled EBS Input 2014-2021 - Lined - IOL |  | -219252 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | -9754.9344 | -37294.7652 | -859799.9177 | -149486.6814 | -1046581.3643 | 0 | 0 | 100% | 0% | 0% | 100% | -1046581.3643 | 0 | 0 | -1046581.3643 | Type A 2AM-MRY1325 | added | 2021-R | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | -348860.4548 | -348860.4548 | -348860.4548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services
7000 | Construction Facilities & Services | 7200 | Milne Port
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Existing Trailer Camp (Shanco) |  | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | 49-person Hard Wall Trailer Camp (previously at Steensby) |  | 950 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 212.9583 | 2661.9792 | 18770.1475 | 29360.5654 | 50792.6921 | 1 | 950 | 100% | 0% | 0% | 100% | 50792.6921 | 0 | 0 | 50792.6921 | Type A 2AM-MRY1325 | Modified (2017A) | 2017 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 50792.6921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Matrix Camp |  | 5392.34 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 967.0263 | 12087.8288 | 85233.6987 | 133323.9169 | 230645.4444 | 0.5 | 2696.17 | 100% | 0% | 0% | 100% | 230645.4444 | 0 | 0 | 230645.4444 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 76881.8148 | 76881.8148 | 76881.8148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tents |  | 0 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 1252.363 | m2 | 0.58283 | 2.2417 | 56.1215 | 80.3552 | 138.7184 | 729.9189 | 2807.3804 | 70284.4766 | 100633.919 | 173725.776 | 0.5 | 626.1815 | 100% | 0% | 0% | 100% | 173725.776 | 0 | 0 | 173725.776 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 57908.592 | 57908.592 | 57908.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Toromont Maintenance Workshops soft (Contaminated) |  | 878.1618 | m2 | 0.58283 | 2.2417 | 56.1215 | 80.3552 | 138.7184 | 511.822 | 1968.546 | 49283.748 | 70564.8949 | 121817.1889 | 0.5 | 439.0809 | 100% | 0% | 0% | 100% | 121817.1889 | 0 | 0 | 121817.1889 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 40605.7296 | 40605.7296 | 40605.7296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 250.24 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 140.2387 | 490.8353 | 12360.6361 | 19334.705 | 32186.1764 | 1 | 250.24 | 100% | 0% | 0% | 100% | 32186.1764 | 0 | 0 | 32186.1764 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 32186.1764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD |  | #N/A |  |  |  |  | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7234-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD |  | #N/A |  |  |  |  | Construction Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Workshop - Demolish floor finish - Gravel | 7234-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 56.1215 | 80.3552 | 138.7184 | 1192.477 | 4586.45 | 114824.5669 | 164406.804 | 283817.8209 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 283817.8209 | 0 | 0 | 283817.8209 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 94605.9403 | 94605.9403 | 94605.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7234 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 255.75 | 3836.25 | 22541.805 | 38362.5 | 64740.555 | 0 | 0 | 100% | 0% | 0% | 100% | 64740.555 | 0 | 0 | 64740.555 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 64740.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1222 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Construction Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 7231-BLD-001 | 267.658 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 60 | 750 | 5288.4 | 8272.2 | 14310.6 | 1 | 267.658 | 100% | 0% | 0% | 100% | 14310.6 | 0 | 0 | 14310.6 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4770.2 | 4770.2 | 4770.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1230 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7231-TK-001 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1225 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single | 7231-BLD-002 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1231 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | 7231-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1226 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Aerodrome Office - Demolish and foundations - Timber Cribbing to Elevate Building | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1227 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Aerodrome Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-002 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1223 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Office - Demolish and foundations - Gravel Base - Skidded Building | 7231-BLD-001 | 267.658 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1224 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Construction Office - Demolish floor finish - Raised Steel or Wooden Floor | 7231-BLD-001 | 267.658 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 33 | 262.5 | 1850.94 | 2895.27 | 5008.71 | 0.3 | 80.2974 | 100% | 0% | 0% | 100% | 5008.71 | 0 | 0 | 5008.71 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1669.57 | 1669.57 | 1669.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 13006.6038 | 23619.8113 | 94.3396 | 1179.2453 | 9433.9623 | 13006.6038 | 23619.8113 | 0 | 0 | 100% | 0% | 0% | 100% | 23619.8113 | 0 | 0 | 23619.8113 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7873.2704 | 7873.2704 | 7873.2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1286 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Heated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-002 | 371.7472 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 58.3333 | 729.1667 | 5141.5 | 8042.4167 | 13913.0833 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 13913.0833 | 0 | 0 | 13913.0833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4637.6944 | 4637.6944 | 4637.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1289 | BLD | FF2 | Fold Away Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-003 | 371.7472 | m2 | 0.15692 | 1.9615 | 13.8306 | 21.6341 | 37.4262 | 58.3333 | 729.1667 | 5141.5 | 8042.4167 | 13913.0833 | 1 | 371.7472 | 100% | 0% | 0% | 100% | 13913.0833 | 0 | 0 | 13913.0833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4637.6944 | 4637.6944 | 4637.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1287 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Heated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-002 | 371.7472 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 53.98 | 674.7505 | 4757.801 | 7442.2285 | 12874.78 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 12874.78 | 0 | 0 | 12874.78 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4291.5933 | 4291.5933 | 4291.5933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1290 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-003 | 371.7472 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 53.98 | 674.7505 | 4757.801 | 7442.2285 | 12874.78 | 0.75 | 278.8104 | 100% | 0% | 0% | 100% | 12874.78 | 0 | 0 | 12874.78 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 4291.5933 | 4291.5933 | 4291.5933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1283 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 32.388 | 404.8503 | 2854.6806 | 4465.3371 | 7724.868 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 7724.868 | 0 | 0 | 7724.868 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2574.956 | 2574.956 | 2574.956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1284 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Construction Equipment Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-001 | 223.0483 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 32.388 | 404.8503 | 2854.6806 | 4465.3371 | 7724.868 | 0.75 | 167.2862 | 100% | 0% | 0% | 100% | 7724.868 | 0 | 0 | 7724.868 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2574.956 | 2574.956 | 2574.956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1285 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Construction Equipment Building - Demolish floor finish - Gravel | 7235-BLD-001 | 223.0483 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Hold/ Remove | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1288 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Heated Warehouse - Demolish floor finish - Gravel | 7235-BLD-002 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 1291 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-003 | 371.7472 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-004 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-004 | 0 | m2 | 0.14521 | 1.8151 | 12.7985 | 20.0196 | 34.6332 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-004 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1271 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-004 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1254 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-009 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1257 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-010 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1272 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1269 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-001 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1273 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7232-TK-007 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 964.8358 | 964.8358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1274 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7232-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1255 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1258 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1239 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1248 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-007 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1251 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-008 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1242 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Office - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-005 | 44.6097 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 10 | 125 | 881.4 | 1378.7 | 2385.1 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2385.1 | 0 | 0 | 2385.1 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1245 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-006 | 44.6097 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 10 | 125 | 881.4 | 1378.7 | 2385.1 | 1 | 44.6097 | 100% | 0% | 0% | 100% | 2385.1 | 0 | 0 | 2385.1 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1270 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7232-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Washcar - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-002 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Washcar - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Quarry Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1260 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7232-BLD-011 | 14.8699 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 8.3333 | 41.6667 | 734.5 | 1148.9167 | 1925.0833 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1925.0833 | 0 | 0 | 1925.0833 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.6944 | 641.6944 | 641.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1240 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1249 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-007 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1252 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7232-BLD-008 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Quarry Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7232-BLD-001 | 0 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Quarry Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities |  | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Quarry Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-001 | 0 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1256 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-009 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1259 | BLD | FW | Timber Cribbing (480 ft2) | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-010 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1261 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1262 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-011 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1243 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Office - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1244 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Office - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-005 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1246 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Fuel Systems Lunchroom - Demolish and foundations - Gravel Base - Skidded Building | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1247 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-006 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1241 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1250 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-007 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1253 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7232-BLD-008 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1372 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 375 | 1312.5 | 33052.5 | 51701.25 | 86066.25 | 1 | 669.145 | 100% | 0% | 0% | 100% | 86066.25 | 0 | 0 | 86066.25 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 28688.75 | 28688.75 | 28688.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1373 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7251-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 375 | 1312.5 | 33052.5 | 51701.25 | 86066.25 | 1 | 669.145 | 100% | 0% | 0% | 100% | 86066.25 | 0 | 0 | 86066.25 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 28688.75 | 28688.75 | 28688.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Batch Plant Stockpile |  | 5180.44 | m2 | 0.012692 | 0.14625 | 1.1187 | 0.40152 | 1.6649 | 65.7495 | 757.6393 | 5795.1644 | 2080.0391 | 8632.8429 | 0 | 0 | 100% | 0% | 0% | 100% | 8632.8429 | 0 | 0 | 8632.8429 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2877.6143 | 2877.6143 | 2877.6143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities | 1374 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7251-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7250 | Construction Facilities | 7251 | Concrete Facilities |  |  |  | #N/A |  |  |  | Batch Plant Building | Batch Plant Building |  | 3281.62 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 43.8396 | 167.6063 | 3864.0252 | 671.8078 | 4703.4393 | 0 | 0 | 100% | 0% | 0% | 100% | 4703.4393 | 0 | 0 | 4703.4393 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1567.8131 | 1567.8131 | 1567.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Lined Storage Area |  | 985.34 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 43.8396 | 167.6063 | 3864.0252 | 671.8078 | 4703.4393 | 0 | 0 | 100% | 0% | 0% | 100% | 4703.4393 | 0 | 0 | 4703.4393 | Type B Construction 2BC-MRY1416 | Check | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1567.8131 | 1567.8131 | 1567.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bladder Farm Decommissioning |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Hazardous Waste Berm |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  |  | #N/A |  |  |  |  | Old STP (RBC) |  | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7300 | Tote Road
7000 | Construction Facilities & Services | 7400 | Mine Site
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Exploration Tent Camp Pad |  | 9432.14 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 1179.0175 | 17685.2625 | 103918.6024 | 176852.625 | 298456.4899 | 0 | 0 | 100% | 0% | 0% | 100% | 298456.4899 | 0 | 0 | 298456.4899 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 298456.4899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Soft-Wall Camp (Weatherhaven) |  | 6017.14 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 1079.0738 | 13488.4222 | 95109.5624 | 148771.9011 | 257369.8857 | 0.5 | 3008.57 | 100% | 0% | 0% | 100% | 257369.8857 | 0 | 0 | 257369.8857 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 257369.8857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp |  | BLD | FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | FF3 | Buildings (Not Contaminated) | Soft walled Building (tent) |  | Exploration Tent Camp Tents |  | 2400 | m2 | 0.17933 | 2.2417 | 15.8064 | 24.7247 | 42.7728 | 430.4 | 5380 | 37935.456 | 59339.248 | 102654.704 | 0.5 | 1200 | 100% | 0% | 0% | 100% | 102654.704 | 0 | 0 | 102654.704 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 102654.704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  |  | #N/A | VP7 | Packaged Facilities |  |  | Exploration STP |  | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Exploration Workshops |  | 182.2 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 102.1079 | 357.3777 | 8999.7918 | 14077.6185 | 23434.788 | 1 | 182.2 | 100% | 0% | 0% | 100% | 23434.788 | 0 | 0 | 23434.788 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 23434.788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | FF3-c | Buildings (Contaminated) | Soft walled Building (tent) |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.58283 | 2.2417 | 56.1215 | 80.3552 | 138.7184 | 1192.477 | 4586.45 | 114824.5669 | 164406.804 | 283817.8209 | 0.5 | 1023 | 100% | 0% | 0% | 100% | 283817.8209 | 0 | 0 | 283817.8209 | Type B Construction 2BC-MRY1416 | Added | 2017-A | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 94605.9403 | 94605.9403 | 94605.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7434 | Garages & Workshops |  | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Soft Wall Maintenance Garage x 6 (assume same size as existing on Tote Road) |  | 2046 | m2 | 0.125 | 1.875 | 11.0175 | 18.75 | 31.6425 | 255.75 | 3836.25 | 22541.805 | 38362.5 | 64740.555 | 0 | 0 | 100% | 0% | 0% | 100% | 64740.555 | 0 | 0 | 64740.555 | Type A 2AM-MRY1325 | Added | 2017-A | Direct |  |  |  | 100% | [9 empty] | 0 | 0 | 0 | 64740.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7435 | Warehouses |  |  | 25ka | Allowance - For Temporary construction warehouses and offices | 25ka | Buildings (Contaminated) | Temporary construction warehouses and offices Allowance |  | Temporary construction warehouses and offices |  | 1 | Lot | 94.3396 | 1179.2453 | 9433.9623 | 13006.6038 | 23619.8113 | 94.3396 | 1179.2453 | 9433.9623 | 13006.6038 | 23619.8113 | 0 | 0 | 100% | 0% | 0% | 100% | 23619.8113 | 0 | 0 | 23619.8113 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 7873.2704 | 7873.2704 | 7873.2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1435 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-004 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1437 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-007 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1439 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-010 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1407 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-004 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 2310.1 | 2310.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1416 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-007 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1419 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-008 | 35.6877 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 20 | 100 | 1762.8 | 2757.4 | 4620.2 | 1 | 35.6877 | 100% | 0% | 0% | 100% | 4620.2 | 0 | 0 | 4620.2 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1540.0667 | 1540.0667 | 1540.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1433 | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | 7432-TK-001 | 1 | Ea | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 31 | 325 | 2732.34 | 3584.62 | 6641.96 | 2 | 2 | 100% | 0% | 0% | 100% | 6641.96 | 0 | 0 | 6641.96 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 3320.98 | 3320.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1436 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - FUEL SYSTEMS WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-005 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 964.8358 | 964.8358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1438 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-008 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1440 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | 7432-TK-011 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1408 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-004 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 333.914 | 333.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1417 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-007 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1401 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-001 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1404 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-003 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 1788.825 | 1788.825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1410 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-005 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1413 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single | 7432-BLD-006 | 66.9145 | m2 | 0.22417 | 2.8021 | 19.758 | 30.9059 | 53.466 | 15 | 187.5 | 1322.1 | 2068.05 | 3577.65 | 1 | 66.9145 | 100% | 0% | 0% | 100% | 3577.65 | 0 | 0 | 3577.65 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1192.55 | 1192.55 | 1192.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1420 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Washcar #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-008 | 35.6877 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 4.4 | 35 | 246.792 | 386.036 | 667.828 | 0.3 | 10.7063 | 100% | 0% | 0% | 100% | 667.828 | 0 | 0 | 667.828 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 222.6093 | 222.6093 | 222.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1434 | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | 7432-TK-002 | 1 | Ea | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 9.6667 | 89.5833 | 852.02 | 988.0683 | 1929.6717 | 1 | 1 | 100% | 0% | 0% | 100% | 1929.6717 | 0 | 0 | 1929.6717 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 643.2239 | 643.2239 | 643.2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1422 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 7432-BLD-009 | 14.8699 | m2 | 0.56042 | 2.8021 | 49.3951 | 77.2646 | 129.4619 | 8.3333 | 41.6667 | 734.5 | 1148.9167 | 1925.0833 | 1 | 14.8699 | 100% | 0% | 0% | 100% | 1925.0833 | 0 | 0 | 1925.0833 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 641.6944 | 641.6944 | 641.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1402 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Batch Plant Office-Lunchroom-W/C - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-001 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1405 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Fuel Systems Lunchroom - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-003 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 626.0888 | 626.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1411 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #1 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-005 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1414 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Site Services Lunchroom #2 - Demolish and foundations - Timber Cribbing to Elevate Building | 7432-BLD-006 | 66.9145 | m2 | 0.12329 | 0.98073 | 6.9153 | 10.8171 | 18.7131 | 8.25 | 65.625 | 462.735 | 723.8175 | 1252.1775 | 0.3 | 20.0743 | 100% | 0% | 0% | 100% | 1252.1775 | 0 | 0 | 1252.1775 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 417.3925 | 417.3925 | 417.3925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1409 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-004 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1418 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-007 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1421 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Washcar #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-008 | 35.6877 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD |  | #N/A |  |  |  |  | Toromont Britespan Workshop - Demolish and Decontaminate Building - Fabric w/ Sea Can Walls | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish and foundations - Gravel Base - Skidded Building | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities |  | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Toromont Britespan Workshop - Demolish floor finish - Gravel | 7434-BLD-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1423 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Smoke Shack - Demolish and foundations - Gravel Base - Skidded Building | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1424 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Smoke Shack - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-009 | 14.8699 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1403 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Batch Plant Office-Lunchroom-W/C - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-001 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1406 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Fuel Systems Lunchroom - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-003 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1412 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #1 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-005 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1415 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Site Services Lunchroom #2 - Demolish floor finish - Raised Steel or Wooden Floor | 7432-BLD-006 | 66.9145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1513 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 375 | 1312.5 | 33052.5 | 51701.25 | 86066.25 | 1 | 669.145 | 100% | 0% | 0% | 100% | 86066.25 | 0 | 0 | 86066.25 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 28688.75 | 28688.75 | 28688.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1514 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 7451-BLD-001 | 669.145 | m2 | 0.56042 | 1.9615 | 49.3951 | 77.2646 | 128.6212 | 375 | 1312.5 | 33052.5 | 51701.25 | 86066.25 | 1 | 669.145 | 100% | 0% | 0% | 100% | 86066.25 | 0 | 0 | 86066.25 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 28688.75 | 28688.75 | 28688.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7450 | Construction Facilities | 7451 | Concrete Facilities | 1515 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Concrete Batch Plant Building - Demolish floor finish - Gravel | 7451-BLD-001 | 669.145 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Containment Area - Existing |  | 0 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond (Existing) |  |  | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bulk Fuel Storage Facility (Bladder Farm) |  | 5787.68 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 257.5048 | 984.4844 | 22696.4716 | 3946.0579 | 27627.0138 | 0 | 0 | 100% | 0% | 0% | 100% | 27627.0138 | 0 | 0 | 27627.0138 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 13813.5069 | 13813.5069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7400 | Mine Site | 7470 | Camp & Site Services | 7473 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Barreled Fuel Line Containment |  | 5411.65 | m2 | 0.044492 | 0.1701 | 3.9215 | 0.6818 | 4.7481 | 240.7745 | 920.5217 | 21221.8645 | 3689.6795 | 25832.0656 | 0 | 0 | 100% | 0% | 0% | 100% | 25832.0656 | 0 | 0 | 25832.0656 | Type A 2AM-MRY1325 |  | 2014 | Direct |  |  | 50% | 50% | [9 empty] | 0 | 0 | 12916.0328 | 12916.0328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 1712000 | 0 | 0 | 98.31% | 1.695% | 0% | 100% | 1682989.5815 | 29010.4185 | 0 | 1712000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 342400 | 428000 | 64894.0678 | 97477.2514 | 64894.0678 | 154080 | 119840 | 111834.5633 | 95244.3059 | 81484.7797 | 34240 | 34240 | 85600
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting | [12 empty] | 3766032 | 0 | 0 | 98.31% | 1.695% | 0% | 100% | 3702215.3151 | 63816.6849 | 0 | 3766032 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 753206.4 | 941508 | 142753 | 214429 | 142753 | 338942.88 | 263622.24 | 246012 | 209517 | 179249 | 75320.64 | 75320.64 | 188301.6
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting - Arbitration Award 2019 (Regulatory Fees) | [12 empty] | 2300000 | 0 | 0 | 98.28% | 1.716% | 0% | 100% | 2260533.6411 | 39466.3589 | 0 | 2300000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 460000 | 575000 | 87182.4509 | 130956.5877 | 87182.4509 | 207000 | 161000 | 150245.0324 | 127956.7194 | 109471.3746 | 46000 | 46000 | 115000
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting - 2021 Increase for Water Treatment | [12 empty] | 70800 | 0 | 0 | 98.28% | 1.717% | 0% | 100% | 69584.6304 | 1215.3696 | 0 | 70800 | Type A 2AM-MRY1325 | Added | 2021 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 14160 | 17700 | 2683.7033 | 4031.1854 | 2683.7033 | 6372 | 4956 | 4624.934 | 3938.8416 | 3369.8145 | 1416 | 1416 | 3540
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting - 2022 Increase for Water Treatment | [12 empty] | 7306.6201 | 0 | 0 | 98.31% | 1.695% | 0% | 100% | 7182.8069 | 123.8131 | 0 | 7306.6201 | Type A 2AM-MRY1325 | Added | 2022 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 1461.324 | 1826.655 | 276.9605 | 416.0218 | 276.9605 | 657.5958 | 511.4634 | 477.2971 | 406.4918 | 347.7677 | 146.1324 | 146.1324 | 365.331
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | PCM |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Short Term C&M, Closure & Post-Closure Monitoring and reporting - 2023 Increase for Water Treatment | [12 empty] | 49360 | 0 | 0 | 98.31% | 1.695% | 0% | 100% | 48523.5781 | 836.4219 | 0 | 49360 | Type A 2AM-MRY1325 | Added | 2023 | Indirect | 20% | 25% | 3.791% | 5.694% | 3.791% | 9% | 7% | 6.532% | 5.563% | 4.76% | 2% | 2% | 5% | 9872 | 12340 | 1871.0112 | 2810.4422 | 1871.0112 | 4442.4 | 3455.2 | 3224.389 | 2746.0625 | 2349.3509 | 987.2 | 987.2 | 2468
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 159526.8647 | 0 | 0 | 100% | 0% | 0% | 100% | 159526.8647 | 0 | 0 | 159526.8647 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 63810.7459 | 47858.0594 | 31905.3729 | 15952.6865 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 59000 | 0 | 0 | 100% | 0% | 0% | 100% | 59000 | 0 | 0 | 59000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 23600 | 17700 | 11800 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees | [12 empty] | 27000 | 0 | 0 | 100% | 0% | 0% | 100% | 27000 | 0 | 0 | 27000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 10800 | 8100 | 5400 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8112 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Engineering Fees - 2019 Arbitration outcome | [12 empty] | 1431000 | 0 | 0 | 100% | 0% | 0% | 100% | 1431000 | 0 | 0 | 1431000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 40% | 30% | 20% | 10% | [7 empty] | 0 | 0 | 572400 | 429300 | 286200 | 143100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 411208.6791 | 0 | 0 | 100% | 0% | 0% | 100% | 411208.6791 | 0 | 0 | 411208.6791 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 74017.5622 | 74017.5622 | 74017.5622 | 41120.8679 | 41120.8679 | 28784.6075 | 20560.434 | 20560.434 | 8224.1736 | 8224.1736 | 20560.434
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration - 2019 Arbitration Outcome | [12 empty] | 4197000 | 0 | 0 | 100% | 0% | 0% | 100% | 4197000 | 0 | 0 | 4197000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 755460 | 755460 | 755460 | 419700 | 419700 | 293790 | 209850 | 209850 | 83940 | 83940 | 209850
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 149000 | 0 | 0 | 100% | 0% | 0% | 100% | 149000 | 0 | 0 | 149000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 26820 | 26820 | 26820 | 14900 | 14900 | 10430 | 7450 | 7450 | 2980 | 2980 | 7450
8000 | Other Indirects | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | Project Management, Engineering and Procurement |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Supervision, Project Management & Contract Administration | [12 empty] | 65000 | 0 | 0 | 100% | 0% | 0% | 100% | 65000 | 0 | 0 | 65000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 11700 | 11700 | 11700 | 6500 | 6500 | 4550 | 3250 | 3250 | 1300 | 1300 | 3250
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 2019000 | 0 | 0 | 100% | 0% | 0% | 100% | 2019000 | 0 | 0 | 2019000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 673000 | 673000 | 673000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive material) | [12 empty] | 2537000 | 0 | 0 | 100% | 0% | 0% | 100% | 2537000 | 0 | 0 | 2537000 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 845666.6667 | 845666.6667 | 845666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 234000 | 0 | 0 | 100% | 0% | 0% | 100% | 234000 | 0 | 0 | 234000 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 78000 | 78000 | 78000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 63000 | 0 | 0 | 100% | 0% | 0% | 100% | 63000 | 0 | 0 | 63000 | Type A 2AM-MRY1325 | Added | 2017 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 21000 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  |  |  | Indirect | Indirect | Indirect |  | Contaminated Soil Treatment | [12 empty] | 5000 | 0 | 0 | 100% | 0% | 0% | 100% | 5000 | 0 | 0 | 5000 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 1666.6667 | 1666.6667 | 1666.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  | MCS - 1 |  | Indirect | Indirect | Indirect |  | Metal Contaminated Soil - Milne Port Ore Stockpile |  | 32772 | m3 |  |  |  |  | 4.3155 |  |  |  |  | 141427.48 | 0 | 0 | 100% | 0% | 0% | 100% | 141427.48 | 0 | 0 | 141427.48 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 47142.4933 | 47142.4933 | 47142.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  | MCS - 1 |  | Indirect | Indirect | Indirect |  | Metal Contaminated Soil - Crusher Pad |  | 10425 | m3 |  |  |  |  | 4.3155 |  |  |  |  | 44989.0601 | 0 | 0 | 100% | 0% | 0% | 100% | 44989.0601 | 0 | 0 | 44989.0601 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 14996.3534 | 14996.3534 | 14996.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Contaminated Soil Treatment |  |  | MCS - 5 |  | Indirect | Indirect | Indirect |  | Metal Contaminated Soil - ROM |  | 8504 | m3 |  |  |  |  | 10.6309 |  |  |  |  | 90404.8283 | 0 | 0 | 100% | 0% | 0% | 100% | 90404.8283 | 0 | 0 | 90404.8283 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 30134.9428 | 30134.9428 | 30134.9428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 222664.9148 | 0 | 0 | 100% | 0% | 0% | 100% | 222664.9148 | 0 | 0 | 222664.9148 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 74221.6383 | 74221.6383 | 74221.6383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 75000 | 0 | 0 | 100% | 0% | 0% | 100% | 75000 | 0 | 0 | 75000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel | [12 empty] | 30000 | 0 | 0 | 100% | 0% | 0% | 100% | 30000 | 0 | 0 | 30000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Fuel |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Fuel - 2019 Arbitration Outcome | [12 empty] | 7383000 | 0 | 0 | 100% | 0% | 0% | 100% | 7383000 | 0 | 0 | 7383000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [8 empty] | 0 | 0 | 2461000 | 2461000 | 2461000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 212200.1482 | 0 | 0 | 100% | 0% | 0% | 100% | 212200.1482 | 0 | 0 | 212200.1482 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 38196.0267 | 38196.0267 | 38196.0267 | 21220.0148 | 21220.0148 | 14854.0104 | 10610.0074 | 10610.0074 | 4244.003 | 4244.003 | 10610.0074
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 64000 | 0 | 0 | 100% | 0% | 0% | 100% | 64000 | 0 | 0 | 64000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 11520 | 11520 | 11520 | 6400 | 6400 | 4480 | 3200 | 3200 | 1280 | 1280 | 3200
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation | [12 empty] | 28000 | 0 | 0 | 100% | 0% | 0% | 100% | 28000 | 0 | 0 | 28000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 5040 | 5040 | 5040 | 2800 | 2800 | 1960 | 1400 | 1400 | 560 | 560 | 1400
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization of Workers Required for Reclamation - 2019 Arbitration Outcome | [12 empty] | 1910000 | 0 | 0 | 100% | 0% | 0% | 100% | 1910000 | 0 | 0 | 1910000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 343800 | 343800 | 343800 | 191000 | 191000 | 133700 | 95500 | 95500 | 38200 | 38200 | 95500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 409043.2427 | 0 | 0 | 100% | 0% | 0% | 100% | 409043.2427 | 0 | 0 | 409043.2427 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 73627.7837 | 73627.7837 | 73627.7837 | 40904.3243 | 40904.3243 | 28633.027 | 20452.1621 | 20452.1621 | 8180.8649 | 8180.8649 | 20452.1621
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 151000 | 0 | 0 | 100% | 0% | 0% | 100% | 151000 | 0 | 0 | 151000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 27180 | 27180 | 27180 | 15100 | 15100 | 10570 | 7550 | 7550 | 3020 | 3020 | 7550
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift | [12 empty] | 70000 | 0 | 0 | 100% | 0% | 0% | 100% | 70000 | 0 | 0 | 70000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 12600 | 12600 | 12600 | 7000 | 7000 | 4900 | 3500 | 3500 | 1400 | 1400 | 3500
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Mobilization and Demobilization of Equipment and Materials by Sealift - 2019 Arbitrtion Outcome | [12 empty] | 3668270 | 0 | 0 | 100% | 0% | 0% | 100% | 3668270 | 0 | 0 | 3668270 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 660288.6 | 660288.6 | 660288.6 | 366827 | 366827 | 256778.9 | 183413.5 | 183413.5 | 73365.4 | 73365.4 | 183413.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2019) |  | 18172 | m3 |  |  |  |  | 103.02 |  |  |  |  | 1872079.44 | 0 | 0 | 100% | 0% | 0% | 100% | 1872079.44 | 0 | 0 | 1872079.44 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 336974.2992 | 336974.2992 | 336974.2992 | 187207.944 | 187207.944 | 131045.5608 | 93603.972 | 93603.972 | 37441.5888 | 37441.5888 | 93603.972
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2019) |  | 49868 | m3 |  |  |  |  | 103.02 |  |  |  |  | 5137401.36 | 0 | 0 | 100% | 0% | 0% | 100% | 5137401.36 | 0 | 0 | 5137401.36 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 924732.2448 | 924732.2448 | 924732.2448 | 513740.136 | 513740.136 | 359618.0952 | 256870.068 | 256870.068 | 102748.0272 | 102748.0272 | 256870.068
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2019) |  | 24756 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2550363.12 | 0 | 0 | 100% | 0% | 0% | 100% | 2550363.12 | 0 | 0 | 2550363.12 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 459065.3616 | 459065.3616 | 459065.3616 | 255036.312 | 255036.312 | 178525.4184 | 127518.156 | 127518.156 | 51007.2624 | 51007.2624 | 127518.156
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2019) |  | 33278 | m3 |  |  |  |  | 103.02 |  |  |  |  | 3428299.56 | 0 | 0 | 100% | 0% | 0% | 100% | 3428299.56 | 0 | 0 | 3428299.56 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 617093.9208 | 617093.9208 | 617093.9208 | 342829.956 | 342829.956 | 239980.9692 | 171414.978 | 171414.978 | 68565.9912 | 68565.9912 | 171414.978
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Shiploading Module (mobilized in 2019) |  | -81400 | m3 |  |  |  |  | 103.02 |  |  |  |  | -8385828 | 0 | 0 | 100% | 0% | 0% | 100% | -8385828 | 0 | 0 | -8385828 | Type A 2AM-MRY1325 | Removed | 2021-D | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -1509449.04 | -1509449.04 | -1509449.04 | -838582.8 | -838582.8 | -587007.96 | -419291.4 | -419291.4 | -167716.56 | -167716.56 | -419291.4
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Shiploading Module (mobilized in 2019) |  | 81400 | m3 |  |  |  |  | 103.02 |  |  |  |  | 8385828 | 0 | 0 | 100% | 0% | 0% | 100% | 8385828 | 0 | 0 | 8385828 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 1509449.04 | 1509449.04 | 1509449.04 | 838582.8 | 838582.8 | 587007.96 | 419291.4 | 419291.4 | 167716.56 | 167716.56 | 419291.4
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2019) |  | 21815 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2247381.3 | 0 | 0 | 100% | 0% | 0% | 100% | 2247381.3 | 0 | 0 | 2247381.3 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 404528.634 | 404528.634 | 404528.634 | 224738.13 | 224738.13 | 157316.691 | 112369.065 | 112369.065 | 44947.626 | 44947.626 | 112369.065
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | 30500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 3142110 | 0 | 0 | 100% | 0% | 0% | 100% | 3142110 | 0 | 0 | 3142110 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 565579.8 | 565579.8 | 565579.8 | 314211 | 314211 | 219947.7 | 157105.5 | 157105.5 | 62842.2 | 62842.2 | 157105.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Crushing Module (mobilized in 2018, installed following expansion approval) |  | -30500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -3142110 | 0 | 0 | 100% | 0% | 0% | 100% | -3142110 | 0 | 0 | -3142110 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -565579.8 | -565579.8 | -565579.8 | -314211 | -314211 | -219947.7 | -157105.5 | -157105.5 | -62842.2 | -62842.2 | -157105.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | 40500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 4172310 | 0 | 0 | 100% | 0% | 0% | 100% | 4172310 | 0 | 0 | 4172310 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 751015.8 | 751015.8 | 751015.8 | 417231 | 417231 | 292061.7 | 208615.5 | 208615.5 | 83446.2 | 83446.2 | 208615.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | BMH Conveyors (mobilized in 2018, installed following expansion approval) |  | -40500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -4172310 | 0 | 0 | 100% | 0% | 0% | 100% | -4172310 | 0 | 0 | -4172310 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -751015.8 | -751015.8 | -751015.8 | -417231 | -417231 | -292061.7 | -208615.5 | -208615.5 | -83446.2 | -83446.2 | -208615.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | 24100 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2482782 | 0 | 0 | 100% | 0% | 0% | 100% | 2482782 | 0 | 0 | 2482782 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 446900.76 | 446900.76 | 446900.76 | 248278.2 | 248278.2 | 173794.74 | 124139.1 | 124139.1 | 49655.64 | 49655.64 | 124139.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Screening Module (mobilized in 2018, installed following expansion approval) |  | -24100 | m3 |  |  |  |  | 103.02 |  |  |  |  | -2482782 | 0 | 0 | 100% | 0% | 0% | 100% | -2482782 | 0 | 0 | -2482782 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -446900.76 | -446900.76 | -446900.76 | -248278.2 | -248278.2 | -173794.74 | -124139.1 | -124139.1 | -49655.64 | -49655.64 | -124139.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | 41500 | m3 |  |  |  |  | 103.02 |  |  |  |  | 4275330 | 0 | 0 | 100% | 0% | 0% | 100% | 4275330 | 0 | 0 | 4275330 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 769559.4 | 769559.4 | 769559.4 | 427533 | 427533 | 299273.1 | 213766.5 | 213766.5 | 85506.6 | 85506.6 | 213766.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Car Dumper Module (mobilized in 2018, installed following expansion approval) |  | -41500 | m3 |  |  |  |  | 103.02 |  |  |  |  | -4275330 | 0 | 0 | 100% | 0% | 0% | 100% | -4275330 | 0 | 0 | -4275330 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -769559.4 | -769559.4 | -769559.4 | -427533 | -427533 | -299273.1 | -213766.5 | -213766.5 | -85506.6 | -85506.6 | -213766.5
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | 25100 | m3 |  |  |  |  | 103.02 |  |  |  |  | 2585802 | 0 | 0 | 100% | 0% | 0% | 100% | 2585802 | 0 | 0 | 2585802 | Type A 2AM-MRY1325 | Added | 2018-C1 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 465444.36 | 465444.36 | 465444.36 | 258580.2 | 258580.2 | 181006.14 | 129290.1 | 129290.1 | 51716.04 | 51716.04 | 129290.1
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | Lot | Rail Construction Materials (mobilized in 2018, installed following expansion approval) |  | -9926 | m3 |  |  |  |  | 103.02 |  |  |  |  | -1022576.52 | 0 | 0 | 100% | 0% | 0% | 100% | -1022576.52 | 0 | 0 | -1022576.52 | Type A 2AM-MRY1325 | Added | 2018-MAY | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | -184063.7736 | -184063.7736 | -184063.7736 | -102257.652 | -102257.652 | -71580.3564 | -51128.826 | -51128.826 | -20451.5304 | -20451.5304 | -51128.826
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - Arbitration Reconciliation |  | 188 | Ea |  |  |  |  | 15964.53 |  |  |  |  | 3001331.64 | 0 | 0 | 100% | 0% | 0% | 100% | 3001331.64 | 0 | 0 | 3001331.64 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 3001331.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - Arbitration Reconciliation |  | 156 | Ea |  |  |  |  | 8202.67 |  |  |  |  | 1279616.52 | 0 | 0 | 100% | 0% | 0% | 100% | 1279616.52 | 0 | 0 | 1279616.52 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 1279616.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - Arbitration Reconciliation |  | 183 | Ea |  |  |  |  | 2785.99 |  |  |  |  | 509836.17 | 0 | 0 | 100% | 0% | 0% | 100% | 509836.17 | 0 | 0 | 509836.17 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 509836.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2020-R |  | 49 | Ea |  |  |  |  | 15964.53 |  |  |  |  | 782261.97 | 0 | 0 | 100% | 0% | 0% | 100% | 782261.97 | 0 | 0 | 782261.97 | Type A 2AM-MRY1325 | Added | 2020-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 782261.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2020-R |  | 61 | Ea |  |  |  |  | 8202.67 |  |  |  |  | 500362.87 | 0 | 0 | 100% | 0% | 0% | 100% | 500362.87 | 0 | 0 | 500362.87 | Type A 2AM-MRY1325 | Added | 2020-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 500362.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2020-R |  | 34 | Ea |  |  |  |  | 2785.99 |  |  |  |  | 94723.66 | 0 | 0 | 100% | 0% | 0% | 100% | 94723.66 | 0 | 0 | 94723.66 | Type A 2AM-MRY1325 | Added | 2020-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 94723.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2021 |  | 5 | ea |  |  |  |  | 8202.67 |  |  |  |  | 41013.35 | 0 | 0 | 100% | 0% | 0% | 100% | 41013.35 | 0 | 0 | 41013.35 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 41013.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2021 |  | 13 | ea |  |  |  |  | 2785.99 |  |  |  |  | 36217.87 | 0 | 0 | 100% | 0% | 0% | 100% | 36217.87 | 0 | 0 | 36217.87 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 36217.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2021-R |  | -6 | ea |  |  |  |  | 15964.53 |  |  |  |  | -95787.18 | 0 | 0 | 100% | 0% | 0% | 100% | -95787.18 | 0 | 0 | -95787.18 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -95787.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2021-R |  | -17 | ea |  |  |  |  | 8202.67 |  |  |  |  | -139445.39 | 0 | 0 | 100% | 0% | 0% | 100% | -139445.39 | 0 | 0 | -139445.39 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -139445.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2021-R |  | -26 | ea |  |  |  |  | 2785.99 |  |  |  |  | -72435.74 | 0 | 0 | 100% | 0% | 0% | 100% | -72435.74 | 0 | 0 | -72435.74 | Type A 2AM-MRY1325 | Added | 2021-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -72435.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2021-D2 |  | -30 | ea |  |  |  |  | 15964.53 |  |  |  |  | -478935.9 | 0 | 0 | 100% | 0% | 0% | 100% | -478935.9 | 0 | 0 | -478935.9 | Type A 2AM-MRY1325 | Added | 2021-D2 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -478935.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2021-D2 |  | -103 | ea |  |  |  |  | 8202.67 |  |  |  |  | -844875.01 | 0 | 0 | 100% | 0% | 0% | 100% | -844875.01 | 0 | 0 | -844875.01 | Type A 2AM-MRY1325 | Added | 2021-D2 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -844875.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2021-D2 |  | -47 | ea |  |  |  |  | 2785.99 |  |  |  |  | -130941.53 | 0 | 0 | 100% | 0% | 0% | 100% | -130941.53 | 0 | 0 | -130941.53 | Type A 2AM-MRY1325 | Added | 2021-D2 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -130941.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | -201 | ea |  |  |  |  | 15964.53 |  |  |  |  | -3208870.53 | 0 | 0 | 100% | 0% | 0% | 100% | -3208870.53 | 0 | 0 | -3208870.53 | Type A 2AM-MRY1325 | Removed | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -3208870.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | -102 | ea |  |  |  |  | 8202.67 |  |  |  |  | -836672.34 | 0 | 0 | 100% | 0% | 0% | 100% | -836672.34 | 0 | 0 | -836672.34 | Type A 2AM-MRY1325 | Removed | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -836672.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | -157 | ea |  |  |  |  | 2785.99 |  |  |  |  | -437400.43 | 0 | 0 | 100% | 0% | 0% | 100% | -437400.43 | 0 | 0 | -437400.43 | Type A 2AM-MRY1325 | Removed | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -437400.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | 44 | ea |  |  |  |  | 15964.53 |  |  |  |  | 702439.32 | 0 | 0 | 100% | 0% | 0% | 100% | 702439.32 | 0 | 0 | 702439.32 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 702439.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | 138 | ea |  |  |  |  | 8202.67 |  |  |  |  | 1131968.46 | 0 | 0 | 100% | 0% | 0% | 100% | 1131968.46 | 0 | 0 | 1131968.46 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 1131968.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2022-R (2021 Equipment Audit) |  | 153 | ea |  |  |  |  | 2785.99 |  |  |  |  | 426256.47 | 0 | 0 | 100% | 0% | 0% | 100% | 426256.47 | 0 | 0 | 426256.47 | Type A 2AM-MRY1325 | Added | 2022-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 426256.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Demob - 2023-R |  | -13 | ea |  |  |  |  | 15964.53 |  |  |  |  | -207538.89 | 0 | 0 | 100% | 0% | 0% | 100% | -207538.89 | 0 | 0 | -207538.89 | Type A 2AM-MRY1325 | Removed | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -207538.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Demob - 2023-R |  | -22 | ea |  |  |  |  | 8202.67 |  |  |  |  | -180458.74 | 0 | 0 | 100% | 0% | 0% | 100% | -180458.74 | 0 | 0 | -180458.74 | Type A 2AM-MRY1325 | Removed | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -180458.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Demob - 2023-R |  | -9 | ea |  |  |  |  | 2785.99 |  |  |  |  | -25073.91 | 0 | 0 | 100% | 0% | 0% | 100% | -25073.91 | 0 | 0 | -25073.91 | Type A 2AM-MRY1325 | Removed | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -25073.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Mob - 2023-R |  | 10 | ea |  |  |  |  | 15964.53 |  |  |  |  | 159645.3 | 0 | 0 | 100% | 0% | 0% | 100% | 159645.3 | 0 | 0 | 159645.3 | Type A 2AM-MRY1325 | Added | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 159645.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Med 3rd Party Equipment Mob - 2023-R |  | 4 | ea |  |  |  |  | 8202.67 |  |  |  |  | 32810.68 | 0 | 0 | 100% | 0% | 0% | 100% | 32810.68 | 0 | 0 | 32810.68 | Type A 2AM-MRY1325 | Added | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 32810.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Light 3rd Party Equipment Mob - 2023-R |  | 8 | ea |  |  |  |  | 2785.99 |  |  |  |  | 22287.92 | 0 | 0 | 100% | 0% | 0% | 100% | 22287.92 | 0 | 0 | 22287.92 | Type A 2AM-MRY1325 | Added | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 22287.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Heavy 3rd Party Equipment Mob - 2023-R Tankers | E-1 E-2 | 2 | ea |  |  |  |  | 15964.53 |  |  |  |  | 31929.06 | 0 | 0 | 100% | 0% | 0% | 100% | 31929.06 | 0 | 0 | 31929.06 | Type A 2AM-MRY1325 | Added | 2023-R | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 31929.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | Other Indirects | 8101 | Other Indirects | TBD | Mobilization | TBD | Mobilization and Demobilization |  |  |  | Indirect | Indirect | Indirect | Indirect | 3rd Party Equipment | Diamond Drill for exploration | E-4 | 1 | ea |  |  |  |  | 15964.53 |  |  |  |  | 15964.53 | 0 | 0 | 100% | 0% | 0% | 100% | 15964.53 | 0 | 0 | 15964.53 | Type A 2AM-MRY1325 | Added | 2023 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 15964.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Off-Site Disposal of Waste & Material |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Off-Site Disposal of Waste & Material | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 |  | 2014 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 868473.2158 | 0 | 0 | 100% | 0% | 0% | 100% | 868473.2158 | 0 | 0 | 868473.2158 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 156325.1788 | 156325.1788 | 156325.1788 | 86847.3216 | 86847.3216 | 60793.1251 | 43423.6608 | 43423.6608 | 17369.4643 | 17369.4643 | 43423.6608
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 826800 | 0 | 0 | 100% | 0% | 0% | 100% | 826800 | 0 | 0 | 826800 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 148824 | 148824 | 148824 | 82680 | 82680 | 57876 | 41340 | 41340 | 16536 | 16536 | 41340
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Mobilization | TBD | Worker Accommodation & Camp Operation |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Worker Accommodation & Camp Operation - 2019 Arbitration Outcome | [12 empty] | 5233000 | 0 | 0 | 100% | 0% | 0% | 100% | 5233000 | 0 | 0 | 5233000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 18% | 18% | 18% | 10% | 10% | 7% | 5% | 5% | 2% | 2% | 5% | 0 | 0 | 941940 | 941940 | 941940 | 523300 | 523300 | 366310 | 261650 | 261650 | 104660 | 104660 | 261650
9000 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | -285291.2224 | 0 | 0 | 100% | 0% | 0% | 100% | -285291.2224 | 0 | 0 | -285291.2224 | Type A 2AM-MRY1325 | Added | 2023 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | -285291.2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 874912.0832 | 0 | 0 | 100% | 0% | 0% | 100% | 874912.0832 | 0 | 0 | 874912.0832 | Type A 2AM-MRY1325 | Added | 2022 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 874912.0832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 139000 | 0 | 0 | 96.01% | 3.987% | 0% | 100% | 133458.4675 | 5541.5325 | 0 | 139000 | Type A 2AM-MRY1325 | Added | 2020 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 139000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 316000 | 0 | 0 | 96.01% | 3.987% | 0% | 100% | 303401.9836 | 12598.0164 | 0 | 316000 | Type A 2AM-MRY1325 | Added | 2021 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 316000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency - 2019 Arbitration Outcome | [12 empty] | 8929000 | 0 | 0 | 96.01% | 3.987% | 0% | 100% | 8573026.3025 | 355973.6975 | 0 | 8929000 | Type A 2AM-MRY1325 | Added | 2019 | Indirect |  |  | 100% | [10 empty] | 0 | 0 | 8929000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-12916.3714
-13000
Note on Q219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Catalina - to discuss - should this be included or removed because item 2019-17 is out of scope?

## 2023 Total Costs
|  | YEAR | YEAR 2 (OPTIONAL)
|  | 2023 | 2023-R
| Total Directs for Activities and Reclaimation of 2021 Activities | 127699.4534 | -1603515.5653
|  |  |  | IOL | Crown | Water | Land
| DIRECT COST SUB-TOTAL (Reconcillation + New Scope) | -1475816.1119 |  | -927720.8624 | -548095.2495 | 60995.48 | -1536811.5919
| TOTAL PERSON-HOURS | -9699.9406 |  | -5517.8251 | -4182.1154 | 293 | -9992.9406
| TOTAL PERSON-DAYS | -969.9941 |  | -551.7825 | -418.2115 | 29.3 | -999.2941
| Off-Site Disposal of Waste & Material | 0 |  | 0 | 0 | 0 | 0
| Fuel | -97515.8391 |  | -55606.8731 | -41908.966 | 2866.1766 | -100382.0156
| Ammonium Nitrate | 0 |  | 0 | 0 | 0 | 0
| Contaminated Soil Treatment | 0 |  | 0 | 0 | 0 | 0
| Mobilization of Workers Required for Reclamation | -86565.6104 |  | -49242.9719 | -37322.6385 | 2614.8329 | -89180.4433
| Worker Accommodation & Camp Operation | -227714.5317 |  | -129535.7387 | -98178.793 | 6878.4295 | -234592.9612
| Demobilization of Phase 2 Modules | 0 |  | 0 | 0 | 0 | 0
| Demobilization of 3rd Party Equipment | -150434.05 |  | -150434.05 | 0 | 0 | -150434.05
10% | Mobilization and Demobilization of Equipment and Materials by Sealift | -147581.6112 |  | -92772.0862 | -54809.5249 | 6099.548 | -153681.1592
| Closure & Post Closure Monitoring | 49360 |  | 49360 | 0 |  | 49360
5% | Engineering Fees | -73790.8056 |  | -46386.0431 | -27404.7625 | 3049.774 | -76840.5796
9.4% | Supervision, Project Management & Contract Administration | -134086.8745 |  | -82565.9211 | -51520.9535 | 5733.5751 | -139820.4496
20% | Contingency (applied to Direct Costs, Contaminated Soils and Post-Closure Monitoring) | -285291.2224 |  | -175672.1725 | -109619.0499 | 12199.096 | -297490.3184
| INDIRECT SUB-TOTAL | -1153620.5449 |  | -732855.8566 | -420764.6883 | 39441.4321 | -1193061.977
| TOTAL | -2629436.6567 |  | -1660576.719 | -968859.9378 | 100436.9121 | -2729873.5689
| INFLATION | 0
| TOTAL | -2629436.6567 |  | -1660576.719 | -968859.9378 | 100436.9121 | -2729873.5689
= pulls data from Indirects spreadsheets
= linked back to EBS 'Estimate Details' Indirects section
| Total Direct Cost |  | -1475816.1119 | -927720.8624 | -548095.2495 | 60995.48 | -1536811.5919
| Total direct cost+Contaminated soil+post closure monitoring |  | -1426456.1119 | -878360.8624 | -548095.2495 | 60995.48 | -1487451.5919
| Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  | -2038751.9152 | -1300345.7092 | -738406.206 | 76588.2904 | -2115340.2056
| Mobilization and Demobilization of Equipment and Materials by Sealift | 10% | -147581.6112 | -92772.0862 | -54809.5249 | 6099.548 | -153681.1592
| Demob of 3rd Party Equipment by sealift |  | -150434.05 | -150434.05 | 0 | 0 | -150434.05
| Engineering | 5% | -73790.8056 | -46386.0431 | -27404.7625 | 3049.774 | -76840.5796
| Project supervision, management & contract administration | 9.4% | -134086.8745 | -82565.9211 | -51520.9535 | 5733.5751 | -139820.4496
| Contingency | 20% | -285291.2224 | -175672.1725 | -109619.0499 | 12199.096 | -297490.3184
FUEL ON-SITE
| Increase to Fuel Capacity @ site (L) | 0 |  | 0 | 0 | 0 | 0
| Demob cost per Litre | 0.10842 |  | 0.10842 | 0.10842 | 0.10842 | 0.10842
| Reclamation Activities (L) | -112828.5987 |  | -64493.6579 | -48334.9409 | 3225 | -116053.5987
| Heat and Power (L) | -112034.3137 |  | -63730.8804 | -48303.4333 | 3384.15 | -115418.4637
| Total fuel required during closure (L) | -224862.9124 |  | -128224.5382 | -96638.3742 | 6609.15 | -231472.0624
| Cost to mob. Fuel per Litre | 0.43367 |  | 0.43367 | 0.43367 | 0.43367 | 0.43367
| Demob 50% of total capacity | 0 |  | 0 | 0 | 0 | 0
| Mob 100% fuel required during closure | -97515.8391 |  | -55606.8731 | -41908.966 | 2866.1766 | -100382.0156
| Total Mob/Demo Fuel | -97515.8391 |  | -55606.8731 | -41908.966 | 2866.1766 | -100382.0156
CAMP FUEL CONSUMPTION
| 1732500 | Avg Monthly Consumption |  | 1732500 | 1732500 | 1732500 | 1732500
| 30 | Days in month |  | 30 | 30 | 30 | 30
| 500 | Average camp population |  | 500 | 500 | 500 | 500
| 115.5 | L/Man-day |  | 115.5 | 115.5 | 115.5 | 115.5
| 1 | $/L fuel cost |  | 1 | 1 | 1 | 1
WORKERS ACCOMODATION
| Cost of accommodation per person-day ($/pp) | 119.2587 |  | 119.2587 | 119.2587 | 119.2587 | 119.2587
| Cost for camp fuel per person-day ($/pp) | 115.5 |  | 115.5 | 115.5 | 115.5 | 115.5
| Accomodation Costs | -227714.5317 |  | -129535.7387 | -98178.793 | 6878.4295 | -234592.9612
| TOTAL | -227714.5317 |  | -129535.7387 | -98178.793 | 6878.4295 | -234592.9612
WORKER MOBILIZATION (FLIGHTS)
| Person Days On-Site | -969.9941 |  | -551.7825 | -418.2115 | 29.3 | -999.2941
| Southern Hires (70%) | -678.9958 |  | -386.2478 | -292.7481 | 20.51 | -699.5058
| Northern Hires (30%) | -290.9982 |  | -165.5348 | -125.4635 | 8.79 | -299.7882
| Cost Southern Communities | -62903.7476 |  | -35782.8873 | -27120.8604 | 1900.0939 | -64803.8415
| Cost northern Communities | -23661.8628 |  | -13460.0846 | -10201.7781 | 714.739 | -24376.6018
| Total Cost | -86565.6104 |  | -49242.9719 | -37322.6385 | 2614.8329 | -89180.4433
Inflation reading (September)
| Base year from which Statistics Canada measures inflation (2002) | 100
| Base year for which the inflation adjustment is taken (2018 Unit Rate Update) | 129.5
| Current year of Property mining operations (2022) | 140.4 | Consumer Price Index by geography, all-items, monthly, percentage change, not seasonally adjusted, Canada, provinces, Whitehorse, Yellowknife and Iqaluit (statcan.gc.ca)
| Inflation Adjustment multiplier - to be applied to Rent and other compensation | 0.08417

## Global Estimate
GLOBAL ESTIMATE
|  |  |  | IOL | Crown | Water | Land
| DIRECT COST SUB-TOTAL (Reconcillation + New Scope) | 39861429.651 |  | 39185964.2549 | 675465.3961 | 1561322.8775 | 38300106.7735
| TOTAL PERSON-HOURS | 219096.5585 |  | 215036.5366 | 4060.0219 | 6715.25 | 212381.3085
| TOTAL PERSON-DAYS | 21909.6559 |  | 21503.6537 | 406.0022 | 671.525 | 21238.1309
| Off-Site Disposal of Waste & Material | 2327000 |  | 2327000 | 0 | 0 | 2327000
| Fuel | 7055758.162 |  | 7016830.8332 | 38927.3289 | 68845.552 | 6986912.6101
| Ammonium Nitrate | 5384363.6364 |  | 5384363.6364 | 0 | 0 | 5384363.6364
| Contaminated Soil Treatment | 633730.4593 |  | 633730.4593 | 0 | 0 | 633730.4593
| Mobilization of Workers Required for Reclamation | 1955293.1454 |  | 1919060.1117 | 36233.0337 | 59929.2037 | 1895363.9416
| Worker Accommodation & Camp Operation | 5143482.046 |  | 5048169.5048 | 95312.5412 | 157646.3275 | 4985835.7185
| Demobilization of Phase 2 Modules | 16798750.26 |  | 16798750.26 | 0 | 0 | 16798750.26
| Demobilization of 3rd Party Equipment | 2110230.2 |  | 2110230.2 | 0 | 0 | 2110230.2
10% | Mobilization and Demobilization of Equipment and Materials by Sealift | 3986142.9651 |  | 3918596.4255 | 67546.5396 | 156132.2877 | 3830010.6773
| Closure & Post Closure Monitoring | 5613466.6201 |  | 5613466.6201 | 0 |  | 5613466.6201
5% | Engineering Fees | 1993071.4825 |  | 1959298.2127 | 33773.2698 | 78066.1439 | 1915005.3387
9.4% | Supervision, Project Management & Contract Administration | 4334210.9127 |  | 4270717.1654 | 63493.7472 | 146764.3505 | 4187446.5622
20% | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 9221725.3461 |  | 9086632.2669 | 135093.0792 | 312264.5755 | 8909460.7706
| INDIRECT SUB-TOTAL | 66557225.2355 |  | 66086845.6959 | 470379.5396 | 979648.4408 | 65577576.7947
| TOTAL | 106418654.8865 |  | 105272809.9508 | 1145844.9357 | 2540971.3183 | 103877683.5682
= pulls data from Indirects spreadsheets
= linked back to EBS 'Estimate Details' Indirects section
| Total Direct Cost |  | 39861429.651 | 39185964.2549 | 675465.3961 | 1561322.8775 | 38300106.7735
| Total direct cost+Contaminated soil+post closure monitoring |  | 46108626.7304 | 45433161.3343 | 675465.3961 | 1561322.8775 | 44547303.8529
| Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  | 59303775.0868 | 58429217.5763 | 874557.5105 | 1935030.6965 | 57368744.3904
| Mobilization and Demobilization of Equipment and Materials by Sealift | 10% | 3986142.9651 | 3918596.4255 | 67546.5396 | 156132.2877 | 3830010.6773
| Demob of Phase 2 Modules |  | 16798750.26 | 16798750.26 | 0 | 0 | 16798750.26
| Demob of 3rd Party Equipment by sealift |  | 2110230.2 | 2110230.2 | 0 | 0 | 2110230.2
| Engineering | 5% | 1993071.4825 | 1959298.2127 | 33773.2698 | 78066.1439 | 1915005.3387
| Project supervision, management & contract administration | 9.4% | 4334210.9127 | 4270717.1654 | 63493.7472 | 146764.3505 | 4187446.5622
| Contingency | 20% | 9221725.3461 | 9086632.2669 | 135093.0792 | 312264.5755 | 8909460.7706
FUEL ON-SITE
| Increase to Fuel Capacity @ site (L) | 82100000 |  | 82100000 | 0 | 0 | 82100000
| Demob cost per Litre | 0.10842 |  | 0.10842 | 0.10842 | 0.10842 | 0.10842
| Reclamation Activities (L) | 3476889.9127 |  | 3434020.1833 | 42869.7294 | 81190.625 | 3395699.2877
| Heat and Power (L) | 2530565.2508 |  | 2483671.9979 | 46893.253 | 77561.1375 | 2453004.1133
| Total fuel required during closure (L) | 6007455.1635 |  | 5917692.1812 | 89762.9824 | 158751.7625 | 5848703.401
| Cost to mob. Fuel per Litre | 0.43367 |  | 0.43367 | 0.43367 | 0.43367 | 0.43367
| Demob 50% of total capacity | 4450517.3745 |  | 4450517.3745 | 0 | 0 | 4450517.3745
| Mob 100% fuel required during closure | 2605240.7875 |  | 2566313.4586 | 38927.3289 | 68845.552 | 2536395.2355
| Total Mob/Demo Fuel | 7055758.162 |  | 7016830.8332 | 38927.3289 | 68845.552 | 6986912.6101
CAMP FUEL CONSUMPTION
| 1732500 | Avg Monthly Consumption |  | 1732500 | 1732500 | 1732500 | 1732500
| 30 | Days in month |  | 30 | 30 | 30 | 30
| 500 | Average camp population |  | 500 | 500 | 500 | 500
| 115.5 | L/Man-day |  | 115.5 | 115.5 | 115.5 | 115.5
| 1 | $/L fuel cost |  | 1 | 1 | 1 | 1
WORKERS ACCOMODATION
| Cost of accomodation per person-day ($/pp) | 119.2587 |  | 119.2587 | 119.2587 | 119.2587 | 119.2587
| Cost for camp fuel per person-day ($/pp) | 115.5 |  | 115.5 | 115.5 | 115.5 | 115.5
| Accomodation Costs | 5143482.046 |  | 5048169.5048 | 95312.5412 | 157646.3275 | 4985835.7185
| TOTAL | 5143482.046 |  | 5048169.5048 | 95312.5412 | 157646.3275 | 4985835.7185
FLIGHTS
| Person Days On-Site | 21909.6559 |  | 21503.6537 | 406.0022 | 671.525 | 21238.1309
| Southern Hires (70%) | 15336.7591 |  | 15052.5576 | 284.2015 | 470.0675 | 14866.6916
| Northern Hires (30%) | 6572.8968 |  | 6451.0961 | 121.8007 | 201.4575 | 6371.4393
| Cost Southern Communities | 1420832.8918 |  | 1394503.8034 | 26329.0884 | 43548.1422 | 1377284.7497
| Cost northern Communities | 534460.2536 |  | 524556.3082 | 9903.9453 | 16381.0616 | 518079.192
| Total Cost | 1955293.1454 |  | 1919060.1117 | 36233.0337 | 59929.2037 | 1895363.9416
| For UR updated in 2018 | Inflation reading (September)
| Base year from which Statistics Canada measures inflation (2002) | 100
| Base year for which the inflation adjustment is taken (2018 Unit Rate Update) | 129.5
| Current year of Property mining operations (2022) | 140.4 | Consumer Price Index by geography, all-items, monthly, percentage change, not seasonally adjusted, Canada, provinces, Whitehorse, Yellowknife and Iqaluit (statcan.gc.ca)
| Inflation Adjustment multiplier - to be applied to Rent and other compensation | 0.08417
| UR not updated in 2018 (2014 rates) | Inflation reading (September)
| Base year from which Statistics Canada measures inflation (2002) | 100
| Base year for which the inflation adjustment is taken (2014 Unit Rate Update) | 118.8
| Current year of Property mining operations (2022) | 140.4 | Consumer Price Index by geography, all-items, monthly, percentage change, not seasonally adjusted, Canada, provinces, Whitehorse, Yellowknife and Iqaluit (statcan.gc.ca)
| Inflation Adjustment multiplier - to be applied to Rent and other compensation | 0.18182

## Cost Summary (hidden)
#REF!
[6 empty] | Quantities have been Superceeded | [14 empty] | 854624.2644
[9 empty] | Unit |  |  | Totals
|  | Area | Qty Code | Unit Price Code | Item | Qty | Qty | Unit | Hours | Fuel ($) | Const. Equip | Hours | Fuel ($) | Labour Cost | Equiment Cost | All in Unit Cost | Final Direct Cost | Round | OLD Cost(REV. C) | Difference | Includes | Check | Unit M3 | Total M3 | Total M3 | Difference
|  | Siteworks |  | A2 | Fill Application |  | #REF! | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 913560.7689 | #REF! | Qty based on 2013 Marginal 2014 workplan (CG). Assume depth of 6 m3 | #REF! | #REF! | #REF! | 0 | #REF!
A2 | A3 |  | A2 | A3 | Grade and Re-Contour | #REF! | 10051234.0182 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4441950.2782 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
A3l | A3l |  | A9 | A3 | Grade and Re-Contour of Building Footprints | #REF! | 69066.8402 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 49918.281 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
Cu | Cu |  | A3l | A3l | Grade and Re-Contour With Liner | #REF! | 128823.76 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 363393.9282 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
Cu | Cu |  | A4 | A4 | Grade and Re-Contour Significant Disturbed Areas |  | 264871 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 512060.6017 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
Bridges | Not in estimate |  | cu | cu | Removal of Culverts | #REF! | 537 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 419185.9494 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
EG | EG |  | BR | BR | Bridge Removal (1/3 of installation of bridge span from schedule) | 4 | 4 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 807355.0658 | #REF! |  | #REF! | #REF! | #REF! | 20000 | #REF!
FW | FW | Flooring/Foundations | EG | EG | Total Gravel Base | #REF! | 21385.7084 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | Included in Buildings Structures demo | #REF! | #REF! | #REF! | 0 | #REF!
FT | FW |  | FW | FW | Wood Floor | #REF! | 17496.4384 | m2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Included in Buildings Structures demo |  | #REF! | #REF! | 5156.3197 | #REF!
CP | CP |  | FT | FW | Timber Cribbing | #REF! | 1892.9368 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 39344.0523 | #REF! |  | #REF! | #REF! | #REF! | 567.881 | #REF!
CS | CS |  | CP | CP | Precast Foundations | #REF! | 16814.6654 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 369655.9211 | #REF! | Assume 100% of pre cast installation | #REF! | #REF! | #REF! | 7207.2491 | #REF!
O1 | O1 |  | CS | CS | Slab on Grade | #REF! | 30243.4783 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 535571.3519 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
O2 | O2 | Mobile Equipment | O1 | O1 | Mobile Equipment 1 (Small) | #REF! | 511 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 169396.0571 | #REF! | Fork Lifts | #REF! | #REF! | #REF! | 720 | #REF!
O3 | O3 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Picks up |  |  |  |  | 0
FTR1-c | FF1-c | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Vehicles around 5T and under |  |  |  |  | 0
FTR2-c | FF1-c | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Scissor Lift |  |  |  |  | 0
FS-c | FF1-c | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Man Lifts |  |  |  |  | 0
FFL-c | FF2-c | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Small Garbage Bins |  |  |  |  | 0
FC-c | FF1-c |  | O2 | O2 | Mobile Equipment 2 (Medium) | #REF! | 482 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 125507.24 | #REF! | Vehicles around 20T | #REF! | #REF! | #REF! | 2016 | #REF!
FTR1 | FF1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Trailers |  |  |  |  | 0
FTR2 | FF1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Buses |  |  |  |  | 0
FS | FF1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Tow Trucks |  |  |  |  | 0
FFL | FF1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Large Garbage Bins |  |  |  |  | 0
FF3 | FF1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Water Trucks |  |  |  |  | 0
FC | FF1 |  | O3 | O3 | Mobile Equipment 3 (Large) | #REF! | 436 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 319502.6222 | #REF! | Vehicles over 10T | #REF! | #REF! | #REF! | 11712 | #REF!
piping | piping | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Boom Trucks |  |  |  |  | 0
Piping - Heat Tracing | No cost | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | All hiboy trailers |  |  |  |  | 0
cable | cable | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Graders |  |  |  |  | 0
MM1 | MM1 | [12 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Cranes |  |  |  |  | 0
MM2 | MM2 | Buildings (Contaminated) | FTR1-c | FF1-c | Single Trailers (modular) | #REF! | 424.2714 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 40626.2492 | #REF! |  | #REF! | #REF! | #REF! | 283.2714 | #REF!
MMED | MM2 |  | FTR2-c | FF1-c | Double Trailer (2 or more) | #REF! | 1338.29 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 191935.0357 | #REF! |  |  | #REF! | #REF! | 1338.29 | #REF!
MM3 | MM3 |  | FS-c | FF1-c | Prefabricated Special Modular | #REF! | 1105.3903 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 158533.008 | #REF! |  |  | #REF! | #REF! | 1105.3903 | #REF!
MT1 | MT1 |  | FFL-c | FF2-c | Fold Away Building | #REF! | 18203.7486 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1513206.1983 | #REF! |  | #REF! | #REF! | #REF! | 10625.7486 | #REF!
MISC | MISC |  | FF3-c | FF3-c | Soft walled Building (tent) | #REF! | 6557.5248 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 316058.771 | #REF! |  | #REF! | #REF! | #REF! | 1065.2624 | #REF!
|  |  | 25ka | 25ka | Temporary construction warehouses and offices Allowance |  | 2 | Lot | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 50000 | #REF! |  | #REF! | #REF! | #REF! | 0 | #REF!
MT2 | MT2 |  | FC-c | FF1-c | ISO Shipping Containers | #REF! | 737.9182 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 34121.7841 | #REF! |  |  | #REF! | #REF! | 237.9182 | #REF!
MT1-d | MT1-d | Buildings (Not Contaminated) | FTR1 | FF1 | Single Trailers (modular) | #REF! | 963.0595 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 46359.8417 | #REF! |  | #REF! | #REF! | #REF! | 780.6691 | #REF!
MT2-d | MT2-d |  | FTR2 | FF1 | Double Trailer (2 or more) | #REF! | 2988.7546 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 97521.9117 | #REF! |  |  | #REF! | #REF! | 1642.2046 | #REF!
MT3-d | MT3-d |  | FS | FF1 | Prefabricated Special Modular | #REF! | 37804.782 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 748700.4049 | #REF! |  |  | #REF! | #REF! | 12607.6208 | #REF!
MT4-d | MT4-d |  | FFL | FF2 | Fold Away Building | #REF! | 2157.7844 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 86538.3711 | #REF! |  | #REF! | #REF! | #REF! | 2081.7844 | #REF!
MISC | MISC |  | FF3 | FF3 | Soft walled Building (tent) | #REF! | 15709.48 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 656058.0091 | #REF! |  | #REF! | #REF! | #REF! | 6904.74 | #REF!
CV | CV |  | FC | FF4 | ISO Shipping Containers | #REF! | 417.658 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7947.4014 | #REF! |  |  | #REF! | #REF! | 267.658 | #REF!
|  | Bulks | piping | piping | Piping | 19623 | 22623 | m | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1299598.8186 | #REF! | Only large bore piping accounted for. Small more piping assumed to included in building removal | #REF! | #REF! | #REF! | 196.23 | #REF!
|  |  | Piping - Heat Tracing |  | Piping - Heat Tracing | #REF! | 10958 | m | [5 empty] | 0 |  | #REF! | 0 | 0 | 0 | 0 | Included in Piping |  |  | 0 | 0 | 0 |  |  | 17657
|  |  | cable | cable | Cable | #REF! | 34300 | m | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 723213.53 | #REF! |  | #REF! | #REF! | #REF! | 273 | #REF! |  |  | 5594
|  | Vendor Packages | VP6 | VP6 | VENDOR PKG - Ship Loader | #REF! | 0 | Lot | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3827468.528 | #REF! | Based on estimated duration of 4mth and crew of 20. Benchmared against 10-12 hrs per MT | #REF! | #REF! | #REF! | 30295 | #REF! |  |  | 7044
|  |  | VP1 | VP1 | VENDOR PKG - Incinerator | #REF! | 4 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19951.8578 | #REF! |  | #REF! | #REF! | #REF! | 658.5366 | #REF! |  |  | 30295
|  |  | VP2 | VP2 | VENDOR PKG - Potable Water | #REF! | 4 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19951.8578 | #REF! |  | #REF! | #REF! | #REF! | 658.5366 | #REF!
|  |  | VP3 | VP3 | VENDOR PKG - Sewage Treatment Plant | #REF! | 4 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 22071.1649 | #REF! |  | #REF! | #REF! | #REF! | 658.5366 | #REF!
|  | Mechanical | MM1 | MM1 | Mechanical - Small | #REF! | 191 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 346639.7175 | #REF! |  | #REF! | #REF! | #REF! | 87.5 | #REF!
|  |  | 0 | [10 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Pumps |  |  | 0 | 0 | 0
|  |  | 0 | [10 empty] | 0 |  |  | 0 | 0 | 0 | 0 | Lab Equipment |  |  |  |  | 0
|  |  | 0 | [10 empty] | 0 |  |  | 0 | 0 | 0 | 0 | shop maintenance equipment |  |  |  |  | 0
|  |  | 0 | [10 empty] | 0 |  |  | 0 | 0 | 0 | 0 | No tanks |  |  |  |  | 0
|  |  | MM2 | MM2 | Mechanical - Medium | #REF! | 182 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 553973.7989 | #REF! | Includes Chutes | #REF! | #REF! | #REF! | 130 | #REF! | Small | #REF!
|  |  | MM3 | MM3 | Mechanical - Large | #REF! | 56 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1112547.096 | #REF! |  | #REF! | #REF! | #REF! | 1512 | #REF! | Med | #REF!
|  |  | MT1 | MT1 | Tanks - Small | #REF! | 28 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 30076.6109 | #REF! |  | #REF! | #REF! | #REF! | 14 | #REF! | Large | #REF!
|  |  | MT2 | MT2 | Tanks - Medium | #REF! | 28 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 155133.611 | #REF! | 3m and larger | #REF! | #REF! | #REF! | 42 | #REF! | Largest | #REF!
|  |  | MT3 | MT3 | Tanks - Large | 0 | 0 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0 | #REF! |  |  | #REF! | #REF! | 0 | #REF!
|  |  | MT1-d | MT1-d | Tanks (Diesel) - Small | #REF! | 22 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 40630.2315 | #REF! |  | #REF! | #REF! | #REF! | 220 | #REF!
|  |  | MT2-d | MT2-d | Tanks (Diesel) - Medium | #REF! | 9 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 84530.203 | #REF! |  | #REF! | #REF! | #REF! | 320 | #REF!
|  |  | MT3-d | MT3-d | Tanks (Diesel) - Large | #REF! | 2 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 154114.1178 | #REF! | Approx. 10m x 10m - 5 million L | #REF! | #REF! | #REF! | 160 | #REF!
|  |  | MT4-d | MT4-d | Tanks (Diesel) - Largest | #REF! | 6 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 531684.1892 | #REF! | Approx. 25m x 15m - 10 million L | #REF! | #REF! | #REF! | 640 | #REF!
|  |  | MT5-d | MT5-d |  |  | #N/A | [15 empty] | #REF! | #REF! | 641 | #REF!
|  |  | MISC | MISC | Minor Items (very small) | #REF! | 0 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6887.7479 | #REF! | Items under 200kg (battery chargers etc.) | #REF! | #REF! | #REF! | 6.5 | #REF!
|  |  | CV | CV | Reclaim Conveyor | 1 | 1 | ea | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1329441.311 | #REF! |  | #REF! | #REF! | #REF! | 1020 | #REF!
[24 empty] | #REF! | 123211.8474 | #REF!
[5 empty] | Total Direct | [6 empty] | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | 23351397.5102 | #REF!
|  | Indirects |  |  | Off-Site Disposal of Waste & Material | [11 empty] | #REF! |  | 311000 | #REF!
[5 empty] | Fuel | [11 empty] | #REF! |  | 2907000 | #REF!
[5 empty] | Ammonium Nitrate | [11 empty] | #REF! |  | 876000 | #REF!
[5 empty] | Contaminated Soil Treatment |  | 5500 | m3 |  |  |  |  | $358/m3 |  |  |  | #REF! |  | 234000 | #REF!
0
[5 empty] | Mobilization of Workers Required for Reclamation |  | 14 | Flights | Confirm unit rate is return |  |  |  | 120000 |  |  |  | #REF! |  | 944000 | #REF!
[5 empty] | Worker Accommodation & Camp Operation |  |  |  | Icluding camp fuel consumption and workers accomodation | [7 empty] | #REF! |  | 2503000 | #REF!
[5 empty] | Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | of Total Direct Cost | [8 empty] | #REF! |  | 2335000 | #REF!
0
[5 empty] | Geotechnical Inspections | [11 empty] | #REF! |  | 150000 | #REF!
[5 empty] | Project Environmental Site Assessment | [11 empty] | #REF! |  | 90000 | #REF!
[5 empty] | Closure & Post Closure Monitoring | [11 empty] | #REF! |  | 851000 | #REF!
0
[5 empty] | Engineering Fees |  | 3.9% | of Total Direct Cost | [8 empty] | #REF! |  | 701000 | #REF!
[5 empty] | Supervision, Project Management & Contract Administration |  | 9.4% | of Total Direct Cost, Contaminated Soil Treatement and Post Closure Monitoring | [8 empty] | #REF! |  | 2195000 | #REF!
0
[5 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring |  | 12.5% | of direct Costs, Mobilization and Post-Closure Monitoring | [8 empty] | #REF! |  | 3022000 | #REF!
0
[5 empty] | Total Inirect | [11 empty] | #REF! |  | 17119000 | #REF!
Sum of QTY
[5 empty] | Total Cost | [11 empty] | #REF! | #REF! | 40470397.5102 | #REF! | [14 empty] | Price Code | Description | Unit | Total
[35 empty] | EG |  |  | 218952
[35 empty] | (blank) |  |  | 21763.63
[35 empty] | Blank |  |  | 0
[35 empty] | FC |  |  | 2880
[35 empty] | FW |  |  | 184940
[24 empty] | #REF! | [10 empty] | O1 |  |  | 180
[12 empty] | Sum of QTY | [22 empty] | O3 |  |  | 122
[12 empty] | Qty Code | Unit | Total |  |  | Direct |  |  |  | 25484018.5943 | [13 empty] | O2 |  |  | 84
[12 empty] | A2 | m2 | 10051234.0182 | 10051234.0182 | TRUE | Indirect |  |  |  | 21190000 | [13 empty] | FTR1 |  |  | 8400
[12 empty] | A3l | m2 | 128823.76 | 128823.76 | TRUE | Total | [17 empty] | MMED - weight req. |  |  | 5
[12 empty] | Br | r | 4 | 4 | TRUE |  |  |  |  | 46674018.5943 | [13 empty] | Conveyor |  |  | 2
[12 empty] | Cable | m | 34300 | 34300 | TRUE | [18 empty] | Ship Loader |  |  | 68
[12 empty] | CP | m2 | 16814.6654 | 16814.6654 | TRUE | [18 empty] | FTR2 |  |  | 7680
[12 empty] | CS | m2 | 30243.4783 | 30243.4783 | TRUE | [18 empty] | FT |  |  | 20368
[12 empty] | cu | r | 537 | 537 | TRUE | [18 empty] | FFL |  |  | 22400
[12 empty] | EG | m2 | 21385.7084 | 21385.7084 | TRUE | [18 empty] | CP |  |  | 103400
[12 empty] | FC | m2 | 417.658 | 417.658 | TRUE | [18 empty] | CS |  |  | 115301.59
[12 empty] | FC-c | m2 | 737.9182 | 737.9182 | TRUE | [18 empty] | Piping |  |  | 17209.97
[12 empty] | FF3 | m2 | 15709.48 | 15709.48 | TRUE | [18 empty] | FS |  |  | 135658
[12 empty] | FFL | m2 | 2157.7844 | 2157.7844 | TRUE | [18 empty] | MISC |  |  | 21
[12 empty] | FFL-c | m2 | 18203.7486 | 18203.7486 | TRUE | [18 empty] | VP incinerator |  |  | 2
[12 empty] | FS | m2 | 37804.782 | 37804.782 | TRUE | [18 empty] | VP Potable water |  |  | 2
[12 empty] | FS-c | m2 | 1105.3903 | 1105.3903 | TRUE | [18 empty] | STP | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | m2 | 1920
[12 empty] | FT | m2 | 1892.9368 | 1892.9368 | TRUE | [19 empty] | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE | Ea | 2
[12 empty] | FTR1 | m2 | 963.0595 | 963.0595 | TRUE | [18 empty] | STP Total |  |  | 1922
[12 empty] | FTR1-c | m2 | 424.2714 | 424.2714 | TRUE | [18 empty] | Piping - Heat Tracing |  |  | 10958
[12 empty] | FTR2 | m2 | 2988.7546 | 2988.7546 | TRUE | [18 empty] | Cable |  |  | 27300
[12 empty] | FTR2-c | m2 | 1338.29 | 1338.29 | TRUE | [18 empty] | VP Truck wash facility |  |  | 1
[12 empty] | FW | m2 | 17496.4384 | 17496.4384 | TRUE | [18 empty] | MM1 |  |  | 172
[12 empty] | MISC | r | 0 | 0 | TRUE | [18 empty] | MM2 |  |  | 110
[12 empty] | MM1 | r | 191 | 191 | TRUE | [18 empty] | MM3 |  |  | 27
[12 empty] | MM2 | r | 182 | 182 | TRUE | [18 empty] | MT2 |  |  | 21
[12 empty] | MM3 | r | 56 | 56 | TRUE | [18 empty] | MT1 |  |  | 14
[12 empty] | MT1 | r | 28 | 28 | TRUE | [18 empty] | MT1-d |  |  | 11
[12 empty] | MT1-d | r | 22 | 22 | TRUE | [18 empty] | MT2-d |  |  | 8
[12 empty] | MT2 | r | 28 | 28 | TRUE | [18 empty] | MT3-d |  |  | 2
[12 empty] | MT2-d | r | 9 | 9 | TRUE | [18 empty] | MT4-d | TANK - ARCTIC DIESEL TANK W: 27800 DI H: 15250 |  | 4
[12 empty] | MT3-d | r | 2 | 2 | TRUE | [18 empty] | MT4-d Total |  |  | 4
[12 empty] | MT4-d | r | 6 | 6 | TRUE | [18 empty] | FFL-c | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 14400
[12 empty] | O1 | r | 511 | 511 | TRUE | [19 empty] | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 14400
[12 empty] | O2 | r | 482 | 482 | TRUE | [19 empty] | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 4000
[12 empty] | O3 | r | 436 | 436 | TRUE | [19 empty] | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 35600
[12 empty] | Piping | m | 22623 | 22623 | TRUE | [19 empty] | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 340
[12 empty] | Piping - Heat Tracing | m | 10958 | 10958 | TRUE | [19 empty] | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) |  | 340
[12 empty] | Ship Loader | r | 14 | #N/A | #N/A | [19 empty] | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 1200
[12 empty] | VP7 | r | 1 | #N/A | #N/A | [19 empty] | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 10800
[12 empty] | (blank) | r | 6 | #N/A | #N/A | [19 empty] | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 3600
[13 empty] | m2 | 5201.62 | 0 | FALSE | [19 empty] | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 9600
[13 empty] | N/A | 0 | 0 | TRUE | [19 empty] | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 9600
[13 empty] | (blank) |  | 0 | TRUE | [13 empty] | Sum of QTY |  | Total Fuel Consumption |  |  |  | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 5800
[12 empty] | 25ka | Lot | 2 | [6 empty] | Price Code | Description | [7 empty] | Price Code | Description | Contaminated | Not Contaminated | Grand Total | FFL-c Total |  |  | 109680
[12 empty] | A4 | m2 | 264871 | [6 empty] | MT2 | TANK - AERODROME OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [7 empty] | FC | Communication Shed - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 | FTR2-c | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 3680
[12 empty] | FF3-c | m2 | 6557.5248 | [7 empty] | TANK - BACKWASH SETTLING TANK | [8 empty] | Communication Shed No. 1 - Demolish and Decontaminate Building - ISO Shipping Container |  | 320 | 320 |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 3840
[12 empty] | VP6 | Lot | 0 | 0 | TRUE | [5 empty] | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 10 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 1120
[12 empty] | VP1 | r | 4 | 4 | TRUE | [5 empty] | TANK - EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 11 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 5760
[12 empty] | VP2 | r | 4 | 4 | TRUE | [5 empty] | TANK - FIRE WATER TANK | [8 empty] | Communication Shed No. 2 - Demolish and Decontaminate Building - ISO Shipping Container |  | 320 | 320 | FTR2-c Total |  |  | 14400
[12 empty] | VP3 | r | 4 | 4 | TRUE | [5 empty] | TANK - FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 3 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 | FTR1-c | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single |  | 360
[12 empty] | CV | r | 1 | 1 | TRUE | [5 empty] | TANK - POTABLE WATER STORAGE TANK | [8 empty] | Communication Shed No. 4 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single |  | 384
[12 empty] | A9 | m2 | 27569 | 69066.8402 | FALSE | [5 empty] | TANK - RAW WATER TANK | [8 empty] | Communication Shed No. 5 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single |  | 768
[12 empty] | Indirect | (blank) |  | #N/A | #N/A | [5 empty] | TANK - SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 6 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single |  | 768
[12 empty] | Fill | r | 1192.1667 | #N/A | #N/A | [5 empty] | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 7 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single |  | 768
[13 empty] | m2 | 40787.0815 | 0 | FALSE | [5 empty] | TANK - TREATED EFFLUENT TANK | [8 empty] | Communication Shed No. 8 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 | FTR1-c Total |  |  | 3048
[12 empty] | MT5-d | r | 25 | #N/A | #N/A | [5 empty] | TANK - WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Communication Shed No. 9 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 | FS-c | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 160
[12 empty] | A5 | m2 | 682 | [6 empty] | MT2 Total | [9 empty] | Emergency Shelter No. 1 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | m2 | 848
[12 empty] | CON | Bed Space | 1989 | [6 empty] | MT1 | TANK - AERODROME OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | [8 empty] | Emergency Shelter No. 2 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1530
[12 empty] | Grand Total |  | 10769027.5354 | [7 empty] | TANK - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1613 W: 737 H: 1676 | [8 empty] | Emergency Shelter No. 3 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1530
[22 empty] | TANK - EMERGENCY RESPONSE OFFICE RAW WATER TANK - NORWESCO L: 1613 W: 737 H: 1676 | [8 empty] | Emergency Shelter No. 4 - Demolish and Decontaminate Building - ISO Shipping Container |  | 160 | 160 |  | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[22 empty] | TANK - FUEL SYSTEMS WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | [7 empty] | FC Total |  |  | 2880 | 2880 |  | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[22 empty] | TANK - SITE SERVICES WASHCAR #1 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | [7 empty] | FTR1 | Aerodrome Office - Demolish and Decontaminate Building - Trailer - Single |  | 1440 | 1440 |  | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[22 empty] | TANK - SITE SERVICES WASHCAR #2 RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | [8 empty] | Batch Plant Office-Lunchroom-W/C - Demolish and Decontaminate Building - Trailer - Single |  | 1440 | 1440 |  | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[22 empty] | TANK - SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK - LAGRANGE MECHANICAL SERVICES L: 3791 W: 1829 H: 610 | [8 empty] | Dock Office - Demolish and Decontaminate Building - Trailer - Single |  | 480 | 480 |  | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[22 empty] | TANK - WORKSHOP OFFICE WASHCAR RAW WATER TANK - PLASTIC-MART 866-310-2556 L: 1803 W: 1245 H: 1346 | [8 empty] | Fuel Systems Lunchroom - Demolish and Decontaminate Building - Trailer - Single |  | 1200 | 1200 |  | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1118
[21 empty] | MT1 Total | [9 empty] | Fuel Systems Office - Demolish and Decontaminate Building - Trailer - Single |  | 480 | 480 |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 559
[21 empty] | Grand Total | [9 empty] | Pit Office Washcar - Demolish and Decontaminate Building - Trailer - Single |  | 480 | 480 |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 559
[31 empty] | Quarry Lunchroom - Demolish and Decontaminate Building - Trailer - Single |  | 0 | 0 | FS-c Total |  |  | 11894
[31 empty] | Quarry Washcar - Demolish and Decontaminate Building - Trailer - Single |  | 0 | 0 | FC-c | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container |  | 320
[31 empty] | Site Services Lunchroom #1 - Demolish and Decontaminate Building - Trailer - Single |  | 1440 | 1440 |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container |  | 480
[31 empty] | Site Services Lunchroom #2 - Demolish and Decontaminate Building - Trailer - Single |  | 1440 | 1440 |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container |  | 160
[30 empty] | FTR1 Total |  |  | 8400 | 8400 |  | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container |  | 640
[30 empty] | FTR2 | Construction Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 2880 | 2880 |  | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container |  | 640
[31 empty] | Emergency Response Office - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 1920 | 1920 |  | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container |  | 320
[31 empty] | Pit Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) |  | 2880 | 2880 | FC-c Total |  |  | 2560
[30 empty] | FTR2 Total |  |  | 7680 | 7680 | FF1 | Exploration Workshops | m2 | 432.44
[30 empty] | FFL | Emergency Response Garage - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 6000 | 6000 |  | Existing Trailer Camp | m2 | 928.45
[31 empty] | Site Services Heated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 4000 | 4000 |  | Matrix Camp | m2 | 5392.34
[31 empty] | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 4000 | 4000 | FF1 Total |  |  | 6753.23
[31 empty] | Water Building - Demolish and Decontaminate Building - Fold-away Building (Steel) |  | 8400 | 8400 | cu | Culverts | each | 356
[30 empty] | FFL Total |  |  | 22400 | 22400 | cu Total |  |  | 356
[30 empty] | FS | Accommodation Laboratory - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 3360 | 3360 | FF3 | Exploration Soft-Wall Camp | m2 | 6017.14
[31 empty] | Accommodation Laundry - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 9120 | 9120 |  | Exploration Tent Camp Tents | m2 | 2400
[31 empty] | Accommodation Office - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 10140 | 10140 |  | Exploration Tents | m2 | 360
[31 empty] | Accommodation Service Core - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 34920 | 34920 | FF3 Total |  |  | 8777.14
[31 empty] | Accommodation Wing AA - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 | VP7 | Exploration STP | Ea | 1
[31 empty] | Accommodation Wing AB - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 | VP7 Total |  |  | 1
[31 empty] | Accommodation Wing AC - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 | A2 | Site Roads | m2 | 71575
[31 empty] | Accommodation Wing AD - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Existing Landfill | m2 | 5031.47
[31 empty] | Accommodation Wing AE - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Existing Laydown Area | m2 | 17366.92
[31 empty] | Accommodation Wing AF - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Ore Stockpiles | m2 | 5100.23
[31 empty] | Accommodation Wing AG - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | 2008 Bulk Sample Pit | m2 | 18207.39
[31 empty] | Accommodation Wing BA - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Pit 1 | m2 | 0
[31 empty] | Accommodation Wing BB - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Waste Rock Dump from Bulk Sample | m2 | 5944.1
[31 empty] | Accommodation Wing BC - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Exploration Phase PWSP | m2 | 1451.9
[31 empty] | Accommodation Wing BD - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 6583 | 6583 |  | Ore Stockpile Laydown | m2 | 230545.88
[31 empty] | Accomodation Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 1280 | 1280 |  | Ore Stockpile Footprints | m2 | 128865.8
[31 empty] | Accomodation Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 800 | 800 |  | Batch Plant Stockpile | m2 | 5180.44
[31 empty] | Aerodrome Area E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 400 | 400 |  | Milne Laydown Area | m2 | 37375
[31 empty] | Crushing & Screening E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 640 | 640 |  | Q1 Quarry | m2 | 290000
[31 empty] | Fuel Tank Farm E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 425 | 425 |  | Q7 Quarry | m2 | 14600
[31 empty] | Raw Water Pumphouse - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 160 | 160 |  | Q11 Quarry | m2 | 17500
[31 empty] | Raw Water Supply E-House - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 400 | 400 |  | Q19 Quarry | m2 | 14600
[31 empty] | Services Area E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 800 | 800 |  | QMR2 Quarry | m2 | 322700
[31 empty] | Services Area E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated |  | 800 | 800 |  | D1Q1 Quarry | m2 | 27500
[30 empty] | FS Total |  |  | 135658 | 135658 |  | D1Q2 Quarry | m2 | 22500
[30 empty] | FFL-c | Concrete Batch Plant Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 14400 |  | 14400 |  | P1 Borrow Source | m2 | 55000
[31 empty] | Concrete Batch Plant Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 14400 |  | 14400 |  | Borrow Pit #1 | m2 | 27250
[31 empty] | Explosives Shop - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4000 |  | 4000 |  | Borrow Pit #2 | m2 | 9460
[31 empty] | Maintenance Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 35600 |  | 35600 |  | Borrow Pit #3 | m2 | 56730
[31 empty] | Marine Manifold Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 340 |  | 340 |  | Borrow Pit #4 | m2 | 31830
[31 empty] | Marine Manifold Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 340 |  | 340 |  | Borrow Pit #5 | m2 | 48240
[31 empty] | Sewage Truck Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 1200 |  | 1200 |  | Rock Quarry / Borrow Area N0. 2 | m2 | 16950
[31 empty] | Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 10800 |  | 10800 |  | Borrow development areas | m2 | 42080
[31 empty] | Truck Weigh Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 3600 |  | 3600 |  | Construction Laydown Area | m2 | 33576
[31 empty] | Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 9600 |  | 9600 | A2 Total |  |  | 1557160.13
[31 empty] | Waste Management Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 9600 |  | 9600 | A3l | Hazardous Waste Containment Area - Existing | m2 | 4550.98
[31 empty] | Welding Shop Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 5800 |  | 5800 |  | Fuel Farm Tank Dike | m2 | 1911.3
[30 empty] | FFL-c Total |  | 109680 |  | 109680 |  | Polishing Waste Stabilization Pond (Existing) | m2 | 7969.14
[30 empty] | FTR2-c | Explosives Plant Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 3680 |  | 3680 |  | Bulk Fuel Storage Facility (Bladder Farm) | m2- | 5787.68
[31 empty] | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 3840 |  | 3840 |  | Barreled Fuel Line Containment | m2 | 5411.65
[31 empty] | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 1120 |  | 1120 |  | Hazardous Waste Containment Area - New | m2 | 384.89
[31 empty] | Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 5760 |  | 5760 |  | Ore Crushing Sedimentation Pond | m2 | 6428.69
[30 empty] | FTR2-c Total |  | 14400 |  | 14400 |  | Existing Lined Storage Area | m2 | 985.34
[30 empty] | FTR1-c | Explosives Magazines - Demolish and Decontaminate Building - Trailer - Single | 360 |  | 360 |  | Ore Stockpile Settling Ponds | m2 | 11423.76
[31 empty] | Fuel Systems Washcar - Demolish and Decontaminate Building - Trailer - Single | 384 |  | 384 |  | Fuel Tank Farm Berm | m2 | 25393
[31 empty] | Site Services Washcar #1 - Demolish and Decontaminate Building - Trailer - Single | 768 |  | 768 |  | Existing Hazardous Waste Berm | m2 | 979.44
[31 empty] | Site Services Washcar #2 - Demolish and Decontaminate Building - Trailer - Single | 768 |  | 768 |  | Future Hazardous Waste Berm | m2 | 1784.35
[31 empty] | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 768 |  | 768 |  | Landfarm | m2 | 5554.73
[30 empty] | FTR1-c Total |  | 3048 |  | 3048 |  | Polishing Waste Stabilization Pond #2 | m2 | 4260.3
[30 empty] | FS-c | Aerodrome Field Electrical Centre - Demolish and Decontaminate Building - Special Modular / Prefabricated | 160 |  | 160 |  | Polishing Waste Stabilization Pond #3 | m2 | 4260.3
[31 empty] | Crushing & Screening Electrical Trailer - Demolish and Decontaminate Building - Special Modular / Prefabricated | 848 |  | 848 | A3l Total |  |  | 87085.55
[31 empty] | Power Generation E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1530 |  | 1530 | Grand Total |  |  | 2701704.24
[31 empty] | Power Generation E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1530 |  | 1530
[31 empty] | Power Generation Module #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #5 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #6 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 1118 |  | 1118
[31 empty] | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 559 |  | 559
[31 empty] | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 559 |  | 559
[30 empty] | FS-c Total |  | 11894 |  | 11894
[30 empty] | FC-c | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 320 |  | 320
[31 empty] | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 480 |  | 480
[31 empty] | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 160 |  | 160
[31 empty] | Power Generation Stores - Demolish and Decontaminate Building - ISO Shipping Container | 640 |  | 640
[31 empty] | Sewage Chemical Storage Container - Demolish and Decontaminate Building - ISO Shipping Container | 640 |  | 640
[31 empty] | Smoke Shack - Demolish and Decontaminate Building - ISO Shipping Container | 320 |  | 320
[30 empty] | FC-c Total |  | 2560 |  | 2560
[30 empty] | Grand Total |  | 141582 | 177018 | 318600
d

## Cost Summary New (hidden)
Associated Work Plan | (Multiple Items)
Type of Costs | Indirect
Row Labels | Unit | Sum of QTY
Indirect
Indirect | (blank)
(blank) | (blank)
Grand Total

## 1 - Volume Summary (hidden)
airstrip lighting removal (lump sum - incl removal & disposal)
Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction); Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
Disassembly & Decontaminate (Heavy), Load & transport, Disposal & Cover (incl compaction). Tear down on non-contaminated steel building
Disassembly & Decontaminate (Light Equipment), Load & transport, Disposal & Cover (incl compaction)
Disassembly & Decontaminate (Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
Fill Application
Grade and Re-Contour
Grade and Re-contour Borrow Source, Application of insulation material, Secondary application of Grade and Re-contour of Borrow Source
Grade and Re-Contour, airstrip lighting removal (lump sum - incl removal & disposal)
Grade and Re-Contour, Culvert Removal
Grade and Re-Contour, Culvert Removal, Removal of cable, Load & transport, Disposal & Cover (incl compaction)
Liner Removal, Liner disposal on-site, Grade & Recontour
Modular Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
Modular Building teardown, Load & transport, Disposal & Cover (incl compaction), Decontamination of a module
Open Pit Stabilization
Removal of bridge span (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
Removal of cable, Load & transport, Disposal & Cover (incl compaction)
Removal of Pipeline, decontaminate, Load & transport, disposal & cover (incl compaction)
Removal of pipeline, Load & transport, Disposal & Cover (incl compaction)
Removal of seacan bridge (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
Soil Excavation, Soil disposal off-site (TBD), Cover Application, Grade & Recontour
Soil Excavation, Soil disposal off-site (TBD), Liner Removal, Liner disposal off-site (TBD), Grade & Recontour
Soil Excavation, Soil disposal off-site, Liner Removal, Liner disposal off-site, Grade & Recontour
Steel Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
Steel Building teardown, Load & transport, Disposal & Cover (incl compaction), Disassembly & Decontaminate (Heavy Equipment)
Stockpile stabilization (?)
Teardown of steel tank, demobilization of fuel, decontaminate, Load & transport, disposal & cover (incl compaction)
Tote Road Culvert Removal, Load & Transport, Disposal & Cover (incl compaction)
|  |  |  | Counts |  | $
Code | Unit Rates | QTY | Unit | Manhours Per Unit | Fuel Consumption | Labour | Material | Equipment | Total Unit Cost | Assumed Volume Impact Per Unit
A1 | Disposal and Cover Incl (Compaction) | 1 | m2 | 0.65661 | 2.3125 | 64.135 |  | 24.6399 | 88.7749
| Disposal | 1 | m2 | 0.5 | 1 | 49.9567 |  | 10 | 59.9567 |  | In-House
| Cover and Compact assume 1m cover |  | m3 | 0.15661 | 1.3125 | 14.1783 |  | 14.6399 | 28.8182 |  | Earthworks Unit rate buildup
A2 | Fill Application - Assumed average Depth of 1.50 m3 | 1 | m2 | 0.23491 | 1.9688 | 21.2674 |  | 21.9599 | 43.2273
| Fill | 1 | m3 | 0.15661 | 1.3125 | 14.1783 |  | 14.6399 | 28.8182 |  | Earthworks Unit rate buildup
A3 | Grade & Re-Contour | 1 | m2 | 0.01269 | 0.14625 | 1.269 |  | 0.39655 | 1.8103 |  | Crew of 2 at all times
| Grade and Re-Countour assume .5m avg | 1 | m3 | 0.02538 | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | Earthworks Unit rate buildup
A3l | Grade & Re-Contour with Liner | 1 | m2 | 0.02269 | 0.15625 | 2.269 |  | 0.49655 | 2.9103 |  | Crew of 2 at all times +labour for liner removal
| Grade and Re-Countour assume .5m avg | 1 | m3 | 0.02538 | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | Earthworks Unit rate buildup
cu | Culvert Removal | 1 | Ea | 6 | 45 | 599.4803 |  | 450 | 1094.4803 |  | Assume 3 hours each x 2 people (including travel time). Assume mostly 6" culverts.
| Culvert Removal - | 1 | Ea | 6 | 45 | 599.4803 |  | 450 | 1094.4803
A5 | Liner Removal | 1 | m2 | 0.01 | 0.01 | 1 |  | 0.1 | 1.1
| Liner removal - 100% of typical installation | 1 | m2 | 0.01 | 0.01 | 1 |  | 0.1 | 1.1 |  | In-House
EM | Open Pit Stabilization | 1 | m3 | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189
| Assume cut and fill per m3? | 1 | m3 | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189
STK | Stockpile Removal | 1 | m2 | 0.17347 | 2.0499 | 14.6508 |  | 16.4435 | 31.0943
|  | 1 | Lot | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189
MM1 | Light Equimpent | 1 | Ea | 8.1 | 106.5 | 809.2984 |  | 1065 | 1980.7984 | 0.5
| Disassembly | 1 | Ea | 5 | 75 | 499.5669 |  | 750 | 1324.5669 |  | Crew of 1 for half day
| Decontaminate | 1 | Ea | 1 |  | 99.9134 |  | 0 | 99.9134 |  | Crew of 1
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Crew of 2 1 Hr
| Transport | 1 | Ea | 0.1 | 1.5 | 9.9913 |  | 15 | 26.4913 |  | Assume 20 Pieces per load
MM2 | Medium Equipment | 1 | Ea | 19.2 | 213 | 1918.3369 |  | 2130 | 4261.3369 | 1
| Disassembly | 1 | Ea | 10 | 150 | 999.1338 |  | 1500 | 2649.1338 |  | Crew of 2 for half a day
| Decontaminate | 1 | Ea | 5 |  | 499.5669 |  | 0 | 499.5669 |  | Crew of 1 for half day
| Load | 1 | Ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535 |  | Crew of 2 for 2 Hrs
| Transport | 1 | Ea | 0.2 | 3 | 19.9827 |  | 30 | 52.9827 |  | Assume 10 Pieces per load
MM3 | Heavy Equipment | 1 | Ea | 168 | 2220 | 16785.448 |  | 22200 | 41205.448 | 56
| Disassembly | 1 | Ea | 120 | 1800 | 11989.6057 |  | 18000 | 31789.6057 |  | Crew of 4 for 3 days
| Decontaminate | 1 | Ea | 20 |  | 1998.2676 |  | 0 | 1998.2676 |  | Crew of 2 for 1 day
| Load | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Crew of 2 for 1 day
| Transport | 1 | Ea | 8 | 120 | 799.307 |  | 1200 | 2119.307 |  | 2 loads required per piece, at 50% speed
O1 | Light Mobile Equipment | 1 | Ea | 6.6667 | 25 | 666.0892 |  | 250 | 941.0892 | 4
| Disassembly | 1 | Ea | 2 | 0 | 199.8268 |  | 0 | 199.8268 |  | Crew of 1
| Decontaminate | 1 | Ea | 3 |  | 299.7401 |  | 0 | 299.7401 |  | Crew of 1
| Load | 1 | Ea | 1 | 15 | 99.9134 |  | 150 | 264.9134 |  | Crew of 2 for 0.5 Hrs
| Transport | 1 | Ea | 0.66667 | 10 | 66.6089 |  | 100 | 176.6089 |  | Crew of 1 Assume 3 per load and 2 hour round trip
O2 | Medium Mobile Equipment | 1 | Ea | 10 | 45 | 999.1338 |  | 450 | 1494.1338 | 24
| Disassembly | 1 | Ea | 3 | 0 | 299.7401 |  | 0 | 299.7401 |  | Crew of 1
| Decontaminate | 1 | Ea | 4 |  | 399.6535 |  | 0 | 399.6535 |  | Crew of 1
| Load | 1 | Ea | 1 | 15 | 99.9134 |  | 150 | 264.9134 |  | Crew of 2 for 0.5 Hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Crew of 1 Assume 1 per load and 2 hour round trip
O3 | Heavy Mobile Equipment | 1 | Ea | 13 | 120 | 1298.874 |  | 1200 | 2618.874 | 96
| Disassembly | 1 | Ea | 5 | 75 | 499.5669 |  | 750 | 1324.5669 |  | Crew of 2 x 2.5 Hrs
| Decontaminate | 1 | Ea | 5 |  | 499.5669 |  | 0 | 499.5669 |  | Crew of 1
| Load | 1 | Ea | 1 | 15 | 99.9134 |  | 150 | 264.9134 |  | Crew of 2 for 0.5 Hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Crew of 1 Assume 1 per load and 2 hour round trip
MT1 | Light Tanks | 1 | Ea | 9.6667 | 107.5 | 965.8293 |  | 1075 | 2148.3293 | 1
| Remove from foundations | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Tank will not be disassembled
| Empty tank | 1 | Ea | 0.5 | 7.5 | 49.9567 |  | 75 | 132.4567
| Decontaminate | 1 | Ea | 2.5 |  | 249.7835 |  | 0 | 249.7835
| Load | 1 | Ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535 |  | Crew of 2 for 2 hours
| Transport | 1 | Ea | 0.66667 | 10 | 66.6089 |  | 100 | 176.6089 |  | Assume 3 tanks per load
MT2 | Medium Tanks | 1 | Ea | 31 | 390 | 3097.3148 |  | 3900 | 7387.3148 | 2
| Disassembly | 1 | Ea | 16 | 240 | 1598.6141 |  | 2400 | 4238.6141 |  | Crew of 2 for 8 Hrs
| Decontaminate | 1 | Ea | 5 |  | 499.5669 |  | 0 | 499.5669 |  | Crew of 1 for half a day
| Empty tank | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Load | 1 | Ea | 6 | 90 | 599.4803 |  | 900 | 1589.4803 |  | Crew of 2 for 3 hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Assume 1 tank per load
MT3 | Large Tanks | 1 | Ea | 269 | 2910 | 26876.6995 |  | 29100 | 58886.6995
| Disassembly | 1 | Ea | 150 | 2250 | 14987.0071 |  | 22500 | 39737.0071
| Decontaminate | 1 | Ea | 75 |  | 7493.5036 |  | 0 | 7493.5036
| Empty tank | 1 | Ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535
| Load | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676
| Transport | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676
MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | 1 | Ea | 15.5 | 195 | 1548.6574 |  | 1950 | 3693.6574 | 20
| Remove from foundations | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Tank will not be disassembled
| Empty tank and Collect Diesel | 1 | Ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535 |  | Crew of 1, and average of 10,000 L Tanks | 41.6667
| Decontaminate | 1 | Ea | 2.5 |  | 249.7835 |  | 0 | 249.7835 |  | Crew of 1
| Load | 1 | Ea | 5 | 75 | 499.5669 |  | 750 | 1324.5669 |  | Crew of 2 for 2.5 Hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | 1 trip required
MT2-d | Medium Diesel Tanks (500k L to 750k L) | 1 | Ea | 43 | 570 | 4296.2754 |  | 5700 | 10566.2754 | 40
| Disassembly | 1 | Ea | 16 | 240 | 1598.6141 |  | 2400 | 4238.6141 |  | Crew of 2 for 8 Hrs to remove piping and Cap
| Empty tank and Collect Diesel | 1 | Ea | 10 | 150 | 999.1338 |  | 1500 | 2649.1338 |  | Crew of 1, and average of 10,000 L Tanks | 833.3333
| Decontaminate | 1 | Ea | 5 |  | 499.5669 |  | 0 | 499.5669 |  | Crew of 1
| Load | 1 | Ea | 8 | 120 | 799.307 |  | 1200 | 2119.307 |  | Crew of 2 for 4 hrs
| Transport | 1 | Ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535 |  | 1 load required but at 50% speed
MT3-d | Large Diesel Tanks Load and Transport (5M L) | 1 | Ea | 303.3333 | 4250 | 30307.0589 |  | 42500 | 77057.0589 | 80
| Disassembly | 1 | Ea | 160 | 2400 | 15986.141 |  | 24000 | 42386.141 |  | Crew of 4 for 4 10 Hr days
| Decontaminate | 1 | Ea | 20 |  | 1998.2676 |  | 0 | 1998.2676 |  | Crew of 2 for 1 day
| Empty tank and Collect Diesel | 1 | Ea | 83.3333 | 1250 | 8326.1151 |  | 12500 | 22076.1151 |  | Use 60,000 L per Hr. Based on 2013 fuel delivery Flow Rates | 13888.8889
| Load | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Crew of 4 for half a day
| Transport | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Assume 10 trips requred
MT4-d | Largest Diesel Tanks (10M L to 12M L) | 1 | Ea | 526.6667 | 7300 | 52621.0473 |  | 73000 | 132921.0473 | 160
| Disassembly | 1 | Ea | 250 | 3750 | 24978.3452 |  | 37500 | 66228.3452 |  | Crew of 5 for 5 days
| Decontaminate | 1 | Ea | 40 |  | 3996.5352 |  | 0 | 3996.5352 |  | Crew of 2 for 2 day
| Empty tank and Collect Diesel | 1 | Ea | 166.6667 | 2500 | 16652.2302 |  | 25000 | 44152.2302 |  | Use 60,000 L per Hr. Based on 2013 fuel delivery Flow Rates | 13888.8889 |  |  | 1577000
| Load | 1 | Ea | 40 | 600 | 3996.5352 |  | 6000 | 10596.5352 |  | Crew of 4 for a full day
| Transport | 1 | Ea | 30 | 450 | 2997.4014 |  | 4500 | 7947.4014 |  | Assume 15 trips required |  |  |  | 5992600 | 96
62422.9167
FF1 | Modular Building Not Contaminated (480 ft2) | 1 | m2 | 0.22417 | 3.3625 | 22.3972 |  | 33.625 | 59.3847 | 1
| Empty and remove or secure items | 1 | Ea | 3 | 45 | 299.7401 |  | 450 | 794.7401 |  | Crew of 1 for 3 Hrs (per 480ft2 building) |  |  |  | Use - > | 60000
| Decontaminate | 1 | Ea |  |  | 0 |  |  | 0
| Load | 1 | Ea | 5 | 75 | 499.5669 |  | 750 | 1324.5669 |  | Crew of 2 for 2.5 Hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | 4 Hour round trip. Building per trip
FF1-c | Modular Building Contaminated (480 ft2) | 1 | m2 | 0.56042 | 3.3625 | 55.9931 |  | 84.0625 | 143.4181 | 1
| Empty and remove or secure items | 1 | Ea | 3 | 45 | 299.7401 |  | 450 | 794.7401 |  | Crew of 1 for 3 Hrs (per 480ft2 building)
| Decontaminate | 1 | Ea | 15 |  | 1498.7007 |  | 2250 | 3748.7007 |  | Crew of 3 for 4 Hrs
| Load | 1 | Ea | 5 | 75 | 499.5669 |  | 750 | 1324.5669 |  | Crew of 2 for 2.5 Hrs
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | 4 Hour round trip. Building per trip |  | 12 | 40 | 480
FF2 | Fold Away Building Not Contaminated (480 ft2) | 1 | m2 | 0.15692 | 2.3537 | 15.6781 |  | 23.5375 | 41.5693 | 1
| Empty and remove or secure items | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Disassembly | 1 | Ea | 3 | 45 | 299.7401 |  | 450 | 794.7401
| Decontaminate | 1 | Ea |  |  | 0 |  |  | 0
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
FF2-c | Fold Away Building Contaminated (480 ft2) | 1 | m2 | 0.56042 | 2.3537 | 55.9931 |  | 84.0625 | 142.4094 | 1
| Empty and remove or secure items | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Crew of 1 for 2 hrs
| Disassembly | 1 | Ea | 3 | 45 | 299.7401 |  | 450 | 794.7401 |  | Crew of 1 for 3 hrs
| Decontaminate | 1 | Ea | 18 |  | 1798.4409 |  | 2700 | 4498.4409 |  | Crew of 3 for 6 Hrs
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | 1 | m2 | 0.17933 | 2.69 | 17.9178 |  | 26.9 | 47.5078 | 0.5
| Disassembly | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Empty and remove or secure items | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Decontaminate | 1 | Ea |  |  | 0 |  |  | 0
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | 1 | m2 | 0.58283 | 2.69 | 58.2328 |  | 87.425 | 148.3478 | 0.5
| Disassembly | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Empty and remove or secure items | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Decontaminate | 1 | Ea | 18 |  | 1798.4409 |  | 2700 | 4498.4409 |  | Type of buildings will required more decontamination
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
FF4 | ISO Container | 1 | m2 | 0.11208 | 1.6812 | 11.1986 |  | 16.8125 | 29.6924 | 1
| Empty and remove or secure items | 1 | Ea | 1 | 15 | 99.9134 |  | 150 | 264.9134 |  | Crew of 1
| Decontaminate | 1 | Ea |  |  | 0 |  |  | 0
| Load | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Crew of 2 for 1 Hr
| Transport | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 |  | Assume round trip of 2 hrs
FW | Timber Cribbing (480 ft2) | 1 | m2 | 0.12329 | 1.1769 | 7.839 |  | 11.7688 | 20.7847 | 0.3
| Disassembly | 1 | Ea | 2 | 30 | 199.8268 |  | 300 | 529.8268
| Decontaminate | 1 | Ea | 2 | [8 empty] | L | W | H | ft3 | m3 | Qty |  | Area ft2 | area m2 |  | 104 | 26
| Load | 1 | Ea | 1 | 15 | 99.9134 |  | 150 | 264.9134 |  |  |  | 2 | 2 | 4 | 16 | 0.4528 | 26 | 11.7728 | 480 | 44.592 | 0.26401
| Transport | 1 | Ea | 0.5 | 7.5 | 49.9567 |  | 75 | 132.4567 |  | Approx 4 x 480ft2 cribbing per load
480
|  |  |  | 0.26401 | 0.26401 | 0.26401 |  | 0.26401 | 0.26401 |  |  |  | 0.608 | 0.608 | 1.216 | 26 |  | 11.6873 |  | 480
CP | Precast Concrete Foundations - (480 ft2) | 1 | m2 | 0.14521 | 2.1781 | 14.5081 |  | 21.7809 | 38.4671 | 0.75
| Demo (not required) | 1 | m3 | 0 | 0 | 0 |  | 0 | 0
| Decontaminate | 1 | m3 | 0 | 0 | 0 |  | 0 | 0
| Load | 1 | m3 | 2 | 30 | 199.8268 |  | 300 | 529.8268 | [8 empty] | 0.26209
| Transport (assume 10 m3 per load. 4 hour round trip) | 1 | m3 | 0.2 | 3 | 19.9827 |  | 30 | 52.9827 |  | Assume 1 day
CS | Slab on Grade - ASSUME 300mm thick | 1 | m2 | 0.125 | 1.875 | 12.4892 |  | 18.75 | 33.1142 | 0 | 7.5 min per m2 of building for drilling of drainage hole. Crew of 1
| Demo | 1 | m3 | 0.125 | 1.875 | 12.4892 |  | 18.75 | 33.1142
| Decontaminate | 1 | m3 |  | 0 | 0 |  | 0 | 0
| Load | 1 | m3 |  | 0 | 0 |  | 0 | 0
| Transport | 1 | m3 |  | 0 | 0 |  | 0 | 0
BR | Bridge Removal | 1 | Lot | 761.9048 | 11428.5714 | 76124.4807 |  | 114285.7143 | 201838.7664 | 5000
| Demo | 1 | Lot | 761.9048 | 11428.5714 | 76124.4807 |  | 114285.7143 | 201838.7664
A10 | Steel Building Teardown | 1 | Ea | 270 | 3450 | 26976.6129 |  | 34500 | 64926.6129 | 0.5
| Disassembly | 1 | Ea | 160 | 2400 | 15986.141 |  | 24000 | 42386.141
| Decontaminate | 1 | Ea | 40 |  | 3996.5352 |  | 0 | 3996.5352
| Load | 1 | Ea | 40 | 600 | 3996.5352 |  | 6000 | 10596.5352
| Transport | 1 | Ea | 30 | 450 | 2997.4014 |  | 4500 | 7947.4014
VP1 | VENDOR PKG - Incenerator | 1 | Lot | 47 | 480 | 4695.9289 |  | 4800 | 9975.9289 | 329.2683
| Disassembly | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Crew of 2, 1 full day (10Hrs)
| Decontaminate | 1 | Ea | 15 |  | 1498.7007 |  | 0 | 1498.7007 |  | Crew of 3 for 5 Hrs
| Load | 1 | Ea | 6 | 90 | 599.4803 |  | 900 | 1589.4803 |  | Crew of 2, 1hr per load. 3 loads (contrainers) per package
| Transport | 1 | Ea | 6 | 90 | 599.4803 |  | 900 | 1589.4803 |  | 3 Trips required, 2 hrs per trip
VP2 | VENDOR PKG - Potable Water | 1 | Lot | 47 | 480 | 4695.9289 |  | 4800 | 9975.9289 | 329.2683
| Disassembly | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Crew of 2, 1 full day (10Hrs)
| Decontaminate | 1 | Ea | 15 |  | 1498.7007 |  | 0 | 1498.7007 |  | Crew of 3 for 5 Hrs
| Load | 1 | Ea | 6 | 90 | 599.4803 |  | 900 | 1589.4803 |  | Crew of 2, 1hr per load. 3 loads (contrainers) per package
| Transport | 1 | Ea | 6 | 90 | 599.4803 |  | 900 | 1589.4803 |  | 3 Trips required, 2 hrs per trip
VP3 | VENDOR PKG - Sewage Treatment Plant | 1 | Lot | 51 | 540 | 5095.5824 |  | 5400 | 11035.5824 | 329.2683
| Disassembly | 1 | Ea | 20 | 300 | 1998.2676 |  | 3000 | 5298.2676 |  | Crew of 2, 1 full day (10Hrs)
| Decontaminate | 1 | Ea | 15 |  | 1498.7007 |  | 0 | 1498.7007 |  | Crew of 3 for 5 Hrs
| Load | 1 | Ea | 8 | 120 | 799.307 |  | 1200 | 2119.307 |  | Crew of 2, 1hr per load. 4 loads (contrainers) per package
| Transport | 1 | Ea | 8 | 120 | 799.307 |  | 1200 | 2119.307 |  | 4 Trips required, 2 hrs per trip
VP5 | VENDOR PKG - Truck wash Facility | 1 | Lot | 300 | 4500 | 29974.0143 |  | 45000 | 79474.0143 | 329.2683
| 30% of Install Hrs | 1 | Ea | 300 | 4500 | 29974.0143 |  | 45000 | 79474.0143 |  | 30% of Installation Hrs
Weight
VP6 | VENDOR PKG - Ship Loader | 1 | Lot | 24080 | 361200 | 2405914.2133 |  | 3612000 | 6379114.2133 | 30295
| Assume Crew of 20 for 4 Months | 1 | Ea | 24080 | 361200 | 2405914.2133 |  | 3612000 | 6379114.2133 |  | 12.2857
CV | Reclaim Conveyor | 1 | ea | 5018.4 | 75276 | 501405.311 |  | 752760 | 1329441.311 | 1020
| Load, Haul and Dispose (30% of Install Hrs) | 1 | ea | 5018.4 | 75276 | 501405.311 |  | 752760 | 1329441.311 |  | Take 30% of (850m x 6Mhrs per ft)
EG | Gravel Base Removal | 1 | m3 | 0 | 0 | 0 |  | 0 | 0 |  | Gravel stays in place. No cost required
| Load, Haul and Dispose | 1 | m3
Piping | Piping | 1 | m | 0.25 | 3.75 | 24.9783 |  | 37.5 | 66.2283 | 0.01
| Disasemble, Load, Haul and Dispose | 1 | m | 0.25 | 3.75 | 24.9783 |  | 37.5 | 66.2283 |  | 30% of Installation. Based on In house data for Hours/Unit. Crew size not considered
cable | Cable | 1 | m | 0.1 | 1.5 | 9.9913 |  | 15 | 26.4913 | 0.01
| Load, Haul and Dispose | 1 | m | 0.1 | 1.5 | 9.9913 |  | 15 | 26.4913 |  | 30% of Installation. Based on In house data for Hours/Unit. Crew size not considered
Misc | Miscellanous Items (Minor) | 1 | ea | 2 | 30 | 199.8268 |  | 300 | 529.8268 | 0.5
| Load, Haul and Dispose | 1 | ea | 4 | 60 | 399.6535 |  | 600 | 1059.6535
A12 | Application of insulation material | 1 | m2 | 0.05 | 0.3 | 4.9957 | 5 | 3 | 13.2957 | 0.01
| HDPE liner | 1 | m2 | 0.05 | 0.3 | 4.9957 | 5 | 3 | 13.2957 |  | In-House (2013 quote for remote site)
ARS | Airstrip Lighting and Removal | 1 | m | 0.1 | 1.5 | 9.9913 | 0 | 15 | 26.4913
| Load, Haul and Dispose | 1 | m | 0.1 | 1.5 | 9.9913 | 0 | 15 | 26.4913
One Offs
| Airstrip Lighting and Removal | 1 | m | 0.05 | 0 | 4.9957 |  |  | 4.9957
| Stockpile stabilization (?) assume cut and fill per m3? | 1 | m3 | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189
| Pipeline removal | 1 | m | 0.25 | 0 | 24.9783 |  |  | 24.9783
Bridge spans
Bridge adbutments
| Cable | 1 | m | 0.1 | 0 | 9.9913 |  |  | 9.9913

## 2018 Total Costs (C2) (hidden)
| Total for C1 Activities and Reclaimation of 2017 Activities - Security Posted March 2018 |  |  |  | IOL | Crown | Water | Land
[5 empty] | 100% | 0% | 24.89% | 75.11%
| DIRECT COST SUB-TOTAL (Reconcillation + New Scope) | 987888.8708 |  |  | 987888.8708 | 0 | 245851.025 | 742037.8458 | 987888.8708 | Notes for Indirects
| TOTAL MAN-HOURS | 6535.2607 |  |  | 6535.2607 | 0 | 1077.5 | 5457.7607 | 6535.2607 | AN and Prepack for 2018 within typical volume set in 2016 and securities paid on
| TOTAL MAN-DAYS | 653.5261 |  |  | 653.5261 | 0 | 107.75 | 545.7761 | 653.5261 | Fuel capacity stays the same as 2017-A, no increase in securities needed
0
| Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 | 0
| Fuel | 55000 | Depends on Man Hours and Fuel Consumption |  | 55000 | 0 | 2000 | 52000 | 54000
| Ammonium Nitrate | 0 | Covered in 2016 posting |  | 0 | 0 | 0 | 0 | 0 |  | Reconcilliation
| Contaminated Soil Treatment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 | 0 |  | -221574 | cross conveyor
[9 empty] | 0 |  | 1564000 | grade and recontour
| Mobilization of Workers Required for Reclamation | 54000 | Depends on Man Hours |  | 54000 | 0 | 9000 | 45000 | 54000 |  | 1071000 | equipment
| Worker Accommodation & Camp Operation | 147000 | Depends on Man Hours |  | 147000 | 0 | 24000 | 123000 | 147000
10% | Mobilization and Demobilization of Equipment and Materials by Sealift | 99000 | % |  | 99000 | 0 | 99000 | 0 | 99000 |  | 2018 Work Plan
[9 empty] | 0 |  | 758000 | buildings
| Geotechnical Inspections | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 | 0 |  | 839000 | equipment
| Project Environmental Site Assessment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 | 0 |  | 3486000 | site works (G&R)
| Closure & Post Closure Monitoring | 8000 | Updated to account for WRF water treatment plant sampling |  | 8000 | 0 | 8000 | 0 | 8000 |  | 207000 | tanks
[9 empty] | 0 |  | 136810 | culverts
3.9% | Engineering Fees | 39000 | % |  | 39000 | 0 | 10000 | 29000 | 39000 |  | 202000 | piping
9.4% | Supervision, Project Management & Contract Administration | 93000 | % |  | 93000 | 0 | 23000 | 70000 | 93000 |  | 7100000 | demob expansion eq
[9 empty] | 0 |  | 112000 | consumables
12.5% | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 161000 | % |  | 161000 | 0 | 47000 | 114000 | 161000 |  | 167000 | fill
[9 empty] | 0 |  | 15421236
| INDIRECT SUB-TOTAL | 656000 |  |  | 656000 | 0 | 222000 | 433000 | 655000
| TOTAL | 1644000 |  |  | 1644000 | 0 | 468000 | 1175000 | 1643000 | #REF!
= pulls data from Indirects spreadsheets
| = linked back to EBS 'Estimate Details' Indirects section | [8 empty] | 247000
|  |  | Check OK | [6 empty] | 1891000
| Total Direct Cost |  | 987888.8708 |  | 987888.8708 | 0 | 245851.025 | 742037.8458
| Total Direct Cost & with Mob and Monitoring |  | 1295888.8708 |  | 1295888.8708 | 0 | 385851.025 | 910037.8458
| Total direct cost+Contaminated soil+post closure monitoring |  | 987888.8708 |  | 987888.8708 | 0 | 245851.025 | 742037.8458
| Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  | 1288047.8876 |  | 1288259.0006 | 0 | 378148.65 | 910110.3506
| Mobilization and Demobilization of Equipment and Materials by Sealift | 10% | 98788.8871 | 10% of direct Cost | 99000 | 0 | 99000 | 0
| Engineering | 3.9% | 38527.666 | 3.9% of direct Cost | 39000 | 0 | 10000 | 29000
| Project supervision, management & contract administration | 9.4% | 92861.5539 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) | 93000 | 0 | 23000 | 70000
| Contingency | 12.5% | 161005.986 | 12.5% of (direct cost+Contaminated soil treatment+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) | 161032.3751 | 0 | 47268.5813 | 113763.7938
[5 empty] | IOL | Crown | Water | Land
FUEL ON-SITE
| Increase to Fuel Capacity @ site (L) | 0 | No increase in fuel capacity in 2018 |  | 0 | 0 | 0 | 0
| Demob cost per Litre | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1
| Reclamation Activites (L) | 199000 |  |  | 199000 | 0 | 0 | 199000
| Heat and Power (L) | 75000 |  |  | 75000 | 0 | 12000 | 63000
| Total fuel reuired during closure (L) | 274000 |  |  | 274000 | 0 | 12000 | 262000
| Cost to mob. Fuel per Litre | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4
| Demob 50% of total capacity | 0 |  |  | 0 | 0 | 0 | 0
| Mob 50% fuel required during closure | 55000 |  |  | 55000 | 0 | 2000 | 52000
| Total Mob/Demo Fuel | 55000 |  |  | 55000 | 0 | 2000 | 52000
CAMP FUEL CONSUMPTION
| 1732500 | Avg Monthly Consumption |  |  | 1732500 | 1732500 | 1732500 | 1732500
| 30 | Days in month |  |  | 30 | 30 | 30 | 30
| 500 | Average camp population in '14 |  |  | 500 | 500 | 500 | 500
| 115.5 | L/Man-day |  |  | 115.5 | 115.5 | 115.5 | 115.5
| 75482.2616 | Cost |  |  | 75482.2616 | 0 | 12445.125 | 63037.1366
WORKERS ACCOMODATION
| Cost per/day | 110 |  |  | 110 | 110 | 110 | 110
| Cost for Fuel consumption per day | 115.5 |  |  | 115.5 | 115.5 | 115.5 | 115.5
| Accomodation Costs | 71887.8682 |  |  | 71887.8682 | 0 | 11852.5 | 60035.3682
| Camp Op Fuel Costs | 75482.2616 |  |  | 75482.2616 | 0 | 12445.125 | 63037.1366
| TOTAL | 147000 |  |  | 147000 | 0 | 24000 | 123000
FLIGHTS
| Person Days On-Site | 653.5261 |  |  | 653.5261 | 0 | 107.75 | 545.7761
| Southern Hires (70%) | 458 |  |  | 458 | 0 | 76 | 383
| Northern Hires (30%) | 197 |  |  | 197 | 0 | 33 | 164
| Cost Southern Communities | 39136.1 |  |  | 39136.1 | 0 | 6494.2 | 32727.35
| Cost northern Communities | 14775 |  |  | 14775 | 0 | 2475 | 12300
| Total Cost | 54000 |  |  | 54000 | 0 | 9000 | 45000
GEOTECHNICAL INVESTIGATIONS
| Cost/hour | 200
| Billable hours per inspection | 46
| Travel Costs | 4500
| Report Costs | 5000
| Cost per Inspection | 18700
| Total # of Inspections | 0
| TOTAL | 0
ANALYSIS & REPORTING
| Cost/hour | 200
| Billable hours per year | 300
| Cost per Year | 60000
| # of Years | 0
| TOTAL | 0
FIELD SAMPLING
| Cost/hour | 200
| Billable hours per inspection | 72
| Travel Costs | 4500
| Samples | 43
| Cost/Sample | 100
| Cost per Inspection | 23200
| Total # of Trips | 0
| TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2018 MAY Removed Costs (hidden)
| Total for equipment not scheduled to arrive on the 2018 Sea lift, as revised in May 2018 following QIA security negotiations |  |  |  | IOL | Crown | Water | Land
[5 empty] | -1789% | 0% | 0% | -1789%
| DIRECT COST SUB-TOTAL (Reconcillation + New Scope) | -171299.6353 |  |  | 3064422.519 | 0 | 0 | 3064422.519 | Notes for Indirects
| TOTAL MAN-HOURS | -780.4333 |  |  | 19992.59 | 0 | 0 | 19992.59 | AN and Prepack for 2018 within typical volume set in 2016 and securities paid on
| TOTAL MAN-DAYS | -78.0433 |  |  | 1999.259 | 0 | 0 | 1999.259 | Fuel capacity stays the same as 2017-A, no increase in securities needed
| Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0
| Fuel | -4000 | Depends on Man Hours and Fuel Consumption |  | 86000 | 0 | 0 | 86000
| Ammonium Nitrate | 0 | Covered in 2016 posting |  | 0 | 0 | 0 | 0 |  | Reconcilliation
| Contaminated Soil Treatment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | -221574 | cross conveyor
[10 empty] | 1564000 | grade and recontour
| Mobilization of Workers Required for Reclamation | -6000 | Depends on Man Hours |  | 165000 | 0 | 0 | 165000 |  | 1071000 | equipment
| Worker Accommodation & Camp Operation | -18000 | Depends on Man Hours |  | 451000 | 0 | 0 | 451000
10% | Mobilization and Demobilization of Equipment and Materials by Sealift | -15112000 | % |  | -15112000 | 0 | 0 | -15112000 |  | 2018 Work Plan
[10 empty] | 758000 | buildings
| Geotechnical Inspections | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 839000 | equipment
| Project Environmental Site Assessment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 3486000 | site works (G&R)
| Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 207000 | tanks
[10 empty] | 136810 | culverts
3.9% | Engineering Fees | -7000 | % |  | 120000 | 0 | 0 | 120000 |  | 202000 | piping
9.4% | Supervision, Project Management & Contract Administration | -16000 | % |  | 288000 | 0 | 0 | 288000 |  | 7100000 | demob expansion eq
[10 empty] | 112000 | consumables
12.5% | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | -1913000 | % |  | -1429000 | 0 | 0 | -1429000 |  | 167000 | fill
15421236
| INDIRECT SUB-TOTAL | -17076000 |  |  | -15431000 | 0 | 0 | -15431000
| TOTAL | -17247000 |  |  | -12367000 | 0 | 0 | -12367000 | #REF!
= pulls data from Indirects spreadsheets
| = linked back to EBS 'Estimate Details' Indirects section | [7 empty] | -1855000
|  |  | Check OK | [5 empty] | -14222000
| Total Direct Cost |  | -171299.6353 |  | 3064422.519 | 0 | 0 | 3064422.519
| Total Direct Cost & with Mob and Monitoring |  | -15307299.6353 |  | -11431577.481 | 0 | 0 | -11431577.481
| Total direct cost+Contaminated soil+post closure monitoring |  | -171299.6353 |  | 3064422.519 | 0 | 0 | 3064422.519
| Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  | -15307136.8905 |  | -11431744.5772 | 0 | 0 | -11431744.5772
| Mobilization and Demobilization of Equipment and Materials by Sealift | 10% | -15112238.4835 | 10% of direct Cost | -15112000 | 0 | 0 | -15112000
| Engineering | 3.9% | -6680.6858 | 3.9% of direct Cost | 120000 | 0 | 0 | 120000
| Project supervision, management & contract administration | 9.4% | -16102.1657 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) | 288000 | 0 | 0 | 288000
| Contingency | 12.5% | -1913392.1113 | 12.5% of (direct cost+Contaminated soil treatment+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) | -1428968.0721 | 0 | 0 | -1428968.0721
[5 empty] | IOL | Crown | Water | Land
FUEL ON-SITE
| Increase to Fuel Capacity @ site (L) | 0 | No increase in fuel capacity in 2018 |  | 0 | 0 | 0 | 0
| Demob cost per Litre | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1
| Reclamation Activites (L) | -9000 |  |  | 199000 | 0 | 0 | 199000
| Heat and Power (L) | -9000 |  |  | 231000 | 0 | 0 | 231000
| Total fuel reuired during closure (L) | -18000 |  |  | 430000 | 0 | 0 | 430000
| Cost to mob. Fuel per Litre | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4
| Demob 50% of total capacity | 0 |  |  | 0 | 0 | 0 | 0
| Mob 50% fuel required during closure | -4000 |  |  | 86000 | 0 | 0 | 86000
| Total Mob/Demo Fuel | -4000 |  |  | 86000 | 0 | 0 | 86000
CAMP FUEL CONSUMPTION
| 1732500 | Avg Monthly Consumption |  |  | 1732500 | 1732500 | 1732500 | 1732500
| 30 | Days in month |  |  | 30 | 30 | 30 | 30
| 500 | Average camp population in '14 |  |  | 500 | 500 | 500 | 500
| 115.5 | L/Man-day |  |  | 115.5 | 115.5 | 115.5 | 115.5
| -9014.005 | Cost |  |  | 230914.4141 | 0 | 0 | 230914.4141
WORKERS ACCOMODATION
| Cost per/day | 110 |  |  | 110 | 110 | 110 | 110
| Cost for Fuel consumption per day | 115.5 |  |  | 115.5 | 115.5 | 115.5 | 115.5
| Accomodation Costs | -8584.7667 |  |  | 219918.4897 | 0 | 0 | 219918.4897
| Camp Op Fuel Costs | -9014.005 |  |  | 230914.4141 | 0 | 0 | 230914.4141
| TOTAL | -18000 |  |  | 451000 | 0 | 0 | 451000
FLIGHTS
| Person Days On-Site | -78.0433 |  |  | 1999.259 | 0 | 0 | 1999.259
| Southern Hires (70%) | -55 |  |  | 1400 | 0 | 0 | 1400
| Northern Hires (30%) | -24 |  |  | 600 | 0 | 0 | 600
| Cost Southern Communities | -4699.75 |  |  | 119630 | 0 | 0 | 119630
| Cost northern Communities | -1800 |  |  | 45000 | 0 | 0 | 45000
| Total Cost | -6000 |  |  | 165000 | 0 | 0 | 165000
GEOTECHNICAL INVESTIGATIONS
| Cost/hour | 200
| Billable hours per inspection | 46
| Travel Costs | 4500
| Report Costs | 5000
| Cost per Inspection | 18700
| Total # of Inspections | 0
| TOTAL | 0
ANALYSIS & REPORTING
| Cost/hour | 200
| Billable hours per year | 300
| Cost per Year | 60000
| # of Years | 0
| TOTAL | 0
FIELD SAMPLING
| Cost/hour | 200
| Billable hours per inspection | 72
| Travel Costs | 4500
| Samples | 43
| Cost/Sample | 100
| Cost per Inspection | 23200
| Total # of Trips | 0
| TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2018 Total Costs (C1) (hidden)
| Total for C1 Activities and Reclaimation of 2017 Activities - Security Posted March 2018 |  |  |  | IOL | Crown | Water | Land
[5 empty] | 100% | 0% | 0% | 100%
| DIRECT COST SUB-TOTAL (Reconcillation + New Scope) | 3064422.519 |  |  | 3064422.519 | 0 | 0 | 3064422.519 | Notes for Indirects
| TOTAL MAN-HOURS | 19992.59 |  |  | 19992.59 | 0 | 0 | 19992.59 | AN and Prepack for 2018 within typical volume set in 2016 and securities paid on
| TOTAL MAN-DAYS | 1999.259 |  |  | 1999.259 | 0 | 0 | 1999.259 | Fuel capacity stays the same as 2017-A, no increase in securities needed
| Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0
| Fuel | 86000 | Depends on Man Hours and Fuel Consumption |  | 86000 | 0 | 0 | 86000
| Ammonium Nitrate | 0 | Covered in 2016 posting |  | 0 | 0 | 0 | 0 |  | Reconcilliation
| Contaminated Soil Treatment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | -221574 | cross conveyor
[10 empty] | 1564000 | grade and recontour
| Mobilization of Workers Required for Reclamation | 165000 | Depends on Man Hours |  | 165000 | 0 | 0 | 165000 |  | 1071000 | equipment
| Worker Accommodation & Camp Operation | 451000 | Depends on Man Hours |  | 451000 | 0 | 0 | 451000
10% | Mobilization and Demobilization of Equipment and Materials by Sealift | 16965000 | % |  | 16965000 | 0 | 0 | 16965000 |  | 2018 Work Plan
[10 empty] | 758000 | buildings
| Geotechnical Inspections | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 839000 | equipment
| Project Environmental Site Assessment | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 3486000 | site works (G&R)
| Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline |  | 0 | 0 | 0 | 0 |  | 207000 | tanks
[10 empty] | 136810 | culverts
3.9% | Engineering Fees | 120000 | % |  | 120000 | 0 | 0 | 120000 |  | 202000 | piping
9.4% | Supervision, Project Management & Contract Administration | 288000 | % |  | 288000 | 0 | 0 | 288000 |  | 7100000 | demob expansion eq
[10 empty] | 112000 | consumables
12.5% | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 2581000 | % |  | 2581000 | 0 | 0 | 2581000 |  | 167000 | fill
15421236
| INDIRECT SUB-TOTAL | 20656000 |  |  | 20656000 | 0 | 0 | 20656000
| TOTAL | 23720000 |  |  | 23720000 | 0 | 0 | 23720000 | #REF!
= pulls data from Indirects spreadsheets
| = linked back to EBS 'Estimate Details' Indirects section | [7 empty] | 3558000
|  |  | Check OK | [5 empty] | 27278000
| Total Direct Cost |  | 3064422.519 |  | 3064422.519 | 0 | 0 | 3064422.519
| Total Direct Cost & with Mob and Monitoring |  | 20645422.519 |  | 20645422.519 | 0 | 0 | 20645422.519
| Total direct cost+Contaminated soil+post closure monitoring |  | 3064422.519 |  | 3064422.519 | 0 | 0 | 3064422.519
| Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  | 20645031.6747 |  | 20645255.4228 | 0 | 0 | 20645255.4228
| Mobilization and Demobilization of Equipment and Materials by Sealift | 10% | 16964776.2519 | 10% of direct Cost | 16965000 | 0 | 0 | 16965000
| Engineering | 3.9% | 119512.4782 | 3.9% of direct Cost | 120000 | 0 | 0 | 120000
| Project supervision, management & contract administration | 9.4% | 288055.7168 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) | 288000 | 0 | 0 | 288000
| Contingency | 12.5% | 2580628.9593 | 12.5% of (direct cost+Contaminated soil treatment+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) | 2580656.9279 | 0 | 0 | 2580656.9279
[5 empty] | IOL | Crown | Water | Land
FUEL ON-SITE
| Increase to Fuel Capacity @ site (L) | 0 | No increase in fuel capacity in 2018 |  | 0 | 0 | 0 | 0
| Demob cost per Litre | 0.1 |  |  | 0.1 | 0.1 | 0.1 | 0.1
| Reclamation Activites (L) | 199000 |  |  | 199000 | 0 | 0 | 199000
| Heat and Power (L) | 231000 |  |  | 231000 | 0 | 0 | 231000
| Total fuel reuired during closure (L) | 430000 |  |  | 430000 | 0 | 0 | 430000
| Cost to mob. Fuel per Litre | 0.4 |  |  | 0.4 | 0.4 | 0.4 | 0.4
| Demob 50% of total capacity | 0 |  |  | 0 | 0 | 0 | 0
| Mob 50% fuel required during closure | 86000 |  |  | 86000 | 0 | 0 | 86000
| Total Mob/Demo Fuel | 86000 |  |  | 86000 | 0 | 0 | 86000
CAMP FUEL CONSUMPTION
| 1732500 | Avg Monthly Consumption |  |  | 1732500 | 1732500 | 1732500 | 1732500
| 30 | Days in month |  |  | 30 | 30 | 30 | 30
| 500 | Average camp population in '14 |  |  | 500 | 500 | 500 | 500
| 115.5 | L/Man-day |  |  | 115.5 | 115.5 | 115.5 | 115.5
| 230914.4141 | Cost |  |  | 230914.4141 | 0 | 0 | 230914.4141
WORKERS ACCOMODATION
| Cost per/day | 110 |  |  | 110 | 110 | 110 | 110
| Cost for Fuel consumption per day | 115.5 |  |  | 115.5 | 115.5 | 115.5 | 115.5
| Accomodation Costs | 219918.4897 |  |  | 219918.4897 | 0 | 0 | 219918.4897
| Camp Op Fuel Costs | 230914.4141 |  |  | 230914.4141 | 0 | 0 | 230914.4141
| TOTAL | 451000 |  |  | 451000 | 0 | 0 | 451000
FLIGHTS
| Person Days On-Site | 1999.259 |  |  | 1999.259 | 0 | 0 | 1999.259
| Southern Hires (70%) | 1400 |  |  | 1400 | 0 | 0 | 1400
| Northern Hires (30%) | 600 |  |  | 600 | 0 | 0 | 600
| Cost Southern Communities | 119630 |  |  | 119630 | 0 | 0 | 119630
| Cost northern Communities | 45000 |  |  | 45000 | 0 | 0 | 45000
| Total Cost | 165000 |  |  | 165000 | 0 | 0 | 165000
GEOTECHNICAL INVESTIGATIONS
| Cost/hour | 200
| Billable hours per inspection | 46
| Travel Costs | 4500
| Report Costs | 5000
| Cost per Inspection | 18700
| Total # of Inspections | 0
| TOTAL | 0
ANALYSIS & REPORTING
| Cost/hour | 200
| Billable hours per year | 300
| Cost per Year | 60000
| # of Years | 0
| TOTAL | 0
FIELD SAMPLING
| Cost/hour | 200
| Billable hours per inspection | 72
| Travel Costs | 4500
| Samples | 43
| Cost/Sample | 100
| Cost per Inspection | 23200
| Total # of Trips | 0
| TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2017-A Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 4598577.9293
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 1198000
[10 empty] | Ammonium Nitrate | 0
Contaminated Soil Treatment
[10 empty] | Mobilization of Workers Required for Reclamation | 151000
[10 empty] | Worker Accommodation & Camp Operation | 414000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 460000
18356.2847
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 1835.6285 |  |  | 1835.6285 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 212932.9028
[7 empty] | 110 | 201919.132 |  | Engineering Fees | 179000 | %
[8 empty] | 414852.0349 |  | Supervision, Project Management & Contract Administration | 432000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 703000 | %
[10 empty] | INDIRECT SUB-TOTAL | 3537000
[10 empty] | TOTAL | 8136000
[7 empty] | Crew Size | 6.7986
Total Direct Cost |  |  | 4598577.9293
Total Direct Cost & with Mob and Monitoring |  |  | 5623577.9293
Total direct cost+Contaminated soil+post closure monitoring |  |  | 4598577.9293
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 5623498.1929
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | 459857.7929 | 10% of direct Cost |  |  |  |  | 460000 | 9200
Engineering |  | 3.9% | 179344.5392 | 3.9% of direct Cost |  |  |  |  | 179000 | 9500
Project supervision, management & contract administration |  | 9.4% | 432266.3254 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 432000 | 130900
0
Contingency |  | 12.5% | 702937.2741 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 703000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 18750000 |  | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites (L) | 1092661.8882 | 1093000
Heat and Power (L) | 212015.0886 | 212000 | 115.5 | L/Man-day
Total fuel reuired during closure (L) | 1304676.9768 | 1305000
|  |  | 212015.0886 | Cost
Cost to mob. Fuel per Litre | 0.4 | 0 |  |  |  |  | 67957.4758
25.55
Demob 50% of total capacity | 937500 | 938000
Mob 50% fuel required during closure | 260935.3954 | 261000
Total Mob/Demo Fuel | 1198435.3954 | 1198000
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 1835.6285
Southern Hires (70%) | 1285 |  | Cost per/day | 110
Northern Hires (30%) | 551 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 109803.25
Cost northern Communities | 41325
|  |  | Accomodation Costs | 201919.132
Total Cost | 151128.25 | 151000 | Camp Op Fuel Costs | 212015.0886
|  |  | TOTAL | 413934.2206 | 414000 | 225.5358 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 0 |  | Cost per Inspection | 23200
TOTAL | 0 |  | Total # of Trips | 0
|  |  | TOTAL | 0
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 0
TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2017 Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 828404.195
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 22000
[10 empty] | Ammonium Nitrate | 0 | Based on 716,519 kg of pre-packaged explosives @ $2.37/kg + 2,342.5 m3 of ammonium nitrate @$358/m3 | attached email (RE: Baffinland Iron Mines Corporation - Supplementary Information.msg) on email from Adam sent on Mon 12/14/2015 11:09 AM
[10 empty] | Contaminated Soil Treatment | 63000 | Assume 1/2 of Milne Port Bladder Farm Contaminated
[10 empty] | Mobilization of Workers Required for Reclamation | 29000
[10 empty] | Worker Accommodation & Camp Operation | 80000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 83000
3546.8906
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 354.6891 |  |  | 354.6891 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline |  |  | 4232.1667
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 41143.9309
[7 empty] | 110 | 39015.7965 |  | Engineering Fees | 32000 | %
[8 empty] | 80159.7274 |  | Supervision, Project Management & Contract Administration | 84000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 135000 | %
[10 empty] | INDIRECT SUB-TOTAL | 528000
[13 empty] | I | 38.94%
[10 empty] | TOTAL | 1356000 |  | D | 61.09%
[7 empty] | Crew Size | 1.3137
Total Direct Cost |  |  | 828404.195
Total Direct Cost & with Mob and Monitoring |  |  | 1020404.195
Total direct cost+Contaminated soil+post closure monitoring |  |  | 891404.195
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 1083529.0474
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | 82840.4195 | 10% of direct Cost |  |  |  |  | 83000 | 9200
Engineering |  | 3.9% | 32307.7636 | 3.9% of direct Cost |  |  |  |  | 32000 | 9500
Project supervision, management & contract administration |  | 9.4% | 83791.9943 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 84000 | 130900
0
Contingency |  | 12.5% | 135441.1309 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 135000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 0 | No increase in bulk fuel capacity | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 67957.4758 | 68000
Heat and Power | 40966.5863 | 41000 | 115.5 | L/Man-day
Total fuel reuired during closure | 108924.0622 | 109000
|  |  | 40966.5863 | Cost
Cost to mob. Fuel per Litre | 0.4 | 0 |  |  |  |  | 67957.4758
25.55
Demob 50% of total capacity | 0 | 0
Mob 50% fuel required during closure | 21784.8124 | 22000
Total Mob/Demo Fuel | 21784.8124 | 22000
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 354.6891
Southern Hires (70%) | 249 |  | Cost per/day | 110
Northern Hires (30%) | 107 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 21277.05
Cost northern Communities | 8025
|  |  | Accomodation Costs | 39015.7965
Total Cost | 29302.05 | 29000 | Camp Op Fuel Costs | 40966.5863
|  |  | TOTAL | 79982.3828 | 80000 | 225.5497 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 0 |  | Cost per Inspection | 23200
TOTAL | 0 |  | Total # of Trips | 0
|  |  | TOTAL | 0
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 0
TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2016 Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 292479.6416
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 9000
[10 empty] | Ammonium Nitrate | 2537000 | Based on 716,519 kg of pre-packaged explosives @ $2.37/kg + 2,342.5 m3 of ammonium nitrate @$358/m3 | attached email (RE: Baffinland Iron Mines Corporation - Supplementary Information.msg) on email from Adam sent on Mon 12/14/2015 11:09 AM
[10 empty] | Contaminated Soil Treatment | 0 | Covered in 2014 Baseline
[10 empty] | Mobilization of Workers Required for Reclamation | 17000
[10 empty] | Worker Accommodation & Camp Operation | 47000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 29000
2091.67
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 209.167 |  |  | 209.167 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 24263.3717
[7 empty] | 110 | 23008.3697 |  | Engineering Fees | 11000 | %
[8 empty] | 47271.7415 |  | Supervision, Project Management & Contract Administration | 27000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 48000 | %
[10 empty] | INDIRECT SUB-TOTAL | 2725000
[13 empty] | I | 90.32%
[10 empty] | TOTAL | 3017000 |  | D | 9.694%
[7 empty] | Crew Size | 0.77469
Total Direct Cost |  |  | 292479.6416
Total Direct Cost & with Mob and Monitoring |  |  | 385479.6416
Total direct cost+Contaminated soil+post closure monitoring |  |  | 292479.6416
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 386180.9137
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | 29247.9642 | 10% of direct Cost |  |  |  |  | 29000 | 9200
Engineering |  | 3.9% | 11406.706 | 3.9% of direct Cost |  |  |  |  | 11000 | 9500
Project supervision, management & contract administration |  | 9.4% | 27493.0863 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 27000 | 130900
0
Contingency |  | 12.5% | 48272.6142 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 48000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 0 | No increase in fuel capacity | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 22508.8496 | 23000
Heat and Power | 24158.7882 | 24000 | 115.5 | L/Man-day
Total fuel reuired during closure | 46667.6378 | 47000
|  |  | 24158.7882 | Cost
Cost to mob. Fuel per Litre | 0.4 | 0
25.55
Demob 50% of total capacity | 0 | 0
Mob 50% fuel required during closure | 9333.5276 | 9000
Total Mob/Demo Fuel | 9333.5276 | 9000
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 209.167
Southern Hires (70%) | 147 |  | Cost per/day | 110
Northern Hires (30%) | 63 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 12561.15
Cost northern Communities | 4725
|  |  | Accomodation Costs | 23008.3697
Total Cost | 17286.15 | 17000 | Camp Op Fuel Costs | 24158.7882
|  |  | TOTAL | 47000 | 47000 | 224.7008 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 0 |  | Cost per Inspection | 23200
TOTAL | 0 |  | Total # of Trips | 0
|  |  | TOTAL | 0
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 0
TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2015 R Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 3044218.5608
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 170000
[10 empty] | Ammonium Nitrate | 0 | Covered in 2014 Baseline
[10 empty] | Contaminated Soil Treatment | 5000 | Anmar Workshop (Memo H349001-1000-07-220-0002, Rev. 0)
[10 empty] | Mobilization of Workers Required for Reclamation | 165000
[10 empty] | Worker Accommodation & Camp Operation | 451000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 304000
20009.1284
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 2000.9128 |  |  | 2000.9128 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 232105.889
[7 empty] | 110 | 220100.412 |  | Engineering Fees | 119000 | %
[8 empty] | 452206.301 |  | Supervision, Project Management & Contract Administration | 287000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 496000 | %
[10 empty] | INDIRECT SUB-TOTAL | 1997000
[13 empty] | I | 39.61%
[10 empty] | TOTAL | 5041218.5608 |  | D | 60.39%
Total Direct Cost |  |  | 3044218.5608
Total Direct Cost & with Mob and Monitoring |  |  | 3964218.5608
Total direct cost+Contaminated soil+post closure monitoring |  |  | 3049218.5608
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 3969636.7115
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | 304421.8561 | 10% of direct Cost |  |  |  |  | 304000
Engineering |  | 3.9% | 118724.5239 | 3.9% of direct Cost |  |  |  |  | 119000
Project supervision, management & contract administration |  | 9.4% | 286626.5447 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 287000
0
Contingency |  | 12.5% | 496204.5889 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 496000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 0 | No increase in fuel capacity | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 619866.8291
Heat and Power | 231105.4326 |  | 115.5 | L/Man-day
Total fuel reuired during closure | 850972.2617
|  |  | 231105.4326 | Cost
Cost to mob. Fuel per Litre | 0.4
25.55
Demob 50% of total capacity | 0
Mob 50% fuel required during closure | 170194.4523
Total Mob/Demo Fuel | 170194.4523
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 2000.9128
Southern Hires (70%) | 1401 |  | Cost per/day | 110
Northern Hires (30%) | 601 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 119715.45
Cost northern Communities | 45075
|  |  | Accomodation Costs | 220100.412
Total Cost | 164790.45 |  | Camp Op Fuel Costs | 231105.4326
|  |  | TOTAL | 451000 | 451000 | 225.3971 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 0 |  | Cost per Inspection | 23200
TOTAL | 0 |  | Total # of Trips | 0
|  |  | TOTAL | 0
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 0
TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2015-A Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 331000
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 9000
[10 empty] | Ammonium Nitrate | 0
[10 empty] | Contaminated Soil Treatment | 0 | Covered in 2014 Baseline
[10 empty] | Mobilization of Workers Required for Reclamation | 17000
[10 empty] | Worker Accommodation & Camp Operation | 47000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 33000
2099.2237
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 209.9224 |  |  | 209.9224 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 24350.9953
[7 empty] | 110 | 23091.4611 |  | Engineering Fees | 13000 | %
[8 empty] | 47442.4564 |  | Supervision, Project Management & Contract Administration | 31000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 0 | %
[10 empty] | INDIRECT SUB-TOTAL | 150000
[13 empty] | I | 31.19%
[10 empty] | TOTAL | 481000 |  | D | 68.81%
[7 empty] | Crew Size | 0.77749
Total Direct Cost |  |  | 330810.2053
Total Direct Cost & with Mob and Monitoring |  |  | 427810.2053
Total direct cost+Contaminated soil+post closure monitoring |  |  | 330810.2053
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 428514.8711
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 10% | 33081.0205 | 10% of direct Cost |  |  |  |  | 33000 | 9200
Engineering |  | 3.9% | 12901.598 | 3.9% of direct Cost |  |  |  |  | 13000 | 9500
Project supervision, management & contract administration |  | 9.4% | 31096.1593 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 31000 | 130900
0
Contingency |  | 12.5% | 53564.3589 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 54000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 0 | No increase in fuel capacity | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 20296.2772
Heat and Power | 24246.0342 |  | 115.5 | L/Man-day
Total fuel reuired during closure | 44542.3114
|  |  | 24246.0342 | Cost
Cost to mob. Fuel per Litre | 0.4
25.55
Demob 50% of total capacity | 0
Mob 50% fuel required during closure | 8908.4623
Total Mob/Demo Fuel | 8908.4623
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 209.9224
Southern Hires (70%) | 147 |  | Cost per/day | 110
Northern Hires (30%) | 63 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 12561.15
Cost northern Communities | 4725
|  |  | Accomodation Costs | 23091.4611
Total Cost | 17286.15 |  | Camp Op Fuel Costs | 24246.0342
|  |  | TOTAL | 47000 | 47000 | 223.8923 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 0 |  | Cost per Inspection | 23200
TOTAL | 0 |  | Total # of Trips | 0
|  |  | TOTAL | 0
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 0
TOTAL | 0
Included in 2014 Re-baseline
Included in 2014 Re-baseline
Included in 2014 Re-baseline

## 2015 Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 710000
[10 empty] | Off-Site Disposal of Waste & Material | 0 | Covered in 2014 Baseline
[10 empty] | Fuel | 29000
Ammonium Nitrate
[10 empty] | Contaminated Soil Treatment | 0 | Covered in 2014 Baseline
[10 empty] | Mobilization of Workers Required for Reclamation | 46000
[10 empty] | Worker Accommodation & Camp Operation | 125243.9101
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 71000
5554.0537
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 0 | Covered in 2014 Baseline
|  |  |  | 555.4054 |  |  | 555.4054 |  |  | Project Environmental Site Assessment | 0 | Covered in 2014 Baseline
[10 empty] | Closure & Post Closure Monitoring | 0 | Covered in 2014 Baseline
[7 empty] | 116 | 64427.0225
[7 empty] | 110 | 61094.5903 |  | Engineering Fees | 28000 | %
[8 empty] | 125521.6128 |  | Supervision, Project Management & Contract Administration | 147000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 225000 | %
[10 empty] | INDIRECT SUB-TOTAL | 671243.9101
[10 empty] | TOTAL | 1381000
[13 empty] | I | 48.61%
[13 empty] | D | 51.41%
[7 empty] | Crew Size | 2.0571
Total Direct Cost |  |  | 709664.5685
Total Direct Cost & with Mob and Monitoring |  |  | 951908.4786
Total direct cost+Contaminated soil+post closure monitoring |  |  | 1560864.5685
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 1802839.9855
Mobilzation |  | 10% | 70966.4568 | 10% of direct Cost |  |  |  |  | 71000 | 9200
Engineering |  | 3.9% | 27676.9182 | 3.9% of direct Cost |  |  |  |  | 28000 | 9500
Project supervision, management & contract administration |  | 9.4% | 146721.2694 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 147000 | 130900
0
Contingency |  | 12.5% | 225354.9982 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 225000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 100000 | Increase in 1 fuel tanks (@100,000 Each) | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 57837.505
Heat and Power | 64149.3198 |  | 115.5 | L/Man-day
Total fuel reuired during closure | 121986.8249
|  |  | 64149.3198 | Cost
Cost to mob. Fuel per Litre | 0.4
25.55
Demob 50% of total capacity | 5000
Mob 50% fuel required during closure | 24397.365
Total Mob/Demo Fuel | 29397.365
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 555.4054
Southern Hires (70%) | 389 |  | Cost per/day | 110
Northern Hires (30%) | 167 |  | Fuel consumption per day | 115.5
Cost Southern Communities | 33240.05
Cost northern Communities | 12525
|  |  | Accomodation Costs | 61094.5903
Total Cost | 45765.05 |  | Camp Op Fuel Costs | 64149.3198
|  |  | TOTAL | 125000 | 125000 | 225.0608 | Assumed 6 southern flights + 8 northern flights
GEOTECHNICAL INVESTIGATIONS |  |  | FIELD SAMPLING
Cost/hour | 200 |  | Cost/hour | 200
Billable hours per inspection | 46 |  | Billable hours per inspection | 72
Travel Costs | 4500 |  | Travel Costs | 4500
Report Costs | 5000
|  |  | Samples | 43
Cost per Inspection | 18700 |  | Cost/Sample | 100
Total # of Inspections | 8 |  | Cost per Inspection | 23200
TOTAL | 149600 |  | Total # of Trips | 16
|  |  | TOTAL | 371200
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 8
TOTAL | 480000

## 2014 Indirect Costs (hidden)
[10 empty] | DIRECT COST SUB-TOTAL | 13876333.9632 |  | 14.19%
[10 empty] | Off-Site Disposal of Waste & Material | 1969000
[10 empty] | Fuel | 2873000
[10 empty] | Ammonium Nitrate | 0
[10 empty] | Contaminated Soil Treatment | 234000
[10 empty] | Mobilization of Workers Required for Reclamation | 652000
[10 empty] | Worker Accommodation & Camp Operation | 1649000
[7 empty] | TOTAL MAN-HOURS |  |  | Mobilization and Demobilization of Equipment and Materials by Sealift | 1388000
73124.0009
|  |  |  | Man Days |  |  | TOTAL MAN-DAYS |  |  | Geotechnical Inspections | 150000
|  |  |  | 7312.4001 | Assuming 10 h/day |  | 7312.4001 |  |  | Project Environmental Site Assessment | 90000
[10 empty] | Closure & Post Closure Monitoring | 851200
[7 empty] | 116 | 848238.41
[7 empty] | 110 | 804364.0095 |  | Engineering Fees | 541000 | %
[8 empty] | 1652602.4195 |  | Supervision, Project Management & Contract Administration | 1406000 | %
[10 empty] | Contingency (applied to Direct Costs, Mobilization of Resouces Required for Reclamation and Post-Closure Monitoring | 2331000 | %
[10 empty] | INDIRECT SUB-TOTAL | 14134200
[10 empty] | TOTAL | 28011000
[7 empty] | Crew Size | 27.083
Total Direct Cost |  |  | 13876333.9632
Total Direct Cost & with Mob and Monitoring |  |  | 18656533.9632
Total direct cost+Contaminated soil+post closure monitoring |  |  | 14961533.9632
Total direct cost+Contaminated soil +Mob/demob + Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  | 18650113.5789
Mobilzation |  | 10% | 1387633.3963 | 10% of direct Cost |  |  |  |  | 1388000
Engineering |  | 3.9% | 541177.0246 | 3.9% of direct Cost |  |  |  |  | 541000
Project supervision, management & contract administration |  | 9.4% | 1406384.1925 | 9.4% of (direct cost+Contaminated soil treatement+post closure monitoring) |  |  |  |  | 1406000
0
Contingency |  | 12.5% | 2331264.1974 | 12.5% of (direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) |  |  |  |  | 2331000
0
FUEL ON-SITE |  |  | CAMP FUEL CONSUMPTION
Total Capacity @ site (L) | 51000000 |  | 1732500 | Avg Monthly Consumption
Demob cost per Litre | 0.1 |  | 30 | Days in month
|  |  | 500 | Average camp population in '14
Reclamation Activites | 771239.0515
Heat and Power | 844582.21 |  | 115.5 | L/Man-day
Total fuel reuired during closure | 1615821.2615
|  |  | 844582.21 | Cost
Cost to mob. Fuel per Litre | 0.4
Demob 50% of total capacity | 2550000
Mob 50% fuel required during closure | 323164.2523
Total Mob/Demo Fuel | 2873164.2523
FLIGHTS |  |  | WORKERS ACCOMODATION
Person Days On-Site | 7312.4001
Southern Hires (70%) | 5119 |  | Cost per/day | 110
Northern Hires (30%) | 2194 |  | Fuel consumption per day | 115.5
Passengers per voyage | 77
Productive days per rotation | 20
Person days per Flight | 1540 |  | Accomodation Costs | 804364.0095
|  |  | Camp Op Fuel Costs | 844582.21
Total Flights Required | 4 |  | TOTAL | 1649000 | 1649000 | 225.5074 | Assumed 6 southern flights + 8 northern flights
Cost per Flight | 118000
TOTAL (Southern Flights) | 472000
FIELD SAMPLING
Passengers per voyage | 24 |  | Cost/hour | 200
Productive days per rotation | 20 |  | Billable hours per inspection | 72
Person days per Flight | 480 |  | Travel Costs | 4500
Total Flights Required | 5
|  |  | Samples | 43 |  | 16
Cost per Flight | 36000 |  | Cost/Sample | 100 |  | 1600
TOTAL (Northern Flights) | 180000
|  |  | Cost per Inspection | 23200
TOTAL (Both Southern and Northern) | 652000
|  |  | Total # of Trips | 16
GEOTECHNICAL INVESTIGATIONS
Cost/hour | 200 |  | TOTAL | 371200
Billable hours per inspection | 46
Travel Costs | 4500
Report Costs | 5000
Cost per Inspection | 18700
Total # of Inspections | 8
TOTAL | 149600
ANALYSIS & REPORTING
Cost/hour | 200
Billable hours per year | 300
Cost per Year | 60000
# of Years | 8
TOTAL | 480000

## Project component breakdown (hidden)
Mary River Project Component Breakdown for the 2014 Reclamation Security Total Project Estimate
Level 0 - Site Location |  | Level 1 - Area |  | Level 2 - Facility / System |  | Level 3 - Sub Facility / Sub System |  | Notes | Uncertainty | Required Reclamation Activities | Required Unit Costs | Required Inputs | Responsibility | Priorority
NOTES
Level 3 FBS definitions
1. “building” refers to the building structure including platforms, walls and enclosure; architectural fit-out including partition
walls, finishes and fixtures; and building services including hvac, lighting, potable water and sewage plumbing, fire
suppression system (building internal spray system only), fire detection and alarm systems and comms/IT systems.
2. "system" generally refers to the mechanical equipment with associated piping, electrical and process control.
1000 | Project Wide
|  | 1100 | General (Project Controls Use)
2000 | Milne Port
|  | 2100 | General
|  |  |  | 2130 | Site Development
[6 empty] | 2131 | Construction Laydown | Assume no contamination | Low | Grade and Re-Contour
[6 empty] | 2133 | Materials Handling | Includes mobile crusher/screener. Need to determine final disposal location | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2138 | Quarry Development | No Quarries at Milne Port. See Tote Road | N/A | N/A
[6 empty] | 2139 | Site Roads | covers interconnecting roads that are not part of the pads | Low | Grade and Re-Contour, Culvert Removal
|  |  |  | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2143 | Mobile Maintenance Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2144 | Mobile Site Services Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
|  | 2200 | Marine
|  |  |  | 2220 | Ore Dock
[6 empty] | 2221 | Dock Structure (includes ship loader foundations) | Pending approval of ERP | TBD | TBD
[6 empty] | 2223 | Dock Office | Pending approval of ERP | TBD | TBD
[6 empty] | 2225 | Mooring Buoys | Pending approval of ERP | TBD | TBD
[6 empty] | 2230 | Causeway | Pending approval of ERP | TBD | TBD
|  |  |  | 2240 | Transshipment and Marine Vessels |  |  | Pending approval of ERP | TBD | TBD
|  | 2300 | Material Handling
|  |  |  | 2340 | Stockpile
[6 empty] | 2341 | Ore Stacking System | Pending approval of ERP | TBD | TBD
[6 empty] | 2342 | Ore Reclaim System | Pending approval of ERP | TBD | TBD
[6 empty] | 2345 | Stockpile Settling Pond | Pending approval of ERP | TBD | TBD
|  |  |  | 2350 | Ship Loading
[6 empty] | 2351 | Ship Loading System | Pending approval of ERP | TBD | TBD
|  | 2400 | Aerodrome
|  |  |  | 2430 | Aerodrome Facilities
[6 empty] | 2435 | Field Electrical Centre | Includes airstrip | Low | Grade and Re-Contour, airstrip lighting removal (lump sum - incl removal & disposal)
|  | 2500 | Non Process Facilities
|  |  |  | 2510 | Accommodations Area
[6 empty] | 2511 | Service Core | Assume no contamination. Uncertain about hazardous materials in kitchen facility | Med. | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction), Decontamination of a module
[6 empty] | 2512 | Accommodation Wings | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2513 | Emergency Services Building | Assume no contamination | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 2520 | Services Area
[6 empty] | 2521 | Services Buildings | Incl. maintenance shop, welding shop, wash cars. Assume contamination | Low | Steel Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Services Buildings | Incl. Warehouse, Office Building. Assume no contamination | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2522 | Services Equipment | Mobile & mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 2530 | Power Generation |  |  | Includes all E-house on-site, Does not include distribution system | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 2540 | Waste Management (building and incinerator) |  |  | Includes fold-a-way building, containerized incinerator, and any other minor support equipment | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction), Disassembly & Decontaminate (Heavy Equipment)
|  |  |  | TBD | Hazardous Waste Storage Area |  |  | Need to confirm contamination type and disposal options for soil from hazardous waste berms | Med. | Soil Excavation, Soil disposal off-site, Liner Removal, Liner disposal off-site, Grade & Recontour
|  |  |  | 2550 | Waste Disposal (Landfarm) |  |  | Need to confirm disposal options for soil from landfarm and final reclamation objectives for landfarm | Med. | Soil Excavation, Soil disposal off-site, Liner Removal, Liner disposal off-site, Grade & Recontour
|  | 2600 | Fuel Systems
|  |  |  | 2610 | Milne Tank Farm
[6 empty] | 2611 | Containment Dyke | Quantity of area requiring off-site disposal of soil and liner TBD | Med | Soil Excavation, Soil disposal off-site (TBD), Liner Removal, Liner disposal off-site (TBD), Grade & Recontour
[6 empty] | 2613 | Arctic Diesel System | Assume contamination | Low | Teardown of steel tank, demobilization of fuel, decontaminate, Load & transport, disposal & cover (incl compaction)
[6 empty] | 2614 | Jet-A System | Assume contamination | Low | Teardown of steel tank, demobilization of fuel, decontaminate, Load & transport, disposal & cover (incl compaction)
[6 empty] | 2615 | Marine Pipeline | Assume contamination | Low | Removal of Pipeline, decontaminate, Load & transport, disposal & cover (incl compaction)
[6 empty] | 2619 | Power Generation | Only applicable if power generation for tank farm separate from site-wide power generation | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  | 2700 | Site Utilities
|  |  |  | 2720 | Water Systems |  |  | includes water building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 2730 | Sewage System
[6 empty] | 2731 | Sewage Treatment Systems | Containerized STP | Low | Modular Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2732 | Sewage Truck Building | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2734 | Treated Effluent Discharge | Above ground pipeline | Low | Removal of pipeline, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 2735 | Off Spec Effluent Pond | Assume no water treatment, would be treated during course of closure at STP, liner disposal on-site | Low | Liner Removal, Liner disposal on-site, Grade & Recontour
|  |  |  | 2750 | Power Distribution System |  |  | includes yard lighting (poles) | Low | Removal of cable, Load & transport, Disposal & Cover (incl compaction)
3000 | Tote Road
|  | 3100 | General
|  |  |  | 3110 | Communication and IT Infrastructure
[6 empty] | 3111 | Communications Facility No. 1 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3112 | Communications Facility No. 2 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3113 | Communications Facility No. 3 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3114 | Communications Facility No. 4 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3115 | Communications Facility No. 5 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3116 | Communications Facility No. 6 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3117 | Communications Facility No. 7 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 3118 | Communications Facility No. 8 | Includes all equipment at communications seacan | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 3130 | Site Development
[6 empty] | 3131 | Road Upgrade | Road left in place (public road). Need to determine culvert type, proximity & quantity impact on reclamation activities. Long-term stability needs to be confirmed | High | Tote Road Culvert Removal, Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | 3132 | River Crossing at STA 17 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | High | Removal of bridge span (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Sea-can bridge at STA 17 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | Med | Removal of seacan bridge (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | 3133 | River Crossing at STA 62 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | High | Removal of bridge span (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Sea-can bridge at STA 62 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | Med | Removal of seacan bridge (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | 3134 | River Crossing at STA 80 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | High | Removal of bridge span (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Sea-can bridge at STA 80 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | Med | Removal of seacan bridge (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | 3135 | River Crossing at STA 97 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | High | Removal of bridge span (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Sea-can bridge at STA 97 | Needs long term physical stability. Need to confirm if leaving abutments in place allow for long term stability | Med | Removal of seacan bridge (incl re-grading), Removal of abutments (?), Load & Transport, Disposal & Cover (incl compaction)
[6 empty] | 3138 | Quarry Development
[6 empty] | TBD | Quarry at Q1 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[6 empty] | TBD | Quarry at Q7 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[6 empty] | TBD | Quarry at Q11 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[6 empty] | TBD | Borrow Source at P1 | TBC individual activities required for each borrow sources. Need to ensure long-term stability, need to ensure proper drainage and pathways. | High | Grade and Re-contour Borrow Source, Application of insulation material, Secondary application of Grade and Re-contour of Borrow Source
[6 empty] | TBD | Quarry at Q19 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[6 empty] | TBD | Borrow Source at Km 97/98 | Need to ensure long-term stability, need to ensure proper drainage and pathways | High | Grade and Re-contour Borrow Source, Application of insulation material, Secondary application of Grade and Re-contour of Borrow Source
[6 empty] | TBD | Borrow Source at Km 102 | Need to ensure long-term stability, need to ensure proper drainage and pathways | High | Grade and Re-contour Borrow Source, Application of insulation material, Secondary application of Grade and Re-contour of Borrow Source
[6 empty] | TBD | Unidentified Borrow Sources | Need to determine reclamation strategy small scale for borrow sources along the Tote Road that have been used but not formalized | High | Grade and Re-contour Borrow Source, Application of insulation material, Secondary application of Grade and Re-contour of Borrow Source
[6 empty] | 3139 | Infrastructure Pads | Assume no contamination | Low | Grade and Re-Contour
|  |  |  | 3160 | Emergency Shelters |  |  | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
4000 | Mine Site
|  | 4100 | General
|  |  |  | 4130 | Site Development
[6 empty] | 4131 | Construction Laydown Areas | Assume no contamination | Low | Grade and Re-Contour
[6 empty] | 4133 | Ore Crushing and Loading | Pending approval of ERP | TBD | TBD
[6 empty] | 4135 | Explosives Pads | Assume no contamination. | Low | Grade and Re-Contour
[6 empty] | 4138 | Quarry Development
[7 empty] | Quarry at QMR2 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[7 empty] | Quarry at D1Q1 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[7 empty] | Quarry at D1Q2 | Needs long term physical stability. Assume operations leaves quarry in long-term stable condition | Med | Grade and Re-contour
[6 empty] | 4139 | Site Roads | covers interconnecting roads that are not part of the pads | Low | Grade and Re-Contour, Culvert Removal
|  |  |  | 4140 | Mobile Equipment
[6 empty] | 4141 | Mine Mobile Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4142 | Mobile Materials Handling Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4143 | Mobile Maintenance Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4144 | Mobile Site Services Equipment | Assumed on-site disposal of deemed inert (decontaminated) | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
|  | 4200 | Mine
|  |  |  | 4210 | Explosives Facility
[6 empty] | 4211 | Explosives Plant Building | Assume contamination. Need to confirm reclamation strategy | Med. | Modular Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4212 | Explosives Shop | Assume contamination. Need to confirm reclamation strategy | Med. | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4213 | Explosives Magazines | Consist of containerized magazine | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4220 | Haul Roads
[6 empty] | 4221 | Pit 1 Haul Road | Need to confirm number of culverts | Low | Grade and Re-Contour, Culvert Removal, Removal of cable, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4230 | Waste Rock Dump |  |  | Small existing stockpile | High | Stockpile stabilization (?)
|  |  |  | 4250 | Open Pit Development |  |  | Need to confirm stability | High | Open Pit Stabilization
|  |  |  | 4280 | Mine Support Facilities
[6 empty] | 4281 | Pit Office Building | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  | 4300 | Material Handling
|  |  |  | 4380 | Crushing and Screening
[6 empty] | 4381 | Crushing and Screening System | Mobile (trailer based) crushing and screening unit | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4382 | Truck Weigh Facility | includes truck weigh building. To confirm truck weigh building design | Med | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction); Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4385 | Crushing Stockpile Settling Pond | Amount of sediment/contamination in pond TBD | Med | Fill Application
|  | 4400 | Aerodrome
|  |  |  | 4410 | Runway & Apron |  |  | Gravel airstrip & apron | Low | Grade and Re-Contour
|  |  |  | 4430 | Aerodrome Facilities
[6 empty] | 4431 | Aerodrome Office | Mobile office trailer used | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4432 | Equipment Building | Small warehouse building | Low | Modular Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4433 | Plant & Equipment | Included equipment required for basic airplane inspections and maintenance | Low | Disassembly & Decontaminate (Light Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4435 | Field Electrical Centre | To be determined what consists of | TBD | TBD
[6 empty] | 4436 | Airfield Lighting and Visual Aids | Surface lighting. No foundations or buried cable. | Low | airstrip lighting removal (lump sum - incl removal & disposal)
[6 empty] | 4439 | Power Generation | Only applicable if power generation for tank farm separate from site-wide power generation | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  | 4500 | Non Process Facilities
|  |  |  | 4510 | Accommodations Area
[6 empty] | 4511 | Service Core | Assume no contamination. Uncertain about hazardous materials in kitchen facility | Med. | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction), Decontamination of a module
[6 empty] | 4512 | Accommodation Wings | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4513 | Emergency Services Building | Assume no contamination | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4520 | Services Area
[6 empty] | 4521 | Services Buildings | Incl. maintenance shop, welding shop, wash cars. Assume contamination | Low | Steel Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4522 | Services Equipment | Incl. Warehouse, Office Building. Assume no contamination | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4523 | Truck Wash Facility | includes truck wash building | Low | Steel Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4530 | Power Generation |  |  | Includes all E-house on-site, Does not include distribution system | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4540 | Waste Management |  | Waste Management (building and incinerator) | Includes fold-a-way building, containerized incinerator, and any other minor support equipment | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction), Disassembly & Decontaminate (Heavy Equipment)
[7 empty] | Waste Disposal (Landfill) | Need to confirm disposal options for soil from landfill if required | Med. | Soil Excavation, Soil disposal off-site (TBD), Cover Application, Grade & Recontour
|  | 4600 | Fuel Systems
|  |  |  | 4610 | Mine Tank Farm
[6 empty] | 4611 | Containment Dyke | Quantity of area requiring off-site disposal of soil and liner TBD | Med | Soil Excavation, Soil disposal off-site (TBD), Liner Removal, Liner disposal off-site (TBD), Grade & Recontour
[6 empty] | 4613 | Arctic Diesel System | Assume contamination | Low | Teardown of steel tank, demobilization of fuel, decontaminate, Load & transport, disposal & cover (incl compaction)
|  | 4700 | Site Utilities
|  |  |  | 4710 | Raw Water Intake
[6 empty] | 4711 | Raw Water Jetty | Assume left in place | Low | Grade and Re-Contour
[6 empty] | 4712 | Raw Water System | include eqt, modular pumphouse and pipe to water building | Low | Disassembly & Decontaminate (Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4720 | Water Systems |  |  | includes water building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4730 | Sewage System
[6 empty] | 4731 | Sewage Treatment Systems | Containerized STP | Low | Modular Building teardown, Decontaminate, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4732 | Sewage Truck Building | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 4733 | Treated Effluent Pond | Assume no water treatment, would be treated during course of closure at STP, liner disposal on-site | Low | Liner Removal, Liner disposal on-site, Grade & Recontour
[6 empty] | 4734 | Treated Effluent Discharge | Above ground pipeline | Low | Removal of pipeline, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 4750 | Power Distribution System |  |  | includes yard lighting (poles) | Low | Removal of cable, Load & transport, Disposal & Cover (incl compaction)
7000 | Construction Facilities & Services
|  | 7100 | Project Wide
|  |  |  | 7110 | Communications & IT
[6 empty] | 7111 | Communications Services | Indirect cost. Will address at later date | TBD | N/A
|  |  |  | 7120 | Air Services
[6 empty] | 7121 | Jet Service | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7122 | Local Air Charter | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7123 | Helicopter Service | Indirect cost. Will address at later date | TBD | N/A
|  | 7200 | Milne Port
|  |  |  | 7210 | Exploration Camp & Facilities
[6 empty] | 7211 | Tent Camp | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7212 | Hardwall Camp | Assume no contamination. Uncertain about hazardous materials in kitchen facility | Med. | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction), Decontamination of a module
[6 empty] | 7213 | Utilities & Services | Including RBC. Power generation considered in Site Services mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7214 | Off-Spec Effluent Pond(s) | Assume no water treatment, would be treated during course of closure at STP, liner disposal on-site | Low | Liner Removal, Liner disposal on-site, Grade & Recontour
|  |  |  | 7230 | Buildings, Shops & Warehouses
[6 empty] | 7231 | Office Facilities | offices and training rooms. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7232 | Workforce Facilities | lunch rms, wash cars & smoke shltrs. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7234 | Garages & Workshops | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7235 | Warehouses | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7238 | Civil Contractor Buildings | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7240 | Vehicles and Equipment
[6 empty] | 7241 | Company Vehicles | Mobile & mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7242 | Emergency Response Equipment | Mobile & mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment, Light Equipment or Minor Equipment), Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7244 | Construction Power Supply | Only applicable if power generation for construction separate from site-wide power generation | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7250 | Construction Facilities
[6 empty] | 7251 | Concrete Facilities | Mobile (trailer-based) batch plant. includes washdown / settling pond | Low | Disassembly & Decontaminate (Heavy), Load & transport, Disposal & Cover (incl compaction). Tear down on non-contaminated steel building
[6 empty] | 7252 | Explosives Facilities | incl. magazines | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7270 | Camp & Site Services
[6 empty] | 7271 | Camp Operations & Catering | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7273 | Site Operations | Includes snow clearing, water, sewage, waste, fuel & aerodrome. Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7275 | Maintenance and Repair | Includes facilities, roads, mobile equipment. Indirect cost. Will address at later date | TBD | N/A
|  |  |  | 7280 | Construction Services
[6 empty] | TBD | Off-Site Waste Disposal | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Off-Site Explosives Disposal | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Off-Site Fuel Disposal | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Heavy Transport Services | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Explosives Supply Services | Indirect cost. Will address at later date | TBD | N/A
|  | 7400 | Mine Site
|  |  |  | 7410 | Exploration Camp & Facilities
[6 empty] | 7411 | Tent Camp | Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7412 | Utilities & Services | Including RBC. Power generation considered in Site Services mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7430 | Buildings, Shops & Warehouses
[6 empty] | 7431 | Office Facilities | offices and training rooms. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7432 | Workforce Facilities | lunch rms, wash cars & smoke shltrs. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7434 | Garages & Workshops | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | 7435 | Warehouses | Fold-Away Building | Low | Steel Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7450 | Construction Facilities
[6 empty] | 7451 | Concrete Facilities | includes washdown / settling pond. Building Only - Batch plant mechanical equipment accounted for at Milne Port concrete facility | Low | Disassembly & Decontaminate (Heavy), Load & transport, Disposal & Cover (incl compaction). Tear down on non-contaminated steel building
[6 empty] | 7452 | Explosives Facilities | magazines and temporary emulsion plant? | Low | Disassembly & Decontaminate ( Light Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7470 | Camp & Site Services
[6 empty] | 7471 | Camp Operations & Catering | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7473 | Site Operations | Includes snow clearing, water, sewage, waste, fuel & aerodrome. Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7475 | Maintenance and Repair | Includes facilities, roads, mobile equipment. Indirect cost. Will address at later date | TBD | N/A
|  |  |  | 7480 | Construction Services
[6 empty] | 7482 | Heavy Transport Services | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 7484 | Explosives Supply Services | Indirect cost. Will address at later date | TBD | N/A
|  | TBD | Mid-Rail
|  |  |  | TBD | Exploration Camp & Facilities
[6 empty] | TBD | Tent Camp | On Crown Land, not in QIA scope. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Utilities & Services | On Crown Land, not in QIA scope. Confrimation, if any, on-site | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | TBD | Buildings, Shops & Warehouses
[6 empty] | TBD | Office Facilities | On Crown Land, not in QIA scope. Includes: offices and training rooms. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Workforce Facilities | On Crown Land, not in QIA scope. Includes: lunch rms, wash cars & smoke shltrs. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Garages & Workshops | None | Low | None
[6 empty] | TBD | Warehouses | None | Low | None
|  |  |  | TBD | Camp & Site Services
[6 empty] | TBD | Camp Operations & Catering | On Crown Land, not in QIA scope. Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Site Operations | On Crown Land, not in QIA scope. Includes snow clearing, water, sewage, waste, fuel & aerodrome. Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Maintenance and Repair | On Crown Land, not in QIA scope. Includes facilities, roads, mobile equipment. Indirect cost. Will address at later date | TBD | N/A
|  | TBD | Steensby Port
|  |  |  | TBD | Exploration Camp & Facilities
[6 empty] | TBD | Tent Camp | On Crown Land, not in QIA scope. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Utilities & Services | On Crown Land, not in QIA scope. Including RBC. Power generation considered in Site Services mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction)
|  |  |  | TBD | Buildings, Shops & Warehouses
[6 empty] | TBD | Office Facilities | On Crown Land, not in QIA scope. offices and training rooms. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Workforce Facilities | On Crown Land, not in QIA scope. Includes: lunch rms, wash cars & smoke shltrs. Assume no contamination | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Garages & Workshops | To be confrimed | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
[6 empty] | TBD | Warehouses | Seacan storage? | Low | Modular Building teardown, Load & transport, Disposal & Cover (incl compaction)
|  |  |  | 7470 | Camp & Site Services
[6 empty] | TBD | Camp Operations & Catering | Indirect cost. Will address at later date | TBD | None
[6 empty] | TBD | Site Operations | Includes snow clearing, water, sewage, waste, fuel & aerodrome. Indirect cost. Will address at later date | TBD | None
[6 empty] | TBD | Maintenance and Repair | Includes facilities, roads, mobile equipment. Indirect cost. Will address at later date | TBD | None
8000 | Other Indirects
|  | 8100 | Other Indirects
|  |  |  | 8110 | EPCM Services
[6 empty] | 8111 | Project Management, Engineering and Procurement | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | 8112 | Construction Management | Indirect cost. Will address at later date | TBD | N/A
|  |  |  | 8120 | Third Party Services
[6 empty] | 8121 | Geotechnical Consultants | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | Environmental Site Assessment | Indirect cost. Will address at later date | TBD | N/A
[6 empty] | TBD | On-Going Water Management | Indirect cost. Will address at later date | TBD | N/A
|  |  |  | TBD | Mobilization | TBD |  | Includes mobilization of all required equipment, fuel, materials needed for A&R purposes. Does not include personnel (in flight charter costs) | TBD | N/A
|  |  |  | TBD | Demobilization | TBD |  | Includes the demobilization of all required equipment, fuel, materials that cannot be disposed of on-site and is no longer needed for A&R purposes. Does not include personnel (in flight charter costs) | TBD | N/A
9000 | Owner Accounts
|  | 9100 | Owner Accounts
|  |  |  | 9120 | Owner Accounts - Project Management
[6 empty] | 9121 | Owner Accounts - Project Management | Indirect cost. Will address at later date | TBD | N/A
|  |  |  | 9190 | Owner Accounts - Contingency, Escalation, Event Risk Allowance
[6 empty] | 9191 | Contingency | Indirect cost. Will address at later date | TBD | N/A

## H349000-MechanicalEquipmentAndM (hidden)
2342-HP-022
Mechanical Equipment and Motor List
Baffinland Iron Mines Corporation: Mary River Project
H349000
|  | Identification | [12 empty] | Technical | [9 empty] | Procurement
[15 empty] | Design Data | [6 empty] | Supp. Information |  | Diagrams
| X | Rev | EWP | CWP | Area | Tag No | Price Code | Price Code Description | Description | Equip Type | Part of | Const. Type | Eng/Data Status | Package Eng | Design Code | Dimension l x w x h | Dry Wgt (kg) | Contractor | Operating Mode | Design Capacity | Design Load (kW) | Remarks |  | PFD No. | Enquiry No | Manufacturer / Model No. | Sealift
[21 empty] | Name Plate |  |  | PID No.
[21 empty] | Emergency Required (Y/N) |  |  | Datasheet No. |  |  |  | Level 0 - Site Location | Level 1 - Area | Level 2 - Facility / System | Level 3 - Sub Facility / Sub System | Level | Description | Tag Number | QTY | Unit
|  | 0 | 502-2000 |  | 2140 | 2140-MO-001 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 502-2000 |  | 2140 | 2140-MO-002 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 502-2000 |  | 2140 | 2140-MO-003 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 502-2000 |  | 2140 | 2140-MO-004 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-001 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | USED | PRELIMINARY | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | 2014 SEALIFT |  | H349000-2340-05-030-0001 / / | PM102 | CAT 988H | 2014
|  | 0 | 502-2000 |  | 2142 | 2142-MO-002 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | USED | PRELIMINARY | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | 2014 SEALIFT |  | / / / | PM102 | CAT 988H | 2014
|  | 0 | 502-2000 |  | 2142 | 2142-MO-003 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | ETA JULY 25, 2013 |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-004 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / |  |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-005 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | WITH 96" FORKS AND QUICK COUPLER |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-006 | #N/A | #N/A | STOCKPILE FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | WITH 96" FORKS AND QUICK COUPLER |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-009 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-010 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-011 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-012 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-013 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-014 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-015 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-016 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-017 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-018 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-019 | #N/A | #N/A | CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3277 W: 1676 H: 3810 | 3175 |  | INTERMITTENT | 885 KG OPERATING LOAD | / / / | C/W QUICK COUPLER, BUCKETS AND FORKS |  | / / / | PM102 | CAT 247B | 2013
|  | 0 | 502-2000 |  | 2142 | 2142-MO-020 | #N/A | #N/A | CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3277 W: 1676 H: 3810 | 3175 |  | INTERMITTENT | 885 KG OPERATING LOAD | / / / | C/W QUICK COUPLER, BUCKETS AND FORKS |  | / / / | PM102 | CAT 247B | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-002 | #N/A | #N/A | SITE MAINTENANCE GRADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 9412 W: 2791 H: 3535 | 24400 |  | INTERMITTENT | 2.28 M MAX SHOULDER REACH | / / / | 2009, 16FT BLADE |  | / / / | PM102 | CAT 14M | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-003 | #N/A | #N/A | SITE MAINTENANCE TRACK DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4064 W: 2464 H: 2439 | 21600 | NUNA | INTERMITTENT |  | / / / |  |  | / / / | PM102 | CAT D6T XW | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-004 | #N/A | #N/A | PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 7300 |  | INTERMITTENT | 7000 LB TELESCOPING CRANE; 11 | / / / | VMAC CRANE |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-005 | #N/A | #N/A | PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 7300 |  | INTERMITTENT |  | / / / | 10000# TELESCOPIC CRANE; AIR COMPRESSOR |  | / / / | PM130 | PETERBILT 348 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-006 | #N/A | #N/A | SITE MAINTENANCE SMALL LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6050 W: 2390 H: 3150 | 9600 |  | INTERMITTENT | 1.3 M3 BUCKET | / / / | QUICK COUPLERS/BUCKETS/FORKS |  | / / / | PM102 | CAT 930K | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-007 | #N/A | #N/A | SITE MAINTENANCE MID SIZE EXCAVATOR | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 11910 W: 3490 H: 3770 | 45000 |  | INTERMITTENT | 345 HP, 3.5 M3 BUCKET | / / / |  |  | / / / | PM102 | CAT 345DL | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-008 | #N/A | #N/A | MAINTENANCE FUEL/LUBE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 1000 GAL FUEL TANK; 7 PRODUCT | / / / | 1000 GAL FUEL TANK; 7 PRODUCT TANKS; HEATED PRESSURIZED HOUSE |  | H349000-2540-05-030-0001 / / | PM130 | KENWORTH T800 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-009 | #N/A | #N/A | MINE/TOTE ROAD MAINTENANCE PLOW/SAND TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | TENCO CHASSIS MOUNT SPREADER; ONE WAY PLOW; RIGHT HAND SIDE DISCHARGE |  | / / / | PM131 | WESTERN STAR 4700 SF | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-011 | #N/A | #N/A | SITE DEWATERING PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 2057 W: 979 H: 1510 | 834 |  | INTERMITTENT | 4" | / / No | DIESEL C/W TRAILER AND SPILL KIT |  | / / / | PM106 | GORMAN-RUPP 14C2-F3L | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-012 | #N/A | #N/A | SITE DEWATERING PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 2057 W: 979 H: 1510 | 834 |  | INTERMITTENT | 4" | / / No | DIESEL C/W TRAILER AND SPILL KIT |  | / / / | PM106 | GORMAN-RUPP 14C2-F3L | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-013 | #N/A | #N/A | MAINTENANCE HOT BOX | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  | L: 4877 W: 2235 H: 1829 | 1850 |  | INTERMITTENT | 1100000 BTU/H | / / / |  |  | / / / | PM104 | ECOBLAZE CUBE 1100 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-014 | #N/A | #N/A | MAINTENANCE HOT BOX | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  | L: 4877 W: 2235 H: 1829 | 1850 |  | INTERMITTENT | 1100000 BTU/H | / / / |  |  | / / / | PM104 | ECOBLAZE CUBE 1100 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-015 | #N/A | #N/A | MAINTENANCE TRAILER WELDER | MOBILE EQUIPMENT |  | NEW | PRELIMINARY | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM104 |  | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-016 | #N/A | #N/A | FREIGHT TELEHANDLER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 6100 W: 2570 H: 2570 | 15800 | NUNA | INTERMITTENT | 4500 KG CAPACITY | / / / |  |  | / / / | PM106 | CAT TH514 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-017 | #N/A | #N/A | TOTE ROAD MAINTENANCE GRADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 9412 W: 2791 H: 3535 | 24400 |  | INTERMITTENT | 2.28 M MAX SHOULDER REACH | / / / | 2009 - WITH SNOW WINGS |  | / / / | PM102 | CAT 14M | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-018 | #N/A | #N/A | TOTE ROAD MAINTENANCE GRADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 9412 W: 2791 H: 3535 | 24400 |  | INTERMITTENT | 2.28 M MAX SHOULDER REACH | / / / | WITH NEW CRAIG SNOW WINGS |  | / / / | PM102 | CAT 14M | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-019 | #N/A | #N/A | TOTE ROAD MAINTENANCE GRADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 9412 W: 2791 H: 3535 | 24400 |  | INTERMITTENT | 2.28 M MAX SHOULDER REACH | / / / | WITH NEW CRAIG SNOW WINGS |  | / / / | PM102 | CAT 14M | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-020 | #N/A | #N/A | TOTE ROAD MAINTENANCE COMPACTOR | MOBILE EQUIPMENT |  | USED | PRELIMINARY | GRAHAM BURTON |  | L: 5860 W: 2300 H: 3070 | 12250 | NUNA | INTERMITTENT | DRUM WIDTH: 2140 MM; DRUM DIA: | / / / | PURCHASED FROM NUNA |  | / / / | PM102 | CAT CS56 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-021 | #N/A | #N/A | TOTE ROAD MAINTENANCE PLOW/SAND TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | TENCO CHASSIS MOUNT SPREADER; ONE WAY PLOW; RIGHT HAND SIDE DISCHARGE |  | / / / | PM131 | WESTERN STAR 4700 SF | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-022 | #N/A | #N/A | TOTE ROAD MAINTENANCE MID SIZE EXCAVATOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 11910 W: 3490 H: 3770 | 45000 |  | INTERMITTENT | 345 HP, 3.5 M3 BUCKET | / / / |  |  | / / / | PM102 | CAT 345DL HEX | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-023 | #N/A | #N/A | ROAD SNOW BLOWER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 6170 W: 2410 H: 3320 | 18338 |  | INTERMITTENT | WITH SNOW BLOWER ATTACHMENTS | / / / | C/W VOHL MODEL DV400 SNOW BLOWER |  | / / / | PM102 | CAT 950H | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-024 | #N/A | #N/A | MINI CRAWLER CRANE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 2.9 T | / / / | DIESEL/ELECTRIC |  | / / / | PM116 | SPYDER CRANE URW295 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-025 | #N/A | #N/A | FORKLIFT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 2540 W: 1300 H: 2540 | 4800 |  | INTERMITTENT | 3500 KG | / / / | DIESEL |  | / / / | PM106 | MITSUBISHI FD35N | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-026 | #N/A | #N/A | SPILL RESPONSE TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | ROLL UP DOORS ON THE SIDE; 10 DOORS; 12 COMPARTMENTS |  | / / / | PM130 | STERLING M8500 | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-027 | #N/A | #N/A | FORKLIFT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3305 W: 1460 H: 2400 | 7160 |  | INTERMITTENT | 5000 KG | / / / | DIESEL |  | / / / | PM106 | CAT DP50K | 2013
|  | 0 | 502-2000 |  | 2143 | 2143-MO-028 | #N/A | #N/A | FORKLIFT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 2000 W: 1100 H: 2040 | 3330 |  | INTERMITTENT | 3880 KG | / / / | ELECTRIC |  | / / / | PM106 | CAT 2ET4000 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-001 | #N/A | #N/A | WATER TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 4000 GAL | / / / | TANDEM AXLE; INSULATED STAINLESS STEEL TANK; 3" PUMP |  | H349000-4720-05-030-0001/H349000-2720-05-030-0001 / / | PM101 | PETERBILT 348 AUTO S/S 100 BBL | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-002 | #N/A | #N/A | CONTAINER HANDLER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 11684 W: 3454 H: 2146 | 72000 |  | INTERMITTENT | 50 TON CAPACITY | / / / | CAPABLE OF 20' & 40' ISO CONTAINERS |  | / / / | PM101 | KALMAR DRF 450-6555 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-003 | #N/A | #N/A | PASSENGER TRANSFER BUS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2440 H: 2900 | 14000 |  | INTERMITTENT | 48 PASSENGER; 2 WHEEL DRIVE | / / / |  |  | / / / | PM101 | BLUE BIRD BBCV DIESEL 3507A | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-004 | #N/A | #N/A | WORKER TRANSFER MINI BUS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7470 W: 2440 H: 1930 | 7080 |  | INTERMITTENT | 24 PASSENGER; 2 WHEEL DRIVE | / / / |  |  | / / / | PM101 | BLUE BIRD BBCV DIESEL 1910 A | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-005 | #N/A | #N/A | WATER DELIVERY TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 5400 GAL | / / / | 367 TRI-DRIVE W/ 36" SLEEPER; TRI-AXLE; INSULATED TANK; CAPABLE OF PULLING 5400 GAL PUP TRAILER |  | H349000-2720-05-030-0001 / / | PM101 | PETERBILT 367 TRI-DRIVE | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-006 | #N/A | #N/A | MILNE/MR FREIGHT HAUL TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | W/ WET KIT; HEADACHE RACK; FENDERS |  | / / / | PM135 | PETERBILT 367 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-007 | #N/A | #N/A | MILNE/MR FREIGHT HAUL TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | W/ WET KIT; HEADACHE RACK; FENDERS |  | / / / | PM135 | PETERBILT 367 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-008 | #N/A | #N/A | MILNE/MR FREIGHT HAUL TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | W/ WET KIT; HEADACHE RACK; FENDERS |  | / / / | PM135 | PETERBILT 367 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-009 | #N/A | #N/A | MILNE/MR FREIGHT HAUL HIBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2438 |  |  | INTERMITTENT | 20' AND 40' ISO CONTIANER CAPA | / / / | CAPABLE OF CARRYING 20' AND 40' ISO SEA CONTAINERS |  | / / / | PM143 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-010 | #N/A | #N/A | MILNE/MR FREIGHT HAUL HIBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2438 |  |  | INTERMITTENT | 20' AND 40' ISO CONTIANER CAPA | / / / | CAPABLE OF CARRYING 20' AND 40' ISO SEA CONTAINERS |  | / / / | PM143 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-011 | #N/A | #N/A | MILNE/MR FREIGHT HAUL HIBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2438 |  |  | INTERMITTENT | 20' AND 40' ISO CONTIANER CAPA | / / / | CAPABLE OF CARRYING 20' AND 40' ISO SEA CONTAINERS |  | / / / | PM143 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-012 | #N/A | #N/A | SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 14-17 TPH (BULK); 1000 L/MIN ( | / / / | 12 M3 CONTAINER CAPACITY; SKID MOUNTED SYSTEM |  | H349000-4720-05-030-0002/H349000-2731-05-030-0001 / / | PM132 | TEXLA | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-013 | #N/A | #N/A | GARBAGE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | CAPABLE OF 20-30 M3 GARBAGE BI | / / / | 60,000# ROLL ON-ROLL OFF HYRDAULIC TYPE |  | H349000-2540-05-030-0001 / / | PM132 | PETERBILT 365 | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-014 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-015 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-016 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-017 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-018 | #N/A | #N/A | GARBAGE BIN - SMALL | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 20 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-019 | #N/A | #N/A | GARBAGE BIN - SMALL | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 20 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 2144 | 2144-MO-025 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 2144 | 2144-MO-026 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 2144 | 2144-MO-027 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-030 | #N/A | #N/A | HEATED/REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT SEA CONTAINER; INSULATED; CAN PROVIDE HEAT TO 12 C |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-031 | #N/A | #N/A | HEATED/REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT SEA CONTAINER; INSULATED; CAN PROVIDE HEAT TO 12 C |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-032 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-033 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-034 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-035 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-036 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-037 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2144 | 2144-MO-038 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 502-2000 |  | 2340 | 2340-GE-001 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2013
|  | 0 | 502-2000 |  | 2340 | 2340-GE-002 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2014
|  | 0 | 502-2000 |  | 2340 | 2340-GE-003 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2014
|  | 0 | 502-2000 |  | 2340 | 2340-GE-004 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2014
|  | 0 | 502-2000 |  | 2340 | 2340-GE-005 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2014
|  | 0 | 502-2000 |  | 2340 | 2340-GE-006 | #N/A | #N/A | STOCKPILE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 6070 W: 2440 H: 3760 | 29440 |  | STANDBY | 3214 L FUEL TANK | / 670 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C500DR6G | 2014
|  | 0 | 502-2000 |  | 2341 | 2341-FE-003 | #N/A | #N/A | FINES STOCKPILE MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 500 TPH | / 135 hp No | NOMINAL: 375 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2341 | 2341-FE-004 | #N/A | #N/A | LUMPS STOCKPILE MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 500 TPH | / 135 hp No | NOMINAL: 375 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2341 | 2341-FE-005 | #N/A | #N/A | LUMPS STOCKPILE MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 500 TPH | / 135 hp No | NOMINAL: 375 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2341 | 2341-ST-006 | #N/A | #N/A | LUMPS STOCKPILE MOBILE STACKER | STACKER / STOCKPILE |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 662 TPH | / 25 hp No | BELT SPEED 350 FPM @ 18 DEGREES |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2341 | 2341-ST-007 | #N/A | #N/A | LUMPS STOCKPILE MOBILE STACKER | STACKER / STOCKPILE |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 662 TPH | / 25 hp No | BELT SPEED 350 FPM @ 18 DEGREES |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2341 | 2341-ST-008 | #N/A | #N/A | FINES STOCKPILE MOBILE STACKER | STACKER / STOCKPILE |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 662 TPH | / 25 hp No | BELT SPEED 350 FPM @ 18 DEGREES |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CH-015 | #N/A | #N/A | RECLAIM CONVEYOR DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 6000 TPH | / / / | NOMINAL: 4500 TPH |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-CH-026 | #N/A | #N/A | RECLAIM CONVEYOR MOBILE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-CH-027 | #N/A | #N/A | RECLAIM CONVEYOR MOBILE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-CH-028 | #N/A | #N/A | RECLAIM CONVEYOR MOBILE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-CH-029 | #N/A | #N/A | RECLAIM CONVEYOR MOBILE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-CV-001 | 1196938.584 | #REF! | RECLAIM CONVEYOR | CONVEYING |  | NEW | FINAL | SANJAY DAHIYA |  | L: 850000 W: 1524 H: 47000 VERTICAL LIFT | SEE REMARKS |  | INTERMITTENT | DESIGN: 6000 TPH | / 3090 hp No | NOMINAL: 4500 TPH; INSTALLED DRY WEIGHT = 1032700 KG; GALLERY WEIGHT = 411400 |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 |  |  | 2342 | 2342-MT-001 | 0 | #REF! | RECLAIM CONVEYOR |  | 2342-CV-001 | NEW | [6 empty] | INTERMITTENT |  | / 3090 hp / |  |  | / / / | PM002
|  | 0 | 502-2000 |  | 2342 | 2342-CV-023 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CV-024 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 25 hp No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CV-025 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 25 hp No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CV-030 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 25 hp No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CV-031 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 25 hp No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-CV-032 | #N/A | #N/A | JUMP CONVEYOR | CONVEYING | 2342-CV-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 25 hp No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-FE-002 | #N/A | #N/A | MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 2500 TPH | / 135 hp No | NOMINAL: 1800 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-FE-003 | #N/A | #N/A | MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 2500 TPH | / 135 hp No | NOMINAL: 1800 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-FE-004 | #N/A | #N/A | MOBILE FEEDER | FEEDER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 2500 TPH | / 135 hp No | NOMINAL: 1800 TPH |  | H349000-2340-05-030-0001 / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 502-2000 |  | 2342 | 2342-HP-022 | #N/A | #N/A | SAMPLER BIN | HOPPER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-SA-019 | #N/A | #N/A | ORE SAMPLER | SAMPLER |  | NEW | FINAL | SANJAY DAHIYA |  | L: N/A W: N/A H: N/A |  |  | INTERMITTENT |  | / 33 hp No | WEIGHTS AND DIMENSIONS TO BE AVAILABLE DURING DETAILED ENGINEERING |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2342 | 2342-SC-018 | #N/A | #N/A | BELT SCALE | SCREEN |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 6000 TPH | / / No | NOMINAL: 4500 TPH |  | H349000-2340-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-003 | 0 | #REF! | SHIPLOADER PROPORTIONAL GATE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 6000 TPH | / / / | NOMINAL: 4500 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-004 | 0 | #REF! | SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 3500 TPH | / / / | NOMINAL: 2250 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-005 | 0 | #REF! | SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 3500 TPH | / / / | NOMINAL: 2250 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-006 | 0 | #REF! | SHIPLOADER DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 3500 TPH | / / / | NOMINAL: 2250 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-008 | 0 | #REF! | SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 3500 TPH | / / / | NOMINAL: 2250 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CH-009 | 0 | #REF! | SHIPLOADER DISCHARGE CHUTE | CHUTE / DIVERTER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | DESIGN: 3500 TPH | / / / | NOMINAL: 2250 TPH |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 | 502-2000 |  | 2351 | 2351-CV-007 | 0 | #REF! | SHIPLOADER LINK CONVEYOR | CONVEYING |  | NEW | FINAL | SANJAY DAHIYA |  |  | 212330 |  | INTERMITTENT | DESIGN: 3500 TPH | / 161.53 hp No | NOMINAL: 2250 TPH; WEIGHT INCLUDES CONVEYOR + TRUSS STRUCTURE + MIDDLE COLUMN + DIVIDER CHUTE |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 |  |  | 2351 | 2351-MT-007A | 0 | #REF! | SHIPLOADER LINK CONVEYOR DRIVE |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 125 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007B | 0 | #REF! | SHIPLOADER LINK CONVEYOR BRAKE |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007C | 0 | #REF! | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 3.65 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007D | 0 | #REF! | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 14.8 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007E | 0 | #REF! | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 5.4 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007F | 0 | #REF! | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-007G | 0 | #REF! | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH |  | 2351-CV-007 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 | 502-2000 |  | 2351 | 2351-SL-001 | 0 | #REF! | SHIPLOADER | SHIPLOADER |  | NEW | FINAL | SANJAY DAHIYA |  |  | 1960000 |  | INTERMITTENT | 29M MAX RADIUS; 6000 TPH DESIG | / 645.24 hp No |  |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 |  |  | 2351 | 2351-MT-001A | 0 | #REF! | SHIPLOADER BOOM CONVEYOR DRIVE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 90 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001AA | 0 | #REF! | SPOT |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 7 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001AB | 0 | #REF! | FEEDER CABIN |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 84 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001B | 0 | #REF! | SHIPLOADER BOOM CONVEYOR BRAKE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001C | 0 | #REF! | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 60 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001D | 0 | #REF! | SHIPLOADER SLEWING DRIVE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 12 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001E | 0 | #REF! | SHIPLOADER SLEWING DRIVE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 12 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001F | 0 | #REF! | SHIPLOADER SLEWING DRIVE BRAKE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001G | 0 | #REF! | SHIPLOADER SLEWING DRIVE BRAKE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001H | 0 | #REF! | SHIPLOADER SLEWING DRIVE TRIMMING SPOON |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 1.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001J | 0 | #REF! | SHIPLOADER LUFFING DRIVE TRIMMING SPOON |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 5.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001K | 0 | #REF! | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 48.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001L | 0 | #REF! | SHIPLOADER SHUTTLE DRIVE FAN |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001M | 0 | #REF! | SHIPLOADER CENTRAL LUBE SYSTEM |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001N | 0 | #REF! | SHIPLOADER PINION LUBE SYSTEM |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001P | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM FAN |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 5.4 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001Q | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 8.8 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001R | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM FAN |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 20.3 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001S | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 8.8 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001T | 0 | #REF! | SHIPLOADER MAINTENANCE WINCH |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001U | 0 | #REF! | SHIPLOADER MAINTENANCE WINCH |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001V | 0 | #REF! | AIR CONDITIONER E-HOUSE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 60 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001W | 0 | #REF! | HEATER E-HOUSE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 54 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001X | 0 | #REF! | DUST COLLECTOR E-HOUSE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 40 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001Y | 0 | #REF! | WELDING RECEPTACLE |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 80 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-001Z | 0 | #REF! | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR |  | 2351-SL-001 | NEW | [6 empty] | INTERMITTENT |  | / 27 hp / |  |  | / / / | PM002
|  | 0 | 502-2000 |  | 2351 | 2351-SL-002 | 0 | #REF! | SHIPLOADER | SHIPLOADER |  | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT | 29M MAX RADIUS; 6000 TPH DESIG | / 1557.64 hp No |  |  | H349000-2350-05-030-0001 / / | PM002 | FAM | 2014
|  | 0 |  |  | 2351 | 2351-MT-002A | 0 | #REF! | SHIPLOADER BOOM CONVEYOR DRIVE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 150 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002AA | 0 | #REF! | SPOT |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 7 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002AB | 0 | #REF! | FEEDER CABIN |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 940 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002B | 0 | #REF! | SHIPLOADER BOOM CONVEYOR BRAKE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002C | 0 | #REF! | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 60 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002D | 0 | #REF! | SHIPLOADER SLEWING DRIVE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 10.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002E | 0 | #REF! | SHIPLOADER SLEWING DRIVE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 10.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002F | 0 | #REF! | SHIPLOADER SLEWING DRIVE BRAKE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002G | 0 | #REF! | SHIPLOADER SLEWING DRIVE BRAKE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.68 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002H | 0 | #REF! | SHIPLOADER SLEWING DRIVE TRIMMING SPOON |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 1.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002J | 0 | #REF! | SHIPLOADER LUFFING DRIVE TRIMMING SPOON |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 5.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002K | 0 | #REF! | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 48.2 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002L | 0 | #REF! | SHIPLOADER SHUTTLE DRIVE BRAKE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002M | 0 | #REF! | SHIPLOADER CENTRAL LUBE SYSTEM |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002N | 0 | #REF! | SHIPLOADER PINION LUBE SYSTEM |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002P | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM FAN |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 5.4 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002Q | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 8.8 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002R | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM FAN |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 20.3 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002S | 0 | #REF! | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 8.8 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002T | 0 | #REF! | SHIPLOADER MAINTENANCE WINCH |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002U | 0 | #REF! | SHIPLOADER MAINTENANCE WINCH |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 6 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002V | 0 | #REF! | AIR CONDITIONER E-HOUSE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 60 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002W | 0 | #REF! | HEATER E-HOUSE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 54 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002X | 0 | #REF! | DUST COLLECTOR E-HOUSE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 40 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002Y | 0 | #REF! | WELDING RECEPTACLE |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 80 hp / |  |  | / / / | PM002
|  | 0 |  |  | 2351 | 2351-MT-002Z | 0 | #REF! | HEATER/ILLUMINATION OUTDOOR/INDOOR SWITCH GEAR |  | 2351-SL-002 | NEW | [6 empty] | INTERMITTENT |  | / 27 hp / |  |  | / / / | PM002
|  | 0 | 502-2000 |  | 2510 | 2510-PP-001 | #N/A | #N/A | RAW SEWAGE LIFT STATION | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-030-0002 / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-MO-001 | #N/A | #N/A | AMBULANCE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 5715 W: 1752 H: 2032 | 6350 |  | INTERMITTENT |  | / / / | WHEELED COACH TYPE 1, 4X4; 7.3L POWER STROKE |  | / / / | PM101 | FORD F350 | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-MO-002 | #N/A | #N/A | FIRE TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10540 W: 3100 H: 3810 | 16500 |  | INTERMITTENT | 1500 GAL WATER TANK | / / / | 210 GAL FOAM TANK; 450 LB DRY CHEMICAL TANK; ARFF WITH SNOZZLE |  | / / / | PM101 | OSHKOSH T1500 | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-PP-005 | #N/A | #N/A | EMERGENCY RESPONSE OFFICE RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | H349000-2720-05-030-0003 / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 2513 | 2513-MT-005 | #N/A | #N/A | RAW WATER TANK PUMP |  | 2513-PP-005 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 502-2000 |  | 2513 | 2513-PP-021 | #N/A | #N/A | MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2513 | 2513-MT-021 | #N/A | #N/A | FUEL OIL PUMP |  | 2513-PP-021 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2513 | 2513-PP-022 | #N/A | #N/A | MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2513 | 2513-MT-022 | #N/A | #N/A | FUEL OIL PUMP |  | 2513-PP-022 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2513 | 2513-SQ-010 | #N/A | #N/A | DRY CHEMICAL REFILL STATION | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No | DRY POWDER CHEMICAL HANDLING SYSTEM |  | / / / | PM104 | TYCO FIRE PROTECTION | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-TK-003 | 6641.96 | #REF! | EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | H349000-2720-05-030-0003 / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-TK-004 | 1929.6717 | #REF! | EMERGENCY RESPONSE OFFICE RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | FREESTANDING WATER TANK |  | H349000-2720-05-030-0003 / / | PX001 | NORWESCO | 2013
|  | 0 | 502-2000 |  | 2513 | 2513-TK-023 | 3320.98 | #REF! | MILNE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 502-2000 |  | 2521 | 2521-PP-003 | #N/A | #N/A | MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2521 | 2521-MT-003 | #N/A | #N/A | FUEL OIL PUMP |  | 2521-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2521 | 2521-PP-004 | #N/A | #N/A | MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2521 | 2521-MT-004 | #N/A | #N/A | FUEL OIL PUMP |  | 2521-PP-004 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2521 | 2521-PP-011 | #N/A | #N/A | MILNE WELDING SHOP FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2521 | 2521-MT-011 | #N/A | #N/A | FUEL OIL PUMP |  | 2521-PP-011 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2521 | 2521-PP-012 | #N/A | #N/A | MILNE WELDING SHOP FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2521 | 2521-MT-012 | #N/A | #N/A | FUEL OIL PUMP |  | 2521-PP-012 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2521 | 2521-PP-051 | #N/A | #N/A | WORKSHOP OFFICE WASHCAR RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | H349000-2720-05-030-0003 / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 2521 | 2521-MT-051 | #N/A | #N/A | RAW WATER TANK PUMP |  | 2521-PP-051 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 502-2000 |  | 2521 | 2521-TK-005 | 3320.98 | #REF! | MILNE WELDING SHOP DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 502-2000 |  | 2521 | 2521-TK-013 | 3320.98 | #REF! | MAINTENANCE BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 20000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 502-2000 |  | 2521 | 2521-TK-050 | 1929.6717 | #REF! | WORKSHOP OFFICE WASHCAR RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | H349000-2720-05-030-0003 / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 502-2000 |  | 2521 | 2521-TK-053 | 6641.96 | #REF! | WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | H349000-2720-05-030-0003 / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-001 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-003 | #N/A | #N/A | DRILL PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 508 W: 356 H: 1778 | 120 |  | INTERMITTENT | CHUCK CAPACITY 15.9 MM | / 2.7 hp No | LENGTH AND WIDTH ARE TABLE DIMENSIONS; 22" WITH LASER |  | / / / | PM104 | AG - DPE18-900 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-004 | 0 | #REF! | MAGNETIC BASE DRILL | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 33 |  | INTERMITTENT | 1650 LBS DRILL POINT PRESSURE | / 0.81 hp No | 1/2 " CHUCK SIZE |  | / / / | PM104 | AG - MTL4210-1 | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-005 | #N/A | #N/A | OIL FILTER PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1524 W: 914 H: 2640 | 680 |  | INTERMITTENT | 32 TON CRUSHING FORCE | / 3.4 hp No | 57 SECOND CYCLE TIME |  | / / / | PM104 | OBERG P300 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-006 | #N/A | #N/A | HYDRAULIC PORTA POWER PUMP | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-009 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-010 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-011 | 0 | #REF! | PORTABLE WELDING FUME EXTRACTOR | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 73 |  | INTERMITTENT | 35 M2 FILTER AREA | / 1 hp No |  |  | / / / | PM104 | AG - NED12634345 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-012 | #N/A | #N/A | PORTABLE WELDING SPARK PROTECTOR | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - NED12375241 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-014 | #N/A | #N/A | SWEEPER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 4.7 hp No | ELECTRIC - AREA 20000 FT2 |  | / / / | PM104 | AG | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-018 | #N/A | #N/A | TIRE CHANGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 2.03 hp No | RIM DIAMATERS: EXTERNAL 9"-30", INTERNAL DIAMETER 11"-32" |  | / / / | PM104 | COATS APX80A | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-022 | #N/A | #N/A | BULK FLUID DISTRIBUTION SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No | OILS, LUBRICANT, COOLANT, GREASE,WATER (WASHDOWN) |  | / / / | PM104 | AG | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-023 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-025 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-026 | 0 | #REF! | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-027 | 0 | #REF! | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-028 | #N/A | #N/A | TIRE SPREADER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT | MAX TIRE: 18R-22.5" | / 2.7 hp No | AIR POWERED WITH LYING BASE. 220V MAX. 18R/22.5 INCH |  | / / / | PM104 | ZHUHAI TEAMROC TR-S825 | 2013
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-029 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 2522 | 2522-MT-029 | #N/A | #N/A | BENCH GRINDER |  | 2522-SQ-029 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-030 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 2522 | 2522-MT-030 | #N/A | #N/A | BENCH GRINDER |  | 2522-SQ-030 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-033 | #N/A | #N/A | TRUCK MOUNT GOODALL BOOST SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-034 | #N/A | #N/A | GOODALL BOOST SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-037 | #N/A | #N/A | A/C RECOVERY RECHARGE UNIT | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 584 W: 864 H: 1120 | 110 |  | INTERMITTENT | MAX TANK SIZE 30 LBS | / / No | MULTI-REFRIGERANT |  | / / / | PM104 | ROBINAIR RBN17800B | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-038 | #N/A | #N/A | BATTERY CHARGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - WSW1JYU3 | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-039 | #N/A | #N/A | BATTERY CHARGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - WSW1JYU3 | 2014
|  | 0 | 502-2000 |  | 2522 | 2522-SQ-040 | #N/A | #N/A | TUBE BENDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 502-2000 |  | 2540 | 2540-PP-002 | #N/A | #N/A | MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2540 | 2540-MT-002 | #N/A | #N/A | FUEL OIL PUMP |  | 2540-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2540 | 2540-PP-003 | #N/A | #N/A | MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2540 | 2540-MT-003 | #N/A | #N/A | FUEL OIL PUMP |  | 2540-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2540 | 2540-SQ-002 | 0 | #REF! | AEROSOL CAN RECYCLING SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 5 |  | INTERMITTENT | CAPABLE OF 76, 114, AND 208 L | / / No |  |  | / / / | PM104 | AG - SAYCPU03 | 2013
|  | 0 | 502-2000 |  | 2540 | 2540-SQ-003 | #N/A | #N/A | DRUM CRUSHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 650 |  | INTERMITTENT | 38000 LBS OF CRUSHING PRESSURE | / 6.8 hp No | CRUSHES 55 GAL DRUMS TO 6" HIGH; RESETS IN 25 SECONDS |  | / / / | PM104 | AG - VESHDC900IDC | 2013
|  | 0 | 502-2000 |  | 2540 | 2540-SQ-004 | #N/A | #N/A | PLATFORM SCALE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT | 10 TON | / / No | 10 TON |  | / / / | PM104 | AG - OHAVX32XW10000X | 2014
|  | 0 | 502-2000 |  | 2540 | 2540-TK-003 | 3320.98 | #REF! | MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 20000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 502-2000 |  | 2540 | 2540-VP-001 | 8954.42 | #REF! | WASTE INCINERATOR VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | - |  | / / / |  |  | H349000-2540-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2610 | 2610-PP-001 | #N/A | #N/A | OIL WATER SEPARATOR FEED PUMP | PUMP |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM005 |  | 2013
|  | 0 | 502-2000 |  | 2610 | 2610-PP-002 | #N/A | #N/A | OIL WATER SEPARATOR FEED PUMP | PUMP |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM005 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-FD-013 | 1925.0833 | #REF! | EXISTING DIESEL FUEL DISPENSING MODULE | FUEL DISPENSER |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-FD-014 | 3850.1667 | #REF! | DIESEL FUEL DISPENSING MODULE | FUEL DISPENSER |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-PP-007 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.1 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-PP-008 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.2 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-PP-009 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.3 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-PP-010 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.4 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-PP-011 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.5 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-PP-012 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.6 | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2613 | 2613-TK-001 | 154284.602 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 27800 DI H: 15250 |  |  | CONTINUOUS | 10 ML | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-TK-002 | 154284.602 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 27800 DI H: 15250 |  |  | CONTINUOUS | 10 ML | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-TK-003 | 154284.602 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 27800 DI H: 15250 |  |  | CONTINUOUS | 10 ML | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-TK-004 | 154284.602 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 27800 DI H: 15250 |  |  | CONTINUOUS | 10 ML | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2613 | 2613-TK-005 | 95690.074 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 25600 DI H: 9760 |  |  | CONTINUOUS | 5 ML | / / / |  |  | / / / | PM004
|  | 0 | 502-2000 |  | 2613 | 2613-TK-006 | 95690.074 | #REF! | ARCTIC DIESEL TANK | TANK |  | EXISTING | EXISTING | FLOYD BUTTS |  | W: 25600 DI H: 9760 |  |  | CONTINUOUS | 5 ML | / / / |  |  | / / / | PM004
|  | 0 | 502-2000 |  | 2614 | 2614-FD-011 | 1925.0833 | #REF! | JET-A1 FUEL DISPENSING MODULE | FUEL DISPENSER |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2614 | 2614-FS-003 | #N/A | #N/A | JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | FIRE SERVICES |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2614 | 2614-FS-004 | #N/A | #N/A | JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | FIRE SERVICES |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2614 | 2614-PP-001 | #N/A | #N/A | JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2614 | 2614-PP-002 | #N/A | #N/A | JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2614 | 2614-TK-007 | 14541.2424 | #REF! | JET-A1 TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 10250 DI H: 9140 |  |  | CONTINUOUS | 750 kL | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2614 | 2614-TK-008 | 14541.2424 | #REF! | JET-A1 TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 10250 DI H: 9140 |  |  | CONTINUOUS | 750 kL | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 502-2000 |  | 2614 | 2614-TK-009 | 14541.2424 | #REF! | JET-A1 TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 10250 DI H: 9140 |  |  | CONTINUOUS | 750 kL | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2614 | 2614-TK-010 | 14541.2424 | #REF! | JET-A1 TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 10250 DI H: 9140 |  |  | CONTINUOUS | 750 kL | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 502-2000 |  | 2619 | 2619-GE-001 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 502-2000 |  | 2619 | 2619-GE-002 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 502-2000 |  | 2619 | 2619-GE-003 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 502-2000 |  | 2619 | 2619-GE-004 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 502-2000 |  | 2619 | 2619-GE-005 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 502-2000 |  | 2619 | 2619-GE-006 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2014
|  | 0 | 502-2000 |  | 2619 | 2619-GE-007 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2014
|  | 0 | 502-2000 |  | 2720 | 2720-PP-002 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / No |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-003 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | STANDBY |  | / / No |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-004 | #N/A | #N/A | DIESEL FIRE WATER PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-005 | #N/A | #N/A | ELECTRIC FIRE WATER PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | STANDBY |  | / / No |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-006 | #N/A | #N/A | JOCKEY PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | STANDBY |  | / / No |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-009 | #N/A | #N/A | POTABLE WATER DISCHARGE PUMP NO.1 | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-010 | #N/A | #N/A | POTABLE WATER DISCHARGE PUMP NO.2 | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-012 | #N/A | #N/A | BACKWASH SLURRY PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-013 | #N/A | #N/A | CLEAN BACKWASH PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-2720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-021 | #N/A | #N/A | RAW WATER UNLOADING PUMP | PUMP |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | CONTINUOUS |  | / / No | 3" x 3" |  | / / / | PM010 | HAYWARD GORDON S-3 | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-PP-031 | #N/A | #N/A | MILNE WATER BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2720 | 2720-MT-031 | #N/A | #N/A | FUEL OIL PUMP |  | 2720-PP-031 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2720 | 2720-PP-032 | #N/A | #N/A | MILNE WATER BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2720 | 2720-MT-032 | #N/A | #N/A | FUEL OIL PUMP |  | 2720-PP-032 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2720 | 2720-TK-001 | 6641.96 | #REF! | RAW WATER TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / / |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-TK-007 | 6641.96 | #REF! | FIRE WATER TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / / |  |  | H349000-2720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-TK-008 | 6641.96 | #REF! | POTABLE WATER STORAGE TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / / |  |  | H349000-2720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-TK-011 | 6641.96 | #REF! | BACKWASH SETTLING TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-2720-05-0002 / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-TK-033 | 3320.98 | #REF! | MILNE WATER BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 502-2000 |  | 2720 | 2720-VP-020 | 8954.42 | #REF! | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | - |  | / / / |  |  | / / / | TX001 |  | 2013
|  | 0 | 502-2000 |  | 2731 | 2731-PP-003 | #N/A | #N/A | TREATED EFFLUENT DISCHARGE PUMP NO.1 | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2731 | 2731-PP-004 | #N/A | #N/A | TREATED EFFLUENT DISCHARGE PUMP NO.2 | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2731 | 2731-SC-001 | #N/A | #N/A | SCREEN | SCREEN |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2731 | 2731-TK-002 | #N/A | #N/A | TREATED EFFLUENT TANK | TANK |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2731 | 2731-VP-005 | 23101 | #REF! | SEWAGE TREATMENT PLANT VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | - |  | / / / |  |  | / / / | PM009 |  | 2013
|  | 0 | 502-2000 |  | 2732 | 2732-PP-001 | #N/A | #N/A | MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2732 | 2732-MT-001 | #N/A | #N/A | FUEL OIL PUMP |  | 2732-PP-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2732 | 2732-PP-002 | #N/A | #N/A | MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 2732 | 2732-MT-002 | #N/A | #N/A | FUEL OIL PUMP |  | 2732-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 502-2000 |  | 2732 | 2732-TK-003 | 3320.98 | #REF! | MILNE SEWAGE TRUCK BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-005 | #N/A | #N/A | MOBILE CRUSHER FRONT-END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | HIGH LIFT SPEC. - TO BE DELIVERED BY JULY 5TH W/ STANDARD BUCKETS |  | H349000-4380-05-030-0001 / / | PM102 | CAT 988H | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-006 | #N/A | #N/A | MOBILE CRUSHER FRONT-END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | HIGH LIFT SPEC. - TO BE DELIVERED BY JULY 5TH W/ STANDARD BUCKETS |  | H349000-4380-05-030-0001 / / | PM102 | CAT 988H | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-007 | #N/A | #N/A | MINE HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10445 W: 6706 H: 5840 | 75200 |  | INTERMITTENT | RATED PAYLOAD 90 TON | / / / | ETA JULY 15, 2013 |  | H349000-4380-05-030-0001 / / | PM102 | CAT 777G | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-008 | #N/A | #N/A | MINE HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10445 W: 6706 H: 5840 | 75200 |  | INTERMITTENT | RATED PAYLOAD 90 TON | / / / | ETA JULY 18, 2013 |  | H349000-4380-05-030-0001 / / | PM102 | CAT 777G | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-009 | #N/A | #N/A | MINE HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10445 W: 6706 H: 5840 | 75200 |  | INTERMITTENT | RATED PAYLOAD 90 TON | / / / | ETA JULY 12, 2013 |  | H349000-4380-05-030-0001 / / | PM102 | CAT 777G | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-010 | #N/A | #N/A | MINE HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10445 W: 6706 H: 5840 | 75200 |  | INTERMITTENT | RATED PAYLOAD 90 TON | / / / |  |  | H349000-4380-05-030-0001 / / | PM102 | CAT 777G | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-024 | #N/A | #N/A | MINE SITE LARGE EXCAVATOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 13470 W: 3500 H: 4782 | 85000 |  | INTERMITTENT | 530 HP, 5.4 M3 BUCKET | / / / | MASS HEX, IRON ORE BUCKET - ETA JULY 19, 2013 |  | H349000-4380-05-030-0001 / / | PM102 | CAT 390DL | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-025 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-026 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-027 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-028 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-029 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-030 | #N/A | #N/A | SINGLE PASS PRODUCTION DRILL | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  |  | 56800 |  | INTERMITTENT |  | / / / | ETA SEPT. 10TH |  | / / / | PM100 | CAT MD6290 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-031 | #N/A | #N/A | SINGLE PASS PRODUCTION DRILL | MOBILE EQUIPMENT |  | NEW | PRELIMINARY | TOROMONT |  | L: 14280 W: 4010 H: 4590 | 56800 |  | INTERMITTENT |  | / / / | 2014 SEALIFT |  | / / / | PM100 | CAT MD6290 | 2014
|  | 0 | 504-2200 |  | 4141 | 4141-MO-033 | #N/A | #N/A | SECONDARY DRILL | MOBILE EQUIPMENT |  | USED | PRELIMINARY | GLACIER |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM100 | TAMROCK 800 | 2013
|  | 0 | 504-2200 |  | 4141 | 4141-MO-035 | #N/A | #N/A | DRILL DUST SUPPRESSION WATER/METHANOL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | NON-INSULATED |  | / / / | PM130 | KENWORTH T800H | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-001A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-001B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-001C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-002A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-002B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-002C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-003A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-003B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-003C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-004A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-004B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-004C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-005A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-005B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-005C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-006A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-006B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-006C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-007A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-007B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-007C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-008A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-008B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-008C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-009A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-009B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-009C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-010A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-010B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-010C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-011A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-011B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-011C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-012A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-012B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-012C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-013A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-013B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-013C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-014A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-014B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-014C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-015A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-015B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-015C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-016A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-016B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-016C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-017A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-017B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-017C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-018A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-018B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-018C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-019A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-019B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-019C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-020A | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10080 W: 3060 H: 3900 | 11400 / |  | INTERMITTENT | 600 HP, 150T (2 75T) | / / / | 6 WHEEL DRIVE, PLANETARY GEAR, 3" PIN |  | H349000-4380-05-030-0001 / / | PM103 | WESTERN STAR 6900XD | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-020B | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-020C | #N/A | #N/A | TOTE ROAD ORE HAUL TRUCK - PUP TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10240 W: 3060 H: 4210 | 34500 |  | INTERMITTENT | 75 T | / / / | DOUBLE TRAIN SIDE DUMP. |  | H349000-4380-05-030-0001 / / | PM113 | SMITHCO S4 (75T) | 2014
|  | 0 | 504-2200 |  | 4142 | 4142-MO-021 | #N/A | #N/A | MINE SITE TRACK DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6630 W: 4310 H: 3815 | 42700 |  | INTERMITTENT | BLADE WIDTH 4310 MM | / / / | ETA JULY 18, 2013 |  | / / / | PM102 | CAT D9T | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-022 | #N/A | #N/A | MINE SITE TRACK DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6630 W: 4310 H: 3815 | 78000 |  | INTERMITTENT | BLADE WIDTH 4310 MM | / / / |  |  | / / / | PM102 | CAT D9T | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-023 | #N/A | #N/A | MINE SITE WHEEL DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 8716 W: 3556 H: 4102 | 46300 |  | INTERMITTENT | BLADE W x H: 4.6M x 1.5M | / / / | SEMI U BLADE |  | / / / | PM102 | CAT 824H | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-024 | #N/A | #N/A | GRADER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 9963 W: 3096 H: 3718 | 30400 |  | INTERMITTENT | 2.6 M MAX SHOULDER REACH | / / / | MADE IN 2002; SECONDARY STEER, RIPPER, HIGH CAB - NO WING - ETA JULY 12, 2013 |  | / / / | PM102 | CAT 16H | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-026 | #N/A | #N/A | PRODUCTION FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 16877 W: 6000 H: 7000 | 100000 |  | INTERMITTENT | 14 - 36 M3 BUCKET | / / / | ETA JULY 25, 2013 - IRON ORE BUCKET DELIVERY IN SEPT. |  | H349000-4380-05-030-0001 / / | PM102 | CAT 992K | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-027 | #N/A | #N/A | PRODUCTION LARGE EXCAVATOR | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 13470 W: 3500 H: 4782 | 85000 |  | INTERMITTENT | 530 HP, 5.4 M3 BUCKET | / / / | MASS HEX, IRON ORE BUCKET |  | H349000-4380-05-030-0001 / / | PM102 | CAT 390DL | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-028 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-029 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-030 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-031 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-032 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-033 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-034 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-035 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-036 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4142 | 4142-MO-037 | #N/A | #N/A | NIGHT WORK AREA LIGHT PLANTS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / 10.8 hp No | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-001 | #N/A | #N/A | MAINTENANCE SERVICE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 7000 LB TELESCOPING CRANE; 11 | / / / | VMAC CRANE |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-002 | #N/A | #N/A | MAINTENANCE SERVICE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | 10000# TELESCOPIC CRANE; AIR COMPRESSOR |  | / / / | PM130 | PETERBILT 348 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-003 | #N/A | #N/A | MAINTENANCE FUEL/LUBE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 1000 GAL FUEL TANK; 7 PRODUCT | / / / | 1000 GAL FUEL TANK; 7 PRODUCT TANKS; HEATED PRESSURIZED HOUSE |  | H349000-4540-05-030-0001 / / | PM130 | KENWORTH T800 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-004 | #N/A | #N/A | LOWBED TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | W/ WET KIT; HEADACHE RACK; FENDERS |  | / / / | PM135 | PETERBILT 367 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-005 | #N/A | #N/A | LOWBED TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | W/ WET KIT; HEADACHE RACK; FENDERS |  | / / / | PM135 | PETERBILT 367 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-006 | #N/A | #N/A | TIRE HANDLER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  |  | 5900 |  | INTERMITTENT | 20000 LBS | / / / | TO FIT ON CAT 988H LOADER - ESTIMATED DELIVERY AUG 25, 2013 |  | / / / | PM102 | WBM T20P-S | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-008 | #N/A | #N/A | FREIGHT HANDLING FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6050 W: 2390 H: 3150 | 9600 |  | INTERMITTENT | 1.3 M3 BUCKET | / / / | QUICK COUPLERS/BUCKETS/FORKS |  | / / / | PM102 | CAT 930K | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-009 | #N/A | #N/A | YARD WORK EXCAVATOR | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 11910 W: 3490 H: 3770 | 45000 |  | INTERMITTENT | 345 HP, 3.5 M3 BUCKET | / / / |  |  | / / / | PM102 | CAT 345DL | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-010 | #N/A | #N/A | CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3277 W: 1676 H: 3810 | 3175 |  | INTERMITTENT | 885 KG OPERATING LOAD | / / / | C/W QUICK COUPLER, BUCKET AND FORKS |  | / / / | PM102 | CAT 247B | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-011 | #N/A | #N/A | CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3277 W: 1676 H: 3810 | 3175 |  | INTERMITTENT | 885 KG OPERATING LOAD | / / / | C/W QUICK COUPLER, BUCKET AND FORKS |  | / / / | PM102 | CAT 247B | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-013 | #N/A | #N/A | CRUSHER MAINTENANCE KNUCKLE CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 9000 KG | / / / | TANDEM AXLE; STEEL DECK; PALFINGER PK32080 KNUCKLE CRANE |  | / / / | PM116 | KENWORTH T800 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-014 | #N/A | #N/A | MAINTENANCE CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 14630 W: 7920 H: 3990 | 42000 |  | INTERMITTENT | 80 T | / / / | HYDRAULICS, ROUGH TERRAIN |  | / / / | PM101 | TEREX RT780 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-015 | #N/A | #N/A | MAINTENANCE CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 15240 W: 7920 H: 3970 | 60500 |  | INTERMITTENT | 130 T | / / / | HYDRAULICS, ROUGH TERRAIN |  | / / / | PM101 | TEREX RT130 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-016 | #N/A | #N/A | WAREHOUSE FORK LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 2790 W: 1290 H: 2500 | 4763 |  | INTERMITTENT | 3 T | / / / | DIESEL ENGINE W/ SCRUBBER |  | / / / | PM106 | CAT P7000-D | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-017 | #N/A | #N/A | MAINTENANCE FORK LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 4240 W: 2390 H: 2845 | 14320 |  | INTERMITTENT | 10 T | / / / | DIESEL ENGINE W/ SCRUBBER, 96" FORKS |  | / / / | PM106 | CAT P20000 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-018 | #N/A | #N/A | FREIGHT TELEHANDLER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 6100 W: 2570 H: 2570 | 15800 | NUNA | INTERMITTENT | 4500 KG CAPACITY | / / / |  |  | / / / | PM106 | CAT TH514 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-019 | #N/A | #N/A | RUN-OFF CONTROL DEWATERING PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  |  |  |  | INTERMITTENT | 6" | / / / | DIESEL W/ TRAILER AND SPILL KIT |  | / / / | PM106 | GORMAN RUPP T6A60S-C4.4T | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-020 | #N/A | #N/A | RUN-OFF CONTROL DEWATERING PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  |  |  |  | INTERMITTENT | 6" | / / / | DIESEL W/ TRAILER AND SPILL KIT |  | / / / | PM106 | GORMAN RUPP T6A60S-C4.4T | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-021 | #N/A | #N/A | MAINTENANCE HOT BOX | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  | L: 4877 W: 2235 H: 1829 | 1850 |  | INTERMITTENT | 1100000 BTU/H | / / / |  |  | / / / | PM104 | ECOBLAZE CUBE 1100 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-022 | #N/A | #N/A | MAINTENANCE HOT BOX | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  | L: 4877 W: 2235 H: 1829 | 1850 |  | INTERMITTENT | 1100000 BTU/H | / / / |  |  | / / / | PM104 | ECOBLAZE CUBE 1100 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-023 | #N/A | #N/A | MAINTENANCE HOT BOX | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  | L: 4877 W: 2235 H: 1829 | 1850 |  | INTERMITTENT | 1100000 BTU/H | / / / |  |  | / / / | PM104 | ECOBLAZE CUBE 1100 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-024 | #N/A | #N/A | YARD MAINTENANCE PLOW/SAND TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | TENCO CHASSIS MOUNT SPREADER; ONE WAY PLOW; RIGHT HAND SIDE DISCHARGE |  | / / / | PM131 | INTERNATIONAL 7600 | 2013
|  | 0 | 507-3200 |  | 4143 | 4143-MO-025 | #N/A | #N/A | GRADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 9994 W: 3077 H: 3524 | 24400 |  | INTERMITTENT | 2.31 M MAX REACH | / / / | 2012 |  | / / / | PM102 | CAT 16M | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-026 | #N/A | #N/A | YARD/TOTE ROAD MAINTENANCE TRACK DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4064 W: 2464 H: 2439 | 21600 |  | INTERMITTENT |  | / / / |  |  | / / / | PM102 | CAT D6T XW | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-027 | #N/A | #N/A | MAINTENANCE TRAILER WELDER | MOBILE EQUIPMENT |  | NEW | PRELIMINARY | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM104 |  | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-029 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 2500 W: 1170 H: 1970 | 6010 |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | JLG450AJ | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-030 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-031 | #N/A | #N/A | ORE HAUL TRUCK RECOVERY TOW TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 55T | / / / | WITH JERR DAN 110/530 WRECKER |  | / / / | PM133 | KENWORTH T800 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-032 | #N/A | #N/A | TOTE ROAD CULVERT MAINTENANCE STEAM TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | (2) 600 GAL TANKS | / / / |  |  | / / / | PM101 | PETERBILT T/A STEAM TRUCK | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-033 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-034 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-035 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-036 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-037 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-038 | #N/A | #N/A | FORKLIFT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 3050 W: 1090 H: 2050 | 3500 |  | INTERMITTENT | 1800 KG | / / / | ELECTRIC |  | / / / | PM106 | MITSUBISHI FB20PNT | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-039 | #N/A | #N/A | MINI CRAWLER CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6.75T | / / / | DIESEL/ELECTRIC |  | / / / | PM116 | SPYDER CRANE URW706 | 2013
|  | 0 | 504-2200 |  | 4143 | 4143-MO-040 | #N/A | #N/A | SPILL RESPONSE TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | ROLL UP DOORS ON THE SIDE; 10 DOORS; 12 COMPARTMENTS |  | / / / | PM130 | STERLING M8500 | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-001 | #N/A | #N/A | WATER TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 4000 GAL | / / / | TANDEM AXLE; INSULATED STAINLESS STEEL TANK; 3" PUMP |  | / / / | PM101 | PETERBILT 348 AUTO S/S 100 BBL | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-002 | #N/A | #N/A | CONTAINER HANDLER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 11684 W: 3454 H: 2146 | 72000 |  | INTERMITTENT | 50 TON CAPACITY | / / / | CAPABLE OF 20' & 40' ISO CONTAINERS |  | / / / | PM101 | KALMAR DRF 450-6555 | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-003 | #N/A | #N/A | PASSENGER TRANSFER BUS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2440 H: 2900 | 14000 |  | INTERMITTENT | 48 PASSENGER; 2 WHEEL DRIVE | / / / |  |  | / / / | PM101 | BLUE BIRD BBCV DIESEL 3507A | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-004 | #N/A | #N/A | PASSENGER TRANSFER BUS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12192 W: 2440 H: 2900 | 14000 |  | INTERMITTENT | 48 PASSENGER; 2 WHEEL DRIVE | / / / |  |  | / / / | PM101 | BLUE BIRD BBCV DIESEL 3507A | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-005 | #N/A | #N/A | WORKER TRANSFER MINI BUS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7470 W: 2440 H: 1930 | 7080 |  | INTERMITTENT | 24 PASSENGER; 2 WHEEL DRIVE | / / / |  |  | / / / | PM101 | BLUE BIRD BBCV DIESEL 1910 A | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-006 | #N/A | #N/A | SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 12 M3 CONTAINER CAPACITY | / / / | 12 M3 CONTAINER CAPACITY; SKID MOUNTED SYSTEM |  | H349000-4731-05-030-0001/H349000-4720-05-030-0004 / / | PM132 | TEXLA | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-007 | #N/A | #N/A | FREIGHT DELIVERY HIBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 14630 W: 2438 |  |  | INTERMITTENT | 60 T | / / / |  |  | / / / | PM143 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-008 | #N/A | #N/A | DIESEL FUEL TRAILER TRACTOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 305 HP ENGINE | / / / | B-TRAIN CAPABLE CLASS 8 TRACTOR FOR WATER AND FUEL TRAILER SETS |  | / / / | PM101 | WESTERN STAR 4900FA | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-009 | #N/A | #N/A | JET-A1 FUEL DELIVERY TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 8052 W: 2960 H: 3589 |  |  | INTERMITTENT | 4400 GAL | / / / | TANDEM AXLE; 40" LOW ROOF SLEEPER; TC406 COMPLIANT TANK |  | / / / | PM101 | MACK/INNOCAR GU813 | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-010 | #N/A | #N/A | DIESEL FUEL DELIVERY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 24384 W: 2590 H: 4013 | 33500 |  | INTERMITTENT | 62 kL (33k L LEAD + 29 kL PUP) | / / / | TC406 COMPLIANT; 5 COMPARTMENTS |  | / / / | PM101 | TREMCAR TC406 SUPER B-TRAIN | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-011 | #N/A | #N/A | MOBILE EQUIPMENT LOWBOY TRAILER | MOBILE EQUIPMENT |  | NEW | PRELIMINARY | GRAHAM BURTON |  | L: 7620 W: 4572 |  |  | INTERMITTENT | 120 T | / / / | TRI-AXLE; 25 FT DECK LENGTH; 15 FT DECK WIDTH |  | / / / | PM101 | SHELTEMA | 2014
|  | 0 | 504-2200 |  | 4144 | 4144-MO-012 | #N/A | #N/A | GARBAGE TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 20-30 M3 GARBAGE BIN CAPABLE | / / / | 60,000# ROLL ON-ROLL OFF HYDRAULIC TYPE |  | H349000-4540-05-030-0001 / / | PM132 | PETERBILT 365 | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-013 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-014 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-015 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-016 | #N/A | #N/A | GARBAGE BIN - LARGE | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 30 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-017 | #N/A | #N/A | GARBAGE BIN - SMALL | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 20 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-018 | #N/A | #N/A | GARBAGE BIN - SMALL | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 20 M3 | / / / |  |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-024 | #N/A | #N/A | ARTICULATED WATER/SAND TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  |  |  |  | INTERMITTENT | 8000 GAL WATER TANK | / / / | WITH WATER CANNON AND SPRAY BARS; CYLINDERS AND TAILGATE - IN FABRICATION PROCESS - ETA AUG 1, 2013 |  | / / / | PM136 | CAT 740 | 2013
|  | 0 |  |  | 4144 | 4144-MO-025 | #N/A | #N/A | DIESEL FUEL DELIVERY TRAILER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 56000L | / / / | QUAD AXLE; ALUMINUM; 5 COMPARTMENTS |  | / / / | PM101 | ADVANCE | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-026 | #N/A | #N/A | SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 12 M3 CONTAINER CAPACITY | / / / | 12 M3 CONTAINER CAPACITY; SKID MOUNTED SYSTEM |  | H349000-4731-05-030-0001/H349000-4720-05-030-0004 / / | PM132 | TEXLA | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-030 | #N/A | #N/A | HEATED/REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT SEA CONTAINER; INSULATED; CAN PROVIDE HEAT TO 12 C |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-031 | #N/A | #N/A | HEATED/REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT SEA CONTAINER; INSULATED; CAN PROVIDE HEAT TO 12 C |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-032 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-033 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-034 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-035 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-036 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 | 504-2200 |  | 4144 | 4144-MO-037 | #N/A | #N/A | REFRIGERATED SEA CONTAINER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6096 W: 2440 H: 2440 |  |  | CONTINUOUS | 20 FOOT SEA CAN | / / / | 20 FT CONTAINER |  | / / / | PM107 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-040 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-041 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-042 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-043 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-044 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 |  |  | 4144 | 4144-MO-045 | #N/A | #N/A | WILDLIFE DETERGENT GARBAGE BIN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 6 M3 | / / / | HYDRAULIC ASSISTEDS, SELF LOCKING LIDS |  | / / / | PM132 |  | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-001 | #N/A | #N/A | PRIMARY CRUSHING PLANT LINE 1 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 3470 W: 4100 H: 3440 | 38000 |  | CONTINUOUS | 600 TPH | / 293 hp No | JAW CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO C125 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-003 | #N/A | #N/A | SECONDARY CRUSHING PLANT LINE 1 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2370 W: 2370 H: 1600 | 23000 |  | CONTINUOUS | 600 TPH | / 490 hp No | CONE CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO HP400 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-005 | #N/A | #N/A | TERTIARY CRUSHING PLANT LINE 1 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2370 W: 2370 H: 1600 | 23000 |  | CONTINUOUS | 600 TPH | / 490 hp No | CONE CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO HP400 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-006 | #N/A | #N/A | PRIMARY CRUSHING PLANT LINE 2 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 3470 W: 4100 H: 3440 | 38000 |  | CONTINUOUS | 600 TPH | / 293 hp No | JAW CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO C125 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-008 | #N/A | #N/A | SECONDARY CRUSHING PLANT LINE 2 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2370 W: 2370 H: 1600 | 23000 |  | CONTINUOUS | 600 TPH | / 490 hp No | CONE CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO HP400 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CR-010 | #N/A | #N/A | TERTIARY CRUSHING PLANT LINE 2 | CRUSHER |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2370 W: 2370 H: 1600 | 23000 |  | CONTINUOUS | 600 TPH | / 490 hp No | CONE CRUSHER |  | H349000-4380-05-030-0001 / / | PM001 | METSO HP400 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-011 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-012 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-001 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-013 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-003 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-014 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-005 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-015 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-006 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-016 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-006 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-017 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-008 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-CV-018 | #N/A | #N/A | LINK CONVEYOR | CONVEYING | 4381-CR-010 | NEW | FINAL | SANJAY DAHIYA |  |  |  |  | CONTINUOUS |  | / / No |  |  | / / / | PM001 | MASABA MINING EQUIPMENT | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-SC-002 | #N/A | #N/A | PRIMARY SCREEN LINE 1 | SCREEN |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2700 W: 6900 | 9000 |  | CONTINUOUS | 600 TPH | / 121.5 hp No |  |  | H349000-4380-05-030-0001 / / | PM001 | METSO FS302 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-SC-004 | #N/A | #N/A | SECONDARY SCREEN LINE 1 | SCREEN |  | NEW | FINAL | SANJAY DAHIYA |  | L: 3000 W: 6900 | 14500 |  | CONTINUOUS | 600 TPH | / 175 hp No |  |  | H349000-4380-05-030-0001 / / | PM001 | METSO FS 353 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-SC-007 | #N/A | #N/A | PRIMARY SCREEN LINE 2 | SCREEN |  | NEW | FINAL | SANJAY DAHIYA |  | L: 2700 W: 6900 | 9000 |  | CONTINUOUS | 600 TPH | / 121.5 hp No |  |  | H349000-4380-05-030-0001 / / | PM001 | METSO FS302 | 2013
|  | 0 | 504-2200 |  | 4381 | 4381-SC-009 | #N/A | #N/A | SECONDARY SCREEN LINE 2 | SCREEN |  | NEW | FINAL | SANJAY DAHIYA |  | L: 3000 W: 6900 | 14500 |  | CONTINUOUS | 600 TPH | / 175 hp No |  |  | H349000-4380-05-030-0001 / / | PM001 | METSO FS 353 | 2013
|  | 0 | 501-3201 |  | 4382 | 4382-SC-001 | #N/A | #N/A | TRUCK WEIGH SCALE | SCREEN |  | NEW | PRELIMINARY | KENTARO IMAI |  | L: 36600 W: 3960 H: 1030 |  |  | INTERMITTENT | 200 T | / / / | SHALLOW PIT, 5 MODULE DESIGN |  | / / / | PM115 | RICE LAKE OTR-XV | 2013
|  | 0 | 504-2200 |  | 4385 | 4385-PP-001 | #N/A | #N/A | CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP | PUMP |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | CONTINUOUS |  | / / No |  |  | H349000-4380-05-030-0001 / / | PM010 | LOBE PRO SM68 | 2013
|  | 0 | 504-2200 |  | 4385 | 4385-PP-002 | #N/A | #N/A | CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP | PUMP |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | STANDBY |  | / / No |  |  | H349000-4380-05-030-0001 / / | PM010 | LOBE PRO SM68 | 2013
|  | 0 | 504-2200 |  | 4431 | 4431-PP-002 | #N/A | #N/A | AERODROME OFFICE RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | H349000-4720-05-030-0003 / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 4431 | 4431-MT-002 | #N/A | #N/A | RAW WATER TANK PUMP |  | 4431-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 504-2200 |  | 4431 | 4431-TK-001 | 1929.6717 | #REF! | AERODROME OFFICE RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | FREESTANDING WATER TANK |  | H349000-4720-05-030-0003 / / | PX001 | NORWESCO | 2013
|  | 0 | 504-2200 |  | 4431 | 4431-TK-004 | 6641.96 | #REF! | AERODROME OFFICE SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | H349000-4720-05-030-0003 / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 504-2200 |  | 4433 | 4433-AE-001 | #N/A | #N/A | SECURITY X-RAY MACHINE | AERODROME EQUIPMENT |  | NEW | PRELIMINARY | KENTARO IMAI |  | L: 2282 W: 1030 H: 1467 |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM008 |  | 2013
|  | 0 | 504-2200 |  | 4433 | 4433-AE-015 | #N/A | #N/A | AIRCRAFT GROUND POWER UNIT | AERODROME EQUIPMENT |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 90 KVA WITH 28.5 VDC OUTPUT | / / / |  |  | / / / | PM008 |  | 2013
|  | 0 | 504-2200 |  | 4433 | 4433-AE-023 | #N/A | #N/A | AIRCRAFT PASSENGER STAIRS | AERODROME EQUIPMENT |  | NEW | PRELIMINARY | KENTARO IMAI |  | L: 9906 W: 2565 H: 3048 |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM008 |  | 2013
|  | 0 | 504-2200 |  | 4434 | 4434-MO-002 | #N/A | #N/A | AIRPORT MAINTENANCE DE-ICING TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 1800 GAL | / / / | 47 FT NOZZLE REACH HEIGHT; TYPE I AND TYPE II DE-ICE FLUID; 3 MILLION BTU (3) HEATER DESIGN |  | / / / | PM101 | FORD SUPERIOR | 2013
|  | 0 | 504-2200 |  | 4510 | 4510-PP-001 | #N/A | #N/A | RAW SEWAGE LIFT STATION | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0002 / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4511 | 4511-LE-001 | #N/A | #N/A | AIR COMPRESSOR | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 15.4 hp No | INGERSOLL RAND - IRN 10H-130 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-002 | #N/A | #N/A | AIR COMPRESSOR | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 15.4 hp No | INGERSOLL RAND - IRN 10H-130 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-003 | #N/A | #N/A | AIR DRYER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.68 hp No | INGERSOLL RAND - D108IN |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-004 | #N/A | #N/A | BALANCE SCALE | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.41 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-005 | #N/A | #N/A | BALANCE SCALE | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.41 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-006 | #N/A | #N/A | BALANCE SCALE | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.41 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-007 | #N/A | #N/A | CARBON/SULFUR ANALYSER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 5.7 hp No | LECO CS230 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-008 | #N/A | #N/A | CHILLER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 5.1 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-016 | #N/A | #N/A | CRUSHER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 12.4 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-017 | #N/A | #N/A | CRUSHER DUST HOOD | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.15 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-018 | #N/A | #N/A | DRYING OVEN | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 16.2 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-019 | #N/A | #N/A | DRYING OVEN | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.41 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-020 | #N/A | #N/A | DUST COLLECTOR | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 24 hp No | DONALDSONS - DF02-12 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-021 | #N/A | #N/A | FUMEHOOD | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.15 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-022 | #N/A | #N/A | FUSION SYSTEM | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 13.4 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-023 | #N/A | #N/A | HOT PLATE | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 6.6 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-024 | #N/A | #N/A | MUFFLE FURNACE | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 5.9 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-027 | #N/A | #N/A | PULVERIZER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 4.1 hp No | RM2000 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-028 | #N/A | #N/A | PULVERIZER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 4.1 hp No | RM2000 |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-029 | #N/A | #N/A | PULVERIZER DUST HOOD | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.15 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-030 | #N/A | #N/A | ROTAP | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 1.22 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-031 | #N/A | #N/A | ROTAP DUST HOOD | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.15 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-032 | #N/A | #N/A | MAGNETITE ANALYSER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 0.41 hp No | SATMAGAN - MAGNETITE CONTENT MEASURING INSTRUMENT |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-033 | #N/A | #N/A | SCRUBBER FAN | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 12.7 hp No | MV-16 SCRUBBER FAN |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-034 | #N/A | #N/A | SCRUBBER RECIRCULATION PUMP | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 3 hp No |  |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-035 | #N/A | #N/A | THERMOGRAVIMETRIC ANALYSER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 7.8 hp No | LECO TGA |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4511 | 4511-LE-036 | #N/A | #N/A | XRF SPECTROMETER | LABORATORY EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 9.5 hp No | XRF SPECTROMETER & UNINTERRUPTED POWER SUPPLY |  | / / / | PM105 |  | 2014
|  | 0 | 504-2200 |  | 4513 | 4513-MO-001 | #N/A | #N/A | AMBULANCE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6680 W: 2438 H: 2024 | 6350 |  | INTERMITTENT |  | / / / | WHEELED COACH TYPE I, 4X4; TURBO DIESEL |  | / / / | PM101 | FORD F450 | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-MO-002 | #N/A | #N/A | FIRE TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 10922 W: 2921 H: 3607 | 39000 GVWR |  | INTERMITTENT | 3000 GAL WATER TANK | / / / | 420 GAL FOAM TANK; 450 LB DRY CHEMICAL TANK; ARFF WITH SNOZZLE |  | / / / | PM101 | OSHKOSH TI3000 | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-MO-003 | #N/A | #N/A | SNOW RESCUE VEHICLE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6900 W: 1870 H: 2400 | 6580 |  | INTERMITTENT |  | / / / | 17 PASSENGER |  | / / / | PM101 | HAGGLUND BV206 | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-PP-006 | #N/A | #N/A | EMERGENCY RESPONSE OFFICE RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | H349000-4720-05-030-0003 / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 4513 | 4513-MT-006 | #N/A | #N/A | RAW WATER TANK PUMP |  | 4513-PP-006 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 504-2200 |  | 4513 | 4513-PP-021 | #N/A | #N/A | MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4513 | 4513-MT-021 | #N/A | #N/A | FUEL OIL PUMP |  | 4513-PP-021 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4513 | 4513-PP-022 | #N/A | #N/A | MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4513 | 4513-MT-022 | #N/A | #N/A | FUEL OIL PUMP |  | 4513-PP-022 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4513 | 4513-SQ-010 | #N/A | #N/A | DRY CHEMICAL REFILL STATION | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No | DRY POWDER CHEMICAL HANDLING SYSTEM |  | / / / | PM104 | TYCO FIRE PROTECTION | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-TK-004 | 6641.96 | #REF! | EMERGENCY RESPONSE OFFICE SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | H349000-4720-05-030-0003 / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-TK-005 | 1929.6717 | #REF! | EMERGENCY RESPONSE OFFICE RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | FREESTANDING WATER TANK |  | H349000-4720-05-030-0003 / / | PX001 | NORWESCO | 2013
|  | 0 | 504-2200 |  | 4513 | 4513-TK-023 | 3320.98 | #REF! | MINE EMERGENCY RESPONSE GARAGE DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4521 | 4521-PP-003 | #N/A | #N/A | WELDING SHOP FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4521 | 4521-MT-003 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4521 | 4521-PP-004 | #N/A | #N/A | WELDING SHOP FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4521 | 4521-MT-004 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-004 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4521 | 4521-PP-011 | #N/A | #N/A | MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4521 | 4521-MT-011 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-011 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4521 | 4521-PP-012 | #N/A | #N/A | MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4521 | 4521-MT-012 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-012 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4521 | 4521-PP-021 | #N/A | #N/A | WAREHOUSE BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4521 | 4521-MT-021 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-021 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4521 | 4521-PP-022 | #N/A | #N/A | WAREHOUSE BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4521 | 4521-MT-022 | #N/A | #N/A | FUEL OIL PUMP |  | 4521-PP-022 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4521 | 4521-PP-051 | #N/A | #N/A | WORKSHOP OFFICE WASHCAR RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | H349000-4720-05-030-0003 / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 4521 | 4521-MT-051 | #N/A | #N/A | RAW WATER TANK PUMP |  | 4521-PP-051 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 504-2200 |  | 4521 | 4521-TK-005 | 3320.98 | #REF! | WELDING SHOP DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 20000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4521 | 4521-TK-013 | 3320.98 | #REF! | MAINTENANCE BUILDING DIESEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS |  | / / / |  |  | / / / | PX004 |  | 2014
|  | 0 | 504-2200 |  | 4521 | 4521-TK-023 | 3320.98 | #REF! | WAREHOUSE BUILDING DIESEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS |  | / / / |  |  | / / / | PX004 |  | 2014
|  | 0 | 504-2200 |  | 4521 | 4521-TK-050 | 1929.6717 | #REF! | WORKSHOP OFFICE WASHCAR RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | H349000-4720-05-030-0003 / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 504-2200 |  | 4521 | 4521-TK-053 | 6641.96 | #REF! | WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | H349000-4720-05-030-0003 / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-001 | #N/A | #N/A | INDUSTRIAL FREEZER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1525 W: 715 H: 1250 | 290 |  | INTERMITTENT | 20 CU.FT. | / 0.35 hp No | RANGE -45C TO -80C. 20 FT3 |  | / / / | PM104 | ONTARIO OVENS 80-12 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-002 | 0 | #REF! | KIDNEY LOOP | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 50 |  | INTERMITTENT | 10 GPM FLOW | / 1.62 hp No | OPERATING TEMP -40 DEG C TO 66 DEG C; HYDRAULIC FILTER CART 10 MFP |  | / / / | PM104 | AG - DYE10MFP240SA10QBV | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-003 | #N/A | #N/A | LARGE SHOP PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1295 W: 1727 H: 3125 | 1970 |  | INTERMITTENT | 150 TON | / / No |  |  | / / / | PM104 | AG - OTC1866 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-004 | #N/A | #N/A | LATHE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 44 H: 64 |  |  | INTERMITTENT | 20 INCH | / 10.13 hp No | THREE LENGTHS: 94" (4730 LBS) / 114" (5590 LBS) / 134" (6800 LBS) |  | / / / | PM104 | SUMMIT MACHINE TOOL | 2013
|  | 0 |  |  | 4522 | 4522-MT-004A | 0 | #REF! | LATHE SPINDLE MOTOR |  | 4522-SQ-004 | NEW | [6 empty] | INTERMITTENT |  | / 10 hp / |  |  | / / / | PM104
|  | 0 |  |  | 4522 | 4522-MT-004B | #N/A | #N/A | LATHE COOLANT PUMP |  | 4522-SQ-004 | NEW | [6 empty] | INTERMITTENT |  | / 0.13 hp / |  |  | / / / | PM104
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-005 | #N/A | #N/A | MILLING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-006 | #N/A | #N/A | LINE BORING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1830 W: 330 H: 280 | 205 |  | INTERMITTENT | BORING DIA. 12" (OPT. 24") | / 10.1 hp No | BORING DIAMETERS 1.5" - 2" |  | / / / | PM104 | CLIMAX BB5000 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-008 | #N/A | #N/A | IRON WORKER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1525 W: 915 H: 1985 | 2300 |  | INTERMITTENT | 84 TON PUNCH STATION | / 3.4 hp No | HYDRAULIC SW-84 / SHIPS IN THREE (3) SEPERATE PACKAGES |  | / / / | PM104 | BAILEIGH INDUSTRIAL 001-99777 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-009 | #N/A | #N/A | HEAVY TRUCK RAMP | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 13360 W: 4980 H: 3990 |  |  | INTERMITTENT | 27 TON LIFTING CAPACITY | / 4.1 hp No | COMPLETE WITH ROLLING JACK AND ROLLING DRAIN PAN |  | / / / | PM104 | ROTARY 60000HDL | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-010 | #N/A | #N/A | LIGHT TRUCK RAMP | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | H: 6990 |  |  | INTERMITTENT | 8 TON LIFTING CAPACITY | / 4.1 hp No | COMPLETE WITH ROLLING JACK AND ROLLING DRAIN PAN |  | / / / | PM104 | ROTARY SM18LO-X | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-011 | #N/A | #N/A | TIRE SIPING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-012 | #N/A | #N/A | AIR FILTER CLEANER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1830 W: 1830 H: 2650 |  |  | INTERMITTENT | 55 GAL DUST DRUM | / 6.8 hp No | REQUIRES COMPRESSED AIR AT 90 PSI |  | / / / | PM104 | DIVERSI-TECH | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-018 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-019 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-021 | #N/A | #N/A | DRILL PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 508 W: 356 H: 1778 | 120 |  | INTERMITTENT | CHUCK CAPACITY 15.9 MM | / 2.7 hp No | LENGTH AND WIDTH ARE TABLE DIMENSIONS; 22" WITH LASER |  | / / / | PM104 | AG - DPE18-900 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-022 | #N/A | #N/A | MAGNETIC BASE DRILL | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 33 |  | INTERMITTENT | 1650 LBS DRILL POINT PRESSURE | / 0.81 hp No | 1/2 " CHUCK SIZE |  | / / / | PM104 | AG - MTL4210-1 | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-023 | #N/A | #N/A | OIL FILTER PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1524 W: 914 H: 2640 | 680 |  | INTERMITTENT | 32 TON CRUSHING FORCE | / 3.4 hp No | 57 SECOND CYCLE TIME |  | / / / | PM104 | OBERG P300 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-026 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-027 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-028 | #N/A | #N/A | PORTABLE WELDING FUME EXTRACTOR | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 73 |  | INTERMITTENT | 35 M2 FILTER AREA | / 1 hp No |  |  | / / / | PM104 | AG - NED12634345 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-029 | #N/A | #N/A | PORTABLE WELDING SPARK PROTECTOR | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - NED12375241 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-031 | #N/A | #N/A | SWEEPER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 4.7 hp No | ELECTRIC - AREA 20000 FT2 |  | / / / | PM104 | AG | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-036 | #N/A | #N/A | TIRE CHANGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / 2.03 hp No | RIM DIAMATERS: EXTERNAL 9"-30", INTERNAL DIAMETER 11"-32" |  | / / / | PM104 | COATS APX80A | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-038 | #N/A | #N/A | TRACK PIN PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-041 | #N/A | #N/A | BULK FLUID DISTRIBUTION SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No | OILS, LUBRICANT, COOLANT, GREASE,WATER (WASHDOWN) |  | / / / | PM104 | AG | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-042 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-043 | #N/A | #N/A | EVAC TANK | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1118 W: 508 H: 1093 | 200 |  | INTERMITTENT | 60 GAL TANK | / / No | SAGE OIL VAC FLUID RECOVERY SYSTEM - 120 GALLONS |  | / / / | PM104 | NORTHERN TOOL 30070V | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-044 | #N/A | #N/A | WELDING MACHINE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 965 W: 584 H: 762 | 192 |  | INTERMITTENT |  | / 54 hp No | 452 MIGRUNNER DIMENSION PACKAGE - 500 AMP |  | / / / | PM104 | AG - MLW951-277 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-046 | #N/A | #N/A | METAL BREAK FLOOR | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 580 |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - GGS13W877 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-047 | #N/A | #N/A | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-048 | #N/A | #N/A | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-049 | #N/A | #N/A | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-050 | #N/A | #N/A | PARTS WASHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 1070 W: 560 H: 406 | 84 |  | INTERMITTENT | 40 GAL TANK CAPACITY | / 2.03 hp No | DIMENSIONS ARE FOR THE TANK ITSELF; SOLV DELUXE HANDIKLEEN |  | / / / | PM104 | AG - GRYPL422A | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-051 | #N/A | #N/A | TIRE SPREADER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT | MAX TIRE: 18R-22.5" | / 2.7 hp No | AIR POWERED WITH LYING BASE. 220V MAX. 18R/22.5 INCH |  | / / / | PM104 | ZHUHAI TEAMROC TR-S825 | 2013
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-052 | #N/A | #N/A | HYDRAULIC PORTA POWER PUMP | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-053 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 4522 | 4522-MT-053 | #N/A | #N/A | BENCH GRINDER |  | 4522-SQ-053 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-054 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 4522 | 4522-MT-054 | #N/A | #N/A | BENCH GRINDER |  | 4522-SQ-054 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-055 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 4522 | 4522-MT-055 | #N/A | #N/A | BENCH GRINDER |  | 4522-SQ-055 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-056 | #N/A | #N/A | BENCH GRINDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | W: 610 H: 345 |  |  | INTERMITTENT | 10 " WHEEL SIZE | / 1 hp No | HD 10" 1 HP 120V |  | / / / | PM104 | AG - WSWBG10D | 2014
|  | 0 |  |  | 4522 | 4522-MT-056 | #N/A | #N/A | BENCH GRINDER |  | 4522-SQ-056 | NEW | [6 empty] | INTERMITTENT |  | / 1 hp / |  |  | / / / | PM104
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-059 | #N/A | #N/A | TRUCK MOUNT GOODALL BOOST SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-060 | #N/A | #N/A | GOODALL BOOST SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-063 | #N/A | #N/A | TRACK PIN PRESS | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - OTC4240 | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-064 | #N/A | #N/A | A/C RECOVERY RECHARGE UNIT | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  | L: 584 W: 864 H: 1120 | 110 |  | INTERMITTENT | MAX TANK SIZE 30 LBS | / / No | MULTI-REFRIGERANT |  | / / / | PM104 | ROBINAIR RBN17800B | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-065 | 0 | #REF! | INCHING TOOL | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No | OPEN LOOP ENERGY |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-066 | 0 | #REF! | BATTERY CHARGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - WSW1JYU3 | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-067 | 0 | #REF! | BATTERY CHARGER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG - WSW1JYU3 | 2014
|  | 0 | 504-2200 |  | 4522 | 4522-SQ-068 | #N/A | #N/A | TUBE BENDER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4523 | 4523-PP-002 | #N/A | #N/A | TRUCK WASH BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4523 | 4523-MT-002 | #N/A | #N/A | FUEL OIL PUMP |  | 4523-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4523 | 4523-PP-003 | #N/A | #N/A | TRUCK WASH BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 0.5 hp No |  |  | / / / | PX004 |  | 2014
|  | 0 |  |  | 4523 | 4523-MT-003 | #N/A | #N/A | FUEL OIL PUMP |  | 4523-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX004
|  | 0 | 504-2200 |  | 4523 | 4523-TK-004 | #N/A | #N/A | TRUCK WASH BUILDING DIESEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS |  | / / / |  |  | / / / | PX004 |  | 2014
|  | 0 | 504-2200 |  | 4523 | 4523-VP-001 | #N/A | #N/A | TRUCK WASH FACILITY VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | CERTIFIED FINAL | SANJAY DAHIYA |  |  |  |  | INTERMITTENT |  | / 7 hp No |  |  | H349000-4720-05-030-0004 / / | PM114 |  | 2013
|  | 0 | 504-2200 |  | 4540 | 4540-PP-005 | #N/A | #N/A | MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4540 | 4540-MT-005 | #N/A | #N/A | FUEL OIL PUMP |  | 4540-PP-005 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4540 | 4540-PP-006 | #N/A | #N/A | MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4540 | 4540-MT-006 | #N/A | #N/A | FUEL OIL PUMP |  | 4540-PP-006 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4540 | 4540-SQ-002 | 0 | #REF! | AEROSOL CAN RECYCLING SYSTEM | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 5 |  | INTERMITTENT | CAPABLE OF 76, 114, AND 208 L | / / No |  |  | / / / | PM104 | AG - SAYCPU03 | 2013
|  | 0 | 504-2200 |  | 4540 | 4540-SQ-003 | #N/A | #N/A | DRUM CRUSHER | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  | 650 |  | INTERMITTENT | 38000 LBS OF CRUSHING PRESSURE | / 6.8 hp No | CRUSHES 55 GAL DRUMS TO 6" HIGH; RESETS IN 25 SECONDS |  | / / / | PM104 | AG - VESHDC900IDC | 2013
|  | 0 | 504-2200 |  | 4540 | 4540-SQ-004 | #N/A | #N/A | PLATFORM SCALE | SHOP / MAINTENANCE EQUIPMENT |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT | 10 TON | / / No |  |  | / / / | PM104 | AG | 2014
|  | 0 | 504-2200 |  | 4540 | 4540-TK-007 | #N/A | #N/A | MILNE WASTE MANAGEMENT BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 20000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4540 | 4540-VP-001 | 8954.42 | #REF! | WASTE INCINERATOR VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | - |  | / / / |  |  | H349000-4540-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4613 | 4613-FD-013 | 3850.1667 | #REF! | DIESEL FUEL DISPENSING MODULE | FUEL DISPENSER |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2013
|  | 0 | 504-2200 |  | 4613 | 4613-PP-001 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-002 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-003 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-004 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-005 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-006 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-007 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-PP-008 | #N/A | #N/A | DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | PUMP |  | NEW | PRELIMINARY | FLOYD BUTTS |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-TK-009 | 14541.2424 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 8350 DIA H: 9140 |  |  | CONTINUOUS | 500 kL | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 504-2200 |  | 4613 | 4613-TK-010 | 14541.2424 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 8350 DIA H: 9140 |  |  | CONTINUOUS | 500 kL | / / / |  |  | / / / | PM004 |  | 2013
|  | 0 | 504-2200 |  | 4613 | 4613-TK-011 | 14541.2424 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 8350 DIA H: 9140 |  |  | CONTINUOUS | 500 kL | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4613 | 4613-TK-012 | 14541.2424 | #REF! | ARCTIC DIESEL TANK | TANK |  | NEW | PRELIMINARY | FLOYD BUTTS |  | W: 8350 DIA H: 9140 |  |  | CONTINUOUS | 500 kL | / / / |  |  | / / / | PM004 |  | 2014
|  | 0 | 504-2200 |  | 4619 | 4619-GE-001 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 504-2200 |  | 4619 | 4619-GE-002 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 504-2200 |  | 4619 | 4619-GE-003 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 504-2200 |  | 4619 | 4619-GE-004 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2013
|  | 0 | 504-2200 |  | 4619 | 4619-GE-005 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2014
|  | 0 | 504-2200 |  | 4619 | 4619-GE-006 | #N/A | #N/A | GENERATOR | GENERATOR |  | NEW | CERTIFIED FINAL | BRIAN PERKINS |  |  |  |  | CONTINUOUS |  | / 1840 hp No |  |  | / / / | PE001 |  | 2014
|  | 0 | 504-2200 |  | 4720 | 4720-PP-002 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 35 hp No |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 |  |  | 4720 | 4720-MT-002 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP |  | 4720-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 35 hp / |  |  | / / / | TX001
|  | 0 | 504-2200 |  | 4720 | 4720-PP-003 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT |  | / 35 hp No |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 |  |  | 4720 | 4720-MT-003 | #N/A | #N/A | RAW WATER DISTRIBUTION PUMP |  | 4720-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 35 hp / |  |  | / / / | TX001
|  | 0 | 504-2200 |  | 4720 | 4720-PP-004 | #N/A | #N/A | DIESEL FIRE WATER PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-005 | #N/A | #N/A | ELECTRIC FIRE WATER PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | STANDBY |  | / / No |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-006 | #N/A | #N/A | JOCKEY PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | STANDBY |  | / / No |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-008 | #N/A | #N/A | RAW WATER FEED PUMP | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 10 HP | / 10 hp No |  |  | H349000-4720-05-030-0001 / / | PM003 |  | 2013
|  | 0 |  |  | 4720 | 4720-MT-008 | #N/A | #N/A | RAW WATER FEED PUMP |  | 4720-PP-008 | NEW | [6 empty] | INTERMITTENT |  | / 10 hp / |  |  | / / / | PM003
|  | 0 | 504-2200 |  | 4720 | 4720-PP-010 | #N/A | #N/A | POTABLE WATER DISCHARGE PUMP NO.1 | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-011 | #N/A | #N/A | POTABLE WATER DISCHARGE PUMP NO.2 | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-013 | #N/A | #N/A | BACKWASH SLURRY PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-014 | #N/A | #N/A | CLEAN BACKWASH PUMP | PUMP |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / No |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-PP-015 | #N/A | #N/A | RAW WATER FEED PUMP | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 10 HP | / 10 hp No | VERTICAL TURBINE PUMP |  | / / / | PM003 |  | 2013
|  | 0 |  |  | 4720 | 4720-MT-015 | #N/A | #N/A | RAW WATER FEED PUMP |  | 4720-PP-015 | NEW | [6 empty] | INTERMITTENT |  | / 10 hp / |  |  | / / / | PM003
|  | 0 | 504-2200 |  | 4720 | 4720-PP-031 | #N/A | #N/A | MINE WATER BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4720 | 4720-MT-031 | #N/A | #N/A | FUEL OIL PUMP |  | 4720-PP-031 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4720 | 4720-PP-032 | #N/A | #N/A | MINE WATER BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4720 | 4720-MT-032 | #N/A | #N/A | FUEL OIL PUMP |  | 4720-PP-032 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4720 | 4720-TK-001 | 6641.96 | #REF! | RAW WATER TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / / |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-TK-007 | 6641.96 | #REF! | FIRE WATER TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | CONTINUOUS |  | / / / |  |  | H349000-4720-05-030-0001 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-TK-009 | 6641.96 | #REF! | POTABLE WATER STORAGE TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-TK-012 | 6641.96 | #REF! | BACKWASH SETTLING TANK | TANK |  | NEW | PRELIMINARY | MATTHEW BUYKX |  |  |  |  | INTERMITTENT |  | / / / |  |  | H349000-4720-05-030-0002 / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-TK-033 | #N/A | #N/A | MINE WATER BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4720 | 4720-VP-020 | 8954.42 | #REF! | POTABLE WATER TREATMENT PLANT VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | - |  | / / / |  |  | / / / | TX001 |  | 2013
|  | 0 | 504-2200 |  | 4731 | 4731-PP-003 | #N/A | #N/A | TREATED EFFLUENT DISCHARGE PUMP NO.1 | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4731 | 4731-PP-004 | #N/A | #N/A | TREATED EFFLUENT DISCHARGE PUMP NO.2 | PUMP |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / No |  |  | / / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4731 | 4731-SC-001 | #N/A | #N/A | SCREEN | SCREEN |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4731 | 4731-TK-002 | 6641.96 | #REF! | TREATED EFFLUENT TANK | TANK |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4731 | 4731-VP-005 | 23101 | #REF! | SEWAGE TREATMENT PLANT VENDOR PACKAGE | VENDOR PACKAGE |  | NEW | PRELIMINARY | RUSI KAPADIA |  |  |  |  | - |  | / / / |  |  | H349000-4731-05-030-0001/H349000-2731-05-030-0001 / / | PM009 |  | 2013
|  | 0 | 504-2200 |  | 4732 | 4732-PP-001 | #N/A | #N/A | MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4732 | 4732-MT-001 | #N/A | #N/A | FUEL OIL PUMP |  | 4732-PP-001 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4732 | 4732-PP-002 | #N/A | #N/A | MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) | PUMP |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | INTERMITTENT | 25 PSI | / 0.5 hp No | DUPLEX FUEL OIL PUMPS, POSITIVE DISPLACEMENT ROTARY |  | / / / | PX002 | VIKING DUPLEX OIL SYSTEMS | 2013
|  | 0 |  |  | 4732 | 4732-MT-002 | #N/A | #N/A | FUEL OIL PUMP |  | 4732-PP-002 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX002
|  | 0 | 504-2200 |  | 4732 | 4732-TK-003 | 3320.98 | #REF! | MINE SEWAGE TRUCK BUILDING DIESEL FUEL TANK | TANK |  | NEW | PRELIMINARY | KENTARO IMAI |  |  |  |  | CONTINUOUS | 10000 L | / / / | DOUBLE WALLED HORIZONTAL ABOVE GRADE TANK |  | / / / | PX002 | DTE ULC601-07 | 2013
|  | 0 | 504-2200 |  | 4733 | 4733-VM-001 | 0 | #REF! | TREATED EFFLUENT POND SLUICE GATE | BULK MATERIAL VALVES |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | BP005 |  | 2013
|  | 0 | 504-2200 |  | 4733 | 4733-VM-002 | 0 | #REF! | TREATED EFFLUENT POND SLUICE GATE SPARE | BULK MATERIAL VALVES |  | NEW | PRELIMINARY | BRADEN LOMANTO |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | BP005 |  | 2013
|  | 0 | 507-3200 |  | 7231 | 7231-PP-003 | #N/A | #N/A | AERODROME OFFICE RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7231 | 7231-MT-003 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7231-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7231 | 7231-TK-001 | 6641.96 | #REF! | AERODROME OFFICE SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7231 | 7231-TK-002 | 1929.6717 | #REF! | AERODROME OFFICE RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | FREESTANDING WATER TANK |  | / / / | PX001 | NORWESCO | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-PP-003 | #N/A | #N/A | BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7232 | 7232-MT-003 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7232-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7232 | 7232-PP-006 | #N/A | #N/A | SITE SERVICES WASHCAR #1 RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7232 | 7232-MT-006 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7232-PP-006 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7232 | 7232-PP-009 | #N/A | #N/A | SITE SERVICES WASHCAR #2 RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7232 | 7232-MT-009 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7232-PP-009 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7232 | 7232-TK-001 | 6641.96 | #REF! | BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-TK-002 | 1929.6717 | #REF! | BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-TK-004 | 6641.96 | #REF! | SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-TK-005 | 1929.6717 | #REF! | SITE SERVICES WASHCAR #1 RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-TK-007 | 1929.6717 | #REF! | SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7232 | 7232-TK-008 | 1929.6717 | #REF! | SITE SERVICES WASHCAR #2 RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-001 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-002 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-003 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-004 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-005 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-006 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-007 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-008 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-009 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-010 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-011 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-012 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-013 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-014 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-024 | #N/A | #N/A | CUBE VAN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | 12' HEATED ENCLOSED VAN BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7241 | 7241-MO-026 | #N/A | #N/A | PICKUP TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 6274 W: 2665 H: 2032 | 6350 |  | INTERMITTENT | 3300 KG PAYLOAD | / / / |  |  | / / / | PM111 | FORD F350 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-001 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-002 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-003 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-004 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-005 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-006 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-007 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-008 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-009 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-010 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | MADE IN 2012; C/W LINERS - AVAILABLE TO SHIP - NEED FIRE SUPPRESSION - WILL TAKE SOME TIME |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-011 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | STANDARD LIFT |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-012 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | STANDARD LIFT |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-014 | #N/A | #N/A | MID SIZE AIR COMPRESSOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  | NUNA | INTERMITTENT | 375 CFM | / / / |  |  | / / / | PM104 | ATLAS COPCO | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-015 | #N/A | #N/A | TRASH PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 711.2 W: 533.4 H: 621.7 | 54 |  | INTERMITTENT | 3" | / / / | AVAILABLE READY TO SHIP |  | / / / | PM106 | GORMAN-RUPP 13D-L700EE S/G | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-016 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-017 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-018 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-019 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-020 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-021 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6050 W: 2390 H: 3150 | 9600 |  | INTERMITTENT | 1.3 M3 BUCKET | / / / | QUICK COUPLERS/BUCKETS/FORKS |  | / / / | PM102 | CAT 930K | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-022 | #N/A | #N/A | TELEHANDLER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6100 W: 2570 H: 2570 | 15800 | NUNA | INTERMITTENT | 5000 KG | / / / |  |  | / / / | PM106 | CAT TH514 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-023 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-024 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-025 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-026 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-027 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-028 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-029 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-030 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-031 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-032 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-033 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-034 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-035 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-036 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-037 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7243 | 7243-MO-046 | #N/A | #N/A | LOWBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 16050 W: 2438 |  |  | INTERMITTENT | 60 T | / / / | STANDARD WIDTH |  | / / / | PM143 |  | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-001 | #N/A | #N/A | ACOMMODATIONS AREA GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 14630 W: 2440 H: 4062 | 68320 |  | STANDBY | 5106 L FUEL TANK | / 2145 hp No | POWER SUPPLY CAN BE SPLIT INTO 2 X 1075 HP; DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C1600D6R | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-002 | #N/A | #N/A | CONCRETE BATCH PLANT GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4674 W: 1730 H: 2085 | 8800 |  | STANDBY | 901 L FUEL TANK | / 200 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C150D6R | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-003 | #N/A | #N/A | CONCRETE BATCH PLANT GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4674 W: 1730 H: 2085 | 8800 |  | STANDBY | 901 L FUEL TANK | / 200 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C150D6R | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-004 | #N/A | #N/A | GENERAL GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4500 W: 1905 H: 2085 | 5322 |  | STANDBY | 606 L FUEL TANK | / 107 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C80D6R | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-005 | #N/A | #N/A | CONSTRUCTION OFFICE/LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4500 W: 1905 H: 2085 | 5230 |  | STANDBY | 606 L FUEL TANK | / 80 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C60D6R | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-006 | #N/A | #N/A | SITE SERVICES LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2110 W: 1020 H: 2315 | 3776 |  | STANDBY | 532 L FUEL TANK | / 47 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSFAA | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-007 | #N/A | #N/A | LOGISTICS TRAILER GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2110 W: 1020 H: 2315 | 3776 |  | STANDBY | 532 L FUEL TANK | / 47 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSFAA | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-008 | #N/A | #N/A | AERODROME LIGHTING GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2160 W: 790 H: 1500 | 2442 |  | STANDBY | 380 L FUEL TANK | / 27 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSKBA | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-009 | #N/A | #N/A | WORKFACE TOOLS GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2160 W: 790 H: 1500 | 2442 |  | STANDBY | 380 L FUEL TANK | / 27 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSKBA | 2013
|  | 0 | 507-3200 |  | 7244 | 7244-GE-010 | #N/A | #N/A | WORKFACE TOOLS GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2160 W: 790 H: 1500 | 2442 |  | STANDBY | 380 L FUEL TANK | / 27 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSKBA | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-002 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | JLG 450AJ | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-003 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | JLG 450AJ | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-004 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | GENIE Z45/25 | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-005 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-006 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-007 | #N/A | #N/A | BOOM TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 26 T | / / / | MOUNTED ON A 2004 FORD STERLING 7501 |  | / / / | PM130 | MAMTEX 26101C | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-008 | #N/A | #N/A | MAINTENANCE CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  | 41400 |  | INTERMITTENT | 80 T | / / / | ETA JULY 15, 2013 |  | / / / | PM116 | GROVE RT890E | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-010 | #N/A | #N/A | WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 3311 |  | INTERMITTENT | 12666 LBS MAXIMUM PAYLOAD | / / / | 12' FLAT DECK BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-011 | #N/A | #N/A | WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 3311 |  | INTERMITTENT | 12666 LBS MAXIMUM PAYLOAD | / / / | 12' FLAT DECK BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7245 | 7245-MO-012 | #N/A | #N/A | WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 3311 |  | INTERMITTENT | 12666 LBS MAXIMUM PAYLOAD | / / / | 12' FLAT DECK BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-001 | #N/A | #N/A | TRACK DOZER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 4674 W: 2000 H: 2900 | 9250 |  | INTERMITTENT | BLADE WIDTH: 3200 MM | / / / |  |  | / / / | PM102 | CAT D6T XW | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-002 | #N/A | #N/A | TRACK DOZER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 4674 W: 2000 H: 2900 | 9250 |  | INTERMITTENT | BLADE WIDTH: 3200 MM | / / / |  |  | / / / | PM102 | CAT D6T XW | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-003 | #N/A | #N/A | TRACK DOZER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4674 W: 2000 H: 2900 | 9250 |  | INTERMITTENT | BLADE WIDTH: 3200 MM | / / / | LGP - LOW GROUND PRESSURE |  | / / / | PM102 | CAT D6-LGP | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-004 | #N/A | #N/A | MID SIZE EXCAVATOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 11910 W: 3490 H: 3770 | 45000 |  | INTERMITTENT | 345 HP, 3.5 M3 BUCKET | / / / |  |  | / / / | PM102 | CAT 345DL HEX | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-014 | #N/A | #N/A | COMPACTOR | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 5970 W: 2300 H: 3070 | 15650 |  | INTERMITTENT | DRUM WIDTH: 2140 MM; DRUM DIA: | / / / | MADE IN 2011 |  | / / / | PM102 | CAT CS74 | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-015 | #N/A | #N/A | COMPACTOR | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 5970 W: 2300 H: 3070 | 15650 |  | INTERMITTENT | DRUM WIDTH: 2140 MM; DRUM DIA: | / / / | MADE IN 2007; 84" PADFOOT VIBRATORY SOIL COMPACTOR |  | / / / | PM102 | CAT CP563E | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-016 | #N/A | #N/A | ROAD SNOW BLOWER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 6170 W: 2410 H: 3320 | 18338 |  | INTERMITTENT | WITH SNOW BLOWER ATTACHMENTS | / / / | C/W VOHL MODEL DV400 SNOW BLOWER |  | / / / | PM102 | CAT 950H | 2013
|  | 0 | 507-3200 |  | 7340 | 7340-MO-017 | #N/A | #N/A | ROAD SNOW BLOWER | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 6170 W: 2410 H: 3320 | 18338 |  | INTERMITTENT | WITH SNOW BLOWER ATTACHMENTS | / / / | C/W VOHL MODEL DV400 SNOW BLOWER |  | / / / | PM102 | CAT 950H | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-PP-003 | #N/A | #N/A | BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7432 | 7432-MT-003 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7432-PP-003 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7432 | 7432-PP-006 | #N/A | #N/A | FUEL SYSTEMS WASHCAR RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7432 | 7432-MT-006 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7432-PP-006 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7432 | 7432-PP-009 | #N/A | #N/A | SITE SERVICES WASHCAR #1 RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7432 | 7432-MT-009 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7432-PP-009 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7432 | 7432-PP-012 | #N/A | #N/A | SITE SERVICES WASHCAR #2 RAW WATER PUMP | PUMP |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 483 W: 275 H: 267 |  |  | INTERMITTENT | 65 PSI | / 0.5 hp No | 1/2 HP ELECTRIC PUMP |  | / / / | PX001 | SIMER JET PUMPS 2205C | 2013
|  | 0 |  |  | 7432 | 7432-MT-012 | #N/A | #N/A | RAW WATER TANK PUMP |  | 7432-PP-012 | NEW | [6 empty] | INTERMITTENT |  | / 0.5 hp / |  |  | / / / | PX001
|  | 0 | 507-3200 |  | 7432 | 7432-TK-001 | 6641.96 | #REF! | BATCH PLANT OFFICE-LUNCHROOM-WC SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-002 | 1929.6717 | #REF! | BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1613 W: 737 H: 1676 |  |  | CONTINUOUS | 400 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-004 | 6641.96 | #REF! | FUEL SYSTEMS WASHCAR SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-005 | 1929.6717 | #REF! | FUEL SYSTEMS WASHCAR RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-007 | 6641.96 | #REF! | SITE SERVICES WASHCAR #1 SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-008 | 1929.6717 | #REF! | SITE SERVICES WASHCAR #1 RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-010 | 6641.96 | #REF! | SITE SERVICES WASHCAR #2 SEWAGE COLLECTION TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 3791 W: 1829 H: 610 |  |  | INTERMITTENT | 1000 GAL | / / / | RECTANGULAR TANK |  | / / / | PX001 | LAGRANGE MECHANICAL SERVICES | 2013
|  | 0 | 507-3200 |  | 7432 | 7432-TK-011 | 1929.6717 | #REF! | SITE SERVICES WASHCAR #2 RAW WATER TANK | TANK |  | NEW | CERTIFIED FINAL | KENTARO IMAI |  | L: 1803 W: 1245 H: 1346 |  |  | CONTINUOUS | 525 GAL TANK | / / / | HORIZONTAL TANK WITH >48 HOURS SUPPLY |  | / / / | PX001 | PLASTIC-MART 866-310-2556 | 2013
|  | 0 | 507-3200 |  | 7441 | 7441-MO-008 | #N/A | #N/A | FUEL/LUBE TRUCK - ARTICULATED | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  |  |  |  | INTERMITTENT | 4175 GAL | / / / | ENCLOSED FUEL LUBE TRUCK; 4175 GAL DIESEL TANK; 6 PRODUCT TANKS IN FABRICATION - ETA SEPT 1, 2013 |  | / / / | PM102 | CAT 740 EFLT | 2013
|  | 0 | 507-3200 |  | 7441 | 7441-MO-025 | #N/A | #N/A | CUBE VAN | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT |  | / / / | 12' HEATED ENCLOSED VAN BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-001 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | ETA JULY 15, 2013 |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-002 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | ETA JULY 15, 2013 |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-003 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | ETA JULY 24, 2013 |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-004 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / | ETA JULY 24, 2013 |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-005 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-006 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-007 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-008 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-009 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-010 | #N/A | #N/A | ARTICULATED HAUL TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | TOROMONT |  | L: 10889 W: 3430 H: 3745 | 34000 |  | INTERMITTENT | 35 TON | / / / |  |  | / / / | PM136 | CAT 740B | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-011 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | STANDARD LIFT |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-012 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 10390 W: 3600 H: 4115 | 43400 |  | INTERMITTENT | 4.5 - 5.4 M3 BUCKET | / / / | STANDARD LIFT |  | / / / | PM102 | CAT 988H | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-014 | #N/A | #N/A | MID SIZE AIR COMPRESSOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  | NUNA | INTERMITTENT | 375 CFM | / / / |  |  | / / / | PM104 | ATLAS COPCO | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-015 | #N/A | #N/A | LARGE AIR COMPRESSOR | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 830 CFM | / / / |  |  | / / / | PM104 | ATLAS COPCO | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-016 | #N/A | #N/A | TRASH PUMP | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 711.2 W: 533.4 H: 621.7 | 54 |  | INTERMITTENT | 3" | / / / |  |  | / / / | PM106 | GORMAN-RUPP 13D-L700EE S/G | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-017 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-018 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-019 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-020 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-021 | #N/A | #N/A | MOBILE LIGHT PLANT | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 4623 W: 2007 H: 9000 | 925 |  | INTERMITTENT | 4000W | / / / | 4 X 1000W LIGHTS |  | / / / | PM106 | TEREX AL4 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-022 | #N/A | #N/A | FRONT END LOADER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6050 W: 2390 H: 3150 | 9600 |  | INTERMITTENT | 1.3 M3 BUCKET | / / / | QUICK COUPLERS/BUCKETS/FORKS |  | / / / | PM102 | CAT 930K | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-023 | #N/A | #N/A | TELEHANDLER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | TOROMONT |  | L: 6100 W: 2570 H: 2570 | 15800 | NUNA | INTERMITTENT |  | / / / |  |  | / / / | PM106 | CAT TH514 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-024 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-025 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-026 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-027 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-028 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-029 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-030 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-031 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-032 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-033 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-034 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-035 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-036 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-037 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-038 | #N/A | #N/A | FROST FIGHTER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 350000 BTU | / / / | OIL FIRED; C/W HEAT RECOVERY SYSTEM |  | / / / | BM104 | FROSTFIGHTER IDF350-11 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-051 | #N/A | #N/A | LOWBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 16050 W: 3658 |  |  | INTERMITTENT | 60T | / / / |  |  | / / / | PM143 |  | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-052 | #N/A | #N/A | HIBOY TRAILER | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 14630 W: 2438 |  |  | INTERMITTENT | 60T | / / / |  |  | / / / | PM143 |  | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-053 | #N/A | #N/A | SECONDARY DRILL | MOBILE EQUIPMENT |  | USED | PRELIMINARY | GLACIER |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM100 | SANDVIK 800 | 2013
|  | 0 | 507-3200 |  | 7443 | 7443-MO-054 | #N/A | #N/A | SECONDARY DRILL | MOBILE EQUIPMENT |  | USED | PRELIMINARY | GLACIER |  |  |  |  | INTERMITTENT |  | / / / |  |  | / / / | PM100 | SANDVIK 800 | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-001 | #N/A | #N/A | ACCOMMODATIONS AREA GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 14630 W: 2440 H: 4065 | 78220 |  | STANDBY | 5106 L FUEL TANK | / 2145 hp No | POWER SUPPLY CAN BE SPLIT INTO 2 X 1075 HP; DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C1600D6RG | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-002 | #N/A | #N/A | CONCRETE BATCH PLANT GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4675 W: 1730 H: 2085 | 10466 |  | STANDBY | 901 L FUEL TANK | / 200 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C150D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-003 | #N/A | #N/A | CONCRETE BATCH PLANT GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4675 W: 1730 H: 2085 | 10466 |  | STANDBY | 901 L FUEL TANK | / 200 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C150D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-004 | #N/A | #N/A | GENERAL GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4496 W: 1905 H: 2085 | 6458 |  | STANDBY | 606 L FUEL TANK | / 107 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C80D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-005 | #N/A | #N/A | AERODROME LIGHTING GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4496 W: 1905 H: 2085 | 6365 |  | STANDBY | 606 L FUEL TANK | / 80 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C60D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-006 | #N/A | #N/A | RAW WATER PUMPHOUSE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4496 W: 1905 H: 2085 | 6365 |  | STANDBY | 606 L FUEL TANK | / 80 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C60D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-007 | #N/A | #N/A | RAW WATER PUMPHOUSE GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4496 W: 1905 H: 2085 | 6365 |  | STANDBY | 606 L FUEL TANK | / 80 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C60D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-008 | #N/A | #N/A | CONSTRUCTION OFFICE/LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 4496 W: 1905 H: 2085 | 6365 |  | STANDBY | 606 L FUEL TANK | / 80 hp No | DIMENSIONS INCLUDE TRAILER |  | / / / | PE001 | CUMMINS C60D6R | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-009 | #N/A | #N/A | SITE SERVICES LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2110 W: 1020 H: 2315 | 4760 |  | STANDBY | 532 L FUEL TANK | / 47 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSFAA | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-010 | #N/A | #N/A | SITE SERVICES LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2110 W: 1020 H: 2315 | 4760 |  | STANDBY | 532 L FUEL TANK | / 47 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSFAA | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-011 | #N/A | #N/A | SITE SERVICES LUNCHROOM/WASHCAR GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2110 W: 1020 H: 2315 | 4760 |  | STANDBY | 532 L FUEL TANK | / 47 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSFAA | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-012 | #N/A | #N/A | WORKFACE TOOLS GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2160 W: 790 H: 1500 | 3145 |  | STANDBY | 380 L FUEL TANK | / 27 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSKBA | 2013
|  | 0 | 507-3200 |  | 7444 | 7444-GE-013 | #N/A | #N/A | WORKFACE TOOLS GENERATOR | GENERATOR |  | NEW | PRELIMINARY | BRIAN PERKINS |  | L: 2160 W: 790 H: 1500 | 3145 |  | STANDBY | 380 L FUEL TANK | / 27 hp No | NO TRAILER; DIMENSIONS ARE FOR GENERATOR ONLY |  | / / / | PE001 | CUMMINS DSKBA | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-002 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | GENIE Z45/25 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-003 | #N/A | #N/A | MAN LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 51' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | GENIE Z45/25 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-006 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-007 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-008 | #N/A | #N/A | SCISSOR LIFT | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 3500 W: 2200 H: 2900 | 4917 |  | INTERMITTENT | 47' WORKING HEIGHT | / / / | DIESEL |  | / / / | PM140 | SKYJACK 8841 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-009 | #N/A | #N/A | MAINTENANCE CRANE | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  | L: 12900 W: 7910 H: 3640 | 113000 |  | INTERMITTENT | 300 T | / / / |  |  | / / / | PM101 | MANITOWOC 2250 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-012 | #N/A | #N/A | BOOM TRUCK | MOBILE EQUIPMENT |  | USED | CERTIFIED FINAL | GRAHAM BURTON |  |  |  |  | INTERMITTENT | 26 T | / / / | MOUNTED ON A 2007 STERLING LT7501 |  | / / / | PM130 | MANITEX 26101C | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-013 | #N/A | #N/A | WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 3311 |  | INTERMITTENT | 12666 LBS MAXIMUM PAYLOAD | / / / | 12' FLAT DECK BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 | 507-3200 |  | 7445 | 7445-MO-014 | #N/A | #N/A | WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS | MOBILE EQUIPMENT |  | NEW | CERTIFIED FINAL | GRAHAM BURTON |  | L: 7264 W: 2418 H: 2022 | 3311 |  | INTERMITTENT | 12666 LBS MAXIMUM PAYLOAD | / / / | 12' FLAT DECK BODY |  | / / / | PM130 | FORD F550 | 2013
|  | 0 |  |  | 7920 | 7920-PP-001 |  |  | DECOMISSIONING PUMP | PUMP |  | NEW | PRELIMINARY | HEATHER REID | [6 empty] | / / / |  |  | / / /
2013-08-20 |  |  |  |  | 0 |  |  |  | Approved for Use |  | S. Carnegie |  |  |  |  | G. Burton |  |  |  | S. Perry |  |  |  | D. Matthews
Date |  |  |  |  | Rev. |  |  |  | Status |  | Prepared By |  |  |  |  | Checked By |  |  |  | Approved By |  |  |  | Approved By

## Additional Scope (hidden)
Component | Quantity | Unit of Measure | Comment | Source
MINE SITE
Site Roads | TBD | m (linear) | Catalina to provide. Assume same as in 2014 Marginal Closure Cost | Assumption
Hazardous Waste Containment Area - Existing | 4550.98 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Exploration Soft-Wall Camp | 6017.14 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Exploration Tent Camp Tents | 2400 | m2 | Assume 40 tents (10m x 6m) | Assumption
Exploration Tent Camp Pad | 9432.14 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Old Incinerator | 1 | ea | Add one pcs of minor mechanical equipment | Assumption
Exploration Camp Sewage Pipeline | 1799.9 | m (linear) |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Fuel Farm Tank Dike | 1911.3 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Exploration STP | 1 | ea | Add one pcs of major mechanical equipment | Assumption
Polishing Waste Stabilization Pond (Existing) | 7969.14 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Existing Landfill | 5031.47 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Bulk Fuel Storage Facility (Bladder Farm) | 5,787,68 | m2- |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Existing Laydown Area | 17366.92 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Barreled Fuel Line Containment | 5411.65 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Hazardous Waste Containment Area - New | 384.89 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Ore Crushing Sedimentation Pond | 6428.69 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Ore Stockpiles | 5100.23 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Ore Stockpile Pad | 35269.45 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
2008 Bulk Sample Pit | 18207.39 | m2 | Perimeter of Bulk Sample Pit = 653.19 m | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Pit 1 | 0 | m2 | Assume no pit development | Assumption
Raw Water Intake Pipeline | 4300.07 | m (linear) |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Waste Rock Dump from Bulk Sample | 5944.1 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
Exploration Workshops | 182.2 | m2 |  | Mine Site Footprint Reclamation Drawing H349000-4000-00-015-0020
MILNE PORT
Portable Water Intake | TBD | m (linear) | On hold – Not built at Milne Port in 2013 | Assumption
Existing Lined Storage Area | 985.34 | m2 | Next to existing runway | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Exploration Phase PWSP | 1451.9 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Ore Stockpile Laydown | 230545.88 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Ore Stockpile Footprints | 128865.8 | m2 | 32,216.45 m2/stockpile | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Ore Stockpile Settling Ponds | 11423.76 | m2 | 6,958.48 m2 – Pond #1 4,465.28 m2 – Pond #2 | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Fuel Tank Farm Berm | 25393 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Bladder Farm Decommissioning | 18482.01 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Existing Trailer Camp | 928.45 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Old STP (RBC) | N/A | N/A | Account for in mechanical equipment | Assumption
Matrix Camp | 5392.34 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Batch Plant Building | 3281.62 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Batch Plant Stockpile | 5180.44 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Polishing Waste Stabilization Pond | 4260.3 | m2 | Constructed in 2013 | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Existing Hazardous Waste Berm | 979.44 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Future Hazardous Waste Berm | 1784.35 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Milne Laydown Area | 919780 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Landfarm | 5554.73 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Site Roads | TBD | m (linear) | Catalina to provide. Assume same as in 2014 Marginal Closure Cost | Assumption
Exploration Workshops | 250.24 | m2 | - | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
Exploration Tents | 360 | m2 | Assume six tents (10m x 6m) | Assumption
TOTE ROAD
Q1 Quarry | TBD | m2 | Catalina to provide.
Q7 Quarry | TBD | m2 | Catalina to provide.
Q11 Quarry | TBD | m2 | Catalina to provide.
Q19 Quarry | TBD | m2 | Catalina to provide.
QMR2 Quarry | TBD | m2 | Catalina to provide.
D1Q1 Quarry | TBD | m2 | Catalina to provide.
D1Q2 Quarry | TBD | m2 | Catalina to provide.
P1 Borrow Source | TBD | m2 | Catalina to provide.
Unidentified Borrow Sources | TBD | m2 | Catalina to provide. Based on EBA Report
Culverts | 356 | each | 378 Culverts are identified, but 22 of them will be removed during construction | Tote Road Culvert Sheets: H349000-3000-10-088-0030, H349000-3000-10-088-0031, H349000-3000-10-088-0032, H349000-3000-10-088-0033 and H349000-3000-10-088-0034

## Indirect List (hidden)
Indirect Cost | Unit of Measure | Basis | Unit Rate |  | Hrs days | Days per Week | Rotation
Camp Costs per Day | Mandays | BIM camp contract rate | 110 | 100% x duration | 10 | 7 | 4 week in | 2 weeks out
Flight Cost | Ea | Mary River estimate rate | 120000
Sealift | per voyage | BIM sealift rate | 1680000
Contractor Mob and Demob | Lump Sum | Prorated based on Bim info | 10% of Contract
Temp camp cost once camp has been dissambled | Monthly rental | Contractor T&M Rates | 109551.64 | 100% x 2 x duration
Contractor On-site staff and supervision | Mandays | Estimated size based on direct manpower | 150 / hour assumed ratio of 10:1 |  |  | Add supervision
Together these should be around 15%
Total Mhrs | #REF!
Total Man Days at site | #REF!
Avg Crew Size | 50
Weeks | #REF!
Mths | #REF!
Mths with Camp (75%) | #REF!
Mths without Camp (25%) | #REF!
Man Days with Camp (75%) | #REF!
Man Days withou Camp (25%) | #REF!
Count of Flights | #REF! | Weeks/4 in x 1 with 50 man per flight

## H349000-1000-00-144-0001 - (2) (hidden)
Master Building Matrix
Baffinland Iron Mines: Mary River Project | [38 empty] | Document: H349000-1000-00-144-0001, Rev. 4
H349000
Changes Since Last Issue | Building Location, Number and Name | [9 empty] | Procurement |  | Building Size & Footprint Area | [7 empty] | Building Structure |  |  | Contained Facilities |  |  |  |  | Building Services | [19 empty] | DO NOT PRINT THESE COLUMNS - ONLY FOR IT AND COMMUNICATIONS USE
| FBS Number | Location | Area | Facility | a | a | Sequence Number | Building/Equipment Number | Building Name | Comments | Building Supply Package | Building Installation Contract | No. of Storeys | Occupancy | Width (ft) Out to Out of Cladding | Length (ft) Out to Out of Cladding | Bldg. Ht. (ft) Grade to Ridge | Building Footprint (ft2) | Floor Area (ft2) (All Storeys) | Occupancy Classification | Building Type (See Legend) | Foundation Type (See Legend) | Floor Finish (See Legend) | Offices & Similar Facilities (Furnished) | Washroom(s) | Dining / Lunchrooms / Kitchen (Furnished) | Dormitory Rooms (Furnished) | Special Rooms / Functions (Furnished) | Temperature A:Ambient/Unheated or Temp in deg C | Heating E:Electric, D:Diesel, M:Mobile heaters | Mechanical Ventilation | Air Conditioning | Raw Water T:Tank or P:Piped supply | Potable Water B:Bottled or P:Piped Supply | Sanitary Sewage T:Local tank or P:Pumped and piped | Fire Water Sprinkler System L:Local system or P:Piped service | Other Fire Supression (HP-CO2 etc.) | Addressable Fire Detection & Alarm System | Smoke Alarm (no signal sent) | Electrical Service D:Distribution system, L:Local Genset | Data Service/External Distribution F:Fibre Optic C:Ethernet Cable M: microwave X: Coaxial Cable | IT Connectivity for Construction F:Fibre Optic C:Ethernet Cable M:Local microwave | Satellite TV Service | Estimate ports to be installed by CT-001 | IT cabinets (13U/24U/special size) | Fire detector alarm model | Fire protection | Fire Alarm Drawings LINKs | IT Network |  |  | IT Peripherals |  |  |  | VoIP |  | Other Communication
[49 empty] | TNS | Hatch | BNS | MFD | Laser Printer | Plotter | TV | Handsets | Conference Phones | Sat Phone | Radio | Comments
| 2110 | Milne Port | General | Communication and IT Infrastructure |  |  | 1 | 2110-BLD-001 | Communication Shed |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 2110 | Milne Port | General | Communication and IT Infrastructure |  |  | 2 | 2110-BLD-002 | Satellite Dish Sea Can |  | - |  | 1 | - | 8 | 40 | 10 | [21 empty] | • | L | F | - | - |  | 24U |  |  |  | • | •
| 2223 | Milne Port | Marine | Ore Dock |  |  | 1 | 2223-BLD-001 | Dock Office | Re-use/relocate construction trailer(s) | - | CC005 | 1 |  | 12 | 40 | 8 | 480 | 480 |  | TS | GB | RA | • | • | - | - | - | 22 | E | - | - | T | B | T | - | - | • |  | D | M | - | - | 2 | 13U | tbc |  |  | • |  | • |  | 1 |  | 1 | 3 | 1 | 1 | 1 | Marine radio
| 2342 | Milne Port | Material Handling | Stockpile |  |  | 1 | 2342-BLD-001 | Shiploading E-House |  | PM002 | CC005 | 1 | - | - | - | - | 0 | 0 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | • | - | D | M | - | - | 2 | 13U | Honeywell 120xls |  |  | • | [6 empty] | 1
| 2351 | Milne Port | Material Handling | Ship Loading |  |  | 1 | 2351-SL-001 | Shiploader E-House #1 | Located on Shiploader #1 | PM002 | CC005 | 1 | - | tbd | tbd | tbd | tbd | tbd |  | tbd | tbd | tbd | - | - | - | - | - | [12 empty] | - | - | - |  | tbd | [5 empty] | •
| 2351 | Milne Port | Material Handling | Ship Loading |  |  | 2 | 2351-SL-002 | Shiploader E-House #2 | Located on Shiploader #2 | PM002 | CC005 | 1 | - | tbd | tbd | tbd | tbd | tbd |  | tbd | tbd | tbd | - | - | - | - | - | [12 empty] | - | - | - |  | tbd | [5 empty] | •
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 1 | 2511-BLD-001 | Accommodation Service Core |  | TX001 | CC005 | 1 | - | 60 | 249 | 13 | 14940 | 14940 |  | SM | GB | RA | • | • | • | - | • | 22 | D | • | • | - | P | P | P | • | • | - | D | F / F | M | • | 4 | (by Horizon) | Honeywell 140/120xls |  |  | • | • | • | 3 |  |  | 2 | 3 | 1
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 2 | 2511-BLD-002 | Accommodation Office |  | TX001 | CC005 | 1 | 33 | 60 | 60 | 13 | 3600 | 3600 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 3 | 1 |  | 1/cubicle | 1/conf room |  | 1 | Fixed radio
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 3 | 2511-BLD-003 | Accommodation Laundry |  | TX001 | CC005 | 1 | 5 | 60 | 76 | 13 | 4560 | 4560 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  |  | Honeywell 120xls
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 1 | 2512-BLD-001 | Accommodation Wing BA |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 2 | 2512-BLD-002 | Accommodation Wing BB |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 3 | 2512-BLD-003 | Accommodation Wing BC |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 4 | 2512-BLD-004 | Accommodation Wing BD |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2513 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 1 | 2513-BLD-001 | Emergency Response Office |  | PX001 | CC005 | 1 | 18 | 24 | 40 | 8 | 960 | 960 | D | TM | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | F | M/C | - | 6 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 2 | 1 | 1 | 1 | Fixed radio
| 2513 | Milne Port | Non Process Facilities | Accommodations Area |  |  | 2 | 2513-BLD-002 | Emergency Response Garage |  | PX002 | CC005 | 1 | 5 | 50 | 60 | 20 | 3000 | 3000 | F-3 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F | C | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1 |  |  | 1 | Portable radio
| 2521 | Milne Port | Non Process Facilities | Services Area |  |  | 1 | 2521-BLD-001 | Maintenance Building |  | PX002 | CC005 | 1 | 10 | 60 | 160 | 25 | 9600 | 9600 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | T | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 4 |  |  |  | Needs full detailed dwg
| 2521 | Milne Port | Non Process Facilities | Services Area |  |  | 2 | 2521-BLD-002 | Welding Shop Building |  | PX002 | CC005 | 1 | 5 | 40 | 40 | 25 | 1600 | 1600 | F-2 | FO | PF | SOG | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | - | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1
| 2521 | Milne Port | Non Process Facilities | Services Area |  |  | 3 | 2521-BLD-003 | Workshop Office Building |  | PX001 | CC005 | 1 | 32 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • |  |  | 1 |  |  | 3 |  |  |  | Hatch network MW only
| 2521 | Milne Port | Non Process Facilities | Services Area |  |  | 4 | 2521-BLD-004 | Workshop Office Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 1 | 2530-BLD-001 | Power Generation Module #1 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 2 | 2530-BLD-002 | Power Generation Module #2 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 3 | 2530-BLD-003 | Power Generation Module #3 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 4 | 2530-BLD-004 | Power Generation Module #4 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 5 | 2530-BLD-005 | Power Generation Module #5 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 6 | 2530-BLD-006 | Power Generation Module #6 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 7 | 2530-BLD-007 | Power Generation Module #7 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 8 | 2530-BLD-008 | Power Generation Module #8 | Future Provision | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 9 | 2530-BLD-009 | Power Generation E-House #1 |  | PE001 | CC005 | 1 | - | 18 | 45 | 12 | 810 | 810 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | WCH-06P |  |  |  | • |  | • |  |  |  |  | 1
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 10 | 2530-BLD-010 | Power Generation E-House #2 |  | PE001 | CC005 | 1 | - | 18 | 45 | 12 | 810 | 810 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | tbd |  |  |  | • |  | • |  |  |  |  | 1
| 2530 | Milne Port | Non Process Facilities | Power Generation |  |  | 11 | 2530-BLD-011 | Power Generation Stores |  | PE001 | CC005 | 1 | - | 8 | 40 | 10 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | D | - | - | -
| 2540 | Milne Port | Non Process Facilities | Waste Management |  |  | 1 | 2540-BLD-001 | Waste Management Building |  | PX002 | CC005 | 1 | 2 | 60 | 80 | 20 | 4800 | 4800 | F-1 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2540 | Milne Port | Non Process Facilities | Waste Management |  |  | 2 | 2540-VP-001 | Waste Incinerators | 3 - 20' ISO Containers | TX001 | CC005 | 1 | - | 20 | 28 | 10 | 560 | 560 |  | TM | GB | RA | - | - | - | - | - | 5 | E | [9 empty] | D | C | - | - | [7 empty] | •
| 2613 | Milne Port | Fuel Systems | Fuel Dispensing Module |  |  | 1 | 2613-FD-013 | Diesel Fuel Dispensing Module | Existing | - | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | no scope | [5 empty] | •
| 2613 | Milne Port | Fuel Systems | Fuel Dispensing Module |  |  | 2 | 2613-FD-014 | Diesel Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | 1 panel by vendor FMS | [5 empty] | •
| 2614 | Milne Port | Fuel Systems | Fuel Dispensing Module |  |  | 1 | 2614-FD-011 | Jet-A1 Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | 1 panel by vendor FMS | [5 empty] | •
| 2615 | Milne Port | Fuel Systems | Marine Equipment Facility |  |  | 1 | 2615-BLD-001 | Marine Manifold Building |  | TM001 | CC005 | 1 | - | 17 | 20 | 8 | 340 | 340 |  | FO | PF | RA | - | - | - | - | - | A | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2720 | Milne Port | Spare | Water Systems |  |  | 1 | 2720-BLD-001 | Water Building |  | PX002 | CC005 | 1 | 2 | 60 | 70 | 20 | 4200 | 4200 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | P | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2731 | Milne Port | Spare | Sewage System |  |  | 1 | 2731-BLD-001 | Sewage Chemical Storage Container |  | PM009 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | • | - | D | - | - | - |  |  | ?
| 2731 | Milne Port | Spare | Sewage System |  |  | 5 | 2731-VP-005 | Sewage Treatment Plant |  | PM009 | YX001 | 1 | - | 24 | 80 | 10 | 1920 | 1920 |  | FO: TM; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: •; -: -; -: C; -: -; -: - |  | 13U | [5 empty] | •
| 2732 | Milne Port | Spare | Sewage System |  |  | 1 | 2732-BLD-001 | Sewage Truck Building |  | PX002 | CC005 | 1 | 2 | 20 | 30 | 20 | 600 | 600 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | - | - | P | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2750 | Milne Port | Spare | Power Distribution System |  |  | 1 | 2750-BLD-001 | Accomodation Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | WCH-06P |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  |  | 2 | 2750-BLD-002 | Accomodation Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | WCH-06P |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  |  | 3 | 2750-BLD-003 | Services Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  |  | 4 | 2750-BLD-004 | Services Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  |  | 5 | 2750-BLD-005 | Fuel Tank Farm E-House |  | PE003 | CC005 | 1 | - | - | 25 | - | 25 | 25 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 7231 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 1 | 7231-BLD-001 | Construction Office |  | PX001 | CC005 | 1 | 17 | 48 | 60 | 8 | 2880 | 2880 | D | TM | GB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | - | • | L | M | M | - | 40 | 1 cabinet by vendor |  |  |  | • | • |  | 2 | 2 | 1 | 1 | 1/cubicle | 1 | 1 |  | Need construction input
| 7231 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 2 | 7231-BLD-002 | Aerodrome Office |  | PX001 | CC005 | 1 | 19 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | L | - | M | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • | [8 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 1 | 7232-BLD-001 | Quarry Lunchroom | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  |  |  |  | 0 | 0 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 2 | 7232-BLD-002 | Quarry Washcar | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  |  |  |  | 0 | 0 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 3 | 7232-BLD-003 | Batch Plant Office-Lunchroom-W/C | Also used for sealift offload | PX001 | CC005 | 1 | 13 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | • | - | - | 22 | E | - | - | T | B | T | - | - | - | • | L | - | M | - | 2 | [15 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 5 | 7232-BLD-005 | Fuel Systems Office | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  | 12 | 40 |  | 480 | 480 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 6 | 7232-BLD-006 | Fuel Systems Lunchroom | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  | 12 | 40 |  | 480 | 480 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 7 | 7232-BLD-007 | Site Services Lunchroom #1 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 8 | 7232-BLD-008 | Site Services Lunchroom #2 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 9 | 7232-BLD-009 | Site Services Washcar #1 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 10 | 7232-BLD-010 | Site Services Washcar #2 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 11 | 7232-BLD-011 | Smoke Shack |  | PX001 | CC005 | 1 | 10 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | L | - | - | - | [16 empty] | Need construction input
| 7234 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 1 | 7234-BLD-001 | Toromont Britespan Workshop |  | TMNT |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7234 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 2 | 7234-BLD-002 | Construction Workshop | Existing Coverall bldg in storage at Mine Site | - |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 1 | 7235-BLD-001 | Construction Equipment Building | Existing on-site. | YX001 | - | 1 |  | 40 | 60 |  | 2400 | 2400 |  | FO: FA; PF: PF; RA: G; -: - | [16 empty] | Need construction input
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 2 | 7235-BLD-002 | Site Services Heated Warehouse |  | PX004 | CC005 | 1 | 5 | 40 | 100 | 25 | 4000 | 4000 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | D | - | M | - | 2 | [15 empty] | Need construction input
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  |  | 3 | 7235-BLD-003 | Site Services Unheated Warehouse |  | PX004 | CC005 | 1 | 2 | 40 | 100 | 25 | 4000 | 4000 | F-3 | FO | PF | G | - | - | - | - | - | A | - | - | - | - | - | - | - | - | - | • | D | - | - | - | [16 empty] | Need construction input
| 7251 | Construction | Milne Port | Construction Facilities |  |  | 1 | 7251-BLD-001 | Concrete Batch Plant Building |  | PX004 | CC005 | 1 | 5 | 60 | 120 | 20 | 7200 | 7200 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 3111 | Tote Road | General | Communication and IT Infrastructure |  |  | 1 | 3111-BLD-001 | Communication Shed No. 1 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3111 | Tote Road | General | Communication and IT Infrastructure |  |  | 2 | 3111-BLD-002 | Communication Shed No. 2 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 3111 | Tote Road | General | Communication and IT Infrastructure |  |  | 3 | 3111-BLD-003 | Communication Shed No. 3 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 3111 | Tote Road | General | Communication and IT Infrastructure |  |  | 4 | 3111-BLD-004 | Communication Shed No. 4 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  |  | 1 | 3112-BLD-001 | Communication Shed No. 5 | Existing tower | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  |  | 2 | 3112-BLD-002 | Communication Shed No. 6 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  |  | 3 | 3112-BLD-003 | Communication Shed No. 7 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  |  | 4 | 3112-BLD-004 | Communication Shed No. 8 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  |  | 1 | 3113-BLD-001 | Communication Shed No. 9 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  |  | 2 | 3113-BLD-002 | Communication Shed No. 10 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  |  | 3 | 3113-BLD-003 | Communication Shed No. 11 | Existing tower. With emergency shelter. | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3160 | Tote Road | General | Emergency Shelters |  |  | 1 | 3160-BLD-001 | Emergency Shelter No. 1 | Located at Comms Shed No. 4 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  |  | 2 | 3160-BLD-002 | Emergency Shelter No. 2 | Located at Comms Shed No. 6 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  |  | 3 | 3160-BLD-003 | Emergency Shelter No. 3 | Located at Comms Shed No. 9 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  |  | 4 | 3160-BLD-004 | Emergency Shelter No. 4 | Located at Comms Shed No. 11 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 4110 | Mine Site | General | Communication and IT Infrastructure |  |  | 1 | 4110-BLD-001 | Communication Shed No. 1 | Front of mountain | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1 | check fire code
| 4110 | Mine Site | General | Communication and IT Infrastructure |  |  | 2 | 4110-BLD-002 | Communication Shed No. 2 | Back of mountain - on haul road | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 4110 | Milne Port | General | Communication and IT Infrastructure |  |  | 3 | 4110-BLD-003 | Satellite Dish Sea Can |  | - |  | 1 | - | 8 | 40 | 10 |  |  |  | -: •; -: L; -: F; -: -; -: -
| 4211 | Mine Site | Mine | Explosives Facility |  |  | 1 | 4211-BLD-001 | Explosives Plant Building |  | SX001 | CC005 | 1 | - | 40 | 92 | 10 | 3680 | 3680 |  | FO: TM; PF: GB; RA: RA; -: L; -: M; -: M; -: - | 2 | 13U |  |  |  | • | [9 empty] | 1 | check fire code
| 4212 | Mine Site | Mine | Explosives Facility |  |  | 1 | 4212-BLD-001 | Explosives Shop |  | SX001 | CC005 | 1 | - | 40 | 100 | 18 | 4000 | 4000 |  | FO: FO; PF: GB; RA: SOGD; -: L; -: -; -: -; -: - | [15 empty] | 1
| 4213 | Mine Site | Mine | Explosives Facility |  |  | 1 | 4213-BLD-001 | Explosives Magazines |  | SX001 | CC005 | 1 | - | 12 | 30 | 10 | 360 | 360 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: -; -: -
| 4281 | Mine Site | Mine | Mine Support Facilities |  |  | 1 | 4281-BLD-001 | Pit Office Building |  | PX001 | CC005 | 1 | 28 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • | [5 empty] | 1 |  |  | 1
| 4281 | Mine Site | Mine | Mine Support Facilities |  |  | 2 | 4281-BLD-002 | Pit Office Washcar | Relocate 7432-BLD-008 | PX001 | CC005 | 1 | 9 | 12 | 40 | 8 | 480 | 480 | F-3 | TS | GB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
• | 4381 | Mine Site | Material Handling | Power Distribution System |  |  | 1 | 4381-BLD-001 | Crushing & Screening Electrical Trailer |  | PM001 | 1 | 1 | - | 8 | 53 | 14 | 424 | 424 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | ? | ? | ? | D | C | - | - | 2 | tbd | [5 empty] | •
• | 4381 | Mine Site | Material Handling | Power Distribution System |  |  | 2 | 4381-BLD-002 | Crushing & Screening Electrical Trailer |  | PM001 | CC005 | 1 | - | 8 | 53 | 14 | 424 | 424 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | ? | ? | ? | D | C | - | - | 2 | tbd | [5 empty] | •
• | 4382 | Mine Site | Material Handling | Crushing and Screening |  |  | 1 | 4382-BLD-001 | Truck Weigh Building |  | PX004 | CC005 | 1 | 1 | 30 | 120 | 20 | 3600 | 3600 | F-3 | FO | PF | G | - | - | - | - | - | - | - | • | - | - | - | - | - | - |  | - | D | F | - | - | 8 | 24U | n/a - discuss with BIM |  |  | • |  | •
| 4431 | Mine Site | Aerodrome | Aerodrome Facilities |  |  | 1 | 4431-BLD-001 | Aerodrome Office |  | PX001 | CC005 | 1 | 19 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | M | M | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 1 |  |  | 1 | fixed radio
| 4432 | Mine Site | Aerodrome | Aerodrome Facilities |  |  | 1 | 4432-BLD-001 | Aerodrome Equipment Building | HOLD - delete or re-use constr'n bldg | - | CC005 | [5 empty] | 0 | 0 | bar: - to -
| 4435 | Mine Site | Aerodrome | Aerodrome Facilities |  |  | 1 | 4435-BLD-001 | Aerodrome Field Electrical Centre |  | PE004 | CC005 | 1 | - | 8 | 20 | 10 | 160 | 160 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | • | - | D | F | - | - | 2 | tbd |  |  |  | • |  | • |  |  |  |  | 1 |  |  |  | waiting for harvie
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 1 | 4511-BLD-001 | Accommodation Service Core |  | TX001 | CC005 | 1 | - | 60 | 333 | 13 | 19980 | 19980 |  | SM | GB | RA | • | • | • | - | • | 22 | D | • | • | - | P | P | P | • | • | - | D | F/F | M | • | 4 | (by Horizon) | Honeywell 140/120xls |  |  | • | • | • | 3 |  |  | 2 | 3 | 1
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 2 | 4511-BLD-002 | Accommodation Office |  | TX001 | CC005 | 1 | 71 | 60 | 109 | 13 | 6540 | 6540 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 3 | 1 |  | 1/cubicle | 1/conf room |  | 1 | Fixed radio
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 3 | 4511-BLD-003 | Accommodation Laundry |  | TX001 | CC005 | 1 | 5 | 60 | 76 | 13 | 4560 | 4560 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  |  | Honeywell 120xls
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 4 | 4511-BLD-004 | Accommodation Laboratory |  | TX001 | CC005 | 1 | 5 | 56 | 60 | 13 | 3360 | 3360 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  | 24U | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 2
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 1 | 4512-BLD-001 | Accommodation Wing AA |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 2 | 4512-BLD-002 | Accommodation Wing AB |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 3 | 4512-BLD-003 | Accommodation Wing AC |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 4 | 4512-BLD-004 | Accommodation Wing AD |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 5 | 4512-BLD-005 | Accommodation Wing AE |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 6 | 4512-BLD-006 | Accommodation Wing AF |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 7 | 4512-BLD-007 | Accommodation Wing AG |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4513 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 1 | 4513-BLD-001 | Emergency Response Office |  | PX001 | CC005 | 1 | 18 | 24 | 40 | 8 | 960 | 960 | D | TM | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | F | M/C | - | 6 | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 2 | 1 | 1 | 1 | Fixed radio
| 4513 | Mine Site | Non Process Facilities | Accommodations Area |  |  | 2 | 4513-BLD-002 | Emergency Response Garage |  | PX002 | CC005 | 1 | 5 | 50 | 60 | 20 | 3000 | 3000 | F-3 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F | C | - | 4 | (by Horizon) | Honeywell 120xls |  |  | • | [6 empty] | 1 |  |  | 1 | Portable radio
| 4521 | Mine Site | Non Process Facilities | Services Area |  |  | 1 | 4521-BLD-001 | Maintenance Building |  | PX004 | CC005 | 1 | 20 | 100 | 260 | 35 | 26000 | 26000 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | T | - | - | - | - | • | - | D | F | M | - | 4 | 13U | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 2
| 4521 | Mine Site | Non Process Facilities | Services Area |  |  | 2 | 4521-BLD-002 | Warehouse |  | PX004 | CC005 | 1 | 5 | 60 | 160 | 25 | 9600 | 9600 | F-3 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | M | - | 4 | 13U | Honeywell 120xls |  |  | • | [6 empty] | 1
| 4521 | Mine Site | Non Process Facilities | Services Area |  |  | 3 | 4521-BLD-003 | Welding Shop Building |  | PX002 | CC005 | 1 | 5 | 60 | 70 | 25 | 4200 | 4200 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1
| 4521 | Mine Site | Non Process Facilities | Services Area |  |  | 4 | 4521-BLD-004 | Workshop Office Building |  | PX001 | CC005 | 1 | 31 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • |  |  | 1 |  |  | 3
| 4521 | Mine Site | Non Process Facilities | Services Area |  |  | 5 | 4521-BLD-005 | Workshop Office Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
| 4523 | Mine Site | Non Process Facilities | Services Area |  |  | 1 | 4523-BLD-001 | Truck Wash Building |  | PX004 | CC005 | 1 | 2 | 60 | 180 | 25 | 10800 | 10800 | F-3 | FO | PF | G | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - |  | - | D | F | - | - | 2 |  | n/a - discussed with BIM
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 1 | 4530-BLD-001 | Power Generation Module #1 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 2 | 4530-BLD-002 | Power Generation Module #2 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 3 | 4530-BLD-003 | Power Generation Module #3 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 4 | 4530-BLD-004 | Power Generation Module #4 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 5 | 4530-BLD-005 | Power Generation Module #5 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 6 | 4530-BLD-006 | Power Generation Module #6 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 7 | 4530-BLD-007 | Power Generation E-House #1 |  | PE001 | CC005 | 1 | - | 16 | 45 | 10 | 720 | 720 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | WCH-06P |  |  |  | • |  | • |  |  |  |  | 1
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 8 | 4530-BLD-008 | Power Generation E-House #2 |  | PE001 | CC005 | 1 | - | 16 | 45 | 10 | 720 | 720 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 |  |  |  |  | • |  | • |  |  |  |  | 1
| 4530 | Mine Site | Non Process Facilities | Power Generation |  |  | 9 | 4530-BLD-009 | Power Generation Stores |  | PE001 | CC005 | 1 | - | 8 | 40 | 10 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | D | - | - | -
| 4540 | Mine Site | Non Process Facilities | Waste Management |  |  | 1 | 4540-BLD-001 | Waste Management Building |  | PX002 | CC005 | 1 | 2 | 60 | 80 | 20 | 4800 | 4800 | F-1 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F/C | - | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4540 | Mine Site | Non Process Facilities | Waste Management |  |  | 2 | 4540-VP-001 | Waste Incinerators | 3 - 20' ISO Containers | TX001 | CC005 | 1 | - | 20 | 28 | 10 | 560 | 560 |  | TM | GB | RA | - | - | - | - | - | 5 | E | [9 empty] | D | C | - | - | [7 empty] | •
| 4613 | Mine Site | Fuel Systems | Fuel Dispensing Module |  |  | 1 | 4613-FD-013 | Diesel Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | FO: SC; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: F; -: -; -: - | 2 | [6 empty] | •
| 4712 | Mine Site | Site Utilities | Raw Water Intake |  |  | 1 | 4712-BLD-001 | Raw Water Pumphouse |  | PM003 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | • | - | D | M | - | - |  | 13U |  |  |  | • |  | • |  |  |  |  | 1
| 4720 | Mine Site | Site Utilities | Water Systems |  |  | 1 | 4720-BLD-001 | Water Building |  | PX002 | CC005 | 1 | 2 | 60 | 70 | 20 | 4200 | 4200 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | P | - | - | - | - | • | - | D | F | M | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4731 | Mine Site | Site Utilities | Sewage System |  |  | 1 | 4731-BLD-001 | Sewage Chemical Storage Container |  | PM009 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | • | - | D | - | - | - |  |  | tbc
| 4731 | Mine Site | Site Utilities | Sewage System |  |  | 5 | 4731-VP-005 | Sewage Treatment Plant |  | PM009 | CC005 | 1 | - | 24 | 80 | 10 | 1920 | 1920 |  | FO: TM; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: •; -: -; -: C; -: - | [7 empty] | •
| 4732 | Mine Site | Site Utilities | Sewage System |  |  | 1 | 4732-BLD-001 | Sewage Truck Building |  | PX002 | CC005 | 1 | 2 | 20 | 30 | 20 | 600 | 600 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | - | - | P | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 1 | 4750-BLD-001 | Accomodation Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 2 | 4750-BLD-002 | Accomodation Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 3 | 4750-BLD-003 | Services Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 4 | 4750-BLD-004 | Services Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 5 | 4750-BLD-005 | Fuel Tank Farm E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 6 | 4750-BLD-006 | Aerodrome Area E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | - | - | - | [12 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 7 | 4750-BLD-007 | Raw Water Supply E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | - | - | - | [12 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  |  | 8 | 4750-BLD-008 | Crushing & Screening E-House |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1 |  |  |  | Mineral Processing E-House
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 1 | 7432-BLD-001 | Batch Plant Office-Lunchroom-W/C |  | PX001 | CC005 | 1 | 13 | 12 | 60 | 8 | 720 | 720 | A-2/D | TS | CB | RA | • | • | • | - | - | 22 | E | - | - | T | B | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 3 | 7432-BLD-003 | Fuel Systems Lunchroom |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 4 | 7432-BLD-004 | Fuel Systems Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 5 | 7432-BLD-005 | Site Services Lunchroom #1 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 6 | 7432-BLD-006 | Site Services Lunchroom #2 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 7 | 7432-BLD-007 | Site Services Washcar #1 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 8 | 7432-BLD-008 | Site Services Washcar #2 | Relocate to 4281-BLD-002 | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | -
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 9 | 7432-BLD-009 | Smoke Shack |  | PX001 | CC005 | 1 | 10 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | L | - | - | - | [16 empty] | Need construction input
| 7434 | Construction | Mine Site | Buildings, Shops & Warehouses |  |  | 1 | 7434-BLD-001 | Toromont Britespan Workshop |  | TMNT |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7451 | Construction | Mine Site | Construction Facilities |  |  | 1 | 7451-BLD-001 | Concrete Batch Plant Building |  | PX004 | CC005 | 1 | 5 | 60 | 120 | 20 | 7200 | 7200 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
288
[13 empty] | NOTES | [7 empty] | RA: BUILDING TYPE; -: FOUNDATION TYPE; -: FLOOR FINISH
|  |  | 4 | In progress | [8 empty] | 1. Occupancy for washcars is number of male water closets/urinals. Ratio of male to female water closets is 5:1. | [7 empty] | RA: FO; -: Fold-away Building (Steel); -: GB; -: Gravel Base - Skidded Building; -: SOG; -: Slab on grade
| 03/09/2013 |  | 3 | Approved for Use | S. Carnegie |  | J. Cleland |  | S. Perry | D. Matthews |  |  | 2. Buiding supply package "TMNT" is Toromont CAT supply arranged by Baffinland. | [7 empty] | RA: FA; -: Fabric w/ Sea Can Walls; -: PP; -: Precast Piers; -: SOGD; -: Slab on grade C/W Drainage
| 22/07/2013 |  | 2 | Approved for Use | K. Imai |  | J. Cleland |  | S. Perry | D. Matthews | [10 empty] | RA: SC; -: ISO Shipping Contianer; -: PF; -: Precast Footing (Perimeter Beam); -: G; -: Gravel
| 10/07/2013 |  | 1 | Approved for Use | K. Imai |  | J. Cleland |  | S. Perry | D. Matthews | [10 empty] | RA: TS; -: Trailer - Single; -: CB; -: Timber Cribbing to Elevate Building; -: RA; -: Raised Steel or Wooden Floor
| 10/04/2013 |  | 0 | Approved for Use | K. Imai |  | J. Lemay |  | S. Perry | D. Matthews | [10 empty] | RA: TM; -: Trailer - Modular (2 or more modules); -: -; -: Not Applicable
| Date |  | Rev | Status | Prepared By |  | Checked By |  | Approved By | Approved By | [10 empty] | RA: SM; -: Special Modular / Prefabricated

## Quantities (hidden)
Tab in Reclaim | Project Location | Reclaim Objective | Activity | Unit Cost |  | Quantities |  | Total Cost ($)
|  |  |  | Value | Unit ($/FU) | 2013 Marginal | 2014 Work plan | 2013 Marginal | 2014 Work plan
Open Pit | Mine Site | CONTROL ACCESS | Fence | 12 | m | - | 643.7 | - | 7724.4
Open Pit | Mine Site | CONTROL ACCESS | Signs | 35.64 | m | - | 2 | - | 71.28
Open Pit | Mine Site | COVER/CONTOUR SLOPES | Place overburden over demolition material | 10.098 | m3 | 33546 | - | 338747.508 | -
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry Q1 | 2.6193 | m2 | - | 92000 | - | 240975.6
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry QMR2 | 2.6193 | m2 | - | 70000 | - | 183351
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry Q7 | 2.6193 | m2 | - | 14600 | - | 38241.78
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry Q11 | 2.6193 | m2 | - | 17500 | - | 45837.75
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry P1 | 2.6193 | m2 | - | 55000 | - | 144061.5
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry Q19 | 2.6193 | m2 | - | 14600 | - | 38241.78
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry D1Q1 | 2.6193 | m2 | - | 27500 | - | 72030.75
Open Pit | Mine Site | RECLAIM QUARRIES | Quarry D1Q2 | 2.6193 | m2 | - | 22500 | - | 58934.25
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate tanks & plumbing | 200 | m2 | - | 132 | - | 26400
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate water treatment plant | 200 | m2 | - | 669 | - | 133800
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate maintenance shop | 200 | m2 | - | 5238 | - | 1047600
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate power plant | 200 | m2 | 30 | 787 | 6000 | 157400
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate bulk fuel storage | 200 | m2 | 2221.5 | - | 444300 | -
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Decontaminate ANFO plant | 200 | m2 | - | 747 | - | 149400
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Other (Waste facilities) | 200 | m2 | - | 498 | - | 99600
Bldgs & Equip | Mine Site | REMOVE CONTAMINATED BUILDINGS | Other (Credit for 2013 contaminated buildings) | -1 | m2 | - | 6000 | - | -6000
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Decontaminate tanks & plumbing | 200 | m2 | - | 91 | - | 18200
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Decontaminate water treatment plant | 200 | m2 | - | 654 | - | 130800
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Decontaminate maintenance shop | 200 | m2 | 268 | 2024 | 53600 | 404800
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Decontaminate power plant | 200 | m2 | 134 | 739 | 26800 | 147800
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Decontaminate bulk fuel storage (Fuel Tank) | 200 | m2 | 16774.5703 | 937.5 | 3354914.0625 | 187500
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Other (Waste facilities) | 200 | m2 | - | 446 | - | 89200
Bldgs & Equip | Milne | REMOVE CONTAMINATED BUILDINGS | Other (Credit for 2013 contaminated buildings) | -1 | m2 | - | 80400 | - | -80400
Bldgs & Equip | Mine Site | REMOVE NON-CONTAMINATED BUILDINGS | water treatment plant | 57.024 | m2 | 557 | - | 31762.368 | -
Bldgs & Equip | Mine Site | REMOVE NON-CONTAMINATED BUILDINGS | offices/warehouse/accom | 57.024 | m2 | 11229 | 17165 | 640322.496 | 978816.96
Bldgs & Equip | Mine Site | REMOVE NON-CONTAMINATED BUILDINGS | consolidate & dump boneyard debris | 57.024 | m2 | 334 | - | 19046.016 | -
Bldgs & Equip | Mine Site | REMOVE NON-CONTAMINATED BUILDINGS | other (Airstrip Extension ) | 57.024 | m2 | 2500 | - | 142560 | -
Bldgs & Equip | Mine Site | REMOVE NON-CONTAMINATED BUILDINGS | Other (Credit for 2013 non-contaminated buildings) | -1 | m2 | - | 691631 | - | -691631
Bldgs & Equip | Milne | REMOVE NON-CONTAMINATED BUILDINGS | offices/warehouse/accom | 57.024 | m2 | 9297 | 16556 | 530152.128 | 944089.344
Bldgs & Equip | Milne | REMOVE NON-CONTAMINATED BUILDINGS | consolidate & dump boneyard debris | 57.024 | m2 | 334 | 52 | 19046.016 | 2965.248
Bldgs & Equip | Milne | REMOVE NON-CONTAMINATED BUILDINGS | water treatment plant | 57.024 | m2 | 446 | - | 25432.704 | -
Bldgs & Equip | Milne | REMOVE NON-CONTAMINATED BUILDINGS | other (Airstrip Extension ) | 57.024 | m2 | 2500 | - | 142560 | -
Bldgs & Equip | Milne | REMOVE NON-CONTAMINATED BUILDINGS | Other (Credit for 2013 non-contaminated buildings) | -1 | m2 | - | 574631 | - | -574631
Bldgs & Equip | Tote Road | REMOVE NON-CONTAMINATED BUILDINGS | offices/warehouse/accom | 57.024 | m2 | 1522 | - | 86790.528 | -
Bldgs & Equip | Tote Road | REMOVE NON-CONTAMINATED BUILDINGS | Other (Credit for 2013 non-contaminated buildings) | -1 | m2 | - | 86791 | - | -86791
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | water treatment plant | 26.73 | m2 | 557 | 446 | 14888.61 | 11921.58
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | maintenance shop | 26.73 | m2 | 1427 | 5091 | 38143.71 | 136082.43
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | power plant | 26.73 | m2 | 30 | - | 801.9 | -
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | bulk fuel storage | 26.73 | m2 | 2221.5 | - | 59380.695 | -
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | offices/warehouse/accom | 26.73 | m2 | 11229 | 892 | 300151.17 | 23843.16
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | Other (Waste facilities) | 26.73 | m2 | 2834 | 446 | 75752.82 | 11921.58
Bldgs & Equip | Mine Site | BREAK BASEMENT SLABS | Other (Credit for 2013 break Basement Slabs) | -1 | m2 | - | 362114 | - | -362114
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | tanks & plumbing | 26.73 | m2 | - | 32 | - | 855.36
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | water treatment plant | 26.73 | m2 | 446 | 446 | 11921.58 | 11921.58
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | maintenance shop | 26.73 | m2 | 268 | 1988 | 7163.64 | 53139.24
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | power plant | 26.73 | m2 | 134 | - | 3581.82 | -
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | bulk fuel storage | 26.73 | m2 | 16774.5703 | - | 448384.2645 | -
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | offices/warehouse/accom | 26.73 | m2 | 9297 | 966 | 248508.81 | 25821.18
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | Other (Waste facilities) | 26.73 | m2 | 2834 | 446 | 75752.82 | 11921.58
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | offices/warehouse/accom | 26.73 | m2 | 1522 | - | 40683.06 | -
Bldgs & Equip | Milne | BREAK BASEMENT SLABS | Other (Credit for 2013 break Basement Slabs) | -1 | m2 | - | 280105 | - | -280105
Bldgs & Equip | Tote Road | BREAK BASEMENT SLABS | Other (Credit for 2013 break Basement Slabs) | -1 | m2 | - | 40683 | - | -40683
Bldgs & Equip | Mine Site | LANDFILL FOR DEMOLITION WASTE | Place soil cover | 15.12 | m3 | - | 37854 | - | 572352.48
Bldgs & Equip | Mine Site | LANDFILL FOR DEMOLITION WASTE | Other (Credit for 2013 landfill for demolition waste) | -1 | m2 | - | 187724 | - | -187724
Bldgs & Equip | Milne | LANDFILL FOR DEMOLITION WASTE | Place soil cover | 15.12 | m3 | - | 30843 | - | 466346.16
Bldgs & Equip | Milne | LANDFILL FOR DEMOLITION WASTE | Other (Credit for 2013 landfill for demolition waste) | -1 | m2 | - | 151091 | - | -151091
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | tanks & plumbing | 2.6193 | m2 | - | 132 | - | 345.7476
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | water treatment plant | 2.6193 | m2 | - | 669 | - | 1752.3117
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | maintenance shop | 2.6193 | m2 | - | 5238 | - | 13719.8934
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | power plant | 2.6193 | m2 | - | 787 | - | 2061.3891
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | ANFO plant | 2.6193 | m2 | - | 747 | - | 1956.6171
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | offices/warehouse/accom | 2.6193 | m2 | - | 17165 | - | 44960.2845
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | Other (Waste facilities) | 2.6193 | m2 | - | 498 | - | 1304.4114
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | Other (Ore Stockpile Pad + Dump Pad + Crusher Pad) | 2.6193 | m2 | - | 167602 | - | 438999.9186
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | water treatment plant | 9.666 | m2 | 557 | - | 5383.962 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | maintenance shop | 9.666 | m2 | 1427 | - | 13793.382 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | power plant | 9.666 | m2 | 30 | - | 289.98 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | bulk fuel storage | 9.666 | m2 | 2221.5 | - | 21473.019 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | offices/warehouse/accom | 9.666 | m2 | 11229 | - | 108539.514 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | other | 9.666 | m2 | 2834 | - | 27393.444 | -
Bldgs & Equip | Mine Site | GRADE AND CONTOUR MILL & PLANT SITE | Other (Credit for 2013 grade and countour) | -1 | m2 | - | 131235 | - | -131235
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | tanks & plumbing | 2.6193 | m2 | - | 91 | - | 238.3563
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | water treatment plant | 2.6193 | m2 | - | 654 | - | 1713.0222
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | maintenance shop | 2.6193 | m2 | - | 2024 | - | 5301.4632
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | power plant | 2.6193 | m2 | - | 739 | - | 1935.6627
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | offices/warehouse/accom | 2.6193 | m2 | - | 16556 | - | 43365.1308
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | Consolidate & dump boneyard debris | 2.6193 | m2 | - | 52 | - | 136.2036
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | Other (waste Facilities) | 2.6193 | m3 | - | 446 | - | 1168.2078
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | Other (Ore Stockpile Pad) | 2.6193 | m2 | - | 235241 | - | 616166.7513
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | water treatment plant | 9.666 | m2 | 446 | - | 4311.036 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | maintenance shop | 9.666 | m2 | 268 | - | 2590.488 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | power plant | 9.666 | m2 | 134 | - | 1295.244 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | bulk fuel storage | 9.666 | m2 | 16774.5703 | - | 162142.9966 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | offices/warehouse/accom | 9.666 | m2 | 9297 | - | 89864.802 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | other | 9.666 | m2 | 2834 | - | 27393.444 | -
Bldgs & Equip | Milne | GRADE AND CONTOUR MILL & PLANT SITE | Other (Credit for 2013 grade and countour) | -1 | m2 | - | 101289 | - | -101289
Bldgs & Equip | Mine Site | RECLAIM ROADS | Remove culverts | 1785 | each | - | 14 | - | 24990
Bldgs & Equip | Mine Site | RECLAIM ROADS | Other (roads) | 2.6193 | m2 | - | 148480 | - | 388913.664
Bldgs & Equip | Mine Site | RECLAIM ROADS | Scarify and install water breaks (Laydown Area) | 1000 | ha | 35.48 | - | 35480 | -
Bldgs & Equip | Mine Site | RECLAIM ROADS | other (Laydown Area) | 1000 | ha | 6.07 | - | 6070 | -
Bldgs & Equip | Milne | RECLAIM ROADS | Remove culverts | 1785 | each | - | 13 | - | 23205
Bldgs & Equip | Milne | RECLAIM ROADS | other (Ramp to the Beach) | 2.6193 | m2 | - | 5177 | - | 13560.1161
Bldgs & Equip | Milne | RECLAIM ROADS | Other (roads) | 2.6193 | m2 | - | 9720 | - | 25459.596
Bldgs & Equip | Milne | RECLAIM ROADS | other (Laydown Area) | 1000 | ha | 8.09 | - | 8090 | -
Bldgs & Equip | Tote Road | RECLAIM ROADS | Remove culverts | 1785 | each | - | 35 | - | 62475
Bldgs & Equip | Mine Site | SPECIALIZED ITEMS | Disposal of Mobile Equipment | 650 | Each | - | 372 | - | 241800
Bldgs & Equip | Milne | SPECIALIZED ITEMS | Remove Mooring Buoys | 14708 | each | - | 2 | - | 29416
Bldgs & Equip | Milne | SPECIALIZED ITEMS | Decommission of existing bladder farm | -1 | m2 | - | 243984 | - | -243984
Chemicals | General | HAZARDOUS MATERIALS TO BE CONSOLIDATED FOR REMOVAL | Waste oils | 2.214 | litre | 23162.5 | - | 51281.775 | -
Chemicals | General | HAZARDOUS MATERIALS TO BE CONSOLIDATED FOR REMOVAL | Fuel - Type 1, eg diesel dregs | 0.1 | litre | 27712201 | 537462 | 2771220.1 | 53746.2
Chemicals | General | HAZARDOUS MATERIALS TO BE CONSOLIDATED FOR REMOVAL | waste batteries | 2.214 | kg | 1820 | - | 4029.48 | -
Chemicals | General | HAZARDOUS MATERIALS TO BE CONSOLIDATED FOR REMOVAL | assay & environmental lab reagents | 2.214 | kg | 10450 | - | 23136.3 | -
Chemicals | General | HAZARDOUS MATERIALS TO BE CONSOLIDATED FOR REMOVAL | machine shop, paints, solvents etc | 2.214 | kg | 4800 | - | 10627.2 | -
Chemicals | General | OTHER | Calcium Chloride | 0.378 | kg | - | 1447683.7 | - | 547224.4386
Chemicals | General | OTHER | Ammonium Nitrate | -1 | m2 | - | 1895057 | - | -1895057
Chemicals | General | OTHER | Calcium Chloride | 2.376 | kg | 920000 | - | 2185920 | -
Water | General | WATER SUPPLY EMBANKMENT | Other (Pond) | 300.5 | m3 | 70 | - | 21035 | -
Water | General | REMOVE PIPELINES | Remove pipes | 5.4 | m | 8200 | - | 44280 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Other (Mobilize Heavy Equipment) | 9.0936 | km | - | 14000 | - | 127310.4
Mobilization | Milne | SPECIALIZED ITEMS | Other (Credit for mobilize 2013 heavy equipment) | -1 | m2 | - | 173688 | - | -173688
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Excavators | 9.0936 | km | 500 | - | 4546.8 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Dump trucks | 9.0936 | km | 200 | - | 1818.72 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Dozers | 9.0936 | km | 500 | - | 4546.8 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Crane | 9.0936 | km | 300 | - | 2728.08 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Light duty vehicles | 9.0936 | km | 5100 | - | 46377.36 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Other (loaders) | 9.0936 | km | 1800 | - | 16368.48 | -
Mobilization | General | MOBILIZE HEAVY EQUIPMENT | Other | 9.0936 | km | 10700 | - | 97301.52 | -
Mobilization | General | MOBILIZE WORKERS | crew transportation | 2300 | each | 53 | - | 121900 | -
Mobilization | General | MOBILIZE MISC. SUPPLIES | Sealift per season | 115 | tonne | - | 2348.75 | - | 270106.25
Mobilization | General | MOBILIZE MISC. SUPPLIES | Sealift per season | 1 | lot | 3000000 | - | 3000000 | -
Mobilization | Milne | SPECIALIZED ITEMS | Other (Credit for 2013 Sealift) | -1 | m2 | - | 3000000 | - | -3000000
Mobilization | General | MOBILIZE MISC. SUPPLIES | Sealift per season (contingency) | 115 | tonne | - | 8700 | - | 1000500
[8 empty] | 16108377.6526 | 2651377.008

## Project component checklist (hidden)
Major Work Element | Milne Port Site | Tote Road | MR Mine Site
PERMANENT FACILITIES
Communications and IT Infrastructure
Site Development
Process and Non-process Areas
Road Construction | ü
Road Upgrade
Road Bridges
Aerodrome Facilities |  |  | ü
Non-process Facilities
Accommodations | ü |  | ü
Services Buildings | ü |  | ü
Power Generation | ü |  | ü
Waste Management Facility | ü |  | ü
Landfill and Land Farm | ü
Fuel Systems | ü |  | ü
Fuel Pipelines | ü |  | ü
Tank Farms | ü |  | ü
Process and Control Systems
Mine Explosives Facilities |  |  | ü
Mine Support Facilities | ü |  | ü
Material Handling | ü |  | ü
Crushing Systems |  |  | ü
Overland Conveyors | ü
Stockpile, Stacker/Reclaimer | ü
Ship Loading | ü
Site Utilities | ü |  | ü
Water Systems | ü |  | ü
Sewage System | ü |  | ü
Power Distribution | ü |  | ü
Marine | ü
Beach Landing Area
Mooring Buoys | ü
Ore Dock and Buildings | ü
Construction Infrastructure | ü |  | ü
Site Development | ü |  | ü
Beach Landing and Push-outs | ü
Laydown Areas | ü |  | ü
Construction Facilities Site Prep | ü |  | ü
Temporary Airstrips – Ice strip? |  |  | ü
Roads and Drainage | ü |  | ü
Quarries and Borrow Pits | ü | ü | ü
Accommodation and Facilities | ü |  | ü
Shops and Warehousing | ü |  | ü
Concrete Batch Plant | ü |  | ü
Explosives Plant |  |  | ü
Explosives Magazines |  |  | ü
MAJOR CONTRACT TYPE OR SERVICE | Milne Port Site | Tote Road | MR Mine Site
SITE CAPTURE 2013 to 2014 | ü |  | ü
Site Services Contractors (summer 2013) | ü |  | ü
Materials Management (includes Canadian Consolidation Hub) | ü |  | ü
Early Site Development (including Roads and Laydown) | ü |  | ü
Install Construction Facilities | ü |  | ü
Install Construction Fuel Power and Utilities | ü |  | ü
Aerodrome (including Temporary Airstrips) |  |  | ü
Camp Catering Service | ü |  | ü
Site Erected Tanks Phase 1 | ü |  | ü
Site Erected Tanks Phase 2 | ü
Construction Explosives Plant |  |  | ü
Construction Fuel Supply
Telecommunications
Geotechnical
Sealift Transportation to Site | ü
Iqaluit Jet Service (Canadian Hub to Iqaluit only) |  |  | ü
Local Air Charter Service
Medical and Emergency Response Service | ü |  | ü
Security Service
Earthworks | ü |  | ü
Foundations | ü | ü | ü
Waste Management Facilities
Process and Control Systems
Mine Support Facilities
Primary and Secondary Crushing
Stockpile, Stacker/Reclaimer | ü
Ship Loader | ü
Water Systems | ü |  | ü
Sewage System | ü |  | ü
Power Distribution | ü |  | ü
Supply, Fabricate and Install Structural Steel | ü |  | ü
Mine Production Explosives and Emulsion Plant BOO |  |  | ü
Permanent Accommodations Design Build | ü |  | ü
Site Erected Buildings Design-Build | ü |  | ü
Power Plants | ü |  | ü
Construction Fuel Supply and Delivery
Construction Camps BOO | ü
EPCM Site Survey Services | ü |  | ü
Off Site Waste Disposal

## Labour Rate (hidden)
|  |  | M | T | W | Th | F | S | Sun
|  | Regular | 8 | 8 | 8 | 8 | 8
|  | Overtime | 4 | 4 | 4 | 4 | 4 | 12 | 12
|  | Total Hours | 84
|  | Regular | 40
|  | OT | 44
Average Rate
|  |  | Contractor #1 | 69
|  |  | Contractor #2 | 96.4819
|  |  | Contractor #3 | 110.9984
|  |  | Contractor #4 | 108
|  |  | Contractor #5 | 85
|  |  | Contractor #6 | 130
|  |  | Average | 99.9134
100
Contractor #1 Rates Jan 2013 | Rate | Contractor #2 Labour Rates
Senior Project Manager | 137.24 | Description | Base Rate | Burdens and Benifts | Small Tools and Consumables | Subtotal | Overhead and Profit | Striaght Time Total | OverTime Rate @1.5 | Overtime Rate @ x2
Project Manager | 118.84 | Carpenter | 45 | 16.2 | 1.84 | 63.04 | 9.46 | 72.49 | 108.74 | 144.98
Assistant Project Manager | 109.01 | Unskilled worker | 38 | 13.68 | 1.55 | 53.23 | 7.98 | 61.21 | 91.82 | 122.43
Senior Superintendent | 134.38 | Heavy Equipment operator AA >6 v³ | 43 | 15.48 | 1.75 | 60.23 | 9.04 | 69.27 | 103.9 | 138.54
Superintendent | 109.44 | Heavy Equipment operator A | 43 | 15.48 | 1.75 | 60.23 | 9.04 | 69.27 | 103.9 | 138.54
Engineer | 90.65 | Excavator operator AA>6 v³ | 46 | 16.56 | 1.88 | 64.44 | 9.67 | 74.1 | 111.15 | 148.2
Foreman | 90.89 | Excavator operator | 45 | 16.2 | 1.84 | 63.04 | 9.46 | 72.49 | 108.74 | 144.98
Safety Superintendent | 98.58 | Crane operator Classe A | 46 | 16.56 | 1.88 | 64.44 | 9.67 | 74.1 | 111.15 | 148.2
Safety Supervisor | 87.87 | Mechanic assistant | 49 | 17.64 | 2 | 68.64 | 10.3 | 78.94 | 118.4 | 157.87
Training Superintendent | 90.65 | Mechanic | 46 | 16.56 | 1.88 | 64.44 | 9.67 | 74.1 | 111.15 | 148.2
Trainer | 81.84 | Blaster | 45 | 16.2 | 1.84 | 63.04 | 9.46 | 72.49 | 108.74 | 144.98
Maintenance Planner | 80.93 | Driller | 45 | 16.2 | 1.84 | 63.04 | 9.46 | 72.49 | 108.74 | 144.98
Mechanical Foreman | 87.42 | Land surveyor | 44 | 15.84 | 1.8 | 61.64 | 9.25 | 70.88 | 106.32 | 141.76
Technician | 73.13 | Pump & compressor operator | 43 | 15.48 | 1.75 | 60.23 | 9.04 | 69.27 | 103.9 | 138.54
Nurse/EMT | 67.84 | Store keeper | 35 | 12.6 | 1.43 | 49.03 | 7.35 | 56.38 | 84.57 | 112.76
Administrator | 70.94 | Site clerk | 33 | 11.88 | 1.35 | 46.23 | 6.93 | 53.16 | 79.74 | 106.32
Warehouse | 68.39 | Truck Driver AA >35 m.t. | 39 | 14.04 | 1.59 | 54.63 | 8.19 | 62.83 | 94.24 | 125.65
Shovel or Senior Operator | 75.4 | Truck Driver A | 38 | 13.68 | 1.55 | 53.23 | 7.98 | 61.21 | 91.82 | 122.43
Excavator Operator | 69
Crane Operator | 85.33 | Contractor #3
Loader Operator (988+) | 72.99 | Description | Base Rate | Burdens and Benefits | Small Tools and Consumables | Subtotal | Overhead and Profit | Straight Time Total | OverTime Rate @1.5 | Overtime Rate @ x2
Loader Operator (<988) | 69 | Labor, Journeyman | 31.9 | 35.54 | 5.86 | 73.3 | 14.66 | 87.96 | 22.74
Dozer Operator (<D8) | 69 | Driller or blaster | 37.08 | 39.97 | 5.86 | 82.91 | 16.582 | 99.492 | 25.85
Grader Operator | 69 | Drill and blast foreman | 39.67 | 39.59 | 5.86 | 85.12 | 17.024 | 102.144 | 27.4
Finish Operator (Grader, Dozer, Excavator) | 71.89 | Drill Mechanics | 38 | 37.43 | 5.86 | 81.29 | 16.258 | 97.548 | 26.4
Operator (multi-purpose) | 71.1 | Drill and blast general foreman | 41.53 | 40.74 | 5.86 | 88.13 | 17.626 | 105.756 | 28.52
Rock Trucks (<789) | 63.17 | Surbeyor | 38.86 | 34.94 | 5.86 | 79.66 | 15.932 | 95.592 | 26.92
Trucks - All Others | 63.17 | Haul truck driver | 33.65 | 33.88 | 5.86 | 73.39 | 14.678 | 88.068 | 23.79
Plant Operator (crushing, asphalt) | 73.32 | Foreman | 43.25 | 37.51 | 5.86 | 86.62 | 17.324 | 103.944 | 29.55
Crusher Labour (bobcat, hammer) | 60.69 | Heavy Equipment Operator | 36.03 | 34.54 | 5.86 | 76.43 | 15.286 | 91.716 | 25.22
Labour (skilled) (packer, bobcat, training in shop) | 60.69 | Parts Clerk | 28.12 | 31.8 | 5.86 | 65.78 | 13.156 | 78.936 | 20.47
Labour (entry level) | 53.81 | Mechanic | 38.61 | 35.25 | 5.86 | 79.72 | 15.944 | 95.664 | 26.77
Mechanic | $ N/C | Capenter | 38.86 | 34.94 | 5.86 | 79.66 | 15.932 | 95.592 | 26.92
Millwright | 84.59 | Excavator operator A | 38.25 | 35.15 | 5.86 | 79.26 | 15.852 | 95.112 | 26.55
Crusher Mechanic | 79.24 | Excavator operator AA | 39.32 | 35.45 | 5.86 | 80.63 | 16.126 | 96.756 | 27.19
Welder | $ N/C | Compressor operator | 35.22 | 33.77 | 5.86 | 74.85 | 14.97 | 89.82 | 24.73
Carpenter | 75.47 | Welder | 38.35 | 34.63 | 5.86 | 78.84 | 15.768 | 94.608 | 26.61
Electrician | 83.99 | General Foreman | 45.22 | 38.54 | 5.86 | 89.62 | 17.924 | 107.544 | 30.73
Serviceman (fuel & lube) | 71.6 | Mechanic Foreman | 42.47 | 37.29 | 5.86 | 85.62 | 17.124 | 102.744 | 29.08
Camp Serviceman | 64.03 | Technician | 31.9 | 35.54 | 5.86 | 73.3 | 14.66 | 87.96 | 22.74
Tireman | 69.71
Note: N/C - No Charge - Included in Equipment Rate.
Mechanic | 103.37
Welder | 97.5

## Equipment Rates Contractors (hidden)
Contractor #1 Equipment Rates Jan 2013 | Hourly Rate | Monthly Rate | Notes | Contractor #2 Equipment Rates
|  |  |  | Equipment Type | Year | Manufacturer | Model | Capacity | Hours | Standby Rate | Operating Rate
Haul Trucks |  |  |  | Zoom Boom | 2013 |  |  |  | TBD | 68.25 $ | 105.00 $
Kenworth Gravel Truck (c/w pup) | 145.89 |  |  | Water truck | 2013 |  |  |  | TBD | 74.75 $ | 115.00 $
Freightliner Gravel truck (c/w pup) | 145.89 |  |  | Camion 775 | 2013 | Caterpillar | 775F | 55 tons | TBD | 156.00 $ | 240.00 $
Kenworth Gravel Truck (w/o pup) | 117.62 |  |  | Truck 740 | 2013 | Caterpillar | 740 | 40 ton | TBD | 128.70 $ | 198.00 $
Freightliner Gravel truck (w/o pup) | 117.62 |  |  | Roller CS56 | 2013 | Caterpillar |  | 180 KN | TBD | 78.00 $ | 120.00 $
Kenworth with Fuel Tanker | 145.89 |  |  | Service truck | 2013 |  |  |  | TBD | 39.00 $ | 60.00 $
Cat 773D Truck | 192.27 |  |  | 988 Wheel loader | 2013 | Caterpillar |  | 8.4m³ | TBD | 195.00 $ | 300.00 $
|  |  |  | 980 Wheel loader | 2013 | Caterpillar |  | 5.0m³ | TBD | 131.30 $ | 202.00 $
Loaders |  |  |  | 966 wheel loader | 2013 | Caterpillar |  | 3.8m³ | TBD | 122.46 $ | 188.40 $
Cat 980H | 175.3 |  |  | 938 wheel loader | 2013 | Caterpillar |  | 2.3m³ | TBD | 78.00 $ | 120.00 $
Cat 966 | 122.14 |  |  | Pickup truck | 2013 | Ford |  |  | TBD | 19.50 $ | 30.00 $
Cat 988 | 236.37 |  |  | Screener fixed | 2013 |  |  | 150mm minus | TBD | 58.50 $ | 90.00 $
Cat 930G | 72.39 |  |  | Grader 14 | 2013 | Caterpillar |  | 140 KW | TBD | 97.50 $ | 150.00 $
|  |  |  | Fuel tanker | 2013 |  |  | 9000 to 11500 L | TBD | 52.65 $ | 81.00 $
Dozers |  |  |  | Excavator 390 | 2013 | Caterpillar | 390 | 4.6m³ | TBD | 214.50 $ | 330.00 $
Cat D8T | 186.61 |  |  | Excavator 49 ton | 2013 | Caterpillar | 349EL | 2.1m³ | TBD | 144.30 $ | 222.00 $
Cat D6 | 124.41 |  |  | Excavator 36 ton | 2013 | Caterpillar | 336DL, 336EL | 1.6m³ | TBD | 128.70 $ | 198.00 $
Cat D7 | 158.34 |  |  | Excavator 36 ton + hamer | 2013 | Caterpillar | 336DL, 336EL | 1.6 m³ | TBD | 273.00 $ | 420.00 $
|  |  |  | Dozer D8 | 2013 | Caterpillar | D8T | 260 KW | TBD | 175.50 $ | 270.00 $
Graders |  |  |  | Dozer D6 | 2013 | Caterpillar | D6T, D6R | 130 KW | TBD | 105.30 $ | 162.00 $
Cat 14H | 126.67 |  |  | Shuttle bus | 2013 | Thomas |  |  | TBD | 22.10 $ | 34.00 $
Cat 16H | 151.55 |  |  | school bus 24 passengers | 2013 | Thomas |  |  | TBD | 50.70 $ | 78.00 $
Excavators
Cat 345 | 230.71 |  |  | Contractor #3
|  |  |  | Equipment Type | Year | Manufacturer | Model | Capacity | Hours | Standby Rate | Operating Rate
Mobile Equipment |  |  |  | Hydraulic Rock Drill | 2013 | Sandvik | DX800 |  |  | TBD | 261.38
Ford Mechanic Truck F550 | 58.81 |  |  | Explosives Truck | 2013 | Kenworth | T800 |  |  | TBD | 61.74
Fuel Tanker | 29.41 |  |  | D6T Dozer (Or similar) | 2012 | Caterpillar | D6T (Or similar) |  |  | TBD | 127.85
Kenworth Lube/ Fuel Truck | 106.31 |  |  | D8T Dozer (Or similar) | 2012 | Caterpillar | D8T (Or similar) |  |  | TBD | 211.88
Sterling Roll-off/Vacuum Truck | 110.83 |  |  | 40 Passenger Bus | 2012 | TBD | TBD |  |  | TBD | 31.25
Cat Packer | 87.09 |  |  | Water Truck | 2012 | Kenworth (Or Similar) | T800 |  |  | TBD | 158.99
Wobbly Wheel Packer | 87.09 |  |  | Camion 10 Roues et Fardier | 2012 | Kenworth (Or Similar) | T800 |  |  | TBD | 122.49
Clemro Crusher | 865.2 |  |  | Fuel Truck | 2012 | Western Star (Or similar) | 4800 |  |  | TBD | 69.24
Water Truck | 76.9 |  |  | Snow Truck | 2012 | Western Star (Or similar) | 4800 |  |  | TBD | 96.49
Kenworth Gravel Truck c/w Sanding Unit Insert | 145.89 |  |  | Vacuum Truck | 2012 | Western Star (Or similar) | 4800 |  |  | TBD | 169.24
Winch Truck and Scissor Deck | 145.89 |  |  | 55T Haul Truck (Or similar) | 2012 | Caterpillar | 773F (Or similar) |  |  | TBD | 213.45
Bobcat | 70.13 |  |  | Ore Truck and Trailer | 2012 | Western Star (Or similar) | 6900 XD (Or similar) |  |  | TBD | 229.84
Single-Axle Fuel Truck | 70.13 |  |  | 40T Haul Truck (Or Similar) | 2012 | Western Star (Or similar) | 6900 XD (Or similar) |  |  | TBD | 135.08
|  |  |  | 980 Loader (or similar) | 2012 | Caterpillar | 980 (Or similar) |  |  | TBD | 160.74
Support Equipment |  |  |  | 980 Loader with snowblower | 2012 | Caterpillar | 980 (Or similar) |  |  | TBD | 185.65
Shanco Baffinland Camp |  | 109551.64 |  | 15T Compactor (or Similar) | 2012 | Hamm (or similar) | TBD |  |  | TBD | 77.49
Pick-up Truck |  | 3511.67 |  | Grader | 2012 | Caterpillar | 14m (Or similar) |  |  | TBD | 202.74
Freightliner Bus |  | 4448.11 |  | 45T Excavator | 2012 | Caterpillar | 349 (Or similar) |  |  | TBD | 148.67
Hot Box - Maxi Heater, 8kW |  | 3745.78 |  | 85T Excavator | 2012 | Caterpillar 385 (or similar) | 390 (Or similar) |  |  | TBD | 289.1
OHV 350 Frostfighter |  | 322.33 |  | Small Compactor | 2012 | P-2500 (or similar) |  |  |  | TBD | 18.09
Light Tower, 8 kW |  | 1697.59 |  | 30kV Generator | 2012 | Caterpillar |  |  |  | TBD | 13.06
Small Portable Lights (L100 and L101) |  | 292.93 |  | Tower Light | 2012 | Allmand (Or similar) |  |  |  | TBD | 8.91
Lincoln Welder 300D |  | 585.84 |  | Hydraulic Rock Breaker | 2012 | Atlas Copco |  |  |  | TBD | 204.24
Grove 60 Ton Crane |  | 13034.46 |  | Light Truck | 2012 | Kenworth (Or Similar) |  |  |  | TBD | 13.06
Ambulance Insert and Pick Up |  | 4295.44 | + $182.26/hour | Service Truck | 2012 | Western Star (Or similar) |  |  |  | TBD | 61.74
Camp Genset |  | 19899.46 |  | Skytrack | 2012 | Caterpillar |  |  |  | TBD | 89.99
Job Shacks with Genset |  | 2341.11 |  | Light Vehicle | 2012 | Dodge Ram |  |  |  | TBD | 21.11
Shop and Lube Rack |  | 1940.75 | Does not include portable lights, heater or lube racks
Shop at Mary River |  | 1357.17 | Does not include portable lights, heater or lube racks
Mobile Welding Trainer (W041) |  | 3161.07
Communication & Handhelds System |  | 28274.31

## CC001 Unit Prices (hidden)
Proposed Contract Price Breakdown
Baffinland Iron Mines Corporation: Mary River Project - ERP
H349000/CC001
Earthworks
STIPULATED SUM PORTION
Item No. | Description | Facility/Activity | Measurement for Payment | Quantity | Unit of Measure | Contractor #1 Unit Price | Contractor #1 Extended Price | Contractor #2 Unit Price | Contractor #2 Extended Price | Contractor #3 Unit Price | Contractor #3 Extended Price | MEAN Proposed Unit Price | VARIANCE Unit Price Contractor #1 | VARIANCE Unit Price Contractor #2 | VARIANCE Unit Price Contractor #3
1.0 | STIPULATED SUM ITEMS
1.1 | MOBILIZATION |  | 1.1 | 1 | S.S | 8173831.85 | 8173831.85 | 7920000 | 7920000 | 6687053.02 | 6687053.02 | 7593628.29 | -580203.56 | -326371.71 | 906575.27
1.2 | DEMOBILIZATION |  | 1.2 | 1 | S.S | 5378811.37 | 5378811.37 | 1080000 | 1080000 | 1043020.13 | 1043020.13 | 2500610.5 | -2878200.87 | 1420610.5 | 1457590.37
1.3 | INSURANCE |  | 1.3 | 1 | S.S | 0 | 0 | 269000 | 269000 | 60191.48 | 60191.48 | 109730.4933 | 109730.4933 | -159269.5067 | 49539.0133
1.4 | CONTRACTOR FACILITIES | 7300 | 1.4 | 1 | S.S | 6766905.24 | 6766905.24 | 3770000 | 3770000 | 1291153.89 | 1291153.89 | 3942686.3767 | -2824218.8633 | 172686.3767 | 2651532.4867
1.5 | PERMITS |  | 1.5 | 1 | S.S | 0 | 0 | 215000 | 215000 | 1 | 1 | 71667 | 71667 | -143333 | 71666
| SUBTOTAL (STIPULATED SUM PORTION) | [5 empty] | 20319548.46 |  | 13254000 |  | 9081419.52
UNIT RATE PORTION
Item No. | Description | Facility/Activity | Measurement for Payment | Quantity | Unit of Measure | Contractor #1 Unit Price | Contractor #1 Extended Price | Contractor #2 Unit Price | Contractor #2 Extended Price | Contractor #3 Unit Price | Contractor #3 Extended Price | MEAN Proposed Unit Price | VARIANCE Unit Price Contractor #1 | VARIANCE Unit Price Contractor #2 | VARIANCE Unit Price Contractor #3
2.0 | UNIT RATE ITEMS
| AREA 2000 - MILNE PORT | Facility/Activity
2.1 | EARTHWORKS
| ORE STOCKPILE PAD | 2133
| Type 1 Excavation |  | 2.1 | 4700 | cubic metre | 48.71 | 228937 | 23.1 | 108570 | 28.02 | 131694 | 33.2767 | -15.4333 | 10.1767 | 5.2567
| Type 2A Excavation |  | 2.2 | 12800 | cubic metre | 44.04 | 563712 | 63.7 | 815360 | 26.92 | 344576 | 44.8867 | 0.84667 | -18.8133 | 17.9667
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 42500 | cubic metre | 52.45 | 2229125 | 40.5 | 1721250 | 45.84 | 1948200 | 46.2633 | -6.1867 | 5.7633 | 0.42333
| Screened Borrow Fill - 150mm minus |  | 2.6 | 8800 | cubic metre | 20.58 | 181104 | 42.6 | 374880 | 45.84 | 403392 | 36.34 | 15.76 | -6.26 | -9.5
| Prepare and Compact Subgrade |  | 2.7 | 128000 | square metre | 0.4 | 51200 | 3.8 | 486400 | 2.43 | 311040 | 2.21 | 1.81 | -1.59 | -0.22
| Place Excavation as Fill |  | 2.13 | 17500 | cubic metre | 2.96 | 51800 | 3.9 | 68250 | 2.72 | 47600 | 3.1933 | 0.23333 | -0.70667 | 0.47333
| ORE STOCKPILE SETTLING POND | 2345
| Excavation , Fill, Subgrade Quantities are included in Activity 2133 |  |  | Incl in 2133 | cubic metre
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 7000 | cubic metre | 75.37 | 527590 | 97.9 | 685300 | 61.31 | 429170 | 78.1933 | 2.8233 | -19.7067 | 16.8833
| Geo-membrane liner |  | 2.15 | 3000 | square metre | 35.52 | 106560 | 21.1 | 63300 | 69.11 | 207330 | 41.91 | 6.39 | 20.81 | -27.2
2.2 | MILNE PORT QUARRY AND BORROW DEVELOPMENT | 2138
| Type 2A Excavation |  | 2.2 | 600 | cubic metre | 44.07 | 26442 | 12.9 | 7740 | 37.33 | 22398 | 35.3067 | -8.7633 | 22.4067 | -13.6433
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 3000 | cubic metre | 49.21 | 147630 | 25.9 | 77700 | 48.95 | 146850 | 47.6267 | -1.5833 | 21.7267 | -20.1433
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 300 | cubic metre | 78.49 | 23547 | 59.3 | 17790 | 67.77 | 20331 | 47.2 | -31.29 | -12.1 | #REF!
| Place Excavation as Fill |  | 2.13 | 600 | cubic metre | 2.96 | 1776 | 3.5 | 2100 | 3.81 | 2286 | 3.4233 | 0.46333 | -0.076667 | -0.38667
AREA 3000 - TOTE ROAD
2.3 | EARTHWORKS
| ROAD UPGRADE | 3131
| Type 1 Excavation |  | 2.1 | 20000 | cubic metre | 54.07 | 1081400 | 24.8 | 496000 | 33.47 | 669400 | 37.4467 | -16.6233 | 12.6467 | 3.9767
| Type 2A Excavation |  | 2.2 | 60000 | cubic metre | 49.4 | 2964000 | 67.4 | 4044000 | 33.47 | 2008200 | 50.09 | 0.69 | -17.31 | 16.62
| Rock fill: Type 5 - 32mm minus |  | 2.4 | 198740 | cubic metre | 65.75 | 13067155 | 81.6 | 16217184 | 76.7 | 15243358 | 74.6833 | 8.9333 | -6.9167 | -2.0167
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 220875 | cubic metre | 54.12 | 11953755 | 58.1 | 12832837.5 | 57.89 | 12786453.75 | 56.7033 | 2.5833 | -1.3967 | -1.1867
| Rock fill: Type 12 - Run of Quarry |  | 2.4 | 379500 | cubic metre | 25.18 | 9555810 | 31.6 | 11992200 | 35.52 | 13479840 | 30.7667 | 5.5867 | -0.83333 | -4.7533
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 6000 | cubic metre | 75.45 | 452700 | 125 | 750000 | 60.36 | 362160 | 86.9367 | 11.4867 | -38.0633 | 26.5767
| Excavate and Place Rip-Rap |  | 2.14 | 4400 | cubic metre | 93.88 | 413072 | 35.7 | 157080 | 47.38 | 208472 | 58.9867 | -34.8933 | 23.2867 | 11.6067
| Non-woven textile material |  | 2.10 | 100000 | square metre | 6.01 | 601000 | 4.06 | 406000 | 2.75 | 275000 | 4.2733 | -1.7367 | 0.21333 | 1.5233
| Geo-grid |  | 2.11 | 75000 | square metre | 8.43 | 632250 | 10.2 | 765000 | 3.9 | 292500 | 7.51 | -0.92 | -2.69 | 3.61
| Culvert - 600mm dia. galvanized CSP |  | 2.5 | 600 | metre | 941.61 | 564966 | 1710 | 1026000 | 2515.45 | 1509270 | 1722.3533 | 780.7433 | 12.3533 | -793.0967
| Culvert - 1000mm dia. galvanized CSP |  | 2.5 | 525 | metre | 831.56 | 436569 | 1940 | 1018500 | 2773.39 | 1456029.75 | 1848.3167 | 1016.7567 | -91.6833 | -925.0733
| Culvert - 1500mm dia. galvanized CSP |  | 2.5 | 400 | metre | 1112.88 | 445152 | 2330 | 932000 | 3998.76 | 1599504 | 2480.5467 | 1367.6667 | 150.5467 | -1518.2133
| Culvert - 2000mm dia. galvanized CSP |  | 2.5 | 250 | metre | 1568.04 | 392010 | 2630 | 657500 | 6752.21 | 1688052.5 | 3650.0833 | 2082.0433 | 1020.0833 | -3102.1267
| Install road edge markers |  | 2.8 | 7200 | ea | 243.95 | 1756440 | 80.8 | 581760 | 195.94 | 1410768 | 173.5633 | -70.3867 | 92.7633 | -22.3767
| Install Culvert Markers |  | 2.9 | 200 | ea | 1216.48 | 243296 | 657 | 131400 | 315.05 | 63010 | 729.51 | -486.97 | 72.51 | 414.46
| Signage |  | 2.12 | 150 | ea | 438.23 | 65734.5 | 648 | 97200 | 428.74 | 64311 | 504.99 | 66.76 | -143.01 | 76.25
2.4 | TOTE ROAD QUARRY AND BORROW DEVELOPMENT | 3138
| Type 2A Excavation |  | 2.2 | 3200 | cubic metre | 47.45 | 151840 | 21.3 | 68160 | 27.67 | 88544 | 32.14 | -15.31 | 10.84 | 4.47
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 14040 | cubic metre | 47.47 | 666478.8 | 42.6 | 598104 | 49.26 | 691610.4 | 46.4433 | -1.0267 | 3.8433 | -2.8167
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 2250 | cubic metre | 81.22 | 182745 | 97.9 | 220275 | 68.72 | 154620 | 82.6133 | 1.3933 | -15.2867 | 13.8933
| Place Excavation as Fill |  | 2.13 | 3200 | cubic metre | 2.96 | 9472 | 3.01 | 9632 | 3.81 | 12192 | 3.26 | 0.3 | 0.25 | -0.55
| Culvert - 600mm dia. galvanized CSP |  | 2.5 | 100 | metre | 576.09 | 57609 | 1850 | 185000 | 2515.45 | 251545 | 1647.18 | 1071.09 | -202.82 | -868.27
AREA 4000 - MINE SITE
2.5 | EARTHWORKS
| ORE CRUSHING AND LOADING | 4133
| Type 1 Excavation |  | 2.1 | 2500 | cubic metre | 50.42 | 126050 | 14.9 | 37250 | 33.5 | 83750 | 32.94 | -17.48 | 18.04 | -0.56
| Type 2A Excavation |  | 2.2 | 8300 | cubic metre | 45.75 | 379725 | 63.7 | 528710 | 28.5 | 236550 | 45.9833 | 0.23333 | -17.7167 | 17.4833
| Rock fill: Type 5 - 32mm minus |  | 2.4 | 6000 | cubic metre | 55.94 | 335640 | 61.7 | 370200 | 66.29 | 397740 | 61.31 | 5.37 | -0.39 | -4.98
| Rock fill: Type 12 - Run of Quarry |  | 2.4 | 28000 | cubic metre | 22.01 | 616280 | 19.1 | 534800 | 22.8 | 638400 | 21.3033 | -0.70667 | 2.2033 | -1.4967
| Prepare and Compact Subgrade |  | 2.7 | 33250 | square metre | 0.4 | 13300 | 3.8 | 126350 | 2.43 | 80797.5 | 2.21 | 1.81 | -1.59 | -0.22
| Place Excavation as Fill |  | 2.13 | 10800 | cubic metre | 2.96 | 31968 | 2.95 | 31860 | 0.92 | 9936 | 2.2767 | -0.68333 | -0.67333 | 1.3567
0
0
| PIT 1 HAUL ROAD | 4221 | [5 empty] | 0
| Type 1 Excavation |  | 2.1 | 8000 | cubic metre | 55.04 | 440320 | 14.9 | 119200 | 28.87 | 230960 | 32.9367 | -22.1033 | 18.0367 | 4.0667
| Type 2A Excavation |  | 2.2 | 54000 | cubic metre | 48.65 | 2627100 | 57.4 | 3099600 | 28.87 | 1558980 | 44.9733 | -3.6767 | -12.4267 | 16.1033
| Type 2B Excavation |  | 2.3 | 162000 | cubic metre | 51.81 | 8393220 | 20.5 | 3321000 | 23.72 | 3842640 | 32.01 | -19.8 | 11.51 | 8.29
| Place Fill (using Types 1 and 2A Excavation) |  | 2.13 | 62000 | cubic metre | 1.95 | 120900 | 5.32 | 329840 | 0.91 | 56420 | 2.7267 | 0.77667 | -2.5933 | 1.8167
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 24000 | cubic metre | 92.66 | 2223840 | 86.2 | 2068800 | 77.5 | 1860000 | 85.4533 | -7.2067 | -0.74667 | 7.9533
| Rock fill: Type 5 - 32mm minus |  | 2.4 | 20240 | cubic metre | 55.83 | 1129999.2 | 41.7 | 844008 | 70.93 | 1435623.2 | 56.1533 | 0.32333 | 14.4533 | -14.7767
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 41760 | cubic metre | 57.26 | 2391177.6 | 42.5 | 1774800 | 57.18 | 2387836.8 | 52.3133 | -4.9467 | 9.8133 | -4.8667
| Culvert - 1000mm dia. galvanized CSP |  | 2.5 | 1200 | metre | 831.72 | 998064 | 1310 | 1572000 | 2773.39 | 3328068 | 1638.37 | 806.65 | 328.37 | -1135.02
0
0
| OPEN PIT DEVELOPMENT | 4250 | [5 empty] | 0
| Type 2B Excavation |  | 2.3 | 155000 | cubic metre | 50.29 | 7794950 | 19.9 | 3084500 | 25.07 | 3885850 | 31.7533 | -18.5367 | 11.8533 | 6.6833
0
0
| CRUSHING STOCKPILE SETTLING POND | 4385 | [5 empty] | 0
| Type 2A Excavation |  | 2.2 | 5000 | cubic metre | 45.75 | 228750 | 15.5 | 77500 | 30.34 | 151700 | 30.53 | -15.22 | 15.03 | 0.19
| Rock fill: Type 8 - 150mm minus (placed as rock berm) |  | 2.4 | 6400 | cubic metre | 65.13 | 416832 | 50.4 | 322560 | 64.62 | 413568 | 60.05 | -5.08 | 9.65 | -4.57
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 3600 | cubic metre | 78.17 | 281412 | 86.3 | 310680 | 77.46 | 278856 | 80.6433 | 2.4733 | -5.6567 | 3.1833
| Place Excavation as Fill |  | 2.13 | 5000 | cubic metre | 2.96 | 14800 | 5.68 | 28400 | 0.79 | 3950 | 3.1433 | 0.18333 | -2.5367 | 2.3533
| Geo-membrane liner |  | 2.15 | 1500 | square metre | 39.25 | 58875 | 21.1 | 31650 | 61.28 | 91920 | 40.5433 | 1.2933 | 19.4433 | -20.7367
0
| MINE SITE QUARRY DEVELOPMENT | 4138 | [5 empty] | 0
| Type 2A Excavation |  | 2.2 | 1250 | cubic metre | 44.04 | 55050 | 16.2 | 20250 | 36.93 | 46162.5 | 32.39 | -11.65 | 16.19 | -4.54
| Rock fill: Type 5 - 32mm minus |  | 2.4 | 1440 | cubic metre | 53.02 | 76348.8 | 48.5 | 69840 | 70.31 | 101246.4 | 57.2767 | 4.2567 | 8.7767 | -13.0333
| Rock fill: Type 8 - 150mm minus |  | 2.4 | 5760 | cubic metre | 44.9 | 258624 | 32.3 | 186048 | 64.64 | 372326.4 | 47.28 | 2.38 | 14.98 | -17.36
| Rock fill: Type 19 - 150mm Clear (placed as rip rap) |  | 2.4 | 400 | cubic metre | 92.65 | 37060 | 72.2 | 28880 | 80.16 | 32064 | 81.67 | -10.98 | 9.47 | 1.51
| Place Excavation as Fill |  | 2.13 | 1250 | cubic metre | 2.96 | 3700 | 3.23 | 4037.5 | 1.27 | 1587.5 | 2.4867 | -0.47333 | -0.74333 | 1.2167
| Culvert - 600mm dia. galvanized CSP |  | 2.5 | 50 | metre | 534.28 | 26714 | 485 | 24250 | 2515.45 | 125772.5 | 1178.2433 | 643.9633 | 693.2433 | -1337.2067
| SUBTOTAL (UNIT RATE PORTION) | [5 empty] | 78913576.9 |  | 76561486 |  | 79982412.2
TIME AND MATERIAL PORTION
Item No. | Description | Facility/Activity | Measurement for Payment | Quantity | Unit of Measure | Contractor #1 Unit Price | Contractor #1 Extended Price | Contractor #2 Unit Price | Contractor #2 Extended Price | Contractor #3 Unit Price | Contractor #3 Extended Price | MEAN Proposed Unit Price | VARIANCE Unit Price Contractor #1 | VARIANCE Unit Price Contractor #2 | VARIANCE Unit Price Contractor #3
3.0 | TIME AND MATERIAL ITEMS
AREA 3000 - TOTE ROAD
3.1 | TOTE ROAD BRIDE CONSTRUCTION
| CONSTRUCT NEW BRIDGE AT KM 17 | 3132 | 3.1 | 1
| CONSTRUCT NEW BRIDGE AT KM 62 | 3133 | 3.1 | 1
| CONSTRUCT NEW BRIDGE AT KM 80 | 3134 | 3.1 | 1
| CONSTRUCT NEW BRDIGE AT KM 97 | 3135 | 3.1 | 1
| REMOVE EXISTING BRIDGES | 3136 | 3.1 | 1
AREA 7000 - CONSTRUCTION INFRASTRUCTURE
3.2 | SERVICES
| EXPLOSIVES SUPPLY | 7824 | 3.2 | 1 | Total Cost | 2999412 | 2999412 | 1240000 | 1240000 | 1310900.49 | 1310900.49 | 1850104.1633 | -1149307.8367 | 610104.1633 | 539203.6733
| TOTE ROAD SNOW CLEARING | 7810.2.3 | 3.3 | 1
| TOTE ROAD FLOOD MANAGEMENT | 7810.3.4 | 3.3 | 1
| TOTE ROAD FRESHET MANAGEMENT | 7810.4.5 | 3.3 | 1
| SUBTOTAL (TIME AND MATERIAL PORTION) | [5 empty] | 2999412 |  | 1240000 |  | 1310900.49 | 1850104.1633
OPTIONAL ITEMS (TO BE PRICED BY ALL PROPONENTS)
Item No. | Description | Facility/Activity | Measurement for Payment | Quantity | Unit of Measure | Contractor #1 Unit Price | Contractor #1 Extended Price | Contractor #2 Unit Price | Contractor #2 Extended Price | Contractor #3 Unit Price | Contractor #3 Extended Price | MEAN Proposed Unit Price | VARIANCE Unit Price Contractor #1 | VARIANCE Unit Price Contractor #2 | VARIANCE Unit Price Contractor #3
4.0 | OPTIONAL ITEMS
AREA 7000 - CONSTRUCTION INFRASTRUCTURE
4.1 | BULK SAMPLE (OPTIONAL)
| 2014 BULK SAMPLE | 7999 | 4.1 | 206899 | cubic metre | 88.2 | 18248491.8 | 129 | 26689971 | 134.91 | 27912744.09 | 117.37 | 29.17 | -11.63 | -17.54
| SUBTOTAL (OPTIONAL ITEMS) | [5 empty] | 18248491.8 |  | 26689971 |  | 27912744.09 | 117.37
| TOTAL PROPOSED CONTRACT PRICE | [5 empty] | 120481029.16 |  | 117745457 |  | 118287476.3

## Buildings Footprints (hidden)
Level 0 | Level 1 | Level 2 | Level 3 | Description | Value | Unit | Unit Cost | Comments
- | - | - | 2511-BLD-001 | Accomodation Service Core | 14940 | ft2 | - | Maintain the cost to remove the bldgs but remove the cost for grade & re-contour bldgs footprint. Quantity to be removed based on Master building list
- | - | - | 2511-BLD-002 | Accomodation Office | 3600 | ft2 | -
- | - | - | 2511-BLD-003 | Accomodation Laundry | 4560 | ft2 | -
- | - | - | 2512-BLD-001 | Accommodation Wing BA | 6583 | ft2 | -
- | - | - | 2512-BLD-002 | Accommodation Wing BB | 0 | ft2 | -
- | - | - | 2512-BLD-003 | Accommodation Wing BC | 6583 | ft2 | -
- | - | - | 2512-BLD-004 | Accommodation Wing BD | 6583 | ft2 | -
- | - | - | 2750-BLD-001 | Accomodation Area E-House #1 | 640 | ft2 | -
- | - | - | 2750-BLD-002 | Accomodation Area E-House #2 | 400 | ft2 | -
- | - | - | 2513-BLD-001 | Emergency Response Office | 960 | ft2 | -
- | - | - | 2513-BLD-002 | Emergency Response Garage | 3000 | ft2 | -
|  |  | 2731-BLD-001 | Sewage Chemical Storage Container | 320 | ft2 | -
|  |  | 2731-VP-005 | Sewage Treatment Plant | 1920 | ft2 | -
|  |  | 2732-BLD-001 | Sewage Truck Building | 600 | ft2 | -
|  |  | 2720-BLD-001 | Water Building | 4200 | ft2 | -
|  |  | 2540-BLD-001 | Waste Management Building | 4800 | ft2 | -
- | - | - | 2540-VP-001 | Waste Incinerators | 560 | ft2 | -
- | - | - | 4382-BLD-001 | Truck Weigh Building | 3600 | ft2 | - | Maintain the cost to remove the bldgs but remove the cost for grade & re-contour bldgs footprint. Quantity to be removed based on Master building list
- | - | - | 4511-BLD-001 | Accommodation Service Core | 19980 | ft2 | -
- | - | - | 4511-BLD-002 | Accommodation Office | 6540 | ft2 | -
- | - | - | 4511-BLD-003 | Accommodation Laundry | 4560 | ft2 | -
- | - | - | 4511-BLD-004 | Accommodation Laboratory | 3360 | ft2 | -
- | - | - | 4512-BLD-001 | Accommodation Wing AA | 6583 | ft2 | -
- | - | - | 4512-BLD-002 | Accommodation Wing AB | 6583 | ft2 | -
- | - | - | 4512-BLD-003 | Accommodation Wing AC | 6583 | ft2 | -
- | - | - | 4512-BLD-004 | Accommodation Wing AD | 6583 | ft2 | -
- | - | - | 4512-BLD-005 | Accommodation Wing AE | 6583 | ft2 | -
- | - | - | 4512-BLD-006 | Accommodation Wing AF | 6583 | ft2 | -
- | - | - | 4512-BLD-007 | Accommodation Wing AG | 6583 | ft2 | -
- | - | - | 4750-BLD-001 | Accomodation Area E-House #1 | 640 | ft2
- | - | - | 4750-BLD-002 | Accomodation Area E-House #2 | 400 | ft2
- | - | - | 4513-BLD-001 | Emergency Response Office | 960 | ft2 | -
- | - | - | 4513-BLD-002 | Emergency Response Garage | 3000 | ft2 | -
- | - | - | 4521-BLD-001 | Maintenance Building | 26000 | ft2 | -
- | - | - | 4521-BLD-003 | Welding Shop Building | 4200 | ft2 | -
- | - | - | 4521-BLD-004 | Workshop Office Building | 2880 | ft2 | -
- | - | - | 4521-BLD-005 | Workshop Office Washcar | 384 | ft2 | -
- | - | - | 4530-BLD-001 | Power Generation Module #1 | 559 | ft2 | -
- | - | - | 4530-BLD-002 | Power Generation Module #2 | 559 | ft2 | -
- | - | - | 4530-BLD-003 | Power Generation Module #3 | 559 | ft2 | -
- | - | - | 4530-BLD-004 | Power Generation Module #4 | 559 | ft2 | -
- | - | - | 4530-BLD-005 | Power Generation Module #5 | 559 | ft2 | -
- | - | - | 4530-BLD-006 | Power Generation Module #6 | 559 | ft2 | -
- | - | - | 4530-BLD-007 | Power Generation E-House #1 | 720 | ft2 | -
- | - | - | 4530-BLD-008 | Power Generation E-House #2 | 720 | ft2 | -
- | - | - | 4731-BLD-001 | Sewage Chemical Storage Container | 320 | ft2 | -
- | - | - | 4731-VP-005 | Sewage Treatment Plant | 1920 | ft2 | -
- | - | - | 4732-BLD-001 | Sewage Truck Building | 600 | ft2 | -
- | - | - | 4720-BLD-001 | Water Building | 4200 | ft2 | -
- | - | - | 7434-BLD-001 | Toromont Britespan Workshop | 13471.52 | ft2 | -
|  |  |  | Total Building Footprint (Already Accounted for) | -208139.52 | ft2
|  |  |  | Total Building Footprint (Already Accounted for) | -19343.8216 | m2

## Items changed to ft2 (hidden)
|  | Ore Stockpile Pad |  | 35269.45 | m2
|  | Additional Buildings by BIM Site Services slab on grade |  | 180 | m2
|  | Exploration Tent Camp Pad |  | 9432.14 | m2
Qty Code | Type | Description | Tag Number | QTY | Unit
EG |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 2540-VP-001 | 6025.6 | ft2
EG |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-013 | 1721.6 | ft2
EG |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2613-FD-014 | 3443.2 | ft2
EG |  | Jet-A1 Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 2614-FD-011 | 1721.6 | ft2
EG |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 2731-VP-005 | 20659.2 | ft2
EG |  | Waste Incinerators - Demolish and foundations - Gravel Base - Skidded Building | 4540-VP-001 | 6025.6 | ft2
EG |  | Diesel Fuel Dispensing Module - Demolish and foundations - Gravel Base - Skidded Building | 4613-FD-013 | 3443.2 | ft2
EG |  | Sewage Treatment Plant - Demolish and foundations - Gravel Base - Skidded Building | 4731-VP-005 | 20659.2 | ft2
Qty Code | Type | Description | Tag Number | QTY | Unit
FC-c |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-013 | 1721.6 | ft2
FC-c |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2613-FD-014 | 3443.2 | ft2
FC-c |  | Jet-A1 Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 2614-FD-011 | 1721.6 | ft2
FC-c |  | Diesel Fuel Dispensing Module - Demolish and Decontaminate Building - ISO Shipping Container | 4613-FD-013 | 3443.2 | ft2
Qty Code | Type | Description | Tag Number | QTY | Unit
FTR2-c |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 6025.6 | ft2
FTR2-c |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 20659.2 | ft2
FTR2-c |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 6025.6 | ft2
FTR2-c |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 20659.2 | ft2
Qty Code | Type | Description | Tag Number | QTY | Unit
FTR2-c |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2540-VP-001 | 6025.6 | ft2
FTR2-c |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 2731-VP-005 | 20659.2 | ft2
FTR2-c |  | Waste Incinerators - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4540-VP-001 | 6025.6 | ft2
FTR2-c |  | Sewage Treatment Plant - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4731-VP-005 | 20659.2 | ft2
Qty Code | Type | Description | Tag Number | QTY | Unit
FW |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 2540-VP-001 | 6025.6 | m2
FW |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-013 | 1721.6 | m2
FW |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2613-FD-014 | 3443.2 | m2
FW |  | Jet-A1 Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 2614-FD-011 | 1721.6 | m2
FW |  | Sewage Treatment Plant - Demolish floor finish - Raised Steel or Wooden Floor | 2731-VP-005 | 20659.2 | m2
FW |  | Waste Incinerators - Demolish floor finish - Raised Steel or Wooden Floor | 4540-VP-001 | 6025.6 | m2
FW |  | Diesel Fuel Dispensing Module - Demolish floor finish - Raised Steel or Wooden Floor | 4613-FD-013 | 3443.2 | m2

## Mary River Exploration (hidden)
Liability Allocation | IOL |  |  | Crown |  |  | Project Total
| Land |  | Total | Land | Water | Total
DIRECT COSTS SUBTOTAL | 120311 | 14808 | 135119 | 886706 | 0 | 886706 | 1021825
Project Management (5% of Direct Costs) | 6016 | 740 | 6756 | 44335 | 0 | 44335 | 51091
Bonding (1% of Direct Costs) | 1203 | 148 | 1351 | 8867 | 0 | 8867 | 10218
Insurance (1% of Direct Costs) | 1203 | 148 | 1351 | 8867 | 0 | 8867 | 10218
Engineering (5% of Direct Costs) | 6016 | 740 | 6756 | 44335 | 0 | 44335 | 51091
Contingency (10% of Direct Costs) | 12031 | 1480 | 13512 | 88671 | 0 | 88671 | 102183
GRAND TOTAL | 146779 | 18066 | 164845 | 1081781 | 0 | 1081781 | 1246627

## H349000-1000-00-144-0001 - Qtys (hidden)
Master Building Matrix
Baffinland Iron Mines: Mary River Project | [37 empty] | Document: H349000-1000-00-144-0001, Rev. 4
H349000
Changes Since Last Issue | Building Location, Number and Name | [8 empty] | Procurement |  | Building Size & Footprint Area | [7 empty] | Building Structure |  |  | Contained Facilities |  |  |  |  | Building Services | [19 empty] | DO NOT PRINT THESE COLUMNS - ONLY FOR IT AND COMMUNICATIONS USE
| FBS Number | Location | Area | Facility |  | Sequence Number | Building/Equipment Number | Building Name | Comments | Building Supply Package | Building Installation Contract | No. of Storeys | Occupancy | Width (ft) Out to Out of Cladding | Length (ft) Out to Out of Cladding | Bldg. Ht. (ft) Grade to Ridge | Building Footprint (ft2) | Floor Area (ft2) (All Storeys) | Occupancy Classification | Building Type (See Legend) | Foundation Type (See Legend) | Floor Finish (See Legend) | Offices & Similar Facilities (Furnished) | Washroom(s) | Dining / Lunchrooms / Kitchen (Furnished) | Dormitory Rooms (Furnished) | Special Rooms / Functions (Furnished) | Temperature A:Ambient/Unheated or Temp in deg C | Heating E:Electric, D:Diesel, M:Mobile heaters | Mechanical Ventilation | Air Conditioning | Raw Water T:Tank or P:Piped supply | Potable Water B:Bottled or P:Piped Supply | Sanitary Sewage T:Local tank or P:Pumped and piped | Fire Water Sprinkler System L:Local system or P:Piped service | Other Fire Supression (HP-CO2 etc.) | Addressable Fire Detection & Alarm System | Smoke Alarm (no signal sent) | Electrical Service D:Distribution system, L:Local Genset | Data Service/External Distribution F:Fibre Optic C:Ethernet Cable M: microwave X: Coaxial Cable | IT Connectivity for Construction F:Fibre Optic C:Ethernet Cable M:Local microwave | Satellite TV Service | Estimate ports to be installed by CT-001 | IT cabinets (13U/24U/special size) | Fire detector alarm model | Fire protection | Fire Alarm Drawings LINKs | IT Network |  |  | IT Peripherals |  |  |  | VoIP |  | Other Communication
[48 empty] | TNS | Hatch | BNS | MFD | Laser Printer | Plotter | TV | Handsets | Conference Phones | Sat Phone | Radio | Comments
| 2110 | Milne Port | General | Communication and IT Infrastructure |  | 1 | 2110-BLD-001 | Communication Shed |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 2110 | Milne Port | General | Communication and IT Infrastructure |  | 2 | 2110-BLD-002 | Satellite Dish Sea Can |  | - |  | 1 | - | 8 | 40 | 10 | [21 empty] | • | L | F | - | - |  | 24U |  |  |  | • | •
| 2223 | Milne Port | Marine | Ore Dock |  | 1 | 2223-BLD-001 | Dock Office | Re-use/relocate construction trailer(s) | - | CC005 | 1 |  | 12 | 40 | 8 | 480 | 480 |  | TS | GB | RA | • | • | - | - | - | 22 | E | - | - | T | B | T | - | - | • |  | D | M | - | - | 2 | 13U | tbc |  |  | • |  | • |  | 1 |  | 1 | 3 | 1 | 1 | 1 | Marine radio
| 2342 | Milne Port | Material Handling | Stockpile |  | 1 | 2342-BLD-001 | Shiploading E-House |  | PM002 | CC005 | 1 | - | - | - | - | 0 | 0 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | • | - | D | M | - | - | 2 | 13U | Honeywell 120xls |  |  | • | [6 empty] | 1
| 2351 | Milne Port | Material Handling | Ship Loading |  | 1 | 2351-SL-001 | Shiploader E-House #1 | Located on Shiploader #1 | PM002 | CC005 | 1 | - | tbd | tbd | tbd | tbd | tbd |  | tbd | tbd | tbd | - | - | - | - | - | [12 empty] | - | - | - |  | tbd | [5 empty] | •
| 2351 | Milne Port | Material Handling | Ship Loading |  | 2 | 2351-SL-002 | Shiploader E-House #2 | Located on Shiploader #2 | PM002 | CC005 | 1 | - | tbd | tbd | tbd | tbd | tbd |  | tbd | tbd | tbd | - | - | - | - | - | [12 empty] | - | - | - |  | tbd | [5 empty] | •
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  | 1 | 2511-BLD-001 | Accommodation Service Core |  | TX001 | CC005 | 1 | - | 60 | 249 | 13 | 14940 | 14940 |  | SM | GB | RA | • | • | • | - | • | 22 | D | • | • | - | P | P | P | • | • | - | D | F / F | M | • | 4 | (by Horizon) | Honeywell 140/120xls |  |  | • | • | • | 3 |  |  | 2 | 3 | 1
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  | 2 | 2511-BLD-002 | Accommodation Office |  | TX001 | CC005 | 1 | 33 | 60 | 60 | 13 | 3600 | 3600 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 3 | 1 |  | 1/cubicle | 1/conf room |  | 1 | Fixed radio
| 2511 | Milne Port | Non Process Facilities | Accommodations Area |  | 3 | 2511-BLD-003 | Accommodation Laundry |  | TX001 | CC005 | 1 | 5 | 60 | 76 | 13 | 4560 | 4560 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  |  | Honeywell 120xls
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  | 1 | 2512-BLD-001 | Accommodation Wing BA |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  | 2 | 2512-BLD-002 | Accommodation Wing BB |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  | 3 | 2512-BLD-003 | Accommodation Wing BC |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2512 | Milne Port | Non Process Facilities | Accommodations Area |  | 4 | 2512-BLD-004 | Accommodation Wing BD |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 2513 | Milne Port | Non Process Facilities | Accommodations Area |  | 1 | 2513-BLD-001 | Emergency Response Office |  | PX001 | CC005 | 1 | 18 | 24 | 40 | 8 | 960 | 960 | D | TM | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | F | M/C | - | 6 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 2 | 1 | 1 | 1 | Fixed radio
| 2513 | Milne Port | Non Process Facilities | Accommodations Area |  | 2 | 2513-BLD-002 | Emergency Response Garage |  | PX002 | CC005 | 1 | 5 | 50 | 60 | 20 | 3000 | 3000 | F-3 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F | C | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1 |  |  | 1 | Portable radio
| 2521 | Milne Port | Non Process Facilities | Services Area |  | 1 | 2521-BLD-001 | Maintenance Building |  | PX002 | CC005 | 1 | 10 | 60 | 160 | 25 | 9600 | 9600 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | T | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 4 |  |  |  | Needs full detailed dwg
| 2521 | Milne Port | Non Process Facilities | Services Area |  | 2 | 2521-BLD-002 | Welding Shop Building |  | PX002 | CC005 | 1 | 5 | 40 | 40 | 25 | 1600 | 1600 | F-2 | FO | PF | SOG | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | - | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1
| 2521 | Milne Port | Non Process Facilities | Services Area |  | 3 | 2521-BLD-003 | Workshop Office Building |  | PX001 | CC005 | 1 | 32 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • |  |  | 1 |  |  | 3 |  |  |  | Hatch network MW only
| 2521 | Milne Port | Non Process Facilities | Services Area |  | 4 | 2521-BLD-004 | Workshop Office Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 1 | 2530-BLD-001 | Power Generation Module #1 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 2 | 2530-BLD-002 | Power Generation Module #2 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 3 | 2530-BLD-003 | Power Generation Module #3 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 4 | 2530-BLD-004 | Power Generation Module #4 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 5 | 2530-BLD-005 | Power Generation Module #5 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 6 | 2530-BLD-006 | Power Generation Module #6 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 7 | 2530-BLD-007 | Power Generation Module #7 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 8 | 2530-BLD-008 | Power Generation Module #8 | Future Provision | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 9 | 2530-BLD-009 | Power Generation E-House #1 |  | PE001 | CC005 | 1 | - | 18 | 45 | 12 | 810 | 810 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | WCH-06P |  |  |  | • |  | • |  |  |  |  | 1
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 10 | 2530-BLD-010 | Power Generation E-House #2 |  | PE001 | CC005 | 1 | - | 18 | 45 | 12 | 810 | 810 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | tbd |  |  |  | • |  | • |  |  |  |  | 1
| 2530 | Milne Port | Non Process Facilities | Power Generation |  | 11 | 2530-BLD-011 | Power Generation Stores |  | PE001 | CC005 | 1 | - | 8 | 40 | 10 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | D | - | - | -
| 2540 | Milne Port | Non Process Facilities | Waste Management |  | 1 | 2540-BLD-001 | Waste Management Building |  | PX002 | CC005 | 1 | 2 | 60 | 80 | 20 | 4800 | 4800 | F-1 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2540 | Milne Port | Non Process Facilities | Waste Management |  | 2 | 2540-VP-001 | Waste Incinerators | 3 - 20' ISO Containers | TX001 | CC005 | 1 | - | 20 | 28 | 10 | 560 | 560 |  | TM | GB | RA | - | - | - | - | - | 5 | E | [9 empty] | D | C | - | - | [7 empty] | •
| 2613 | Milne Port | Fuel Systems | Fuel Dispensing Module |  | 1 | 2613-FD-013 | Diesel Fuel Dispensing Module | Existing | - | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | no scope | [5 empty] | •
| 2613 | Milne Port | Fuel Systems | Fuel Dispensing Module |  | 2 | 2613-FD-014 | Diesel Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | 1 panel by vendor FMS | [5 empty] | •
| 2614 | Milne Port | Fuel Systems | Fuel Dispensing Module |  | 1 | 2614-FD-011 | Jet-A1 Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | [12 empty] | F | - | - | 2 | 1 panel by vendor FMS | [5 empty] | •
| 2615 | Milne Port | Fuel Systems | Marine Equipment Facility |  | 1 | 2615-BLD-001 | Marine Manifold Building |  | TM001 | CC005 | 1 | - | 17 | 20 | 8 | 340 | 340 |  | FO | PF | RA | - | - | - | - | - | A | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 2720 | Milne Port | Spare | Water Systems |  | 1 | 2720-BLD-001 | Water Building |  | PX002 | CC005 | 1 | 2 | 60 | 70 | 20 | 4200 | 4200 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | P | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2731 | Milne Port | Spare | Sewage System |  | 1 | 2731-BLD-001 | Sewage Chemical Storage Container |  | PM009 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | • | - | D | - | - | - |  |  | ?
| 2731 | Milne Port | Spare | Sewage System |  | 5 | 2731-VP-005 | Sewage Treatment Plant |  | PM009 | YX001 | 1 | - | 24 | 80 | 10 | 1920 | 1920 |  | FO: TM; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: •; -: -; -: C; -: -; -: - |  | 13U | [5 empty] | •
| 2732 | Milne Port | Spare | Sewage System |  | 1 | 2732-BLD-001 | Sewage Truck Building |  | PX002 | CC005 | 1 | 2 | 20 | 30 | 20 | 600 | 600 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | - | - | P | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 2750 | Milne Port | Spare | Power Distribution System |  | 1 | 2750-BLD-001 | Accomodation Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | WCH-06P |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  | 2 | 2750-BLD-002 | Accomodation Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | WCH-06P |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  | 3 | 2750-BLD-003 | Services Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  | 4 | 2750-BLD-004 | Services Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 2750 | Milne Port | Spare | Power Distribution System |  | 5 | 2750-BLD-005 | Fuel Tank Farm E-House |  | PE003 | CC005 | 1 | - | - | 25 | - | 25 | 25 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 7231 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 1 | 7231-BLD-001 | Construction Office |  | PX001 | CC005 | 1 | 17 | 48 | 60 | 8 | 2880 | 2880 | D | TM | GB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | - | • | L | M | M | - | 40 | 1 cabinet by vendor |  |  |  | • | • |  | 2 | 2 | 1 | 1 | 1/cubicle | 1 | 1 |  | Need construction input
| 7231 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 2 | 7231-BLD-002 | Aerodrome Office |  | PX001 | CC005 | 1 | 19 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | L | - | M | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • | [8 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 1 | 7232-BLD-001 | Quarry Lunchroom | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  |  |  |  | 0 | 0 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 2 | 7232-BLD-002 | Quarry Washcar | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  |  |  |  | 0 | 0 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 3 | 7232-BLD-003 | Batch Plant Office-Lunchroom-W/C | Also used for sealift offload | PX001 | CC005 | 1 | 13 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | • | - | - | 22 | E | - | - | T | B | T | - | - | - | • | L | - | M | - | 2 | [15 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 5 | 7232-BLD-005 | Fuel Systems Office | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  | 12 | 40 |  | 480 | 480 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 6 | 7232-BLD-006 | Fuel Systems Lunchroom | Nuna Demob. Sept (TBC) | - | CC005 | 1 |  | 12 | 40 |  | 480 | 480 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 7 | 7232-BLD-007 | Site Services Lunchroom #1 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 8 | 7232-BLD-008 | Site Services Lunchroom #2 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 9 | 7232-BLD-009 | Site Services Washcar #1 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 10 | 7232-BLD-010 | Site Services Washcar #2 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7232 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 11 | 7232-BLD-011 | Smoke Shack |  | PX001 | CC005 | 1 | 10 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | L | - | - | - | [16 empty] | Need construction input
| 7234 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 1 | 7234-BLD-001 | Toromont Britespan Workshop |  | TMNT |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7234 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 2 | 7234-BLD-002 | Construction Workshop | Existing Coverall bldg in storage at Mine Site | - |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 1 | 7235-BLD-001 | Construction Equipment Building | Existing on-site. | YX001 | - | 1 |  | 40 | 60 |  | 2400 | 2400 |  | FO: FA; PF: PF; RA: G; -: - | [16 empty] | Need construction input
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 2 | 7235-BLD-002 | Site Services Heated Warehouse |  | PX004 | CC005 | 1 | 5 | 40 | 100 | 25 | 4000 | 4000 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | D | - | M | - | 2 | [15 empty] | Need construction input
| 7235 | Construction | Milne Port | Buildings, Shops & Warehouses |  | 3 | 7235-BLD-003 | Site Services Unheated Warehouse |  | PX004 | CC005 | 1 | 2 | 40 | 100 | 25 | 4000 | 4000 | F-3 | FO | PF | G | - | - | - | - | - | A | - | - | - | - | - | - | - | - | - | • | D | - | - | - | [16 empty] | Need construction input
| 7251 | Construction | Milne Port | Construction Facilities |  | 1 | 7251-BLD-001 | Concrete Batch Plant Building |  | PX004 | CC005 | 1 | 5 | 60 | 120 | 20 | 7200 | 7200 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 3111 | Tote Road | General | Communication and IT Infrastructure |  | 1 | 3111-BLD-001 | Communication Shed No. 1 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3111 | Tote Road | General | Communication and IT Infrastructure |  | 2 | 3111-BLD-002 | Communication Shed No. 2 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 3111 | Tote Road | General | Communication and IT Infrastructure |  | 3 | 3111-BLD-003 | Communication Shed No. 3 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 3111 | Tote Road | General | Communication and IT Infrastructure |  | 4 | 3111-BLD-004 | Communication Shed No. 4 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  | 1 | 3112-BLD-001 | Communication Shed No. 5 | Existing tower | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  | 2 | 3112-BLD-002 | Communication Shed No. 6 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  | 3 | 3112-BLD-003 | Communication Shed No. 7 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3112 | Tote Road | General | Communication and IT Infrastructure |  | 4 | 3112-BLD-004 | Communication Shed No. 8 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  | 1 | 3113-BLD-001 | Communication Shed No. 9 | With emergency shelter | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  | 2 | 3113-BLD-002 | Communication Shed No. 10 |  | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3113 | Tote Road | General | Communication and IT Infrastructure |  | 3 | 3113-BLD-003 | Communication Shed No. 11 | Existing tower. With emergency shelter. | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1
| 3160 | Tote Road | General | Emergency Shelters |  | 1 | 3160-BLD-001 | Emergency Shelter No. 1 | Located at Comms Shed No. 4 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  | 2 | 3160-BLD-002 | Emergency Shelter No. 2 | Located at Comms Shed No. 6 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  | 3 | 3160-BLD-003 | Emergency Shelter No. 3 | Located at Comms Shed No. 9 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 3160 | Tote Road | General | Emergency Shelters |  | 4 | 3160-BLD-004 | Emergency Shelter No. 4 | Located at Comms Shed No. 11 | PX001 | CC005 | 1 | 2 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | CB | RA | - | - | - | - | • | 22 | E | - | - | - | - | - | - | - | - | • | L | - | - | - | [14 empty] | 1 | 1
| 4110 | Mine Site | General | Communication and IT Infrastructure |  | 1 | 4110-BLD-001 | Communication Shed No. 1 | Front of mountain | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | - | [15 empty] | 1 | check fire code
| 4110 | Mine Site | General | Communication and IT Infrastructure |  | 2 | 4110-BLD-002 | Communication Shed No. 2 | Back of mountain - on haul road | PT002 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | - | • | L | M,C,X | - | -
| 4110 | Milne Port | General | Communication and IT Infrastructure |  | 3 | 4110-BLD-003 | Satellite Dish Sea Can |  | - |  | 1 | - | 8 | 40 | 10 |  |  |  | -: •; -: L; -: F; -: -; -: -
| 4211 | Mine Site | Mine | Explosives Facility |  | 1 | 4211-BLD-001 | Explosives Plant Building |  | SX001 | CC005 | 1 | - | 40 | 92 | 10 | 3680 | 3680 |  | FO: TM; PF: GB; RA: RA; -: L; -: M; -: M; -: - | 2 | 13U |  |  |  | • | [9 empty] | 1 | check fire code
| 4212 | Mine Site | Mine | Explosives Facility |  | 1 | 4212-BLD-001 | Explosives Shop |  | SX001 | CC005 | 1 | - | 40 | 100 | 18 | 4000 | 4000 |  | FO: FO; PF: GB; RA: SOGD; -: L; -: -; -: -; -: - | [15 empty] | 1
| 4213 | Mine Site | Mine | Explosives Facility |  | 1 | 4213-BLD-001 | Explosives Magazines |  | SX001 | CC005 | 1 | - | 12 | 30 | 10 | 360 | 360 |  | FO: TS; PF: GB; RA: RA; -: -; -: -; -: -; -: -
| 4281 | Mine Site | Mine | Mine Support Facilities |  | 1 | 4281-BLD-001 | Pit Office Building |  | PX001 | CC005 | 1 | 28 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • | [5 empty] | 1 |  |  | 1
| 4281 | Mine Site | Mine | Mine Support Facilities |  | 2 | 4281-BLD-002 | Pit Office Washcar | Relocate 7432-BLD-008 | PX001 | CC005 | 1 | 9 | 12 | 40 | 8 | 480 | 480 | F-3 | TS | GB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
• | 4381 | Mine Site | Material Handling | Power Distribution System |  | 1 | 4381-BLD-001 | Crushing & Screening Electrical Trailer |  | PM001 | 1 | 1 | - | 8 | 53 | 14 | 424 | 424 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | ? | ? | ? | D | C | - | - | 2 | tbd | [5 empty] | •
• | 4381 | Mine Site | Material Handling | Power Distribution System |  | 2 | 4381-BLD-002 | Crushing & Screening Electrical Trailer |  | PM001 | CC005 | 1 | - | 8 | 53 | 14 | 424 | 424 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | ? | ? | ? | D | C | - | - | 2 | tbd | [5 empty] | •
• | 4382 | Mine Site | Material Handling | Crushing and Screening |  | 1 | 4382-BLD-001 | Truck Weigh Building |  | PX004 | CC005 | 1 | 1 | 30 | 120 | 20 | 3600 | 3600 | F-3 | FO | PF | G | - | - | - | - | - | - | - | • | - | - | - | - | - | - |  | - | D | F | - | - | 8 | 24U | n/a - discuss with BIM |  |  | • |  | •
| 4431 | Mine Site | Aerodrome | Aerodrome Facilities |  | 1 | 4431-BLD-001 | Aerodrome Office |  | PX001 | CC005 | 1 | 19 | 12 | 60 | 8 | 720 | 720 | A-2 / D | TS | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | M | M | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 1 |  |  | 1 | fixed radio
| 4432 | Mine Site | Aerodrome | Aerodrome Facilities |  | 1 | 4432-BLD-001 | Aerodrome Equipment Building | HOLD - delete or re-use constr'n bldg | - | CC005 | [5 empty] | 0 | 0 | bar: - to -
| 4435 | Mine Site | Aerodrome | Aerodrome Facilities |  | 1 | 4435-BLD-001 | Aerodrome Field Electrical Centre |  | PE004 | CC005 | 1 | - | 8 | 20 | 10 | 160 | 160 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | • | - | D | F | - | - | 2 | tbd |  |  |  | • |  | • |  |  |  |  | 1 |  |  |  | waiting for harvie
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  | 1 | 4511-BLD-001 | Accommodation Service Core |  | TX001 | CC005 | 1 | - | 60 | 333 | 13 | 19980 | 19980 |  | SM | GB | RA | • | • | • | - | • | 22 | D | • | • | - | P | P | P | • | • | - | D | F/F | M | • | 4 | (by Horizon) | Honeywell 140/120xls |  |  | • | • | • | 3 |  |  | 2 | 3 | 1
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  | 2 | 4511-BLD-002 | Accommodation Office |  | TX001 | CC005 | 1 | 71 | 60 | 109 | 13 | 6540 | 6540 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 3 | 1 |  | 1/cubicle | 1/conf room |  | 1 | Fixed radio
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  | 3 | 4511-BLD-003 | Accommodation Laundry |  | TX001 | CC005 | 1 | 5 | 60 | 76 | 13 | 4560 | 4560 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  |  | Honeywell 120xls
| 4511 | Mine Site | Non Process Facilities | Accommodations Area |  | 4 | 4511-BLD-004 | Accommodation Laboratory |  | TX001 | CC005 | 1 | 5 | 56 | 60 | 13 | 3360 | 3360 |  | SM | GB | RA | • | • | - | - | • | 22 | D | • | - | - | P | P | - | - | • | - | D | C | C | - |  | 24U | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 2
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 1 | 4512-BLD-001 | Accommodation Wing AA |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 2 | 4512-BLD-002 | Accommodation Wing AB |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 3 | 4512-BLD-003 | Accommodation Wing AC |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 4 | 4512-BLD-004 | Accommodation Wing AD |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 5 | 4512-BLD-005 | Accommodation Wing AE |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 6 | 4512-BLD-006 | Accommodation Wing AF |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4512 | Mine Site | Non Process Facilities | Accommodations Area |  | 7 | 4512-BLD-007 | Accommodation Wing AG |  | TX001 | CC005 | 1 | 30 | 29 | 227 | 13 | 6583 | 6583 |  | SM | GB | RA | - | • | - | • | • | 22 | E/D | • | - | - | P | P | P | - | • | - | D | C | C | • |  | (by Horizon) | Honeywell 120xls |  |  | • | [5 empty] | 1/room | 1/room
| 4513 | Mine Site | Non Process Facilities | Accommodations Area |  | 1 | 4513-BLD-001 | Emergency Response Office |  | PX001 | CC005 | 1 | 18 | 24 | 40 | 8 | 960 | 960 | D | TM | CB | RA | • | • | - | - | • | 22 | E | - | - | T | B | T | - | - | • | - | D | F | M/C | - | 6 | (by Horizon) | Honeywell 120xls |  |  | • |  |  |  | 1 |  |  | 2 | 1 | 1 | 1 | Fixed radio
| 4513 | Mine Site | Non Process Facilities | Accommodations Area |  | 2 | 4513-BLD-002 | Emergency Response Garage |  | PX002 | CC005 | 1 | 5 | 50 | 60 | 20 | 3000 | 3000 | F-3 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F | C | - | 4 | (by Horizon) | Honeywell 120xls |  |  | • | [6 empty] | 1 |  |  | 1 | Portable radio
| 4521 | Mine Site | Non Process Facilities | Services Area |  | 1 | 4521-BLD-001 | Maintenance Building |  | PX004 | CC005 | 1 | 20 | 100 | 260 | 35 | 26000 | 26000 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | T | - | - | - | - | • | - | D | F | M | - | 4 | 13U | Honeywell 120xls |  |  | • |  |  | 1 | 1 |  |  | 2
| 4521 | Mine Site | Non Process Facilities | Services Area |  | 2 | 4521-BLD-002 | Warehouse |  | PX004 | CC005 | 1 | 5 | 60 | 160 | 25 | 9600 | 9600 | F-3 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | M | - | 4 | 13U | Honeywell 120xls |  |  | • | [6 empty] | 1
| 4521 | Mine Site | Non Process Facilities | Services Area |  | 3 | 4521-BLD-003 | Welding Shop Building |  | PX002 | CC005 | 1 | 5 | 60 | 70 | 25 | 4200 | 4200 | F-2 | FO | PF | SOGD | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - | • | - | D | F | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | [6 empty] | 1
| 4521 | Mine Site | Non Process Facilities | Services Area |  | 4 | 4521-BLD-004 | Workshop Office Building |  | PX001 | CC005 | 1 | 31 | 48 | 60 | 8 | 2880 | 2880 | D | TM | CB | RA | • | - | • | - | • | 22 | E | - | - | - | B | - | - | - | • | - | D | F | M | - | 40 | 1 cabinet by vendor | Honeywell 120xls |  |  | • | • |  |  | 1 |  |  | 3
| 4521 | Mine Site | Non Process Facilities | Services Area |  | 5 | 4521-BLD-005 | Workshop Office Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | D | - | - | -
| 4523 | Mine Site | Non Process Facilities | Services Area |  | 1 | 4523-BLD-001 | Truck Wash Building |  | PX004 | CC005 | 1 | 2 | 60 | 180 | 25 | 10800 | 10800 | F-3 | FO | PF | G | - | - | - | - | - | 22 | D | • | - | - | - | - | - | - |  | - | D | F | - | - | 2 |  | n/a - discussed with BIM
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 1 | 4530-BLD-001 | Power Generation Module #1 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 2 | 4530-BLD-002 | Power Generation Module #2 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 3 | 4530-BLD-003 | Power Generation Module #3 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 4 | 4530-BLD-004 | Power Generation Module #4 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 5 | 4530-BLD-005 | Power Generation Module #5 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 6 | 4530-BLD-006 | Power Generation Module #6 |  | PE001 | CC005 | 1 | - | 13 | 43 | 14 | 559 | 559 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | C | - | -
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 7 | 4530-BLD-007 | Power Generation E-House #1 |  | PE001 | CC005 | 1 | - | 16 | 45 | 10 | 720 | 720 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 | WCH-06P |  |  |  | • |  | • |  |  |  |  | 1
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 8 | 4530-BLD-008 | Power Generation E-House #2 |  | PE001 | CC005 | 1 | - | 16 | 45 | 10 | 720 | 720 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F/C | - | - | 2 |  |  |  |  | • |  | • |  |  |  |  | 1
| 4530 | Mine Site | Non Process Facilities | Power Generation |  | 9 | 4530-BLD-009 | Power Generation Stores |  | PE001 | CC005 | 1 | - | 8 | 40 | 10 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | D | - | - | -
| 4540 | Mine Site | Non Process Facilities | Waste Management |  | 1 | 4540-BLD-001 | Waste Management Building |  | PX002 | CC005 | 1 | 2 | 60 | 80 | 20 | 4800 | 4800 | F-1 | FO | PF | SOGD | - | - | - | - | - | 5 | D | • | - | - | - | - | - | - | • | - | D | F/C | - | - | 2 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4540 | Mine Site | Non Process Facilities | Waste Management |  | 2 | 4540-VP-001 | Waste Incinerators | 3 - 20' ISO Containers | TX001 | CC005 | 1 | - | 20 | 28 | 10 | 560 | 560 |  | TM | GB | RA | - | - | - | - | - | 5 | E | [9 empty] | D | C | - | - | [7 empty] | •
| 4613 | Mine Site | Fuel Systems | Fuel Dispensing Module |  | 1 | 4613-FD-013 | Diesel Fuel Dispensing Module |  | PM004 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | FO: SC; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: F; -: -; -: - | 2 | [6 empty] | •
| 4712 | Mine Site | Site Utilities | Raw Water Intake |  | 1 | 4712-BLD-001 | Raw Water Pumphouse |  | PM003 | CC005 | 1 | - | 8 | 20 | 8 | 160 | 160 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | • | - | D | M | - | - |  | 13U |  |  |  | • |  | • |  |  |  |  | 1
| 4720 | Mine Site | Site Utilities | Water Systems |  | 1 | 4720-BLD-001 | Water Building |  | PX002 | CC005 | 1 | 2 | 60 | 70 | 20 | 4200 | 4200 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | P | - | - | - | - | • | - | D | F | M | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4731 | Mine Site | Site Utilities | Sewage System |  | 1 | 4731-BLD-001 | Sewage Chemical Storage Container |  | PM009 | CC005 | 1 | - | 8 | 40 | 8 | 320 | 320 |  | SC | GB | RA | - | - | - | - | - | 5 | E | • | - | - | - | - | - | - | • | - | D | - | - | - |  |  | tbc
| 4731 | Mine Site | Site Utilities | Sewage System |  | 5 | 4731-VP-005 | Sewage Treatment Plant |  | PM009 | CC005 | 1 | - | 24 | 80 | 10 | 1920 | 1920 |  | FO: TM; PF: GB; RA: RA; -: -; -: -; -: -; -: -; -: -; -: •; -: -; -: C; -: - | [7 empty] | •
| 4732 | Mine Site | Site Utilities | Sewage System |  | 1 | 4732-BLD-001 | Sewage Truck Building |  | PX002 | CC005 | 1 | 2 | 20 | 30 | 20 | 600 | 600 | F-3 | FO | PF | G | - | - | - | - | - | 5 | D | • | - | - | - | P | - | - | • | - | D | F/C | - | - | 4 | 1 cabinet by vendor | Honeywell 120xls |  |  | • |  | • |  |  |  |  | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 1 | 4750-BLD-001 | Accomodation Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 2 | 4750-BLD-002 | Accomodation Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 3 | 4750-BLD-003 | Services Area E-House #1 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 4 | 4750-BLD-004 | Services Area E-House #2 |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 5 | 4750-BLD-005 | Fuel Tank Farm E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 6 | 4750-BLD-006 | Aerodrome Area E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | - | - | - | [12 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 7 | 4750-BLD-007 | Raw Water Supply E-House |  | PE003 | CC005 | 1 | - | 16 | 25 | 11 | 400 | 400 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | - | - | - | [12 empty] | 1
| 4750 | Mine Site | Site Utilities | Power Distribution System |  | 8 | 4750-BLD-008 | Crushing & Screening E-House |  | PE003 | CC005 | 1 | - | 16 | 40 | 11 | 640 | 640 |  | SM | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | • | - | - | D | F | - | - | 2 | 13U |  |  |  | • | [6 empty] | 1 |  |  |  | Mineral Processing E-House
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 1 | 7432-BLD-001 | Batch Plant Office-Lunchroom-W/C |  | PX001 | CC005 | 1 | 13 | 12 | 60 | 8 | 720 | 720 | A-2/D | TS | CB | RA | • | • | • | - | - | 22 | E | - | - | T | B | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 3 | 7432-BLD-003 | Fuel Systems Lunchroom |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 4 | 7432-BLD-004 | Fuel Systems Washcar |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 5 | 7432-BLD-005 | Site Services Lunchroom #1 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 6 | 7432-BLD-006 | Site Services Lunchroom #2 |  | PX001 | CC005 | 1 | 30 | 12 | 60 | 8 | 720 | 720 | A-2 | TS | CB | RA | - | - | • | - | - | 22 | E | - | - | - | B | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 7 | 7432-BLD-007 | Site Services Washcar #1 |  | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 8 | 7432-BLD-008 | Site Services Washcar #2 | Relocate to 4281-BLD-002 | PX001 | CC005 | 1 | 9 | 12 | 32 | 8 | 384 | 384 | F-3 | TS | CB | RA | - | • | - | - | - | 22 | E | - | - | T | - | T | - | - | - | • | L | - | - | -
| 7432 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 9 | 7432-BLD-009 | Smoke Shack |  | PX001 | CC005 | 1 | 10 | 8 | 20 | 8 | 160 | 160 | A-2 | SC | GB | RA | - | - | - | - | - | 22 | E | • | - | - | - | - | - | - | - | - | L | - | - | - | [16 empty] | Need construction input
| 7434 | Construction | Mine Site | Buildings, Shops & Warehouses |  | 1 | 7434-BLD-001 | Toromont Britespan Workshop |  | TMNT |  | 1 | tbd | [6 empty] | FO: FA; PF: GB; RA: G
| 7451 | Construction | Mine Site | Construction Facilities |  | 1 | 7451-BLD-001 | Concrete Batch Plant Building |  | PX004 | CC005 | 1 | 5 | 60 | 120 | 20 | 7200 | 7200 | F-3 | FO | PF | G | - | - | - | - | - | 22 | M | • | - | - | - | - | - | - | - | • | L | - | - | - | [16 empty] | Need construction input
288
[12 empty] | NOTES | [7 empty] | RA: BUILDING TYPE; -: FOUNDATION TYPE; -: FLOOR FINISH
|  |  | 4 | In progress | [7 empty] | 1. Occupancy for washcars is number of male water closets/urinals. Ratio of male to female water closets is 5:1. | [7 empty] | RA: FO; -: Fold-away Building (Steel); -: GB; -: Gravel Base - Skidded Building; -: SOG; -: Slab on grade
| 03/09/2013 |  | 3 | Approved for Use | S. Carnegie | J. Cleland |  | S. Perry | D. Matthews |  |  | 2. Buiding supply package "TMNT" is Toromont CAT supply arranged by Baffinland. | [7 empty] | RA: FA; -: Fabric w/ Sea Can Walls; -: PP; -: Precast Piers; -: SOGD; -: Slab on grade C/W Drainage
| 22/07/2013 |  | 2 | Approved for Use | K. Imai | J. Cleland |  | S. Perry | D. Matthews | [10 empty] | RA: SC; -: ISO Shipping Contianer; -: PF; -: Precast Footing (Perimeter Beam); -: G; -: Gravel
| 10/07/2013 |  | 1 | Approved for Use | K. Imai | J. Cleland |  | S. Perry | D. Matthews | [10 empty] | RA: TS; -: Trailer - Single; -: CB; -: Timber Cribbing to Elevate Building; -: RA; -: Raised Steel or Wooden Floor
| 10/04/2013 |  | 0 | Approved for Use | K. Imai | J. Lemay |  | S. Perry | D. Matthews | [10 empty] | RA: TM; -: Trailer - Modular (2 or more modules); -: -; -: Not Applicable
| Date |  | Rev | Status | Prepared By | Checked By |  | Approved By | Approved By | [10 empty] | RA: SM; -: Special Modular / Prefabricated

## PIVOT_ESTIMATE DETAILS 1 (hidden)
Level 0 |  | Level 1 |  | Level 2 |  | Level 3
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator)
|  |  |  | 2550 | Waste Disposal | 2550 | Waste Disposal
|  |  |  | 2510 | Accommodations Area | 2511 | Service Core
[6 empty] | 2512 | Accommodation Wings
[6 empty] | 2510 | Accommodations Area
[6 empty] | 2511 | Service Core
[6 empty] | 2512 | Accommodation Wings
[6 empty] | 2513 | Emergency Services Building
[6 empty] | 2513 | Emergency Services Building
|  |  |  | 2520 | Services Area | 2521 | Services Buildings
[6 empty] | 2521 | Services Buildings
[6 empty] | 2521 | Services Buildings
[6 empty] | 2522 | Services Equipment
[6 empty] | 2523 | Services Area
|  |  |  | 2530 | Power Generation | 2530 | Power Generation
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure
|  |  |  | 2130 | Site Development | 2131 | Construction Laydown
[6 empty] | 2133 | Materials Handling
[6 empty] | 2134 | (blank)
[6 empty] | 2136 | Milne Port
[6 empty] | 2138 | Quarry Development
[6 empty] | 2139 | Site Roads
|  |  |  | 2140 | Mobile Equipment | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
|  |  |  | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure
|  |  |  | 2140 | Mobile Equipment | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
[6 empty] | 2143 | Mobile Maintenance Equipment
[6 empty] | 2144 | Mobile Site Services Equipment
[6 empty] | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
[6 empty] | 2143 | Mobile Maintenance Equipment
[6 empty] | 2144 | Mobile Site Services Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2200 | Marine | 2220 | Ore Dock | 2221 | Dock Structure (includes ship loader foundations)
[6 empty] | 2225 | Mooring Buoys
[6 empty] | 2230 | Causeway
|  |  |  | 2240 | Transshipment and Marine Vessels | 2240 | Transshipment and Marine Vessels
|  |  |  | 2220 | Ore Dock | 2223 | Dock Office
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond
[6 empty] | 2341 | Ore Stacking System
|  |  |  | 2340 | Stockpile | 2341 | Ore Stacking System
[6 empty] | 2342 | Ore Reclaim System
[6 empty] | 2341 | Ore Stacking System
[6 empty] | 2342 | Ore Reclaim System
[6 empty] | 2342 | Ore Reclaim System
|  |  |  | 2350 | Ship Loading | 2351 | Ship Loading System
[6 empty] | 2351 | Ship Loading System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2430 | Aerodrome Facilities
[6 empty] | 2435 | Field Electrical Centre
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke
|  |  |  | 2610 | Milne Tank Farm | 2614 | Jet-A System
[6 empty] | 2610 | Milne Tank Farm
[6 empty] | 2613 | Arctic Diesel System
[6 empty] | 2613 | Arctic Diesel System
[6 empty] | 2614 | Jet-A System
[6 empty] | 2614 | Jet-A System
[6 empty] | 2615 | Marine Pipeline
[6 empty] | 2619 | Power Generation
[6 empty] | 2616 | Weatherhaven camp
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Treated Effluent Discharge
[6 empty] | 2735 | Off Spec Effluent Pond
|  |  |  | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System
|  |  |  | 2720 | Water Systems | 2720 | Water Systems
[6 empty] | 2720 | Water Systems
[6 empty] | 2720 | Water Systems
|  |  |  | 2730 | Sewage System | 2731 | Sewage Treatment Systems
[6 empty] | 2731 | Sewage Treatment Systems
[6 empty] | 2732 | Sewage Truck Building
[6 empty] | 2732 | Sewage Truck Building
[6 empty] | 2734 | Treated Effluent Discharge
|  |  |  | 2750 | Power Distribution System | 2750 | Power Distribution System
[6 empty] | 2750 | Power Distribution System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 2710 | Additional Tanks | 2710 | Additional Tanks
|  |  |  | 0 | Power Distribution System |  | Power Distribution System
3000 | Mine Site | 3500 | Non Process Facilities | 3510 | Accommodations Area | 3512 | Accommodation Wings
| Tote Road | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 3100 | General | 3110 | Communication and IT Infrastructure | 3114 | Communications Facility No. 4
|  |  |  | 3130 | Site Development | 3130 | Site Development
[6 empty] | 3131 | Road Upgrade
[6 empty] | 3132 | River Crossing at STA 17
[6 empty] | 3133 | River Crossing at STA 62
[6 empty] | 3134 | River Crossing at STA 80
[6 empty] | 3135 | River Crossing at STA 97
[6 empty] | 3136 | Mary River
[6 empty] | 3138 | Borrow Source at Km 102
Borrow Source at Km 97/98
Borrow Source at P1
Quarry at Q1
Quarry at Q11
Quarry at Q19
Quarry at Q7
Quarry Development
Unidentified Borrow Sources
Borrow Source at Km 2
Quarry at Q13
Quarry at Q14
Quarry at Q15
Quarry at Q16A
Quarry at P5
Quarry at P6
Quarry at P7
Quarry at P8
Quarry at P10
Quarry at P13
Quarry at P14
Quarry at P15
Quarry at PQ5A
Quarry at PQ5B
Quarry at PQ2A
Quarry at PQ6A
Quarry at PQ6B
Quarry at PQ12B
Quarry at PQ14A
Quarry at PQ14B
Quarry at PQ4A
Quarry at PQ4B
Quarry at Q12
Quarry at Q5
Q13 Quarry (marginal increase to existing)
[6 empty] | 3139 | Infrastructure Pads
[6 empty] | TBD | Sea-can bridge at STA 17
Sea-can bridge at STA 62
Sea-can bridge at STA 80
Sea-can bridge at STA 97
|  |  |  | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1
[6 empty] | 3112 | Communications Facility No. 2
[6 empty] | 3113 | Communications Facility No. 3
|  |  |  | 3160 | Emergency Shelters | 3160 | Emergency Shelters
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 3200 | General | 3210 | Exploration Camp & Facilities | 3212 | Hardwall Camp
[5 empty] | Explosives Facility | 3213 | Explosives Magazines
4000 | Construction Facilities & Services | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
| Milne Port | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
| Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
Mine Mobile Equipment
Raw Water System
[6 empty] | 4133 | Ore Crushing and Loading
[6 empty] | 4135 | Explosives Pads
[6 empty] | 4138 | Quarry Development
[6 empty] | 4139 | Site Roads
|  |  |  | 4140 | Mobile Equipment | 4140 | Mobile Equipment
|  |  |  | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment
[6 empty] | 4142 | Mobile Materials Handling Equipment
Mobile Site Services Equipment
[6 empty] | 4143 | Mobile Maintenance Equipment
[6 empty] | 4144 | Mobile Site Services Equipment
[6 empty] | 4141 | Mine Mobile Equipment
[6 empty] | 4142 | Mobile Materials Handling Equipment
[6 empty] | 4143 | Mobile Maintenance Equipment
[6 empty] | 4144 | Mobile Site Services Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure
[5 empty] | Site Development | 4136 | Tote Road
|  | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building
[6 empty] | 4212 | Explosives Shop
[6 empty] | 4213 | Explosives Magazines
|  |  |  | 4220 | Accommodations Area | 4222 | Explosive pad haul road
[5 empty] | Haul Roads | 4221 | Pit 1 Haul Road
|  |  |  | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump
[5 empty] | Waste Rock Pond | 4230 | Waste Rock Pond
|  |  |  | 4250 | Open Pit Development | 4250 | Open Pit Development
|  |  |  | 4280 | Mine Support Facilities | 4281 | Pit Office Building
|  |  |  | 4280 | Mine Support Facilities | 4281 | Pit Office Building
[6 empty] | 4281 | Pit Office Building
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System
[6 empty] | 4382 | Truck Weigh Facility
[6 empty] | 4385 | Crushing Stockpile Settling Pond
|  |  |  | 4380 | Crushing and Screening | 4381 | Crushing and Screening System
[6 empty] | 4382 | Truck Weigh Facility
[6 empty] | 4385 | Crushing Stockpile Settling Pond
[6 empty] | 4381 | Crushing and Screening System
[6 empty] | 4381 | Crushing and Screening System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4400 | Aerodrome | 4410 | Runway & Apron | 4410 | Runway & Apron
|  |  |  | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities
[6 empty] | 4436 | Airfield Lighting and Visual Aids
[6 empty] | 4439 | Power Generation
|  |  |  | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office
[6 empty] | 4431 | Aerodrome Office
[6 empty] | 4432 | Equipment Building
[6 empty] | 4433 | Plant & Equipment
[6 empty] | 4435 | Field Electrical Centre
[6 empty] | 4434 | Plant & Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building
|  | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings
|  |  |  | 4540 | Waste Management | 4540 | Waste Management
|  |  |  | 4510 | Accommodations Area | 4510 | Accommodations Area
[6 empty] | 4511 | Service Core
[6 empty] | 4512 | Accommodation Wings
[6 empty] | 4513 | Emergency Services Building
|  |  |  | 4520 | Services Area | 4521 | Services Buildings
[6 empty] | 4522 | Services Equipment
[6 empty] | 4523 | Truck Wash Facility
|  |  |  | 4530 | Aerodrome Facilities | 4530 | Aerodrome Facilities
[5 empty] | Crushing and Screening | 4530 | Crushing and Screening
[5 empty] | Mobile Equipment | 4530 | Mobile Equipment
[5 empty] | Power Generation | 4530 | Power Generation
[5 empty] | Raw Water Intake | 4530 | Raw Water Intake
[5 empty] | Services Area | 4530 | Services Area
[5 empty] | Waste Management | 4530 | Waste Management
|  |  |  | 4540 | Waste Management | 4540 | Waste Management
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4614 | Jet-A System
[6 empty] | 4619 | Generator
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4700 | Site Utilities | 4710 | Raw Water Intake | 4711 | Raw Water Jetty
[6 empty] | 4712 | Raw Water System
|  |  |  | 4720 | Water Systems | 4720 | Water Systems
|  |  |  | 4730 | Sewage System | 4731 | Sewage Treatment Systems
[6 empty] | 4732 | Sewage Truck Building
[6 empty] | 4733 | Treated Effluent Pond
[6 empty] | 4734 | Treated Effluent Discharge
|  |  |  | 4750 | Power Distribution System | 4750 | Power Distribution System
|  |  |  | 4720 | Water Systems | 4720 | Water Systems
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 4740 | Additional Tanks | 4740 | Additional Tanks
| Tote Road | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp
[6 empty] | 7212 | Hardwall Camp
[6 empty] | 7213 | Utilities & Services
[6 empty] | 7214 | Off-Spec Effluent Pond(s)
|  |  |  | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities
[6 empty] | 7232 | Workforce Facilities
[6 empty] | 7234 | Garages & Workshops
[6 empty] | 7235 | Warehouses
[6 empty] | 7238 | Civil Contractor Buildings
|  |  |  | 7240 | Vehicles and Equipment | 7241 | Company Vehicles
[6 empty] | 7242 | Emergency Response Equipment
[6 empty] | 7244 | Construction Power Supply
[6 empty] | 7243 | Site Operations Mobile Equipment
[6 empty] | 7245 | Cranes and Lifting Equipment
|  |  |  | 7250 | Construction Facilities | 7251 | Concrete Facilities
[6 empty] | 7252 | Explosives Facilities
|  |  |  | 7270 | Camp & Site Services | 7271 | Camp Operations & Catering
[6 empty] | 7273 | Site Operations
[6 empty] | 7275 | Maintenance and Repair
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 7100 | Project Wide | 7110 | Communications & IT | 7111 | Communications Services
|  |  |  | 7120 | Air Services | 7121 | Jet Service
[6 empty] | 7122 | Local Air Charter
[6 empty] | 7123 | Helicopter Service
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 7300 | Tote Road | (blank) | (blank) | (blank) | (blank)
|  |  |  | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment
|  | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp
[6 empty] | 7412 | Utilities & Services
|  |  |  | 7430 | Buildings, Shops & Warehouses | 7431 | Office Facilities
[6 empty] | 7432 | Workforce Facilities
[6 empty] | 7434 | Garages & Workshops
[6 empty] | 7435 | Warehouses
|  |  |  | 7470 | Camp & Site Services | 7470 | Camp & Site Services
[6 empty] | 7471 | Camp Operations & Catering
[6 empty] | 7473 | Site Operations
[6 empty] | 7475 | Maintenance and Repair
|  |  |  | 7480 | Construction Services | 7482 | Heavy Transport Services
[6 empty] | 7484 | Explosives Supply Services
|  |  |  | 7450 | Construction Facilities | 7451 | Concrete Facilities
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 7440 | Vehicles and Equipment | 7441 | Company Vehicles
[6 empty] | 7443 | Site Operations Mobile Equipment
[6 empty] | 7444 | Construction Power Supply
[6 empty] | 7445 | Cranes and Lifting Equipment
8000 | Other Indirects | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | EPCM Services
Project Management, Engineering and Procurement
[6 empty] | 8112 | Project Management, Engineering and Procurement
|  |  |  | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement
[6 empty] | TBD | Closure & Post Closure Monitoring
Environmental Site Assessment
|  |  |  | TBD | Material Disposal | TBD | Fuel
Ammonium Nitrate (explosive Material)
Off-Site Disposal of Waste & Material
Contaminated Soil Treatment
[5 empty] | Mobilization | TBD | Mobilization and Demobilization
Worker Accommodation & Camp Operation
|  |  |  | (blank) | (blank) | (blank) | (blank)
9000 | Owner Accounts | 9100 | Owner Accounts | 9120 | Project Management | 9121 | Owner Accounts - Project Management
|  |  |  | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency
|  |  |  | (blank) | (blank) | (blank) | (blank)
Grand Total

## Sheet8 (hidden)
Row Labels
25ka
A2
A3
A3l
A4
Br
cable
CP
CS
Cu
CV
EG
FF1
FF1-c
FF2
FF2-c
FF3
FF3-c
FF4
FW
MISC
MM1
MM2
MM3
MT1
MT1-d
MT2
MT2-d
MT3-d
MT4-d
O1
O2
O3
piping
VP1
VP2
VP3
VP6
(blank)
MT5-d
A5
CON
Grand Total

## Removed Items 2015 R (hidden)
Items Removed from EBS
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Notes | Uncertainty | Required Reclamation Activities
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-001 | 200 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 44.8333 | 672.5 | 4479.4499 | 6725 | 11876.9499 | 1 | 200 | 100% | 0% | 0% | 100% | 11876.9499 | 0 | 0 | 11876.9499 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3958.9833 | 3958.9833 | 3958.9833 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-001 | 200 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-001 | 200 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Change Rooms - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-004 | 267.5608 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 59.9782 | 899.6731 | 5992.6252 | 8996.7307 | 15889.0291 | 1 | 267.5608 | 100% | 0% | 0% | 100% | 15889.0291 | 0 | 0 | 15889.0291 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 5296.343 | 5296.343 | 5296.343 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Change Rooms - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-004 | 267.5608 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 004 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Change Rooms - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-004 | 267.5608 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-005 | 200.6706 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 44.9837 | 674.7548 | 4494.4689 | 6747.5481 | 11916.7718 | 1 | 200.6706 | 100% | 0% | 0% | 100% | 11916.7718 | 0 | 0 | 11916.7718 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3972.2573 | 3972.2573 | 3972.2573 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-005 | 200.6706 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-005 | 200.6706 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2511-BLD-006 | 210 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 47.075 | 706.125 | 4703.4224 | 7061.25 | 12470.7974 | 1 | 210 | 100% | 0% | 0% | 100% | 12470.7974 | 0 | 0 | 12470.7974 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 4156.9325 | 4156.9325 | 4156.9325 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 2511-BLD-006 | 210 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 2511-BLD-006 | 210 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BE - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-005 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing BE - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-005 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BE - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-005 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BF - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-006 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing BF - Demolish and foundations - Gravel Base - Skidded Building | 2512-BLD-006 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BF - Demolish floor finish - Raised Steel or Wooden Floor | 2512-BLD-006 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 007 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BG - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-007 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing BH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2512-BLD-008 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Maintenance Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-005 | 557.4183 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 312.3865 | 1312.0232 | 31211.5898 | 46857.9726 | 79381.5856 | 1 | 557.4183 | 100% | 0% | 0% | 100% | 79381.5856 | 0 | 0 | 79381.5856 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 26460.5285 | 26460.5285 | 26460.5285 | 0 | 0 | 0 | 0 | 0 | Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Maintenance Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-005 | 557.4183 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 80.9407 | 1214.1098 | 8087.0542 | 12141.0978 | 21442.2617 | 0.75 | 418.0637 | 100% | 0% | 0% | 100% | 21442.2617 | 0 | 0 | 21442.2617 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 7147.4206 | 7147.4206 | 7147.4206 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 005 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Maintenance Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 2521-BLD-005 | 557.4183 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 69.6773 | 1045.1592 | 6961.6929 | 10451.5924 | 18458.4445 | 0 | 0 | 100% | 0% | 0% | 100% | 18458.4445 | 0 | 0 | 18458.4445 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 6152.8148 | 6152.8148 | 6152.8148 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2521-BLD-006 | 148.6449 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 83.3031 | 349.8729 | 8323.0906 | 12495.4594 | 21168.4228 | 1 | 148.6449 | 100% | 0% | 0% | 100% | 21168.4228 | 0 | 0 | 21168.4228 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 7056.1409 | 7056.1409 | 7056.1409 | 0 | 0 | 0 | 0 | 0 | Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2- Demolish and foundations - Precast Footing (Perimeter Beam) | 2521-BLD-006 | 148.6449 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 21.5842 | 323.7626 | 2156.5478 | 3237.6261 | 5717.9365 | 0.75 | 111.4837 | 100% | 0% | 0% | 100% | 5717.9365 | 0 | 0 | 5717.9365 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1905.9788 | 1905.9788 | 1905.9788 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2 - Demolish floor finish - Slab on grade C/W Drainage | 4521-BLD-007 | 334.451 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 41.8064 | 627.0955 | 4177.0157 | 6270.9554 | 11075.0667 | 0 | 0 | 100% | 0% | 0% | 100% | 11075.0667 | 0 | 0 | 11075.0667 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3691.6889 | 3691.6889 | 3691.6889 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Truck Wash (Repurposed Warehouse) - Demolish and Decontaminate Building - Fold-away Building (Steel) | 2523-BLD-001 | 371.6122 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 208.2577 | 874.6822 | 20807.7265 | 31238.6484 | 52921.0571 | 1 | 371.6122 | 100% | 0% | 0% | 100% | 52921.0571 | 0 | 0 | 52921.0571 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 17640.3524 | 17640.3524 | 17640.3524 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Truck Wash (Repurposed Warehouse) - Demolish and foundations - Precast Footing (Perimeter Beam) | 2523-BLD-001 | 371.6122 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 53.9604 | 809.4065 | 5391.3694 | 8094.0652 | 14294.8411 | 0.75 | 278.7091 | 100% | 0% | 0% | 100% | 14294.8411 | 0 | 0 | 14294.8411 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 4764.947 | 4764.947 | 4764.947 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2523 | Services Area | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Truck Wash (Repurposed Warehouse) - Demolish floor finish - Gravel | 2523-BLD-001 | 371.6122 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-008 | 37.1612 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3303 | 124.9546 | 832.3091 | 1249.5459 | 2206.8096 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 2206.8096 | 0 | 0 | 2206.8096 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 735.6032 | 735.6032 | 735.6032 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-008 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-008 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Services Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 2750-BLD-009 | 37.1612 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3303 | 124.9546 | 832.3091 | 1249.5459 | 2206.8096 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 2206.8096 | 0 | 0 | 2206.8096 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 735.6032 | 735.6032 | 735.6032 | 0 | 0 | 0 | 0 | 0 | Not Contaminated
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Services Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 2750-BLD-009 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2750 | Power Distribution System | 2750 | Power Distribution System | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Services Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 2750-BLD-009 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  |  | A4 | Grade & Re-Contour Type A quarry | A4 | Site Works | Grade and Re-Contour Significant Disturbed Areas |  | Unidentified High Priority Disturbed Areas |  | 31521 | m2 | 0.019035 | 0.21937 | 1.9035 | 0.59482 | 2.7154 | 599.9966 | 6914.9194 | 59999.6606 | 18749.2588 | 85663.8387 | 0 | 0 | 100% | 0% | 0% | 100% | 85663.8387 | 0 | 0 | 85663.8387 | Type A 2AM-MRY1325 | Remove | 2014 | Direct | 50% | 50% | [6 empty] | 42831.9193 | 42831.9193 | 0 | 0 | 0 | 0 | 0 | 0 | Based on EBA Report
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3138 | Unidentified Borrow Sources |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Unidentified Borrow Sources |  | 948730 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 12039.2707 | 138751.7625 | 1203927.0742 | 376214.4659 | 1718893.3026 | 0 | 0 | 100% | 0% | 0% | 100% | 1718893.3026 | 0 | 0 | 1718893.3026 | Type A 2AM-MRY1325 | Remove | 2014 | Direct | 50% | 50% | [6 empty] | 859446.6513 | 859446.6513 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Assumption
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Pit Office Lunchroom Building - Demolish and Decontaminate Building - Trailer - Single | 4281-BLD-002 | 66.8902 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 14.9946 | 224.9183 | 1498.1563 | 2249.1827 | 3972.2573 | 1 | 66.8902 | 100% | 0% | 0% | 100% | 3972.2573 | 0 | 0 | 3972.2573 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1324.0858 | 1324.0858 | 1324.0858 | 0 | 0 | 0 | 0 | 0 | 224.9183
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Pit Office Lunchroom Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4281-BLD-002 | 66.8902 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 8.247 | 78.7214 | 524.3547 | 787.2139 | 1390.29 | 0.3 | 20.0671 | 100% | 0% | 0% | 100% | 1390.29 | 0 | 0 | 1390.29 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 463.43 | 463.43 | 463.43 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4200 | Mine | 4280 | Mine Support Facilities | 4281 | Pit Office Building | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Pit Office Lunchroom Building - Demolish floor finish - Raised Steel or Wooden Floor | 4281-BLD-002 | 66.8902 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Service Core Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-001 | 220 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 49.3167 | 739.75 | 4927.3949 | 7397.5 | 13064.6449 | 1 | 220 | 100% | 0% | 0% | 100% | 13064.6449 | 0 | 0 | 13064.6449 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 4354.8816 | 4354.8816 | 4354.8816 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Service Core Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-001 | 220 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 001 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Service Core Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-001 | 220 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Exercise Facility - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-005 | 200.6706 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 44.9837 | 674.7548 | 4494.4689 | 6747.5481 | 11916.7718 | 1 | 200.6706 | 100% | 0% | 0% | 100% | 11916.7718 | 0 | 0 | 11916.7718 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3972.2573 | 3972.2573 | 3972.2573 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Exercise Facility - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-005 | 200.6706 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 005 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Exercise Facility - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-005 | 200.6706 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Arctic Corridor Extension - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4511-BLD-006 | 60 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.45 | 201.75 | 1343.835 | 2017.5 | 3563.085 | 1 | 60 | 100% | 0% | 0% | 100% | 3563.085 | 0 | 0 | 3563.085 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1187.695 | 1187.695 | 1187.695 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Arctic Corridor Extension - Demolish and foundations - Gravel Base - Skidded Building | 4511-BLD-006 | 60 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Arctic Corridor Extension - Demolish floor finish - Raised Steel or Wooden Floor | 4511-BLD-006 | 60 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AH - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-008 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AH - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-008 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AH - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-008 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AI - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-009 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AI - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-009 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AI - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-009 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AJ - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-010 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AJ - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-010 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AJ - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-010 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AK - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-011 | 458.012 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 102.671 | 1540.0654 | 10258.2092 | 15400.6537 | 27198.9282 | 1 | 458.012 | 100% | 0% | 0% | 100% | 27198.9282 | 0 | 0 | 27198.9282 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 9066.3094 | 9066.3094 | 9066.3094 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AK - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-011 | 458.012 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AK - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-011 | 458.012 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AL - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-012 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AL - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-012 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 012 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AL - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-012 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Wing AM - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4512-BLD-013 | 611.5807 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 137.096 | 2056.4402 | 13697.7264 | 20564.4022 | 36318.5688 | 1 | 611.5807 | 100% | 0% | 0% | 100% | 36318.5688 | 0 | 0 | 36318.5688 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12106.1896 | 12106.1896 | 12106.1896 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Wing AM - Demolish and foundations - Gravel Base - Skidded Building | 4512-BLD-013 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings | 013 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Wing AM - Demolish floor finish - Raised Steel or Wooden Floor | 4512-BLD-013 | 611.5807 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR1-c | Buildings (Contaminated) | Single Trailers (modular) |  | Workshop Office Washcar - Demolish and Decontaminate Building - Trailer - Single | 4521-BLD-009 | 35.6748 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 19.9927 | 119.9564 | 1997.5417 | 2998.9102 | 5116.4084 | 1 | 35.6748 | 100% | 0% | 0% | 100% | 5116.4084 | 0 | 0 | 5116.4084 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1705.4695 | 1705.4695 | 1705.4695 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Workshop Office Washcar - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-009 | 35.6748 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 4.3984 | 41.9847 | 279.6558 | 419.8474 | 741.488 | 0.3 | 10.7024 | 100% | 0% | 0% | 100% | 741.488 | 0 | 0 | 741.488 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 247.1627 | 247.1627 | 247.1627 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 009 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Workshop Office Washcar - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-009 | 35.6748 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Welding Shop Building #2 - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4521-BLD-007 | 334.451 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 187.4319 | 787.2139 | 18726.9539 | 28114.7836 | 47628.9514 | 1 | 334.451 | 100% | 0% | 0% | 100% | 47628.9514 | 0 | 0 | 47628.9514 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 15876.3171 | 15876.3171 | 15876.3171 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 007 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Welding Shop Building #2 - Demolish and foundations - Precast Footing (Perimeter Beam) | 4521-BLD-007 | 334.451 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 48.5644 | 728.4659 | 4852.2325 | 7284.6587 | 12865.357 | 0.75 | 250.8382 | 100% | 0% | 0% | 100% | 12865.357 | 0 | 0 | 12865.357 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 4288.4523 | 4288.4523 | 4288.4523 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 006 | BLD | CS | Slab on Grade - ASSUME 300mm thick | CS | Flooring / Foundations | Slab on Grade |  | Welding Shop Building #2- Demolish floor finish - Slab on grade | 2521-BLD-006 | 148.6449 | m2 | 0.125 | 1.875 | 12.4892 | 18.75 | 33.1142 | 18.5806 | 278.7091 | 1856.4514 | 2787.0913 | 4922.2519 | 0 | 0 | 100% | 0% | 0% | 100% | 4922.2519 | 0 | 0 | 4922.2519 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1640.7506 | 1640.7506 | 1640.7506 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Truck Workshop Office Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-008 | 267.5608 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 149.9455 | 899.6731 | 14981.5631 | 22491.8269 | 38373.063 | 1 | 267.5608 | 100% | 0% | 0% | 100% | 38373.063 | 0 | 0 | 38373.063 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12791.021 | 12791.021 | 12791.021 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Truck Workshop Office Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-008 | 267.5608 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 32.988 | 314.8856 | 2097.4188 | 3148.8558 | 5561.1602 | 0.3 | 80.2682 | 100% | 0% | 0% | 100% | 5561.1602 | 0 | 0 | 5561.1602 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1853.7201 | 1853.7201 | 1853.7201 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Truck Workshop Office Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-008 | 267.5608 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FTR2-c | Buildings (Contaminated) | Double Trailer (2 or more) |  | Ore Haul Maintenance Building - Demolish and Decontaminate Building - Trailer - Modular (2 or more modules) | 4521-BLD-006 | 2415.4791 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 1353.6748 | 8122.0486 | 135250.2224 | 203051.2147 | 346423.4857 | 1 | 2415.4791 | 100% | 0% | 0% | 100% | 346423.4857 | 0 | 0 | 346423.4857 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 115474.4952 | 115474.4952 | 115474.4952 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD | FW | Timber Cribbing (480 ft2) | FT | Flooring / Foundations | Timber Cribbing |  | Ore Haul Maintenance Building - Demolish and foundations - Timber Cribbing to Elevate Building | 4521-BLD-006 | 2415.4791 | m2 | 0.12329 | 1.1769 | 7.839 | 11.7688 | 20.7847 | 297.8084 | 2842.717 | 18935.0311 | 28427.1701 | 50204.9182 | 0.3 | 724.6437 | 100% | 0% | 0% | 100% | 50204.9182 | 0 | 0 | 50204.9182 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 16734.9727 | 16734.9727 | 16734.9727 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 006 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Ore Haul Maintenance Building - Demolish floor finish - Raised Steel or Wooden Floor | 4521-BLD-006 | 2415.4791 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | FF2-c | Fold Away Building Contaminated (480 ft2) | FFL-c | Buildings (Contaminated) | Fold Away Building |  | Ore Haul Truck Wash Building - Demolish and Decontaminate Building - Fold-away Building (Steel) | 4523-BLD-002 | 483.0958 | m2 | 0.56042 | 2.3537 | 55.9931 | 84.0625 | 142.4094 | 270.735 | 1137.0868 | 27050.0445 | 40610.2429 | 68797.3742 | 1 | 483.0958 | 100% | 0% | 0% | 100% | 68797.3742 | 0 | 0 | 68797.3742 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 22932.4581 | 22932.4581 | 22932.4581 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Ore Haul Truck Wash Building - Demolish and foundations - Precast Footing (Perimeter Beam) | 4523-BLD-002 | 483.0958 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 70.1486 | 1052.2285 | 7008.7803 | 10522.2847 | 18583.2935 | 0.75 | 362.3219 | 100% | 0% | 0% | 100% | 18583.2935 | 0 | 0 | 18583.2935 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 6194.4312 | 6194.4312 | 6194.4312 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 002 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Ore Haul Truck Wash Building - Demolish floor finish - Gravel | 4523-BLD-002 | 483.0958 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #7 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-022 | 51.9328 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.104 | 174.624 | 2907.8798 | 4365.6011 | 7448.1049 | 1 | 51.9328 | 100% | 0% | 0% | 100% | 7448.1049 | 0 | 0 | 7448.1049 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 2482.7016 | 2482.7016 | 2482.7016 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation Module #7 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-022 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 022 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #7 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-022 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #8 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-023 | 51.9328 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.104 | 174.624 | 2907.8798 | 4365.6011 | 7448.1049 | 1 | 51.9328 | 100% | 0% | 0% | 100% | 7448.1049 | 0 | 0 | 7448.1049 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 2482.7016 | 2482.7016 | 2482.7016 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation Module #8 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-023 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 023 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #8 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-023 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #9 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-026 | 51.9328 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.104 | 174.624 | 2907.8798 | 4365.6011 | 7448.1049 | 1 | 51.9328 | 100% | 0% | 0% | 100% | 7448.1049 | 0 | 0 | 7448.1049 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 2482.7016 | 2482.7016 | 2482.7016 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation Module #9 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-026 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 026 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #9 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-026 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation Module #10 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-027 | 51.9328 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 29.104 | 174.624 | 2907.8798 | 4365.6011 | 7448.1049 | 1 | 51.9328 | 100% | 0% | 0% | 100% | 7448.1049 | 0 | 0 | 7448.1049 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 2482.7016 | 2482.7016 | 2482.7016 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation Module #10 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-027 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 027 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Module #10 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-027 | 51.9328 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-029 | 75.2515 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 42.1722 | 253.0331 | 4213.5646 | 6325.8263 | 10792.424 | 1 | 75.2515 | 100% | 0% | 0% | 100% | 10792.424 | 0 | 0 | 10792.424 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3597.4747 | 3597.4747 | 3597.4747 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-029 | 75.2515 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 029 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-029 | 75.2515 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FS-c | Buildings (Contaminated) | Prefabricated Special Modular |  | Power Generation E-House #4 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-030 | 75.2515 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 42.1722 | 253.0331 | 4213.5646 | 6325.8263 | 10792.424 | 1 | 75.2515 | 100% | 0% | 0% | 100% | 10792.424 | 0 | 0 | 10792.424 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3597.4747 | 3597.4747 | 3597.4747 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation E-House #4 - Demolish and foundations - Gravel Base - Skidded Building | 4530-BLD-030 | 75.2515 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 030 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation E-House #4 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-030 | 75.2515 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | FF1-c | Modular Building Contaminated (480 ft2) | FC-c | Buildings (Contaminated) | ISO Shipping Containers |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 29.729 | m2 | 0.56042 | 3.3625 | 55.9931 | 84.0625 | 143.4181 | 16.6606 | 99.9637 | 1664.6181 | 2499.0919 | 4263.6737 | 1 | 29.729 | 100% | 0% | 0% | 100% | 4263.6737 | 0 | 0 | 4263.6737 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1421.2246 | 1421.2246 | 1421.2246 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Power Generation Stores #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4530-BLD-031 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4530 | Power Generation | 4530 | Power Generation | 031 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Power Generation Stores #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4530-BLD-031 | 29.729 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Accommodation Area E-House #3 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-008 | 37.1612 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 8.3303 | 124.9546 | 832.3091 | 1249.5459 | 2206.8096 | 1 | 37.1612 | 100% | 0% | 0% | 100% | 2206.8096 | 0 | 0 | 2206.8096 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 735.6032 | 735.6032 | 735.6032 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Accommodation Area E-House #3 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-008 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 008 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Accommodation Area E-House #3 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-008 | 37.1612 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #1 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-010 | 59.4579 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.3285 | 199.9273 | 1331.6945 | 1999.2735 | 3530.8953 | 1 | 59.4579 | 100% | 0% | 0% | 100% | 3530.8953 | 0 | 0 | 3530.8953 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1176.9651 | 1176.9651 | 1176.9651 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Crushing and Screening E-House #1 - Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 010 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #1 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-010 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FS | Buildings (Not Contaminated) | Prefabricated Special Modular |  | Crushing and Screening E-House #2 - Demolish and Decontaminate Building - Special Modular / Prefabricated | 4750-BLD-011 | 59.4579 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 13.3285 | 199.9273 | 1331.6945 | 1999.2735 | 3530.8953 | 1 | 59.4579 | 100% | 0% | 0% | 100% | 3530.8953 | 0 | 0 | 3530.8953 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1176.9651 | 1176.9651 | 1176.9651 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Crushing and Screening E-House #2- Demolish and foundations - Gravel Base - Skidded Building | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4750 | Power Distribution System | 4750 | Power Distribution System | 011 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Crushing and Screening E-House #2 - Demolish floor finish - Raised Steel or Wooden Floor | 4750-BLD-011 | 59.4579 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FFL | Buildings (Not Contaminated) | Fold Away Building |  | Site Services Unheated Warehouse - Demolish and Decontaminate Building - Fold-away Building (Steel) | 7235-BLD-004 | 371.6122 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 83.3031 | 1249.5459 | 8323.0906 | 12495.4594 | 22068.0959 | 1 | 371.6122 | 100% | 0% | 0% | 100% | 22068.0959 | 0 | 0 | 22068.0959 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 7356.032 | 7356.032 | 7356.032 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | CP | Precast Concrete Foundations - (480 ft2) | CP | Flooring / Foundations | Precast Foundations |  | Site Services Unheated Warehouse - Demolish and foundations - Precast Footing (Perimeter Beam) | 7235-BLD-004 | 371.6122 | m2 | 0.14521 | 2.1781 | 14.5081 | 21.7809 | 38.4671 | 53.9604 | 809.4065 | 5391.3694 | 8094.0652 | 14294.8411 | 0.75 | 278.7091 | 100% | 0% | 0% | 100% | 14294.8411 | 0 | 0 | 14294.8411 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 4764.947 | 4764.947 | 4764.947 | 0 | 0 | 0 | 0 | 0
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7235 | Warehouses | 004 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Total Gravel Base |  | Site Services Unheated Warehouse - Demolish floor finish - Gravel | 7235-BLD-004 | 371.6122 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Mine Site | 4540 | Waste Disposal (Landfarm) | 4540 | Waste Disposal (Landfarm) |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Landfarm |  | 14083 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 626.551 | 2507.4781 | 62655.0993 | 10062.9421 | 75225.5196 | 0 | 0 | 100% | 0% | 0% | 100% | 75225.5196 | 0 | 0 | 75225.5196 | Type A 2AM-MRY1325 | Remove | 2015 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 25075.1732 | 25075.1732 | 25075.1732 | 0 | 0 | 0 | 0 | 0 | Assumed same size as landfarm at Milne
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – West side |  | 9000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 114.2089 | 1316.25 | 11420.8928 | 3568.9081 | 16292.6581 | 0 | 0 | 100% | 0% | 0% | 100% | 16292.6581 | 0 | 0 | 16292.6581 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 5430.886 | 5430.886 | 5430.886 | 0 | 0 | 0 | 0 | 0 | -
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4512 | Accommodation Wings |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Accommodation extension – East Side |  | 2700 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 34.2627 | 394.875 | 3426.2679 | 1070.6724 | 4887.7974 | 0 | 0 | 100% | 0% | 0% | 100% | 4887.7974 | 0 | 0 | 4887.7974 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1629.2658 | 1629.2658 | 1629.2658 | 0 | 0 | 0 | 0 | 0 | -
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (North West) |  | 3500 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 44.4146 | 511.875 | 4441.4583 | 1387.9087 | 6336.0337 | 0 | 0 | 100% | 0% | 0% | 100% | 6336.0337 | 0 | 0 | 6336.0337 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 2112.0112 | 2112.0112 | 2112.0112 | 0 | 0 | 0 | 0 | 0 | -
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Utility pad extension (South West) |  | 1800 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 22.8418 | 263.25 | 2284.1786 | 713.7816 | 3258.5316 | 0 | 0 | 100% | 0% | 0% | 100% | 3258.5316 | 0 | 0 | 3258.5316 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1086.1772 | 1086.1772 | 1086.1772 | 0 | 0 | 0 | 0 | 0 | -
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4614 | Jet-A System | 416 | TK- | MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | MT5-d | Mechanical Equipment | Medium Mobile Diesel Tanks |  | Tank - Jet-A tanks @ aerodrome apron |  | 3 | Ea | 42.725 | 564.75 | 4268.7992 | 5647.5 | 10481.0492 | 128.175 | 1694.25 | 12806.3976 | 16942.5 | 31443.1476 | 30 | 90 | 100% | 0% | 0% | 100% | 31443.1476 | 0 | 0 | 31443.1476 | Type A 2AM-MRY1325 | Hold/ Remove | 2015 | Direct | 50% | 50% | [6 empty] | 15721.5738 | 15721.5738 | 0 | 0 | 0 | 0 | 0 | 0 | Assume 2x50,000 L plus 1x75,000 Jet-A
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems |  | VP- | VP2 | VENDOR PKG - Potable Water | VP2 | Packaged Facilities | Potable Water |  | VENDOR PACKAGE - POTABLE WATER TREATMENT PLANT VENDOR PACKAGE |  | 1 | Ea | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 47 | 480 | 4695.9289 | 4800 | 9975.9289 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 9975.9289 | 0 | 9975.9289 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 3325.3096 | 3325.3096 | 3325.3096 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems |  | VP- | VP3 | VENDOR PKG - Sewage Treatment Plant | VP3 | Packaged Facilities | Sewage Treatment Plant |  | VENDOR PACKAGE - SEWAGE TREATMENT PLANT VENDOR PACKAGE |  | 1 | Ea | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 51 | 540 | 5095.5824 | 5400 | 11035.5824 | 329.2683 | 329.2683 | 100% | 0% | 100% | 0% | 11035.5824 | 0 | 11035.5824 | 0 | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 50% | 50% | [6 empty] | 5517.7912 | 5517.7912 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Milne Port | 2340 | Stockpile | 2340 | Stockpile |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional sealift laydown area |  | 72000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 913.6714 | 10530 | 91367.1427 | 28551.2649 | 130341.2649 | 0 | 0 | 100% | 0% | 0% | 100% | 130341.2649 | 0 | 0 | 130341.2649 | Type B Construction 2BC-MRY1416 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 43447.0883 | 43447.0883 | 43447.0883 | 0 | 0 | 0 | 0 | 0 | -
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7210 | Exploration Camp & Facilities | 7212 | Hardwall Camp |  | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR2 | Buildings (Not Contaminated) | Double Trailer (2 or more) |  | Existing Trailer Camp (Shanco) |  | 928.45 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 208.1275 | 3121.9131 | 20794.7264 | 31219.1312 | 55135.7707 | 1 | 928.45 | 100% | 0% | 0% | 100% | 55135.7707 | 0 | 0 | 55135.7707 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 18378.5902 | 18378.5902 | 18378.5902 | 0 | 0 | 0 | 0 | 0 | - |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Bladder Farm Decommissioning |  | 18482.01 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 822.2624 | 3290.7219 | 82226.2424 | 13206.2342 | 98723.1985 | 0 | 0 | 100% | 0% | 0% | 100% | 98723.1985 | 0 | 0 | 98723.1985 | Type B Construction 2BC-MRY1416 | Remove | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 32907.7328 | 32907.7328 | 32907.7328 | 0 | 0 | 0 | 0 | 0 | - |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) |  |  | A3 | Grade & Re-Contour | A2 | Site Works | Grade and Re-Contour | Grade and Contour | Additional Laydown Areas |  | 20000 | m2 | 0.01269 | 0.14625 | 1.269 | 0.39655 | 1.8103 | 253.7976 | 2925 | 25379.7619 | 7930.9069 | 36235.6688 | 0 | 0 | 100% | 0% | 0% | 100% | 36235.6688 | 0 | 0 | 36235.6688 | Type A 2AM-MRY1325 | Remove | 2015 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 12078.5563 | 12078.5563 | 12078.5563 | 0 | 0 | 0 | 0 | 0 | Inclusive of Crusher Stockpile Pad (600 m2) @ Mine Site
2000 | Project Wide | 2500 | General (Project Controls Use) | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Hazardous Waste Berm at Milne Inlet - New waste management building |  | 160 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 0% | 0% | 100% | #REF! | #REF! | #REF! | #REF! | Type B Construction 2BC-MRY1416 | Remove | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Future Hazardous Waste Berm |  | 1784.35 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 0% | 0% | 100% | #REF! | #REF! | #REF! | #REF! | Type B Construction 2BC-MRY1416 | Remove | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | - |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
2000 | Milne Port | 2500 | Non Process Facilities | 2550 | Waste Disposal | 2550 | Waste Disposal |  |  | A5 | Liner Removal | A5 | Site Works | Liner Removal | Liner Removal | Hazardous Waste Berm |  | 972 | m2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 0% | 0% | 100% | #REF! | #REF! | #REF! | #REF! | Type A 2AM-MRY1325 | Remove | 2015 A | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | -
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Existing Hazardous Waste Berm |  | 979.44 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 43.5752 | 174.3893 | 4357.5169 | 699.8543 | 5231.7605 | 0 | 0 | 100% | 0% | 0% | 100% | 5231.7605 | 0 | 0 | 5231.7605 | Type B Construction 2BC-MRY1416 | Remove | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 1743.9202 | 1743.9202 | 1743.9202 | 0 | 0 | 0 | 0 | 0 | - |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7270 | Camp & Site Services | 7273 | Site Operations |  |  |  | #N/A |  |  |  |  | Old STP (RBC) |  | 0 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Accounted for in mechanical equipment |  | Assumption
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 1451.9 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 64.5949 | 258.5108 | 6459.4858 | 1037.4484 | 7755.445 | 0 | 0 | 100% | 0% | 0% | 100% | 7755.445 | 0 | 0 | 7755.445 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 100% | [6 empty] | 0 | 7755.445 | 0 | 0 | 0 | 0 | 0 | 0 | Ore stockpile pad constructed over top |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7270 | Camp & Site Services | 7273 | Site Operations |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Exploration Phase PWSP |  | 1451.9 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 64.5949 | 258.5108 | 6459.4858 | 1037.4484 | 7755.445 | 0 | 0 | 100% | 0% | 0% | 100% | 7755.445 | 0 | 0 | 7755.445 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 100% | [6 empty] | 0 | 7755.445 | 0 | 0 | 0 | 0 | 0 | 0 | Duplicate? |  | Milne Port Footprint Reclamation Drawing H349000-2000-00-015-0020
4000 | Mine Site | 4200 | Mine Site | 4250 | Open Pit Development | 4250 | Open Pit Development |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | 2008 bulk sample PWSP |  | 361 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 16.0608 | 64.276 | 1606.0847 | 257.9509 | 1928.3116 | 0 | 0 | 100% | 0% | 0% | 100% | 1928.3116 | 0 | 0 | 1928.3116 | Type B Construction 2BC-MRY1416 | Removed | 2015 R | Direct |  |  | 100% | [6 empty] | 0 | 0 | 1928.3116 | 0 | 0 | 0 | 0 | 0 | 0 | Ore stockpile pad constructed over top
2000 | Milne Port | 2700 | Milne Port | 2730 | Sewage System | 2735 | Off Spec Effluent Pond |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond #3 |  | 4260.3 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 189.5402 | 758.5464 | 18954.024 | 3044.1775 | 22756.7479 | 0 | 0 | 100% | 0% | 0% | 100% | 22756.7479 | 0 | 0 | 22756.7479 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 7585.5826 | 7585.5826 | 7585.5826 | 0 | 0 | 0 | 0 | 0 | To be constructed in 2014
7000 | Construction Facilities & Services | 7400 | Construction Facilities & Services | 7470 | Camp & Site Services | 7470 | Camp & Site Services |  |  | A3l | Grade & Re-Contour with Liner | A3l | Site Works | Grade and Re-Contour With Liner |  | Polishing Waste Stabilization Pond (Existing) |  | 7969.14 | m2 | 0.04449 | 0.17805 | 4.449 | 0.71455 | 5.3083 | 354.5461 | 1418.9054 | 35454.609 | 5694.3119 | 42567.8263 | 0 | 0 | 100% | 0% | 0% | 100% | 42567.8263 | 0 | 0 | 42567.8263 | Type A 2AM-MRY1325 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 14189.2754 | 14189.2754 | 14189.2754 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 5 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 48.3333 | 537.5 | 4829.1467 | 5375 | 10741.6467 | 1 | 5 | 100% | 0% | 0% | 100% | 10741.6467 | 0 | 0 | 10741.6467 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  | 50% | 50% | [6 empty] | 0 | 5370.8234 | 5370.8234 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2710 | Additional Tanks | 2710 | Additional Tanks |  | TK- | MT2 | Medium Tanks | MT2 | Mechanical Equipment | Medium Tanks |  | Additional Medium Size tanks |  | 3 | Ea | 31 | 390 | 3097.3148 | 3900 | 7387.3148 | 93 | 1170 | 9291.9444 | 11700 | 22161.9444 | 2 | 6 | 100% | 0% | 0% | 100% | 22161.9444 | 0 | 0 | 22161.9444 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  | 50% | 50% | [6 empty] | 0 | 11080.9722 | 11080.9722 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - RAW WATER TANK (25 m3) |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER TANK - SIMER JET PUMPS 2205C L: 1803, W: 1245, H: 1346 |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 716.1098 | 716.1098 | 716.1098 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | TANK - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR SEWAGE COLLECTION TANK |  | 1 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 1 | 1 | 100% | 0% | 0% | 100% | 2148.3293 | 0 | 0 | 2148.3293 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct |  | 50% | 50% | [6 empty] | 0 | 1074.1647 | 1074.1647 | 0 | 0 | 0 | 0 | 0 | 0
4000 | Mine Site | 4700 | Site Utilities | 4740 | Additional Tanks | 4740 | Additional Tanks |  | TK- | MT1 | Light Tanks | MT1 | Mechanical Equipment | Light Tanks |  | Additional Light Size tanks |  | 5 | Ea | 9.6667 | 107.5 | 965.8293 | 1075 | 2148.3293 | 48.3333 | 537.5 | 4829.1467 | 5375 | 10741.6467 | 1 | 5 | 100% | 0% | 0% | 100% | 10741.6467 | 0 | 0 | 10741.6467 | Type B Construction 2BC-MRY1416 | Removed | 2015 A | Direct |  | 50% | 50% | [6 empty] | 0 | 5370.8234 | 5370.8234 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | VP6 | VENDOR PKG - Ship Loader | VP6 | Packaged Facilities | Ship Loader |  | Shiploader Package | 2351-SL-001 | 1 | Lot | 14448 | 216720 | 1443548.528 | 2167200 | 3827468.528 | 14448 | 216720 | 1443548.528 | 2167200 | 3827468.528 | 30295 | 30295 | 0% | 100% | 0% | 100% | 0 | 3827468.528 | 0 | 3827468.528 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 1275822.8427 | 1275822.8427 | 1275822.8427 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 159 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DRIVE | 2351-MT-007A | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 160 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR BRAKE | 2351-MT-007B | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 161 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DIVIDER CHUTE MOVING SADDLE | 2351-MT-007C | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 162 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM FAN | 2351-MT-007D | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 163 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR DEDUSTING SYSTEM COMPRESSOR | 2351-MT-007E | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 164 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007F | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 165 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LINK CONVEYOR MAINTENANCE WINCH | 2351-MT-007G | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 167 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-001A | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 170 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-001B | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 171 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-001C | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 172 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001D | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 173 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-001E | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 174 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001F | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 175 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-001G | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 176 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-001H | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 177 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-001J | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 178 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-001K | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 179 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE FAN | 2351-MT-001L | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 180 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-001M | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 181 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-001N | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 182 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001P | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 183 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001Q | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 184 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-001R | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 185 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-001S | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 186 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001T | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 187 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-001U | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 194 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR DRIVE | 2351-MT-002A | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 197 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER BOOM CONVEYOR BRAKE | 2351-MT-002B | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 198 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER HOISTING WINCH DRIVE TELESCOPIC CHUTE | 2351-MT-002C | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 199 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002D | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 200 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE | 2351-MT-002E | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 201 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002F | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 202 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE BRAKE | 2351-MT-002G | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 203 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SLEWING DRIVE TRIMMING SPOON | 2351-MT-002H | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 204 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER LUFFING DRIVE TRIMMING SPOON | 2351-MT-002J | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 205 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE DISCHARGE CONVEYOR | 2351-MT-002K | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 206 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER SHUTTLE DRIVE BRAKE | 2351-MT-002L | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 207 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER CENTRAL LUBE SYSTEM | 2351-MT-002M | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 208 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER PINION LUBE SYSTEM | 2351-MT-002N | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 209 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002P | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 210 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002Q | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 211 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM FAN | 2351-MT-002R | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 212 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER DEDUSTING SYSTEM COMPRESSOR | 2351-MT-002S | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 213 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002T | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 214 | MT- |  | Ship Loader | Ship Loader |  | Ship Loader |  | SHIPLOADER MAINTENANCE WINCH | 2351-MT-002U | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 099 | BLD | FF1 | Modular Building Not Contaminated (480 ft2) | FTR1 | Buildings (Not Contaminated) | Single Trailers (modular) |  | Dock Office - Demolish and Decontaminate Building - Trailer - Single | 2223-BLD-001 | 44.6097 | m2 | 0.22417 | 3.3625 | 22.3972 | 33.625 | 59.3847 | 10 | 150 | 999.1338 | 1500 | 2649.1338 | 1 | 44.6097 | 0% | 100% | 0% | 100% | 0 | 2649.1338 | 0 | 2649.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 883.0446 | 883.0446 | 883.0446 | 0 | 0 | 0 | 0 | 0 | Not Contaminated | FF1
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 100 | BLD | EG | Gravel Base Removal | EG | Flooring / Foundations | Gravel Base |  | Dock Office - Demolish and foundations - Gravel Base - Skidded Building | 2223-BLD-001 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | EG
2000 | Milne Port | 2200 | Marine | 2220 | Ore Dock | 2223 | Dock Office | 101 | BLD |  | #N/A | FW | Flooring / Foundations | Wood Floor |  | Dock Office - Demolish floor finish - Raised Steel or Wooden Floor | 2223-BLD-001 | 44.6097 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[31 empty] | vol |  | area
[29 empty] | #REF! |  | #REF! |  | #REF!
[31 empty] | #REF! |  | #REF!
#REF!

## Removed Mob. Equip. 2015 R (hidden)
Mobile Equipment Removed from EBS
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Notes | Uncertainty | Required Reclamation Activities
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 013 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274 W: 2665, H: 2032, 6350 kg | 2140-MO-001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 014 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 015 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment | 016 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 2140-MO-004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 018 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 019 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 020 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 021 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 022 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 023 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 2142-MO-006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 024 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 025 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 026 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 027 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 028 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 029 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 030 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-015 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 031 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 032 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 033 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 2142-MO-018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 034 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment | 035 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CONVEYOR CLEANUP/SNOW REMOVAL ALL TERRAIN LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 2142-MO-020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 037 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - SITE MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 038 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - SITE MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 2143-MO-003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 039 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 040 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - PLANT AND MOBILE EQUIPMENT MAINTENANCE SERVICE TRUCK - PETERBILT 348 L: 7264, W: 2418, H: 2022, 7300 kg | 2143-MO-005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 041 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - SITE MAINTENANCE SMALL LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 2143-MO-006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 042 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 043 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 2143-MO-008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 044 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MINE/TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-009 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 045 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 046 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - SITE DEWATERING PUMP - GORMAN-RUPP 14C2-F3L L: 2057, W: 979, H: 1510, 834 kg | 2143-MO-012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 047 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 048 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 2143-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 049 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 2143-MO-015 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 050 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 2143-MO-016 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 051 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 052 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 053 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 14M | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE GRADER - CAT 14M L: 9412, W: 2791, H: 3535, 24400 kg | 2143-MO-019 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 054 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Compactor | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE COMPACTOR - CAT CS56 L: 5860, W: 2300, H: 3070, 12250 kg | 2143-MO-020 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 055 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE PLOW/SAND TRUCK - WESTERN STAR 4700 SF | 2143-MO-021 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 056 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - TOTE ROAD MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 2143-MO-022 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 057 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170, W: 2410, H: 3320, 18338 kg | 2143-MO-023 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 058 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW295 | 2143-MO-024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 059 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FD35N L: 2540, W: 1300, H: 2540, 4800 kg | 2143-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 060 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 2143-MO-026 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 061 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT DP50K L: 3305, W: 1460, H: 2400, 7160 kg | 2143-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment | 062 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - CAT 2ET4000 L: 2000, W: 1100, H: 2040, 3330 kg | 2143-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 064 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 2144-MO-001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 065 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 2144-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 066 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 2144-MO-003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 067 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 2144-MO-004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 068 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER DELIVERY TRUCK - PETERBILT 367 TRI-DRIVE | 2144-MO-005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 069 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-006 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 070 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 071 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL TRACTOR - PETERBILT 367 | 2144-MO-008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 072 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 073 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 074 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - MILNE/MR FREIGHT HAUL HIBOY TRAILER L: 12192, W: 2438 | 2144-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 075 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 2144-MO-012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 470.5446 | 470.5446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 076 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 2144-MO-013 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 077 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-014 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 078 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 079 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-016 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 080 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 2144-MO-017 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 081 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 082 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 2144-MO-019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 083 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 084 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 085 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 2144-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 086 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 087 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 088 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 089 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 090 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 091 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 092 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 093 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment | 094 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 2144-MO-038 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 131 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-023 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 132 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 133 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-025 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 134 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-030 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 135 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-031 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 136 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT | 2342-CV-032 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 256 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg | 2513-MO-001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 257 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Fire Truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH T1500 L: 10540, W: 3100, H: 3810, 16500 kg | 2513-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 599 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 600 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHER FRONT-END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 4141-MO-006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 601 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 602 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 603 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 604 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg | 4141-MO-010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 605 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - MINE SITE LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4141-MO-024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 606 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 607 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 608 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 609 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 610 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4141-MO-029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 611 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 56800 kg | 4141-MO-030 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 612 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg | 4141-MO-031 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 613 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL size | MOBILE EQUIPMENT - SECONDARY DRILL - TAMROCK 800 | 4141-MO-033 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment | 614 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - DRILL DUST SUPPRESSION WATER/METHANOL TRUCK - KENWORTH T800H | 4141-MO-035 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 616 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-001A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 617 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 618 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-001C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 619 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-002A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 620 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 621 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-002C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 622 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-003A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 623 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 624 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-003C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 625 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-004A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 626 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 627 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-004C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 628 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-005A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 629 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 630 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-005C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 631 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-006A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 632 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 633 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-006C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 634 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-007A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 635 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 636 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-007C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 637 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-008A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 638 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 639 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-008C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 640 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-009A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 641 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 642 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-009C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 643 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-010A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 644 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 645 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-010C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 646 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-011A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 647 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 648 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-011C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 649 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-012A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 650 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 651 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-012C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 652 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-013A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 653 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 654 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-013C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 655 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-014A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 656 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 657 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-014C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 658 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-015A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 659 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 660 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-015C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 661 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-016A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 662 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 663 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-016C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 664 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-017A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 665 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 666 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-017C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 667 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-018A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 668 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 669 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-018C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 670 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-019A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 671 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 672 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-019C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 673 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD L: 10080, W: 3060, H: 3900, 11400 kg | 4142-MO-020A | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 674 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020B | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 675 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210, 34500 kg | 4142-MO-020C | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 676 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 42700 kg | 4142-MO-021 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 677 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg | 4142-MO-022 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 678 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE WHEEL DOZER - CAT 824H L: 8716, W: 3556, H: 4102, 46300 kg | 4142-MO-023 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 679 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16H L: 9963, W: 3096, H: 3718, 30400 kg | 4142-MO-024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 680 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg | 4142-MO-026 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 681 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION LARGE EXCAVATOR - CAT 390DL L: 13470, W: 3500, H: 4782, 85000 kg | 4142-MO-027 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 682 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 683 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 684 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 685 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 686 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 687 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 688 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 689 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 690 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment | 691 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - NIGHT WORK AREA LIGHT PLANTS - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 4142-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 693 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - FORD F550 | 4143-MO-001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 694 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - MAINTENANCE SERVICE TRUCK - PETERBILT 348 | 4143-MO-002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 695 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - KENWORTH T800 | 4143-MO-003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 696 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 697 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - LOWBED TRACTOR - PETERBILT 367 | 4143-MO-005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 698 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Tire Handler | MOBILE EQUIPMENT - TIRE HANDLER - WBM T20P-S 5900 kg | 4143-MO-006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 699 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FREIGHT HANDLING FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 4143-MO-008 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 700 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - YARD WORK EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg | 4143-MO-009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 701 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 702 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | bobcat size | MOBILE EQUIPMENT - CLEANUP/SNOW REMOVAL ALL TERRAIN FRONT END LOADER - CAT 247B L: 3277, W: 1676, H: 3810, 3175 kg | 4143-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 703 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - CRUSHER MAINTENANCE KNUCKLE CRANE - KENWORTH T800 | 4143-MO-013 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 704 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT780 L: 14630, W: 7920, H: 3990, 42000 kg | 4143-MO-014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 705 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - TEREX RT130 L: 15240, W: 7920, H: 3970, 60500 kg | 4143-MO-015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 706 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - WAREHOUSE FORK LIFT - CAT P7000-D L: 2790, W: 1290, H: 2500, 4763 kg | 4143-MO-016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 707 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - MAINTENANCE FORK LIFT - CAT P20000 L: 4240, W: 2390, H: 2845, 14320 kg | 4143-MO-017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 708 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - FREIGHT TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 4143-MO-018 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 709 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 710 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - RUN-OFF CONTROL DEWATERING PUMP - GORMAN RUPP T6A60S-C4.4T | 4143-MO-020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 711 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-021 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 712 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-022 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 713 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Light sized | MOBILE EQUIPMENT - MAINTENANCE HOT BOX - ECOBLAZE CUBE 1100 L: 4877, W: 2235, H: 1829, 1850 kg | 4143-MO-023 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 714 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - YARD MAINTENANCE PLOW/SAND TRUCK - INTERNATIONAL 7600 | 4143-MO-024 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 715 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg | 4143-MO-025 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 716 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - YARD/TOTE ROAD MAINTENANCE TRACK DOZER - CAT D6T XW L: 4064, W: 2464, H: 2439, 21600 kg | 4143-MO-026 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 717 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | welder | MOBILE EQUIPMENT - MAINTENANCE TRAILER WELDER | 4143-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 718 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG450AJ L: 2500, W: 1170, H: 1970, 6010 kg | 4143-MO-029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 719 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 4143-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 720 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Kenworth Truck | MOBILE EQUIPMENT - ORE HAUL TRUCK RECOVERY TOW TRUCK - KENWORTH T800 | 4143-MO-031 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 721 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD CULVERT MAINTENANCE STEAM TRUCK - PETERBILT T/A STEAM TRUCK | 4143-MO-032 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 722 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 723 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 724 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 725 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 726 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 4143-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 727 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Forklift | MOBILE EQUIPMENT - FORKLIFT - MITSUBISHI FB20PNT L: 3050, W: 1090, H: 2050, 3500 kg | 4143-MO-038 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 728 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MINI CRAWLER CRANE - SPYDER CRANE URW706 | 4143-MO-039 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment | 729 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sterling Trucks | MOBILE EQUIPMENT - SPILL RESPONSE TRUCK - STERLING M8500 | 4143-MO-040 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 731 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT 348 AUTO S/S 100 BBL | 4144-MO-001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 732 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg | 4144-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 733 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 734 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - PASSENGER TRANSFER BUS - BLUE BIRD BBCV DIESEL 3507A L: 12192, W: 2440, H: 2900, 14000 kg | 4144-MO-004 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 735 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - WORKER TRANSFER MINI BUS - BLUE BIRD BBCV DIESEL 1910 A L: 7470, W: 2440, H: 1930, 7080 kg | 4144-MO-005 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 736 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 470.5446 | 470.5446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 737 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - FREIGHT DELIVERY HIBOY TRAILER L: 14630 W: 2438 | 4144-MO-007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 738 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - DIESEL FUEL TRAILER TRACTOR - WESTERN STAR 4900FA | 4144-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 739 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - JET-A1 FUEL DELIVERY TRUCK - MACK/INNOCAR GU813 L: 8052, W: 2960, H: 3589 | 4144-MO-009 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 740 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - TREMCAR TC406 SUPER B-TRAIN L: 24384, W: 2590, H: 4013, 33500 kg | 4144-MO-010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 741 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - MOBILE EQUIPMENT LOWBOY TRAILER - SHELTEMA L: 7620, W: 4572 | 4144-MO-011 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 742 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - GARBAGE TRUCK - PETERBILT 365 | 4144-MO-012 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 743 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-013 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 744 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-014 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 745 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 746 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Garbage Bin (Large) | MOBILE EQUIPMENT - GARBAGE BIN - LARGE | 4144-MO-016 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 747 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 748 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - GARBAGE BIN - SMALL | 4144-MO-018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 749 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Cat 740 | MOBILE EQUIPMENT - ARTICULATED WATER/SAND TRUCK - CAT 740 | 4144-MO-024 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 750 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | trailer (Fuel) | MOBILE EQUIPMENT - DIESEL FUEL DELIVERY TRAILER - ADVANCE | 4144-MO-025 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 751 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage tank and vacuum | MOBILE EQUIPMENT - SEWAGE HOLDING TANK SKID MOUNTED VACUUM UNIT - TEXLA | 4144-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 470.5446 | 470.5446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 752 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 753 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - HEATED/REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 754 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 755 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 756 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 757 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 758 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 759 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Sea Container | MOBILE EQUIPMENT - REFRIGERATED SEA CONTAINER L: 6096, W: 2440, H: 2440 | 4144-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 760 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-040 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 761 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-041 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 762 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-042 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 763 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-043 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 764 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-044 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment | 765 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Small Garbage bin | MOBILE EQUIPMENT - WILDLIFE DETERGENT GARBAGE BIN | 4144-MO-045 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 807 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 808 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 809 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-013 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 810 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-014 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 811 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-015 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 812 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 813 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 814 | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - LINK CONVEYOR - MASABA MINING EQUIPMENT | 4381-CV-018 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4434 | Plant & Equipment | 848 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Bus sized | MOBILE EQUIPMENT - AIRPORT MAINTENANCE DE-ICING TRUCK - FORD SUPERIOR | 4434-MO-002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 927 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F450 L: 6680, W: 2438, H: 2024, 6350 kg | 4513-MO-001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 928 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | large fire truck | MOBILE EQUIPMENT - FIRE TRUCK - OSHKOSH TI3000 L: 10922 W: 2921, H: 3607, 39000 kg | 4513-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 929 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | small tank | MOBILE EQUIPMENT - SNOW RESCUE VEHICLE - HAGGLUND BV206 L: 6900, W: 1870, H: 2400, 6580 kg | 4513-MO-003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1295 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-001 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1296 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1297 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1298 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1299 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1300 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1301 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1302 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1303 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-009 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1304 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1305 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1306 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1307 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1308 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1309 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7241-MO-024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7241 | Company Vehicles | 1310 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg | 7241-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1313 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1314 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1315 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1316 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1317 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1318 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1319 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1320 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1321 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1322 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7243-MO-010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1323 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1324 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7243-MO-012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1325 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7243-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1326 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7243-MO-015 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1327 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1328 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1329 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1330 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1331 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7243-MO-020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1332 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7243-MO-021 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1333 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7243-MO-022 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1334 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-023 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1335 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1336 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1337 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1338 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1339 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1340 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1341 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1342 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1343 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1344 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1345 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1346 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1347 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1348 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7243-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7243 | Site Operations Mobile Equipment | 1349 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7243-MO-046 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1360 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1361 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - JLG 450AJ | 7245-MO-003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1362 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7245-MO-004 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1363 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-005 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1364 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7245-MO-006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1365 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MAMTEX 26101C | 7245-MO-007 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1366 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - GROVE RT890E 41400 kg | 7245-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1367 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-010 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1368 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-011 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7245 | Cranes and Lifting Equipment | 1369 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7245-MO-012 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1386 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-001 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1387 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-002 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1388 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - TRACK DOZER - CAT D6T XW L: 4674, W: 2000, H: 2900, 9250 kg | 7340-MO-003 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1389 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - MID SIZE EXCAVATOR - CAT 345DL HEX L: 11910, W: 3490, H: 3770, 45000 kg | 7340-MO-004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1390 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CS74 L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-014 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1391 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E L: 5970, W: 2300, H: 3070, 15650 kg | 7340-MO-015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1392 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-016 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7300 | Tote Road | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment | 1393 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - ROAD SNOW BLOWER - CAT 950H L: 6170 W: 2410, H: 3320, 18338 kg | 7340-MO-017 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1446 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader size | MOBILE EQUIPMENT - FUEL/LUBE TRUCK - ARTICULATED - CAT 740 EFLT | 7441-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7441 | Company Vehicles | 1447 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Cube Van | MOBILE EQUIPMENT - CUBE VAN - FORD F550 | 7441-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1448 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-001 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1449 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-002 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1450 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-003 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1451 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-004 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1452 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-005 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1453 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-006 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1454 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-007 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1455 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-008 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1456 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1457 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - ARTICULATED HAUL TRUCK - CAT 740B L: 10889, W: 3430, H: 3745, 34000 kg | 7443-MO-010 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1458 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-011 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1459 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg | 7443-MO-012 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1460 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Compressor | MOBILE EQUIPMENT - MID SIZE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1461 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Compressor | MOBILE EQUIPMENT - LARGE AIR COMPRESSOR - ATLAS COPCO | 7443-MO-015 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1462 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pump | MOBILE EQUIPMENT - TRASH PUMP - GORMAN-RUPP 13D-L700EE S/G L: 711.2, W: 533.4, H: 621.7, 54 kg | 7443-MO-016 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1463 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-017 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1464 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-018 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1465 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-019 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1466 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-020 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1467 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg | 7443-MO-021 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1468 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | FEL | MOBILE EQUIPMENT - FRONT END LOADER - CAT 930K L: 6050, W: 2390, H: 3150, 9600 kg | 7443-MO-022 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1469 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Telehandler | MOBILE EQUIPMENT - TELEHANDLER - CAT TH514 L: 6100, W: 2570, H: 2570, 15800 kg | 7443-MO-023 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1470 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-024 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1471 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-025 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1472 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-026 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1473 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-027 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1474 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-028 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1475 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-029 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1476 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-030 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1477 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-031 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1478 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-032 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1479 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-033 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1480 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-034 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1481 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-035 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1482 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-036 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1483 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-037 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1484 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Frost Fighter | MOBILE EQUIPMENT - FROST FIGHTER - FROSTFIGHTER IDF350-11 | 7443-MO-038 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1485 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER L: 16050, W: 2438 | 7443-MO-051 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1486 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER L: 14630, W: 2438 | 7443-MO-052 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1487 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-053 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7443 | Site Operations Mobile Equipment | 1488 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - SECONDARY DRILL - SANDVIK 800 | 7443-MO-054 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1502 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-002 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1503 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - MAN LIFT - GENIE Z45/25 | 7445-MO-003 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1504 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-006 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1505 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-007 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1506 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Man Lift | MOBILE EQUIPMENT - SCISSOR LIFT - SKYJACK 8841 L: 3500, W: 2200, H: 2900 4917 kg | 7445-MO-008 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1507 | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Large Crane | MOBILE EQUIPMENT - MAINTENANCE CRANE - MANITOWOC 2250 L: 12900, W: 7910, H: 3640, 113000 kg | 7445-MO-009 | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1508 | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Boom truck | MOBILE EQUIPMENT - BOOM TRUCK - MANITEX 26101C | 7445-MO-012 | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1509 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-013 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7445 | Cranes and Lifting Equipment | 1510 | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - WAREHOUSE FREIGHT DELIVERY FLAT DECK TRUCKS - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg | 7445-MO-014 | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2140 | Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  | 10 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 66.6667 | 250 | 6660.8921 | 2500 | 9410.8921 | 4 | 40 | 100% | 0% | 0% | 100% | 9410.8921 | 0 | 0 | 9410.8921 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 3136.964 | 0 | 3136.964 | 0 | 0 | 0 | 0 | 3136.964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - STOCKPILE RECLAIM FRONT END LOADER - CAT 988H L: 10390, W: 3600, H: 4115, 43400 kg |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - MOBILE LIGHT PLANT - TEREX AL4 L: 4623, W: 2007, H: 9000, 925 kg |  | 5 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 33.3333 | 125 | 3330.446 | 1250 | 4705.446 | 4 | 20 | 100% | 0% | 0% | 100% | 4705.446 | 0 | 0 | 4705.446 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1568.482 | 0 | 1568.482 | 0 | 0 | 0 | 0 | 1568.482 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - FREIGHTLINER |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - AMBULANCE - FORD F350 L: 5715, W: 1752, H: 2032, 6350 kg |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O3
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - FREIGHT HAUL TRACTOR - WeSTERN STAR 4900 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Large Trailer | MOBILE EQUIPMENT - LOWBOY TRAILER |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Trailer | MOBILE EQUIPMENT - HIBOY TRAILER, SEMI DUMP |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 313.6964 | 0 | 313.6964 | 0 | 0 | 0 | 0 | 313.6964 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
2000 | Milne Port | 2100 | General | 2140 | Mobile Equipment | 2144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 740 | MOBILE EQUIPMENT - WATER TRUCK - CAT 740 (8000 GAL) |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - JUMP CONVEYOR - MASABA MINING EQUIPMENT L: 230000, W: 1524 |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | CV- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment |  | CONVEYING - STOCKPILE RECLAIM EXTENSION CONVEYOR |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
3000 | Tote Road | 3100 | General | 3130 | Site Development | 3130 | Site Development |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT -EXCAVATOR - CAT M322D |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - CAT 777 DUMP BOX |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | COMPACTOR | MOBILE EQUIPMENT - COMPACTOR - CAT CP563E |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck | MOBILE EQUIPMENT - MINE HAUL TRUCK - CAT 777G L: 10445, W: 6706, H: 5840, 75200 kg |  | 6 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 78 | 720 | 7793.2437 | 7200 | 15713.2437 | 96 | 576 | 100% | 0% | 0% | 100% | 15713.2437 | 0 | 0 | 15713.2437 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 5237.7479 | 0 | 5237.7479 | 0 | 0 | 0 | 0 | 5237.7479 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - MINE SITE GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - PICKUP TRUCK - FORD F350 L: 6274, W: 2665, H: 2032, 6350 kg |  | 2 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 13.3333 | 50 | 1332.1784 | 500 | 1882.1784 | 4 | 8 | 100% | 0% | 0% | 100% | 1882.1784 | 0 | 0 | 1882.1784 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 627.3928 | 0 | 627.3928 | 0 | 0 | 0 | 0 | 627.3928 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dozer | MOBILE EQUIPMENT - MINE SITE TRACK DOZER - CAT D9T L: 6630, W: 4310, H: 3815, 78000 kg |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK DX780 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Sandvik Drill | MOBILE EQUIPMENT - PIONEER DRILL - SANDVIK SDX800 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | FEL | MOBILE EQUIPMENT - PRODUCTION FRONT END LOADER - CAT 992K L: 16877, W: 6000, H: 7000, 100000 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Drill | MOBILE EQUIPMENT - SINGLE PASS PRODUCTION DRILL - CAT MD6290 L: 14280, W: 4010, H: 4590, 56800 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | 45 MT | MOBILE EQUIPMENT - SITE MAINTENANCE MID SIZE EXCAVATOR - CAT 345DL L: 11910, W: 3490, H: 3770, 45000 kg |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Grader | MOBILE EQUIPMENT - GRADER - CAT 16M L: 9994, W: 3077, H: 3524, 24400 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - MOBILE CRUSHING FRONT END LOADER - CAT 988H, L: 10390, W: 3600, H: 4115, 43400 kg |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | CAT 988H | MOBILE EQUIPMENT - ORE HAUL TRUCK FRONT END LOADER - CAT 988H L: 3277, W: 1676, H: 3810, 3175 kg |  | 2 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 26 | 240 | 2597.7479 | 2400 | 5237.7479 | 96 | 192 | 100% | 0% | 0% | 100% | 5237.7479 | 0 | 0 | 5237.7479 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1745.916 | 0 | 1745.916 | 0 | 0 | 0 | 0 | 1745.916 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT -TOTE ROAD ORE HAUL TRUCK - LEAD TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  | 17 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 221 | 2040 | 22080.8572 | 20400 | 44520.8572 | 96 | 1632 | 100% | 0% | 0% | 100% | 44520.8572 | 0 | 0 | 44520.8572 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 14840.2857 | 0 | 14840.2857 | 0 | 0 | 0 | 0 | 14840.2857 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Materials Handling Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Haul Truck trailer | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - PUP TRAILER - SMITHCO S4 (75T) L: 10240, W: 3060, H: 4210 |  | 19 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 247 | 2280 | 24678.6051 | 22800 | 49758.6051 | 96 | 1824 | 100% | 0% | 0% | 100% | 49758.6051 | 0 | 0 | 49758.6051 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 16586.2017 | 0 | 16586.2017 | 0 | 0 | 0 | 0 | 16586.2017 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4142 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - TOTE ROAD ORE HAUL TRUCK - TRACTOR - WESTERN STAR 6900XD |  | 15 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 195 | 1800 | 19483.1093 | 18000 | 39283.1093 | 96 | 1440 | 100% | 0% | 0% | 100% | 39283.1093 | 0 | 0 | 39283.1093 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13094.3698 | 0 | 13094.3698 | 0 | 0 | 0 | 0 | 13094.3698 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Pick up | MOBILE EQUIPMENT - FLAT DECK TRUCK - FORD F550 L: 7264, W: 2418, H: 2022, 3311 kg |  | 2 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 13.3333 | 50 | 1332.1784 | 500 | 1882.1784 | 4 | 8 | 100% | 0% | 0% | 100% | 1882.1784 | 0 | 0 | 1882.1784 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 627.3928 | 0 | 627.3928 | 0 | 0 | 0 | 0 | 627.3928 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | telehandler | MOBILE EQUIPMENT - INTEGRATED TOOL CARRIER CAT IT38 |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | Lights | MOBILE EQUIPMENT - LARGE MOBILE LIGHT PLANT - TEREX L: 4623, W: 2007, H: 9000, 925 kg |  | 5 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 33.3333 | 125 | 3330.446 | 1250 | 4705.446 | 4 | 20 | 100% | 0% | 0% | 100% | 4705.446 | 0 | 0 | 4705.446 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1568.482 | 0 | 1568.482 | 0 | 0 | 0 | 0 | 1568.482 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4143 | Mobile Maintenance Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Hwy Truck | MOBILE EQUIPMENT - SERVICE TRUCK - PETERBILT |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | school bus | MOBILE EQUIPMENT - COACH PASSENGER TRANSFER BUS |  | 2 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 20 | 90 | 1998.2676 | 900 | 2988.2676 | 24 | 48 | 100% | 0% | 0% | 100% | 2988.2676 | 0 | 0 | 2988.2676 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 996.0892 | 0 | 996.0892 | 0 | 0 | 0 | 0 | 996.0892 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O3 | Heavy Mobile Equipment | O3 | Mobile Equipment | Heavy Mobile Equipment | Container Handler | MOBILE EQUIPMENT - CONTAINER HANDLER - KALMAR DRF 450-6555 L: 11684, W: 3454, H: 2146, 72000 kg |  | 1 | Ea | 13 | 120 | 1298.874 | 1200 | 2618.874 | 13 | 120 | 1298.874 | 1200 | 2618.874 | 96 | 96 | 100% | 0% | 0% | 100% | 2618.874 | 0 | 0 | 2618.874 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 872.958 | 0 | 872.958 | 0 | 0 | 0 | 0 | 872.958 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - FREIGHTLINER |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Dump Truck | MOBILE EQUIPMENT - FUEL DELIVERY TRUCK - INTERNATIONAL |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Trailer | MOBILE EQUIPMENT - Live Bottom Trailer |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Peterbilt Truck | MOBILE EQUIPMENT - MAINTENANCE FUEL/LUBE TRUCK - PETERBILT |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O3
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment | Ford Truck | MOBILE EQUIPMENT - MAINTENANCE LUBE TRUCK - Ford |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O2
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O1 | Light Mobile Equipment | O1 | Mobile Equipment | Light Mobile Equipment | sewage vacuum truck | MOBILE EQUIPMENT - SEWAGE VACUUM TRUCK - FREIGHTLINER |  | 1 | Ea | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 6.6667 | 25 | 666.0892 | 250 | 941.0892 | 4 | 4 | 100% | 0% | 0% | 100% | 941.0892 | 0 | 0 | 941.0892 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 50% | 50% | [6 empty] | 470.5446 | 470.5446 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | O1
4000 | Mine Site | 4100 | General | 4140 | Mobile Equipment | 4144 | Mobile Site Services Equipment |  | MO- | O2 | Medium Mobile Equipment | O2 | Mobile Equipment | Medium Mobile Equipment |  | MOBILE EQUIPMENT - WATER TRUCK - PETERBILT (5400 GAL) |  | 1 | Ea | 10 | 45 | 999.1338 | 450 | 1494.1338 | 10 | 45 | 999.1338 | 450 | 1494.1338 | 24 | 24 | 100% | 0% | 0% | 100% | 1494.1338 | 0 | 0 | 1494.1338 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 498.0446 | 0 | 498.0446 | 0 | 0 | 0 | 0 | 498.0446 |  |  |  | O1
[31 empty] | vol |  | area
[29 empty] | 876036.0017 |  | 22600 |  | 3766.6667
[31 empty] | 167122.2836 |  | 167122.2836
1043158.2854

## Removed Mech. Equip. 2015 R (hidden)
Mechanical Equipment Removed from EBS
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Notes | Uncertainty | Required Reclamation Activities
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 107 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-001 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 108 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-002 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 109 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-003 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 110 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-004 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 111 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-005 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2340 | Stockpile | 112 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Power plant generators | GENERATOR - STOCKPILE GENERATOR - CUMMINS C500DR6G L: 6070, W: 2440, H: 3760, 29440 kg | 2340-GE-006 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 114 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - FINES STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-003 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 115 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-004 | 1 | Ea | 168 | p | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 116 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - LUMPS STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT | 2341-FE-005 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 117 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-006 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 118 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - LUMPS STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-007 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System | 119 | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - FINES STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT | 2341-ST-008 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - STOCKPILE MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2341 | Ore Stacking System |  | ST- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | STACKER / STOCKPILE - STOCKPILE MOBILE STACKER - MASABA MINING EQUIPMENT |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 124 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR DISCHARGE CHUTE - FAM | 2342-CH-015 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 125 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-026 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 126 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-027 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 127 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-028 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 128 | CH- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | CHUTE / DIVERTER - RECLAIM CONVEYOR MOBILE CHUTE - FAM | 2342-CH-029 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 137 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-002 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 138 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-003 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 139 | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - MOBILE FEEDER - MASABA MINING EQUIPMENT | 2342-FE-004 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 140 | HP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | sampler bin | HOPPER - SAMPLER BIN - FAM | 2342-HP-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 141 | SA- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SAMPLER - ORE SAMPLER - FAM L: N/A, W: N/A, H: N/A | 2342-SA-019 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System | 142 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - BELT SCALE - FAM | 2342-SC-018 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2300 | Material Handling | 2340 | Stockpile | 2342 | Ore Reclaim System |  | FE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Mining Equipment | FEEDER - RECLAIM MOBILE FEEDER - MASABA MINING EQUIPMENT |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and Decontaminate Building - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish and foundations - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #1 - Demolish floor finish - Undefined | 2351-SL-001 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and Decontaminate Building - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish and foundations - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System |  | SL- | [6 empty] | Shiploader E-House #2 - Demolish floor finish - Undefined | 2351-SL-002 | 0 | m2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 152 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADER PROPORTIONAL GATE - FAM | 2351-CH-003 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 153 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-004 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 154 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADING PROPORTIONAL DIVERTER DISCHARGE CHUTE - FAM | 2351-CH-005 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 155 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-006 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 156 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADER LINK CONVEYOR DISCHARGE CHUTE - FAM | 2351-CH-008 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 157 | CH- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CHUTE / DIVERTER - SHIPLOADER DISCHARGE CHUTE - FAM | 2351-CH-009 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 158 | CV- |  | Ship Loader | Ship Loader | Mechanical Equipment |  |  | CONVEYING - SHIPLOADER LINK CONVEYOR - FAM 212330 kg | 2351-CV-007 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 166 | SL- |  | Ship Loader | Ship Loader |  |  |  | SHIPLOADER - SHIPLOADER - FAM 1960000 kg | 2351-SL-001 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2300 | Material Handling | 2350 | Ship Loading | 2351 | Ship Loading System | 193 | SL- |  | Ship Loader | Ship Loader |  |  |  | SHIPLOADER - SHIPLOADER - FAM | 2351-SL-002 | 1 | Ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 100% | 0% | 100% | 0 | 0 | 0 | 0 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2510 | Accommodations Area | 225 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 2510-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 258 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2513-PP-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 259 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2513-MT-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 260 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 261 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 262 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2513-PP-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 263 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2513-MT-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2510 | Accommodations Area | 2513 | Emergency Services Building | 264 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 2513-SQ-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 282 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 283 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 284 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 285 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 286 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 287 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 288 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2521-PP-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 289 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2521-MT-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 290 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 2521-PP-051 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2521 | Services Buildings | 291 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 2521-MT-051 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 299 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 300 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 2522-SQ-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 301 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 2522-SQ-004 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 302 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 2522-SQ-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 303 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 2522-SQ-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 304 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-009 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 305 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 306 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 2522-SQ-011 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 307 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 2522-SQ-012 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 308 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 2522-SQ-014 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 309 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 2522-SQ-018 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 310 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 2522-SQ-022 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 311 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 2522-SQ-023 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 312 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 2522-SQ-025 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 313 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-026 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 314 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 2522-SQ-027 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 315 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 2522-SQ-028 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 316 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-029 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 317 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-029 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 318 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610, H: 345 | 2522-SQ-030 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 319 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 2522-MT-030 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 320 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 2522-SQ-033 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 321 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 2522-SQ-034 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 322 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584, W: 864, H: 1120, 110 kg | 2522-SQ-037 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 323 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-038 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 324 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 2522-SQ-039 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2520 | Services Area | 2522 | Services Equipment | 325 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 2522-SQ-040 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 367 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 368 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 369 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2540-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 370 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2540-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 371 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 2540-SQ-002 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 372 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 2540-SQ-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator) | 373 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG - OHAVX32XW10000X | 2540-SQ-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 380 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2610 | Milne Tank Farm | 381 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - OIL WATER SEPARATOR FEED PUMP | 2610-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 390 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - EXISTING DIESEL FUEL DISPENSING MODULE | 2613-FD-013 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 391 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 2613-FD-014 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 392 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.1 | 2613-PP-007 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 393 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.2 | 2613-PP-008 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 394 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.3 | 2613-PP-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 395 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.4 | 2613-PP-010 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 396 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.5 | 2613-PP-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System | 397 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE ARCTIC DIESEL PUMP NO.6 | 2613-PP-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 408 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - JET-A1 FUEL DISPENSING MODULE | 2614-FD-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 409 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 2130.6685 | 2130.6685 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 410 | FS- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Jet Fuel Dispenser | FIRE SERVICES - JET-A1 FUEL DIESPENSING MODULE FUELLING STATION | 2614-FS-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 2130.6685 | 2130.6685 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 411 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2614 | Jet-A System | 412 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JET-A1 FUEL DIESPENSING MODULE DISCHARGE PUMP | 2614-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 422 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 423 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-002 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 424 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 425 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 426 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 427 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2600 | Fuel System | 2610 | Milne Tank Farm | 2619 | Power Generation | 428 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 2619-GE-007 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 434 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 435 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 2720-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 436 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 2720-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 437 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 2720-PP-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 438 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 2720-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 439 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 2720-PP-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 440 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 2720-PP-010 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 441 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 2720-PP-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 442 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 2720-PP-013 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 443 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER UNLOADING PUMP - HAYWARD GORDON S-3 | 2720-PP-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 444 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-031 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 445 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-031 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 446 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2720-PP-032 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2720 | Water Systems | 2720 | Water Systems | 447 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2720-MT-032 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 462 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 2731-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 463 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 2731-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Sewage Treatment Systems | 464 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 2731-SC-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 473 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 474 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 475 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MILNE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 2732-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
2000 | Milne Port | 2700 | Site Utilities | 2730 | Sewage System | 2732 | Sewage Truck Building | 476 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 2732-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 801 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 1 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-001 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 802 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-003 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 803 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 1 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-005 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 804 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 2 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg | 4381-CR-006 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 805 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-008 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 806 | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 2 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg | 4381-CR-010 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 815 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 1 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-002 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 816 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 1 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-004 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 817 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - PRIMARY SCREEN LINE 2 - METSO FS302 L: 2700, W: 6900, 9000 kg | 4381-SC-007 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System | 818 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREEN LINE 2 - METSO FS 353 L: 3000, W: 6900, 14500 kg | 4381-SC-009 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - PRIMARY CRUSHING PLANT LINE 3 - METSO C125 L: 3470, W: 4100, H: 3440, 38000 kg |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | PRIMARY SCREENING PLANT LINE 3 - METSO FS303 |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - SECONDARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600, 23000 kg |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - SECONDARY SCREENING PLANT LINE 3 - METSO FS 353 L: 3000, W: 6900, 14500 kg |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System |  | CR- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Crusher | CRUSHER - TERTIARY CRUSHING PLANT LINE 3 - METSO HP400 L: 2370, W: 2370, H: 1600 |  | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4382 | Truck Weigh Facility | 823 | SC- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Screen | SCREEN - TRUCK WEIGH SCALE - RICE LAKE OTR-XV L: 36600 W: 3960, H: 1030 | 4382-SC-001 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 825 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4300 | Material Handling | 4380 | Crushing and Screening | 4385 | Crushing Stockpile Settling Pond | 826 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CRUSHER STOCKPILE RUNOFF POND DISCHARGE PUMP - LOBE PRO SM68 | 4385-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 836 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 4431-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office | 837 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4431-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 845 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | x-ray | AERODROME EQUIPMENT - SECURITY X-RAY MACHINE L: 2282, W: 1030, H: 1467 | 4433-AE-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 846 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT GROUND POWER UNIT | 4433-AE-015 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4400 | Aerodrome | 4430 | Aerodrome Facilities | 4433 | Plant & Equipment | 847 | AE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Aircraft equip | AERODROME EQUIPMENT - AIRCRAFT PASSENGER STAIRS L: 9906, W: 2565, H: 3048 | 4433-AE-023 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4510 | Accommodations Area | 857 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW SEWAGE LIFT STATION | 4510-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 871 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 872 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR COMPRESSOR | 4511-LE-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 873 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - AIR DRYER | 4511-LE-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 874 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 875 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 876 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - BALANCE SCALE | 4511-LE-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 877 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CARBON/SULFUR ANALYSER | 4511-LE-007 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 878 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CHILLER | 4511-LE-008 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 879 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER | 4511-LE-016 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 880 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - CRUSHER DUST HOOD | 4511-LE-017 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 881 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-018 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 882 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DRYING OVEN | 4511-LE-019 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 883 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - DUST COLLECTOR | 4511-LE-020 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 884 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUMEHOOD | 4511-LE-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 885 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - FUSION SYSTEM | 4511-LE-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 886 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - HOT PLATE | 4511-LE-023 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 887 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MUFFLE FURNACE | 4511-LE-024 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 888 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-027 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 889 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER | 4511-LE-028 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 890 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - PULVERIZER DUST HOOD | 4511-LE-029 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 891 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP | 4511-LE-030 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 892 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - ROTAP DUST HOOD | 4511-LE-031 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 893 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - MAGNETITE ANALYSER | 4511-LE-032 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 894 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - SCRUBBER FAN | 4511-LE-033 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 895 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LABORATORY EQUIPMENT - SCRUBBER RECIRCULATION PUMP | 4511-LE-034 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 896 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - THERMOGRAVIMETRIC ANALYSER | 4511-LE-035 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4511 | Service Core | 897 | LE- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Lab Equip. | LABORATORY EQUIPMENT - XRF SPECTROMETER | 4511-LE-036 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 930 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - EMERGENCY RESPONSE OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4513-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 931 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4513-MT-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 932 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (PUMP) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 933 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 934 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE EMERGENCY RESPONSE GARAGE FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4513-PP-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 935 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4513-MT-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4510 | Accommodations Area | 4513 | Emergency Services Building | 936 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRY CHEMICAL REFILL STATION - TYCO FIRE PROTECTION | 4513-SQ-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 957 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 958 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 959 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WELDING SHOP FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4521-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 960 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 961 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 962 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 963 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MAINTENANCE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 964 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 965 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (DUTY) | 4521-PP-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 966 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-021 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 967 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WAREHOUSE BUILDING FUEL OIL PUMP (STANDBY) | 4521-PP-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 968 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4521-MT-022 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 969 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - WORKSHOP OFFICE WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483 W: 275 H: 267 | 4521-PP-051 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings | 970 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 4521-MT-051 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings |  | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ORE HAUL TRUCK WORKSHOP OFFICE WASHCAR RAW WATER PUMP - PLASTIC-MART L: 483, W: 275, H: 267 |  | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 978 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - INDUSTRIAL FREEZER - ONTARIO OVENS 80-12 L: 1525, W: 715, H: 1250, 290 kg | 4522-SQ-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 979 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - KIDNEY LOOP - AG - DYE10MFP240SA10QBV 50 kg | 4522-SQ-002 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 980 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LARGE SHOP PRESS - AG - OTC1866 L: 1295, W: 1727, H: 3125, 1970 kg | 4522-SQ-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 981 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LATHE - SUMMIT MACHINE TOOL W: 44, H: 64 | 4522-SQ-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 982 | MT- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | LATHE SPINDLE MOTOR | 4522-MT-004A | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 983 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | LATHE COOLANT PUMP | 4522-MT-004B | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 984 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MILLING MACHINE - AG | 4522-SQ-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 985 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LINE BORING MACHINE - CLIMAX BB5000 L: 1830 W: 330 H: 280 205 kg | 4522-SQ-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 986 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - IRON WORKER - BAILEIGH INDUSTRIAL 001-99777 L: 1525, W: 915, H: 1985, 2300 kg | 4522-SQ-008 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 987 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HEAVY TRUCK RAMP - ROTARY 60000HDL L: 13360, W: 4980, H: 3990 | 4522-SQ-009 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 988 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - LIGHT TRUCK RAMP - ROTARY SM18LO-X H: 6990 | 4522-SQ-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 989 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SIPING MACHINE - AG | 4522-SQ-011 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 990 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - AIR FILTER CLEANER - DIVERSI-TECH L: 1830, W: 1830, H: 2650 | 4522-SQ-012 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 991 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-018 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 992 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-019 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 993 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRILL PRESS - AG - DPE18-900 L: 508, W: 356, H: 1778, 120 kg | 4522-SQ-021 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 994 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - MAGNETIC BASE DRILL - AG - MTL4210-1 33 kg | 4522-SQ-022 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 995 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - OIL FILTER PRESS - OBERG P300 L: 1524, W: 914, H: 2640, 680 kg | 4522-SQ-023 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 996 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-026 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 997 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965 W: 584 H: 762 192 kg | 4522-SQ-027 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 998 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING FUME EXTRACTOR - AG - NED12634345 73 kg | 4522-SQ-028 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 999 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PORTABLE WELDING SPARK PROTECTOR - AG - NED12375241 | 4522-SQ-029 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1000 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - SWEEPER - AG | 4522-SQ-031 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1001 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE CHANGER - COATS APX80A | 4522-SQ-036 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1002 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG | 4522-SQ-038 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1003 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BULK FLUID DISTRIBUTION SYSTEM - AG | 4522-SQ-041 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1004 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-042 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1005 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - EVAC TANK - NORTHERN TOOL 30070V L: 1118, W: 508, H: 1093, 200 kg | 4522-SQ-043 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1006 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - WELDING MACHINE - AG - MLW951-277 L: 965, W: 584, H: 762, 192 kg | 4522-SQ-044 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1007 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - METAL BREAK FLOOR - AG - GGS13W877 580 kg | 4522-SQ-046 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1008 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-047 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1009 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-048 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1010 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-049 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1011 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PARTS WASHER - AG - GRYPL422A L: 1070, W: 560, H: 406, 84 kg | 4522-SQ-050 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1012 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TIRE SPREADER - ZHUHAI TEAMROC TR-S825 | 4522-SQ-051 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1013 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - HYDRAULIC PORTA POWER PUMP - AG | 4522-SQ-052 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1014 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-053 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1015 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-053 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1016 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-054 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1017 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-054 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1018 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-055 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1019 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-055 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1020 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - BENCH GRINDER - AG - WSWBG10D W: 610 H: 345 | 4522-SQ-056 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1021 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Bench grinder | BENCH GRINDER | 4522-MT-056 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1022 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRUCK MOUNT GOODALL BOOST SYSTEM - AG | 4522-SQ-059 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1023 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - GOODALL BOOST SYSTEM - AG | 4522-SQ-060 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1024 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TRACK PIN PRESS - AG - OTC4240 | 4522-SQ-063 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1025 | SQ- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment |  | SHOP / MAINTENANCE EQUIPMENT - A/C RECOVERY RECHARGE UNIT - ROBINAIR RBN17800B L: 584 W: 864 H: 1120 110 kg | 4522-SQ-064 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1026 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - INCHING TOOL - AG | 4522-SQ-065 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1027 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-066 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1028 | SQ- | MISC | Miscellanous Items (Minor) | Misc | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - BATTERY CHARGER - AG - WSW1JYU3 | 4522-SQ-067 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4522 | Services Equipment | 1029 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - TUBE BENDER - AG | 4522-SQ-068 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1034 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (DUTY) | 4523-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1035 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1036 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TRUCK WASH BUILDING FUEL OIL PUMP (STANDBY) | 4523-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4520 | Services Area | 4523 | Truck Wash Facility | 1037 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4523-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1075 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1076 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1077 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WASTE MANAGEMENT BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4540-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1078 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4540-MT-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1079 | SQ- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | SHOP / MAINTENANCE EQUIPMENT - AEROSOL CAN RECYCLING SYSTEM - AG - SAYCPU03 5 kg | 4540-SQ-002 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1080 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - DRUM CRUSHER - AG - VESHDC900IDC 650 kg | 4540-SQ-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4500 | Non Process Facilities | 4540 | Waste Management | 4540 | Waste Management | 1081 | SQ- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Shop Equipment | SHOP / MAINTENANCE EQUIPMENT - PLATFORM SCALE - AG | 4540-SQ-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1092 | FD- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Fuel dispenser | FUEL DISPENSER - DIESEL FUEL DISPENSING MODULE | 4613-FD-013 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1093 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1094 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1095 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1096 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1097 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1098 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1099 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-007 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4613 | Arctic Diesel System | 1100 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FUEL DISPENSING MODULE DISCHARGE PUMP | 4613-PP-008 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1105 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1106 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-002 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1107 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1108 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1109 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  | 1110 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERATOR | 4619-GE-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4600 | Fuel System | 4610 | Mine Tank Farm | 4619 |  |  | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - 1.35 MW GENERATOR |  | 3 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 57.6 | 639 | 5755.0107 | 6390 | 12784.0107 | 1 | 3 | 100% | 0% | 0% | 100% | 12784.0107 | 0 | 0 | 12784.0107 | Type A 2AM-MRY1325 | Removed | 2015 A | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 4261.3369 | 0 | 4261.3369 | 0 | 0 | 0 | 0 | 4261.3369 |  |  |  | MM2
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1124 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1125 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1126 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER DISTRIBUTION PUMP | 4720-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1127 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER DISTRIBUTION PUMP | 4720-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1128 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - DIESEL FIRE WATER PUMP | 4720-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1129 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - ELECTRIC FIRE WATER PUMP | 4720-PP-005 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1130 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - JOCKEY PUMP | 4720-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1131 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-008 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1132 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-008 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1133 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.1 | 4720-PP-010 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1134 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - POTABLE WATER DISCHARGE PUMP NO.2 | 4720-PP-011 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1135 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BACKWASH SLURRY PUMP | 4720-PP-013 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1136 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - CLEAN BACKWASH PUMP | 4720-PP-014 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1137 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - RAW WATER FEED PUMP | 4720-PP-015 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1138 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER FEED PUMP | 4720-MT-015 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1139 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-031 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1140 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-031 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1141 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE WATER BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4720-PP-032 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4720 | Water Systems | 4720 | Water Systems | 1142 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4720-MT-032 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1157 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.1 | 4731-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1158 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - TREATED EFFLUENT DISCHARGE PUMP NO.2 | 4731-PP-004 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4731 | Sewage Treatment Systems | 1159 | SC- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Screen | SCREEN - SCREEN | 4731-SC-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1168 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (DUTY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1169 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-001 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1170 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - MINE SEWAGE TRUCK BUILDING FUEL OIL PUMP (STANDBY) - VIKING DUPLEX OIL SYSTEMS | 4732-PP-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4732 | Sewage Truck Building | 1171 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | FUEL OIL PUMP | 4732-MT-002 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1174 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE | 4733-VM-001 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
4000 | Mine Site | 4700 | Site Utilities | 4730 | Sewage System | 4733 | Treated Effluent Pond | 1175 | VM- | MISC | Miscellanous Items (Minor) | MISC | Mechanical Equipment | Miscellaneous Items (Minor) |  | BULK MATERIAL VALVES - TREATED EFFLUENT POND SLUICE GATE SPARE | 4733-VM-002 | 1 | Ea | 2 | 30 | 199.8268 | 300 | 529.8268 | 2 | 30 | 199.8268 | 300 | 529.8268 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 529.8268 | 0 | 0 | 529.8268 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% | 33.33% | 33.33% | [5 empty] | 176.6089 | 176.6089 | 176.6089 | 0 | 0 | 0 | 0 | 0 |  |  |  | MISC
7000 | Construction Facilities & Services | 7200 | Construction Facilities & Services | 7210 | Exploration Camp & Facilities | 7213 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 5 | ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 96 | 1065 | 9591.6846 | 10650 | 21306.6846 | 1 | 5 | 100% | 0% | 0% | 100% | 21306.6846 | 0 | 0 | 21306.6846 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 7102.2282 | 0 | 7102.2282 | 0 | 0 | 0 | 0 | 7102.2282 | Including RBC. Power generation considered in Site Services mechanical equipment | Low | Disassembly & Decontaminate (Heavy Equipment), Load & transport, Disposal & Cover (incl compaction) | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1228 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - AERODROME OFFICE RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7231-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities | 1229 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7231-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1263 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1264 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1265 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1266 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1267 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7232-PP-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7230 | Buildings, Shops & Warehouses | 7232 | Workforce Facilities | 1268 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7232-MT-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1350 | GE- | MM3 | Heavy Equipment | MM3 | Mechanical Equipment | Heavy Equipment | Generator | GENERATOR - ACOMMODATIONS AREA GENERATOR - CUMMINS C1600D6R L: 14630, W: 2440, H: 4062, 68320 kg | 7244-GE-001 | 1 | Ea | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 168 | 2220 | 16785.448 | 22200 | 41205.448 | 56 | 56 | 100% | 0% | 0% | 100% | 41205.448 | 0 | 0 | 41205.448 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 13735.1493 | 0 | 13735.1493 | 0 | 0 | 0 | 0 | 13735.1493 |  |  |  | MM3
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1351 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-002 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1352 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4674, W: 1730, H: 2085, 8800 kg | 7244-GE-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1353 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1354 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4500, W: 1905, H: 2085, 5322 kg | 7244-GE-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1355 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 3776 kg | 7244-GE-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1356 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - LOGISTICS TRAILER GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315m 3776 kg | 7244-GE-007 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1357 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-008 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1358 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-009 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7200 | Milne Port | 7240 | Vehicles and Equipment | 7244 | Construction Power Supply | 1359 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 2442 kg | 7244-GE-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type B Construction 2BC-MRY1416 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Construction Facilities & Services | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Old Incinerator (Medium sized equipment) |  | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 | Add one pcs of minor mechanical equipment |  | Assumption | MM2
7000 | Construction Facilities & Services | 7400 | Construction Facilities & Services | 7410 | Exploration Camp & Facilities | 7412 | Utilities & Services |  |  | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment |  | Legacy Equipment |  | 5 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 96 | 1065 | 9591.6846 | 10650 | 21306.6846 | 1 | 5 | 100% | 0% | 0% | 100% | 21306.6846 | 0 | 0 | 21306.6846 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 7102.2282 | 0 | 7102.2282 | 0 | 0 | 0 | 0 | 7102.2282 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1425 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - BATCH PLANT OFFICE-LUNCHROOM-WC RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1426 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-003 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1427 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - FUEL SYSTEMS WASHCAR RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 50% | 50% | [6 empty] | 990.3992 | 990.3992 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1428 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-006 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1429 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #1 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1430 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-009 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1431 | PP- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | PUMP - SITE SERVICES WASHCAR #2 RAW WATER PUMP - SIMER JET PUMPS 2205C L: 483, W: 275, H: 267 | 7432-PP-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661 |  |  |  | MM1
7000 | Construction Facilities & Services | 7400 | Mine Site | 7430 | Buildings, Shops & Warehouses | 7432 | Workforce Facilities | 1432 | MT- | MM1 | Light Equimpent | MM1 | Mechanical Equipment | Light Equipment | Pump | RAW WATER TANK PUMP | 7432-MT-012 | 1 | Ea | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 8.1 | 106.5 | 809.2984 | 1065 | 1980.7984 | 0.5 | 0.5 | 100% | 0% | 0% | 100% | 1980.7984 | 0 | 0 | 1980.7984 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 660.2661 | 0 | 660.2661 | 0 | 0 | 0 | 0 | 660.2661
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1489 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - ACCOMMODATIONS AREA GENERATOR - CUMMINS C1600D6RG L: 14630, W: 2440, H: 4065, 78220 kg | 7444-GE-001 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1490 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-002 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1491 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - CONCRETE BATCH PLANT GENERATOR - CUMMINS C150D6R L: 4675, W: 1730, H: 2085, 10466 kg | 7444-GE-003 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1492 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - GENERAL GENERATOR - CUMMINS C80D6R L: 4496, W: 1905, H: 2085, 6458 kg | 7444-GE-004 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1493 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-005 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1494 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-006 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1495 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-007 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1496 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - AERODROME LIGHTING GENERATOR - CUMMINS C60D6R L: 4496, W: 1905, H: 2085, 6365 kg | 7444-GE-008 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1497 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-009 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1498 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-010 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1499 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - SITE SERVICES LUNCHROOM/WASHCAR GENERATOR - CUMMINS DSFAA L: 2110, W: 1020, H: 2315, 4760 kg | 7444-GE-011 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1500 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-012 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
7000 | Construction Facilities & Services | 7400 | Mine Site | 7440 | Vehicles and Equipment | 7444 | Construction Power Supply | 1501 | GE- | MM2 | Medium Equipment | MM2 | Mechanical Equipment | Medium Equipment | Generator | GENERATOR - WORKFACE TOOLS GENERATOR - CUMMINS DSKBA L: 2160, W: 790, H: 1500, 3145 kg | 7444-GE-013 | 1 | Ea | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 19.2 | 213 | 1918.3369 | 2130 | 4261.3369 | 1 | 1 | 100% | 0% | 0% | 100% | 4261.3369 | 0 | 0 | 4261.3369 | Type A 2AM-MRY1325 | Removed | 2014 | Direct | 33.33% |  | 33.33% |  |  |  |  | 33.33% | 1420.4456 | 0 | 1420.4456 | 0 | 0 | 0 | 0 | 1420.4456 |  |  |  | MM2
[31 empty] | vol |  | area
[29 empty] | 2347411.4057 |  | 2183.5 |  | 363.9167
[31 empty] | 16146.5268 |  | 16146.5268
2363557.9326

## Indirect Cost 2015 R (hidden)
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Notes | Uncertainty | Required Reclamation Activities
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Geotechnical Inspections |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 150000 | 0 | 0 | 100% | 0% | 0% | 100% | 150000 | 0 | 0 | 150000 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 30000 | 30000 | 30000 | 30000 | 30000 | Indirect cost. Will address at later date | TBD | N/A | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Geotechnical Inspections |  |  |  |  | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Indirect cost. Will address at later date | TBD | N/A | 0
8000 | Other Indirects | 8100 | Other Indirects | 8120 | Third Party Services | 8121 | Geotechnical Inspections |  |  |  |  | Indirect | Indirect | Indirect |  | Geotechnical Inspections | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Indirect cost. Will address at later date | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 90000 | 0 | 0 | 100% | 0% | 0% | 100% | 90000 | 0 | 0 | 90000 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 18000 | 18000 | 18000 | 18000 | 18000 | Indirect cost. Will address at later date | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Environmental Site Assessment |  |  |  |  | Indirect | Indirect | Indirect |  | Project Environmental Site Assessment | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect |  |  |  |  | 20% | 20% | 20% | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Closure & Post Closure Monitoring | [12 empty] | 851000 | 0 | 0 | 100% | 0% | 100% | 0% | 851000 | 0 | 851000 | 0 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  |  |  | 40% | 30% | 20% | 5% | 5% | 0 | 0 | 0 | 0 | 340400 | 255300 | 170200 | 42550 | 42550 | Fiel Sampling, analysis and reporting | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2015 R | Indirect |  |  |  |  | 40% | 30% | 20% | 5% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fiel Sampling, analysis and reporting | TBD | N/A | 0
8000 | Other Indirects | 8000 | Other Indirects | 8120 | Third Party Services | TBD | Closure & Post Closure Monitoring |  |  |  |  | Indirect | Indirect |  |  | Closure & Post Closure Monitoring | [12 empty] | 0 | 0 | 0 | 100% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Added | 2016 | Indirect |  |  |  |  | 40% | 30% | 20% | 5% | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fiel Sampling, analysis and reporting | TBD | N/A | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive Material) | [12 empty] | 876000 | 0 | 0 | 100% | 0% | 0% | 100% | 876000 | 0 | 0 | 876000 | Type A 2AM-MRY1325 | Removed | 2014 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 292000 | 292000 | 292000 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Ammonium Nitrate (explosive Material) | [12 empty] | 553110.6 | 0 | 0 | 100% | 0% | 0% | 100% | 553110.6 | 0 | 0 | 553110.6 | Type A 2AM-MRY1325 | Removed | 2015 | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 184370.2 | 184370.2 | 184370.2 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 A | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | Other Indirects | 8100 | Other Indirects | TBD | Material Disposal | TBD | Ammonium Nitrate (explosive Material) |  |  |  |  | Indirect | Indirect |  |  | Ammonium Nitrate (explosive Material) | [12 empty] | 0 | 0 | 0 | 100% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Type A 2AM-MRY1325 | Removed | 2015 R | Indirect |  |  | 33.33% | 33.33% | 33.33% | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF!

## Sheet2 (hidden)
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description | ID CODE | Equipment Type | Price Code | Price Code Description | Qty Code | Area - QTY Code | QTY Code Description | Type | Description | Tag Number | QTY | Unit | Manhours Per Unit | Unit Fuel Consumption | Unit Labour | Unit Equipment | Unit Rate | Total Manhours | Total Fuel Consumption | Total Labour | Total Equipment | Total Cost ($) | Unit M3 | Total Vol (m3) | IOL (%) | Crown Land (%) | Water Liability (%) | Land Liability (%) | IOL Cost ($) | Crown Land Cost ($) | Water Liability Cost ($) | Land Liability Cost ($) | License | Adjustment Tag | Associated Work Plan | Type of Costs | Year 0 - % | Year 0+1 - % | Year 1 - % | Year 2 - % | Year 3 - % | Year 4 - % | Year 5 - % | Year 6 - % | Year 7 - % | Year 8 - % | Year 0- Cost ($) | Year 0+1- Cost ($) | Year 1 - Cost ($) | Year 2 - Cost ($) | Year 3 - Cost ($) | Year 4 - Cost ($) | Year 5 - Cost ($) | Year 6 - Cost ($) | Year 7 - Cost ($) | Year 8 - Cost ($) | Notes | Uncertainty | Required Reclamation Activities
9000 | Owner Accounts | 9100 | Owner Accounts | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency |  |  |  | Indirect | Indirect | Indirect | Indirect |  | Contingency | [12 empty] | 846000 | 0 | 0 | 0.79044 | 0.20956 | 0 | 1 | 668713.4251 | 177286.5749 | 0 | 846000 | Type A 2AM-MRY1325 | Added | 2017-A | Indirect |  |  | 1 | [7 empty] | 0 |  | 846000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% of Total direct cost, Contaminated soil treatement, Mob/demob, Workers accomodation & camps Opp, Workers mob/demob and post closure monitoring |  | TBD

## Breakdown per licence (hidden)
ROUGH NUMBERS | [8 empty] | ROUNDED NUMBERS
| A | B | C | D | E | F | G | H |  | A | B | C | D | E | F | G | H
Row | Authorization | Liability | Pre-baseline Liability ($) | 2014 Re-Baseline ($) | Difference ($) | Marginal 2015 ($) | Total ($) | Adjustment to be posted ($) | Row | Authorization | Liability | Pre-baseline Liability ($) | 2014 Re-Baseline ($) | Difference ($) | Marginal 2015 ($) | Total ($) | Adjustment to be posted ($)
| E: D-C; G: D+F; H: E+F-Type B construction | [5 empty] | D-C |  | D+F | E+F-Type B construction
1 | Type A 2AM-MRY1325 | IOL | 40231000 | 38886019 | -1344981 | 2236019.717 | 41122038.717 | 744038.717 | 1 | Type A 2AM-MRY1325 | IOL | 40231000 | 38886000 | -1345000 | 2236000 | 41122000 | 744000
2 |  | Crown | 166000 | 0 | -166000 | 0 | 0 | -166000 | 2 |  | Crown | 166000 | 0 | -166000 | 0 | 0 | -166000
3 |  | Water | 2172000 | 2192622 | 20622 | 0 | 2192622 | 20622 | 3 |  | Water | 2172000 | 2193000 | 21000 | 0 | 2193000 | 21000
4 |  | Land | 38225000 | 36693398 | -1531602 | 2236019.717 | 38929417.717 | 557417.717 | 4 |  | Land | 38225000 | 36693000 | -1532000 | 2236000 | 38929000 | 557000
5 | Subtotal Type A |  | 40397000 | 38886019 | -1510981 | 2236019.717 | 41122038.717 | 578038.717 | 5 | Subtotal Type A |  | 40397000 | 38886000 | -1511000 | 2236000 | 41122000 | 578000
6 | Type B Construction 2BC-MRY1416 | IOL | 147000 | See note 3 | 0 | 0 | 0 | 0 | 6 | Type B Construction 2BC-MRY1416 | IOL | 147000 | See note 3 | 0 | 0 | 0 | 0
7 |  | Crown | 0 |  | 0 | 0 | 0 | 0 | 7 |  | Crown | 0 |  | 0 | 0 | 0 | 0
8 |  | Water | 0 |  | 0 | 0 | 0 | 0 | 8 |  | Water | 0 |  | 0 | 0 | 0 | 0
9 |  | Land | 147000 |  | 0 | 0 | 0 | 0 | 9 |  | Land | 147000 |  | 0 | 0 | 0 | 0
10 | Subtotal Type B Construction |  | 147000 |  | 0 | 0 | 0 | 0 | 10 | Subtotal Type B Construction |  | 147000 |  | 0 | 0 | 0 | 0
11 | Type B Exploration 2BE-MRY1421 | IOL | 165000 | 165000 | 0 | 0 | 165000 | 0 | 11 | Type B Exploration 2BE-MRY1421 | IOL | 165000 | 165000 | 0 | 0 | 165000 | 0
12 |  | Crown | 1082000 | 1082000 | 0 | 0 | 1082000 | 0 | 12 |  | Crown | 1082000 | 1082000 | 0 | 0 | 1082000 | 0
13 |  | Water | 18000 | 18000 | 0 | 0 | 18000 | 0 | 13 |  | Water | 18000 | 18000 | 0 | 0 | 18000 | 0
14 |  | Land | 1229000 | 1229000 | 0 | 0 | 1229000 | 0 | 14 |  | Land | 1229000 | 1229000 | 0 | 0 | 1229000 | 0
15 | Subtotal Type B Exploration |  | 1247000 | 1247000 | 0 | 0 | 1247000 | 0 | 15 | Subtotal Type B Exploration |  | 1247000 | 1247000 | 0 | 0 | 1247000 | 0
16 | DFO | IOL | 0 | 0 | 0 | 0 | 0 | 0 | 16 | DFO | IOL | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Crown | 3566000 | 3566000 | 0 | 0 | 3566000 | 0 | 17 |  | Crown | 3566000 | 3566000 | 0 | 0 | 3566000 | 0
18 |  | Water | 3566000 | 3566000 | 0 | 0 | 3566000 | 0 | 18 |  | Water | 3566000 | 3566000 | 0 | 0 | 3566000 | 0
19 |  | Land | 0 | 0 | 0 | 0 | 0 | 0 | 19 |  | Land | 0 | 0 | 0 | 0 | 0 | 0
20 | Subtotal DFO |  | 3566000 | 3566000 | 0 | 0 | 3566000 | 0 | 20 | Subtotal DFO |  | 3566000 | 3566000 | 0 | 0 | 3566000 | 0
21 | AANDC Land Lease 47H/16-1-2 | IOL | 0 | 0 | 0 | 0 | 0 | 0 | 21 | AANDC Land Lease 47H/16-1-2 | IOL | 0 | 0 | 0 | 0 | 0 | 0
22 |  | Crown | 0 | 5931082 | 5931082 | 0 | 5931082 | 5931082 | 22 |  | Crown | 0 | 5931000 | 5931000 | 0 | 5931000 | 5931000
23 |  | Water | 0 | 0 | 0 | 0 | 0 | 0 | 23 |  | Water | 0 | 0 | 0 | 0 | 0 | 0
24 |  | Land | 0 | 5931082 | 5931082 | 0 | 5931082 | 5931082 | 24 |  | Land | 0 | 5931000 | 5931000 | 0 | 5931000 | 5931000
25 | Subtotal AANDC Land Lease |  | 0 | 5931082 | 5931082 | 0 | 5931082 | 5931082 | 25 | Subtotal AANDC Land Lease |  | 0 | 5931000 | 5931000 | 0 | 5931000 | 5931000
27 | GRAND TOTAL |  | 45357000 | 49630101 | 4420101 | 2236019.717 | 51866120.717 | 6509120.717 | 27 | GRAND TOTAL |  | 45357000 | 49630000 | 4420000 | 2236000 | 51866000 | 6509000
Note 1 : Total for each licence is the sum of IOL and Crown Land (which equals the sum of Water and Land)
Note 2: Captured under 2014 rebaseline exercise. proposed to be re-allocated under typeA licence upon ammendment
References
Column A - Based on Table 3-1 of Baffinland Response to AANDC Questions Regarding 2014 Workplan and Security Estimate
Column B' - 2014 Complete Project Financial Security Assessment
Column B (type A) - Real Baseline minus Type B construction

## Breakdown per Year (hidden)
Associated Work Plan | 2015 A
Values
Row Labels | Year 1 ($) | Year 2 ($) | Year 3 ($) | Year 4 ($) | Year 5 ($) | Year 6 ($) | Year 7 ($) | Year 8 ($) | Total ($)
Direct | 55471.8993 | 254022.046 | 44747.0693 | 0 | 0 | 0 | 0 | 0 | 354241.0147
Indirect | 35000 | 33600 | 32200 | 14600 | 13200 | 13200 | 6600 | 6600 | 155000
Mary River Exploration Activities | 1247000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247000
DFO Financial Security for Ore Dock (Construction and Monitoring) | 3566000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3566000
Grand Total ($) | 4903471.8993 | 287622.046 | 76947.0693 | 14600 | 13200 | 13200 | 6600 | 6600 | 5322241.0147

## PIVOT_ESTIMATE DETAILS (hidden)
Level 0 |  | Level 1 |  | Level 2 |  | Level 3
Level 0 - Site Location | Level 0 - Description | Level 1 - Area | Level 1 - Description | Level 2 - Facility / System | Level 2 - Description | Level 3 - Sub Facility / Sub System | Level 3 - Description
1000 | Project Wide | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use) | 1100 | General (Project Controls Use)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
2000 | Milne Port | 2500 | Non Process Facilities | 2540 | Waste Management (building and incinerator) | 2540 | Waste Management (building and incinerator)
|  |  |  | 2550 | Waste Disposal | 2550 | Waste Disposal
|  |  |  | 2510 | Accommodations Area | 2511 | Service Core
[6 empty] | 2512 | Accommodation Wings
[6 empty] | 2510 | Accommodations Area
[6 empty] | 2511 | Service Core
[6 empty] | 2512 | Accommodation Wings
[6 empty] | 2513 | Emergency Services Building
[6 empty] | 2513 | Emergency Services Building
|  |  |  | 2520 | Services Area | 2521 | Services Buildings
[6 empty] | 2521 | Services Buildings
[6 empty] | 2521 | Services Buildings
[6 empty] | 2522 | Services Equipment
[6 empty] | 2523 | Services Area
|  |  |  | 2530 | Power Generation | 2530 | Power Generation
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 2100 | General | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure
|  |  |  | 2130 | Site Development | 2131 | Construction Laydown
[6 empty] | 2133 | Materials Handling
[6 empty] | 2134 | (blank)
[6 empty] | 2136 | Milne Port
[6 empty] | 2138 | Quarry Development
[6 empty] | 2139 | Site Roads
|  |  |  | 2140 | Mobile Equipment | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
|  |  |  | 2110 | Communication and IT Infrastructure | 2110 | Communication and IT Infrastructure
|  |  |  | 2140 | Mobile Equipment | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
[6 empty] | 2143 | Mobile Maintenance Equipment
[6 empty] | 2144 | Mobile Site Services Equipment
[6 empty] | 2140 | Mobile Equipment
[6 empty] | 2142 | Mobile Materials Handling Equipment
[6 empty] | 2143 | Mobile Maintenance Equipment
[6 empty] | 2144 | Mobile Site Services Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2200 | Marine | 2220 | Ore Dock | 2221 | Dock Structure (includes ship loader foundations)
[6 empty] | 2225 | Mooring Buoys
[6 empty] | 2230 | Causeway
|  |  |  | 2240 | Transshipment and Marine Vessels | 2240 | Transshipment and Marine Vessels
|  |  |  | 2220 | Ore Dock | 2223 | Dock Office
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2300 | Material Handling | 2340 | Stockpile | 2345 | Stockpile Settling Pond
[6 empty] | 2341 | Ore Stacking System
|  |  |  | 2340 | Stockpile | 2341 | Ore Stacking System
[6 empty] | 2342 | Ore Reclaim System
[6 empty] | 2341 | Ore Stacking System
[6 empty] | 2342 | Ore Reclaim System
[6 empty] | 2342 | Ore Reclaim System
|  |  |  | 2350 | Ship Loading | 2351 | Ship Loading System
[6 empty] | 2351 | Ship Loading System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2400 | Aerodrome | 2430 | Aerodrome Facilities | 2430 | Aerodrome Facilities
[6 empty] | 2435 | Field Electrical Centre
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2600 | Fuel System | 2610 | Milne Tank Farm | 2611 | Containment Dyke
|  |  |  | 2610 | Milne Tank Farm | 2614 | Jet-A System
[6 empty] | 2610 | Milne Tank Farm
[6 empty] | 2613 | Arctic Diesel System
[6 empty] | 2613 | Arctic Diesel System
[6 empty] | 2614 | Jet-A System
[6 empty] | 2614 | Jet-A System
[6 empty] | 2615 | Marine Pipeline
[6 empty] | 2619 | Power Generation
[6 empty] | 2616 | Weatherhaven camp
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 2700 | Site Utilities | 2730 | Sewage System | 2731 | Treated Effluent Discharge
[6 empty] | 2735 | Off Spec Effluent Pond
|  |  |  | 2610 | Milne Tank Farm | 2613 | Arctic Diesel System
|  |  |  | 2720 | Water Systems | 2720 | Water Systems
[6 empty] | 2720 | Water Systems
[6 empty] | 2720 | Water Systems
|  |  |  | 2730 | Sewage System | 2731 | Sewage Treatment Systems
[6 empty] | 2731 | Sewage Treatment Systems
[6 empty] | 2732 | Sewage Truck Building
[6 empty] | 2732 | Sewage Truck Building
[6 empty] | 2734 | Treated Effluent Discharge
|  |  |  | 2750 | Power Distribution System | 2750 | Power Distribution System
[6 empty] | 2750 | Power Distribution System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 2710 | Additional Tanks | 2710 | Additional Tanks
|  |  |  | 0 | Power Distribution System |  | Power Distribution System
3000 | Mine Site | 3500 | Non Process Facilities | 3510 | Accommodations Area | 3512 | Accommodation Wings
| Tote Road | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 3100 | General | 3110 | Communication and IT Infrastructure | 3114 | Communications Facility No. 4
|  |  |  | 3130 | Site Development | 3130 | Site Development
[6 empty] | 3131 | Road Upgrade
[6 empty] | 3132 | River Crossing at STA 17
[6 empty] | 3133 | River Crossing at STA 62
[6 empty] | 3134 | River Crossing at STA 80
[6 empty] | 3135 | River Crossing at STA 97
[6 empty] | 3136 | Mary River
[6 empty] | 3138 | Borrow Source at Km 102
Borrow Source at Km 97/98
Borrow Source at P1
Quarry at Q1
Quarry at Q11
Quarry at Q19
Quarry at Q7
Quarry Development
Unidentified Borrow Sources
Borrow Source at Km 2
Quarry at Q13
Quarry at Q14
Quarry at Q15
Quarry at Q16A
Quarry at P5
Quarry at P6
Quarry at P7
Quarry at P8
Quarry at P10
Quarry at P13
Quarry at P14
Quarry at P15
Quarry at PQ5A
Quarry at PQ5B
Quarry at PQ2A
Quarry at PQ6A
Quarry at PQ6B
Quarry at PQ12B
Quarry at PQ14A
Quarry at PQ14B
Quarry at PQ4A
Quarry at PQ4B
Quarry at Q12
Quarry at Q5
Q13 Quarry (marginal increase to existing)
[6 empty] | 3139 | Infrastructure Pads
[6 empty] | TBD | Sea-can bridge at STA 17
Sea-can bridge at STA 62
Sea-can bridge at STA 80
Sea-can bridge at STA 97
|  |  |  | 3110 | Communication and IT Infrastructure | 3111 | Communications Facility No. 1
[6 empty] | 3112 | Communications Facility No. 2
[6 empty] | 3113 | Communications Facility No. 3
|  |  |  | 3160 | Emergency Shelters | 3160 | Emergency Shelters
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 3200 | General | 3210 | Exploration Camp & Facilities | 3212 | Hardwall Camp
[5 empty] | Explosives Facility | 3213 | Explosives Magazines
4000 | Construction Facilities & Services | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
| Milne Port | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
| Mine Site | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
Mine Mobile Equipment
Raw Water System
[6 empty] | 4133 | Ore Crushing and Loading
[6 empty] | 4135 | Explosives Pads
[6 empty] | 4138 | Quarry Development
[6 empty] | 4139 | Site Roads
|  |  |  | 4140 | Mobile Equipment | 4140 | Mobile Equipment
|  |  |  | 4140 | Mobile Equipment | 4141 | Mine Mobile Equipment
[6 empty] | 4142 | Mobile Materials Handling Equipment
Mobile Site Services Equipment
[6 empty] | 4143 | Mobile Maintenance Equipment
[6 empty] | 4144 | Mobile Site Services Equipment
[6 empty] | 4141 | Mine Mobile Equipment
[6 empty] | 4142 | Mobile Materials Handling Equipment
[6 empty] | 4143 | Mobile Maintenance Equipment
[6 empty] | 4144 | Mobile Site Services Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 4110 | Communication and IT Infrastructure | 4110 | Communication and IT Infrastructure
[5 empty] | Site Development | 4136 | Tote Road
|  | 4200 | Mine | 4210 | Explosives Facility | 4211 | Explosives Plant Building
[6 empty] | 4212 | Explosives Shop
[6 empty] | 4213 | Explosives Magazines
|  |  |  | 4220 | Accommodations Area | 4222 | Explosive pad haul road
[5 empty] | Haul Roads | 4221 | Pit 1 Haul Road
|  |  |  | 4230 | Waste Rock Dump | 4230 | Waste Rock Dump
[5 empty] | Waste Rock Pond | 4230 | Waste Rock Pond
|  |  |  | 4250 | Open Pit Development | 4250 | Open Pit Development
|  |  |  | 4280 | Mine Support Facilities | 4281 | Pit Office Building
|  |  |  | 4280 | Mine Support Facilities | 4281 | Pit Office Building
[6 empty] | 4281 | Pit Office Building
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 4300 | Material Handling | 4380 | Crushing and Screening | 4381 | Crushing and Screening System
[6 empty] | 4382 | Truck Weigh Facility
[6 empty] | 4385 | Crushing Stockpile Settling Pond
|  |  |  | 4380 | Crushing and Screening | 4381 | Crushing and Screening System
[6 empty] | 4382 | Truck Weigh Facility
[6 empty] | 4385 | Crushing Stockpile Settling Pond
[6 empty] | 4381 | Crushing and Screening System
[6 empty] | 4381 | Crushing and Screening System
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4400 | Aerodrome | 4410 | Runway & Apron | 4410 | Runway & Apron
|  |  |  | 4430 | Aerodrome Facilities | 4430 | Aerodrome Facilities
[6 empty] | 4436 | Airfield Lighting and Visual Aids
[6 empty] | 4439 | Power Generation
|  |  |  | 4430 | Aerodrome Facilities | 4431 | Aerodrome Office
[6 empty] | 4431 | Aerodrome Office
[6 empty] | 4432 | Equipment Building
[6 empty] | 4433 | Plant & Equipment
[6 empty] | 4435 | Field Electrical Centre
[6 empty] | 4434 | Plant & Equipment
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  | Non Process Facilities | 4430 | Aerodrome Facilities | 4432 | Equipment Building
|  | 4500 | Non Process Facilities | 4520 | Services Area | 4521 | Services Buildings
|  |  |  | 4540 | Waste Management | 4540 | Waste Management
|  |  |  | 4510 | Accommodations Area | 4510 | Accommodations Area
[6 empty] | 4511 | Service Core
[6 empty] | 4512 | Accommodation Wings
[6 empty] | 4513 | Emergency Services Building
|  |  |  | 4520 | Services Area | 4521 | Services Buildings
[6 empty] | 4522 | Services Equipment
[6 empty] | 4523 | Truck Wash Facility
|  |  |  | 4530 | Aerodrome Facilities | 4530 | Aerodrome Facilities
[5 empty] | Crushing and Screening | 4530 | Crushing and Screening
[5 empty] | Mobile Equipment | 4530 | Mobile Equipment
[5 empty] | Power Generation | 4530 | Power Generation
[5 empty] | Raw Water Intake | 4530 | Raw Water Intake
[5 empty] | Services Area | 4530 | Services Area
[5 empty] | Waste Management | 4530 | Waste Management
|  |  |  | 4540 | Waste Management | 4540 | Waste Management
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4600 | Fuel System | 4610 | Mine Tank Farm | 4611 | Containment Dyke
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4613 | Arctic Diesel System
[6 empty] | 4614 | Jet-A System
[6 empty] | 4619 | Generator
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 4700 | Site Utilities | 4710 | Raw Water Intake | 4711 | Raw Water Jetty
[6 empty] | 4712 | Raw Water System
|  |  |  | 4720 | Water Systems | 4720 | Water Systems
|  |  |  | 4730 | Sewage System | 4731 | Sewage Treatment Systems
[6 empty] | 4732 | Sewage Truck Building
[6 empty] | 4733 | Treated Effluent Pond
[6 empty] | 4734 | Treated Effluent Discharge
|  |  |  | 4750 | Power Distribution System | 4750 | Power Distribution System
|  |  |  | 4720 | Water Systems | 4720 | Water Systems
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 4740 | Additional Tanks | 4740 | Additional Tanks
| Tote Road | 4100 | General | 4130 | Site Development | 4131 | Construction Laydown Areas
7000 | Construction Facilities & Services | 7200 | Milne Port | 7210 | Exploration Camp & Facilities | 7211 | Tent Camp
[6 empty] | 7212 | Hardwall Camp
[6 empty] | 7213 | Utilities & Services
[6 empty] | 7214 | Off-Spec Effluent Pond(s)
|  |  |  | 7230 | Buildings, Shops & Warehouses | 7231 | Office Facilities
[6 empty] | 7232 | Workforce Facilities
[6 empty] | 7234 | Garages & Workshops
[6 empty] | 7235 | Warehouses
[6 empty] | 7238 | Civil Contractor Buildings
|  |  |  | 7240 | Vehicles and Equipment | 7241 | Company Vehicles
[6 empty] | 7242 | Emergency Response Equipment
[6 empty] | 7244 | Construction Power Supply
[6 empty] | 7243 | Site Operations Mobile Equipment
[6 empty] | 7245 | Cranes and Lifting Equipment
|  |  |  | 7250 | Construction Facilities | 7251 | Concrete Facilities
[6 empty] | 7252 | Explosives Facilities
|  |  |  | 7270 | Camp & Site Services | 7271 | Camp Operations & Catering
[6 empty] | 7273 | Site Operations
[6 empty] | 7275 | Maintenance and Repair
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 7100 | Project Wide | 7110 | Communications & IT | 7111 | Communications Services
|  |  |  | 7120 | Air Services | 7121 | Jet Service
[6 empty] | 7122 | Local Air Charter
[6 empty] | 7123 | Helicopter Service
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  | 7300 | Tote Road | (blank) | (blank) | (blank) | (blank)
|  |  |  | 7340 | Vehicles and Equipment | 7340 | Vehicles and Equipment
|  | 7400 | Mine Site | 7410 | Exploration Camp & Facilities | 7411 | Tent Camp
[6 empty] | 7412 | Utilities & Services
|  |  |  | 7430 | Buildings, Shops & Warehouses | 7431 | Office Facilities
[6 empty] | 7432 | Workforce Facilities
[6 empty] | 7434 | Garages & Workshops
[6 empty] | 7435 | Warehouses
|  |  |  | 7470 | Camp & Site Services | 7470 | Camp & Site Services
[6 empty] | 7471 | Camp Operations & Catering
[6 empty] | 7473 | Site Operations
[6 empty] | 7475 | Maintenance and Repair
|  |  |  | 7480 | Construction Services | 7482 | Heavy Transport Services
[6 empty] | 7484 | Explosives Supply Services
|  |  |  | 7450 | Construction Facilities | 7451 | Concrete Facilities
|  |  |  | (blank) | (blank) | (blank) | (blank)
|  |  |  | 7440 | Vehicles and Equipment | 7441 | Company Vehicles
[6 empty] | 7443 | Site Operations Mobile Equipment
[6 empty] | 7444 | Construction Power Supply
[6 empty] | 7445 | Cranes and Lifting Equipment
8000 | Other Indirects | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
|  | 8100 | Other Indirects | 8110 | EPCM Services | 8111 | EPCM Services
Project Management, Engineering and Procurement
[6 empty] | 8112 | Project Management, Engineering and Procurement
|  |  |  | 8120 | Third Party Services | 8121 | Project Management, Engineering and Procurement
[6 empty] | TBD | Closure & Post Closure Monitoring
Environmental Site Assessment
|  |  |  | TBD | Material Disposal | TBD | Fuel
Ammonium Nitrate (explosive Material)
Off-Site Disposal of Waste & Material
Contaminated Soil Treatment
[5 empty] | Mobilization | TBD | Mobilization and Demobilization
Worker Accommodation & Camp Operation
|  |  |  | (blank) | (blank) | (blank) | (blank)
9000 | Owner Accounts | 9100 | Owner Accounts | 9120 | Project Management | 9121 | Owner Accounts - Project Management
|  |  |  | 9190 | Contingency, Escalation, Event Risk Allowance | 9191 | Contingency
|  |  |  | (blank) | (blank) | (blank) | (blank)
Grand Total

## Unit Rate Analysis (hidden)
Code | Unit Rates | Quantities (As pER estimate) |  | BASE CASE | [6 empty] | SCENARIO 1 | [5 empty] | VARIACE
|  | QTY | Unit | Manhours Per Unit | Fuel Consumption | Labour | Material | Equipment | Total Unit Cost | Total Cost | Fuel Consumption | Labour | Material | Equipment | Total Unit Cost | Total Cost | Total Unit Cost | Total Cost
| Blended Rate |  |  |  | 10% | 100 |  | 150 |  |  | 10% | 100 |  | 150
| Fuel Cost [$/L] | [5 empty] | 0.966 | [5 empty] | 0.966
| Rock Drill Purchase | [6 empty] | 375000 | [5 empty] | 375000
| Mobile Crushing Plant Purchase | [6 empty] | 2500000 | [5 empty] | 2500000
| CAT 980 FEL Purchase | [6 empty] | 243194 | [5 empty] | 243194
| CAT 740 Hault Truck Purchase | [6 empty] | 425000 | [5 empty] | 425000
| CAT D8T Dozer Purchase | [6 empty] | 324955 | [5 empty] | 324955
| CAT 385 Excavator Purchase | [6 empty] | 572500 | [5 empty] | 572500
| Pentax Boost | [5 empty] | 10.48 | [5 empty] | 10.48
| Detonator | [5 empty] | 15 | [5 empty] | 15
| Cordex [$/m] | [5 empty] | 0.89 | [5 empty] | 0.89
| ANFO [$/mt] | [5 empty] | 650 | [5 empty] | 650
Code | Unit Rates | Quantities (As pER estimate) |  | BASE CASE | [6 empty] | SCENARIO 1 | [5 empty] | VARIACE
|  | QTY | Unit | Manhours Per Unit | Fuel Consumption | Labour | Material | Equipment | Total Unit Cost | Total Cost | Fuel Consumption | Labour | Material | Equipment | Total Unit Cost | Total Cost | Total Unit Cost | Total Cost
A1 | Disposal and Cover Incl (Compaction) | 0 | m2 | 0.66304 | 2.3514 | 64.7694 |  | 24.8098 | 89.5792 | 0 | 2.3514 | 64.7694 |  | 24.8098 | 89.5792 | 0 | 0 | 0
- | Disposal |  | m2 | 0.5 | 1 | 50 |  | 10 | 60 |  | 1 | 50 |  | 10 | 60 |  | 0
- | Cover and Compact assume 1m cover |  | m3 | 0.16304 | 1.3514 | 14.7694 |  | 14.8098 | 29.5792 |  | 1.3514 | 14.7694 |  | 14.8098 | 29.5792 |  | 0
46.3958
A2 | Fill Application - Assumed average Depth of 1.50 m3 | 35124.3549 | m2 | 0.24456 | 2.0271 | 22.1541 |  | 22.2146 | 44.3687 | 1558423.6454 | 2.0271 | 22.1541 |  | 22.2146 | 44.3687 | 1558423.6454 | 0 | 0
- | Fill |  | m3 | 0.16304 | 1.3514 | 14.7694 |  | 14.8098 | 29.5792 |  | 1.3514 | 14.7694 |  | 14.8098 | 29.5792 |  | 0
A3 | Grade & Re-Contour | 3291322.9011 | m2 | 0.01269 | 0.14625 | 1.269 |  | 0.39655 | 1.8103 | 5958266.5294 | 0.14625 | 1.269 |  | 0.39655 | 1.8103 | 5958266.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | Grade and Re-Countour assume .5m avg |  | m3 | 0.02538 | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | 0
A3l | Grade & Re-Contour with Liner | 120231.76 | m2 | 0.04449 | 0.17805 | 4.449 |  | 0.71455 | 5.3083 | 638225.692 | 0.17805 | 4.449 |  | 0.71455 | 5.3083 | 638225.692 | 0 | 0
- | Grade and Re-Countour assume .5m avg |  | m3 | 0.02538 | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | 0.2925 | 2.538 |  | 0.79309 | 3.6206 |  | 0
A4 | Grade & Re-Contour Type A quarry | 263371 | m2 | 0.019035 | 0.21937 | 1.9035 |  | 0.59482 | 2.7154 | 715168.9433 | 0.21937 | 1.9035 |  | 0.59482 | 2.7154 | 715168.9433 | 0 | 0
- | Add 50% to A3 |  | m2 | 0.01269 | 0.14625 | 1.269 |  | 0.39655 | 1.8103 |  | 0.14625 | 1.269 |  | 0.39655 | 1.8103 |  | 0
cu | Culvert Removal | 383 | Ea | 6 | 45 | 600 |  | 450 | 1095 | 419385 | 45 | 600 |  | 450 | 1095 | 419385 | 0 | 0
- | Culvert Removal - |  | Ea | 6 | 45 | 600 |  | 450 | 1095 |  | 45 | 600 |  | 450 | 1095 |  | 0
A5 | Liner Removal | 682 | m2 | 0.0318 | 0.0318 | 3.18 |  | 0.318 | 3.498 | 2385.636 | 0.0318 | 3.18 |  | 0.318 | 3.498 | 2385.636 | 0 | 0
- | Liner removal - 100% of typical installation |  | m2 | 0.0318 | 0.0318 | 3.18 |  | 0.318 | 3.498 |  | 0.0318 | 3.18 |  | 0.318 | 3.498 |  | 0
EM | Open Pit Stabilization | 0 | m3 | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 | 0 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 | 0 | 0 | 0
- | Assume cut and fill per m3? |  | m3 | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 |  | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 |  | 0
STK | Stockpile Removal | 0 | m2 | 0.17347 | 2.0499 | 14.6508 |  | 16.4435 | 31.0943 | 0 | 2.0499 | 14.6508 |  | 16.4435 | 31.0943 | 0 | 0 | 0
- | Stockpile Removal |  | Lot | 0.034693 | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 |  | 0.40997 | 2.9302 |  | 3.2887 | 6.2189 |  | 0
MM1 | Light Equimpent | 135 | Ea | 8.1 | 106.5 | 810 |  | 1065 | 1981.5 | 267502.5 | 106.5 | 810 |  | 1065 | 1981.5 | 267502.5 | 0 | 0
- | Disassembly |  | Ea | 5 | 75 | 500 |  | 750 | 1325 |  | 75 | 500 |  | 750 | 1325 |  | 0
- | Decontaminate |  | Ea | 1 |  | 100 |  | 0 | 100 |  |  | 100 |  | 0 | 100 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 0.1 | 1.5 | 10 |  | 15 | 26.5 |  | 1.5 | 10 |  | 15 | 26.5 |  | 0
MM2 | Medium Equipment | 53 | Ea | 19.2 | 213 | 1920 |  | 2130 | 4263 | 225939 | 213 | 1920 |  | 2130 | 4263 | 225939 | 0 | 0
- | Disassembly |  | Ea | 10 | 150 | 1000 |  | 1500 | 2650 |  | 150 | 1000 |  | 1500 | 2650 |  | 0
- | Decontaminate |  | Ea | 5 |  | 500 |  | 0 | 500 |  |  | 500 |  | 0 | 500 |  | 0
- | Load |  | Ea | 4 | 60 | 400 |  | 600 | 1060 |  | 60 | 400 |  | 600 | 1060 |  | 0
- | Transport |  | Ea | 0.2 | 3 | 20 |  | 30 | 53 |  | 3 | 20 |  | 30 | 53 |  | 0
MM3 | Heavy Equipment | 6 | Ea | 168 | 2220 | 16800 |  | 22200 | 41220 | 247320 | 2220 | 16800 |  | 22200 | 41220 | 247320 | 0 | 0
- | Disassembly |  | Ea | 120 | 1800 | 12000 |  | 18000 | 31800 |  | 1800 | 12000 |  | 18000 | 31800 |  | 0
- | Decontaminate |  | Ea | 20 |  | 2000 |  | 0 | 2000 |  |  | 2000 |  | 0 | 2000 |  | 0
- | Load |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
- | Transport |  | Ea | 8 | 120 | 800 |  | 1200 | 2120 |  | 120 | 800 |  | 1200 | 2120 |  | 0
O1 | Light Mobile Equipment | 264 | Ea | 6.6667 | 25 | 666.6667 |  | 250 | 941.6667 | 248600 | 25 | 666.6667 |  | 250 | 941.6667 | 248600 | 0 | 0
- | Disassembly |  | Ea | 2 | 0 | 200 |  | 0 | 200 |  | 0 | 200 |  | 0 | 200 |  | 0
- | Decontaminate |  | Ea | 3 |  | 300 |  | 0 | 300 |  |  | 300 |  | 0 | 300 |  | 0
- | Load |  | Ea | 1 | 15 | 100 |  | 150 | 265 |  | 15 | 100 |  | 150 | 265 |  | 0
- | Transport |  | Ea | 0.66667 | 10 | 66.6667 |  | 100 | 176.6667 |  | 10 | 66.6667 |  | 100 | 176.6667 |  | 0
O2 | Medium Mobile Equipment | 143 | Ea | 10 | 45 | 1000 |  | 450 | 1495 | 213785 | 45 | 1000 |  | 450 | 1495 | 213785 | 0 | 0
- | Disassembly |  | Ea | 3 | 0 | 300 |  | 0 | 300 |  | 0 | 300 |  | 0 | 300 |  | 0
- | Decontaminate |  | Ea | 4 |  | 400 |  | 0 | 400 |  |  | 400 |  | 0 | 400 |  | 0
- | Load |  | Ea | 1 | 15 | 100 |  | 150 | 265 |  | 15 | 100 |  | 150 | 265 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
O3 | Heavy Mobile Equipment | 323 | Ea | 13 | 120 | 1300 |  | 1200 | 2620 | 846260 | 120 | 1300 |  | 1200 | 2620 | 846260 | 0 | 0
- | Disassembly |  | Ea | 5 | 75 | 500 |  | 750 | 1325 |  | 75 | 500 |  | 750 | 1325 |  | 0
- | Decontaminate |  | Ea | 5 |  | 500 |  | 0 | 500 |  |  | 500 |  | 0 | 500 |  | 0
- | Load |  | Ea | 1 | 15 | 100 |  | 150 | 265 |  | 15 | 100 |  | 150 | 265 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
MT1 | Light Tanks | 21 | Ea | 9.6667 | 107.5 | 966.6667 |  | 1075 | 2149.1667 | 45132.5 | 107.5 | 966.6667 |  | 1075 | 2149.1667 | 45132.5 | 0 | 0
- | Remove from foundations |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Empty tank |  | Ea | 0.5 | 7.5 | 50 |  | 75 | 132.5 |  | 7.5 | 50 |  | 75 | 132.5 |  | 0
- | Decontaminate |  | Ea | 2.5 |  | 250 |  | 0 | 250 |  |  | 250 |  | 0 | 250 |  | 0
- | Load |  | Ea | 4 | 60 | 400 |  | 600 | 1060 |  | 60 | 400 |  | 600 | 1060 |  | 0
- | Transport |  | Ea | 0.66667 | 10 | 66.6667 |  | 100 | 176.6667 |  | 10 | 66.6667 |  | 100 | 176.6667 |  | 0
MT2 | Medium Tanks | 26 | Ea | 31 | 390 | 3100 |  | 3900 | 7390 | 192140 | 390 | 3100 |  | 3900 | 7390 | 192140 | 0 | 0
- | Disassembly |  | Ea | 16 | 240 | 1600 |  | 2400 | 4240 |  | 240 | 1600 |  | 2400 | 4240 |  | 0
- | Decontaminate |  | Ea | 5 |  | 500 |  | 0 | 500 |  |  | 500 |  | 0 | 500 |  | 0
- | Empty tank |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Load |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
MT3 | Large Tanks | 0 | Ea | 269 | 2910 | 26900 |  | 29100 | 58910 | 0 | 2910 | 26900 |  | 29100 | 58910 | 0 | 0 | 0
- | Disassembly |  | Ea | 150 | 2250 | 15000 |  | 22500 | 39750 |  | 2250 | 15000 |  | 22500 | 39750 |  | 0
- | Decontaminate |  | Ea | 75 |  | 7500 |  | 0 | 7500 |  |  | 7500 |  | 0 | 7500 |  | 0
- | Empty tank |  | Ea | 4 | 60 | 400 |  | 600 | 1060 |  | 60 | 400 |  | 600 | 1060 |  | 0
- | Load |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
- | Transport |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
MT1-d | Light Diesel (Day tanks 10,000L to 20,000L) | 12 | Ea | 15.5 | 195 | 1550 |  | 1950 | 3695 | 44340 | 195 | 1550 |  | 1950 | 3695 | 44340 | 0 | 0
- | Remove from foundations |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Empty tank and Collect Diesel |  | Ea | 4 | 60 | 400 |  | 600 | 1060 |  | 60 | 400 |  | 600 | 1060 |  | 0
- | Decontaminate |  | Ea | 2.5 |  | 250 |  | 0 | 250 |  |  | 250 |  | 0 | 250 |  | 0
- | Load |  | Ea | 5 | 75 | 500 |  | 750 | 1325 |  | 75 | 500 |  | 750 | 1325 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
MT5-d | Medium Mobile Diesel Tanks (3000 L to 500k L) | 4 | Ea | 42.725 | 564.75 | 4272.5 |  | 5647.5 | 10484.75 | 41939 | 564.75 | 4272.5 |  | 5647.5 | 10484.75 | 41939 | 0 | 0
- | Disassembly |  | Ea | 14 | 210 | 1400 |  | 2100 | 3710 |  | 210 | 1400 |  | 2100 | 3710 |  | 0
- | Empty tank and Collect Diesel |  | Ea | 9.65 | 144.75 | 965 |  | 1447.5 | 2557.25 |  | 144.75 | 965 |  | 1447.5 | 2557.25 |  | 0
- | Decontaminate |  | Ea | 5.075 |  | 507.5 |  | 0 | 507.5 |  |  | 507.5 |  | 0 | 507.5 |  | 0
- | Load |  | Ea | 8 | 120 | 800 |  | 1200 | 2120 |  | 120 | 800 |  | 1200 | 2120 |  | 0
- | Transport |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
MT2-d | Medium Diesel Tanks (500k L to 750k L) | 8 | Ea | 65.79 | 872.1 | 6579 |  | 8721 | 16172.1 | 129376.8 | 872.1 | 6579 |  | 8721 | 16172.1 | 129376.8 | 0 | 0
- | Disassembly |  | Ea | 24.48 | 367.2 | 2448 |  | 3672 | 6487.2 |  | 367.2 | 2448 |  | 3672 | 6487.2 |  | 0
- | Empty tank and Collect Diesel |  | Ea | 15.3 | 229.5 | 1530 |  | 2295 | 4054.5 |  | 229.5 | 1530 |  | 2295 | 4054.5 |  | 0
- | Decontaminate |  | Ea | 7.65 |  | 765 |  | 0 | 765 |  |  | 765 |  | 0 | 765 |  | 0
- | Load |  | Ea | 12.24 | 183.6 | 1224 |  | 1836 | 3243.6 |  | 183.6 | 1224 |  | 1836 | 3243.6 |  | 0
- | Transport |  | Ea | 6.12 | 91.8 | 612 |  | 918 | 1621.8 |  | 91.8 | 612 |  | 918 | 1621.8 |  | 0
MT3-d | Large Diesel Tanks Load and Transport (5M L) | 2 | Ea | 418.6 | 5865 | 41860 |  | 58650 | 106375 | 212750 | 5865 | 41860 |  | 58650 | 106375 | 212750 | 0 | 0
- | Disassembly |  | Ea | 220.8 | 3312 | 22080 |  | 33120 | 58512 |  | 3312 | 22080 |  | 33120 | 58512 |  | 0
- | Decontaminate |  | Ea | 27.6 |  | 2760 |  | 0 | 2760 |  |  | 2760 |  | 0 | 2760 |  | 0
- | Empty tank and Collect Diesel |  | Ea | 115 | 1725 | 11500 |  | 17250 | 30475 |  | 1725 | 11500 |  | 17250 | 30475 |  | 0
- | Load |  | Ea | 27.6 | 414 | 2760 |  | 4140 | 7314 |  | 414 | 2760 |  | 4140 | 7314 |  | 0
- | Transport |  | Ea | 27.6 | 414 | 2760 |  | 4140 | 7314 |  | 414 | 2760 |  | 4140 | 7314 |  | 0
MT4-d | Largest Diesel Tanks (10M L to 12M L) | 4 | Ea | 679.4 | 9417 | 67940 |  | 94170 | 171527 | 686108 | 9417 | 67940 |  | 94170 | 171527 | 686108 | 0 | 0
- | Disassembly |  | Ea | 322.5 | 4837.5 | 32250 |  | 48375 | 85462.5 |  | 4837.5 | 32250 |  | 48375 | 85462.5 |  | 0
- | Decontaminate |  | Ea | 51.6 |  | 5160 |  | 0 | 5160 |  |  | 5160 |  | 0 | 5160 |  | 0
- | Empty tank and Collect Diesel |  | Ea | 215 | 3225 | 21500 |  | 32250 | 56975 |  | 3225 | 21500 |  | 32250 | 56975 |  | 0
- | Load |  | Ea | 51.6 | 774 | 5160 |  | 7740 | 13674 |  | 774 | 5160 |  | 7740 | 13674 |  | 0
- | Transport |  | Ea | 38.7 | 580.5 | 3870 |  | 5805 | 10255.5 |  | 580.5 | 3870 |  | 5805 | 10255.5 |  | 0
25ka | Allowance - For Temporary construction warehouses and offices | 2 | Lot | 94.3396 | 1415.0943 | 9433.9623 |  | 14150.9434 | 25000 | 50000 | 1415.0943 | 9433.9623 |  | 14150.9434 | 25000 | 50000 | 0 | 0
FF1 | Modular Building Not Contaminated (480 ft2) | 14321.5962 | m2 | 0.22417 | 3.3625 | 22.4167 |  | 33.625 | 59.4042 | 850762.4853 | 3.3625 | 22.4167 |  | 33.625 | 59.4042 | 850762.4853 | 0 | 0
- | Empty and remove or secure items |  | Ea | 3 | 45 | 300 |  | 450 | 795 |  | 45 | 300 |  | 450 | 795 |  | 0
- | Decontaminate |  | Ea |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
- | Load |  | Ea | 5 | 75 | 500 |  | 750 | 1325 |  | 75 | 500 |  | 750 | 1325 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF1-c | Modular Building Contaminated (480 ft2) | 3464.8699 | m2 | 0.56042 | 3.3625 | 56.0417 |  | 84.0625 | 143.4667 | 497093.3333 | 3.3625 | 56.0417 |  | 84.0625 | 143.4667 | 497093.3333 | 0 | 0
- | Empty and remove or secure items |  | Ea | 3 | 45 | 300 |  | 450 | 795 |  | 45 | 300 |  | 450 | 795 |  | 0
- | Decontaminate |  | Ea | 15 |  | 1500 |  | 2250 | 3750 |  |  | 1500 |  | 2250 | 3750 |  | 0
- | Load |  | Ea | 5 | 75 | 500 |  | 750 | 1325 |  | 75 | 500 |  | 750 | 1325 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF2 | Fold Away Building Not Contaminated (480 ft2) | 2157.7844 | m2 | 0.15692 | 2.3537 | 15.6917 |  | 23.5375 | 41.5829 | 89726.9683 | 2.3537 | 15.6917 |  | 23.5375 | 41.5829 | 89726.9683 | 0 | 0
- | Empty and remove or secure items |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Disassembly |  | Ea | 3 | 45 | 300 |  | 450 | 795 |  | 45 | 300 |  | 450 | 795 |  | 0
- | Decontaminate |  | Ea |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF2-c | Fold Away Building Contaminated (480 ft2) | 14103.7486 | m2 | 0.56042 | 2.3537 | 56.0417 |  | 84.0625 | 142.4579 | 2009190.6356 | 2.3537 | 56.0417 |  | 84.0625 | 142.4579 | 2009190.6356 | 0 | 0
- | Empty and remove or secure items |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Disassembly |  | Ea | 3 | 45 | 300 |  | 450 | 795 |  | 45 | 300 |  | 450 | 795 |  | 0
- | Decontaminate |  | Ea | 18 |  | 1800 |  | 2700 | 4500 |  |  | 1800 |  | 2700 | 4500 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF3 | Soft Walled Building (tent) Not Contaminated (480 ft2) | 14759.48 | m2 | 0.17933 | 2.69 | 17.9333 |  | 26.9 | 47.5233 | 701419.6879 | 2.69 | 17.9333 |  | 26.9 | 47.5233 | 701419.6879 | 0 | 0
- | Disassembly |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Empty and remove or secure items |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Decontaminate |  | Ea |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF3-c | Soft Walled Building (tent) Contaminated (480 ft2) | 2130.5248 | m2 | 0.58283 | 2.69 | 58.2833 |  | 87.425 | 148.3983 | 316166.3294 | 2.69 | 58.2833 |  | 87.425 | 148.3983 | 316166.3294 | 0 | 0
- | Disassembly |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Empty and remove or secure items |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Decontaminate |  | Ea | 18 |  | 1800 |  | 2700 | 4500 |  |  | 1800 |  | 2700 | 4500 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FF4 | ISO Container | 267.658 | m2 | 0.11208 | 1.6812 | 11.2083 |  | 16.8125 | 29.7021 | 7950 | 1.6812 | 11.2083 |  | 16.8125 | 29.7021 | 7950 | 0 | 0
- | Empty and remove or secure items |  | Ea | 1 | 15 | 100 |  | 150 | 265 |  | 15 | 100 |  | 150 | 265 |  | 0
- | Decontaminate |  | Ea |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0
- | Load |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
FW | Timber Cribbing (480 ft2) | 1892.9368 | m2 | 0.12329 | 1.1769 | 7.8458 |  | 11.7688 | 20.7915 | 39356.9167 | 1.1769 | 7.8458 |  | 11.7688 | 20.7915 | 39356.9167 | 0 | 0
- | Disassembly |  | Ea | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Decontaminate |  | Ea | 2 | [12 empty] | 0
- | Load |  | Ea | 1 | 15 | 100 |  | 150 | 265 |  | 15 | 100 |  | 150 | 265 |  | 0
- | Transport |  | Ea | 0.5 | 7.5 | 50 |  | 75 | 132.5 |  | 7.5 | 50 |  | 75 | 132.5 |  | 0
CP | Precast Concrete Foundations - (480 ft2) | 12481.6654 | m2 | 0.14521 | 2.1781 | 14.5206 |  | 21.7809 | 38.4797 | 480290.4102 | 2.1781 | 14.5206 |  | 21.7809 | 38.4797 | 480290.4102 | 0 | 0
- | Demo (not required) |  | m3 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
- | Decontaminate |  | m3 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
- | Load |  | m3 | 2 | 30 | 200 |  | 300 | 530 |  | 30 | 200 |  | 300 | 530 |  | 0
- | Transport (assume 10 m3 per load. 4 hour round trip) |  | m3 | 0.2 | 3 | 20 |  | 30 | 53 |  | 3 | 20 |  | 30 | 53 |  | 0
CS | Slab on Grade - ASSUME 300mm thick | 18151.4783 | m2 | 0.125 | 1.875 | 12.5 |  | 18.75 | 33.125 | 601267.7184 | 1.875 | 12.5 |  | 18.75 | 33.125 | 601267.7184 | 0 | 0
- | Demo |  | m3 | 0.125 | 1.875 | 12.5 |  | 18.75 | 33.125 |  | 1.875 | 12.5 |  | 18.75 | 33.125 |  | 0
- | Decontaminate |  | m3 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
- | Load |  | m3 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
- | Transport |  | m3 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0
BR | Bridge Removal | 4 | Lot | 761.9048 | 11428.5714 | 76190.4762 |  | 114285.7143 | 201904.7619 | 807619.0476 | 11428.5714 | 76190.4762 |  | 114285.7143 | 201904.7619 | 807619.0476 | 0 | 0
- | Demo |  | Lot | 761.9048 | 11428.5714 | 76190.4762 |  | 114285.7143 | 201904.7619 |  | 11428.5714 | 76190.4762 |  | 114285.7143 | 201904.7619 |  | 0
A10 | Steel Building Teardown | 0 | Ea | 270 | 3450 | 27000 |  | 34500 | 64950 | 0 | 3450 | 27000 |  | 34500 | 64950 | 0 | 0 | 0
- | Disassembly |  | Ea | 160 | 2400 | 16000 |  | 24000 | 42400 |  | 2400 | 16000 |  | 24000 | 42400 |  | 0
- | Decontaminate |  | Ea | 40 |  | 4000 |  | 0 | 4000 |  |  | 4000 |  | 0 | 4000 |  | 0
- | Load |  | Ea | 40 | 600 | 4000 |  | 6000 | 10600 |  | 600 | 4000 |  | 6000 | 10600 |  | 0
- | Transport |  | Ea | 30 | 450 | 3000 |  | 4500 | 7950 |  | 450 | 3000 |  | 4500 | 7950 |  | 0
VP1 | VENDOR PKG - Incenerator | 2 | Lot | 47 | 480 | 4700 |  | 4800 | 9980 | 19960 | 480 | 4700 |  | 4800 | 9980 | 19960 | 0 | 0
- | Disassembly |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
- | Decontaminate |  | Ea | 15 |  | 1500 |  | 0 | 1500 |  |  | 1500 |  | 0 | 1500 |  | 0
- | Load |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
- | Transport |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
VP2 | VENDOR PKG - Potable Water | 2 | Lot | 47 | 480 | 4700 |  | 4800 | 9980 | 19960 | 480 | 4700 |  | 4800 | 9980 | 19960 | 0 | 0
- | Disassembly |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
- | Decontaminate |  | Ea | 15 |  | 1500 |  | 0 | 1500 |  |  | 1500 |  | 0 | 1500 |  | 0
- | Load |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
- | Transport |  | Ea | 6 | 90 | 600 |  | 900 | 1590 |  | 90 | 600 |  | 900 | 1590 |  | 0
VP3 | VENDOR PKG - Sewage Treatment Plant | 2 | Lot | 51 | 540 | 5100 |  | 5400 | 11040 | 22080 | 540 | 5100 |  | 5400 | 11040 | 22080 | 0 | 0
- | Disassembly |  | Ea | 20 | 300 | 2000 |  | 3000 | 5300 |  | 300 | 2000 |  | 3000 | 5300 |  | 0
- | Decontaminate |  | Ea | 15 |  | 1500 |  | 0 | 1500 |  |  | 1500 |  | 0 | 1500 |  | 0
- | Load |  | Ea | 8 | 120 | 800 |  | 1200 | 2120 |  | 120 | 800 |  | 1200 | 2120 |  | 0
- | Transport |  | Ea | 8 | 120 | 800 |  | 1200 | 2120 |  | 120 | 800 |  | 1200 | 2120 |  | 0
VP5 | VENDOR PKG - Truck wash Facility | 0 | Lot | 300 | 4500 | 30000 |  | 45000 | 79500 | 0 | 4500 | 30000 |  | 45000 | 79500 | 0 | 0 | 0
- | 30% of Install Hrs |  | Ea | 300 | 4500 | 30000 |  | 45000 | 79500 |  | 4500 | 30000 |  | 45000 | 79500 |  | 0
VP6 | VENDOR PKG - Ship Loader | 0 | Lot | 14448 | 216720 | 1444800 |  | 2167200 | 3828720 | 0 | 216720 | 1444800 |  | 2167200 | 3828720 | 0 | 0 | 0
- | Assume Crew of 20 for 4 Months |  | Ea | 14448 | 216720 | 1444800 |  | 2167200 | 3828720 |  | 216720 | 1444800 |  | 2167200 | 3828720 |  | 0
CV | Reclaim Conveyor | 1.1667 | ea | 5018.4 | 75276 | 501840 |  | 752760 | 1329876 | 1551522 | 75276 | 501840 |  | 752760 | 1329876 | 1551522 | 0 | 0
- | Load, Haul and Dispose (30% of Install Hrs) |  | ea | 5018.4 | 75276 | 501840 |  | 752760 | 1329876 |  | 75276 | 501840 |  | 752760 | 1329876 |  | 0
EG | Gravel Base Removal | 21385.7084 | m3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- | Load, Haul and Dispose |  | m3 | [13 empty] | 0
Piping | Piping | 19623 | m | 0.25 | 3.75 | 25 |  | 37.5 | 66.25 | 1300023.75 | 3.75 | 25 |  | 37.5 | 66.25 | 1300023.75 | 0 | 0
- | Disasemble, Load, Haul and Dispose |  | m | 0.25 | 3.75 | 25 |  | 37.5 | 66.25 |  | 3.75 | 25 |  | 37.5 | 66.25 |  | 0
cable | Cable | 34300 | m | 0.1 | 1.5 | 10 |  | 15 | 26.5 | 908950 | 1.5 | 10 |  | 15 | 26.5 | 908950 | 0 | 0
- | Load, Haul and Dispose |  | m | 0.1 | 1.5 | 10 |  | 15 | 26.5 |  | 1.5 | 10 |  | 15 | 26.5 |  | 0
Misc | Miscellanous Items (Minor) | 0 | ea | 2 | 30 | 200 |  | 300 | 530 | 0 | 30 | 200 |  | 300 | 530 | 0 | 0 | 0
- | Load, Haul and Dispose |  | ea | 4 | 60 | 400 |  | 600 | 1060 |  | 60 | 400 |  | 600 | 1060 |  | 0
A12 | Application of insulation material | 0 | m2 | 0.05 | 0.3 | 5 | 5 | 3 | 13.3 | 0 | 0.3 | 5 | 5 | 3 | 13.3 | 0 | 0 | 0
- | HDPE liner |  | m2 | 0.05 | 0.3 | 5 | 5 | 3 | 13.3 |  | 0.3 | 5 | 5 | 3 | 13.3 |  | 0
ARS | Airstrip Lighting and Removal | 0 | m | 0.1 | 1.5 | 10 |  | 15 | 26.5 | 0 | 1.5 | 10 |  | 15 | 26.5 | 0 | 0 | 0
- | Load, Haul and Dispose |  | m | 0.1 | 1.5 | 10 |  | 15 | 26.5 |  | 1.5 | 10 |  | 15 | 26.5 |  | 0
CON | Consumables | 599 | bed space |  | 700.8009 |  |  |  | 700.8009 | 419779.7445 | 700.8009 |  |  |  | 700.8009 | 419779.7445 | 0 | 0
- | Remove Consumables (Disassembly (if required), load, transport) |  | ea |  | 67.1982 |  |  |  | 67.1982 |  | 67.1982 |  |  |  | 67.1982 |  | 0
- | Fill Application |  | ea |  | 577.9927 |  |  |  | 577.9927 |  | 577.9927 |  |  |  | 577.9927 |  | 0
- | Mobilization/demobilization of workers |  | ea |  | 14.87 |  |  |  | 14.87 |  | 14.87 |  |  |  | 14.87 |  | 0
- | Worker accommodation and camp operation |  | ea |  | 40.74 |  |  |  | 40.74 |  | 40.74 |  |  |  | 40.74 |  | 0
TOTAL DIRECT COST | [9 empty] | 23386167.2734 | [5 empty] | 23386167.2734 |  | 0
Earthworks Unit Rates
Project Constants
[7 empty] | Code | Description | Variable
Unit Rate For: 7ea001 - Drill & Blast - 12m x 12m x 15 m deep | [6 empty] | zz | Fuel Cost | 0.966 | [$/L]
[7 empty] | y | Years to write down Equipment | 3 | [yr]
[7 empty] | x | Continuous work hours per year | 4320 | [hr/yr] = 30 days * 12 months *12 hrs / day
| Code | Description | Quantity | Unit |  |  | w | Write Down % over period | 85%
Variables | [6 empty] | b | Pentax Boost | 10.48
| a | Crew Shift Duration | 12 | [hr] |  |  | d | Detonator | 15
| b | Drill Count per footprint area | 12 | [m2] |  |  | c | Cordex | 0.89 | [$/m]
| c | Drill hold depth | 15 | [m] |  |  | e | ANFO | 650 | [$/mt]
| d | Footprint | 144 | [m2] |  |  |  | Labour Rate | 100
| e | Efficiency | 1
| f | Drilled-Blasted Volume per 12 hour day w/ 1 crew | 2160 | [m3/day] = d * c |  |  |  | 8ehydril - Rock Drill
| g | Hole Density | 180 | =d*c / b |  |  |  | Variables - z
Production |  |  |  |  | #REF! |  |  | Fuel Usage | 35 | [L/hr]
| h | Productivity | 2160 | [m3/day] = f * e
| i | Hourly Production | 150 | [m3/hr] |  |  |  | Equipment Cost - v
| j | Crew Members | 4 |  |  |  |  | Rock Drill Purchase | 375000 | 50% of Purchase
| k | Earthwork Productivity Factor | 1.33
| l | Labour Rate | 100 | [$/hr] |  |  |  | Hourly Cost
| m | Rock Drill | 152.8449 |  |  |  |  | Rock Drill Purchase per hour | 24.5949 | [$/hr] = v / y/ x*w
| n | Blasting Materials per hole | 313.36 |  |  |  |  | Rock Drill Operating Cost | 94.44 | [$/hr]
Labour & Equipment | [7 empty] | Fuel | 33.81 | [$/hr] = z * zz
|  | All in Labour Rate Earthworks | 3.5467 | = l / i * (j*k) |  |  |  | Subtotal
Plant Equipment | [7 empty] | Rock Drill Composite | 152.8449 | [$/hr]
| 8ehydril | Rock Drill Composite | 1.019 | = m/i
Materials | [7 empty] | 8exm001 - Blasting Material
| 8exm001 | Blasting Material Complex | 1.7409 | = n/i |  |  |  | Variables -
| eamnfoo | Blasting Mats | 0.8 |  |  |  |  | Pentax Booster | 2 | [BOOST] = [ea]
| exadrilx | SANVIK DX800 drill-bits & Consumables | 0.95 |  |  |  |  | Detonator | 2 | [DET] = [ea]
Subtotal: |  | Unit Rate / m3 | 8.0565 |  |  |  |  | Cordex | 10 | [CORD] = [m]
|  | Labour / m3 | 3.5467 |  |  |  |  | ANFO | 0.39 | [EMUL] =[mt/hole]
|  | Equipment / m3 | 4.5099
|  | Fuel Usage / m3 | 0.23333 | =Fuel per hour / Production per hour |  |  |  | Cost
|  | Labour Hours / m3 | 0.038615 |  |  |  |  | Pentax Booster | 20.96 | = b * [Boost]
[8 empty] | Detonator | 30 | = d * [DET]
[8 empty] | Cordex | 8.9 | = c * [CORD]
Unit Rate For: 7eq002 - Agregate Crushing, 2-25mm | [7 empty] | ANFO | 253.5 | = e * [EMUL]
Subtotal
[8 empty] | Blasting Material Composite | 313.36 | [$/hole]
8emcrush - Mobile Crushing Plant
| Code | Description | Quantity | Unit |  |  |  | Variables - z
Variables | [7 empty] | Fuel Usage | 13 | [L/hr]
| a | Crew shift Duration | 12 | [hr]
| b | Productivity Factor | 0.77 |  |  |  |  | Equipment Cost - v
| c | Optimal Production | 150 | [m3/hr] |  |  |  | Mobile Crushing Plant Purchase | 2500000 | 50% of Purchase
Production
| d | Production per hour | 115.5 | [m3/hr] |  |  |  | Hourly Cost
| e | Production per day | 1386 | [m3/day] |  |  |  | Crushing Plant Purchase per hour | 163.966 | [$/hr] = v / y/ x*w
| f | Labour Rate | 100 | [$/hr] |  |  |  | Crushing Plant Operating Cost | 125 | [$/hr]
| g | Earthwork Productivity Factor | 1.33 |  |  |  |  | Fuel | 12.558 | [$/hr] = z * zz
| h | Operators | 4 |  |  |  |  | Subtotal
| i | FEL Operators | 1 |  |  |  |  | Mobile Crushing Plant Composite | 301.524 | [$/hr]
| j | Mobile Crushing Plant | 301.524
| k | CAT 980 FEL | 81.3602 |  |  |  |  | 8e980 - CAT 980 FEL
Cost - Labour & Equipment | [7 empty] | Variables - z
|  | All in Labour Rate - Earthworks | 4.6061 | = f * i* g / d |  |  |  | Fuel Usage | 35 | [L/hr]
| FEL | All in Labour Rate - Earthworks | 1.1515 | = f * h * g / d
| 8emcrush | Mobile Crushing Plant Composite | 5.2212 | =Crushing Plant Cost x 2 plants/d |  |  |  | Equipment Cost - v
| 8e980 | CAT 980 FEL Composite | 0.70442 | = CAT Cost /d |  |  |  | CAT 980 FEL Purchase | 243194 | 50% of Purchase
Subtotal: |  | Unit Rate / m3 | 11.6832
|  | Labour / m3 | 5.7576 |  |  |  |  | Hourly Cost
|  | Equipment / m3 | 5.9256 |  |  |  |  | CAT Purchase per hour | 15.9502 | [$/hr] = v / y/ x*w
|  | Fuel Usage / m3 | 0.41558 | =Fuel per hour / Production per hour |  |  |  | CAT Operating Cost | 31.6 | [$/hr]
|  | Labour Hours / m3 | 0.064355 |  |  |  |  | Fuel | 33.81 | [$/hr] = z * zz
Subtotal
[8 empty] | CAT 980 FEL Composite | 81.3602 | [$/hr]
Unit Rate For: 7ep001na Excavate, Load & Haul 2km
1. Excavate Gravel
2. Load
3. Haul
| Code | Description | Quantity | Unit |  |  |  | 8eex85 - CAT 385 Excavator
Variables | [7 empty] | Variables - z
| a | Haul Distance | 2 | [km] |  |  |  | Fuel Usage | 30 | [L/hr]
| b | Speed | 26 | [km/hr]
| c | Swell | 1.15 | [factor %] |  |  |  | Equipment Cost - v
Production | [7 empty] | CAT 385 Excavator Purchase | 572500 | 50% of Purchase
| d | Shift | 12 | [hr]
| e | Haul Truck Capacity | 43.5 | [mt] |  |  |  | Hourly Cost
| f | Density | 1.8 | [mt/m3] |  |  |  | CAT Purchase per hour | 37.5482 | [$/hr] = v / y/ x*w
| g | Haul Volume | 21.0145 | [m3] = e / f /c |  |  |  | CAT Operating Cost | 95 | [$/hr]
| h | Loud, Wait and Unload time per cycle | 8 | [min] |  |  |  | Fuel | 28.98 | [$/hr] = z * zz
| i | Cycle Delay Factor | 1 |  |  |  |  | Subtotal
| j | Cycle Time | 17.2308 | [min] = a/b*60+h*i |  |  |  | CAT 7385 Excavator Composite | 161.5282 | [$/hr]
| k | Production Rate | 73.1755 | [m3/cycle] = g * 60/j
| l | Efficiency | 0.77
| m | Truck Count | 1.54 | = 2 * k |  |  |  | 8edum40 - CAT 740 Haul Truck
| n | Production | 112.6902 | [m3/hour] = j * k |  |  |  | Variables - z
| o | Earthwork PF Factor | 1.3 | Factor |  |  |  | Fuel Usage | 30 | [L/hr]
| p | All in Labour Rate - Earthworks | 100 | $ / Hour
| q | CAT 385 Excavator | 161.5282 |  |  |  |  | Equipment Cost - v
| r | CAT 740 Haul Truck | 135.7642 |  |  |  |  | CAT 740 Hault Truck Purchase | 425000 | 50% of Purchase
Cost - Excavate & Load
|  | Labour | 1.1536 | =(n*m)/n
| 8eex85 | CAT 385 Excavator Composite | 1.4334 | = q / n |  |  |  | Hourly Cost
Cost - Haul & Dump | [7 empty] | CAT Purchase per hour | 27.8742 | [$/hr] = v / y/ x*w
|  | Labour | 1.7766 | = (n*m)/l*k |  |  |  | CAT Operating Cost | 78.91 | [$/hr]
| 8edum40 | CAT 740 Haul Truck Composite | 1.8553 | = r / l*k |  |  |  | Fuel | 28.98 | [$/hr] = z * zz
Subtotal: |  | Unit Rate / m3 | 6.2189 |  |  |  |  | Subtotal
|  | Labour / m3 | 2.9302 |  |  |  |  | CAT 740 Haul Truck Composite | 135.7642 | [$/hr]
|  | Equipment / m3 | 3.2887
|  | Fuel Usage / m3 | 0.40997 | =Fuel per hour / Production per hour
|  | Labour Hours / m3 | 0.034693 |  |  |  |  | 8ed08t - CAT D8T Dozer
Variables - z
A3 |  | Grade and Re-Contour | [5 empty] | Fuel Usage | 30 | [L/hr]
Unit Rate For: 7eq011 - Backfill & Compact w/D8
Equipment Cost - v
[8 empty] | CAT D8T Dozer Purchase | 324955 | 50% of Purchase
| Code | Description | Quantity | Unit
Variables | [7 empty] | Hourly Cost
| a | Crew shift Duration | 12 | [hr] |  |  |  | CAT Purchase per hour | 21.3126 | [$/hr] = v / y/ x*w
| b | Haul Truck Capacity | 40 | [mt] |  |  |  | CAT Operating Cost | 61.05 | [$/hr]
| c | Density | 2.1 | [mt/m3] |  |  |  | Fuel | 28.98 | [$/hr] = z * zz
| d | Haul Volume | 19.0476 | [m3] |  |  |  | Subtotal
| e | Truck Loads per hour | 7 |  |  |  |  | CAT D8T Dozer Composite | 111.3426 | [$/hr]
| f | Efficiency | 0.76923
Production
| g | Production per hour | 102.5641 | [m3/hr]
| h | Compaction Rate per hour | 230.7692 | [m3/hr]
| i | Earthwork Productivity Factor | 1.3
| j | All in Labour Rate - Earthworks | 100 | [$/hr]
| k | CAT D8T Dozer | 111.3426
Cost - Labour & Equipment
|  | All in Labour Rate - Earthworks | 1.2675 | = i* j / g
|  | All in Labour Rate - Earthworks | 1.2675 | = i* j / g
| 8ed08t | CAT D8T Dozer Composite | 1.0856 | =k /d
Subtotal: |  | Unit Rate | 3.6206
|  | Labour / m3 | 2.535
|  | Equipment / m3 | 1.0856 | 0.79309
|  | Fuel Usage | 0.2925
|  | Labour Hours | 0.02538 |  | 2.538
A2 |  | Fill Aplication | Hatch |  |  | 29.5861
Total |  | Unit Rate | 29.5792 |  |  | 14.7694
|  | Labour / m3 | 14.7694 |  |  | 14.8167
|  | Equipment / m3 | 14.8098 |  |  | 1.3514
|  | Fuel Usage | 1.3514 |  |  | 0.16304
|  | Labour Hours | 0.16304

## Indirect cost Analysis (hidden)
Work Plan | 2014 | 2015 | 2015 A | 2015 R | 2016 | 2017 | TOTAL - BASE CASE | TOTAL - SCENARIO 1
DIRECT COST SUB-TOTAL | 15248190.3478 | 758350.4942 | 354255.9995 | 5130684.0485 | 584402.892 | 1174709.1043 | 23250592.8862 | 23386167.2734
TOTAL MAN-HOURS | 72848.7883 | 5551.8693 | 2080.9651 | 29587.1665 | 3463.7663 | 4806.1787 | 118338.7343 | 163828.6802
TOTAL MAN-DAYS (Assuming 10 h day) | 7284.8788 | 555.1869 | 208.0965 | 2958.7167 | 346.3766 | 480.6179 | 11833.8734 | 16382.868
Southern Hires (70%) | 5100 | 389 | 146 | 2072 | 243 | 337 | 8287 | 11474
Northern Hires (30%) | 2186 | 167 | 63 | 888 | 104 | 145 | 3553 | 4920
Mobilzation (% of direct Cost) | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
Engineering (% of direct Cost) | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9%
Project supervision, management & contract administration (% of direct cost+Contaminated soil treatement+post closure monitoring) | 9.4% | 9.4% | 9.4% | 9.4% | 9.4% | 9.4% | 9.4% | 9.4%
Contingency (of direct cost+Contaminated soil treatement+Mob/demob+Workers accomodation & camps Opp+workers mob/demob+post closure monitoring) | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5%
INDIRECT SUB-TOTAL | 14653200 | 690194.6519 | 155000 | 3141000 | 2888000 | 706000 | 22233394.6519
Off-Site Disposal of Waste & Material | 1969000 | 0 | 0 | 0 | 0 | 0 | 1969000
Fuel | 2889000 | 30000 | 9000 | 209000 | 14000 | 28000 | 3179000
Total Capacity @ site (L) | 51000000 | 100000 | 0 | 0 | 0 | 0 | 51100000
Demob cost per Litre | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
Reclamation Activites | 852215.8556 | 58906.488 | 20684.9565 | 705629.8136 | 31233.7095 | 86136.3373 | 1754807.1605
Heat and Power | 841403.5052 | 64124.09 | 24035.1469 | 341731.7736 | 40006.5004 | 55511.3645 | 1366812.3806
Avg Monthly Consumption | 1732500 | 1732500 | 1732500 | 1732500 | 1732500 | 1732500 | 1732500
Days in month | 30 | 30 | 30 | 30 | 30 | 30 | 30
Average camp population in '14 | 500 | 500 | 500 | 500 | 500 | 500 | 500
L/Man-day | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5
Total fuel reuired during closure | 1693619.3608 | 123030.578 | 44720.1034 | 1047361.5872 | 71240.21 | 141647.7018 | 3121619.5411
Cost to mob. Fuel per Litre | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Demob 50% of total capacity | 2550000 | 5000 | 0 | 0 | 0 | 0 | 2555000
Mob 50% fuel required during closure | 338723.8722 | 24606.1156 | 8944.0207 | 209472.3174 | 14248.042 | 28329.5404 | 624323.9082
Total Mob/Demo Fuel | 2888723.8722 | 29606.1156 | 8944.0207 | 209472.3174 | 14248.042 | 28329.5404 | 3179323.9082
Ammonium Nitrate | 0 | 0 | 0 | 0 | 2537000 | 0 | 2537000
Contaminated Soil Treatment | 234000 | 0 | 0 | 5000 | 0 | 63000 | 302000
Mobilization of Workers Required for Reclamation | 652000 | 46000 | 17000 | 244000 | 29000 | 40000 | 1028000
Passengers per voyage | 77
Productive days per rotation | 20
Person days per Flight | 1540 | 0 | 0 | 0 | 0 | 0
Total Flights Required | 4
Cost per Flight | 118000
TOTAL (Southern Flights) | 472000 | 33240.05 | 12475.7 | 177052.4 | 20764.35 | 28796.65 | 744329.15
Passengers per voyage | 24
Productive days per rotation | 20
Person days per Flight | 480
Total Flights Required | 5
Cost per Flight | 36000
TOTAL (Northern Flights) | 180000 | 12525 | 4725 | 66600 | 7800 | 10875
TOTAL (Both Southern and Northern) | 652000 | 45765.05 | 17200.7 | 243652.4 | 28564.35 | 39671.65
Worker Accommodation & Camp Operation | 1643000 | 125194.6519 | 47000 | 667000 | 78000 | 108000 |  | 2668194.6519
Camp Fuel Consumption | 841403.5052 | 64124.09 | 24035.1469 | 341731.7736 | 40006.5004 | 55511.3645
Cost per/day | 110 | 110 | 110 | 110 | 110 | 110
Fuel consumption per day | 115.5 | 115.5 | 115.5 | 115.5 | 115.5 | 115.5
Accomodation Costs | 801336.6716 | 61070.5619 | 22890.6161 | 325458.832 | 38101.429 | 52867.9662
Camp Op Fuel Costs | 841403.5052 | 64124.09 | 24035.1469 | 341731.7736 | 40006.5004 | 55511.3645
TOTAL | 1642740.1768 | 125194.6519 | 46925.7629 | 667190.6057 | 78107.9294 | 108379.3307
Mobilization and Demobilization of Equipment and Materials by Sealift | 1525000 | 76000 | 35000 | 513000 | 58000 | 117000 |  | 2324000
Geotechnical Inspections | 150000 | 0 | 0 | 0 | 0 | 0 |  | 150000
Cost/hour | 200 | 200 | 200 | 200
Billable hours per inspection | 46 | 46 | 46 | 46
Travel Costs | 4500 | 4500 | 4500 | 4500
Report Costs | 5000 | 5000 | 5000 | 5000
Cost per Inspection | 18700 | 18700 | 18700 | 18700
Total # of Inspections | 8 | 8 | 0 | 0
TOTAL | 149600 | 149600 | 0 | 0
Project Environmental Site Assessment | 90000 | 0 | 0 | 0 | 0 | 0 |  | 90000
Closure & Post Closure Monitoring | 851200 | 0 | 0 | 0 | 0 | 0 |  | 851200
FIELD SAMPLING
Cost/hour | 200 | 200 | 200 | 200 | 200 | 200
Billable hours per inspection | 72 | 72 | 72 | 72 | 72 | 72
Travel Costs | 4500 | 4500 | 4500 | 4500 | 4500 | 4500
Samples | 43 | 43 | 43 | 43 | 43 | 43
Cost/Sample | 100 | 100 | 100 | 100 | 100 | 100
Cost per Inspection | 23200 | 23200 | 23200 | 23200 | 23200 | 23200
Total # of Trips | 16 | 16 | 0 | 0 | 0 | 0
TOTAL FIELD SAMPLING | 371200 | 371200 | 0 | 0 | 0 | 0
ANALYSIS & REPORTING
Cost/hour | 200 | 200 | 200 | 200 | 200 | 200
Billable hours per year | 300 | 300 | 300 | 300 | 300 | 300
Cost per Year | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
# of Years | 8 | 8 | 0 | 0 | 0 | 0
TOTAL | 480000 | 480000 | 0 | 0 | 0 | 0
Short Term C&M, Closure & Post-Closure Monitoring and reporting |  |  |  | 3766032 |  |  |  | 3766032
Engineering Fees | 595000 | 30000 | 14000 | 200000 | 23000 | 46000 |  | 908000
Supervision, Project Management & Contract Administration | 1535000 | 151000 | 33000 | 483000 | 55000 | 116000 |  | 2373000
Contingency | 2520000 | 232000 |  | 820000 | 94000 | 188000 |  | 3854000
TOTAL (DIRECT + INDIRECT) | 29901390.3478 | 1448545.146 | 509255.9995 | 8271684.0485 | 3472402.892 | 1880709.1043
| Distribution between closure requirements |  |  | Comment
INDIRECT SUB-TOTAL | Fuel | Equipment | Labour
Off-Site Disposal of Waste & Material | 70% | 0% | 30% | Waste to be disposed of will depend on the activities to be conducted during closure, which ultimately depends on the ammount of fuel required onsite. Some waste will be generated due to the presence of personnel during closure.
Fuel | 53% |  | 47% | Fuel is dependant on Reclamation Activites and labbour (heat and power for personnel on site).The average breakdown is 53% of the fuel for reclamation activities, and 47% for heat and power
Ammonium Nitrate |  |  |  | No relation to fuel/labour/equipment for reclamation activities.
Contaminated Soil Treatment |  |  |  | No relation to fuel/labour/equipment for reclamation activities
Mobilization of Workers Required for Reclamation |  |  | 100% | Mobilization of workers will depend on the total man-hours required for the reclamaion activities
Worker Accommodation & Camp Operation |  |  | 100% | Mobilization of workers will depend on the total man-hours required for the reclamaion activities
Mobilization and Demobilization of Equipment and Materials by Sealift |  | 100% |  | Mobilization of workers will depend on the total equipment-hours required for the reclamaion activities
Geotechnical Inspections |  |  |  | No relation to fuel/labour/equipment for reclamation activities
Project Environmental Site Assessment |  |  |  | No relation to fuel/labour/equipment for reclamation activities
Closure & Post Closure Monitoring |  |  |  | No relation to fuel/labour/equipment for reclamation activities
Short Term C&M, Closure & Post-Closure Monitoring and reporting |  |  |  | No relation to fuel/labour/equipment for reclamation activities
Engineering Fees |  |  |  | 3.9% of direct Cost equally distributed between labour, equipment and fuel
Supervision, Project Management & Contract Administration |  |  |  | 9.4% of direct Cost equally distributed between labour, equipment and fuel
Contingency |  |  |  | 12.5% of direct Cost equally distributed between labour, equipment and fuel
Percentages to be applied over direct cost - BASE CASE
INDIRECT COST | % over sum of direct cost | Fuel | Equipment | Labour
Off-Site Disposal of Waste & Material | 8.469% | 5.928% | 0% | 2.541%
Fuel | 13.67% | 7.247% | 0% | 6.426%
Ammonium Nitrate | 10.91%
Contaminated Soil Treatment | 1.299%
Mobilization of Workers Required for Reclamation | 4.421% | 0% | 0% | 4.421%
Worker Accommodation & Camp Operation | 11.48% | 0% | 0% | 11.48%
Mobilization and Demobilization of Equipment and Materials by Sealift | 9.995% | 0% | 9.995% | 0%
Geotechnical Inspections | 0.6451%
Project Environmental Site Assessment | 0.3871%
Closure & Post Closure Monitoring | 3.661%
Short Term C&M, Closure & Post-Closure Monitoring and reporting
Engineering Fees | 3.9%
Supervision, Project Management & Contract Administration | 9.4%
Contingency | 12.5%
| Calculatd Indirect Cost - BASE CASE |  |  |  | Calculatd Indirect Cost - SCENARIO 1 |  |  |  | Variance
INDIRECT COST | Fuel | Equipment | Labour | Total | Fuel | Equipment | Labour | Total | Total
Off-Site Disposal of Waste & Material | 1378300 | 0 | 590700 | 1969000 | 1386336.878 | 0 | 594144.3763 | 1980481.2542 | 11481.2542
Fuel | 1684870 | 0 | 1494130 | 3179000 | 1694694.49 | 0 | 1502842.2836 | 3197536.7736 | 18536.7736
Ammonium Nitrate | 0 | 0 | 0 | 2537000 | 0 | 0 | 0 | 2551793.2666 | 14793.2666
Contaminated Soil Treatment | 0 | 0 | 0 | 302000 | 0 | 0 | 0 | 303760.9643 | 1760.9643
Mobilization of Workers Required for Reclamation | 0 | 0 | 1028000 | 1028000 | 0 | 0 | 1033994.276 | 1033994.276 | 5994.276
Worker Accommodation & Camp Operation | 0 | 0 | 2668194.6519 | 2668194.6519 | 0 | 0 | 2683752.9155 | 2683752.9155 | 15558.2637
Mobilization and Demobilization of Equipment and Materials by Sealift | 0 | 2324000 | 0 | 2324000 | 0 | 2337551.262 | 0 | 2337551.262 | 13551.262
Geotechnical Inspections | 0 | 0 | 0 | 150000 | 0 | 0 | 0 | 150874.6512 | 874.6512
Project Environmental Site Assessment | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 90524.7907 | 524.7907
Closure & Post Closure Monitoring | 0 | 0 | 0 | 851200 | 0 | 0 | 0 | 856163.3538 | 4963.3538
Short Term C&M, Closure & Post-Closure Monitoring and reporting | 0 | 0 | 0 | 3766032
Engineering Fees | 0 | 0 | 0 | 908000 | 0 | 0 | 0 | 912060.5237 | 4060.5237
Supervision, Project Management & Contract Administration | 0 | 0 | 0 | 2373000 | 0 | 0 | 0 | 2198299.7237 | -174700.2763
Contingency | 0 | 0 | 0 | 3854000 | 0 | 0 | 0 | 2923270.9092 | -930729.0908
TOTAL INDIRECT |  |  |  | 25999426.6519 |  |  |  | 21220064.6645 | -4779361.9873
TOTAL (DIRECT + INDIRECT) |  |  |  | 49250019.5381 |  |  |  | 44606231.938 | -4643787.6001