## Commitment List
COMMITMENTS FROM TECHNICAL MEETING (Baker Lake, April 28 to April 29, 2017)
(Baker Lake, April 28 to April 29, 2017)
NOTES:
List of acronyms to be provided at a later date
1) Where it is requested that data be provided, it is expected a related discussion will also be included within the submission.
2) Where no timelines are indicated, Agnico Eagle Mines Ltd. (Agnico Eagle) is to provide as per requests of the party putting the commitment forth.
Color Code
Commitment to be completed by party other than Agnico Eagle
Commitment # | Concerned Party | Reference (previous IR or TRC) | Draft Commitment | Timeline | Additional Notes | NIRB/NWB Review Process
DAY 1 and DAY 2
GENERAL
1 | KivIA |  | Agnico Eagle to update the figure as presented on slide 15, presentation i to show an outline of the Whale Tail Pit. Will be provided as figure | Prior to PHC | Complete, submitted to NIRB May 1, 2017 | NIRB
2 | DFO | TRC-9 | Agnico Eagle to adapt its Water Quality and Flow monitoring program to include 2 stations in Whale Tail Lake North Basin during post closure; one in the pit and one in the attenuation pond area. | July 2017 |  | NIRB
3 | KivIA |  | Agnico Eagle commits to referencing only the Whale Tail Project (not Amaruq) in all documents and discussions related to the Whale Tail Project going forward. | N/A
Atmospheric Environment including Climate, Air Quality, Noise and Vibration
4 | ECCC | ECCC-2 | Agnico Eagle commits to work with ECCC to select a feasible location of the active sampling location for particulate matter and emissions at the Whale Tail Pit to monitor for the air quality impacts of the Project and provided in an updated Air Quality and Dustfall Monitoring Plan | July 2017 |  | NIRB
5 | KivIA | KivIA-TC-Air-04 | Agnico Eagle has committed to continue dustfall monitoring along the AWAR and to use the results of this dustfall monitoring to validate the predictions in the FEIS and to include results in the Annual Air Quality Monitoring Report. | Current reporting schedule.
6 | KivIA | KivIA-TC-Air-05 | Agnico Eagle has committed to include adaptive management and mitigation for haul road dust along the Whale Tail Pit and Haul Road as outlined in KivIA-TC-Air-05. | n/a | Prior to construction
7 | KivIA | NEW | Agnico Eagle commits to use the dustfall monitoring stations on the Vault Pit Haul Road to validate and improve modelling of the Whale Tail haul road dust and provide results in the form of a technical memo. | July 2017
Terrestrial Environment
8 | KivIA (GN)+B34 | GN-6 / KivIA-TC-Terrestrial-06 | Agnico Eagle commits to conduct analyses to determine the potential extent of the caribou zone of influence (abundance and distribution) around the existing Meadowbank mine, vault pit and haul road and the AWAR in the form of technical memo. | July 2017 | Analysis to be completed following receipt of data from the Government of Nunavut (GN) as per the Memorandum of Understanding. Following review of data received from the GN, the Proponent will consult with the GN and KivIA regarding appropriate methods of analysis | NIRB
9 | GN | GN-16 and17 | Agnico Eagle commits to conducting supplementary analyses of collar data by herd and season to characterize the rates and duration of caribou encounters as well as conduct a cumulative effects analysis that includes all Project features. | July 2017 | The study area for these analyses will be a 14 km radius around all Project sites including the Whale Tail pit and haul road, the Meadowbank mine and AWAR, the Vault Pit and haul road. Calculated metrics will include the proportion of collared individuals that enter the study area and the duration of their residency within this area. Includes the Meadowbank mine, AWAR, Vault pit and Vault haul road.
10 | GN / KivIA | GN-6 / KivIA-TC-Terrestrial-02 | Agnico Eagle commits to updating the caribou cumulative effects assessment (in the form of a technical memo) to include analysis of the rates and duration of caribou encounters with the Whale Tail Project and other past, present and reasonably forseeable projects within the spring and fall migration corriders of herds. | July 2017 | Metrics for encounter rates and duration of encounter. For the purpose of calculating these metrics a zone-of-influence will be delineated around each project included in the cumulative effects analysis. | NIRB
11 | KivIA/GN |  | Agnico Eagle commits to provide the next iteration of the draft-Terrestrial Ecosystem Management Plan (TEMP) to workshop participants (KivIA, HTO, GN) in May, with a final TEMP to be completed and submitted after the workshop, to be held in June. The next TEMP will take into account recommendations made by the GN and KivIA in technical comments | July 2017 |  | NIRB
12 | GN |  | Agnico Eagle commits to work with the GN to revise caribou group size thresholds for triggering adaptive management for inclusion in the TEMP. | July 2017 |  | NIRB
13 | GN |  | Agnico Eagle commits to provide the GN with data for the Meadowbank AWAR to facilitate the analysis of road effects on caribou movements. | 2017-05-05 | Requested data are listed in GN IR-8 | NIRB
14 | ECCC | ECCC-6 | Agnico Eagle commits to continue to monitor upland breeding birds as part of the bird monitoring program at the Tailings Storage Faculty. | Current reporting schedule. |  | NIRB
15 | ECCC | ECCC-6 | Agnico Eagle commits to add semipalmated sandpipers as a wildlife receptor as part of the Wildlife Screening Level Risk Assessment. | Current reporting schedule.
16 | ECCC | ECCC-6 | Agnico Eagle commits to have the Wildlife Screening Level Risk Assessment Plan include risk assessments for potential ingestion of water/sediment at the tailings storage facility for all wildlife receptors of concern. | Current reporting schedule.
17 | ECCC | ECCC-10 | Agnico Eagle commits to provide in the next iteration of the TEMP an appendix that will describe mitigation and monitoring to reduce impacts to migratory bird nests during flooding | July 2017
18 | KivIA | KivA-TC-Terrestrial-04 | Agnico Eagle commits to establish a Terrestrial Advisory Group ("TAG") which will act as an advisory group related to management, monitoring and mitigation measures for the protection of the terrestrial environment but will not duplicate regulatory authority by appropriate government agencies and departments. The TAG should address the terrestrial environment for all aspects of the Whale Tail project, including the All Weather Access Road (AWAR) and the Meadowbank mine site. Membership in the TAG should include Agnico Eagle, GN, ECCC, KivIA, and the Qamani'tuaq HTO. | Draft Terms of Reference should be provided to NIRB within six (6) months of issuance of the project certificate.
19 | KivIA | KivA-TC-Terrestrial-01 | GN commits to ensure an analysis is completed (currently being conducted by the GN) of caribou collar data to determine the extent of deflection or change in movements and crossing timing or rates for the existing All Weather Access Road (AWAR). | July 2017 | Commitment for the GN not AEM
20 | KivIA | KivA-TC-Terrestrial-03 | Agnico Eagle commits to providing a revised Terrestrial Ecosystem Management Plan (TEMP) to workshop participants, which shall include but not be limited to the following: a. Details of the methods and rationale for monitoring at intermediate to near distances (<5 km) from the mine infrastructure; b. Details of clear and effective monitoring thresholds/triggers for intensifying mitigation and management to reduce/eliminate potential sensory disturbance to caribou; and c. Clarity methods of mitigation. | Revised draft TEMP by mid-May; workshop to follow in late June; final draft TEMP in July 2017
21 | KivIA | New | Agnico Eagle commits to report annually on its terrestrial environment monitoring program. Agnico Eagle commits to developing an agreed terms of reference for the TAG that will consider the following items: a. Description of all updates to terrestrial ecosystem baseline data; b. An explanation of the annual results relative to the scale of natural variability; c. A detailed presentation and analysis of caribou and other terrestrial mammal distribution relative to mine structures and activities; d. Results of the annual monitoring program, including field methodologies and statistical approaches used to support conclusions drawn; e. A summary of the chronology and level of mine activities (such as vehicle frequency and type); f. An assessment and presentation of annual environmental conditions including timing of snowmelt and green-up, as well as standard weather summaries; and, g. A discussion of any proposed changes to the monitoring survey methodologies, statistical approaches or proposed adaptive management stemming from the results of the monitoring program. | Draft Terms of Reference should be provided to NIRB within six (6) months of issuance of the project certificate.
Marine Environment
22 | KivIA |  | Agnico Eagle to provide consultation records regarding shipping routes and concerns raised by Coral Harbour and how the concerns were included within the EIS | Prior to PHC | Complete, submitted to NIRB May 1, 2017 | NIRB
Human Environment and Socio-Economics
23 | NTI |  | Agnico Eagle to provide a summary of the discussions that have occurred between Agnico Eagle and the HTO regarding ramps including the heights, numbers of ramps for the Whale Tail pit haul road including consultation regarding improvements at km 12. | Prior to PHC | Complete, submitted to NIRB May 1, 2017 | NIRB
24 | INAC | INAC-11 | AEM committed to provide an updated rationale (in the form of an addendum) for no-linkage pathways, residual impact classification and cumulative pathway analysis that provides rationale for the conclusions in the FEIS, using literature review and other existing evidence prior to final hearing. | July 2017 |  | NIRB
25 | INAC/TC | INAC-13 | Agnico Eagle to provide TK workshop minutes to confirm that the socio-economics issues have been addressed | Prior to PHC | Complete, submitted to NIRB May 1, 2017 | NIRB
26 | INAC |  | AEM commits to provide a Labour Force Analysis to INAC prior to final hearing. | July 2017
27 | INAC |  | AEM committed to sharing TK and IQ detailed meeting notes and other meeting notes where concerns were raised regarding the Whale Tail Pit project up to April 2017. In addition, AEM will provide information on how the concerns were addressed and where information appears in the EIS. Information will be provided to INAC prior to the final hearing in the form of meeting notes and summary table. | July 2017
28 | INAC |  | AEM committed to provide procedure and information on community liaison committee, their selection process and AEM’s justification on how this committee represents community perspective, prior to final hearing | July 2017
Freshwater Environment
29 | ECCC |  | Agnico Eagle to provide cross section schematic of Whale Tail pit, and overlying north basin water, including lake bathymetry, and schematic of groundwater flow. | July 2017 |  | NWB
30 | ECCC/INAC |  | Agnico Eagle to complete a sensitivity analysis of the flooded open pit in water quality modelling, to represent the scenario where the contingency of removing a portion of the ultramafic rock in the north wall would be executed to decrease the transfer of arsenic to the flooded open pit. This will be done together with the update of the downstream water quality model where the new treatment levels for arsenic and phosphorous are applied at the mine effluent discharge into Mammoth lake as per commitment no. 37 | July 2017 |  | NIRB/NWB
31 | DFO |  | Agnico Eagle consider all fish in the study area, and assign equal value to all species when planning for conceptual offsetting plan | n/a |  | NIRB
32 | NIRB |  | Agnico Eagle to collect water samples for analysis of arsenic III and arsenic V; samples to be collected in July and data will be included in the baseline report to be provided before construction | n/a |  | NIRB/NWB
33 | NWB |  | Agnico Eagle commits to have the independent dike review board in place with an annual review to be conducted of the dike performance as per the licence requirements | n/a |  | NWB
34 | NWB |  | Agnico Eagle to provide water balance data for Nemo Lake to the NWB and parties for review | July 2017 |  | NWB
35 | KivIA | KivIA-TC-Freshwater Environment 03 and 04 | Agnico Eagle commits to establishing additional water monitoring wells at locations to be agreed upon between Agnico Eagle and KivIA, to better monitor water quality, in particular, the concentrations of arsenic, mercury and phosphorous that are discharged during operations and post-closure. | Two years after production start-up of the Whale Tail open pit
Waste Management
36 | ECCC |  | Agnico Eagle commits to defining the treatment options for arsenic and phosphorous that will allow meeting the site specific water quality objectives for arsenic and the oligotrophic level for phosphorous, as a minimum. Water quality predictions will be updated using these arsenic and phosphorous treatment targets, as stated in commitment no.30, and reporting the results per commitment no. 37 | Prior to Final Hearing | Related to slide 25 | NIRB/NWB
37 | ECCC |  | Agnico Eagle commit to update Appendix 6H with the results of modelling specified in commitments no. 30 and 36. | July 2017 |  | NIRB/NWB
38 | INAC | INAC-TRC #3 | Agnico Eagle commit to recommend, in consultation with ECCC, and in the form of a technical memo, discharge criteria for water from the Whale Tail waste rock storage facility pond that would be discharged to Mammoth Lake post closure | Criteria to be provided in the final closure plan |  | NWB
39 | NWB | NRCan #3; INAC-TRC#1 | Agnico Eagle commit to provide information in the form of a technical memo regarding the thermal modelling of the WRSF, incorporating climate change and acquired information from the Meadowbank WRSF monitoring program, and will use the result of the model to support final design of the WRSF including that of the proposed cover and revised designs prior to the final hearing. | July 2017 |  | NWB
40 | ECCC |  | Agnico Eagle commit to adding monitoring for temporal trends in sediments at reference and depositional areas for mercury in addition to the water and fish tissue monitoring. | To be provided in the baseline conditions report (due before construction) and as part of the annual CREMP reports as new sediment data are collected |  | NIRB/NWB
41 | NWB |  | Agnico Eagle will provide a table that describes the water source, location and phase of the project (construction, operation, closure) | July 2017 or with an updated amended/new water licence application. | Likely to be determined in the PHC. | NWB
42 | INAC | INAC-TRC#3 | Agnico Eagle commits to doing sensitivity analysis of the cover thickness and composition of the Whale Tail Waste rock storage facility as part of the interim closure plan for the Whale Tail Pit | Prior to operation |  | NWB
43 | INAC | INAC-TRC#2 | Agnico Eagle to provide technical memo to outline the control of arsenic leaching in the tailings facility. | July 2017 |  | NIRB/NWB

## Sheet1
4 | KIA | 6 | Agnico Eagle commits to complete adequate analysis of the caribou collar data to determine the extent of deflection or changes in movement and crossing rates by caribou from the existing All Weather Access Road (AWAR) between Baker Lake and Meadowbank | Timing? | Analysis to be completed following receipt of data from the Government of Nunavut (GN) as per the Memorandum of Understanding | NIRB
7 | GN | GN-17 | Agnico Eagle will extend the local study area to include… |  | GN-17: size of the zone is relatively small as seen at other mines and may minimize the extend of the impacts and the analysis should be redone. The response was in disagreement to the GN comments | NIRB