## Nanuq and Nanuq N-DDH-2011
PEREGRINE DIAMONDS LTD. - 2011 DRILL LOG FOR NANUQ AND NANUQ NORTH PROJECTS
NOTE 1: "NNQ" = Nanuq drillholes. "NQN" = Nanuq North drillhole.
NOTE 2: 8 holes drilled from 5 setups
Drillhole # | Lat. (WGS84) | Long. (WGS84) | Dip | Azimuth | Length (m) | Topography | Elev. (m) | Start Date | End Date | Comment
NNQ-382-11-DD01 | 65° 21’ 12.375” | 90° 23’ 51.157” | -50 | 290 | 38.46 | Land | N/A | 2011-06-18 | 2011-06-23 | hole not completed
NNQ-382-11-DD02 | 65° 21’ 12.375” | 90° 23’ 51.157” | -55 | 290 | 95 | Land | N/A | 2011-06-24 | 2011-06-26 | setup same location
NNQ-359-11-DD01 | 65° 20’ 14.470” | 91° 00’ 21.416” | -50 | 328 | 149 | Land | N/A | 2011-06-27 | 2011-06-30
NNQ-402-11-DD01 | 65° 34’ 42.102” | 90° 54’ 33.136” | -50 | 55 | 32 | Land | N/A | 2011-07-01 | 2011-07-06 | hole not completed
NNQ-402-11-DD02 | 65° 34’ 42.102” | 90° 54’ 33.136” | -55 | 55 | 150 | Land | N/A | 2011-07-06 | 2011-07-08 | setup same location
NQN-411-11-DD01 | 65° 38’ 49.302” | 90° 56’ 10.166” | -50 | 39 | 214 | Land | N/A | 2011-07-29 | 2011-08-02
NNQ-414-11-DD01 | 65° 27’ 40.585” | 90° 56’ 34.639” | -50 | 342 | 0 | Land | N/A | 2011-08-02 | 2011-08-06 | hole not completed
NNQ-414-11-DD02 | 65° 27’ 40.585” | 90° 56’ 34.639” | -55 | 342 | 121 | Land | N/A | 2011-08-06 | 2011-08-12 | setup same location
TOTAL METRES - NANUQ: |  |  |  |  | 585.46
TOTAL METRES - NANUQ NORTH: |  |  |  |  | 214