## Sheet1
Reclamation Costs Estimate for Ulu Minesite (present conditions) Updated June 21, 2011
Activity | Quantity | Units | No. Men | Total Hrs | Rate/hr | Cost Labour | Equipment | Hrs | Rate/hr | Cost Eqpt | Materials | Cost | Total Cost | Cost/Activity
Cap vent raise | 11.5 | m^3 | 3 | 44 | 52 | 6864 | Zoom Boom | 22 | 40 | 880 | concrete | 17000 | 24744 | 24744
Dismantle 350,000 gal fuel tanks | 2 | ea | 5 | 154 | 52 | 40040 | Badger Crane | 154 | 300 | 46200 |  |  | 86240
|  |  | 2 | 154 | 52 | 16016 | Zoom Boom | 154 | 40 | 6160 |  |  | 22176 | 108416
Dismantle Weatherhaven Camp |  |  | 2 | 165 | 75 | 24750 | Badger Crane | 11 | 300 | 3300 | Trav Expense | 2500 | 30550
|  |  | 10 | 165 | 41.5 | 68475 | Flat Deck | 165 | 25 | 4125 |  |  | 72600 | 103150
Dismantle Ulu trailers, etc. |  |  | 12 | 330 | 41.5 | 164340 | [6 empty] | 164340
Remove fence - powder mags |  |  | 2 | 10 | 41.5 | 830 | CAT966 | 10 | 55 | 550 |  |  | 1380
Labour Crew |  |  | 10 | 165 | 41.5 | 68475 | [6 empty] | 68475
Catering |  |  | 3 | 660 | 52 | 102960 | Incl food | [5 empty] | 102960
Re-supply flights | [6 empty] | Dornier | 5 | 12500 | 62500 |  |  | 62500
Crew change flights | [6 empty] | Dornier | 3 | 7500 | 22500 |  |  | 22500 | 422155
Fuel
Fuel purchase cost (Jet-B) | 130000 | litres |  |  |  |  | For Buffalo Aircraft |  | 1.5 | 195000 |  |  | 195000
Transportation cost to Ulu (Jet-B) | 130000 | litres |  |  |  |  | Hercules Aircraft |  | 1.5 | 195000 |  |  | 195000
Fuel Handling - Ulu |  |  | 2 | 66 | 41.5 | 5478 | Fuel Truck | 22 | 35 | 770 |  |  | 6248 | 396248
Fly Ulu Fuel Inventory to High Lake | 500000 | [5 empty] | Buffalo Aircraft | 58 | 3300 | 191400 | mob/demob | 13000 | 204400 | 204400
Freight Haul - Ulu to High Lake
(assume 1.0 million lbs)
Ulu freight transfer crew |  |  | 4 | 330 | 41.5 | 54780 | Forklift | 56 | 40 | 2240 |  |  | 57020
High Lake freight receiving crew |  |  | 4 | 330 | 41.5 | 54780 | Forklift | 56 | 40 | 2240 |  |  | 57020 | 114040
Freight Flights - Ulu to High Lake | [6 empty] | Buffalo Aircraft | 56 | 3300 | 184800 | mob/demob | 13000 | 197800 | 197800
Uncover Portal
dig | 400 | m^3 | 1 | 11 | 52 | 572 | CAT966 | 11 | 55 | 605 |  |  | 1177
blast |  |  | 1 | 11 | 57.5 | 632.5 |  |  |  |  | explosives | 1200 | 1832.5 | 3009.5
Block portal with waste (final) | 800 | m^3 | 1 | 22 | 52 | 1144 | CAT966 | 22 | 55 | 1210 |  |  | 2354 | 2354
Remove ore from pad to portal | 1222 | m^3 | 1 | 18 | 52 | 936 | CAT966 | 18 | 55 | 990 |  |  | 1926
| 1222 | m^3 | 1 | 18 | 52 | 936 | CAT769 | 18 | 65 | 1170 |  |  | 2106 | 4032
Grade sides of ore pad to 30deg | 800 | m^3 | 1 | 11 | 52 | 572 | D8N | 11 | 75 | 825 |  |  | 1397 | 1397
Grade sides of camp pad to 30deg | 400 | m^3 | 1 | 6 | 52 | 312 | D8N | 6 | 75 | 450 |  |  | 762 | 762
Grade road edges to 30deg slope | 12500 | m^3 | 1 | 22 | 52 | 1144 | D8N | 22 | 75 | 1650 |  |  | 2794 | 2794
Grade airstrip edges to 30deg slope | 400 | m^3 | 1 | 4 | 52 | 208 | D8N | 4 | 75 | 300 |  |  | 508 | 508
Grade sides of portal pad to 30deg | 400 | m^3 | 1 | 4 | 52 | 208 | D8N | 4 | 75 | 300 |  |  | 508 | 508
Tram ore underground | 1222 | m^3 | 1 | 22 | 52 | 1144 | ST-7.5 | 22 | 95 | 2090 |  |  | 3234 | 3234
Dig out Camp 3 tank farm | 617 | m^3 | 1 | 22 | 52 | 1144 | CAT966 | 22 | 55 | 1210 |  |  | 2354
Haul to portal |  |  | 1 | 22 | 52 | 1144 | CAT769 | 22 | 65 | 1430 |  |  | 2574
Haul u/g |  |  | 2 | 14 | 52 | 1456 | ST-7.5 | 14 | 95 | 1330 |  |  | 2786 | 7714
Dig out Ulu tank farm | 457 | m^3 | 1 | 5 | 52 | 260 | CAT966 | 5 | 55 | 275 |  |  | 535
haul to portal |  |  | 1 | 5 | 52 | 260 | CAT769 | 5 | 65 | 325 |  |  | 585
haul u/g |  |  | 2 | 10 | 52 | 1040 | ST-7.5 | 10 | 95 | 950 |  |  | 1990 | 3110
Scarify
Ulu camp | 26000 | m^2 | 1 | 13 | 52 | 676 | D8N | 13 | 75 | 975 |  |  | 1651
Portal pad | 8000 | m^2 | 1 | 4 | 52 | 208 | D8N | 4 | 75 | 300 |  |  | 508
Ore Pad | 19000 | m^2 | 1 | 10 | 52 | 520 | D8N | 10 | 75 | 750 |  |  | 1270
Roads | 140000 | m^2 | 1 | 70 | 52 | 3640 | D8N | 70 | 75 | 5250 |  |  | 8890
Airstrip | 23000 | m^2 | 1 | 12 | 52 | 624 | D8N | 12 | 75 | 900 |  |  | 1524 | 13843
Remove road culverts | 6 | ea | 1 | 22 | 50 | 1100 | backhoe | 22 | 25 | 550 |  |  | 1650
|  |  | 1 | 22 | 52 | 1144 | D8N | 22 | 75 | 1650 |  |  | 2794 | 4444
Subtotal |  |  |  | 2953 |  | 628812.5 |  |  |  | 943150 |  | 46700 | 1618662.5 | 1618662.5
Contingency (15%) | [12 empty] | 242799.375 | 242799.375
Totals | [12 empty] | 1861461.875 | 1861461.875