## Ulu Reclamation Costs
RECLAMATION COSTS ESTIMATE FOR ULU MINESITE (present condition) | [6 empty] | up dated March 30, 2010 |  |  |  |  | 2010 Ulu Reclamation Costs.xls
Activity | Quantity | units | No. | Total | Rate/ | Cost | Equip. | hrs | Rate/ | Cost | Materials | Cost | Total | Cost/
|  |  | men | hrs | hr | Labour |  |  | hr | eqpt |  |  | Cost | activity
Cap vent raise | 11.5 | m^3 | 3 | 44 | 50 | 6600 | Zoom Boom | 22 | 40 | 880 | concrete | 17000 | 24480 | 24480
Dismantle 350,000 gal fuel tanks | 2 | ea | 5 | 154 | 50 | 132000 | Badger Crane | 154 | 300 | 46200 |  |  | 178200
|  |  | 2 | 154 | 50 | 15400 | Zoom Boom | 154 | 40 | 6160 |  |  | 21560 | 199760
Dismantle Weatherhaven camp |  |  | 2 | 165 | 75 | 24750 | Badger Crane | 11 | 300 | 3300 | Trav expens. | 2500 | 30550
|  |  | 10 | 165 | 40 | 66000 | Flat deck | 165 | 25 | 4125 |  |  | 70125 | 100675
Dismantle Ulu trailers, etc. |  |  | 12 | 330 | 40 | 158400 | [6 empty] | 158400
Remove fence - powder mags |  |  | 2 | 10 | 40 | 800 | CAT966 | 10 | 55 | 550 |  |  | 1350
Labor crew |  |  | 10 | 165 | 40 | 66000 | [6 empty] | 66000
Catering |  |  | 3 | 660 | 50 | 99000 | incl food | [5 empty] | 99000
Re-supply flights | [6 empty] | Dornier | 5 | 12500 | 62500 |  |  | 62500
Crew change flights | [6 empty] | Dornier | 3 | 7500 | 22500 |  |  | 22500 | 409750
Fuel
Fuel purchase cost (Jet-B) | 130000 | liters |  |  |  |  | For Buffalo aircraft |  | 1.5 | 195000 |  |  | 195000
Transportation cost to Ulu (Jet-B) | 130000 | litres |  |  |  |  | Herules aircraft |  | 1.5 | 195000 |  |  | 195000
Fuel Handling - Ulu |  |  | 2 | 66 | 40 | 5280 | Fuel truck | 22 | 35 | 770 |  |  | 6050 | 396050
Fly Ulu Fuel Inventory to High Lake | 500000 | [5 empty] | Buffalo aircraft | 58 | 3300 | 191400 | mob/demob | 13000 | 204400 | 204400
Freight Haul - Ulu to High Lake
(assume 1.0 million lbs)
Ulu freight transfer crew |  |  | 4 | 330 | 40 | 52800 | Forklift | 56 | 40 | 2240 |  |  | 55040
High Lake freight receiving crew |  |  | 4 | 330 | 40 | 52800 | Forklift | 56 | 40 | 2240 |  |  | 55040 | 110080
Freight flights - Ulu to High Lake | [6 empty] | Buffalo aircraft | 56 | 3300 | 184800 | mob/demob | 13000 | 197800 | 197800
Uncover portal
dig | 400 | m^3 | 1 | 11 | 50 | 550 | CAT966 | 11 | 55 | 605 |  |  | 1155
blast |  |  | 1 | 11 | 55 | 605 |  |  |  |  | explosives | 1200 | 1805 | 2960
Block portal with waste (final) | 800 | m^3 | 1 | 22 | 50 | 1100 | CAT966 | 22 | 55 | 1210 |  |  | 2310 | 2310
Remove ore from pad to portal | 1222.2222 | m^3 | 1 | 18 | 50 | 900 | CAT966 | 18 | 55 | 990 |  |  | 1890
| 1222.2222 | m^3 | 1 | 18 | 50 | 900 | CAT769 | 18 | 65 | 1170 |  |  | 2070 | 3960
Grade sides of ore pad to 30deg | 800 | m^3 | 1 | 11 | 50 | 550 | D8N | 11 | 75 | 825 |  |  | 1375 | 1375
Grade sides of camp pad to 30deg | 400 | m^3 | 1 | 6 | 50 | 300 | D8N | 6 | 75 | 450 |  |  | 750 | 750
Grade road edges to 30deg slope | 12500 | m^3 | 1 | 22 | 50 | 1100 | D8N | 22 | 75 | 1650 |  |  | 2750 | 2750
Grade airstrip edges to 30deg slope | 400 | m^3 | 1 | 4 | 50 | 200 | D8N | 4 | 75 | 300 |  |  | 500 | 500
Grade sides of portal pad to 30deg | 400 | m^3 | 1 | 4 | 50 | 200 | D8N | 4 | 75 | 300 |  |  | 500 | 500
Tram ore underground | 1222 | m^3 | 1 | 22 | 50 | 1100 | ST-7.5 | 22 | 95 | 2090 |  |  | 3190 | 3190
Dig out Camp 3 tank farm | 617 | m^3 | 1 | 22 | 50 | 1100 | CAT966 | 22 | 55 | 1210 |  |  | 2310
Haul to portal |  |  | 1 | 22 | 50 | 1100 | CAT769 | 22 | 65 | 1430 |  |  | 2530
Haul u/g |  |  | 2 | 14 | 50 | 1400 | ST-7.5 | 14 | 95 | 1330 |  |  | 2730 | 7570
Dig out Ulu tank farm | 457 | m^3 | 1 | 5 | 50 | 250 | CAT966 | 5 | 55 | 275 |  |  | 525
Haul to portal |  |  | 1 | 5 | 50 | 250 | CAT769 | 5 | 65 | 325 |  |  | 575
Haul u/g |  |  | 2 | 10 | 55 | 1100 | ST-7.5 | 10 | 95 | 950 |  |  | 2050 | 3150
Scarify
Ulu Camp | 26000 | m^2 | 1 | 13 | 50 | 650 | D8N | 13 | 75 | 975 |  |  | 1625
Portal pad | 8000 | m^2 | 1 | 4 | 50 | 200 | D8N | 4 | 75 | 300 |  |  | 500
Ore pad | 19000 | m^2 | 1 | 10 | 50 | 500 | D8N | 10 | 75 | 750 |  |  | 1250
Roads | 140000 | m^2 | 1 | 70 | 50 | 3500 | D8N | 70 | 75 | 5250 |  |  | 8750
Airstrip | 23000 | m^2 | 1 | 12 | 50 | 600 | D8N | 12 | 75 | 900 |  |  | 1500 | 13625
Remove road culverts | 6 | ea | 1 | 22 | 48.4263 | 1065.3784 | backhoe | 22 | 25 | 550 |  |  | 1615.3784
|  |  | 1 | 22 | 50 | 1100 | D8N | 22 | 75 | 1650 |  |  | 2750 | 4365.3784
Subtotal | [12 empty] | 1690000.3784 | 1690000.3784
Contingency (15%) | [12 empty] | 253500.0568 | 253500.0568
TOTALS |  |  |  | 2953 |  | 700150.3784 |  |  |  | 943150 |  | 46700 | 1943500.4351 | 1943500.4351
Note on K22: DaveS: 5 trips x $5700/trip (Includes fuel and other expenses)
Note on K24: DaveS: 3 trips x $5700/trip (Includes fuel and other expenses)
Note on B27: DaveS: Buffalo 1125 liters per round trip x 114 trips = 128,250 liters
Note on B28: DaveS: Buffalo 1125 liters per round trip x 114 trips = 128,250 liters
Note on B31: DaveS: 500,000 liters of diesel currently stored at Ulu
Note on I31: DaveS: 500,000 liters/205 liters per barrel/42 barrels per trip = 58 trips
Note on A34: DaveS: EBM estimated 420,000 lbs of freight to be flown from Ulu to Lupin. I assumed more than double that from their esitmate of freight weight to be trucked to Lupin.
Note on I38: DaveS: 1.0 million lbs/18,000 lbs per trip = 56 trips