## Party Comments
| AGENCY | TOPIC | COMMENT | RECOMMENDATION
1 | NWB | Compliance Plan | A compliance plan from the Licensee, detailing the plan they have in place with clear timelines so that they can deliver all outstanding plans/info requested by NWB, EC and INAC, as detailed below. | NWB is requesting for this Plan
2 | NWB | Annual Report | The 2015 annual report has not been received. The reports submitted from 2010 and 2011 are incomplete, pertaining to Part B, Item 3. | NWB is requesting for the info or an explanation as to why it could not be provided
3 | NWB | Monitoring terms in Licence | 2011 Annual report is notably missing all licence mandated lab sample results. The reports from 2012 to 2014 do not follow the monitoring requirements as prescribed in Part H, Item 1 and 9. Where is the information for ARV-7, ARV-8 and ARV-9. Monthly sampling is prescribed for the monitoring stations (with annual Acute Toxicity). | NWB is requesting for the missing info, if sampling was not conducted please provide explanation i.e not thawed, etc.
4 | NWB | Stamped Drawings | In accordance with Part C, Item 4, The Licensee still needs to submit to the Board for approval in writing as built drawings stamped and signed by an Engineer confirming compliance with the DFO guideline “Freshwater Intake End of Pipe Fish Screen Guideline”. The drawings shall include information regarding the operating capacity of the pump used and the intake screen size. | NWB is requesting for the revised drawings
5 | NWB | Sewage Disposal Facility Report | In accordance with Part D, Item 5 a revised Sewage Disposal Facility Report was submitted however an additional revision has not been submitted with the application in order to address the comments from INAC on April 1, 2011 | NWB is requesting for the revised report
6 | NWB | Solid Waste Management Report | In accordance with Part D, Item 14 a revised Solid Waste Management Report was submitted however an additional revision has not been submitted with the application in order to address the comments from INAC on April 1, 2011 | NWB is requesting for the revised report
7 | NWB | Geotechnical Engineer’s inspection Report | According to Part D, Item 16 and 17 the Licensee still needs to submit annual reports to the Board, for geotechnical inspection to be carried out by a Geotechnical Engineer ( between the months of June and September) that takes into account all facilities intended to contain, withhold, divert or retain Water or Wastes. | NWB is requesting for the reports
8 | NWB | Sewage Treatment O&M | In accordance with Part F, Item 1 a revision to the Plan entitled “Sewage Treatment Facility Operation and Maintenance (O&M) Plan, Hamlet of Arviat” was submitted however it did not address the revisions required by the NWB in the licence, including the need for a clear sludge management plan. The plan is revised by Nuna Burnside Eng. & Envi. Ltd. | NWB is requesting for the revised plan
9 | NWB | Solid Waste O&M | In accordance with Part F, Item 2 a revision to the Plan entitled “Solid Waste Management Facility Operation and Maintenance (O&M) Plan, Hamlet of Arviat” was submitted however it did not address the revisions required by the NWB in the licence, including the need for a clear Bulky Waste Management Plan. The plan is revised by Nuna Burnside Eng. & Envi. Ltd. | NWB is requesting for the revised plan
10 | NWB | A&R Plan | The Abandonment and Restoration plans for the old sewage lagoons (as referenced in Part G, Item 2) need to be revised to address comments received from INAC on April 1, 2011. | NWB is requesting for the revised plan
11 | INAC, May 4 2016, Completeness Review | Compliance Plan | INAC is in support of a 24 year water licence renewal, if the NWB and Hamlet set out compliance objectives to be met during the course of the licence. | INAC would also like to recommend that should these objectives not be met then the NWB should use their authority in cancelling a licence.
12 | INAC, May 4 2016, Completeness Review | Reservoir | INAC notes that the storage capacity of the Hamlet’s two reservoirs is only 143,000 m3 and the Hamlet is requesting water volume use of 175,000 m 3 by 2039. | INAC recommends that the Hamlet briefly explain how the Hamlet plans to accommodate for the extra water in the future.
13 | INAC, May 4 2016, Completeness Review | Monitoring | INAC notes that there are still many non-compliance issues outstanding in regards to the water licence (i.e., Monitoring). These non-compliance issues will be further commented on in detail at the technical review stage of the water licence process. | INAC recommends that this be addressed by the Licensee
14 | INAC, May 4 2016, Completeness Review | Audit Report on the Solid Waste Disposal Facility | INAC acknowledges that the Hamlet has done some good work in regards to their solid waste deposal facility, including having an audit carried out and the report submitted to the NWB. | INAC is interested to know whether or not the Hamlet will implement any of the recommendations made in the report and given the results of the report where does the Hamlet go from here in operating its solid waste facility.
15 | INAC, May 4 2016, Completeness Review | Reservoir | INAC also notes that in February of 2011 there was a failure of one of the reservoirs with a substantial amount of water being lost. | INAC would like the Hamlet to briefly submit to the NWB for review a status update to the current effectiveness of the reservoirs.
16 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Licence Term | The Proponent is requesting a 24 year licence which would be valid until 2039. This includes an increase in the authorized amount of water from 86,000 cubic metres to 175,000 cubic metres annually to meet the 24 year water demand of the community. | EC recommends that the Proponent request a shorter Licence term (such as 5 years) due to the compliance issues resulting in lack of information. Water allocation for the designated term should be re-calculated based on projected annual consumption in the final year of the licence.
17 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Sublethal Toxicity Testing | The application indicates that the Proponent is requesting that the condition to conduct acute toxicity testing be removed from the licence. This request is based on difficulty in satisfying laboratory protocols of sampling and shipping large volumes of water within holding times. Alternatively, it is proposed that sampling results from monitoring stations ARV-2a, ARV-4, and ARV-2b be compared to CCME guidelines for protection of aquatic life to confirm there is no adverse impact from the solid waste site and sewage wetlands. | EC recommends that the Proponent provide recent historical monitoring data to evaluate this request.
18 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Monitoring | Water quality and toxicity testing is required under the existing licence yet it does not appear to have been completed. Non-compliance with the existing water licence inhibits EC's ability to complete a thorough review of the amendments requested. No water quality samples or toxicity testing from the previous licence have been included in the amendment application. | EC recommends that if water quality and toxicity results are in fact available, they should be provided by the Proponent.
19 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Water Use | The renewal application requests an increase in water use from 86,000 cubic metres to 175,000 cubic metres to meet the 24 year water demand of the community | EC recommends that the Proponent clarify whether the existing sewage lagoon system has the capacity to manage the increased volumes that are anticipated over the course of the requested licence. EC also recommends that the Proponent clarify the holding time required for meeting objectives prior to discharge, and whether these objectives would be satisfied with increased sewage without removing sludge
20 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Sewage System | The application indicates that if the sludge accumulates to the point that it interferes with the treatment process that it may need to be removed. The sludge management plan is included in the Sewage Treatment Facility Report. This report was not included in the application package (Only the Sewage Treatment Facility OM Plan from May 2010). | EC recommends that the Proponent clarify how sludge accumulation is monitored, and how is it determined that the sludge is interfering with the treatment process.
21 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Solid Waste | The application summary indicates that "hazardous waste is stored next to the garage". EC had previously commented on lack of detail on how access to the hazardous waste storage area is controlled. | EC recommends that the Proponent provide information on how EC’s prior comments were incorporated into practice to increase containment and reduce spills or leaching into the environment.
22 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Solid Waste | The Proponent would like the conditions relating to the New Solid Waste Site to remain on the renewed licence, though there are no immediate plans for these facilities to be constructed. The Solid Waste Disposal Facility is nearing the end of its life and will be necessary within the 24 year period of the requested licence. The Solid Waste Management Facility OM Plan from 2010 states that "the landfill is nearing capacity and an expansion or a new site will be required in the next few years". | EC recommends that the Proponent clarify for how many years the existing facility is expected to function until capacity is reached. EC recommends that the Proponent clarify whether an expansion was needed in the previous licence term in order to create sufficient capacity. EC recommends that the Proponent clarify whether closure plans have been prepared.
23 | EC, May 4 2016, Completeness Review | Amendment Renewal Application Compliance | A number of instances of non-compliance are noted in the Compliance Plan. | EC recommends that the Proponent must ensure that any effluent discharged from a system’s final discharge point is in compliance with Section 36(3) of the Fisheries Act. According to the Fisheries Act, Section 36(3), the deposition of deleterious substances of any type in water frequented by fish, or in any place under any conditions where the deleterious substance, or any other deleterious substance that results from the deposit of the deleterious substance, may enter any such water, is prohibited. Additionally, we would like to highlight that there are federal wastewater regulations in force in areas outside Canada's Far North. EC recommends that the Proponent review and strive to attain the level of treatment described in the Wastewater Systems Effluent Regulations.
24 | EC, May 4 2016, Completeness Review | Environmental Monitoring and QAQC Plan Sampling locations | It is noted that sampling station ARV-5 (discharge from bulky metal waste area) and ARV-6 (discharge from hazardous waste storage area) are not included on the figures. | EC recommends that the Proponent identify the location of ARV-5 and ARV-6 on the figures.
25 | EC, May 4 2016, Completeness Review | Environmental Monitoring and QAQC Plan Sampling locations | There are inconsistent descriptions of sampling station ARV-3 between the Environmental Monitoring Plan (sampling of effluent discharge from the Final Discharge Point of the Solid Waste Disposal Facility) and the Licence (raw sewage at truck offload point - not active) as well as ARV 6 (discharge from the hazardous waste storage area vs. sampling of effluent discharge from the FDP of wetland treatment area of the sewage disposal facilities). | EC recommends that the Proponent verify the description of ARV-3 and ARV-6, whether they are active or inactive, and their location. All plans should be amended to include the correct descriptions and locations.
26 | EC, May 4 2016, Completeness Review | Supporting documents | EC notes that all provided plans have not been updated since the previous renewal process. | EC recommends that the Proponent should update all Plans according to changes and improvements that may have occurred during the previous licence term.

## Timeline
Date | Activity
2015-02-27 | NWB acknowledges receipt of the application and supporting documentation for the Amend/Renew of 3AM-ARV1016
2015-03-27 | NWB goes out for comments from parties for "Completeness review and an initial technical assessment". NPC and NIRB were asked to complete their review of the application and offer their determinations.
2015-05-04 | Comments were received from EC and AANDC
2015-04-10 | NPC responded back to the NWB with a conformity determination
2015-05-20 | GN-CGS (Megan Lusty) confirmed that a response to NWB's, EC's and AANDC’s questions/comments would be sent by May 22, 2016
2015-03-21 | From May of 2015 till date, the NWB's Tech and Licence team has sent followup communications to GN-CGS (Megan Lusty) requesting a followup in information, no response was gotten back.
2015-03-22 | Tech Advisor (Cynthia Ene) sent a followup communication to Megan detailing the required submissions.
2016-03-22 | Tech Advisor (Cynthia Ene) sent a followup communication to Megan Lusty which included a file overview and a very detailed list of required submissions in order to move the file forward. No response was received back from anyone at GN-CGS.
2017-02-02 | Melissa Pinto, an Environmental Assessment Coordinator, Environment and Climate Change Canada contacted the NWB requesting a file update for the 2AM-ARV file. In response to this request, the NWB Tech Advisor (Cynthia Ene) sent a follow-up email to Megan Lusty requesting for a file update. Till date, no response was received back from anyone at GN-CGS.