## Commitments
No. | Issue | Party(s) who raised issue | Pre-Hearing Commitment (DRAFT) | Party Responsible for Commitment | Timeline for Submission | Additional Comment
1 | Char River flow data. | AANDC/NWB | Char River Flow data iavailability (maybe from Agnico-Eagle Mines Ltd.?). If no flow information available, would it be possible to get and provide flow data in the future. | GN-CGS | 2014-02-07 | If the information is not available the timeline should be revisited.
2 | Existing fish habitat compensation agreement. | AANDC | Confirmation from DFO that withdrawal of water from Char River wouldn't affect the existing fish habitat compensation agreement (an agreement exists between DFO and Agnico Eagle Mines Ltd.). | GN-CGS | 2014-02-07
3 | Water Chemistry of Lower Landing Lake and Char River | AANDC/NWB | It is recommended that the Proponent provide additional information on water chemistry within Lower Landing Lake and Char River and whether or not it is substantially different from Nipissar Lake, outlining any potential impacts water transfers will have on water quality of the source and discharge water-bodies. | GN-CGS | 2014-02-07 | GN-CGS has some water chemistry data. If analysis can't be completed based on the existing data the timeline should be revisited.
4 | Operational Procedures for the new Intake | AANDC/NWB | Operation and Maintanance Plan for Water Supply Facilities shall be updataed to include the additional Intake Operational Procedures with daily measuring of water depth in Char River, and stoping of withdrawal if the actual dept is less than the treshold dept (0,5m). | GN-CGS | 2014-02-21
5 | Spill Contingency Plan | AANDC | The Spill Contingency Plan shall be updated to include new facilities (intake, pumphouse). | GN-CGS | 2014-02-21
6 | Schedule of water saving measures recommended by RMSi/FSC 2010 Study. | NWB | Part C, Item 8 (e) requires: A schedule to address the recommendations of the report, that is consistent with the conservation and utilization of waters and provides for the optimum benefit from those waters for the residents of Nunavut. When a Schedule may be provided including all water saving meusures for the implementation. | GN-CGS | 2014-02-21
7
8
9