# APPENDIX D:  List of Commitments

| List of Commitments Resulting from Technical Meeting for Water Licence No. 3AM-RUT---- Application |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Party Responsible for Commitment | Party(s) who raised (Item#) | Issue - TM Commitment | Timeline for Submission | Form of Submission | Status |
| 1. | GN-CGS | CIRNA-2.1 | To provide Environmental Management Plan Note: it was prepared but need more time so that the consultant can proofread it | August 7, 2020 | Management Plan | Submitted on August 12, 2020 |
| 2. | GN-CGS | CIRNA-2.2 | To provide Decommissioning and Remediation Plan for the old structures including intake from Char Lake, intake line from Pump House, Macerator Unit building, old pump station, Blue Building, Disposal Pipe from the Macerator Unit to the sea | Partly by the end of 2020, the WWTP affiliated infrastructure in 2024; Licence requirement is generally at least 6 months prior to abandoning. | Decommissioning Plan | Outstanding ** Will be provided after PH |
| 3. | GN-CGS | CIRNA-3.1 | Install a new flow meter to record extraction volumes of Water from the Char Lake and at the Macerator | September 14, 2020 | Correspondence from GN-CGS confirming the installation | Outstanding ** Meter already installed in the Macerator unit, but not at pump station |
| 4. | GN-CGS | CIRNA-3.3 ECCC-3 | To provide the detailed Design Report for the Wastewater Treatment Plant (WWTP), include treatment targets for CBOD and Ammonia into this report | At least sixty (60) days prior to initiating construction | Design Report | Outstanding ** Will be provided after PH |
| 5. | GN-CGS | CIRNA-4.1 | To provide O&M Manual for the Water Treatment Plant | Within ninety (90) days from the approval of the Licence | Updated Manual | Outstanding ** Only provided the WTP Design Summary on September 22, 2020 |
| 6. | GN-CGS | CIRNA-4.3 | To provide Manual for Sewage Treatment addressing safety concerns in the Macerator Unit building | August 14. 2020 | New Manual | Submitted on August 4, 2020 |
| 7. | GN-CGS | CIRNA-8.1 ECCC-4 & 7 | To update Quality Assurance/ Quality Plan to include the trip blanks in addition to the already proposed field blanks and duplicates; also remove all irrelevant (Pangnirtung-related) information from the Plan; and to include ECCC potential concerns | Prior to PH or Licence requirement | Updated QA/QC Plan | Outstanding |
| 8. | GN-CGS | CIRNA-9, ECCC-7 | To update Spill Contingency Plan to address deficiencies to remove all irrelevant (Pangnirtung-related) information from the Plan and to include ECCC potential concerns | Prior to PH or Licence requirement | Updated Management Plan | Outstanding |
| 9. | GN-CGS | ECCC-5 | Review of Fecal Coliforms data to provide the estimates and advise the Board whether the criteria from Guidelines for the Discharge of Treated Municipal Wastewater in the NWT and the Wastewater Systems Effluent Regulations can be met | July 31, 2020 | Correspondence from GN-CGS | Submitted on September 2. 2020 |
| 10. | GN-CGS | ECCC-8 | Provide information on the typical performance for Ammonia | With final design document | Correspondence from GN-CGS | Submitted on September 15, 2020 |
| 11. | GN-CGS | CIRNA-8.2 ECCC-9 | Provide Toxicity Test validation results within 6 months of commissioning of WWTP Provide monthly effluent quality data to the NWB following commissioning of the WWT system. | Will be Licence condition | Test Results | Outstanding ** Will be provided after PH |
| 12. | GN-CGS | ECCC-10 | Provide existing effluent quality data to support potentially reduced sampling frequency for the current system as discussed within CIRNA submission | July 31, 2020 | Test Results | Provided Wastewater Test Results for 2014 to 2020 on July 16, 2020 |
| 13. | GN-CGS | CIRNA-10 | Amend the term of the licence requested to a longer term | July 31, 2020 | Updated Application form and associated correspondence | Submitted the Updated Application form, Consumption numbers and a Letter of Clarification on August 4, 2020 |