C-NGO Committee Bay Project 2000

The 3-year geological mapping project on the northeastern mainland of Nunavut is proposed to start in 2000, and has as a primary goal, new bedrock and surficial materials map coverage of the of the following NTS 1:250 000-scale map areas.



56J
Walker Lake



56K
Laughland Lake



56O
Armshow River



56P
Ellice Hills

2000 Study Area: 56K Laughland Lake



Field work: 
June 25 – August 25, 2000



Move-in: June 25-26



Field Work June 27 – August 22



Restoration & clean-up: August 22 – 23



Move-out: August 24 – 25

Staging area: Baker Lake

Base camp: 10 sleeping tents, a kitchen tent, a storage tent and an office tent would be established on a gravel terrace on an unnamed lake, approx. 300km northeast of Baker Lake (site of previously occupied exploration camp); see attached map.   Machinery limited to: a helicopter (stationed well away from the lake), and Honda generators to power the computers. Camp would be completely assembled and disassembled at the start and end of the field season. Refuse (fuel drums, propane cylinders, garbage) from previous occupants would also be cleaned up.

Daily activities: foot traverses with helicopter drop-offs and pick-ups; bedrock sampling (fist-sized pieces); compilation of data with computers in camp; no chemicals required.

Helicopter usage: drop-offs and pick-ups of traverse teams; sample collection, geophysical surveys; equipment and supplies movement; personnel moves to/from main camp.

Fuel: 75 sealed 205 litre drums of helicopter fuel would be moved by Twin Otter from the airstrip at Baker Lake (sealift drop-off point in 1999) to the main camp before the start of the field season.  Fuel drums would be stored away from any surface drainage on a gravel pad.  All drums (empty and full) will be removed by Twin Otter at the end of field season and transported to Baker Lake for re-use or disposal.

