## Table 1
HAMLET OF CAPE DORSET
PLAN FOR COMPLIANCE LICENCE NO. 3BM-CAP0810 (EXPIRED)
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
| The Hamlet must maintain a valid Water Licence | The Hamlet’s Water Licence expired on March 01,2010. | The GN has initiated the water licence renewal process on behalf of the Hamlet | The water Licence renewal process has been started |  Prior to expiration of future water licence ,the GN will initiate the renewal of the future water licence on behalf of the Hamlet  The GN and the Hamlet commit to ongoing compliance with the Nunavut Waters Act and maintaining a water licence | The water licence renewal process will be started minimum 6 months prior to expiration of the active licence renewal
Part B | General Conditions
B-1 | The Licensee shall file an Annual Report with the Board not later than March 31st of the year following the calendar year | Compliance | The GN will ensure the community submit to the NWB the Annual Report, in accordance with the criteria outlined in the issued water licence. | The GN will ensure that the Hamlet record all the activities carried out for all the water licensed facilities under their water licence during the reporting year. |  GN will monitor to ensure the Hamlet submits their Annual Report to the NWB, in accordance with the criteria outlined in the issued water licence  GN monitoring will include weekly checks of the Hamlet’s log sheets, along with monthly Regional water committee meeting to discuss and action any issues. | The Regional Municipal Engineer will train the Hamlet foreman gradually how to write Annual Report and submit to NWB on time. This training will be conducted during Community visit for the infrastructure inspection once or twice annually.
B-2 | The Licensee shall comply with the Monitoring Program described in this Licence, and any amendments to the Monitoring Program as may be made from time to time, pursuant to the conditions of this Licence. | In Compliance, Hamlet is currently following the Monitoring program of the existing facilities except the P-Lake Seawge Lagoon. They are following the INAC inspector's direction as needed. | The GN retained the services of the Consulting firm exp Services Inc. for the preparation of a QA/QC plan which identifies sampling protocols and testing requirements  This QA/QC Plan which meets the requirements of Monitoring Program described in Part H of the water licence.The QA/QC Plan was already submitted to NWB. | Monitoring is being implemented during winter and summer seasons as described in the QA/QC Plan prepared by exp. |  Regional Municipal Engineer will continue to train the Hamlet staffs once or twice a year. Also develop a training plan for a TRAIN THE TRAINER for GN staff to develop resources within the GN to allow for ongoing training of Hamlet Staff.  The GN has created a central data base for all reports to be held and accessible to GN staff for review and action. |  All sampling and tseting data will be kept in the Regional office in Pond Inlet and CGS head office in Iqaluit.  The TRAIN THE TRAINER program will be continued.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
B-5 | The Licensee shall, within ninety (90) days after the first visit by the Inspector following issuance of this License, post the necessary signs to identify the stations of the “Monitoring Program”. All signage postings shall be in the Official Languages of Nunavut. | In compliance | Monitoring stations were already established with Co-ordinates. Signs were installed as per the requirements of the Water licence. | These Monitoring stations will be maintained. | Each summer inspection, the monitoring stations will be inspected. And the missing signs will be reinstalled. | The missing signs will be reinstalled prior to the summer sampling .
B-6 | The Licensee shall submit to the Board, for approval in writing, within the lesser of ninety (90) days or the filing of any application in relation to the Licence, a Plan for Compliance that clearly demonstrates the ways and means the Licensee will undertake to achieve full compliance with the conditions of this Licence. | In compliance | GN has decided not to use the P-Lake Seawge lagoon. Hamlet is maintaining the existing lagoons with close collaboartion of INAC inspector and GN. | Until the new Mechanical Plant is built, the current treatment process will be continued as it is. | The Feasibility study for treating Community wastewater was completed. A RFP (Request For Proposal) to hire a consulting firm is being advertised within three months. The new metal crusher was used there in 2017 to crush the metals and stockpiled for future disposal to the South. | The new Wastewater Mechnaical Treatemnt Plant is expected to be built and commissioned sometimes in 2022.
B-10 | The Licensee shall ensure a copy of this Licence is maintained at the municipal office at all times. | In Compliance | Available for the Public | A copy is available always at the front desk | Always keep the Licence available at the front desk for the Public | A copy will be kept avaiable always at the front desk.
Part D | Conditions Applying To Waste Disposal
D-8 | All effluent discharged from the 2007 Sewage Disposal Facility at the Final Discharge Point at Monitoring station CAP-14 and effluent discharge from monitoring stations CAP-3 and CAP-4 prior | Not applicable any more because Hamlet has not used this lagoon and will not use in future. | The P-lake Sewage Lagoon has been abandoned. | Never used | Will not be used | Will never be used.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
D-8 Cont’d | to the point of entry at the ocean, shall be demonstrated to be non-acutely toxic under the following tests to be conducted once annually, approximately mid-way through the discharge period. |  | Sampling is being taken from CAP-4 during Summer seaon. | Sampling will be continued during Summer season from CAP-4. | Sampling will be continued during Summer season from CAP-4. | Sampling will be continued during Summer season from CAP-4. Winter sampling might be needed as required if there is any emergency.
Part E | Conditions Applying To Waste Disposal
E-5 | The Licensee shall, within 60 days of issuance of the license, provide a summary report along with revised stamped as built plans and record drawings of the 2007 Sewage Disposal Facility, to reflect the clarifications and omissions identified through the License application review and detailed in the attached Schedule 1. | Not applicable any more because Hamlet has not used this lagoon and will not use in future. | This facility has been abandoned and excluded from this licensing process | Not applicable | Planning to build a new wastewater Mechanical Treatemnt Plant | The as built drawings of the new Mechanical Traetment plant will be submitted to NWB once it is built , which is expected sometimes in 2022.
Part F | Conditions Applying To Operation And Maintenance
F-1 | The Licensee shall submit to the Board, for approval in writing, within ninety (90) days of issuance of the Licence and prior to commissioning of the 2007 Sewage Disposal Facilities, a revised Operation and Maintenance Manual, Sewage Treatment System, Hamlet of Cape Dorset, November 7, 2007. The revision shall include the requirements of Schedule 2. | Not applicable any more because Hamlet has not used this lagoon and will not use in future. This lagoon has been abandoned. | The Feasibily Study of the Community wastewater Treatment system was completed. GN has decided to abandon the P-Lake Sewage Lagoon and build a new Wastewater Mechanical Treatment Plant. | A RFP is being advertised to Hire a consulting firm for detail design works and the preparation of Tender document for construction. | The O&M Manual will be developed once the new Plant construction is completed sometimes in 2022. | The Design of the new plant is expected to be completed in 2019, contruction completed in 2020 and the O&M will be developed following the as built drawings in 2022 as per the GN letter dated November 17,2016 to INAC.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
F-2 | The Licensee shall submit to the Board, for approval in writing, within ninety (90).days of issuance of the Licence, an Operation and Maintenance Manual for the Water Supply Facilities and the Solid Waste Disposal Facilities prepared in accordance with the “Guidelines for Preparing an Operation and Maintenance Manual for Sewage and Solid Waste Disposal Facilities”, October 1996. The Plan shall include a specific section addressing waste management and the proper diversion and segregation of wastes, the storage, transport and disposal of hazardous wastes materials | In Compliance | The O&M documents for the water supply and waste management were already submitted to NWB. | These manuals are kept as they are until these facilities are upgraded. | The O&M Manuals will be reviewed annually and revised if required in accordance to the criteria outlined in the issued water licence and submitted to the NWB. | Any Amendment to O&M Manuals to be submitted with the Annual Report if required prior to March 31st of the following year.
F-5 | An inspection of all engineered facilities related to the management of water and waste shall be carried out annually in July, by a Geotechnical Engineer in accordance with the Canadian Dam Association, Dam Safety Guidelines, November 2007, where applicable. This inspection shall include the access road alignment with respect to water resources and the diversion and passage of water through culverts. The engineer’s report shall be submitted to the Board within sixty (60) days of the inspection, including a covering letter from the Licensee outlining an implementation plan addressing each of the Engineer’s recommendations. | In Compliance. The P lake lagoon is an Engineered facility but has been abandoned. The waste management facilty and the existing lagoons are non-engineered facilities.However Hamlet submits annual report on time. | An inspection of facilities relating to the management of water and waste is being conducted by the Regional Engineer especially duing summer season annully alone or together with the INAC inspector. Issues and Concerns are reported in the Annual Report. | Development of a plan recommending capital improvements is being done along with Capital Planning staff each year. |  An inspection of facilities relating to the management of water and waste shall be carried out annually by the Municipal Engineer in accordance to the Canadian Dam Association, Dam Safety Guidelines.  An engineer’s report shall be prepared and submitted to the NWB along with the Hamlet annual report. |  Geotechnical inspection of the facility shall be carried out annually in July or August by the Regional Municipal Engineer.  The Engineer’s report shall be prepared and submitted to the NWB within sixty (60) days of the inspection,  Development of a plan recommending Capital improvements will follow the Engineer's recommendations.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part G | Conditions Applying to Abandonment, Restoration and Closure
G-1 | The Licensee shall submit to the board, for approval in writing, within 90 days of issuance of the License, a detailed Final Abandonment and Restoration Plan for the 2001 Sewage Disposal Facility and the Emergency Sewage Disposal Facility. The Plan should incorporate, where applicable, the appropriate sections as described in Part G item 2 | Non-Compliance | Initial plan was to commission of the P-Lake Seawge Lagoon and then decommisison of the existing lagoons. Since P lake lagoon can not be used, therefore the existing the three cells lagoon will be continued to using. | Maintain the existing sewage lagoons as best as spossible. | The abandonment and restoration of the existing lagoons will be on hold until the new wastewater mechnaical plan is built and commissioned. | The A&R Plan(s) shall be submitted to the NWB six (6) months prior to the planned decommissioning of Three Cell Lagoon and / or Emergency Lagoon. The future Consultant who will design the new Mechanical wastewater Treatemnt Plant & will develop an abandonment and restoration Plan at the same time by 2022.
G-2 | The Licensee shall submit to the Board, for approval in writing, within six (6) months of issuance of this Licence, a preliminary or conceptual Abandonment and Restoration Plan for the Hamlet of Cape Dorset, Water and Waste Disposal Facilities and all associated structures not covered under Part G, Item 1, with end objectives to return the site to pre-use conditions. | Non Compliance |  The GN will retain the services of a consultanting firm to assist with the preparation of A&R Plan.  The A&R Plan(s) shall be submitted to the NWB in accordance with the criteria as outlined in the issued water licence |  Scope of required plan will be assessed during site visit .  Follow up visit to gather technical information and include in the annual report. |  Annual review of need for A&R Plan, and revise if required including schedule for preparation  The A&R Plan(s) shall be submitted to the NWB in accordance with the criteria as outlined in the issued water licence. The future consultant will develop the A&R plan after completion of the design for the new wastewater Water Treatment plant. |  Submit all outstanding A&R Plans to the NWB in accordance with the criteria outlined in the issued water licence by 2022.  Amended A&R Plan identified as part of the Annual review will be submitted to the NWB in accordance with the criteria outlined in the issued water licence.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part H | Conditions Applying to the Monitoring Program
H-1 | The Licensee shall maintain Monitoring Program Stations at the SNP locations | In Compliance |  As part of the community visit by the past Consulant exp, a review of monitoring points were undertaken, including the presence or absence of signage. As part of exp’s mandate they prepared a tender document for procurement of the required signs with installation by Hamlet staff |  The site visit report by exp which identified deficiencies and signage for the monitoring sites were issued by March 31st, 2013.  Procurement of signage prior to June 30th, 2013 was done.  Signs were installed prior to August 31st, 2013 | Monitoring signs will be replaced in case any missing. | Annual inspections by GN staff will be continued to oversee the Hamlet's monitoring program.
H-6 | The Licensee shall install thermistors for the purpose of validating assumptions made in the geothermal analyses for the 2007 Sewage Disposal Facilities as recommended by the Geotechnical Engineer of record and agreed upon by the Licensee, subject to a minimum of three 20 to 25 metre deep thermistors installed in crest of the west berm and at least one thermistor of that depth in the east berm. | No application any more because the P lake lagoon has been abandoned and all the works related to thermistors were stopped. | This project is abandoned | No action is taken on the berm of the P Lake seawge Lagoon. | A New wastewater Mechanical Treatemnt Plant will be built there. | The new Wastewater Mechnaical Treatemnt Plant is expected to be built and commissioned sometimes in 2022.
H-7 | The results of thermistor monitoring required under Part H Item 6, shall be submitted to the Board for approval in writing prior to commissioning of the 2007 Sewage Disposal Facility. The results shall include an Engineer's Report, validating the assumptions of the geothermal analysis through adequate monitoring of the thermal regime for the east and west berms and downstream foundations. | Not applicable any more | Monitoring Program of Thermistors was stopped. | No action is currently taken on the berm of the P Lake Sewage Lagoon because this facility is declared abandoned. | This facility will be kept unuse. | Currently there is no plan to decommission. This facility was never commissioned.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
H-9 | The Licensee shall, within 90 days of issuance of the license, provide a Temperature Monitoring program and implementation Plan for on-going collection of ground temperatures within each berm structure and foundation of the 2007 Sewage Disposal Facility through the installation of thermisters. The Plan shall take into consideration the following (i through vi). | Not applicable any more | Temperature data collection from the thermistors were stopped long time ago. | No action | No action | No action