## Sheet1
Cape Dorset WL-3BM-CAP 0810
License Condition | Deliverables | Original due date | Due Date, as per Compliance Plan | Status of Compliance | Documented |  | General Comments
[5 empty] | on CIDMS (#) | On NWB ftp server (Y/N) |  | Present tustus
B2 | A monitoring program, which will include all sampling | 2008-03-07 | 2013-03-31 | Outstanding |  | N | Sampling has been included in the 2013 Annual Report. However, the sampling included is unacceptable because the sampling results do not correspond to any approved monitoring stations. This will have to be clarified for the 2013 sampling program and moving forward. All samples need to be clearly labeled. Also, given the number of samples provided, it does not appear that a full monitoring program was implemented. Provide appropriate clarification by April 14, 2014.
GN Comments: B13-19825: CAP-2-Leachate sample from dump site; B13-19822-Raw wastewater directly from the sewage truck-CAP-3, and B13-16710 for drinking water. | [7 empty] | The Monitoring stations are in order. The Test results
These samples were taken after signs were installed. Again, no sample was taken from CAP-5 because it is retained as the emergency ditch, sewage is not being dumped there every year. | [7 empty] | will be submitted with 2014 Annual report.
Sample was tested from CAP-4 in 2012. No water was found in CAP-17 and CAP-18. However, from 2014 summer on, samples will be restricted to each signed station with GPS coordinates
B5 | Posted Signs | 2008-11-16 | 2013-08-31 | Outstanding |  | N | Signs CAP-1, 2, 3, 4, 5 have been installed. Signs CAP-6 to 18 need to be installed when 2007 Sewage Facility is commissioned. Signs CAP-18 to CAP-24 are outstanding. | We need Monitoring stations only for the existing facilities.
GN Comments: All 24 signs are in the community. The rest of the signs will be installed once 2007 sewage lagoon is commissioned.
D8 | Conduct Acute Lethality Tests | 2009-03-31 | 2013-08-31 | Outstanding |  | N | The GN has not completed Acute Lethality tests to date. The GN claims that logistics are preventing them from achieving this. On February 10, 2014 a letter was submitted to the NWB explaining the issue. If the GN would like this condition removed, a formal amendment application will have to be filed. This item is still outstanding. Have this completed by April 10, 2014.
GN Comments: Working with NWB to delete this item from the Water Licence. This might be done after renewal of the licence as an amendment. Waiting for NWB direction on this. | [7 empty] | waiting for Board Direction.
D8 | Plan of Action | NA | 2013-07-01 | Outstanding |  | N | A plan of Action on how to commission the 2007 Sewage Lagoon has not been provided. In order to fulfill this criteria, it would require outlining specific timelines of the necessary steps required to commission the 2007 Sewage Facility. This will remain outstanding until a Formal Plan is submitted.
GN Comments: We will conduct a feasibility study in summer and will submit a detailed plan of action by October 30,2014. | [7 empty] | Working with the consultant Stantec and waiting for the
inspection report.
F1 | O&M Manual for 2001 Sewage Treatment System | 2008-06-07 | 2014-07-01 | Outstanding |  | N | The exp report has stated that an O&M Manual for the 2001 Sewage Disposal Facility has been prepared but it does not meet the requirements of the water licence. This is to be completed by July 1, 2014. | Submitted.
GN Comments: The O&M manual will be submitted by July 1, 2014
F2 | O&M Manual for Solid Waste Disposal Facilities | 2008-06-07 | 2014-07-01 | Awaiting Submission |  | N | GNs states that this O&M is not prepared and they are waiting for a new project. It is not clear what this new project is and regardless, this is an unacceptable reason for delay. This report was supposed to be submitted on June 7, 2008. The Solid Waste Disposal Facility needs an O&M Manual. This is to be completed by July 1, 2014. | Submitted
GN Comments: The O&M manual will be submitted by July 1,2014
F5 | Development of a Plan recommending Capital Improvements | NA | 2014-03-31 | Outstanding |  | N | The GN states that, "A Study will be completed in the summer of 2014 to identify the root cause of the failure of the Cape Dorset sewage lagoon. Once the root cause has been identified, the solution will be placed on to the Capital Plan for GN funding." What is the progress of this study? Has a consultant been hired? | The consltant Stantec is on board.Waiting for the report.
GN Comments: Once the consultant is hired, AANDC will be notified.
G1 | Detailed A&R for 2001 Sewage Lagoon | 2008-06-07 | 2014-02-28 | Outstanding |  | N | GN states, "A&R plan will be ready once 2007 built lagoon is commissioned." This is unacceptable. The A&R Plan was supposed to be submitted June 7, 2008. This plan is 6 years overdue and is a requirement of the licence. This item will remain outstanding until submitted, further enforcement action may result if further delays. | Will be ready by December 31.2014.
GN Comments: The A&R plan will be submitted by July 1,2014.
G1 | Detailed Emergency Sewage Disposal facility | 2008-06-07 | 2014-02-28 | Outstanding |  | N | GN states, "A&R plan will be ready once 2007 built lagoon is commissioned." This is unacceptable. The A&R Plan was supposed to be submitted June 7, 2008. This plan is 6 years overdue and is a requirement of the licence. This item will remain outstanding until submitted. | Will be submitted by December 31,2014
GN Comments: The A&R Plan will be submitted by July 1,2014.
G2 | Conceptual A&R for all facilities not covered under G1 | 2008-09-08 | 2014-02-28 | Outstanding |  | N | This is still outstanding and was due 6 months after the issuing of the license. What is the status of these Conceptual A&R Plans. | Will be submitted by December 31,2014 for solidwaste.
GN Comments: The Conceptional/Generic A&R Plan will be submitted by July 1,2014.
H1 | Posted Signs | 2008-11-16 | 2013-08-31 | Outstanding |  | N | See B2. | Monitoring signs were installed. Facilities signs will be ready by December 2015.
GN Comments: Will be followed as mentioned in B2.
H6 | Have appropriate thermistors | Friday, March 07, 2008 | 2014-09-15 | Awaiting Submission |  | N | A letter was sent to NWB by GN informing them that they would like to amend this section of the licence. This is not an amendment application. Until this is completed or appropriate thermistors are installed, this remain outstanding.
GN Comments: Working with NWB. The amendment from 25m to 18.8m depth might be done after issuing the licence. Waiting for direction from NWB. We want to get the licence renewed ASAP. | [7 empty] | Amendemnt is requested at the same time of renewal
the water Licence.