## Cape Dorset
License Condition | Deliverables | Original due date | Due Date, as per Compliance Plan | Status of Compliance | Documented |  | General Comments
[5 empty] | on CIDMS (#) | On NWB ftp server (Y/N)
B1 | 2004 Annual Report | 2005-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2005 Annual Report | 2006-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2006 Annual Report | 2007-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2007 Annual Report | 2008-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2008 Annual Report | 2009-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2009 Annual Report | 2010-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2010 Annual Report | 2011-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2011 Annual Report | 2012-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2012 Annual Report | 2013-03-31 | 2013-03-31 | Fulfilled |  | Y
B1 | 2013 Annual Report | 2014-03-31 | 2014-03-31 | Fulfilled | On USB
B1/B2 | exp report | 2013-03-31 | 2013-03-31 | Fulfilled | 777015
B2 | Action Plan including QA/QC Protocols | NA | 2013-08-31 | Fulfilled |  | Y | GN said this was submitted with renewal application. Please provide a copy to the AANDC Inspector.
B2 | Training Program Report | NA | 2013-08-31 | Fulfilled |  | Y | Available on NWB ftp server, in Application -> 2011 Renewal Revised
B2 | A monitoring program, which will include all sampling | 2008-03-07 | 2013-03-31 | Outstanding |  | N | Sampling has been included in the 2013 Annual Report. However, the sampling included is unacceptable because the sampling results do not correspond to any approved monitoring stations. This will have to be clarified for the 2013 sampling program and moving forward. All samples need to be clearly labeled. Also, given the number of samples provided, it does not appear that a full monitoring program was implemented. Provide appropriate clarification by April 14, 2014.
B5 | Posted Signs | 2008-11-16 | 2013-08-31 | Outstanding |  | N | Signs CAP-1, 2, 3, 4, 5 have been installed. Signs CAP-6 to 18 need to be installed when 2007 Sewage Facility is commissioned. Signs CAP-18 to CAP-24 are outstanding.
B6 | Plan for Compliance | 2008-06-07 | On-Going | Fulfilled |  |  | Currently in Hard Copy in File
D8 | Conduct Acute Lethality Tests | 2009-03-31 | 2013-08-31 | Outstanding |  | N | The GN has not completed Acute Lethality tests to date. The GN claims that logistics are preventing them from achieving this. On February 10, 2014 a letter was submitted to the NWB explaining the issue. If the GN would like this condition removed, a formal amendment application will have to be filed. This item is still outstanding. Have this completed by April 10, 2014.
D8 | Plan of Action | NA | 2013-07-01 | Outstanding |  | N | A plan of Action on how to commission the 2007 Sewage Lagoon has not been provided. In order to fulfill this criteria, it would require outlining specific timelines of the necessary steps required to commission the 2007 Sewage Facility. This will remain outstanding until a Formal Plan is submitted.
E5 | Provide Summary Report and as-builts for 2007 Sewage Disposal Facility | 2008-05-07 | 2014-01-31 | Fulfilled |  | Y
F1 | exp Report on status of O&M Manuals | NA | 2013-03-31 | Fulfilled |  | Y
F1 | O&M Manual for 2001 Sewage Treatment System | 2008-06-07 | 2014-07-01 | Outstanding |  | N | The exp report has stated that an O&M Manual for the 2001 Sewage Disposal Facility has been prepared but it does not meet the requirements of the water licence. This is to be completed by July 1, 2014.
F1 | Geotechnical Inspection | NA | 2013-09-01 | Fulfilled for 2013 |  | Y | It's called 'Dam Safety Review' on the ftp
F2 | O&M Manual for Water Supply Facilities | 2008-06-07 | 2014-07-01 | Awaiting Submission |  | Y | This document was recently submitted to AANDC.
F2 | O&M Manual for Solid Waste Disposal Facilities | 2008-06-07 | 2014-07-01 | Awaiting Submission |  | N | GNs states that this O&M is not prepared and they are waiting for a new project. It is not clear what this new project is and regardless, this is an unacceptable reason for delay. This report was supposed to be submitted on June 7, 2008. The Solid Waste Disposal Facility needs an O&M Manual. This is to be completed by July 1, 2014.
F5 | Geotechnical Inspection of all engineered facilities | 2008-09-30 | 2013-11-01 | Fulfilled for 2013 |  | Y | It's called Dam Safety Review on the ftp
F5 | Development of a Plan recommending Capital Improvements | NA | 2014-03-31 | Outstanding |  | N | The GN states that, "A Study will be completed in the summer of 2014 to idenify the root cause of the failure of the Cape Dorset sewage lagoon. Once the root cause has been identified, the solution will be placed on to the Capital Plan for GN funding." What is the progress of this study? Has a consultant been hired?
G1 | Detailed A&R for 2001 Sewage Lagoon | 2008-06-07 | 2014-02-28 | Outstanding |  | N | GN states, "A&R plan will be ready once 2007 built lagoon is commissioned." This is unacceptable. The A&R Plan was supposed to be submitted June 7, 2008. This plan is 6 years overdue and is a requirement of the licence. This item will remain outstanding until submitted, further enforcement action may result if further delays.
G1 | Detailed Emergency Sewage Disposal facility | 2008-06-07 | 2014-02-28 | Outstanding |  | N | GN states, "A&R plan will be ready once 2007 built lagoon is commissioned." This is unacceptable. The A&R Plan was supposed to be submitted June 7, 2008. This plan is 6 years overdue and is a requirement of the licence. This item will remain outstanding until submitted.
G2 | Conceptual A&R for all facilities not covered under G1 | 2008-09-08 | 2014-02-28 | Outstanding |  | N | This is still outstanding and was due 6 months after the issuing of the license. What is the status of these Conceptual A&R Plans.
H1 | Posted Signs | 2008-11-16 | 2013-08-31 | Outstanding |  | N | See B2.
H6 | Provide report on thermistors | NA | 2013-03-31 | Fulfilled |  | Y
H6 | Apply for Amendment to NWB to change depth of Thermistors | NA | 2013-06-01 | Fulfilled |  | N | A letter was sent to NWB by GN informing them that they would like to amend this section of the licence. This is not an amendment application. Until this is completed, this remain outstanding.
H6 | Have appropriate thermistors | Friday, March 07, 2008 | September 15, 2014 | Awaiting Submission |  | N | A letter was sent to NWB by GN informing them that they would like to amend this section of the licence. This is not an amendment application. Until this is completed or appropriate thermistors are installed, this remain outstanding.
H7 | Engineer's Report on thermistor monitoring | Before commissioning of 2007 Sewage Disposal Facility | Before commissioning of 2007 Sewage Disposal Facility | Awaiting Submission
H9 | Temperature Monitoring Program and Implementation Plan | Saturday, June 07, 2008 |  | Fulfilled |  | Y | This plan is contained within the Sewage Treatment Plant O&M on the NWB ftp server
H9 | Assessment of Existing Thermo-Data | NA | September 30, 2013 | Fulfilled |  | Y | This is a requirement of the Compliance Plan
Hamlet of Cape Dorset