## Gjoa Haven
License Condition | Deliverables | Original due date | Due Date, as per Compliance Plan | Status of Compliance | Documented |  | General Comments
[5 empty] | on CIDMS (#) | On NWB ftp server (Y/N)
B1 | Annual Report 2004 | 2005-03-31 | none | outstanding
B1 | Annual Report 2005 | 2006-03-31 | none | outstanding
B1 | Annual Report 2006 | 2007-03-31 | 2013-03-31 | Fulfilled |  | Y
B1 | Annual Report 2007 | 2008-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2008 | 2009-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2009 | 2010-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2010 | 2011-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2011 | 2012-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2012 | 2014-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | Annual Report 2013 | 2014-03-31 | 2014-03-31 | outstanding
B1/B2 | exp report | 2013-03-31 | 2013-03-31 | Fulfilled |  | Y | Available at AANDC
B2 | Training Program Report | NA | 2013-08-31 |  |  | Y
B2 | A monitoring program, which will include all sampling |  | 2013-03-31 | Outstanding |  |  | The 2013 Annual Report has not been submitted. Sampling results as stipulated in Part H were to be included.
B11 | Plan for Compliance |  | Ongoing | Ongoing
B2 | Action Plan including QA/QC Protocols |  | 2013-08-31 | Fulfilled
B5 | Posted Signs |  | 2013-08-31 | Outstanding |  |  | Require photo evidence or Inspector to verify. Outstanding as of 2013 Inspection.
B9 | Exp report on status of outstanding reports |  | 2013-05-31 | Outstanding
D3 | Maintain freeboard limit of 1.0m at sewage disposal facility |  | Since beginning of license | Outstanding |  |  | The new wastewater treatment facility that is currently under construction will address this. What is the plan of commissioning for this facility.
D5 | Geotechnical Report by Engineer of Sewage Disposal Facility |  |  | Fulfilled
D5 | Development of a Plan recommending Capital Improvements |  | 2014-03-31 | Outstanding
D7 | Actioning operational recommendations |  | 2013-10-31 | Outstanding |  |  | GN says, "Seperation/segregation of hazardous waste materials started in Summer 2012 and will be continued summer 2014 & 2015. KBL has been retained for assessment of hazardous waste materials in 2013 and looking into budget to implement the hazardous clean up." Since hazardous waste clean-up has not occured, this is still outstanding.
D7 | Develop new Municipal Solid Waste Strategy |  | 2014-07-31 | Outstanding
D8 | A report identifying final discharge point |  | 2013-06-01 | Outstanding |  |  | AANDC has not received the final discharge report
F1 | O&M Manual for old sewage lagoon |  | 2014-07-01 | Fulfilled
F1 | O&M Manual for solid waste facility |  | 2014-07-02 | Fulfilled
F1 | O&M Manual for new sewage lagoon |  | 2014-07-03 | Outstanding
G1 | A&R Plan for New Sewage Lagoon |  | 2015-10-01
G1 | A&R Plan for existing lagoon |  | 2014-07-31
Part H | Submit all conditions related to monitoring program |  | 2014-03-31 | March 31, 2014