## Table 1
Municipality of Hall Beach
PLAN FOR COMPLIANCE LICENCE NO. 3BM-HAL1520
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
| The Hamlet must maintain a valid Water Licence | The Hamlet’s Water Licence will expire on April 29,2020. | The GN-CGS has initiated the water licence renewal process on behalf of the Hamlet | The water Licence renewal process has been started |  Prior to expiration of future water licence ,the GN will initiate the renewal of the future water licence on behalf of the Hamlet  The GN and the Hamlet commit to ongoing compliance with the Nunavut Waters Act and maintaining a water licence | In normal situation, The water licence renewal process will be started minimum 6 months prior to expiration of the active licence renewal
Part B | General Conditions
B-1 | The Licensee shall file an Annual Report with the Board not later than March 31 of the year following the calendar year reported which shall contain the following information: | In Compliance | The GN will ensure the community submit to the NWB the Annual Report, in accordance with the criteria outlined in the issued water licence. | The GN will ensure that the Hamlet record all the activities carried out for all the water licensed facilities under their water licence during the reporting year. |  GN will monitor to ensure the Hamlet submits their Annual Report to the NWB, in accordance with the criteria outlined in the issued water licence  GN monitoring will include weekly checks of the Hamlet’s log sheets, along with monthly Regional water committee meeting to discuss and action any issues. | The Regional Municipal Engineer will train the Hamlet foreman gradually how to write Annual Report and submit to NWB on time. This training will be conducted during Community visit for the infrastructure inspection once or twice annually.
B-a | tabular summaries of all data generated under the "Monitoring Program"; | In Compliance | The Process will continue | The Process will continue | The Process will continue | The Process will continue
B-b | the monthly and annual quantities in cubic meters of fresh Water obtained at the Water Supply Facility; | Only Leachate | Continue as it is | Continue as it is | Continue as it is | Continue as it is
B-c | the monthly and annual quantities in cubic metres of each and all waste discharged;
B-d | a summary of modifications and/or major maintenance carried out on the Water Supply Facility, Sewage Disposal Facility and Solid Waste Disposal Facility, including all associated structures and facilities; | No modification and /or major maintenance was needed. | The facility will be used as it is condition | Continue to Use | The new site has been identified for solid waste management | The new site will be designed , built and commissioned , anticipated in next 3 yrs.
B-e | a list of unauthorized discharges and summary of follow up action taken; | Non Compliance. Leachate is uncontrolled. | This will continue as it is. | Leachate is naturally treated prior to discharge to the sea. | This process will be continued | This process will be continued until the new facility is built and commissioned, anticipated in next 3 yrs.
B-f | A summary of any abandonment and restoration work completed during the year and an outline of any work anticipated for the next year; | Not applicable | Not applicable | Not applicable | Not applicable | The existing waste sites will be abandoned once the new facility is built and commissioned, anticipated in next 3yrs.
B-g | Any updates or revisions for manuals and plans (Including Operations and Maintenance Plans, Spills Contingency, Abandonment and Restoration, QA/QC) as required by changes in operation and/or technology; | Nil | Nil | Nil | Nil | The manual will be only updated and revised for the operation of the new facilities.
B-h | a summary of any studies, reports and plans requested by the Board that relate to Waste disposal or reclamation, and a brief description of any future studies planned; | The feasibility study is in progress | The document is under review | The document review will be completed within two months. | The next step is to start design works | The construction is anticipated in next 3 yrs.
B-i | any other details on Waste disposal requested by the Board by November 1st of the year being reported. | Segregation of hazardous wastes | In progress | In progress | In progress | The hazardous waste will be managed in a separate cell in the new facility.
B-2 | The Licensee shall comply with the "Monitoring Program" described in this Licence, and any amendments to the "Monitoring Program" as may be made from time to time, pursuant to the conditions of this Licence. | In Compliance. Hamlet is currently following the Monitoring program of the existing facilities. | This QA/QC Plan which meets the requirements of Monitoring Program described in Part H of the water licence. The QA/QC Plan was already submitted to NWB. | Monitoring is being implemented during winter and summer seasons as described in the QA/QC Plan. |  Regional Municipal Engineer will continue to train the Hamlet staffs once or twice a year. Also develop a training plan for a TRAIN THE TRAINER for GN staff to develop resources within the GN to allow for ongoing training of Hamlet Staff.  The GN has created a central data base for all reports to be held and accessible to GN staff for review and action. |  All sampling and testing data will be kept in the Regional office in Pond Inlet and CGS head office in Iqaluit.  The TRAIN THE TRAINER program will be continued.
B-3 | The "Monitoring Program" and compliance dates specified in the Licence may be modified at the discretion of the Board. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
B-4 | Meters, devices or other such methods used for measuring the volumes of water used and waste discharged shall be installed, operated and maintained by the Licensee. | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
B-5 | The Licensee shall, within ninety (90) days after the first visit by the Inspector following issuance of this Licence, post the necessary signs to identify the stations of the "Monitoring Program". All signage postings shall be in the Official Languages of Nunavut. | In compliance. Leachate sampling stations have been established already. | Monitoring stations were already established with Co-ordinates. Signs were installed as per the requirements of the Water licence. | These Monitoring stations will be maintained. | Each summer inspection, the monitoring stations will be inspected. And the missing signs will be reinstalled. | The missing signs will be reinstalled prior to the summer sampling .
B-6 | The Licensee shall immediately report to the 24 hour Spill Report Line (867) 920-8130 any spills of Waste, which are reported to, or observed by the Licensee, within the municipal boundaries or in the areas of the Water Supply or Waste Disposal Facilities | In compliance | Will be Maintained | Will be Maintained | Will be maintained | Will be maintained
B-7 | The Licensee shall ensure a copy of this Licence is maintained at the site of operations at all times. Any communication with respect to this Licence shall be made in writing to the attention of: See WL 3BM-HAL 1520 | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
B-8 | The Licensee shall submit one paper copy and one electronic copy of all reports, studies, and plans to the Board. Reports or studiessubmitted to the Board by the Licensee shall include a detailed executive summary in Inuktitut. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-9 | The Licensee shall ensure that all documents and correspondence submitted by the Licensee to the Board are received and acknowledge by the Manager of Licensing. | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed
B-10 | The Licensee shall, for all Plans submitted under this Licence, include a proposed timetable for implementation. Plans submitted, cannot be undertaken without subsequent written Board approval and direction. The Board may alter or modify a Plan if necessary to achieve the legislation objectives and will notify the License in writing of aceptance, rejection or alteration of the Plan. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-11 | The Licensee shall, for all Plans submitted under this Licence, implement the Plan as approved by the Board in writing. | Will be done as directed | Available for the Public | A copy is available always at the front desk | Always keep the Licence available at the front desk for the Public | A copy will be kept available always at the front desk.
B-12 | Every Plan to be carreied out persuant to the terms and conditions of this Licence shall become a part of this Licence, and any additional terms and condition imposed upon approval of a Plan by the Board become part of this Licence. All terms and conditions of the Licence should be contemplated in the development of a Plan where appropriate. | Same a site B-11
B-13 | This Licensee is not assignable except as provided in Section 44 of the Act. | In compliance | always done | continue | Will be continued | Will be continued
Part C: | CONDITIONS APPLYING TO WATER USE
C-1 | The Licensee shall obtain all fresh water processed by Water Treatment Facility and/or used for puposes under this licence fromWater Supply Lake as described in the Application. The total volume of water for all purposes under this licence shall not exceed thirty-five thousand (35,000) cubic metres per year and two and ninety nine (299) cubic metres per day. | In compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
C-2 | The Licensee shall equip all water intake hoses with a screen of an appropriate mesh size to ensure that fish are not entrained and shall withdraw water at a rate such that fish do not become impinged on the screen. | In compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
C-3 | The Licensee shall not remove any material from below the ordinary High Water Mark of any water body unless otherwise approved by the Board in writing. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
C-4 | The Licensee shall not cause erosion to the banks of any body of water and shall provide necessary controls to prevent such erosion. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
C-5 | Sediment and erosion control measures shall be implemented prior to and maintained during the operation to prevent entry of sediment into water. | In Compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
Part D: | CONDITIONS APPLYING TO WASTE DISPOSAL
D-1 | The Licensee shall direct all Sewage to the Sewage Disposal Facility or as otherwise approved by the Board in writing. | In compliance | All the different types of wastes are contained within the solid waste sites | will be continued | will be continued | will be continued
D-2 | The Licensee shall provide notice to an Inspector annually when flow is observed from the Sewage Disposal Facility and upon commencing the Monitoring Program at Monitoring Station HAL-4. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-3 | All effluent discharged from the Sewage Disposal Facility at Monitoring Station HAL-4 shall meet the following effluent quality standards: SEE WL 3BM-HAL1520 | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-4 | The Licensee shall maintain at all times, a freeboard of at least 1.0 metre, or as recommended by a qualified geotechnical engineer and as approved by the Board in writing, for all dams, dykes or other structures intended to contain, withhold, divert, or retain water or wastes. | In compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
D-5 | The Sewage Disposal Facility shall be maintained and operated in such a manner as to perevent structural failure. | Non complinace | The Sewage Lagoon cell -1 is still leaking | A consultant has been hired to address this issue | Repairing is expected to be done in summer | Will be fixed in 2020.
D-6 | All Effluent discharged from the Sewage Disposal Facility, shall be demonstrated to be Not Acutely Toxic at Monitoring Station HAL-5 prior to entering Foxe Basi, under the following tests to be conducted once annually approximately midway through discharge: a) Acute lethality to Rainbow Trout, Oncorhynchus mykiss (as per Environment Canada's Environmental Protection Series Biological Test Method EPS/1/RM/14); b) Acute lethality to the crustacean, Daphnia magna (as per Envirnoment Canada's Environmental Protection Series Biological Test Method EPS/1/RM/14). | Non Compliance | For seawge lagoon effluent, this test is not being conducted following the discussion with CIRNAC inspector | No further action is required | No further action is required | No further action is required
D-7 | The Licensee shall dispose of and contain all solid wastes at the Solid Waste Disposal Facility or as otherwise approved by the Board in writing. | In compliance | Will be maintained | Will be maintained | Will be maintained | A new solid waste facility is expected in next 3 to 5 yrs.
D-8 | The Licensee shall segregate and store all hazardous materials and/or hazardous waste within the Solid Waste Disposal Facility in a manner as to prevent the deposit of deleterious substance into any Water, until such a time as proper disposal arrangements are made. | In compliance | Will be maintained | Will be maintained and stored in the Sea Can. | Will be maintained | A new solid waste facility is expected in next 3 to 5 yrs.
D-9 | The Licensee shall implement measures to control wind blown litter at the Solid Waste Disposal Facility. | In compliance | The site is fenced. The garbage is burned and covered in every now nad then during summer. | Will be continued | Will be continued | A new solid waste facility is expected in next 3 to 5 yrs. A better management is expected at that time.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part E: | CONDITIONS APPLYING TO MODIFICATIONS AND CONSTRUCTION
E-1 | The Licensee shall submit to the Board for approval in writing, for-construction design drawings, stamped and signed by a qualified Engineer registered in Nunavut, prior to the construction of any dams, dykes or structures intended to contain, withhold, divert or retain water or Waste. | In compliance | This protocol will be followed | This protocol will be followed | This protocol will be managed | This protocol will be managed
E-2 | The Licensee may, without written consent from the Board, carry out Modifications to theWater Supply and Waste Disposal Facilities provided that such Modifications are consistent with the terms of this Licence and the following requirements are met: | In compliance | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed
E-2 a | the Licensee has notified the Board in writing of such proposed Modifications at least sixty (60) days prior to beginning the Modifications; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 b | such Modifications do not place the Licensee in contravention of the Licence or the Act; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 c | the Board has not, during the sixty (60) days following notification of the proposed Modifications, informed the Licensee that review of the proposal will require more then sixty (60) days; and | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-2 d | the Board has not rejected the proposed Modifications. | NA | NA | NA | NA | NA
E-3 | The Modifications for which all of the conditions referred to in Part E, Item 2, have not been met, may only be carried out upon written approval from the Board. The Licensee shall provide as-built plans and drawings of the Modifications referred to in this LIcence within ninety (90) days of completion of the Modification. These plans and drawings shall be stamped by and Engineer. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-4 | All activities shall be conducted in such a way as to minimize impacts on surface drainage and the Licensee shall immediately undertake any corrective measures in the event of any impacts on surface drainage. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
E-5 | The Licensee shall implement and maintain sediment and erosion control measures prior to and during activities carried out under this Part, to prevent negative impacts to Water resulting from the release of sediment and to minimize erosion. | In Compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
Part F: | CONDITIONS APPLYING TO OPERATION AND MAINTENANCE
F-1 | The Board has approved the manual entitled Hamlet of Hall Beach, Sewage Treatment Facility Operation and Maintenance Manual, dated June 2011, which was submitted as additional information in support of the Application. | In compliance | Will be followed | Will be followed | The new facility has its own O&M manual | This manual will be prepared once the new facility is constructed and it is expected in next 3 to 5 yrs.
F-2 | The Board has approved the manual entitled Hamlet of Hall Beach, NU, Solid Waste Facility Operationa and Maintenance Manual, dated June 2011, submitted as additional information in support of the Application. | In compliance | The feasibility study of the waste management for this Community is completed | The new site has been selected | The design works will be started soon | The construction of the solid wasre site is anticipated in next 3 to 5 yrs.
F-3 | The Licensee shall submit to the Board for approval, within ninety (90) following issuance of the Licence, an Operations and Maintenance Manual for the Water Supply Facility developed in accordance with applicable guidelines. | In Compliance | The current manual is being used | The current manual of the non engineered solid wastes sites is being used | The new manual will be developed for the future engineered facilities | The new manual will be available in next 3 yrs.
F-4 | The Board has approved the plan entitled Hamlet of Hall Beach, NU, Spill Contingency Plan, Sewage Treatment and Solid Waste Sites, dated June 2011, which was submitted as additional information in support of the Application. The Licensee shall review the plans and/or technology and modify the documents accordingly. Revisions are to be submitted in the form of Addendums to be included with the Annual Report. | In Compliance | Will be followed | Will be followed | Will be followed | The SCP will be modified as and when required
F-5 | The Licensee shall arrange for inspections to be conducted by an appropriate Engineer, at least once annually, of all engineered structures or facilities designed to contain, withhold, divert, or retain Water or Waste, during the summer months (July/August) and/or during periods of flow. An Engineer's report shall be submitted to the Board within sixty (60) days of the date inspection, including a cover letter from the Licensee outlining an implementation plan to address each of the Engineer's recommendations. | In compliance | Municipal Engineer joins with CIRNAC inspector to conduct annual inspection to all the licensed facilities. | Will be continued | Will be continued | Will be continued
F-6 | An inspection of all engineered facilities related to the management of Waste shall be carried out by an Engineer at a minimum of once annually following spring freshette and during open water conditions in order to detect flow from the Solid Waste Facilities and, before commissioning any engineered facility related to the management of Waste. The Engineer's report shall be submitted to the Board within sixty (60) days of the inspection, including a cover letter from the Licensee outlining an implementation plan to address each of the Engineer's recommendations. | In compliance. | Leachate flow ways and location of sampling leachate are identifed by a Sign and with coordinates | Will be maintained | Will be maintained | Will be maintained
F-7 | The Licensee shall perform more frequent inspections of the engineered facilities at the request of an Inspector. | In Complaince | Municipal Engineer inspect the licensed facilities more than one time a year. | Municipal Engineer inspect the licensed facilities more than one time a year. | Municipal Engineer inspect the licensed facilities more than one time a year. | Municipal Engineer inspect the licensed facilities more than one time a year.
F-8 | If during the period of this Licence, an unauthorized discharge of Waste occurs, or if such a discharge is foreseeable, the Licensee shall:
F-8a | employ the appropriate contingency measures as approved under the Spill Contingency Plan; | In compliance | CIRNAC inspector and Regional Engineer inspects these facilities at least once a year. | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-8b | report the incident immediately via the 24-Hour Spill Reporting Line at (867) 920-8130 and to the Inspector at (867) 975-4295; and | In compliance | The Municipal Engineer visits these facilities minimum twice a year as required | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-8c | submit to the Inspector , a detailed report on each occurance, not later than thirty (30) days after initially reporting the event , that provides the necessary information on the location (including the GPS coordinates), initial response action, remedation/cleanup, status of response (ongoing, complete), proposed disposal options for dealing with contaminated materials and preventative measures to be implemented. | In compliance. | If it is happened in future, the items F-8a, F-8b, F-8c will be followed. | Working forward | Working forward | Working forward
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part G: | Conditions Applying to Abandonment, Restoration and Temporary Closing
G-1 | The Licensee shall submit to the Board for approval an Abandonment and Restoration Plan at least six (6) months prior to abandoning any facilities or upon submission of the final design drawings for the construction of new facilities to replace existing ones. Where applicable, the Planshall include information on the following: | In compliance | No A&R plan needs to be implemented now. | No A&R plan needs to be implemented now. | Once the new facility is commissioned, the existing waste facilities will be planned to be decommissioned. | It is anticipated in next 3 yrs.
G-1a | water intake facilities; | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
G-1b | the water treatment and waste disposal sites and facilities; | In Compliance | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed
G-1c | petroleum and chemical storage areas; | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-1d | any site affected by waste spills; | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-1e | leachate prevention; | In Compliance | This process of remediation has not yet started | This process of remediation has not yet started | This is expected to be addressed in next 3 yrs. | This is expected to be addressed in next 3 yrs. Once the new facility is operational.
G-1f | an implementation schedule; | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1g | maps delineating all disturbed areas, and site facilities; | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1h | consideration of altered drainage patterns; | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1i | type and source of cover materials; | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1j | future area use; | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1k | hazardous wastes; and | Not know yet | Not applicable | Not applicable | Not applicable | Once scheduled, the NWB will be notified.
G-1l | a proposal identifying measures by which restoration costs will be financed by the Licensee upon abandonment. | Not know yet | Will be followed | Will be followed | Will be followed | Yes, GN and the licensee will finance this project once ready.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part H | Conditions Applying to the Monitoring Program
H-1 | The Licensee shall maintain Monitoring Stations at the following locations: See WL 3BM-HAL1520 | In Compliance | The monitoring stations are being maintained correctly. | Will be maintained | Will be maintained | Will be maintained
H-2 | The Licensee shall sample at Monitoring Program Stations HAL-4 and HAL-5 upon providing notice to the inspector and every four weeks there after when flow is observed. Samples shall be analyzed for the following parameters: See WL 3BM-HAL1520 | In Compliance | The GPS coordinates will be maintained | The GPS coordinates will be maintained | The GPS coordinates will be maintained | The GPS coordinates will be maintained
H-3 | The Licensee shall sample at Monitoring Program Staion HAL-2 once annually during periods of runoff or seepage. Samples shall be analyzed for the following parameters: See WL 3BM-HAL1520 | In Compliance | The sign and coordinates are maintained | Will be continued | Will be continued | Will be Continued
H-4 | The Licensee shall report all results of acute toxicity testing as required under Part D, Item 6 and the results of monitoring required under Part H, Items 2 and 3 within the Annual report as per Part b, Item 1. | Non Compliance. Leachate is uncontrolled. | No plan to control leachate | No plan to control leachate | Will be continued as it is. | Will be continued as it is
H-5 | The Licensee shall measure and record, in cubic metres, the monthly and annual quantities of Water pumped at Monitoring Program Station HAL-3, for all purposes. | In compliance | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is
H-6 | The Licensee shall measure and record, in cubic metres, the monthly and annual quantities of Water pumped at Monitoring Program Station HAL-3, for all purposes. | In compliance. Consumption volume is considred as the extraction volume. | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is
H-7 | The Licensee shall measure and record the annual quantities of any sewage solids removed from the Sewage Disposal Facility, in accordance with detailed protocol for monitoring quantities of sewge sludge removed from the Sewage Disposal Facility included the Hamlet of Hall Beach, NU Sewage Treatment Operations and Maintenance Manual, dated June 2011. | In compliance. Water consumption volume is considered as the sewage disposal volume. | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
H-8 | The Licensee shall include all of the data and information required by the "Monitoring Program" in the Licence's Annual Report, as required per Part B, Item 1, or as requested by an Inspector. | In compliance | This process will be continued | This process will be continued | This process will be continued | This process will be continued
H-9 | Modifications to the Monitoring Program may be made only upon written approval from the NWB. | In Compliance | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged
H-10 | If additional Final Discharge Points are identified during the term of this Licence, the Licensee shall submit a report to include: a. Plans, specifications, geographic coordinates and a general description of each Final Discharge Point; and | not required yet. If yes, this instruction will be followed. | Will be followed | Will be followed | Will be followed | Will be followed
H-11 | All sampling, sample preservation and analyses shall be conducted in accordance with methods prescribed in the current edition of Standard Methods for the Examination of Water and Wastewater, or by such other methods approved by the Board in writing. | In complianace | Will be maintained | Will be maintained | Will be mainatined | Will be mainatined
H-12 | All analyses shall be performed by a laboratory certified by the Canadian Association of Environment Analytical Laboratories (CAEAL), or as otherwise approved by an Analyst. | In compliance. Caduceon Lab is an accredited Lab. | Will be maintianed | Will be maintained | Will be maintained | Will be maintained
H-13 | The Board has accepted the plan entitled Hamlet of Hall Beach Quality Assurance/ Quality Control Plan, dated August 15, 2013, which was submitted as additional informationin support of the Application. | In Complaince | Will be followed | Will be followed | Will be followed | Will be followed
H-14 | The Licensee shall review the plans, referred to in Part H, Items 13, as required by changes in operation and/or technology and modify accordingly. Revisions including a cover letter indicating that changes are acceptable to an Analyst are to be submitted in the form of an Addendum to be included with the Annual Report. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed