## Hall Beach
License Condition | Deliverables | Original due date | Due Date, as per Compliance Plan | Status of Compliance | Documented |  | General Comments
[5 empty] | on CIDMS (#) | On NWB ftp server (Y/N)
B1 | 2007 Annual Report | 2008-03-31 | 2014-03-31 | Fulfilled | on USB
B1 | 2008 Annual Report | 2009-03-31 | 2014-03-31 | Fulfilled | on USB
B1 | 2009 Annual Report | 2010-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2010 Annual Report | 2011-03-31 | 2014-03-31 | Fulfilled | on USB
B1 | 2011 Annual Report | 2012-03-31 | 2014-03-31 | Fulfilled |  | Y
B1 | 2012 Annual Report | 2013-03-31 | 2013-03-31 | Fulfilled |  | Y
B1 | 2013 Annual Report | 2014-03-31 | 2014-03-31 | Fulfilled |  | Y
B1/B2 | exp report | 2013-03-31 | 2013-03-31 | Fulfilled | 777017 |  | Available in CIDMS.
B2 | Action Plan including QA/QC Protocols | NA | 2013-08-31 | Fulfilled | on USB |  | Due as part of Compliance Plan. GN said this was submitted with renewal application on June 1, 2013
B2 | Training Program Report | NA | 2013-08-31 | Fulfilled |  | Y
B2 | A monitoring program, which will include all sampling | 2008-05-16 | 2013-03-31 | Outstanding |  |  | Four samples were conducted and this information is attached to the 2013 Annual Report. The sampling program completed in 2013 is unacceptable because sampling results do not correspond to any monitoring stations. This will have to be clarified for the 2013 sampling as well moving forward, all samples need to be clearly labelled.
B5 | Posted Signs | 2008-08-16 | 2013-08-31 | Outstanding |  |  | Photos were submitted for HAL-1, 2 and 3a. However, 3a is not an approved site and photos of HAL-4 and 5 were not provided. Provide appropriate documentation by April 10, 2014.
B10 | Plan for Compliance | 2008-08-16 | On-Going | Fulfilled
D2 | QA/QC Protocols | NA | June 1, 2013 | Fulfilled
D5 | Geotechnical Engineer Report |  | November 1, 2013 | Fulfilled
D5 | Development of a Capital Plan |  | March 31, 2014 | Outstanding |  |  | GN says, "After reviewing the recommended options, CGS has placed the Hall Beach lagoon repair on the Capital Plan as a top priority. This will be presented to NCIAC April 1, 2014 to be brought forward as part the the GNs Capital Planning Process." This is not a Capital Plan. This item will remain outstanding until an actual Capital Plan is submitted.
D6 | Conduct Acute Lethality Tests | 2009-03-31 | 2013-08-31 | Outstanding |  |  | The GN has not completed Acute Lethality tests to date. The GN claims that logistics are preventing them from achieving this. On February 10, 2014 a letter was submitted to the NWB explaining the issue. If the GN would like this removed, a formal amendment application will have to be filed. This item is still outstanding. Have this completed by April 10, 2014.
D8 | Sergregate wastes | 2008-05-16 | October 1, 2013 | Outstanding |  |  | CGS says this will be complete in summer 2014. Until an inspection or photos are provided to verify, this is still outstanding.
D8 | Develop new solid waste action plan |  | July 31, 2014 | Outstanding |  |  | This is due as part of the Compliance Plan, and GN has said this will be complete June 31, 2014. What is the progress of this deliverable?
D9 | Wind Control measures | 2008-05-16 | August 31, 2014 | Outstanding |  |  | This was initally due May 16, 2008. What controls does the Licensee use to control the wind's effects on the landfill?
F1 | O&M for Sewage | 2008-08-16 | July 1, 2014 | Outstanding |  |  | What is the progress of this O&M?
F1 | O&M for Solid Waste | 2008-08-16 | July 1, 2014 | Outstanding |  |  | What is the progress of this O&M?
H | Sampling Program | 2008-03-31 | March 31, 2014 | Outstanding |  |  | See comments in section B2.
Hamlet of Hall Beach