## Table 1
Municipality of Resolute Bay
PLAN FOR COMPLIANCE LICENCE NO. 3BM-RES1520
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
| The Hamlet must maintain a valid Water Licence | The Hamlet’s Water Licence will expire on March 29,2020. | The GN-CGS has initiated the water licence renewal process on behalf of the Hamlet | The water Licence renewal process has been started |  Prior to expiration of future water licence ,the GN will initiate the renewal of the future water licence on behalf of the Hamlet  The GN and the Hamlet commit to ongoing compliance with the Nunavut Waters Act and maintaining a water licence | In normal situation, The water licence renewal process will be started minimum 6 months prior to expiration of the active licence renewal
Part B | General Conditions
B-1 | The Licensee shall file an Annual Report on the Appurtenant Undertaking with the Board for review, no later then March 31st of the year following the calendar year being reported, containing the following information: | In Compliance | The GN will ensure the community submit to the NWB the Annual Report, in accordance with the criteria outlined in the issued water licence. | The GN will ensure that the Hamlet record all the activities carried out for all the water licensed facilities under their water licence during the reporting year. |  GN will monitor to ensure the Hamlet submits their Annual Report to the NWB, in accordance with the criteria outlined in the issued water licence  GN monitoring will include weekly checks of the Hamlet’s log sheets, along with monthly Regional water committee meeting to discuss and action any issues. | The Regional Municipal Engineer will train the Hamlet foreman gradually how to write Annual Report and submit to NWB on time. This training will be conducted during Community visit for the infrastructure inspection once or twice annually.
B-a | tabular summaries of all data generated under the "Monitoring Program"; | In Compliance | The Process will continue | The Process will continue | The Process will continue | The Process will continue
B-b | summary of modifications to the "Monitoring Program"; | Only Leachate | Continue as it is | Continue as it is | Continue as it is | Continue as it is
B-c | the monthly and yearly quantities of all Waste types disposed of at the Solid Waste Facilities: bulky metal, hazardous, wood and soil;
B-d | a summary of modifications and/or major maintenance work carried out on the Solid Waste Facilities, including all associated structures and facilities; | No modification and /or major maintenance was needed. | The facility will be used as it is condition | Continue to Use | The new site has been identified for solid waste management | The new site will be designed , built and commissioned , anticipated in next 3 yrs.
B-e | A list of unauthorized discharges and summary of follow-up action taken; | Non Compliance. Leachate is uncontrolled. | This will continue as it is. | Leachate is naturally treated prior to discharge to the sea. | This process will be continued | This process will be continued until the new facility is built and commissioned, anticipated in next 3 yrs.
B-f | A summary of any abandonment and restoration work completed during the year and an outline of any work anticipated for the next year; | Not applicable | Not applicable | Not applicable | Not applicable | The existing waste sites will be abandoned once the new facility is built and commissioned, anticipated in next 3yrs.
B-g | Any updates or revisions for manuals and plans (Including Operations and Maintenance Plans, Spills Contingency, Abandonment and Restoration, QA/QC) as required by changes in operation and/or technology; | Nil | Nil | Nil | Nil | The manual will be only updated and revised for the operation of the new facilities.
B-h | a summary of any studies, reports and plans requested by the Board that relate to Waste disposal or reclamation, and a brief description of any future studies planned; | The feasibility study is in progress | The document is under review | The document review will be completed within two months. | The next step is to start design works | The construction is anticipated in next 3 yrs.
B-i | summary of any inspections completed by federal or territorial authorities, geotechnical or municipal engineers, on undertakings related to Waste Disposal, or reclamation activities and associated work carried out as a result of these inspections and any deficiencies; and | Suggested a new facility to effectively manage wastes | Working forward | Working forward | Working Forward | The new facility will effectively manage wastes and leachate to bring the water licence into full compliancy.
B-j | any other details on Waste disposal requested by the Board by November 1st of the year being reported. | Segregation of hazardous wastes | In progress | In progress | In progress | The hazardous waste will be managed in a separate cell in the new facility.
B-2 | The Licensee shall notify the NWB of any changes in operating plans or conditions associated with this project at least thirty (30) days prior to any such changes. | In Compliance. Hamlet is currently following the Monitoring program of the existing facilities. | This QA/QC Plan which meets the requirements of Monitoring Program described in Part H of the water licence. The QA/QC Plan was already submitted to NWB. | Monitoring is being implemented during winter and summer seasons as described in the QA/QC Plan. |  Regional Municipal Engineer will continue to train the Hamlet staffs once or twice a year. Also develop a training plan for a TRAIN THE TRAINER for GN staff to develop resources within the GN to allow for ongoing training of Hamlet Staff.  The GN has created a central data base for all reports to be held and accessible to GN staff for review and action. |  All sampling and testing data will be kept in the Regional office in Pond Inlet and CGS head office in Iqaluit.  The TRAIN THE TRAINER program will be continued.
B-3 | The Licensee shall comply with the "Monitoring Program" described in this Licence, and any amendments to the "Monitoring Program" as may be made from time to time, pursuant to the conditions of this Licence. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
B-4 | The "Monitoring Program" and compliance dates specified in the Licence may be modified at the discretion of the Board. | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
B-5 | The Licensee shall install flow meters or other such devices, or implement suitable methods as required under Part H, Item 1. | In compliance. Leachate sampling stations have been established already. | Monitoring stations were already established with Co-ordinates. Signs were installed as per the requirements of the Water licence. | These Monitoring stations will be maintained. | Each summer inspection, the monitoring stations will be inspected. And the missing signs will be reinstalled. | The missing signs will be reinstalled prior to the summer sampling .
B-6 | The Licensee shall, post the necessary signs, where possible, to identify the stations of the "Monitoring Program". All signage postings shall be in the Official Languages of Nunavut, and shall be located and maintained to the satisfaction of an Inspector. | In compliance | Will be Maintained | Will be Maintained | Will be maintained | Will be maintained
B-7 | The Licensee shall, for all plans submitted under this Licence, include a proposed timetable for implementation. Plans submitted, cannot be undertaken without subsequent written Board approval and/or direction. The Board may alter or modify a Plan if necessary to achieve the legislative objectives and will notify the Licensee in writing of acceptance, rejection or alteration of the Plan. | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
B-8 | The Licensee shall, for all plans submitted under this Licence, implement the Plan as approved by the Board in writing. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-9 | The Licensee shall review the Plans referred to in this Licence, as required by changes in operation and/or technology, and modify the Plans accordingly. Revisions to the Plans shall be submitted in the form of an Addendum to be included with the Annual Report. | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed
B-10 | Every Plan to be carried out pursuant to the terms and conditions of this Licence shall become a part of this Licence, and any additional terms and conditions imposed upon approval of a Plan by the Board become part of this Licence. All terms and conditions of the Licence should be contemplated in the development of a Plan where appropriate. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-11 | The Licensee shall ensure a copy of this Licence is maintained at the site of operations at all times. Any communication with respect to this Licence shall be made in writing to the attention of: | Will be done as directed | Available for the Public | A copy is available always at the front desk | Always keep the Licence available at the front desk for the Public | A copy will be kept available always at the front desk.
B-11 a | (a) Manager of Licensing: Nunavut Water Board P.O. Box 119 Gjoa Haven, NU X0B 1J0 Telephone: (867) 360-6338 Fax: (867) 360-6369 Email: licensing@nwb-oen.ca (b) Inspector Contact: Manager of Field Operations, AANDC Nunavut District, Nunavut Region P.O. Box 100 Iqaluit, NU X0A 0H0 Telephone (867) 975-4295 Fax: (867) 975-6445 | Same a site B-11
B-12 | The Licensee shall submit one paper copy and one electronic copy of all reports, studies, and plans to the Board. Reports or studies submitted to the Board by the Licensee shall include a detailed executive summary in English and Inuktitut. | In compliance | always done | Continue | Will be continued | Will be continued
B-13 | The Licensee shall ensure that any document(s) or correspondence submitted by the Licensee to the NWB is received and acknowledged by the Manager of Licensing. | In compliance | Followed | Followed | Will be followed | Will be followed
B-14 | The Licence is assignable as provided for in Section 44 of the Act. | In compliance | No action is required now | No action is required now | no action is required now | No action is required now.
Part C: | CONDITIONS APPLYING TO WATER USE
C-1 | No use of Water is authorized under this Licence. | not applicable | not applicable | not applicable | not applicable | not applicable
C-2 | The Licensee shall implement sediment and erosion control measures prior to and maintain as required during Hamlet operations, to prevent entry of sediment into water. | not applicable | not applicable | not applicable | not applicable | not applicable
Part D: | CONDITIONS APPLYING TO WASTE DISPOSAL
D-1 | The Licensee shall dispose of and permanently contain all solid waste at the Solid Waste Facilties or as otherwise approved by the Board in writing. | In compliance | All the different types of wastes are contained within the solid waste sites | will be continued | will be continued | will be continued
D-2 | The Licensee shall not open burn plastics, wood treated with preservatives, electric wire, Styrofoam, asbestos or painted wood to prevent the deposition of Waste materials of incomplete combustion and/or leachate from contaminated ash residual, from impacting any surrounding Waters, unless otherwise approved by the Board in writing. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-3 | The Licensee shall provide a minimum of ten (10) days' notice to an Inspector, of the intent to open burn municipal Waste in accordance with the Government of Nunavut's Environmental Guideline for the Burning and Incineration of Solid Waste (2012), at the designated location at the Solid Waste Facilities, including the details of the types and quantity of Waste to be burned, proposed dates, protocols to be followed, ultimate disposal of residual ash and the person responsible for the activity. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-4 | The Licensee shall segregate and store all hazardous waste within the Solid Waste Facilities in such a manner as to prevent the deposit of deleterious substances into any Water, until such a time that the materials have been removed for proper disposal at an approved facility. | In compliance | Hazardous wastes are stored separately | This protocol will be managed | This protocol will be managed | This protocol will be managed
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part E: | CONDITIONS APPLYING TO MODIFICATIONS AND CONSTRUCTION
E-1 | The Licensee shall submit to the Board for approval in writing, for-construction design drawings, stamped and signed by a qualified Engineer registered in Nunavut, at least sixty (60) days prior to the construction of any dams, dykes or structures intended to contain, withhold, divert or retain Waste. | In compliance | This protocol will be followed | This protocol will be followed | This protocol will be managed | This protocol will be managed
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
E-2 | The Licensee may, without written consent from the Board, carry out Modifications to the Waste Disposal Facilities provided that such Modifications are consistent with the terms of this Licence and the following requirements are met: | In compliance | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed
E-2 a | the Licensee has notified the Board in writing of such proposed Modifications at least sixty (60) days prior to beginning the Modifications; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 b | such Modifications do not place the Licensee in contravention of the Licence or the Act; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 c | the Board has not, during the sixty (60) days following notification of the proposed Modifications, informed the Licensee that review of the proposal will require more then sixty (60) days; and | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-2 d | the Board has not rejected the proposed Modifications. | NA | NA | NA | NA | NA
E-3 | The Modifications for which all of the conditions referred to in Part E, Item 2, have not been met, may only be carried out upon written approval from the Board. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-4 | The Licensee shall, within ninety (90) days of completion of the Modification or Construction of facilities and/or infrastructure associated with the project, submit to the Board for review, a construction summary report along with stamped as-built plans and drawings, providing explanation to reflect any deviations from the for construction drawing, taking into account construction and field decisions and how they may affect the performance of engineered facilities. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
E-5 | All activities shall be conducted in such a way as to minimize impacts on surface drainage and the Licensee shall immediately undertake any corrective measures in the event of any impacts on surface drainage. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
E-6 | The Licensee shall implement and maintain sediment and erosion control measures prior to and during activities carried out under this Part, to prevent negative impacts to Water resulting from the release of sediment and to minimize erosion. | In Compliance | Will be Maintained | Will be Maintained | Will be Maintained | Will be Maintained
E-7 | With respect to earthworks, the deposition of derbies or sediment into or onto any Water body is prohibited. These materials shall be disposed of at a distance of at least thirty-one (31) metres from the ordinary High Water Mark in such a fashion that they do not enter Water. | In compliance | This restriction will be followed | This restriction will be followed | This restriction will be followed | This restriction will be followed
E-8 | The Licensee shall only use material that is free of contaminants, for construction, operation, and maintenance activities and that is obtained from approved sources, demonstrated not to be potentially acid generating or metal leaching. | In Compliance | This protocol is being maintained | This protocol is being maintained | This protocol will be maintained | This protocol will be maintained
Part F: | CONDITIONS APPLYING TO OPERATION AND MAINTENANCE
F-1 | The submitted renewal application dated May 30, 2014 included an Operation and Maintenance Plan. This Operation and Maintenance Plan has been approved by the Board with the issuance of this Licence. The Licensee shall implement the Operation and Maintenance Plan for the Solid Waste Facilities, in accordance with Part B Item 1 and 2 of this licence. | In compliance | Will be followed | Will be followed | The new facility has its own O&M manual | This manual will be prepared once the new facility is constructed and it is expected in next 3 yrs.
F-2 | The Licensee shall submit to the Board for review, within six (6) months of the issuance of this Licence, a Long-term Solid Waste Management Plan for the Hamlet of Resolute Bay, that provides definitive objectives for building new or upgrading existing Solid Waste management infrastructure. | In compliance | The feasibility study of the waste management for this Community is completed | The new site has been selected | The design works will be started soon | The construction is anticipated in next 3 yrs.
F-3 | All Operation and Maintenance Plans developed shall be prepared in accordance with the appropriate sections of the Guidelines for the Preparation of an Operation and Maintenance Manual for Sewage and Solid Waste Facilities in the Northwest Territories (1996) and the Guidelines for the Planning, Design, Operations and Maintenance of Modified Solid Waste Sites in the Northwest Territories (2003). | In Compliance | The current manual is being used | The current manual of the non engineered solid wastes sites is being used | The new manual will be developed for the future engineered facilities | The new manual will be available in next 3 yrs.
F-4 | The Licensee shall submit to the Board for review with the annual report, an addendum to the Spill contingency Plan that addresses the following: | In compliance. All the spills in the Community are addressed in the Annual report. This covers items F-4a, F-4b, F-4c, F-4d. | will be continued | will be continued | will be continued | will be continued
F-4 a | The specific name and address of the owner or person in charge, management or control of the site(s);
F-4 b | The name, job title and 24-hour telephone number for the person(s) responsible for activating the Spill Contingency plan;
F-4 c | The contact information for the AANDC, Manager of Field Operations; and
F-4 d | Confirmation that a spill kit is available at the hazardous waste and bulky metals area.
F-5 | An inspection of all engineered facilities related to the management of Waste shall be carried out by an Engineer at a minimum of once annually following spring freshette and during open water conditions in order to detect flow from the Solid Waste Facilities and, before commissioning any engineered facility related to the management of Waste. The Engineer's report shall be submitted to the Board within sixty (60) days of the inspection, including a cover letter from the Licensee outlining an implementation plan to address each of the Engineer's recommendations. | In compliance | CIRNAC inspector and Regional Engineer inspects these facilities at least once a year. | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-6 | The Licensee shall perform more frequent inspections of the engineered facilities at the request of an Inspector. | In compliance | The Municipal Engineer visits these facilities many times a year as required | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-7 | If during the period of this Licence, an unauthorized discharge of Waste occurs, or if such a discharge is foreseeable, the Licensee shall: | In compliance. It was never happened. | If it is happened in future, the items F-7a, F-7b, F-7c will be followed. | Working forward | Working forward | Working forward
F-7 a | employ the Spill Contingency Plan for the Hamlet of Resolute Bay. Take whatever steps are immediately practicable to protect human life, health and the environment;
F-7 b | report the incident immediately via the NWT/NU 24-Hour Spill Reporting Line at (867)920-8130 and to the AANDC Manager of Field Operations at (867) 975-4295; and
F-7 c | for each spill occurrence, submit to the Inspector not later then thirty (30) days after initially reporting the event, a detailed report that provides the necessary information on the location (including the GPS coordinates), amount and type of spilled product, initial response action, remediation/clean-up, status of response (ongoing, complete), proposed disposal options for dealing with contaminated materials and any preventative measures to be implemented.
F-8 | The Licensee shall, regardless of the quantity of releases of harmful substances, report to the NWT/NU Spill Line if the release is near or into a Water body. | In Compliance | Community spills were always reported to the Spill hot line | Will be continued | Working forward | Working forward
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part G: | Conditions Applying to Abandonment, Restoration and Temporary Closing
G-1 | The Submitted renewal application dated May 30, 2014 included an Abandonment and Restoration Plan. This Abandonment and Restoration Plan has now been approved by the Board. The Licensee shall implement the Abandonment and Restoration Plan for the Solid Waste Facilities, in accordance with Part B of this licence. | In compliance | No A&R plan needs to be implemented now. | No A&R plan needs to be implemented now. | Once the new facility is commissioned, the existing waste facilities will be planned to be decommissioned. | It is anticipated in next 3 yrs.
G-2 | The Licensee shall submit to the Board for approval in writing, an amendment to the Abandonment and Restoration Plan reference in Part G, Item 1 at least six (6) months prior to abandoning any facilities or upon submission of the final design drawings for the construction of new facilities to replace existing ones. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
G-3 | The Licensee shall complete all restoration work within the time schedule specified in the Plan, or as subsequently revised and approved by the Board in writing. | In Compliance | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed
G-4 | The Licensee shall carry out progressive reclamation of any components of the project no longer required for the Licensee's operations. | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-5 | In order to promote growth of vegetation and the needed microclimate for seed deposition, all disturbed surfaces shall be prepared by ripping, grading, or scarifying the surface to conform to the natural topography. | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-6 | Areas that have been contaminated by hydrocarbons shall be reclaimed to meet objectives or as outlined in the Government of Nunavut's Environmental Guideline for Site Remediation, January 2002. The use of reclaimed soils for the purpose of backfill or general site grading may be carried out only upon consultation and approval by the Government of Nunavut, Department of Environment and an Inspector. | In Compliance | This process of remediation has not yet started | This process of remediation has not yet started | This is expected to be addressed in next 3 yrs. | This is expected to be addressed in next 3 yrs. Once the new facility is operational.
G-7 | The Licensee shall submit for review, within six (6) months of Licence issuance, a Closure and Remediation Report for the site of the Solid Waste Facilities used prior to 2002. This report is to be stamped by an Engineer and describe the history of the site and its decommissioning, and also the Engineer's assessment of weather further reclamation is required at the site to mitigate the possibility of contamination to surrounding freshwater systems. | In compliance | The decommissioning process has not yet started. | The decommissioning process has not yet started. | The decommissioning process has not yet started. | This is expected soon after the new facility is built and operation. It is anticipated in next 3 yrs.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part H | Conditions Applying to the Monitoring Program
H-1 | The Licensee shall maintain a Monitoring Program Station at the following location: See Licence No. 3BM-RES1520 for following list. | In Compliance | The monitoring stations are being maintained correctly. | Will be maintained | Will be maintained | Will be maintained
H-2 | The Licensee shall provide the GPS coordinates (in degrees, minutes and seconds of latitudes and longitude) of all locations where there is a deposit of Waste and all Monitoring Program Stations. | In Compliance | The GPS coordinates will be maintained | The GPS coordinates will be maintained | The GPS coordinates will be maintained | The GPS coordinates will be maintained
H-3 | The Licensee shall confirm the locations and GPS coordinates for all Monitoring Program Stations referred to in Part H Item 1 with an Inspector. | In Compliance | The coordinates are maintained | Will be continued | Will be continued | Will be Continued
H-4 | The Licensee shall sample monthly any runoff or discharges at Monitoring Program Station 1571-5 and analyze for the following parameters: See Licence 3BM-RES1520 for the following list | Non Compliance. Leachate is uncontrolled. | No plan to control leachate | No plan to control leachate | Will be continued as it is. | Will be continued as it is
H-5 | The Licensee shall submit to the Board for review, within ninety (90) days of the issuance of the Licence, a Quality Assurance/Quality Control Plan based on the guidance document Quality Assurance (QA) and Quality Control (QC) Guidelines for Use by Class "B" Licensees in Collecting Representative Water Samples in the Field and for Submission of a QAQC Plan INAC (1996). The Plan shall include a cover letter from an accredited laboratory confirming acceptance of the Plan for the monitoring and analyses to be performed under the Licence. | In compliance | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is
H-6 | The Licensee shall conduct all sampling, sample preservation and analyses in accordance with methods prescribed in the current edition of Standard methods for the Examination of Water and Wastewater, or by such other methods approved a laboratory certified by the Canadian Association for Laboratory Accreditation (CALA). | In compliance | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is
H-7 | All analyses shall be performed in a laboratory accredited according to ISO/IEC Standard 17025. The accreditation shall be current and in good standing. | In compliance | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice | The same accredited Lab will be used until further notice
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
H-8 | The Licensee shall include all of the data and information required by the Monitoring Program and as requested by an Inspector within the annual report under Part B, Item 1. | In compliance | This process will be continued | This process will be continued | This process will be continued | This process will be continued
H-9 | Modifications to the Monitoring Program including the Monitoring Program Stations and parameters may be made only upon written approval for the Board. | In Compliance | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged
H-10 | Additional monitoring stations, sampling and analysis may be requested by an Inspector. | Will be followed as directed by CIRNAC inspector | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged | The monitoring stations are still unchanged