## Table 1
Municipality of Sanikiluaq
PLAN FOR COMPLIANCE LICENCE NO. 3BM-SANI1520
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
| The Hamlet must maintain a valid Water Licence | The Hamlet’s Water Licence will expire on March 29,2020. | The GN-CGS has initiated the water licence renewal process on behalf of the Hamlet | The water Licence renewal process has been started |  Prior to expiration of future water licence ,the GN will initiate the renewal of the future water licence on behalf of the Hamlet  The GN and the Hamlet commit to ongoing compliance with the Nunavut Waters Act and maintaining a water licence | In normal situation, The water licence renewal process will be started minimum 6 months prior to expiration of the active licence renewal
Part B | General Conditions
B-1 | The Licensee shall file an Annual Report on the Appurtenant Undertaking with the Board no later then March 31st of the year following the calendar year being reported, containing the following information: | In Compliance | The GN will ensure the community submit to the NWB the Annual Report, in accordance with the criteria outlined in the issued water licence. | The GN will ensure that the Hamlet record all the activities carried out for all the water licensed facilities under their water licence during the reporting year. |  GN will monitor to ensure the Hamlet submits their Annual Report to the NWB, in accordance with the criteria outlined in the issued water licence  GN monitoring will include weekly checks of the Hamlet’s log sheets, along with monthly Regional water committee meeting to discuss and action any issues. | The Regional Municipal Engineer will train the Hamlet foreman gradually how to write Annual Report and submit to NWB on time. This training will be conducted during Community visit for the infrastructure inspection once or twice annually.
B-a | Tabular summaries of all data generated under the "Monitoring Program"; | In Compliance | The Process will continue | The Process will continue | The Process will continue | The Process will continue
B-b | summary of modifications to the "Monitoring Program" in accordance with Part H, Item 13; | In compliance | Continue as it is | Continue as it is | Continue as it is | Continue as it is
B-c | the daily, monthly and annual quantities in cubic metres of freshwater obtained from all sources;
B-d | the daily, monthly and annual quantities in cubic metres of sewage effluent discharged; and the monthly and yearly quantities of every type of Waste-landfill, bulky metal, hazardous, wood and soil--accepted at the Solid Waste Facilities; the total volume of sludge removed from the sewage lagoon and the disposal method; | In compliance | Waste water volume is as equal to the water consumption volume. Other wastes are based on the population. | Continue to Use | Continue as it is | The new waste site will have more control.
B-e | a summary of modifications and/or major maintenance work carried out on the Water Supply and Waste Disposal Facilities, including all associated structures and facilities; | In compliance | No modification took place | No modification took place | Water supply, Wastewater Treatment and Waste Management are expected to be modified. | These are anticipated in next 3 to 5 yrs.
B-f | a list of unauthorized discharges and summary of follow-up action taken; | Non Compliance. Sewage effluent and Leachate are uncontrolled. | Continued | Continued | This will be modified once new facilities are built. | In the new facilities, both sewage effluent and leachate will be controlled.
B-g | a summary of any abandonment and restoration work completed during the year and an outline of any work anticipated for the next year; | In compliance | This was not done | This was not done | Once the new facility is commissioned, the existing waste facilities will be planned to be decommissioned. | This is expected in next 4 to 5 yrs.
B-h | any updates or revisions for manuals and plans (Including Operations and Maintenance Plans, Spill Contingency, Abandonment and Restoration, QA/QC) as required by changes in operation and/or technology; | In Compliance | Nothing is changed | QA/QC will remain unchanged | QA/QC will be revised | This will be done once the new facilities will be built and commissioned in next 3to 4 yrs.
B-i | a summary of any studies, reports and plans requested by the Board that relate to Waste disposal, Water use or reclamation, and a brief description of any future studies planned; | In compliance | Working forward | Working forward | The studies to upgrade the water supply system, wastewater and waste management are in progress. | These new facilities will be built in next 3 to 4 years.
B-j | a summary of any inspections completed by federal or territorial authorities, geotechnical or municipal engineers, on undertakings related to Waste disposal, Water use or reclamation activities; and | In Compliance | Annual inspection is done by CIRNAC inspector and GN Regional Municipal Engineer | Continue as it is | Continue as it is | CIRNAC inspection report is always published and will be continued to be published.
B-k | any other details on Water use or Waste disposal requested by the Board by November 1st of the year being reported. | Yes | Monthly testing of raw and treated water on chemical properties are continued | Continued until further instruction | Continued until further instruction | More data is required to optimize the water Plant in next 2 to 3 years
B-2 | The Licensee shall notify the NWB of any changes in operating plans or conditions associated with this project at least thirty (30) days prior to any such change. | In Compliance. Hamlet is currently following the Monitoring program of the existing facilities. | This QA/QC Plan which meets the requirements of Monitoring Program described in Part H of the water licence. The QA/QC Plan was already submitted to NWB. | Monitoring is being implemented during winter and summer seasons as described in the QA/QC Plan. |  Regional Municipal Engineer will continue to train the Hamlet staffs once or twice a year. Also develop a training plan for a TRAIN THE TRAINER for GN staff to develop resources within the GN to allow for ongoing training of Hamlet Staff.  The GN has created a central data base for all reports to be held and accessible to GN staff for review and action. |  All sampling and testing data will be kept in the Regional office in Pond Inlet and CGS head office in Iqaluit.  The TRAIN THE TRAINER program will be continued.
B-3 | The Licensee shall comply with the "Monitoring Program" described in this Licence, and any amendments to the "Monitoring Program" as may be made from time to time, pursuant to the conditions of this Licence. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
B-4 | The "Monitoring Program" and compliance dates specified in the Licence may be modified at the discretion of the Board. | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
B-5 | The Licensee shall install flow meters or other such devices, or implement suitable methods required for the measuring of Water volumes as required under Part H, Item 2. | Not in Compliance | We are working forward on this | We are working forward on this | We are working forward on this | This plant is going to be updated with the flow meter or other devices.
B-6 | The Licensee shall implement the Plan of Compliance that was submitted as additional information with the renewal Application, and accepted by the Board with the issuance of the Licence. | In compliance | Will be Maintained | Will be Maintained | Will be maintained | Will be maintained
B-7 | The Licensee shall maintain the necessary signs, where possible, to identify the stations of the "Monitoring Program". All signage postings shall be in the Official Languages of Nunavut, and shall be located and maintained to the satisfaction of an Inspector. | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
B-8 | The Licensee shall, for all Plans submitted under this Licence, including a proposed timetable for implementation. Plans submitted cannot be undertaken without subsequent written Board for approval and/or direction. The Board may alter or modify a Plan if necessary to achieve the legislative objectives and will notify the Licensee in writing of acceptance, rejection or alteration of the Plan. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-9 | The Licensee shall, for all Plans submitted under this Licence, implement the Plan as approved by the Board in writing. | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed | Will be done as directed
B-10 | The Licence shall review the Plans referred to in this Licence, as required by changes in operation and/or technology, and modify the Plan accordingly, Revisions to the Plans shall be submitted in the form of an Addendum to be included with the Annual Report. | Will be carried out | Will be carried out | Will be carried out | Will be carried out | Will be carried out
B-11 | Every Plan to be carried out pursuant to the terms and conditions of the Licence shall become a part of this Licence, and any additional terms and conditions imposed upon approval of a Plan by the Board become part of this Licence. All terms and conditions of the Licence should be contemplated in the development of a Plan where appropriate. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
B-12 | The Licensee shall ensure a copy of this Licence is maintained at the site of operations at all times. Any communication with respect to this Licence shall be made in writing to the attention of: | Will be done as directed | Available for the Public | A copy is available always at the front desk | Always keep the Licence available at the front desk for the Public | A copy will be kept available always at the front desk.
| (a) Manager of Licensing: Nunavut Water Board P.O. Box 119 Gjoa Haven, NU X0B 1J0 Telephone: (867) 360-6338 Fax: (867) 360-6369 Email: licensing@nwb-oen.ca (b) Inspector Contact: Manager of Field Operations, AANDC Nunavut District, Nunavut Region P.O. Box 100 Iqaluit, NU X0A 0H0 Telephone (867) 975-4295 Fax: (867) 975-6445 | Same a site B-11
B-13 | The Licensee shall submit one paper copy and one electronic copy of all reports, studies, and plans to the Board. Reports or studies submitted to the Board by the Licensee shall include a detailed executive summary in Inuktitut. | In compliance | always done | Continue | Will be continued | Will be continued
B-14 | The Licensee shall ensure that any document(s) or correspondence submitted by the Licensee to the NWB is received and acknowledged by the Manager of Licensing. | In compliance | Followed | Followed | Will be followed | Will be followed
B-15 | The Licence is assignable as provided for in Section 44 of the Act. | In compliance | No action is required now | No action is required now | no action is required now | No action is required now.
Part C: | CONDITIONS APPLYING TO WATER USE
C-1 | The Licensee shall obtain all freshwater for municipal purposes from Sanikiluaq Lake, at the Truck-Fill Station, or as otherwise approved in writing by the Board. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
C-2 | The annual quantity of Water use for all purposes shall not exceed two-hundred ninety-nine (299) cubic metres per day, to a maximum of forty thousand (40,000) cubic metres per year. | In Compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
C-3 | Where the use of Water is of a sufficient volume that the source Water body may be drawn down, the Licensee shall submit to the Board for approval in writing, the following: details of Water volume involved, hydrological overview of the Water body, details of impacts, and proposed mitigation measures. | In compliance. Hydrology study was done and submitted to NWB | Will be monitored | Will be monitored | Will be monitored | Will be monitored
C-4 | The Licensee shall maintain the Water Supply Facility to the satisfaction of the Inspector. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
C-5 | The Licensee shall equip all Water intake hoses with a screen of appropriate mesh size to ensure that fish are not entrained and shall withdraw Water at a rate such that fish do not become impinged on the screen. | In Compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
C-6 | The Licensee shall not remove any material from below the ordinary High Water Mark of any Water body unless approved by the Board in writing. | In Compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
C-7 | The Licensee shall not cause erosion to the banks of any body of Water and shall provide necessary controls to prevent such erosion. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
C-8 | The Licensee shall implement sediment and erosion control measures prior to and maintain as required during Hamlet operations, to prevent entry of sediment into Water. | In compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
Part D: | CONDITIONS APPLYING TO WASTE DISPOSAL
D-1 | The Licensee shall direct all Sewage, generated by the Hamlet of Sanikiluaq to the Sewage Disposal Facility or as otherwise approved by the Board. | In compliance | The entire sewage produced in the Community is contained within the Sewage Lagoon | will be continued | will be continued | will be continued
D-2 | The Licensee shall provide a minimum of ten (10) days' notice to an Inspector prior to initiating any decant of the Sewage Disposal Facility. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-3 | All Effluent discharged from the Sewage Disposal Facility at Monitoring Program Station SAN-4 shall not exceed the following Effluent quality limit: See Licence 3BM-SAN1520 for the following list, | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
D-4 | A freeboard limit of at least 1.0 metre, or as recommended by a qualified Geotechnical Engineer and as approved by the Board in writing, shall be maintained at all dams, dykes, or structures intended to contain, withhold, divert or retain Water or Waste. | In compliance | Will be followed | Will be followed | This protocol will be managed | This protocol will be managed
D-5 | The Sewage Disposal Facility shall be maintained and operated, to the satisfaction of an Inspector and in such manner as to prevent structural failure. | In compliance | Will be maintained | Will be maintained | Will be maintained | Will be maintained
D-6 | The Licensee shall dispose of and permanently contain, all Solid Wastes at the Solid Waste Disposal Facility or as otherwise approved by the Board in writing. | In compliance | Will be followed | Will be followed | The new facility is expected soon | Each waste has its individual cell in the new solid wastes site.
D-7 | The Licensee shall not open burn plastics, wood treated with preservatives, electric wire, Styrofoam, asbestos or painted wood to prevent the deposition of Waste materials of incomplete combustion and/or leachate from contaminated ash residual, from impacting any surrounding Waters, unless otherwise approved by the Board in writing. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
D-8 | The Licensee shall provide a minimum of ten (10) days' notice to an Inspector, of the intent to open burn municipal Waste in accordance with the Government of Nunavut's Environmental Guideline for the Burning and Incineration of Solid Waste (2012), at the designated location at the Solid Waste Disposal Facility, including the details of the types and quantity of Waste to be burned, proposed dates, protocols to be followed, ultimate disposal of residual ash and the person responsible for the activity. | In compliance | This protocol will be followed | This protocol will be followed | This protocol will be followed | This protocol will be followed
D-9 | The Licensee shall segregate and store all hazardous materials and/or Hazardous Waste within the Solid Waste Disposal Facility in such a manner as to prevent the deposit of deleterious substances into any Water, until such a time that the materials have been removed for proper disposal at an approved facility. | In Compliance | Hazardous wastes are kept in the Sea Can. | This process will be followed | This process will be continued | This process will be continued
D-10 | The Licensee shall implement measures to ensure Hazardous Waste and/or leachate from the Solid Waste Disposal Facility does not enter Water. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part E: | CONDITIONS APPLYING TO MODIFICATIONS AND CONSTRUCTION
E-1 | The Licensee shall submit to the Board for approval in writing, for-construction design drawings, stamped and signed by a qualified Engineer registered in Nunavut, at least sixty (60) days prior to the construction of any dams, dykes or structures intended to contain, withhold, divert or retain Waste or Waste. | In compliance | This protocol will be followed | This protocol will be followed | This protocol will be managed | This protocol will be managed
E-2 | The Licensee may, without written consent from the Board, carry out Modifications to the Water Supply Facility and Waste Disposal Facilities provided that such Modifications are consistent with the terms of this Licence and the following requirements are met; | In compliance | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed | This guidelines will be followed
E-2 a | the Licensee has notified the Board in writing of such proposed Modifications at least sixty (60) days prior to beginning the Modifications; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 b | such Modifications do not place the Licensee in contravention of the Licence or the Act; | In compliance | Will be followed as advised | Will be followed as advised | Will be followed as advised | Will be followed as advised
E-2 c | the Board has not, during the sixty (60) days following notification of the proposed Modifications, informed the Licensee that review of the proposal will require more then sixty (60) days; and | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-2 d | the Board has not rejected the proposed Modifications. | NA | NA | NA | NA | NA
E-3 | The Modifications for which all of the conditions referred to in Part E, Item 2, have not been met, may only be carried out upon written approval from the Board. | Will be followed | Will be followed | Will be followed | Will be followed | Will be followed
E-4 | The Licensee shall, within ninety (90) days of completion of the Modification or Construction of facilities and/or infrastructure associated with the project, submit to the Board a Construction Summary Report along with stamped as-built plans and drawings, providing explanation to reflect any deviations from the issued for constuction drawings, taking into account construction and field decisions and how they may affect the performance of engineered facilities. | In compliance | Will be followed | Will be followed | Will be followed | Will be followed
E-5 | All activities shall be conducted in such a way as to minimize impacts on surface drainage and the Licensee shall immediately undertake any corrective measures in the event of any impacts on surface drainage. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
E-6 | The Licensee shall implement and maintain sediment and erosion control measures prior to and during activities carried out under this Part, to prevent negative impacts to Water resulting from the release of sediment and to minimize erosion. | In Compliance | Will be Maintained | Will be Maintained | Will be Maintained | Will be Maintained
E-7 | With respect to earthworks, the deposition of derbris or sediment into or onto any Water body is prohibited. These materials shall be disposed of at a distance of at least thirty-one (31) metres from the ordinary High Water Mark in such a fashion that they do not enter Water. | In compliance | This restriction will be followed | This restriction will be followed | This restriction will be followed | This restriction will be followed
E-8 | The Licensee shall only use material that is free of contaminants, for construction, operation, and maintenance activities and that is obtained from approved sources, demonstrated not to be potentially acid generating or metal leaching. | In Compliance | This protocol is being maintained | This protocol is being maintained | This protocol will be maintained | This protocol will be maintained
E-9 | The Licensee shall maintain a minimum of thirty-one (31) metres buffer zone between the periphery of quarry sites and the high water mark of any water body. The Licensee shall not excavate and/or remove material from the quarry beyond a depth of one (1) metre above the high water mark or above the groundwater table so as to prevent the contamination of groundwater sources. Further the Licensee is advised that quarrying shall be carried out in accordance with all applicable legislation and industry standards including the Northern Land Use Guidelines, Pits and Quarries (INAC,2010).
Part F: | CONDITIONS APPLYING TO OPERATION AND MAINTENANCE
F-1 | The Board has approved the Manual entitled "Operation and Maintenance Manual of Water Truck Fill Station Municipality of Sanikiluaq, Vol. I and II" dated July 2011 submitted as additional information with the Application. The Licensee shall submit to the Board for review, within ninety (90) days from the date of issuance of this Licence, an updated O&M Manual. The updated O&M Manual shall include a Spill Contingency Plan (SCP) for the Water Supply Facility, prepared in the format set out by the Consolidation of Spill Contingency Planning and Reporting Regulations R-068-93, the SCP shall include a detailed description of the secondary system employed to prevent spills. | In compliance | Will be followed | Will be followed | The new facility has its own O&M manual | This manual will be prepared once the new facility is constructed and it is expected in next 3 yrs.
F-2 | The Board has approved the Operation and Maintenance Manual for the Existing Sewage Lagoons, dated September 2014, submitted as additional information with the Application. | In compliance | Will be used | Will be used | Will be used | Will be used
F-3 | The Board has approved the Solid Waste Operation and Maintenance Plan for the Hamlet of Sanikiluaq, dated September 2014, submitted as additional information with the Application. The Licensee shall submit to the Board, for review, within ninety (90) days from the date of issuance of this Licence, an updated O&M Plan. The updated Plan shall include a revised "Hazardous Waste Management Procedure" (HWMP) for the solid Waste Facility. The revised HWMP shall include but not be limited to the following: | In Compliance. This covers F-3a.F-3b, F-3c,F3-d,F3-e, F3-f, F3-g and F-3 h. | The current manual is being used | The current manual of the non engineered solid wastes sites is being used | The new manual will be developed for the future engineered facilities | The new manual will be available in next 3 -4yrs.
F-3 a | date of issuance; | Follow F-3
F-3 b | period of cover; | Follow F-3
F-3 c | considerations related to fencing; | Follow F-3
f-3 d | considerations related to signage; | Follow F-3
F-3 e | inventory of hazardous Waste; | Follow F-3
F-3 f | hazardous Waste runoff management; | Follow F-3
F-3 g | a description of how facilities are operated and maintained and how often these task are performed; and | Follow F-3
F-3 h | name of the person responsible for the Facility operations. | Follow F-3
F-4 | The Board has approved the Spill Contingency Plan Existing the Proposed Municipal Quarry Sites, Sanikiluaq, Nunavut, dated May 2013 submitted as additional information with the Application. | In compliance | CIRNAC inspector and Regional Engineer inspects these facilities at least once a year. | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-5 | An inspection of all engineered facilities related to the management of Water and Waste shall be carried out by an Engineer at a minimum of once annually, and before commissioning any engineered facility related to the management of Water and Waste. The Engineer's report shall be submitted to the Board within sixty (60) days of the inspection, including a cover letter from the Licensee outlining an implementation plan to address each of the Engineer's recommendations. | In compliance | The Municipal Engineer visits these facilities many times a year as required | This protocol will be continued | This protocol will be continued | This protocol will be continued
F-6 | An inspection of all engineered facilities related to the management of Water and Waste shall be conducted by a Geotechnical Engineer in accordance with the Canadian Dam Safety Guidelines, at least one (1) year prior to the expiry of the Licence, during the open Water period (June/July/August). The Geotechnical Engineer's report shall be submitted to the Board for review within sixty (60) days of the inspection, including a cover letter from the Licensee outlining an implementation plan to address the Engineer's recommendations. | In compliance | Municipal Engineer along with the CIRNAC inspector conducts annual inspection. | This will be continued | This will be continued | This will be continued
F-7 | The Licensee shall perform more frequent inspections of the engineered facilities at the request of an Inspector. | In Compliance. | Municipal Engineer visits this community as and when required. | This will be continued | This will be continued | This will be continued
F-8 | If during the period of this Licence, an unauthorized discharge of Waste occurs, or if such a discharge is foreseeable, the Licensee shall: | In Compliance. The Hamlet will follow F-8a,F-8b, and F-8c | Will be followed | Will be followed | Will be followed | Will be followed
F-8 a | employ the appropriately approved Spill Contingency Plan for the Hamlet of Sanikiluaq, take whatever steps are immediately practicable to protect human life, health and the environment;
F-8 b | report the incident immediately via the NWT/NU 24-Hour Spill Reporting Line at (867)920-8130 and to the AANDC Manager of Field Operations at (867) 975-4295; and
F-8 c | for each spill occurrence, submit to the Inspector not later then thirty (30) days after initially reporting the event, a detailed report that provides the necessary information on the location (including the GPS coordinates), amount and type of spilled product, initial response action, remediation/clean-up, status of response (ongoing, complete), proposed disposal options for dealing with contaminated materials and any preventative measures to be implemented. | D91:D94
F-9 | The Licensee shall, in addition to Part F, Item 8, regardless of the quantity of releases of harmful substances, report to the NWT/NU Spill Line if the release is near or into a Water body. | In Compliance | Community spills were always reported to the Spill hot line | Will be continued | Working forward | Working forward
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part G: | CONDITIONS APPLYING TO ABANDONMENT AND RESTORATION
G-1 | The Licensee shall submit to the Board, for approval, an Abandonment and Restoration Plan at least six (6) months prior to abandoning any facilities or upon submission of the final design drawings for the construction of new facilities to replace existing ones. Where applicable, the Plan shall include information on the following: | In compliance. The Plan will satisfy G-1a,G-3b,G-3c, G-3d,G-3e,G-3f,G-3g,G-3h,G-3i,G-3j,G-3K,G-3l,and G-3m | No A&R plan needs to be implemented now. | No A&R plan needs to be implemented now. | Once the new facility is commissioned, the existing waste facilities will be planned to be decommissioned. | It is anticipated in next 3 yrs.
G-1 a | Water intake facilities;
G-1 b | the Water treatment and Waste disposal sites and facilities;
G-1 c | abandoned Water and Waste facilities;
G-1 d | petroleum and chemical storage areas;
G-1 e | any site affected by Waste spills;
G-1 f | leachate prevention;
G-1 g | an implementation schedule;
G-1 h | maps delineating site facilities;
G-1 i | consideration of altered drainage patterns;
G-1 j | type and source of cover materials;
G- 1 k | future area use;
G- 1 l | Hazardous Wastes; and
G-1 m | a proposal identifying measures by which restoration costs will be financed by the Licensee upon abandonment related to Water use, Waste deposit to Water, or appurtenant undertakings related to Water use and/or deposit of Waste to Water, subject to the act and regulations.
G-2 | The Licensee shall complete all restoration work within the time schedule specified in the Plan, or as subsequently revised and approved by the Board. | In Compliance | Will be followed | Will be followed | Will be followed | Will be followed
G-3 | The Licensee shall carry out progressive reclamation of any components of the project no longer required for the Licensee's operations. | In Compliance | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed | The Protocol will be followed
G-4 | In order to promote growth of vegetation and the needed microclimate for seed deposition, all disturbed surfaces shall be prepared by ripping, grading, or scarifying the surface to conform to the natural topography. | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-5 | Areas that have been contaminated by hydrocarbons shall be reclaimed to meet objectives or as outlined in the Government of Nunavut's Environmental Guideline for Site Remediation, January 2002. The use of reclaimed soils for the purpose of back fill or general site grading may be carried out only upon consultation and approval by the Government of Nunavut, Department of Environment and an Inspector. | In Compliance | Will be followed as directed | Will be followed as directed | Will be followed as directed | Will be followed as directed
G-6 | The Licensee shall submit to the Board for review, within ninety (90) days of insurance of this Licence, a Closure and Remediation Report for the "contaminated site" including: | In Compliance | This process of remediation has not yet started | This process of remediation has not yet started | This is expected to be addressed in next 3 yrs. | This is expected to be addressed in next 3 yrs. Once the new facility is operational.
G-6 a | mapped GPS coordinates delineating the extents of the disposal areas (metal waste, landfill site and unauthorized disposal site) referred to in Figure 2 of the Solid Waste Operation and Maintenance Plan; and | In compliance and this covers G-6b. | The decommissioning process has not yet started. | The decommissioning process has not yet started. | The decommissioning process has not yet started. | This is expected soon after the new facility is built and operation. It is anticipated in next 3 yrs.
G-6 b | a work Plan assess, close and remediate the unauthorized disposal areas.
Licence Condition |  | Status of Compliance | Short Term Plan for Compliance | Schedule for Implementation of Short Term Plan for Compliance (including funding status where applicable to municipal developments) | Long Term Plan for Compliance | Schedule for Implementation of Long Term Plan for Compliance (including funding status where applicable to municipal developments)
Part H | Conditions Applying to the Monitoring Program
H-1 | The Licensee shall maintain a Monitoring Program Station at the following location: See Licence No. 3BM-SANI1520 for the following list | In Compliance | The monitoring stations are being maintained correctly with the GPS coordinates. | Will be maintained | Will be maintained | Will be maintained
H-2 | The Licensee shall measure and record, in cubic metres, the daily, monthly, and annual quantities of Water extracted for all purposes at Monitoring Program Station SAN-1. | In Compliance | The Meter located inside the plant records daily extraction volume of water from the Lake. Also Consumption volume is considered as the cross check. | This process will be continued | This process will be continued | This process will be continued
H-3 | The Licensee shall measure and record, in cubic metres, the daily, monthly, and annual quantities of raw sewage offloaded from trucks at Monitoring Program Station SAN-3. | In Compliance | The coordinates are maintained | Will be continued | Will be continued | Will be Continued
H-4 | The Licensee shall measure and record in cubic metres, when flow is occurring, the monthly and annual quantities of Effluent discharged from SAN-4. | Non Compliance. Flow is uncontrolled. Consumption/extraction volume is considered as equal to the discharge volume. | Will be continued | Will be continued | Will be continued | Will be continued
H-5 | The Licensee shall sample at SAN-4, a minimum of three (3) times annually, once upon commencing discharge, once half-way through discharge and once just prior to the end of discharge. | In compliance | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is | Will be maintained as it is
H-6 | All Samples obtained at SAN-4 shall be analyzed for the following parameters: See Licence 3BM-SANI1520 for the following list. | In compliance. An accredited Lab named ALS lab in Winnipeg conducts all the testing. | Will be continued | Will be continued | Will be continued | Will be continued
H-7 | The Licensee shall measure and record the annual quantities of sludge removed from the sewage lagoon, along with the methods of storage, treatment and disposal. This information shall be included in the Annual Report. | None compliance. The sludge is retained at the bed of the lagoon and never removed. | Will be continued | Will be continued | Will be continued | Will be continued
H-8 | The Licensee shall sample for Water quality analysis at Monitoring Stations SAN-2 and SAN-5 once per month in June, July and August during periods of observed flow. Samples shall be analyzed for the parameters listed in Part H Item 6, as well as Total Petroleum Hydrocarbons. | In compliance | This process will be continued | This process will be continued | This process will be continued | This process will be continued
H-9 | The Licensee shall conduct all sampling, sample preservation and analyses in accordance with methods prescribed in the current edition of Standard Methods for the Examination of Water and Wastewater, or by such other methods approved by a laboratory certified by the Canadian Association for Laboratory Accreditation (CALA). | In Compliance. ALS Lab, a certified and accredited lab in Winnipeg conducts testing of all the water, wastewater and Leachate samples | This process will be continued | This process will be continued | This process will be continued | This process will be continued
H-10 | All analyses shall be performed in a laboratory accredited according to ISO/IEC Standard 17025. The accreditation shall be current and in good standing. | Will be followed as directed using ALS , accredited Lab. | This will be followed | This will be followed | This will be followed | This will be followed
H-11 | The Licensee shall submit to the Board for review, within ninety (90) days of the issuance of the Licence, a Quality Assurance/Quality Control Plan based on the guidance document Quality Assurance (QA) and Quality Control (QC) Guidelines for Use by Class "B" Licensees in Collecting Representative Water Samples in the Field and for Submission of a QAQC Plan INAC (1996). The Plan shall include a covering letter from an accredited laboratory confirming acceptance of the Plan for the monitoring and analyses to be performed under the Licence and shall meet the standards set out in Part H, Item 9 and Part H, Item 10 of the Licence. | In compliance. Submitted QA/QC as per the guidance of the NWB. | Will remain same | Will remain same | The QA/QC will be revised once the new facilities are built. | The revised QA/QC will be available for the new and existing facilities in next 3 yrs.
H-12 | The Licensee shall include all of the data and information required by the Monitoring Program, as required under Part B, Item 1, or as requested by an Inspector. | in Compliance. | Will be followed | Will be followed | Will be followed | Will be followed
H-13 | Modifications to the Monitoring Program including the Monitoring Program Stations and parameters may be made only upon written approval of the Board. | In compliance | Follow this protocol | Follow this protocol | Follow this protocol | Follow this Protocol
H-14 | Additional monitoring stations, sampling and analysis may be requested by an Inspector. | Will be followed as directed by the Inspector | Will be followed as directed by the Inspector | Will be followed as directed by the Inspector | Will be followed as directed by the Inspector | Will be followed as directed by the Inspector