## Taloyoak
License Condition | Deliverables | Original due date | Due Date, as per Compliance Plan | Status of Compliance | Documented |  | General Comments
[5 empty] | on CIDMS (#) | On NWB ftp server (Y/N) |  | GN Comments
B1 | 2004 Annual Report | 2005-03-31 | 2014-03-31 | Outstanding |  |  |  | not available
B1 | 2005 Annual Report | 2006-03-31 | 2014-03-31 | Outstanding |  |  |  | not available
B1 | 2006 Annual Report | 2007-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted to NWB March 13, 2014
B1 | 2007 Annual Report | 2008-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted to NWB March 13, 2014
B1 | 2008 Annual Report | 2009-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted to NWB March 13, 2014
B1 | 2009 Annual Report | 2010-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted to NWB March 13, 2014
B1 | 2010 Annual Report | 2011-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted to NWB March 13, 2014
B1 | 2011 Annual Report | 2012-03-31 | 2014-03-31 | Fulfilled |  | Y |  | submitted on Dec 10, 2012(shah)
B1 | 2012 Annual Report | 2013-03-31 | 2013-03-31 | Fulfilled |  | Y |  | submitted on January 30, 2013 (shah)
B1 | 2013 Annual Report | 2014-03-31 | 2014-03-31 | Fulfilled |  |  |  | submitted on March 4, 2014 (Shah)
B1/B2 | exp report | 2013-03-31 | 2013-03-31 | Fulfilled | 77016 |  |  | submitted on March 31, 2013
B2 | Training Program Report | NA | 2013-08-31 |  |  | Y |  | submitted on March 31, 2013
B2 | Action Plan including QA/QC Protocols | NA | 2013-08-31 | Fulfilled |  | Y | Due as part of Compliance Plan. GN said this was submitted with renewal application on June 1, 2013 | submitted by exp Consultant inAug 2013
B2 | A monitoring program, which will include all sampling | 2008-12-11 | 2013-03-31 | Fulfilled |  |  |  | samplin results of Monitoring Program includes 2013 Annual Report (shah)
B5 | Posted Signs | 2009-11-01 | 2013-08-31 | Outstanding |  |  | This is outstanding until photo evidence or an inspection confirms otherwise.
B8 | Consultant Report on Outstanding reports | NA | 2013-05-31 | Fulfilled |  |  | exp report submitted on March 31, 2013 | consultants report submitted on March 31, 2013
B8 | Submit all outstanding reports | As they become available | 2013-07-01 | Awaiting Submission |  |  |  | All available reports submitted in 2013
B10 | Plan for Compliance | 2009-03-11 | On-Going | Fulfilled |  | y |  | updated last in January 2014
D1 | Application for new Licence to include sewage disposal, treatment and discharge, solid waste collection, containment or disposal | NA | NA | Outstanding |  |  | A Renewal Application was submitted on Aug 12, 2013, with the request for inclusion of sewage and solid waste facilities. The application is currently under review with the NWB; however, it is not clear if this is a Renewal Application, an Amendment Application (to change the activities being licensed to include soild waste and sewage disposal, or an Renewal/Amendment Application. In order to achieve compliance, you will need to clearly apply for a Renewal/Amendment Application. | New Amendment Application submitted on Aug 12, 2013, with the request for inclusion of sewage and solid waste facilities. Application under review.
E1 | Construction Design Drawings |  |  | Awaiting technical review from NWB |  |  | A number of construction drawings have been submitted, I will ask the NWB to comment on the completeness of this term. | submitted by consultants and NWB conformed
E3 | Report on the status of modifications | NA | 2013-03-31 | Awaiting technical review from NWB |  |  | There have been modifications done to the water source of Canso Lake). GN has submitted as-built drawings to NWB. I will ask the NWB to comment on the completeness of this term. | No modification to sewage and solid waste facilities, hence no outstanding
E3 | As built Drawings |  | 2014-03-31 | Awaiting technical review from NWB |  |  | There have been modifications done to the water source of Canso Lake). GN has submitted as-built drawings to NWB. I will ask the NWB to comment on the completeness of this term. | submitted before and also re-submitted
F1 | O&M Manual Sewage | 2009-03-11 | 2013-12-01 | Outstanding |  |  | The GN is late submitting these, it says these will be submitted July 31 2014 | The Licensee will submit it by July 31, 2014.
F1 | O&M Manual Solid Waste | 2009-03-11 | 2013-12-01 | Outstanding |  |  | The GN is late submitting these, it says these will be submitted July 31 2014 | The Licensee will submit it by July 31, 2014.
G1 | A&R for existing water intake facility | 2009-03-11 | 2015-03-31 | Awaiting Submission |  |  | GN will submit February 28, 2014 | The licensee will submit A&R plan by Sep 30, 2014.
H1 | Annual Report that includes water use | 2009-03-31 | 2014-03-31 | Fulfilled |  |  |  | Annual reports updated since 2011
H2 | Data from Monitoring Program in Annual Report | 2009-03-31 | 2014-03-31 | Outstanding |  |  |  | sample results data and information of monitoring statins are updated 2011-13