## Commitments
No. | Issue | Party(s) who raised issue | Pre-Hearing Commitment (DRAFT) | Party Responsible for Commitment | Timeline for Submission | Additional Comment | Additional Comment (As of July 5, 2010)
1 | Drawdown of Wolf Creek | DFO | Provide confirmation whether information or data is available regarding fish presence and fish habitat in Wolf Creek. | DFO | 2010-04-16 |  | During the TM/PHC, the community stated that there is fish in Wolf River/(creek?); Is the proponent required to prove same independently?
2 |  |  | Provide a copy of the study completed by IEG in 2005 evaluating the long term capacity of the Wolf Creek water supply. | GN-CGS | 2010-04-16 |  | Received May 31, 2010
3 |  |  | Provide work plan and timeline to assess impacts of drawdown on fish habitat and details of water intake. | GN-CGS | 2010-04-16 | Local knowledge confirms that Wolf Creek flows all year and that fish are present. Impact of drawdown on fish habitat can only be assessed during late summer pumping conditions. | I have not seen records of this in Central-sj
4 | Drawings | NWB | Provide work plan and timelines for (1) preparing Operations and Maintenance Plans for interim use of the Bulky Waste Management Area and Hazardous Waste Storage Area (2) creating as-built drawings of the Bulky Waste Management Area and Hazardous Waste Storage Area (3) testing soil and water in the vicinity of the Bulky Waste Management Area and Hazardous Waste Storage Area; and (4) preparing Abandonment and Restoration Plans for the Bulky Waste Management Area and Hazardous Waste Storage Area | GN-CGS | 2010-04-16 |  | Revisions received June 2, 2010, as part of the Solid waste management facility O&M plan
5 |  | NWB | Provide signed as-built drawings of the new 2005 sewage lagoon cell. | GN-CGS | 2010-04-16 |  | Received June 2, 2010
6 | Solid Waste O&M Plan | INAC, GN-DOE, EC | Revise Solid Waste Operations & Maintenance Plan and Environmental Emergency Contingency Plan to address burning procedures and hazardous waste issue. | GN-CGS | 2010-04-16 |  | Received June 2, 2010
7 |  | EC | Revise Solid Waste Operations & Maintenance Plan to address recommended reuse and recycling edits. | GN-CGS | 2010-04-16 |  | Received June 2, 2010
8 |  | EC, INAC | Revise Solid Waste Operation & Maintenance Plan to address proper handling of hydrocarbon contaminated soil. | GN-CGS | 2010-04-16 |  | Received June 2, 2010
9 | Hazardous Waste Storage | EC | Provide work plan and timeline for preparing Operations and Maintenance Plan for interim use of the Hazardous Waste Storage Area | GN-CGS | 2010-04-16 |  | Received June 2, 2010
10 | Effectiveness of Sewage Treatment | EC, INAC | Provide copies of study conducted by summer student on wetland treatment and attempt to obtain data from Fleming College. Also provide work plan and timeline to address outstanding issues. | GN-CGS | 2010-04-16 |  | I have not seen records of this in Central- sj
11 | Sewage | INAC, EC | Provide background documents (including FSC report) regarding sewage lagoon and wetland design and operation (ie. contribution from precipitation and snowmelt, retention time, surface water flow path through wetland, effectiveness of wetland treatment). | GN-CGS | 2010-04-16 |  | Revisions received June 2, 2010
12 |  | INAC | Provide work plan for verifying the integrity of the sewage lagoon berm wall and the location in the berm where effluent is discharged. | GN-CGS | 2010-04-16 |  | Received June 2, 2010 as part of sewage treatment plant O&M manual
13 |  | INAC, EC | Provide work plan and timeline for determining the intent of the design of the sewage lagoon and wetland and the location of the final discharge point. | GN-CGS | 2010-04-16 |  | Received June 2, 2010
14 | Sewage Disposal Facility O&M Plan | NWB | Revise Sewage Disposal Facility Operations and Maintenance Plan section 4.2 regarding locations of ARV-2 and ARV-4. | GN-CGS | 2010-04-16 |  | Revised Plan Received June 2, 2010
15 |  | EC | Revise Sewage Disposal Facility Operations and Maintenance Plan to address sludge removal recommendations. | GN-CGS | 2010-04-16 |  | Revised Plan Received June 2, 2010
16 |  | INAC | Revise Sewage Disposal Facility Operations and Maintenance Plan to address sewage decant. | GN-CGS | 2010-04-16 |  | Revised Plan Received June 2, 2010
17 | Supporting Plans | EC | Revise the Environmental Monitoring and Quality Assurance and Quality Control Plan to address EC recommendations. | GN-CGS | 2010-04-16 |  | Revised Plan Received June 2, 2010
18 |  | EC, GN-DOE | Revise the Environmental Emergency Contingency Plan to address edits recommended by Environment Canada and Government of Nunavut Department of Environment. | GN-CGS | 2010-04-16 |  | Revised Plan received May 31, 2010
Draft