## OG (hidden)
No. | Topic | Reviewer Comment | Reviewer Recommendation | Assigned To | Proponent Response
Environmental Monitoring Advisory Board - EMAB
1 | Evaluate RECLAIM estimates versus actual expenditures | EMAB's view is that the cost of mine closure should be borne by the proponent, not the taxpayer. The comment on p. 1 of the CIRNAC review that "However, it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." raises a major concern. Security should cover the entire cost of closure, and RECLAIM should calculate security that meets the full cost of closure. | CIRNAC/GNWT should carry out a quantitative evaluation of how much current RECLAIM estimates differ from actual expenditures. | GNWT/CIRNAC
2 | Depositing waste rock in open pit | Some mines have included depositing waste rock into open pits as a means of disposal. This activity does not appear to be addressed in the RECLAIM manual or tables. | Expand tables, and manual, to include placing waste rock and other materials, into open pits. | AtkinsRéalis
3 | Revegetation | The reference tables for vegetation include hydroseeding and tree planting. This is a good start, but the range of activities should be expanded to include all activities required for successful revegetation. | Reference tables for vegetation should also include application of amendments and planting of container forb seedlings as well as other activities required for successful revegetation. | AtkinsRéalis | Add Other Specific if not there already
4 | Long-term maintenance and monitoring | Traditional Knowledge Monitoring by members of Affected Communities is an important component of ensuring successful closure and future use of the area affected by the mine for cultural activities by the Indigenous people who live in the area and use it. | Add Traditional Knowledge Monitoring to the list of post-closure activities. | GNWT/CIRNAC
5 | Long-term maintenance and monitoring | EMAB was pleased to see the expansion of the Mobilization sheet to include construction and use of winter roads for both mobilization and demobilization. It is not clear whether this is intended to cover mob/demob for post-closure maintenance. Once the mine closes there is no guarantee that the winter road will continue to exist. If there is a significant maintenance requirement, there may be a need to build a winter road to mobilize heavy equipment etc., and to demobilize it after the maintenance is completed. | Include the cost of building a winter road to the mine as part of long-term maintenance, if this is the only means for mobilizing/demobilizing heavy equipment required for maintenance. Costing should include building the winter road for the following season to demobilize heavy equipment. | AtkinsRéalis | Maintaining a road for the duration of the Post Closure Monitoring may be expensive.
6 | Long-term maintenance and monitoring | Post-closure monitoring activities may require air transportation to and from the site, which could involve use of the airstrip. In order to use the airstrip it will need to be maintained until all monitoring is completed. | Include costs to maintain the airstrip until post-closure monitoring is completed. | AtkinsRéalis | Yes this maybe required.
7 | Long-term maintenance and monitoring | The scope of post-closure maintenance activities includes cover maintenance and spillway maintenance. Maintenance could include other components such as tailings dams, discharge channels, revegetation, or emergency or ongoing water treatment; so the list should be expanded to provide for these and other potential maintenance activities. | Expand the scope of post-closure maintenance activities to include dams and discharge channels, revegetation maintenance, and a category for other potential maintenance requirements. | AtkinsRéalis | Agreed – but any list would not be exhaustive
8 | RECLAIM User Manual | The User Manual will need to be updated to reflect all changes and additions to the RECLAIM tables. | Ensure the RECLAIM User Manual is updated to provide clear explanations of all the activities and changes to the tables. | Brodie
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han
1 | Owners Representative Cost | Costs for the Owners Representative are included at a rate of 8% of the total capital costs estimate. This appears to be a duplication of costs associated with Engineering Design (8%) and Project Management (10%). | Suggest removing the Owners Representative line item in the Indirect Costs summary or reducing the default factor to 2% of Capital Costs or providing a description and basis for this percentage and how it differs. | AtkinsRéalis and Brodie
2 | Human Health and Ecological Risk Assessment | Human Health and Ecological Risk Assessment (3% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
3 | Finalize Closure and Reclamation Plan | Finalize Closure and Reclamation Plan (4% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
4 | Unit Price Cost References are not Regional | There do not appear to be any references to NWT or Nunavut specific unit costs in UR-Short list in workbook RECLAIM 8 Reference Tables_WorkingCopy.xlsx | Suggest that V8 include reference to northern unit price equivalents. | AtkinsRéalis
5 | Remediation | There are no referenced unit prices for remediation of any sort – bioremediation and landfill unit prices do not have any reference or backup. | Add unit prices for standard remediation techniques (e.g. biocell) | AtkinsRéalis | We don’t have a ref for this costs
6 | Land Ownership | The Reclaim Model Version 8.0 does not consider the value of owned land in determining (i.e., reducing) security. | Add consideration for land ownership as a reduction for overall security. | GNWT/CIRNAC
7 | Identify Unit Components without a reference for unit price | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | AtkinsRéalis & Brodie
8 | Unit Prices different from Price Sources | The unit prices in the Reference Table (TABLE 2: RECLAIM v 8.0 Price Sources, Basis and References) do not always match the unit prices in the RECLAIM 8.0 Unit Cost Table. For example, see the unit rate SB1 for "excavate/load/short haul" $16.27 vs $17.00). | Consider integrating the unit prices basis/reference worksheet into the model to reduce inconsistencies and reduce standalone components. | AtkinsRéalis | Discrepancies a result of rounding (need to confrim)
9 | Application of Mining RECLAIM Model feedback into the Oil and Gas RECLAIM Model. | Oil and Gas Producers utilize the "Oil and Gas RECLAIM Model". A similar consultation process should be facilitated for any proposed updates to the Oil and Gas RECLAIM Model. | Conduct a similar consultation and stakeholder engagement process for the Oil and Gas RECLAIM Model 8.0. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
WLWB - Meghan Schnurr
1 | Implementation of RECLAIM V8 | It may help reviewers if the authors could describe how they envision the updated model being implemented. For example: - Do the authors intend to start submitting closure cost estimates generated via RECLAIM V8 for all security-related reviews from the date of publication onward? Would this approach include existing projects that have previously had closure costs estimated using V7? Will the authors expect licensees and applicants to use RECLAIM V8 for all closure cost estimates from the date of publication onward? | Please describe how the authors intend to implement RECLAIM V8. | GNWT/CIRNAC
2 | Comparison against current estimates using RECLAIM V7 | The proposed updates in RECLAIM V8 are noted. Based on the proposed updates, closure cost estimates will be higher than when estimated using RECLAIM V7. This could have implications to the mining industry in the north, so it may be helpful for reviewers to have examples of how closure cost estimates using RECLAIM V8 differ from those generated using RECLAIM V7. | Is there data available that compares how closure cost estimates generated using RECLAIM V8 differ from previous estimates generated using RECLAIM V7? If not, could this data be prepared and shared? Or perhaps the authors could estimate how different the closure cost estimates will be? What are the potential implications to the mining industry in the north? | GNWT/CIRNAC
3 | Comparison against known costs to close and reclaim sites | Further to the comment and recommendation above, it may also help reviewers understand the purpose of the proposed changes to the RECLAIM model if data could be provided that compares actual costs to close and reclaim sites to estimates generated using RECLAIM V7 and V8, though, it is not apparent whether this data is available. | Have the authors undertaken an analysis that compares the actual costs to close and reclaim sites against closure cost estimates generated using RECLAIM V7 or V8? Can this data be provided? | GNWT/CIRNAC | There are sensitives with sharing this data
4 | RECLAIM Oil and Gas Model | It is noted this update pertains to the mining version of RECLAIM. Do the authors intend to update the oil and gas model as well? | Are there plans to update the RECLAIM Model for oil and gas? If so, are approximate timelines available, and would the process be similar to this update? If not, please explain why the oil and gas model will not be updated. | GNWT/CIRNAC
5 | User Manual - Discussion throughout on the status of Closure and Reclamation Plans. | The User Manual speaks to the need for applicants and licensees to have CRPs in order to develop closure cost estimates. In some instances, these speak to the need for an approved CRP. For example: - Section 2 Considerations for Northern Settings, “To derive accurate closure cost estimates, it is imperative that the company have an approved CRP which demonstrates a comprehensive understanding…”; and - Section 4.3.1 Engineering Desing, "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities." While it is important to develop a CRP to the point where it can be fully approved, this can take years (specifically for projects that require a type A water licence). This means that closure cost estimates developed during the application phase (pre-construction), during construction, and for the majority of the operational lifespan will be based on CRPs that have not been fully approved. This seems to be acknowledged in Section 4.3.6 Contingency where it is discussed that most CRPs for mining and associated estimates are at the feasibility or advanced conceptual level until near the end of operations. While this helps, it may reduce confusion further if the entirety of the User Manual recognized that CRPs typically require years of development to receive full approval. And for closure cost estimating purposes, it may be more realistic to indicate the applicant/licensee should advance the CRP as early as possible in the project lifecycle. | Consider whether the User Manual should be updated to clarify that it typically requires years to get a CRP fully approved and that applicants/licensees are encouraged to advance closure planning as early as possible. Consider revising certain messages, for example Section 2, to indicate, for closure cost estimating purposes, it is imperative that the applicant/licensee advance the CRP as early as possible in the project lifecycle. | Brodie
6 | User Manual - Definition of Contingency | A definition for contingency is provided in the Definitions and Acronyms table on page 4. A reference is provided from AACE costing terminology which seems to indicate this definition has been accepted by the construction or engineering community for costing purposes. However, it is not clear whether this definition aligns with how the term contingency is used throughout the document (specifically Section 4.3.6. Contingency) as well as how it is used for the purpose of generating a closure cost estimate via RECLAIM. For example the definition indicates contingency is "Typically estimated using statistical analysis or judgment based on past asset or project experience." Section 4.3.6 does not speak to statistical analysis, rather, the description in this section states "The determination of the contingency percentage is a subjective and project-specific task that relies on the judgement of the estimator." This could create confusion for applicants and licensees in terms of what they are expected to do when proposing contingency percentages. | Review the definition of contingency and consider whether it appropriately speaks to how users of the model are expected to derive contingencies. | Brodie
7 | User Manual - Section 4.2.5 | This section describes a worksheet within RECLAIM V8 for Interim Care and Maintenance. It states that this worksheet captures the costs from cessation of mining activities to when active remediation begins. Is this meant to only cover the time period from cessation until active remediation? What about the period up to executing closure activities - perhaps the use of the term remediation in this case is analogous to closure activities? Please note that remediation and reclamation in the general sense have different meanings. | Consider whether a revision is necessary to ensure this messaging covers the entirety of the intended period. For example, "the period between cessation of mining activities and when active remediation, or closure and reclamation begins." | Brodie
8 | User Manual - Section 4.2.6 | This section states "These should reflect the monitoring and maintenance plans and commitments identified in the Closure and Reclamation Plan" and later that "it reflects the monitoring and maintenance commitments in the Closure and Reclamation Plan." The LWBs' Standard Water Licence Conditions include Post-Closure Monitoring and Maintenance Plans, and it is typical for LWBs to require these for projects that require a water licence. Post-Closure Monitoring and Maintenance Plans are the home for the licensee to describe their approach to post-closure monitoring and maintenance. | Consider whether this section should be updated to also reference Post-Closure Monitoring and Maintenance Plans. | Brodie
9 | User Manual - Section 4.3 | The introductory sentence of this section speaks to indirect costs, indicating they are "typically allocated or spread across all activities on a predetermined basis." It is not clear what is meant by "predetermined basis," though, the final sentence in this section indicates indirect costs are calculated based on professional judgement. Either way, please note that this term / the way it is used could lead the user to think that they determine indirect costs, when, regulatory process-wise, the user proposes indirect costs, just like any other cost, and determinations are by the Land and Water Boards. | Consider clarifying the intent of the term "predetermined basis" and its usage, or whether another term could be used instead. | Brodie
10 | User Manual - Section 4.3 | The introductory sentence to this section seems incomplete: "Costs not directly attributable to the completion of an activity, which are typically allocated or spread across all activities on a predetermined basis." Pending any revisions as per the above comment and recommendation, should this sentence read as follows?: "Indirect costs are costs that are not directly attributable to the completion of an activity. They are typically allocated or spread across all activities on a predetermined basis." | Consider revising the sentence to improve clarity. | Brodie
11 | User Manual - Section 4.3 | RECLAIM V8 proposes an increase of 21% in indirect costs over RECLAIM V7, applied to the summary tab. The LWBs are responsible for setting the amount of security. Overall, it is challenging to consider what evidence is required to justify deviations from the "pre-determined" indirect costs when it is unclear how the "pre-determined costs" were derived. It is unclear what considerations went into deriving these percentages, except for the contingency indirect cost, and therefore how any deviations could be considered in the future. | Please clarify whether RECLAIM has considered deviations from the "pre-determined costs" proposed in section 4.3. Is additional information to support these pre-determined costs available? What evidence could be provided to support a deviation from these costs? | Brodie
12 | User Manual - Administrative Edits | It seems the hyperlinks in the User Manual do not work. | Review and insert links as necessary. | Brodie
13 | User Manual - Administrative Edits | Should Table 2 Column 3 be titled "Typical CRP Phase"? | For consideration. | Brodie
14 | Supplementary Information on RECLAIM V8 February 18,2025 | The supplemental information document references a "Technical Work Group and review of actual cost for Mine Closure and Reclamation at various locations across Canada." Further information beyond this has not been provided. It may be helpful to understand the range of projects and range of costs/percentages considered as part of developing the proposed indirect cost percentages. For example, the supporting information for Owners Representative states "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | If possible, provide additional information to understand the range of projects (e.g. size of project, type of mine: open pit, underground, etc.) and range of costs/percentages that were considered as part of developing the proposed indirect cost percentages in RECLAIM V8. | GNWT/CIRNAC
15 | RECLAIM V8 - New Line Item - Finalize CRP (% Closure Costs) | The ICM [Interim Care and Maintenance] tab of RECLAIM V8 includes a new line item titled, "Finalize Closure and Reclamation Plan (% Closure Costs)." This is calculated as 4% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between the cost of finalizing a CRP and the associated direct costs (i.e. closure work), and whether/how this considers how advanced the CRP is. This line item also does not seem to align with the text in section 4.3.1 of the Manual which states "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities (i.e. engineering is not required to develop a closure plan) and that there are no dramatic departures from the approved Closure and Reclamation Plan." | If possible, discuss how the 4% cost proposed was developed and whether/how this considers the varying degree of closure planning across different projects. | AtkinsRéalis
16 | RECLAIM V8 - New Line Item -HHERA (% Closure Costs) | The ICM tab of RECLAIM V8 includes a new line item "Human Health and Ecological Risk Assessment (HHERA; % Closure Costs)." This is calculated as 3% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between these direct costs and the development of an HHERA, and how the percentage was derived. | Please provide further information as to how the 3% cost proposed for HHERA was derived. | AtkinsRéalis
17 | Use of Historical Costs | The information provided indicates that costs to clean-up historical federal contaminated sites informed RECLAIM V8. It is noted that the regulatory context and expectations have changed significantly since some of those sites were operational/abandoned. It is unclear how/whether the change in regulatory regime and expectations was considered when reviewing these historical clean-up costs. | Please describe how/whether the change in regulatory expectations was considered when reviewing the historic clean-up costs of federally contaminated sites. | GNWT/CIRNAC
18 | Owners Representative | The supplemental information provided to support the indirect cost associated with "Owners Representative" references support to CIRNAC and scrutiny of the Federal Contaminated Sites Program. Given that the GNWT would be responsible for clean-up for the majority of current projects in the Mackenzie Valley, it is unclear whether GNWT has adopted this same approach to the clean-up of abandoned sites. | Clarify whether the GNWT has adopted this same approach of hiring an Owners Representative. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Independent Environmental Monitoring Agency - Jamie Mistry
1 | Post Closure – Annual Requirements | The Post-Closure sheet requires an estimate of annual costs and the number of years of post closure activities. The overall sum of activities is then multiplied by the number of years to give a total cost. Some post-closure activities will likely occur less frequently than annually, and the spreadsheet calculation will not function correctly in these cases. | Revise the Post-Closure sheet to include columns that list the frequency of each activity, and the number of events expected over the post-closure period, rather than assuming that all costs are annual costs. | AtkinsRéalis
2 | ICM – Water Management | The ICM sheet does not include activities specifically focused on water management during interim care-and-maintenance. These costs are also not specifically addressed in the Water Management or Water Treatment sheets. However, water management is often (perhaps usually) a primary focus of interim care-and-maintenance activities at mine sites, including during temporary closures and in the early stages before active implementation of a closure and reclamation plan. Requirements for accessing security bonds typically arise when there is an early, unplanned mine closure. In these circumstances water management is likely to be a significant activity for maintaining water levels in tailings ponds, managing flood flows, managing runoff from disturbed areas, and dewatering of mines (pits and underground). It is not uncommon for dewatering of mines to continue during periods of interim care-and-maintenance, especially in the event of early/unplanned closure when there may be interest in selling the project – allowing mines to flood is often considered to devalue the “asset” and therefore is part of the necessary care-and-maintenance activities. While there are currently no heap leach projects in NWT, water and solution management at heap leach mines is likely to be the largest cost during periods of interim care-and-maintenance. | Revise the ICM sheet to include activities focused on water management that will be required during interim care-and-maintenance. | AtkinsRéalis
3 | Interim Care-and-Maintenance | The Supplementary Information states that the default interim care-and-maintenance period in RECLAIM is 2 years, but the Interim Care-and-Maintenance (ICM) sheet in the model sets the value at 3 years. Past experience indicates that, in the event of early/unplanned mine closure, interim care-and-maintenance periods can be lengthy because of the time required to sort out financial matters, explore sale/re-opening options, complete CRP development/permitting and procure contractors. 3 years should be the minimum period applied. | Clarify the default duration of interim care-and-maintenance as 3 years, as currently applied in the model. | AtkinsRéalis
4 | Water Management - Sediment/Erosion Management and Control | The Water Management sheet addresses closure and reclamation of operational sediment control facilities. However, it does not directly address the potential need for continued sediment control measures during reclamation activities, or after reclamation activities are complete. This could require construction of new sediment control facilities or improvement (e.g., expansion, armouring) of existing ones. It could also require ongoing operational activities to manage sediment. | Revise the Water Management sheet to include lines related to development and implementation of sediment control measures for the closure and post-closure periods. | AtkinsRéalis
5 | UG Mine – Contact Water Management | The UG (Underground) Mine sheet does not include costs for treatment of mine water. The sheet appears to assume that underground mines will be flooded but no treatment would be required. Some mines may fill and drain over time, with water quality that is not acceptable for discharge. In other cases, leakage from the mine through groundwater is possible, again raising possible water quality concerns. These conditions may require some measures for ongoing or periodic water management or water treatment, including possible active or passive treatment outside of the underground mine, or some form of mine-pool treatment within the mine. | Add water management and treatment as potential costs in the UG Mine sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
6 | Chemicals – Soil Handling | The Chemicals sheet includes costs for excavating contaminated soils and transporting them to an onsite remediation facility, for example a land-farm. There will also be costs for rehandling these soils to a final disposal location at the conclusion of land-farming. | Revise the Chemicals sheet to include lines for final disposal of remediated soils. | AtkinsRéalis
7 | Post Closure – Maintenance | The scope of maintenance activities described in the Post Closure sheet is limited to covers, spillways and wetland treatment systems. For many mine sites, the maintenance requirements will be much more extensive. For example, tailings dams, diversions and sediment control facilities may all require maintenance. Passive treatment systems other than wetlands may also require maintenance or replacement. Wetlands may also require maintenance that is more extensive than what is described, including removal and replacement of substrates and vegetation after some period of time. In most cases, “passive” treatment systems require some periodic maintenance and operational activities, and are therefore better described as semi-passive. | Expand the maintenance components of the Post Closure sheet to address a broader scope of expected maintenance requirements. | AtkinsRéalis
8 | Rock Pile – Heap Leaching | According to the manual, the Rock Pile sheet is intended to address not only waste rock piles, but also heap leach facilities. Closure of heap leach facilities is usually substantially more complex than for rock piles. Heap leach facility closure entails continued solution circulation, heap rinsing, heap detoxification and associated water treatment, managed draindown, decommissioning of pumping and piping equipment, establishment of permanent drainage systems, among other things. The activities listed in the Rock Pile sheet are not adequate to address potential heap leach facility closure. | Incorporate specific activities and costing for heap leach facility closure in the model. | AtkinsRéalis
9 | Bldgs & Equip – Roads | The Bldgs & Equip sheet is missing some activities that may be common for closure and reclamation of roads. Reclamation frequently includes flattening of safety berms along the length of the road, and establishment of effective road blocks and any access points. Also, complete removal of roads back to the native landscape may be necessary in some cases, or overall re-grading of road embankments. Construction or upgrading of drainage works along road alignments may also be required. | Additional road reclamation and closure activities should be added to the Bldgs & Equip sheet. | AtkinsRéalis
10 | Mobilization – Annual Mobilization | The Mobilization sheet includes a column for quantity of mobilization with each type of equipment or supply. In some cases, mobilization/demobilization of equipment could be required annually through the closure and reclamation phase, or periodically during post-closure. For transparency, it would be useful to separate the quantity and the number of annual mobilization requirements – e.g., how many dump trucks have to be mobilized to site in each year. This would provide a better understanding of the equipment requirements and costs over time, and information about what equipment would be expected to remain on site year-round, versus mobilization each year. | Revise the Mobilization sheet to separately identify the annual mobilization requirements. | AtkinsRéalis
11 | Indirect Costs | The Summary Report and Supplementary Information describe the rationale for proposed changes in the default percentages for indirect costs. The rationale is consistent with experience from mine closure and reclamation projects and with current approaches to engineering. The Summary Report also notes that costs for mobilization and interim care-and-maintenance are now included in the base costs for calculating indirect costs. This also makes sense because both of these costs will be subject to the same indirect costs as the rest of the capital costs. | Retain the proposed default indirect costs percentages and the inclusion of mobilization and interim care-and-maintenance costs as part of the capital cost for calculating indirect costs. | AtkinsRéalis
12 | Summary – Indirect Costs | N/a | The updates to the recommended percentages for indirect costs appear to reflect the experience with mine closure and reclamation projects and should be retained. | AtkinsRéalis
13 | User Manual – Section 1 | The final bullet in the list of principles in Section 1 of the User Manual states that financial security must retain its full value throughout the life of the mine and if applicable, beyond. The value of required security may vary through the life of the mine and the wording of the principle should be clarified | The final bullet in the list of principles should be reworded to clearly state that adequate security must be in place throughout the life of the mine and in post-closure to fully address the liabilities associated with the site. | Brodie
14 | Summary – Future Value | The future value calculations appear to assume that the 3 year period of Interim Care-and-Maintenance starts immediately at the time the calculations are completed. This means that if the security amount is set based on today’s calculations, but unplanned closure begins 1 year later, the security will be 3% too low, or 16% too low if closure begins 5 years later. | The potential shortfall in liability estimates caused by assumptions about timing for the start of interim care-and-maintenance should be addressed in the model. One option is to establish requirements for frequent adjustments of security (e.g., every 2 years) to account for these shortfalls. | AtkinsRéalis
15 | Summary – Future Value | N/a | The addition of future value is a good idea and should be retained. | AtkinsRéalis
16 | Land Reclamation Activities | In response to a comment/recommendation to include a more comprehensive list of land reclamation activities in the model, the Supplementary Information responds that site-specific activities should be proposed based on end land use and the CRP. The response does not address the comment that was raised. Of course, site-specific closure activities should be defined in site-specific CRPs. However, the model is intended to provide a comprehensive tool for estimating costs of closure and reclamation activities, no matter what activities are selected for a specific site. As a result, the model should include a more comprehensive list of land reclamation activities and provide for estimating their costs, as suggested in the comment. The following comments below identify several specific instances where the model should be revised to include more comprehensive listings of activities. While this is likely not a complete list, it should be considered a starting point for more thoroughly identifying potential closure measures and activities. | Undertake a process to develop a more comprehensive list of possible closure and reclamation activities and incorporate these into the costing model. | AtkinsRéalis & Brodie
17 | Water Management - Reclamation Quarries | The Water Management sheet includes costs for installing and removing pumping systems for managing water in a reclamation quarry. Other costs associated with both quarry development (e.g., material testing, land clearing, road development, etc.) and water management (e.g., diversions, sediment control) for reclamation quarries are not addressed. Reclamation activities often require development of new quarries (in undisturbed areas, or in waste [e.g., overburden] storage facilities) or expansion of existing ones to provide the materials necessary for closure and reclamation. | The Water Management sheet should be revised to include lines that address additional water management activities that may be associated with quarries. Costs for quarry development should also be addressed within the overall model. | AtkinsRéalis
18 | Water Management – Passive Treatment | The activities identified for passive treatment are all associated with construction of wetland treatment. There are other forms of passive treatment that may also be relevant, for example permeable reactive barriers, bioreactors or underground mine pool or groundwater treatment. | The Water Management sheet should be revised to include activities that may be associated with other forms of passive treatment that are not wetlands. | AtkinsRéalis
19 | User Manual – Section 4.2.5 | Section 4.2.5 of the User Manual describes expectations for costing for interim care-and-maintenance activities. The description of a typical scenario states that open pit and underground mines would be allowed to flood. In cases of early or unplanned mine closures (i.e., where there are draws on security bonds), there are often lengthy periods of discussion about mine re-opening and sale. In these cases, mine dewatering often continues in order to avoid reducing the value of a potential asset. The assumption that mine dewatering would be discontinued may underestimate the actual costs that would be incurred. | The default assumption for interim care-and-maintenance costing should be that mine-dewatering will continue for this period. | Brodie
20 | Future Value and Unit Cost Updates | The Supplementary Information describes the new approach taken for estimating the future value for liability estimates. This approach is a positive addition and attempts to address the challenge that the security bonding regime and the forms of security do not allow for bond amounts to grow to address inflation and other escalation of costs. The User Manual defines “escalation” as “a provision in costs or prices for uncertain changes in technical, economic, and market conditions over time. Inflation (or deflation) is a component of escalation.” This acknowledges that inflation is only one component of escalation, with other components (e.g., labour market conditions in northern Canada, or availability of construction contractors) that may also lead to increases in costs. Nonetheless, the User Manual and model only rely on inflation as a cost escalator when calculating future value (Summary sheet) or for updating unit costs (Unit Cost sheet). Other than in the definition of “escalation” there is little further mention of other possible influences on cost escalation, though Section 4.5.1 of the User Manual does identify some other possible sources of information about escalation | Revise the User Manual and the model to require consideration of other factors for cost escalation. This should include requirements in the User Manual for proponents to provide rationale for selected escalation factors. In the model, it would be useful to include separate entries for inflation and other cost escalators so that there is a requirement to consider whether other escalators are relevant or not. | AtkinsRéalis & Brodie
21 | General Comment – Site Management | The model lacks clear information about person-hours for ongoing administrative responsibilities at the site, for example security, health and safety, personnel management, etc. during the implementation of the closure. Some of these are addressed for interim care-and-maintenance (e.g., on-site caretaker), but would also be required throughout the implementation of closure and reclamation. | Costs for ongoing site management should be addressed either in the Summary sheet, or an additional Site Management sheet should be added. | AtkinsRéalis
22 | Water Treatment – Post Closure | The post-closure component of the Water Treatment sheet does not address major maintenance and equipment replacement activities. Water treatment facilities that have to operate in a long post-closure period will wear out and require refurbishment and replacement at some point in time. Costs and timing for these major capital expenditures need to be included. | Revise the Water Treatment sheet to include lines for costs related to major refurbishment or replacement of post-closure water treatment facilities. | AtkinsRéalis
23 | General | The Independent Environmental Monitoring Agency (Agency) has reviewed the proposed changes for RECLAIM v8.0 and associated user manual (RECLAIM) submitted by Crown-Indigenous Relations and Northern Affairs Canada (CIRNAC) and the Government of Northwest Territories (GNWT). The Agency submits the following comments for your consideration. | N/A | AtkinsRéalis | See Comments 24 to 32
24 | User Manual – Section 1 | Section 1 of the User Manual states a principle that costs should be based on having a third-party contractor carry out the reclamation work. On-site equipment including both mobile equipment and fixed facilities (e.g., water treatment plants) may not be owned by the proponent and costs would be incurred to access the equipment and facilities. | The principle that costs should be based on the cost of having work done by a third-party contractor should be expanded to clarify that the costs must also be estimated assuming that all equipment, supplies and facilities will be provided separately. | Brodie
25 | Tailings – Water Treatment | The Tailings sheet refers to treatment of seepage, which may not be the only treatment that is required for a tailings facility. In some cases, treatment of tailings pond supernatant water may also be required, either during implementation of closure and reclamation, or post-closure. | Revise the water treatment references in the Tailings sheet to include broader references to types of treatment that may be required. | AtkinsRéalis
26 | Open Pit – Pit Closure Methods | The Open Pit sheet considers a narrow range of potential closure options for pits, focused on flooding of pits. There are other options for closure of pits that need to be addressed. For example, some pits may be closed in a dry condition, with associated water management, or some may be backfilled with waste and covered (e.g., Giant Mine Remediation Project). | Revise the Pits sheet to address a broader range of closure options for pits. | AtkinsRéalis
27 | Open Pit – Contact Water Management | The only water treatment option addressed in the Open Pit sheet is the possible addition of in-pit treatment during flooding – either by chemical or biological means. There is no water treatment line linked to the Water Treatment sheet. However, there are some instances where it may be necessary to actively pump and treat water that has accumulated in a pit, potentially before flooding, or to establish dry conditions. | Add active water treatment as a potential cost in the Open Pit sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
28 | HHERA and Regulatory | The Summary Report states that the model was revised to include 3% indirect costs for Human Health and Ecological Risk Assessment (HHERA), and 4% indirect costs to finalize the Closure Reclamation Plan (CRP). These additions make sense, but it is unclear where they are included in the model. If they are already included in the Summary sheet calculations, they should be specifically identified. | Provide additional clarity about where the indirect costs for HHERA and CRP finalization are incorporated into the model. | AtkinsRéalis & Brodie
29 | General Comment – Winter Road costs | The Water Treatment and Mobilization sheets include lines for costs associated with use of the winter road. In Water Treatment this appears to be related to site access and reagents, while in Mobilization it is related to equipment, fuel and accommodation (i.e., camp), with a focus on materials that must be brought to site. However, closure for some other components (e.g., buildings, hazardous wastes, contaminated soils) may require shipping off site. Also, it is not clear that winter road costs have been incorporated for all closure and reclamation supplies, for example liner construction materials. These activities may also incur winter road costs. | Where closure and reclamation activities will require off-site shipping or the delivery of supplies to site, sheets should be revised to include lines for winter road costs and other shipping costs. | AtkinsRéalis
30 | Summary – Future Value | The spreadsheet requires the user to enter timing for “when will post-closure begin”, by entering a number. Some additional clarity should be provided about what this number represents: Is it the number of years from the current time until post-closure, or the number of years between cessation of operations and post-closure, or the number of years after completion of interim care-and-maintenance before post-closure begins, or some other value? If the timing is intended to start at the time that the estimate is made, then the same shortfall issues identified above for the interim care-and-maintenance timing will also apply to the timing for start of post-closure. | Clarify the intended definitions of timing for when post-closure will begin. | AtkinsRéalis
31 | User Manual – Section 2 | Section 2 of the User Manual describes special considerations for estimating costs for reclamation activities in northern settings. One important factor that appears to be missing is the potential cost implications of meeting requirements for northern participation in contracting and work opportunities. | The bullet list of factors that may affect costs for projects in northern settings should be expanded to include the potential for increased costs associated with meeting requirements for northern participation in reclamation activities. | Brodie
32 | Buildings & Equipment (Bldgs & Equip) – Landfill | The Bldgs & Equip sheet addresses closure of landfills (e.g., placement of cover material) but it does not cover the cost of constructing a landfill. Even for non-hazardous materials, construction of landfills can be a substantial cost. Landfills developed and used during mine operations typically do not have capacity to contain all of the material arising from closure and reclamation. Costs for non-hazardous landfill construction can be substantial in some cases (e.g., Giant Mine). | Revise the Bldgs & Equip sheet to include costs for development and construction of landfills. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Teck Metals Ltd. - Dr. Bjorn Weeks
1 | Feedback Letter | Please see initial feedback in the attached letter. Inflation Application Without Discounting. The RECLAIM 8.0 update proposes incorporating inflation into cost estimates but does not address the standard practice of discounting to reflect the time value of money. Applying inflation without discounting leads to distorted financial obligations, potentially resulting in excessive and unrealistic financial security requirements. Without discounting, even minimal recurring annual costs (e.g., $20,000 per year) would result in infinite bonding requirements, which contradicts financial principles and international best practices. Financial assurance practices that deviate substantially from international best practices may place the region at a competitive disadvantage, while failing to deliver real benefits | Paraphrased: Include discounting into cost estimate | GNWT/CIRNAC
2 | Feedback Letter | Please see initial feedback in the attached letter. Absence of Any Credit for Company Size and Environmental Performance We believe the bonding requirements should take into account both past environmental performance and the financial resources available to the company to meet its environmental liabilities. Teck is one of several International Council on Mining and Metals (ICMM) member companies operating in the region. No ICMM member company has ever defaulted on its closure obligations, nor would doing so be feasible in the context of maintaining a global social license to operate. | Paraphrased: Credit for environmental performance and the financial resources | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm
1 | Increased Unit Costs | Please see initial feedback in the attached letter. The justification for increased excavation and hauling costs (e.g., short-haul soil movement increasing from $4.3/m³ to $17/m³) lacks transparency on how these figures were derived. What specific contractor quotes, productivity rates, or haul distances were used in these calculations? Were regional variations considered, or was a blanket rate applied regardless of site-specific factors? Can industry propose alternative short-hauling costs based on regional/site-specific factors such as terrain, available borrow pits, road conditions, access to rail, and equipment availability? For example, a mine site with established all weather and paved road networks and short, efficient haul routes may have significantly lower hauling costs than a remote site requiring seasonal ice road access. Will proponents have flexibility in presenting alternative cost estimates to justify lower unit costs? | Paraphrased: Provide more detail on unit rate development. Unit rates should include regional variation. Clarify if user-specified rates can be used in RECLAIM. | AtkinsRéalis
2 | Higher Indirect Cost Percentages | Questions Asked Contingency Increase (20% to 25%): While uncertainty exists in closure planning, what empirical data justifies a 25% contingency rather than the previous 20%? Can examplesof cost overruns from past projects be provided to support this increase? Engineering Design (5% to 8%) & Project Management (5% to 10%): These increases suggest significantly greater complexity in closure execution. What historical data from northern mine sites demonstrate that these cost assumptions are necessary? Bonding/Insurance (1% to 3%): Can specific case studies or actuarial assessments be provided to validate this change? | Paraphrased: Provide further justification to increased contingency percentages. Provide further northern justification to increased engineering design percentages. Provide case studies to justify increase in bonding/insurance percentage. | AtkinsRéalis
3 | Reclassification of Mobilization and Interim Care & Maintenance (ICM) as Capital Costs | Moving these costs to Capital Costs now subjects them to contingency and indirect cost multipliers. How does this align with the principle of accurately reflecting third-party contractor costs? Industry projects varying durations of ICM depending on site conditions. How was the assumption of a minimum 3-year ICM period determined, and why is it being applied universally? | Paraphrased: Include more rationale as to why Mob and ICM were moved to Capital Costs and whether this accurately reflects third-party contractor costs. Provide rationale and justification for minimum 3-year ICM period. | AtkinsRéalis
4 | Owner’s Representative Cost (10% of Direct Costs) | This is a new addition to RECLAIM. While we acknowledge the role of an Owner’s Representative in some government-managed projects, why is this now mandated for all projects, including those with active operator management? Can industry proponents provide alternative methodologies for project oversight rather than defaulting to a 10% additional cost? | Paraphrased: Provide rationale for why Owners Rep costs are applied to all mines. Can industry propose an alternate methodology for oversight rather than the default. | AtkinsRéalis
5 | Human Health and Ecological Risk Assessment (HHERA) Cost (3% of Capital Costs) | Industry already conducts environmental monitoring as part of regulatory requirements. What additional studies are being assumed under this cost, and how is the 3% figure justified? Given that mines with comprehensive monitoring programs may already demonstrate minimal risk, why is this cost not applied selectively based on site-specific needs? Can proponents outline their monitoring programs and propose a more phased cost-structure alignment with project-specific timelines? | Paraphrased: Can CIRNAC and GNWT provide additional studies to industry to justify the 3%? HHERA should be applied to mines selectively based on environmental performance. There should phased cost structure that could align with project timelines. | AtkinsRéalis | Not sure what is meant with third recommendation.
6 | Future Value Calculation (3% Inflation Rate) | While inflation is a factor in cost projections, applying a fixed 3% escalation rate does not account for fluctuating economic conditions. Has any sensitivity analysis been conducted to assess alternative inflation scenarios? Can proponents propose their own escalation methodologies based on contractual arrangements and project-specific timelines? | Paraphrased: Sensitivity analysis should be conducted on applying a fixed inflation rate for future value calculations. Proponents should be able to propose their own escalation methodologies based on contractual arrangements and project-specific timelines. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
De Beers Canada Inc. - Gahcho Kue - Kurtis Trefry
1 |  | De Beers is supportive extended engagement period granted to allow further opportunity for industry feedback to be considered into any changes. The initial deadline coincided with our annual reporting timelines, creating challenges in dedicating the necessary time and resources to this review. The additional time granted will allow us to prepare a thorough and well-considered submission that adequately addresses the updates. Given the potential for significant implications to the mining industry, the proposed changes to the RECLAIM model require significant time and resources to allow for a detailed review by all parties. De Beers looks forward to partaking in further engagement sessions and will provide more detailed comments following that period. | N/A | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Fisheries and Oceans Canada (DFO) - Mr. Derek Donald
1 | Financial security associated with Fisheries Offsetting Plans. Specified under Section 2 (1)(b) and Schedule 1, Section 16, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations. | Fisheries and Oceans Canada (DFO) would like to thank CIRNAC and the GNWT, for developing and updating the RECLAIM model and providing this opportunity for review and comment. The RECLAIM model can be an important part of the Fisheries Act authorization process in that the model is often used by proponents when developing an itemized list of costs for conducting the Offsetting work and monitoring the project to inform the Letter of Credit associated with an Offsetting Pan, and by DFO when reviewing the financial liability associated with these plans. Fisheries Act authorizations can follow the lifecycle of a mine from pre-operational permitting to post-closure Offsetting Project monitoring. Financial liability and associated security in the form of an irrevocable Letter of Credit, is a key component of the Fisheries Act and associated Regulations. Mine development in Nunavut and the Northwest Territories often necessitates activities that directly or indirectly result in the Death of Fish, the Harmful Alteration, Disruption or Destruction of fish habitat, and/or the deposit of deleterious substances in water frequented by fish, governed respectively by Section 34.4, 35, and 36 of the Fisheries Act. These activities can be authorized under the Fisheries Act so that the activity is carried out in accordance with conditions set out in the authorization and the Regulations. Section 2 (1)(b) and Section 16 of Schedule 1, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations, requires the development of a Fish Offsetting Plan, including the financial liability and associated security, to cover the costs of implementing the fish Offsetting Plan. These Fish Offsetting Plans often include activities associated with general construction, ground and water works, culvert installation, long-term monitoring, etc. Costs associated with these Fish Offsetting Plan activities can be subject to individual cost estimates based on a proponent’s experience and can also be scrutinized with limited referenceable sources. This type of subjective cost estimation and review creates risk and introduces uncertainty, for both proponents and liable governmental parties (DFO and ECCC). DFO believes this update to the RECLAIM model is an excellent opportunity and the appropriate location to include constrained cost estimates for these types of activities. DFO would like to discuss this further with CIRNAC and the GNWT during the week of May 12 - 16, 2025. DFO would also be interested in hearing feedback from all interested parties. | DFO recommends that the RECLAIM Model include in a Summary line item, and associated sheet in the Excel model specific to the implementation of a fish Offsetting Plan. This could include, but not limited to works associated with discipline specific construction, ground and water works, culvert installation, and long-term monitoring. Adding this to the model would reduce financial risk by providing a more predictable process of securing a Fish Offsetting Plan, which is ultimately tied to the final reclamations of a mine site that has impacted fish and fish habitat. DFO would like to discuss this possibility with CIRNAC, the GNWT, and all interested parties during this update of the RECLAIM model. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo
1 | Letter | Please see attached letter.
2 | Origin of Unit Rates | Burgundy Diamond Mines (Burgundy) and other proponents have been requesting that CIRNAC and GNWT provide the level of transparency and justification for RECLAIM unit rates that is demanded of proponents who put forward site-specific unit rates. This long-standing request remains wholly unsatisfied by the information provided with RECLAIM 8.0. For example, the proposed "load/haul/place" unit rates are described as being derived from "First Principles". However, simply referencing "First Principles" and listing a few assumptions under additional notes does not provide proponents with the information needed to adequately understand the unit rate or assess appropriateness for a specific site. | RECLAIM 8.0 should be accompanied by clear, detailed data on the derivation of the proposed unit rates, ensuring proponents can adequately understand the rates and make a rational determination of their appropriateness for an individual site or closure activity. | AtkinsRéalis
3 | Moving Mobilization and ICM to Capital Costs | Mobilization and ICM costs were previously included under Indirect Costs which excluded them from the indirect percentage calculations. The new approach introduces a compounding effect and will significantly inflate the overall security estimate. This would result in overestimations that do not accurately reflect actual closure and reclamation needs particularly for major operations such as Ekati Diamond Mine (Ekati) with substantial security requirements. | The Mobilization and ICM costs should be maintained under Indirect Costs where the existing indirect cost percentages can adequately account for variations. This would avoid the compounding effect introduced by their inclusion in Capital Costs while still ensuring these costs are adequately captured within the model. | AtkinsRéalis
4 | Owner's Representative | A new line has been added under Indirect Costs for Owners Representative to ensure that project objectives are met, with a default percentage of 10% of the direct costs assigned. The assigned percentage appears excessively high particularly for licencees with substantial direct costs. | The assigned 10% default percentage should be reevaluated and a reduction considered to better align with actual project requirements and industry norms. Additionally, more information should be provided to clarify the methodology and rationale behind determining this percentage and to assess its applicability across different projects. An alternate approach, such as an estimated cost (rather than a percentage) should also be developed and evaluated. | AtkinsRéalis
5 | HHERA and Final CRP Costs | The cost to complete a Human Health and Ecological Risk Assessment (HHERA) and Final Closure and Reclamation Plan (FCRP) has been added to the model at 3% and 4% of Capital Costs, respectively. While it is acknowledged that FCRP costs may not have been explicitly included in RECLAIM 7.0, the regular review of security estimates has ensured their incorporation for operations like Ekati. The most recent review by the GNWT in 2022 determined a significantly lower FCRP rate of approximately 1% of direct costs. There is no rationale for applying these items as a percentage of total rather than an estimated cost. These items are well established and well defined in scope and cost such that actual estimates can readily be developed. A percentage of total as proposed provides a grossly over-costed estimate for large site such as Ekati. Moreover, the risks addressed by HHERA are already evaluated as part of the permitting process. Monitoring data is utilized to assess operational and closure risks, which are accounted for in interim CRPs that are mandatory and regularly updated. As such, the addition of these costs in the proposed model is deemed unnecessary and the proposed percentages appear excessively high. | Burgundy recommends that HHERA and FCRP costs be excluded from the model. Alternatively, these percentages should not be based on Capital Costs given that risk evaluations and FCRP development will rely significantly on existing assessments and CRP plans developed during ongoing operations. A reduction or redefinition of these percentages is necessary to ensure they more accurately reflect the actual scope of work and associated costs. An alternate approach of an estimated cost (i.e., not a percentage) should be developed and evaluated. | AtkinsRéalis
6 | Future Value Calculation | The future value calculation has been introduced to capture the anticipated costs of activities based on when they are expected to occur. A default inflation rate of 3% is applied which corresponds to the Bank of Canada’s upper target for annual inflation. For example, a cost estimate developed in 2028 using RECLAIM 8.0 standard rates would undergo a 3% annual inflation increase over four years (2024 to 2028). However, applying a predetermined, singular inflation rate is not appropriate when actual data is available. It is also not always suitable to apply the same inflation rate across all work included in a closure estimate. RECLAIM 8.0 documentation acknowledges the existence of various inflation estimates beyond the broad-based consumer-oriented CPI, but it discounts these approaches. Since the majority of mine closure plan costs are not consumer-oriented, it may not be appropriate to apply the general CPI across the entire estimate. Ekati's security estimates already incorporate an inflation calculator developed with stakeholders' input. This calculator considers the development year of each unit cost and applies inflation rates accordingly, resulting in inflation rates of less than 2%. Applying the upper target of the Bank of Canada’s inflation range may lead to overestimations, given that average inflation rates have remained between 1.5% and 2%. This approach is not ideal for long-term mine closure costing, as it introduces inflation without accounting for interest. It assumes that the financial security is cash in hand, which does not accrue interest over time. By comparison, the Province of British Columbia uses a net discount factor (i.e., net of both inflation and interest) for recurring long-term costs. The approach proposed in RECLAIM 8.0 introduces a substantial cost factor that could significantly affect project viability. This issue requires detailed engagement and financial analysis by the government before any consideration for implementation. | 1. RECLAIM 8.0 should provide a clear rationale for adopting a single pre-determined inflation factor and consider developing an alternative approach that utilizes inflation rates most appropriate to the specific work and costs within the closure cost estimate. The future value inflation rate should be revised to reflect a more accurate figure, such as the average of historical inflation data over a relevant timeframe, rather than defaulting to the upper target of 3%. This adjustment would result in a more balanced and accurate estimate, avoiding excessive conservatism in the model. Additionally, greater transparency is needed in how inflation rates are applied to different unit costs over time to ensure consistency and confidence. 2. This cost item should not be implemented without specific, in-depth engagement and financial analysis including an evaluation of experiences in other regulatory jurisdictions. | GNWT/CIRNAC
7 | Incentivizing Progressive Reclamation | The proposed updates to RECLAIM 8.0 emphasize increasing securities to address potential reclamation costs. It is equally important to incentivize progressive reclamation during operations. Progressive reclamation not only reduces overall closure liabilities but also demonstrates ongoing commitment to environmental stewardship. Models used in jurisdictions such as Quebec and the Alberta oilsands provide practical examples of incentivizing progressive reclamation by allowing operators to utilize existing securities during operations, thereby encouraging earlier action rather than deferring it until closure. | Burgundy recommends that the GNWT implement mechanisms to incentivize progressive reclamation activities during operations. This could include provisions that allow for the partial release or reallocation of securities to fund reclamation efforts. Such measures would enhance operational efficiency, reduce the financial burden of increasing securities and encourage operators to proactively incorporate reclamation into their operational plans. This approach would ultimately lead to more sustainable and cost-effective closure outcomes. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Tlicho Government - Jessica Pacunayen
1 | General | The Tłı̨chǫ Government reviewed CIRNAC and GNWT's proposed revisions to RECLAIM 8.0, the RECLAIM User Manual, and supporting documentation. These documents are used by the GNWT, CIRNAC, mining companies, and the Land and Water Boards to set mining security deposits. RECLAIM and the User Manual are also a resource for all parties reviewing security deposits. Tłı̨chǫ Government may also wish to use RECLAIM to estimate security deposits for future mines on Tłı̨chǫ Lands. | N/A | GNWT/CIRNAC
2 | Increased security deposits | RECLAIM 8.0 includes numerous substantial increases. Most unit costs went up to varying degrees, and a few went down. On average unit costs appear to have more than doubled. Some key unit costs have increased far more than this, for example the lower estimate for winter road construction went up by more than 10 times. Indirect costs are now up to 58% of direct costs instead of 32%, plus there are new costs for a human health and ecological risk assessment and finalization of the closure plan (totaling 7% of capital costs). There is also a newly proposed cost for inflation during closure and post-closure. Post-closure monitoring and maintenance and mobilization/demobilization now have indirect costs (as percentages) added to them. These and other increases would result in very large increases to security deposits at existing mines. CIRNAC/GNWT explained that the increases are because the current unit costs (in RECLAIM 7) are more than 10 years old and because costs in the current RECLAIM spreadsheet (version 7.0) are too low compared to actual costs the government has incurred for actual reclamation projects. As noted in "Review of Mine Financial Security Estimates and RECLAIM": "it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." CIRNAC and its consultants are perhaps in the best position to provide actual costs of closure activities. There has been talk over the years that RECLAIM is dramatically underestimating closure costs. It is possible that even with the proposed revisions, RECLAIM 8.0 would continue to underestimate reclamation costs. For example, the Supplementary Information provided on Feb 18 says that the Owner's Representative costs are actually 12% to over 20% of costs, not the 8% adopted in the proposed revisions to RECLAIM. This is just one of several examples that may mean the RECLAIM 8.0 continues to underestimate reclamation costs. Others are in comments below. | RECLAIM should estimate the actual costs of closure and reclamation, even though it appears that the new estimates will likely be much greater than current security deposits. However, this does not mean that the Boards should immediately increase all security deposits in the North to reflect actual reclamation costs. This could have serious economic and social repercussions, and could undermine the objectives set for resource management under the modern treaties, to balance conservation and development for 'optimum benefit'. Instead, updating RECLAIM to reflect actual costs is a necessary first step to fixing some serious and far-reaching problems related to security deposits and more broadly to sustainable and responsible mining in the North. Actual reclamation costs must be known and on the table in order to have informed discussions about the impacts, benefits, and risks of mining, including the risk of having to pay for cleanup of abandoned mines. Underestimating security can also enable companies with insufficient financial resources to mine in the North, which poses a serious risk to the Northern economy and the environment. Greater attention should be given to a mining company's financial health and the risks for each project (e.g., risks from market conditions, remoteness, logistical issues, etc.) when weighing the impacts, benefits, and risks of approving a full-scale mine. Decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis, and input from citizens and residents. If the federal and territorial governments, or the Boards in working to achieve the treaty-based objectives for resource management, wish to offset the burden of posting security for actual reclamation costs, this should be done in a transparent, carefully considered manner informed by the actual costs of clean-up and the views of all parties. The Tłı̨chǫ Government would like to be involved in any such discussions, and as a treaty partner, must be involved in these discussions. Other topics raised in our comments are inextricably intertwined with the issue of RECLAIM estimates, for example relinquishment of liability, promoting progressive reclamation, and financial security for potential disasters. These issues should be discussed holistically along with RECLAIM updates. Some of these issues may need legislative amendments to properly address them in the long run. | GNWT/CIRNAC
3 | Increased security deposits - incentives for progressive reclamation | The RECLAIM Manual includes a policy that the security deposit cannot be reduced for progressive reclamation (reclamation completed during operations) until the mining company has completed the reclamation work. This is a sensible approach to ensure there is always enough money for reclamation if a company goes bankrupt. However, a more refined and strategic approach to this problem should be considered to enable work to proceed while limiting risks if a company goes bankrupt. This would allow more parts of a mine to be reclaimed early in the mine life, which benefits the environment, the taxpayer, and the company. A company's financial capacity, the financial and environmental risks of leaving parts of the mine unreclaimed, and other factors would need to be considered. | Financial mechanisms to promote progressive reclamation should be evaluated and discussed with all parties. | GNWT/CIRNAC
4 | Increased security deposits - case studies | Based on our participation at the meeting hosted by CIRNAC and GNWT during the PDAC conference in March 2025, we understand there may be disagreement over whether RECLAIM 8.0 is overestimating or underestimating closure costs. CIRNAC and the GNWT have actual cost data from abandoned mine reclamation in the North. Using this data to validate RECLAIM 8.0 is an indispensable step to deal with these opposing views and to ensure security deposits cover the full costs of reclamation without unduly burdening industry. The Discussion Paper says that CIRNAC and GNWT had originally intended to use historical data to help populate RECLAIM 8.0 (which is different than historical data for validation). However, the Discussion Paper says this did not happen because "contractor confidentiality, limited examples available to provide a sufficient range and average of costs (which can vary considerably depending on the size and scope), and the effort required to synthesize data." While these issues might make it challenging to use historical cost information to update RECLAIM 8.0's costs and assumptions, it should not prevent validation of the model. Validation is about running information from past projects through RECLAIM 8.0 and comparing this to the actual cost of the project. If confidentiality issues cannot be addressed, CIRNAC and GNWT should at least conduct this validation step internally and publicize whether the exercise validated the model. Further, "the effort required to synthesize data" may be a barrier, but it is arguably a relatively small price to pay compared to the benefits of improved cost estimates. In addition to this validation step, CIRNAC and GNWT should use historical cost data to improve RECLAIM. Based on the unit cost reference tables provided as supporting documentation, it appears this may have been done to some extent. If not, CIRNAC and GNWT should take advantage of historic cost data in ways that maintain confidentiality and account for limitations in the data. | 1. Before finalizing RECLAIM 8.0, CIRNAC and GNWT should validate it, by running RECLAIM (i.e., entering actual quantities, selecting the appropriate unit costs, etc.) with information from actual reclamation projects at abandoned mine sites. The resulting RECLAIM 8.0 estimate should be compared to the actual cost. If these are substantially different, adjustments should then be made to RECLAIM 8.0 from lessons learned from this comparison. 2. Historical cost data should also be used, to the extent possible, to update RECLAIM with actual cost information, without compromising confidentiality. | GNWT/CIRNAC
5 | Internal government costs | RECLAIM does not include the substantial internal costs for CIRNAC and GNWT, for example government employee salaries. This means there is no transparency about what these costs are or what the actual costs are when a mine is abandoned. | Please explain why these costs are not considered when estimating the costs of reclaiming a mine. | GNWT/CIRNAC
6 | Calculating security annually | The proposed RECLAIM Manual update includes a new requirement that "The total financial security for final reclamation required at any time during the life of the mine should be equal to the total outstanding reclamation liability for land and water combined (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period)." This mirrors the Mine Site Reclamation Policy for the NT, which is well over 20 years old. It is not clear how this would be implemented. Is GNWT/CIRNAC anticipating that water licences would have a schedule with annual increases to security? This has not been recent practice. Or is a RECLAIM review anticipated each year? TG is concerned that this would place a big resource demand on all parties. Also, how would the common practice of increasing security at project milestones (e.g., commencement of construction, mining, or milling, percent of pit filled, etc.) fit into this approach? | Clarify how this requirement would be implemented. | GNWT/CIRNAC & Brodie
7 | Human health and ecological risk assessment | The proposed revisions to RECAIM include the cost of a human health and ecological risk assessment (HHERA). The User's Manual notes that this is completed in accordance with federal risk assessment guidance. Modern mines are different than mines abandoned in the past in that they have approved closure objectives and in many cases, approved closure criteria. It is our understanding that, in the past, HHERAs at federal sites have been used to set the standard for cleanup, for example the water or soil contaminant thresholds that must be met. If a modern mine is abandoned during operations and is in compliance with its water licence, land use permit, and other authorizations, unexpected contamination (beyond what is addressed in the approved closure plan) may be less than in the past. Some mines may include an HHERA in their approved closure plan to confirm predicted risks. However, it is not clear what role an HHERA would play at an abandoned mine. We are concerned that use of HHERA's could lower the standard compared to approved closure criteria. Closure criteria have been publicly reviewed, vetted and debated in countless workshops, and represent substantial input from all parties. Closure criteria have been deliberated by the Boards and Board decisions on them have been transparently documented. Ignoring approved closure criteria after abandonment would be inconsistent with the land claim agreements that established the Land and Water Boards. | If an HHERA is part of an approved closure and reclamation plan, then the cost of it should be in RECLAIM. Also, if the GNWT and CIRNAC expect that new risks will emerge after abandonment of mines with modern, approved closure plans, then an HHERA should be a default cost in RECLAIM. However, the RECLAIM Manual should acknowledge that Board-approved closure criteria are the clean-up standard at abandoned mines, unless it is demonstrated that these cannot be achieved or that new criteria are needed for risks that developed after abandonment. An HHERA may play a role in this effort, but HHERA's should not be a replacement for closure objectives and criteria. | AtkinsRéalis & Brodie
8 | Monitoring | The draft RECLAIM Manual says that monitoring will be conducted "with respect to the effectiveness of the mitigative measures, the accuracy of the environmental assessment and any unforeseen environmental impacts". Although true, this statement does not appear to reflect current practice. To our knowledge, all closure plans (and therefore security deposits) in the NT are founded on the MVLWB/AANDC Guidelines for the Closure and Reclamation of Advanced Mineral Exploration and Mine Sites in the Northwest Territories. Therefore, all mines have Board-approved modern closure plans that are based on closure goals, principles, closure objectives and closure criteria. This means closure criteria will dictate monitoring plans and duration. The effectiveness of mitigative measures and the accuracy of the environmental assessment will be reflected in the criteria. If there are unforeseen environmental impacts, closure criteria should be updated. | The RECLAIM Manual should state that monitoring will depend on closure criteria. | Brodie
9 | Relinquishment of liability | The revised Manual states that "Following mine closure, mining companies or their future owners should continue to be responsible for the site , including the remediation of any additional environmental complications which develop." This raises questions about relinquishment of liability. For many years, many parties have been requesting clarity on how liability will be relinquished at mine closure. This is especially important with mines like Diavik approaching the end of operations. This gap creates uncertainty and may inhibit investment in sustainable and responsible mining in the North. | 1. It is understood that additional policy, legislative, or regulatory amendments may be needed to address how and to what extent companies are released from liability once all closure criteria have been met. For example, will companies be required to leave funds for future monitoring, maintenance, or unforeseeable events at the closed mine? These funds may require supporting legislation and/or policy. Even if the GNWT cannot undertake an effort to better address relinquishment before the RECLAIM updates are finalized, the Manual (or another document) should include more information on this topic. This would assist all parties in understanding how GNWT and CIRNAC will approach relinquishment of liability under existing legislation. 2. The GNWT and CIRNAC should immediately begin the effort to outline the conditions and criteria that will allow relinquishment, establish how much money will be required for monitoring, maintenance and unforeseeable events, clarify the extent to which companies will be released from liability, and develop a relinquishment process. This effort will need to involve Indigenous Governments early on. | GNWT/CIRNAC
10 | Performance holdback | The revised Manual states that "If the company carries out progressive reclamation during operations as proposed, such as revegetation of disturbed areas during operations, then the closure cost estimate could be reduced by the associated costs for that component when the company demonstrates that the closure activity has been successfully completed and closure objectives and criteria have been met." It is our understanding that the LWB/GNWT/CIRNAC Guidelines for Closure and Reclamation Cost Estimates for Mines allows for some money to be refunded to companies, even if criteria have not been met. This is allowed so long as a performance holdback is set. The same Guidelines explain how a performance holdback could be set, including three different methods. The first method uses a simple percentage-based approach by mine component, the second method uses RECLAIM, and third uses a "factored risk" approach. | RECLAIM should reflect the CIRNAC/GNWT/LWB Guidelines as they relate to performance holdbacks. Calculations based on the Guidelines should be inserted into RECLAIM. This would include simple calculations supporting Table 1 of the Guidelines (the percentage-based approach). It could also include calculations to support the "factored risk" approach on page 19 of the Guidelines. Support for companies to estimate performance holdbacks will promote a quicker and more efficient security refund process. Although all regulators that use RECLAIM may not require performance holdbacks, those regulators could simply ignore the calculations, or the GNWT could develop them for use in the NT only. While it is beneficial to have only one version of the RECLAIM model across the North, add-ons to reflect jurisdictional differences could help to ensure that RECLAIM is useful everywhere while maintaining a core set of shared calculations and inputs. | GNWT/CIRNAC & Brodie
11 | Documentation of security refunds | Similarly, security refunds for completed progressive reclamation or completed work during active closure is becoming more common and is an important way to promote and reward early closure work. Currently, RECLAIM does not document these refunds, which means there is no record of the original estimate, the refunds given, and what the refund was based on. This may make it difficult to determine refunds during active closure, since it may not be clear what has already been refunded and what is still being held as security. | RECLAIM should document all security refunds. For example, RECLAIM could include a refund summary sheet showing the original estimate, all refunds, and links to documentation supporting the refund (e.g., RECLAIM estimates used to calculate refunds, Board decisions, etc.) | Brodie | This cost estimating tool is not the mechanism for tracking security refunds
12 | Disasters | RECLAIM does not cover the costs of disasters. With numerous mines using the RECLAIM model across Canada's North, there is a significant risk that one or more of these mines will have an environmental disaster during the life of the mine. Currently, disaster clean-up costs would fall entirely to the taxpayer. The recent disaster at the Eagle Mine in Yukon is an excellent demonstration of how the taxpayer will be forced to carry the burden of disaster clean-up. Such costs could easily be in the hundreds of millions of dollars or more. The Mount Polley disaster in 2014 is another example of taxpayers covering significant costs for a mining disaster. Although this may be considered a policy decision that is outside of the scope of RECLAIM, RECLAIM by necessity houses many policy decisions by virtue of the costs it includes or excludes. RECLAIM unavoidably sets policy through its underlying principles and assumptions. Excluding disaster costs is as much a policy decision as including them. | Security for potential future disasters should be required. Since most mines are unlikely to experience a disaster, the amount held by any single mine should only be a fraction of potential disaster clean-up costs. This could be determined based on the risk profile of a project (e.g., potential for acid drainage, geotechnical failures, proximity to highly valued areas, etc.). If disaster costs are not included in RECLAIM, another mechanism is urgently needed to ensure that industry contributes towards a pot of money for future disasters. | GNWT/CIRNAC
13 | Revegetation | Revegetation of a site after closure is an important part of restoring the land, enabling long-term future cultural use, making the site look and feel like the surrounding area, and supporting wildlife. The revegetation unit costs in RECLAIM include seeding and tree planting. Planting cuttings, transplants, or plugs are other examples of revegetation, and likely have different costs than seeding and tree planting. Placement of stockpiled reclamation materials such as topsoil, till, lakebed sediments, etc. should also be included in direct costs for revegetation. | RECLAIM should include the cost for all types of revegetation, including cuttings, plugs, transplants, and spreading stockpiled dirt and soil. | AtkinsRéalis & Brodie | Suggest a User Specified activity and cost in RECLAIM
14 | Traditional Knowledge monitoring | Traditional Knowledge (TK) Monitoring is a critical part of ensuring the closed site meets closure objectives and goals. TK Monitoring is also essential for building community confidence in the closed site to enable long-term future use of the site. (For example, we note that the WLWB requires Diavik to prepare a TK Monitoring Plan). | RECLAIM should include the costs of a Traditional Knowledge Monitoring Program. This would involve regular (e.g., initially annual) site visits from Elders, youth, and staff to evaluate water quality, wildlife safety and movement, vegetation, and more. It is important to note that this is not the same as engagement or regulatory costs. This TK Monitoring Program is similar to other monitoring programs and should be a line item in the Post Closure sheet along with the scientific monitoring programs. | GNWT/CIRNAC | AtkinsRéalis supports this as its something that would like fall on governments books if a site were to be abandoned and this cost can be substantial.
15 | Net Present Value | To date, RECLAIM has included the ability to calculate the net present value. This was used for very long-term costs (e.g., more than 20 years) such as maintenance of constructed wetlands. This reduced the amount of security a company needed to post, without exposing the tax payer to increased risk. This is because the net present value accounted for the fact that money set aside for the future can be invested and will grow. The discount rate used in those calculations was generally an assumed modest growth in investment (e.g., 5%) minus an assumed inflation (e.g., 2%). | Why has the net present value function been removed from the draft RECLAIM? | AtkinsRéalis & Brodie
16 | Interim Care and Maintenance | The RECLAIM model includes an estimate for interim care and maintenance, meaning the period after bankruptcy and abandonment and before active closure begins. The total cost is based on an annual cost (commonly a few million dollars) times the number of years the site is likely to be in interim care and maintenance. The draft RECLAIM 8.0 model includes a default of 3 years of interim care and maintenance. However, the supporting documentation for the RECLAIM updates (Review of Mine Financial Security Estimates and RECLAIM) says "Importantly, the duration of Interim Care and Maintenance is typically limited to two to three years. It is known that government experience has been much different than this, both in scope and duration. This is an obvious category for which government could be under secured". The same document provides some evidence that the actual period could be five to ten years. | The estimated time a site is in interim care should be based on the expected or average duration not the minimum. | GNWT/CIRNAC | AtkinsRéalis agrees that even 3 years is low for ICM. However, we question whether its fair to hold additional securities to account for a transfer from the mine to government. For discussion.
17 | Unit costs - reference table and sources | During the public review, a reference table showing the source for unit cost assumptions was provided. | 1. This reference table is a significant improvement and should be included in the finalized model. It improves transparency and credibility of the unit costs and enables industry and decision-makers to discuss alternative site-specific unit costs. 2. Unit costs adopted from projects in the South (e.g., Sudbury) should be increased if these costs are going to be higher in northern, remote conditions. | AtkinsRéalis
18 | Fish habitat | The Open Pit tab does not explicitly include costs for building fish habitat (littoral zones), even though these may be required in pit lakes or pits that will be reconnected with larger lakes. Some of the activities in the tab may address fish habitat construction (e.g., placing fill), but it is not clear whether all activities required to build littoral zones are in RECLAIM. (Fish habitat construction may be required by the Department of Fisheries and Oceans and/or the Land and Water Boards. In either case the estimate should be included in RECLAIM. If DFO already holds security for this activity, it can be subtracted from the RECLAIM estimate. If it is only required by the Land and Water Boards, then it would remain in the final total.) | RECLAIM should include costs for construction of fish habitat in pits. | GNWT/CIRNAC | Seems out of scope of for the default RECLAIM, but if it has been agreed with DFO costs are not held with them then it should be captured here.
19 | Scientific and Traditional Knowledge research | Typically, the CRP will have several approved reclamation research plans. If a mining company abandons a mine, important reclamation research may not have been carried out. The results of this research will be needed to properly reclaim the site. | RECLAIM should include the costs of scientific and Traditional Knowledge reclamation research. As noted by BCL in their memo, this could result in mines not proposing research, in order to avoid higher security deposits. BCL proposed some alternatives to address this problem (page 18 and 19 of the BCL memo). These could be considered, provided the details of the approaches are publicly reviewed. | GNWT/CIRNAC
20 | Risk communication | The RECLAIM model does not include the costs of risk communication. In order to restore confidence in the mine site area so that closure objectives related to cultural use can be met, a good risk communication plan must be developed and carried out. This may involve public meetings, posters, online tools, social media, radio, newspapers, etc. | RECLAM should include the cost of risk communication. If this cost is lumped in with other costs (e.g., engagement and regulatory compliance costs), this should be mentioned in the User's Manual. This will ensure that the portion of security held for risk communication is not returned until it has been carried out. It will also inform any future disagreements about the percentage of direct costs that should be held for engagement and regulatory compliance. | Brodie | This should be added to User Manual
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Diavik Diamond Mines (2012) Inc. - Sean Sinclair
1 | General | DDMI appreciates the opportunity to take part in this important review process. Since receiving preliminary feedback at the January 23rd, 2025 engagement session, DDMI understands that on February 18th, 2025 and on March 11th, 2025 the RECLAIM v8.0 team uploaded additional information to explain the rationale for some proposed changes to the model. DDMI has not yet been able to review all posted materials. DDMI also understands the RECLAIM v8.0 team will be providing further additional information including but not limited to a jurisdictional scan to support this review process. This complete set of information will inform ongoing collaborative discussion on this proposed update. | Given the complexity and importance of this review process DDMI recommends that the review timeline allows for thorough review and analysis of all information. DDMI is pleased to see the initial extended engagement process proposed by CIRNAC and GNWT and DDMI recommends the next steps for the RECLAIM v8.0 review process are discussed in detail and agreed at the GNWT and CIRNAC in-person workshop the week of May 14th, 2025. | GNWT/CIRNAC
2 | General | An initial review of the proposed changes to the RECLAIM model suggest that its application could have a very significant increase on securities. Current proposed changes are focussed on: 1) increased unit rates, 2) increased indirect costs, 3) increased owners costs, 4) increases regulatory costs, 5) increased mobilization and ICM costs, and 6) a future value calculation without corresponding discounting. | DDMI recommends this review process also consider changes focussed on: 1) incentivizing progressive reclamation, 2) managing the return of security process, 3) managing the security holdback process, 4) consideration of financial mechanisms to provide security as a function of both the liability and asset value, and 5) risk associated with a proponents commitment to orderly closure of the site including its financial and technical capacity to carry it out. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
A Member of the Public - Todd Slack
1 | Model Utility - One Long Comment, Pt. 1 | Obviously an updated reclaim model is in the interests of all parties. Recent years have seen significant increases in costs and an adjustment to better reflect this is a valuable effort to protect taxpayers and ensure that the polluter pays principle is effectively applied. However, the operational modifications of the model are not the only step needed to ensure our territory is protected. A higher-level review focusing on the overall effectiveness of the bonding system should be undertaken using real world closure examples to test the predictive utility of the RECLAIM approach. No model is perfect and the review should be asking if this model meaningfully serves the polluter pays principle. Ground-truthing with real world examples is essential. For example, the MVLWB held approximately $70M in security for Snap Lake (it isn’t particularly easy to know exactly what the security amount was). According to public reporting, as of 2023 De Beers had spent $135M. In that case, it seems that NWT taxpayers – with a government already seeking financial relief - were considerably exposed. Should this be an indicator of a larger trend, the risk is even larger as it seems a widely held belief that industry, already mobilized and familiar with their site, can complete a closure in a more cost effective manner. Yet, the final cost for this site, with a modern security bond, will be more than twice what was held. | Starting with the NWT, publish real world examples of closed sites versus the reclaim estimates | GNWT/CIRNAC
2 | Model Utility - Pt. 2 | Other real world examples available to test the utility of RECLAIM estimates can be found in ongoing Strategic Oil abandonment and closure as well as the 2014 Snowfield property. Based on anecdotal information (as accounts have not been published, despite the expenditure of public monies), for the former, the GNWT has paid tens of millions for the reclamation, while the in the latter, the GNWT paid far in excess of the security held (nevermind the six-figure pre-existing debts that the company owed GNWT). Examples from Nunavut can be researched as well, extending back to Tahera/Jericho which was established with a modern regulatory regime and cost taxpayers more than the security that was held (as opposed to GIANT which is not appropriate as a test case). Yukon examples, over which there are a number of selections (Victoria, Wolverine, Minto) may provide further insight into the effective security estimates and bonding (considering the Yukon government has appropriated $100M for early stages of the Victoria mine they’ve inherited, which was permitted in a modern system). To summarize, before undertaking minor adjustments to the mechanics of the model, the overall utility needs to be verified, confirming fit for purpose. Notwithstanding the financial limitations of GNWT means that they lack the robustness to absorb and large mine failures (noting the daily cost cutting measures that are occurring), more importantly, the citizens of the NWT should have confidence that those overseeing the accessing and sale of our public resources are ensuring that the closure is paid for and completed by those exploiting the resource. | 1) Undertake analysis that looks at closure estimates versus the security held for sites across the NWT, Nunavut, and the Yukon. 2) Search for similar examples in Southern Canada were the structures ensuring the protection of taxpayers and governments are similar to those employed in the north. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Qikiqtani Inuit Association – Conor Goddard
1 | Updated Unit Rates | Understanding unit rates are based on first principles; however further detail on unit rate development and assumptions is required. For Example. Load and haul costs have been split into ‘short haul’ and ‘long haul’; however, there is no detail on what haul distance constitutes a short vs. long haul. To provide greater accuracy in haulage costs, specific unit rates should be calculated based on the actual haul distance between stockpiles and the facility being reclaimed. Dozer equipment rates are classified as either ‘small’ or ‘large’ scale equipment; however, no detail is provided on what is classified as a large dozer. This results in greater uncertainty in which equipment rate should be used when calculating equipment costs. | Paraphrased: Provide additional details on how unit rates were derived. | AtkinsRéalis | Additional details were provided in the follow up memorandum. Short haul and long haul are defined in Table 2: RECLAIM v 8.0 Price Sources, Basis and References. This could be defined in the user manual but a decision was made to keep the details out of the text portion of the manual for ease of future updates. These unit rates could be used as a starting point but should be refined based on actual mine closure and reclamation plans and site conditions. Dozer unit rates were escalated from RECLAIM 7.0. It was assumed large dozers would be utilized given the scale of work. The cost per cubic meter depends on several factors including fuel costs, labour, maintenance and efficiency. On average large dozers (D10/D11 Class) range in price from 1.50 to 3.50 per cubic meter. However, in remote Arctic operations the costs can be 20 to 50% higher. The range for dozing in RECLAIM 8.0 is $1.52/m3 to $6.08/m3
2 | Increased Indirect Percentages | An alternate methodology for calculating indirect costs should be provided. For example, engineering design could be estimated to be 8% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outlined in the reclamation and closure plan. This would allow engineering costs to depend on the level of project definition and the work to be completed. This incentivises further project definition within closure designs earlier in the life of project. | An alternate methodology for calculating indirect costs should be provided. | AtkinsRéalis
3 | Mobilization and Interim Care and Maintenance as Capital Costs | Mobilization / demobilization of equipment is typically considered as an indirect cost when it is being calculated as a percentage of direct costs. As RECLAIM calculates mobilization / demobilization costs directly, Okane supports its inclusion as a direct cost such that contingency can be applied. If mobilization / demobilization costs change to being calculated based on percentage, Okane does not support it being included as a direct cost. | Okane recommends mobilization / demobilization to be calculated via percentage of direct costs, similar to other Canadian jurisdictions. The quantity of equipment, and therefore the cost to mobilization / demobilization equipment, is tied to the reclamation timeframe and schedule. In the event of sudden closure, CIRNAC may implement closure activities on an alternate timeframe than what is outlined within the closure plan. | AtkinsRéalis & Brodie
4 | Owners Representative | Okane supports the costing of an Owners Representative within closure cost estimates. However, Okane is interested in the percentage used for determining this cost. In comparison, the updated project management cost of the entire reclamation phase is estimated to be 10% and includes costs for project coordination, accounting and project control, quality assurance/quality control and oversight, change orders and as-built reports. Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | AtkinsRéalis
5 | HHERA and Finalize CRP | An alternate methodology for calculating HHERA and CRP costs should be provided. For example, finalizing the CRP could be estimated to be 4% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outline in the reclamation and closure plan. This would allow the costs for finalizing the CRP depending on the level of project definition and the work to be completed. | An alternate methodology for calculating HHERA and CRP costs should be provided. | AtkinsRéalis & Brodie
6 | Future Value Calculation | Okane supports the consideration of future valuation with respect to years associated with ICM; however, does not agree on how it is being represented within RECLAIM with respect to post closure activities and the removal of net present value calculations as outlined in the virtual engagement session. While inflation can add considerable costs to reclamation, solely accounting for inflation does not capture the true costs and value of money. | Okane would recommend included inflation within a real discount rate to be used within a net present value analysis | AtkinsRéalis
7 | Detail for Unit Rates | Although RECLAIM provides a list of potential closure activities for each facility, it lacks the level of detail required to understand how these activities have been costed and relies strictly on unit rates and lump sum estimates. | To improve transparency and accuracy withing closure cost estimates, more inputs should be provided to show how that activity is being costed. Specifically, within post-closure activities such as monitoring the current RECLAIM model only provides an annual lump sum input for a monitoring activity. To improve transparency, it should provide more detail such as sampling/monitoring frequencies, number of sampling locations, analytic costs, reporting, etc. | AtkinsRéalis
8 | Post-closure monitoring and maintenance contingency | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. Post-closure maintenance activities are not excluded from having uncertainty and a contingency should be applied within this cost category. Specifically, activities such as long-term water treatment which is tied closely to geochemistry which typically carries large uncertainty. | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. | GNWT/CIRNAC
9 | Timeframe and Post-Closure Activities | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. There is potential for post-closure monitoring and maintenance activities to extend into perpetuity, such as DSIs, DSRs, and water treatment. What is the expected period of which these activities should be assessed over. | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. | GNWT/CIRNAC
10 | Discount Rates | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. Okane would welcome guidance on what ‘real’ discount rate should be applied to post-closure activities. | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Baffinland Iron Mines Corporation – Lou Kamermans
1 | Procedural Fairness | Due to the short timeline to review the proposed changes, Baffinland has not had a full opportunity to conduct an in-depth review of the technical information supporting the RECLAIM 8.0 update. Respectfully, the timeline that was provided to industry for this initial round of comments is not adequate given the importance of RECLAIM to the Nunavut mining industry and the very serious potential impacts that have already been identified through the minimal consultation that has occurred to date. We are concerned that RECLAIM 8.0 could be advanced further despite these procedural deficiencies and the serious concerns expressed by industry to date. Given the significance of these changes to the mining industry in Nunavut and the Northwest Territories, and the potential direct impacts that it will have on Baffinland, we are providing initial high-level comments and recommendations below. In providing these comments, we reserve the right to provide further and more detailed comments, following further industry engagement and once better information is shared by CIRNAC and GNWT. | A. CIRNAC should engage stakeholders and Inuit organizations in a meaningful consultation process before finalizing the changes. Respectfully, the process described in the letter to the Chamber of March 18, 2025 does not achieve this standard. B. Third public review and comment period should only occur after CIRNAC has produced a version of RECLAIM 8.0 revised based on comments. A further workshop may be necessary to review this revised RECLAIM 8.0 before any final comment period. C. The overall timelines suggested in the process letter of March 18 are inadequate. For example, with respect to the suggested expected date of implementation of RECLAIM 8.0 [August 1, 2025], it is apparent that there would be no meaningful opportunity for feedback provided during the third round of public feedback (due July 16, 2025). D. CIRNAC should advise how they intend to engage with NTI and RIOs on impacts to their rights resulting from this policy change, with associated timelines, before RECLAIM 8.0 is adopted. E. CIRNAC should advise how they intend to engage with GN resulting on impacts relating to devolution resulting from this policy change (including spinoff economic effects), with associated timelines, before RECLAIM 8.0 is adopted. | GNWT/CIRNAC | A-E: CIRNAC and GNWT to discuss.
2 | Economic impact of RECLAIM 8.0 | As Canada is trying to promote economic development and critical minerals development, which includes high grade iron ore, the additional security concepts and requirements proposed by CIRNAC in RECLAIM 8.0 will only make it harder to develop and maintain what we have. The changes proposed by CIRNAC will negatively impact mine financing and development by increasing security requirements and financial obligations without an adequate and corresponding industry consultation process. Any potential lack of engagement with industry and designated Inuit organizations undermines the legitimacy of these updates as a policy framework. Furthermore, as highlighted above, the RECLAIM 8.0 approach appears to disincentive projects with longer lifespans and greater water liability marks, which is in direct opposition to existing territorial and federal economic development policies and mandates. Without proper consultation, these changes will create uncertainty and deter investment in northern mining projects. Baffinland recommends that a comprehensive economic impact analysis be conducted to assess the implications of RECLAIM 8.0 on northern mining investment and development. Given the closure of major diamond mines in the North-West Territories and the absence of advanced stage projects in both the North-West Territories and Nunavut, apart from government funded infrastructure, the economic consequences of these changes should be thoroughly evaluated before implementation. An industry-commissioned economist could provide valuable insight into these potential impacts, and the results should be available before major policy decisions are finalized. | A. CIRNAC should conduct a comprehensive economic impact analysis to assess how RECLAIM 8.0 will affect mining investment and development in Nunavut. Industry and other stakeholders should be engaged on this question specifically as part of this analysis. B. As part of this analysis, CIRNAC should produce a third party expert prepared report on the potential economic impact of the proposed cost escalations on the mining industry in Nunavut. RECLAIM 8.0 has been provided without assessment of the negative economic impacts that could result from the significant policy change RECLAIM 8.0 represents. The independent economist selected for this task should have experience representing industry and have Northern expertise. | GNWT/CIRNAC | A: Agreed – third part economist could provide valuable insight as to the economic implication for mineral development in the NWT and Nunavut. B: As above.
3 | Rates and Cost Estimates | The proposed updates to RECLAIM 8.0 introduce significant cost increases that could have long-term economic implications for mining projects in the North. These cost escalations require careful scrutiny to ensure they align with real-world reclamation expenditures and do not hinder responsible resource development. | A. Review and adjust cost estimates to ensure they are reasonable, justified, and do not include duplication in indirect costs. B. Develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. | AtkinsRéalis & Brodie | A: There was every attempt to ensure costs were reasonable, justified and did not include duplication. We will review the rates again to ensure they meet these criteria. B: We do not suggest that CIRNAC develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. It should be clear in RECLAIM User Manual as to why the default percentages are chosen and the mining company should propose the appropriate rate for their own mines and current stage within the lifecycle.
4 | Rates and Cost Estimates | The unit rates proposed for RECLAIM 8.0 are substantially higher than those in RECLAIM 7.0, often reflecting worst-case scenarios without adequate justification, despite the additional materials provided following the January Workshop in Vancouver. While CIRNAC states that proponents may propose alternative rates, industry experience suggests that the highest rates are typically applied in practice, unless a clear security policy is in place (see Section 3 – Security Policy). First principles derivations for these rates has not been provided (as is typical when justifying modifying rates in a security estimate) and the references are highly generalized, which hinders review, especially in light of the limited review timeline. | C. CIRNAC and GNWT must provide more detailed first principles derivations for rates, at a level that would be expected of a proponent justifying its own rates in an estimate. Specific references are required and generalized references provided to date are not adequate to provide expert feedback and advice. | AtkinsRéalis | C: CIRNAC provided links and references to the majority of the sources for increased rates applicable to remote mine working in NWT and Nunavut. CIRNAC used First Principles to develop rates for soil and rock movement and provided the factors considered in the costs estimating tool. Its is up to the mining company to counter these rates and provide rationale as why a different unit rates should be proposed (high or lower).
5 | Rates and Cost Estimates | The increase in indirect percentages represents an overall 23% increase in costs, and several of these items overlap, resulting in duplication of costs (see Table 1). For example the increase in contingency seems to be duplicated by an increase in project management, engagement and regulatory compliance, and owner’s representative costs. These increases do not appear to be justified through a detailed cost analysis. | D. Justification must be provided by CIRNAC to address the duplication described in the comment, and a detailed cost analysis must be provided to justify these statements | AtkinsRéalis | D: AR to investigate
6 | Rates and Cost Estimates | Upon initial review, the observations regarding indirect costs provided in the ”Review of Mine Financial Security Estimates and RECLAIM” (Brodie, 2020) do not align with the proposed Reclaim 8.0 Indirect costing changes. For example, the report states “BCL recommends that the default percentage for Project Management be increased based upon CIRNAC’s experience. Whereas the default percentage for Engineering should be maintained but with the RECLAIM User Manual revised to be even more explicit as to what is and is not assumed to be covered in this amount.: Baffinland notes that the proposed Reclaim 8.0 changes include an increase in project management indirect percentages (an increase from 5% to 8%), an additional owners engineer indirect (an increase of 8%) and an increase in engineering design indirects (5% to 8%). This appears to be in contradiction to the recommendations of the review report. | E. CIRNAC should align observations re indirect costs in RECLAIM 8.0 with Brodie, 2020 (subject to adjustment based on further submissions in future on each of these categories) | AtkinsRéalis & Brodie | E: Default increases in percentage of indirects were increased from the Brody recommendations based on consultation with our consultants cost estimators and based on incurred cost at other orphaned and abandoned mine across Canada.
7 | Rates and Cost Estimates | Within the proposed update, contingency has been increased to a maximum of 25%, which the Reclaim review report (Brodie, 2020) describes as appropriate for “Very basic engineering only and costs based upon typical unit costs”. This guidance is not provided in the proposed RECLAIM 8.0 documentation. As Baffinland has noted above, in its experience when Reclaim is applied by reviewers the highest level of contingency/indirect is used as a manner of course, as there is little specific guidance provided how to select an appropriate contingency/indirect within the provided model. For example, although Baffinland’s closure plan has advanced to the ICRP stage and has had significant engineering completed, a 20% contingency has been consistently applied by CIRNAC reviewers. Without specific risk based guidance regarding how to select indirect percentages based on project stage and level of engineering completed, Reclaim 8.0 could be used in an overconservative manner due to the lack of specific guidance, which could have a significant impact on Baffinland and other resource development projects in Nunavut. | F. 25% is not an appropriate contingency percentage for most advanced projects with current RECLAIM 8.0 guidance there is a risk this value is applied broadly, like 20% contingency is now. Adjust contingency percentage to reflect a range of risk based standards adjustable based on criteria, such as reductions below 20% where projects already have significant completion of engineering | AtkinsRéalis | F: CIRNAC could develop a matrix to define
8 | Rates and Cost Estimates | The future value calculation for water treatment and other long-term liabilities places a significant financial burden on mining companies, particularly in the absence of strong offsetting mechanisms, such as security discounting based on known reserves—an approach used in other jurisdictions like British Columbia (BC) and Quebec (Government of BC, 2022; Government of Quebec, 2017). For instance, in 2022, the BC Ministry of Energy, Mines and Low Carbon Innovation introduced the Major Mines Reclamation Security Policy, which considers a mine’s stage of development and promotes long-term operations by applying different security rates at various points in a mine’s lifespan based on default risk. The policy states that “mines that have been operating for more than five years, and that have economically viable reserves for at least the next ten years at the permitted production rate, will be eligible to secure up to 25% of the reclamation liability against a portion of the reserve value.” (Government of BC, 2022). Adopting a similar approach in Nunavut provide much-needed financial flexibility for long-term mining projects like Baffinland, reducing upfront security costs while maintaining strong environmental protection measures. This would enhance the economic viability of long-life mines, encourage continued investment, and support sustainable resource development in the region. Tying financial security to the mine life cycle would help mining companies spread out financial security payments over the mine’s life, which would increase investor confidence while supporting responsible mining development that considers the projected mine life. | G.RECLAIM 8.0 should be revised to provide a clear mechanism for discounting security based on reserves, similar to those adopted in other jurisdictions such as BC and Quebec. | GNWT/CIRNAC | The BC “interim” policy is based on years of operations and mineral reserves. Proven final securities through the Exploration Incentive. Shifting security to mineral reserves could be an issue as Canada is not in the mining business and if a site were abandoned, they would need to reopen a mine to get access to the money required to close it. The BC policy mentions that mines with proven reserves are attractive to other operators if a mine were to go bankrupt. STILL SEEMS RISKY TO ME, TULSEQUAH, MINTO, ETC. “This policy seeks to ensure that permittees for major mines pay the full cost of environmental cleanup and reclamation for their mine. New mines and any existing mines (whether in operation, in care & maintenance or closed) having less than five years of remaining mineral reserves will be required to post full reclamation security equal to the company’s reclamation liability on the mine site. A partial exploration incentive security will be available to mines that have invested in sufficient exploration to demonstrate at least five years of remaining reserves. The policy seeks to ensure that new mines are fully bonded moving forward and seeks to reduce the differential between reclamation liabilities and reclamation securities for existing mines.” 0 to 5 years: (100% posted cash security) > 5 years: (75% posted cash security and 25% against the mineral reserves) > 5 years but less than 10 years (85% posted cash security and 15% against the mineral reserves) No more than 10% of the value of the reserve used reclamation security Discount rate of 8% applied to the mineral reserves Default contingency set to 15% but higher may be required depending on the level of risk or uncertainty. Lower may be proposed by the permittee
9 | Update of 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) is required. | Before publishing a RECLAIM 8.0 model, Baffinland recommends that the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) be revised to reflect current conditions in the mining industry. There has been no suggestion that current Nunavut production mines are undersecured – as an example, Baffinland’s security is reviewed annually in a comprehensive process. The investment decision for Mary River was made on the suite of government and Inuit approvals in place, including RECLAIM 7.0. | A. Before RECLAIM 8.0 is adopted for Nunavut projects, the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) should be updated to reflect current conditions in the mining industry and best practices across Canada and globally. B. Current approved Nunavut projects should follow RECLAIM 7.0, unless the proponent consents to application of RECLAIM 8.0. | GNWT/CIRNAC | A: TBD B: Current mine securities are set. At the time of renewal, RECLAIM v 8.0 will be in place and new indirects and calculations of contingencies and future costs will be negotiated.
10 | Misc. | No Comment | A. Only a simple markup of the updates to the User Manual has been provided. A detailed markup is requested as a simple markup does not clearly present the changes. | Brodie
11 | Misc. | No Comment | B. With reference to the “proprietary civil rate tool” referenced at p. 20 of the User Manual for RECLAIM 8.0, if a tool is being adopted in a government policy, it must be made publicly available. If it is not publicly available, it should not be included in the policy. This is a matter of fairness and transparency. | AtkinsRéalis | B: AtkinsRéalis suggests removal “proprietary” replace with “construction cost estimating”
12 | Misc. | No Comment | C. Costs relating to the Crown’s legal obligation to consult (which would be incurred in any event, whether the Crown steps in as director of reclamation or participates in review of closure plans led by a proponent) should not be included in RECLAIM 8.0, as this is a fixed government cost, not a cost of reclamation. The suggested 3% includes items that are fixed government obligations that do not belong in a reclamation estimate. | GNWT/CIRNAC | C: The 3% Owners Costs are meant to capture expenses required to complete consultation during the ICM and Post Closure Phase that typically are budgeted for in day to day government spending (i.e., flights, vehicle rentals, accommodations, per diems to northern and remote communities to discuss the remediation, reclamation and closure plan. Costs of permitting and other third party costs related to government activities would be captured here.
13 | Misc. | No Comment | D. How is RECLAIM 8.0 accounting for Nunavut devolution relating to lands and waters from CIRNAC to the GN? | GNWT/CIRNAC | D: CIRNAC to elaborate.
14 | Misc. | No Comment | E. RECLAIM 8.0 should recognize reasonable salvage value where justified by the proponents estimate. The current position is unreasonably conservative and results in over bonding in many circumstances. This statement should be revised accordingly “GNWT/CIRNAC does not recognize salvage value because of the problems associated with creditors rights, sale of equipment and uncertainty as to the actual value at the time of insolvency”. | GNWT/CIRNAC | E: Revised text looks appropriate to AtkinsRéalis.
15 | Misc. | No Comment | F. Citation for precautionary principle definition should be to the CEPA not to the CEPA guide. | Brodie | F: Revision seems appropriate to AtkinsRéalis
16 | Misc. | No Comment | G. Progressive reclamation should be credited in mine reclamation costs. This aligns with the following statement from the 2002 Nunavut Reclamation Policy – “Mining operators should be credited for approved progressive reclamation, and the value of financial security required should be adjusted in a timely fashion” | GNWT/CIRNAC | G: CIRNAC recognizes this statement and has worked with mining companies to reduce securities based on progressive reclamation activities and will continue to do so on a case by case basis.
17 | Misc. | No Comment | H. RECLAIM 8.0 adds an additional owners representative indirect cost, which is in addition to the proposed project management indirect cost. The owners representative indirect has been insufficiently justifying in the provided accompanying documentation, and it should be noted that an owners representative is not required during proponent lead reclamation. This overly conservative indirect requirement could have significant implicants on mine financing and development. | AtkinsRéalis | H: CIRNAC and GNWT would not lead the development and finalization of the Closure and Reclamation Plan, nor would they oversee the construction or monitoring and maintenance activities. It has been shown that this is not the case as seen at Faro and Giant mines. CIRNAC and GNWT would hire an engineering firm to provide Owners Representative services (technical resources to government) to manage and oversee another engineering firm (e.g. a design-build team) who would be contracted to complete the closure, reclamation and long term monitoring activities.
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
B2G Back River Corp. Nunavut – Merle Keefe
1 | Review Data Extension | B2Gold Nunavut is presently unable to meet the requested date for the submission of comments and therefore supports a recent request made by the NWT& Nunavut Chamber of Mines (Chamber) to extend the comment period deadline. B2Gold Nunavut also supports the request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM. The Chamber submission is attached to this letter. | Request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
NWT & Nunavut, Chamber of Mines – Karen Costello
1 | Review Data Extension | The Chamber respectfully requests a 4-month review period (including potential options for a workshop) to fulfill the first step in the review process. We would also ask for access to the Review of Mine Financial Security Estimates dated March 2020 at your earliest convenience. | Four month date extension for review comments | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Agnico Eagle Mines Limited – Jamie Quesnel
1 | Review Data Extension | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. As was apparent at the January 23, 2025 Engagement and Feedback Session, and echoed again in the NWT & Nunavut Chamber of Mines letter, there were many uncertainties and risks identified by Industry, including time to complete a detailed and adequate review of all the proposed changes under RECLAIM 8.0. As outlined in Section 2 of this letter, Agnico Eagle has undertook an initial review and provided some comments and recommendations; however, a detailed fulsome review has not been executed at this stage. | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. | GNWT/CIRNAC
2 | Documents received | This is a preliminary review due to the short timeline | More time is required to complete a comprehensive review of the documentation provided | GNWT/CIRNAC
3 | Reclamation Policy | As the reason is unknown why the Reclaim V8 was changed, plus we have an undefined process we are following, and this creates uncerntainity. | Develop a plocy update with a defined process of consulation, etc., and define the triggers for a material change. | GNWT/CIRNAC
4 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" and "'Work week for earthwork (rock, soil, riprap excavation, hauling to waste dump is 7 days a week x 10 hours per day = 70 hours per week" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No overnight work is considered. | Unit rates should be developed assuming 24 hour operation where practical. SUPPORTING RATIONALE: Operating Mines, particularly in the North, require round the clock operation for maximum equipment utilization and operation effectiveness. Haul trucks engines must be active around the clock to ensure operability and neglecting night shift utilization ignores real operating expenditures. | AtkinsRéalis
5 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No night work is considered. | Operating Mines, particularly in the North require round the clock operation for maximum equipment utilization and operation effectiveness. SUPPORTING RATIONALE: Neglecting potential night shift work unnecessarily extends project schedule and therefore unnecessarily inflates overall project costs. | AtkinsRéalis
6 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'The labour cost included in the unit rates considered the following cost: … - Indirect labour" | The battery limits for "indirect labour" included in unit rate development is not adequately defined. RECLAIM includes indirect activities such as Project Management and Engineering Design applied as a general percentage of direct costs. | Clarify what indirect labour is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | AtkinsRéalis
7 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "The labour cost included in the unit rates considered the following cost: … - Site supervision and administration" | The labour cost included in the unit rates considered the following cost: Site supervision and administration | Clarify what site supervision and administration is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.). SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. Project management, Health and Safety Monitoring & QC as an indirect cost is applied as a blanket % to all costs. | AtkinsRéalis
8 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "Exclusion ...- Project indirect cost" | The battery limits for "indirect cost" included in unit rate development is not adequately defined. | Clarify what indirect cost is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | AtkinsRéalis
9 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 5 Exclusions LINE: "- First Fills" | First fills are excluded from unit cost build up. | Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup that excludes first fills. SUPPORTING RATIONALE: Consistent application inclusions and exclusions are important for usability of RECLAIM. Suggest using one data source for all unit rate buildup. | AtkinsRéalis
10 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- Freight for the bulk materials such as granular, concrete and HDPE pipes are included with the unit rates" | Proposed unit rate buildup includes freight for bulk materials. This necessitates site specific unit rate for all bulk materials as freight costs can very substantially between sites. There is already a section within the RECALIM mobilization tab to capture freight cost. | Bulk material default unit rates should exclude freight. Freight for materials should be included separately based on a site specific unit cost for material mobilization, captured in the RECLAIM Mobilization tab. | AtkinsRéalis
11 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- It is assumed there is no batch plant required. All concrete will be delivered to site to use" | The clarification that no batch plant will be required constricts operational planning. In some cases it is more cost effective to commission a batch plant and ship bulk concrete than to use premix product. | Freight of premix concrete products is not always practical for northern projects based on mobilization constraints and the use of a batch plant should be considered when operationally and financially advantageous. | AtkinsRéalis
12 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects LINE: Mobilization/Demobilization 6.0% | Contractor indirects, specifically mobilization/demobilization, are shown as separate adders to the base rates for equipment and labour direct costs. RECLAIM considers mobilization and demobilization costs separately from operating unit rates as part of the Mobilization tab. | Exclude mobilization/demobilization cost from unit rate development. Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup and if mobilization/demobilization cost has been accounted for with respect to the overall RECLAIM workbook. | AtkinsRéalis
13 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects | A variety of sources for equipment operating costs as well as labour costs are indicated as being used as a basis for unit rate calculations. There are substantial differences in the factors included in each of the sources for equipment operating costs. For example, BC Blue Book and Alberta Equipment Rental Rates Guide are used interchangeably in FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Rates but BC Blue Book equipment operating rates do not explicitly include contractor overhead and profit whereas Alberta Equipment Rental Rates Guide does. The provided unit rate example in FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects, if using Alberta Equipment Rental Rates Guide for equipment or manpower hourly rates is applying an additional 12.50% Mark-up & Profit on a rate that already includes Mark-up & Profit. | Default unit rates provided in RECLAIM 8 should use a consistent source reference for all equipment and manpower hourly rates with clearly defined buildup of direct and indirect components. | AtkinsRéalis
14 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Buildings - Remove" COST CODE: BRW, BRC, BRS1, BRS2 | Cost Codes: BRW, BRC, BRS1, BRS2 have no default HIGH unit rate provided as part of RECLAIM 8.0 example. RECLAIM 7.0 provided a HIGH unit rate for these cost codes resulting in a 1:1 comparison between RECLAIM 8.0 default unit costs and RECLAIM 7.0 unit costs. | RECLAIM 8.0 should include a default HIGH unit rate for all default cost codes that have a defined HIGH unit rate in RECLAIM 7.0 | AtkinsRéalis
15 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB1, RB2 | The detail defining what activity COST CODES RB1 and RB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines RB1 as "drill/blast/load/short haul" RECLAIM 8.0 defines RB1 as "load/haul/place"RECLAIM 7.0 defines RB2 as "drill/blast/load/long haul" RECLAIM 8.0 defines RB2 as "RB1 + spread and compact"This respondent uses COST CODE RB2 to represent activities requiring "drill/blast/load/long haul" but NOT "spread and compact" To accommodate the change in COST CODE detail from RECLAIM 7.0 to RECLAIM 8.0 >$10 million of activities on a single site would need to be recoded to avoid implying "spread and compact" is required for these activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
16 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB3, RB4 | COST CODE: RB3 and RB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RB3 DETAIL: "RB1 + spread and compact" is the same as RECLAIM 8.0 CODE RB2 DETAIL: "RB1 + spread and compact"RECLAIM 7.0 COST CODE RB4 DETAIL: "RB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RB3 and RB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
17 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - High Spec (i.e. Rip Rap, Screened)" COST CODE: RC3, RC4 | COST CODE: RC3 and RC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RC3 DETAIL: "RC1 + spread and compact" is the same as RECLAIM 8.0 CODE RC2 DETAIL: "RC1 + spread and compact"RECLAIM 7.0 COST CODE RC4 DETAIL: "RC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RC3 and RC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
18 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB1, SB2 | The detail defining what activity COST CODES SB1 and SB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SB1 as "excavate/load/short haul" RECLAIM 8.0 defines SB1 as "excavate/load/haul/place"RECLAIM 7.0 defines SB2 as "excavate/load/long haul" RECLAIM 8.0 defines SB2 as "SB1 + spread and compact"This respondent uses COST CODE SB2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
19 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB3, SB4 | COST CODE: SB3 and SB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SB3 DETAIL: "SB1 + spread and compact" is the same as RECLAIM 8.0 CODE SB2 DETAIL: "SB1 + spread and compact"RECLAIM 7.0 COST CODE SB4 DETAIL: "SB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SB3 and SB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. This respondent would need to recode >$35 million of activities at one site. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
20 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC1, SC2 | The detail defining what activity COST CODES SC1 and SC2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SC1 as "excavate/load/short haul" RECLAIM 8.0 defines SC1 as "excavate/load/haul/place"RECLAIM 7.0 defines SC2 as "excavate/load/long haul" RECLAIM 8.0 defines SC2 as "SC1 + spread and compact"This respondent uses COST CODE SC2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
21 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC3, SC4 | COST CODE: SC3 and SC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SC3 DETAIL: "SC1 + spread and compact" is the same as RECLAIM 8.0 CODE SC2 DETAIL: "SC1 + spread and compact"RECLAIM 7.0 COST CODE SC4 DETAIL: "SC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SC3 and SC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
22 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, small (<6in dia.)" COST CODE: PSS, PSI | COST CODES: PSS and PSI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes. | AtkinsRéalis
23 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, large (>6in dia.)" COST CODE: PPLR, PLS, PLI | COST CODES: PLR, PLS and PLI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes | AtkinsRéalis
24 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: PS | Pumps, Pump shipping COST CODE: PS unit changed from RECLAIM 7.0 lump sum (each) to, RECLAIM 8.0 percentage (%) of pump cost.Existing RECLAIM 7.0 projects have taken to account shipping of pumps, by lump sum (each) as part of the mobilization calculation. Shipping cost is generally site specific and existing calculations should remain valid. Shipping cost as a % of pump capital cost could be a useful default unit rate for establishing projects. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND adding new cost code for shipping as a % of capital cost | AtkinsRéalis
25 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: POC | Pumps, Pump operating cost COST CODE: POC unit changed from RECLAIM 7.0 m3 (volume pumped) to, RECLAIM 8.0 kw-h (power cost).Pump operating cost is certainly predicated on site power cost but the relationship between pumped volume and power draw is based on site specific conditions. Volume of water is the unit of measure for reclamation activities and using a second unit of measure to determine cost would introduce additional complexity. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND pump operation based on cost per volume pumped. | AtkinsRéalis
26 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Human Health and Ecological Risk Assessment (% Closure Costs) | Human Health and Ecological Risk Assessment (% Closure Costs): Cost to develop a site specific HHERA is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for HHERA related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
27 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Finalize Closure and Reclamation Plan (% Closure Costs) | Finalize Closure and Reclamation Plan (% Closure Costs): Cost to develop Final Closure and Reclamation plan is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Finalize Closure and Reclamation Plan related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
28 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engineering Design | Indirect Costs: Engineering Design : Cost for engineering design is warranted and should consider work already completed to capture the real effort and cost to achieve closure | Implement a sliding scale for Engineering Design Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
29 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Project Management | Indirect Costs: Project Management : Cost for project management is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Project Management Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
30 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Health and Safety Plans/Monitoring & QC | Indirect Costs: Health and Safety Plans/Monitoring & QC : Cost for Health and Safety Plans/Monitoring & QC is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale to account for project maturity and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
31 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Bonding / Insurance | Indirect Costs: Bonding / Insurance : Cost for Bonding and Insurance is warranted and should consider work already completed to capture the real effort and cost to achieve closure. This cost should also account for the reliability and ease of use of the financial assurance instrument used by the mine owner as well as the financial reliability of the mine owner, represented by third party credit rating. Typical operating project bonding and insurance costs for third parties are historically <1% total project cost. | Implement a sliding scale to account for owner reliability, project maturity, and the cost and effort required to achieve closure. Established mining companies at low risk of becoming insolvent should have their efforts to achieve closure recognized. | GNWT/CIRNAC | For group discussion
32 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engagement and Regulatory Compliance | Indirect Costs: engagement and regulatory compliance cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations, including through regulatory compliance and engagement, should not be made to bear burden of costs outside their influence. | GNWT/CIRNAC
33 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Contingency | Indirect Costs: Contingency : Cost for contingency is warranted and should consider work already completed to capture the real effort and cost to achieve closure. There is currently a sliding scale for contingency, codified in the RECALIM 7.0 user manual, but the benchmarks set out are not representative of the level of contingency requested by CIRNAC and recommended by Brodie Consulting. The RECLAIM 8.0 contingency scale, based on AACE International Recommended Practice No. 10S- 90 representative of current industry practice and can be augmented with other factors such as owner financial strength, path to closure, and financial instrument of security. | Contingency sliding scale should reflect project lifecycle maturity, the financial strength of the owner, the financial instrument of closure security and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
34 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Owners Representative | Indirect Costs: Owners representative cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations should not be made to bear burden of costs outside their influence. This line item addition represents a significant burden to all mining companies and it may impact the viability of future developments. | GNWT/CIRNAC
35 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Site Specific Future Value Inputs | FILE: reclaim 8.0 User Manual_Working Copy.pdf affirms that the determination of future costs must include all parameters including the Net Present Value of those costs. The Site Specific Future Value Inputs projects a future cost without including for the future value of the security | If RECLAIM is to project factors such as inflation it should also account for the present value of money at the time of projection. A prescribed NPV calculation with appropriate discount rate should be applied alongside all Post-Closure costs and future projections. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Kivalliq Inuit Association – Luis Manzo
1 | General comment | The Kivalliq Inuit Association (KivIA), as the responsible DOI, through Security Management Agreement holds 50% of the financial security estimates for Meadowbank, Meliadine and Whale Tail mines Canada holds the other 50%. Therefore, any changes to the RECLAIM financial model must be reviewed and agreed by KivIA. | Paraphrased: Table 1 provides the comments and recommendations from KivIA and are summarized in comments 2 to 20 below. Table 2 provides operational costs for drill/blast/load/haul/spread/compact unit rates. Assumption is we should consider these rates. Table 3 includes an example comparison of the increased costs based on the new percentages for indirects. It is recommended that any changes to the RECLAIM financial model must be reviewed and agreed by KivIA | GNWT/CIRNAC
2 | General comment | The timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site needs to be explained. | The KivIA requests that CIRNAC explain the timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site. | GNWT/CIRNAC
3 | General comment | Project or mine’s asset value to a company. Will CIRNAC consider the asset value of an advanced project or mine as part of the initial financial security. | The KivIA requests that CIRNAC explain if there would be consideration of the asset value of an advanced project or mine as part of the initial financial security. | GNWT/CIRNAC
4 | General comment | What is the procedure for the return of financial security to the proponent? | The KivIA requests that CIRNAC explain the procedure for returning financial security to the proponent. | GNWT/CIRNAC
5 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | The changes made to the direct costs need to reflect each individual project/mine site. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that direct costs will need to be project specific versus “one cost fits all” with a range of costs being a more appropriate approach. | AtkinsRéalis
6 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References -Excavation costs. | Excavation costs for load/haul/place for excavating and spreading rock and soil show significant increases from RECLAIM 7.0 to RECLAIM 8.0. Using known operating costs from a northern gold mine calculated in RECLAIM 7.0 and comparing these costs to the proposed rates in RECLAIM 8.0 the costs for load/haul/place for excavating and spreading rock and soil have increased by 50% to 430% (see Table 2 attached). In addition, the RECLAIM 7.0 costs included drill and blast which the RECLAIM 8.0 costs do not. However, without any detail provided on how the Civil Est. Tool calculates the RECLAIM 8.0 costs it is not possible to evaluate these cost differences. | The KivIA requests that CIRNAC and their engineering consultants provide the detail on how the Civil Est. Tool calculates the RECALIM 8.0 excavation costs. | AtkinsRéalis
7 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | Will an inflation factor be used. Will this factor be applied to direct costs? Or to Indirect costs? Will an inflation factor be used on the direct costs? Or indirect costs? Over what time period will the inflation facto be reviewed. | The KivIA requests that CIRNAC and their engineering consultants respond to their proposed plan for an inflation factor. | AtkinsRéalis
8 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Indirect Costs | The changes made to the percentages used for Indirect Costs from RECLAIM 7.0 (31%) to RECLAIM 8.0 (58%). Using the $100M Direct Cost example in Table 2 the changes made to the percentages would result in an 87% increase to the InDirect Costs from $31M to $58M. | A cost increase of 87% is significant and will have a negative impact on the business model used to develop currently operating advanced projects and mines. In addition, a cost increase of this magnitude will have a negative impact on new investment “North of 60”. The KivIA’s comments on the recommended changes make up the remainer of this table (Table 1). | GNWT/CIRNAC
9 | RECLAIM 8.0 – User Manual – Indirect Costs – Engineering Design; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engineering Design | The percentage change made to the Engineering Design component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (8%). This should be a range from 5% to 8% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
10 | RECLAIM 8.0 – User Manual – Indirect Costs – Project Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Project Management | The percentage change made to the Project Management component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (10%). This should be a range from 5% to 10% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
11 | RECLAIM 8.0 – User Manual – Indirect Costs – Engagement and Regulatory Compliance; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engagement and Regulatory Compliance | The Engagement and Regulatory Compliance component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (3%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2)the cost information that was used to determined that this new category would cost $3M per every $100M of financial security. | AtkinsRéalis
12 | RECLAIM 8.0 – User Manual – Indirect Costs – Contingency Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Contingency | The percentage change made to the Contingency component of Indirect Costs from RECLAIM 7.0 (20%) to RECLAIM 8.0 (25%). This should be a range from 15% to 25% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
13 | RECLAIM 8.0 – User Manual – Indirect Costs – Owners Representative; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Owners Representative | The Owners Representative component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (8%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2) the cost information that was used to determined that this new category would cost $8M per every $100M of financial security. | AtkinsRéalis
14 | RECLAIM 8.0 – User Manual – Future Value calculations: Summary Report: Proposed Changes to RECLAIM Version 8.0 – Future Value calculations | It states that the Future Value calculations will capture Closure and post-Closure activities and that a default inflation rate of 3% will be applied. Will there be an annual or a multi-year review of the inflation rate in order to adjust the financial security. | The KivIA requests that CIRNAC and their engineering consultants provide the timeline over which the inflation rate will be reviewed (ie. Annually review? Multi-year review?). | GNWT/CIRNAC
15 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet; Table 1 – Basis of Unit Rates Development | It states that “The below references are used in unit rates development -Published data sources”. All the published data sources used are from southern Canada. Are there any “North of 60” data sources? Are there any permafrost related data sources? Also, are these labour and contractor rates union or non-union rates? | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) northern data sources or explain why these cannot be provided. 2) Are the labour and contractor rates union or non-union rates. | AtkinsRéalis
16 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References – column Price Base/References | In the column for price Base/References several price references are either Civil Est. Tool or Historical Database. For transparency and ensuring a proper evaluation of costs by all intervenor’s full disclosure of all price references is necessary. | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) the details of the Civil Est. Tool. 2) the Historical Database. | AtkinsRéalis
17 | RECLAIM 8 Model Working Copy – Excel Sheet; Instruction Tab – Conditions of Use | It states that “This model is not intended to dictate how much should be spent on reclamation.” What is the purpose of this financial model if it is not supposed to dictate how much should be spent on reclamation by the proponent? Is it possible that if a proponent disagrees with CIRNAC’s final dollar amount created by this model that the proponent could set their own financial security? | The KivIA requests that CIRNAC: 1) provide clarity on the purpose of the RECLAIM financial model. 2) provide clarity on the proponents responsibility to adhere to the final dollar amount calculated by the RECLAIM financial model. | GNWT/CIRNAC
18 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Fuel and Electricity | Fuel costs for gas and diesel are listed. No fuel costs for Jet A, Jet B or Av gas are included. | The KivIA requests that CIRNAC and their engineering consultants provide fuel costs for Jet A, Jet B and Av gas. | AtkinsRéalis
19 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Mobilize Workers (round trip) | Hourly costs for small, medium and heavy helicopters. Are these hourly costs “dry” (do not include fuel cost) or “wet” (do included fuel cost). | The KivIA requests that CIRNAC and their engineering consultants determine if the hourly costs for small, medium and heavy helicopters are “dry” or “wet”. | AtkinsRéalis
20 | RECLAIM 8 Model Working Copy – Excel Sheet; Estimator Tab – Excavator Ratings | The cycle times and productivity for excavators are based on southern Canadian conditions (ie. digging in sandstone and caliche; non-Arctic conditions). There is no reference to permafrost or Arctic conditions for the cycle times and productivity for excavators. | The KivIA requests that CIRNAC and their engineering consultants determine what changes to the cycle times and productivity for excavators will occur in permafrost and Arctic conditions, in particular, metal fatigue under extremely cold conditions (ie. > -40oC). | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Burgundy Diamond Mines Ltd – Sheila Chernys
1 | Transparency of Unit Rates Derivation | The derivation of the proposed RECLAIM 8.0 unit rates remains unclear, which makes it challenging for proponents to assess their applicability to specific sites. | Provide detailed explanations and supporting data for these rates would enhance understanding and confidence in their application. | AtkinsRéalis
2 | Mobilization and Indirect Cost Management (ICM) Costs | Reassigning these costs to Capital Costs introduces a compounding effect that significantly inflates estimates. | Retaining them under Indirect Costs would better account for site-specific variations without leading to overestimations. | AtkinsRéalis
3 | Default Percentages for Costs | The percentages allocated for Owners Representative, HHERA, and Final CRP costs are high and do not align with typical closure project requirements in the region. | Revisiting these percentages and considering fixed cost estimates will ensure more balanced and accurate calculations. | AtkinsRéalis
4 | Inflation Rate Methodology | Applying a fixed 3% inflation rate across all closure costs is not appropriate for all closure activities. | A more flexible approach based on historical inflation data and specific project conditions will better reflect actual cost variability. | AtkinsRéalis
5 | Incentives for Progressive Reclamation | The updates focus on increasing securities but could also include measures to encourage progressive reclamation during operations. For example, allowing partial release of securities to execute reclamation activities would promote progressive reclamation, reduce liabilities and support sustainable closure outcomes. | Update should encourage progressive reclamation during operations. | GNWT/CIRNAC

## Sheet1 (hidden)
No. | Topic | Reviewer Comment | Reviewer Recommendation | Assigned To | Proponent Response
Environmental Monitoring Advisory Board - EMAB
1 | Evaluate RECLAIM estimates versus actual expenditures | EMAB's view is that the cost of mine closure should be borne by the proponent, not the taxpayer. The comment on p. 1 of the CIRNAC review that "However, it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." raises a major concern. Security should cover the entire cost of closure, and RECLAIM should calculate security that meets the full cost of closure. | CIRNAC/GNWT should carry out a quantitative evaluation of how much current RECLAIM estimates differ from actual expenditures. | GNWT/CIRNAC
2 | Depositing waste rock in open pit | Some mines have included depositing waste rock into open pits as a means of disposal. This activity does not appear to be addressed in the RECLAIM manual or tables. | Expand tables, and manual, to include placing waste rock and other materials, into open pits. | AtkinsRéalis
3 | Revegetation | The reference tables for vegetation include hydroseeding and tree planting. This is a good start, but the range of activities should be expanded to include all activities required for successful revegetation. | Reference tables for vegetation should also include application of amendments and planting of container forb seedlings as well as other activities required for successful revegetation. | AtkinsRéalis | Add Other Specific if not there already
4 | Long-term maintenance and monitoring | Traditional Knowledge Monitoring by members of Affected Communities is an important component of ensuring successful closure and future use of the area affected by the mine for cultural activities by the Indigenous people who live in the area and use it. | Add Traditional Knowledge Monitoring to the list of post-closure activities. | GNWT/CIRNAC
5 | Long-term maintenance and monitoring | EMAB was pleased to see the expansion of the Mobilization sheet to include construction and use of winter roads for both mobilization and demobilization. It is not clear whether this is intended to cover mob/demob for post-closure maintenance. Once the mine closes there is no guarantee that the winter road will continue to exist. If there is a significant maintenance requirement, there may be a need to build a winter road to mobilize heavy equipment etc., and to demobilize it after the maintenance is completed. | Include the cost of building a winter road to the mine as part of long-term maintenance, if this is the only means for mobilizing/demobilizing heavy equipment required for maintenance. Costing should include building the winter road for the following season to demobilize heavy equipment. | AtkinsRéalis | Maintaining a road for the duration of the Post Closure Monitoring may be expensive.
6 | Long-term maintenance and monitoring | Post-closure monitoring activities may require air transportation to and from the site, which could involve use of the airstrip. In order to use the airstrip it will need to be maintained until all monitoring is completed. | Include costs to maintain the airstrip until post-closure monitoring is completed. | AtkinsRéalis | Yes this maybe required.
7 | Long-term maintenance and monitoring | The scope of post-closure maintenance activities includes cover maintenance and spillway maintenance. Maintenance could include other components such as tailings dams, discharge channels, revegetation, or emergency or ongoing water treatment; so the list should be expanded to provide for these and other potential maintenance activities. | Expand the scope of post-closure maintenance activities to include dams and discharge channels, revegetation maintenance, and a category for other potential maintenance requirements. | AtkinsRéalis | Agreed – but any list would not be exhaustive
8 | RECLAIM User Manual | The User Manual will need to be updated to reflect all changes and additions to the RECLAIM tables. | Ensure the RECLAIM User Manual is updated to provide clear explanations of all the activities and changes to the tables. | Brodie
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han
1 | Owners Representative Cost | Costs for the Owners Representative are included at a rate of 8% of the total capital costs estimate. This appears to be a duplication of costs associated with Engineering Design (8%) and Project Management (10%). | Suggest removing the Owners Representative line item in the Indirect Costs summary or reducing the default factor to 2% of Capital Costs or providing a description and basis for this percentage and how it differs. | AtkinsRéalis and Brodie
2 | Human Health and Ecological Risk Assessment | Human Health and Ecological Risk Assessment (3% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
3 | Finalize Closure and Reclamation Plan | Finalize Closure and Reclamation Plan (4% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
4 | Unit Price Cost References are not Regional | There do not appear to be any references to NWT or Nunavut specific unit costs in UR-Short list in workbook RECLAIM 8 Reference Tables_WorkingCopy.xlsx | Suggest that V8 include reference to northern unit price equivalents. | AtkinsRéalis
5 | Remediation | There are no referenced unit prices for remediation of any sort – bioremediation and landfill unit prices do not have any reference or backup. | Add unit prices for standard remediation techniques (e.g. biocell) | AtkinsRéalis | We don’t have a ref for this costs
6 | Land Ownership | The Reclaim Model Version 8.0 does not consider the value of owned land in determining (i.e., reducing) security. | Add consideration for land ownership as a reduction for overall security. | GNWT/CIRNAC
7 | Identify Unit Components without a reference for unit price | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | AtkinsRéalis & Brodie
8 | Unit Prices different from Price Sources | The unit prices in the Reference Table (TABLE 2: RECLAIM v 8.0 Price Sources, Basis and References) do not always match the unit prices in the RECLAIM 8.0 Unit Cost Table. For example, see the unit rate SB1 for "excavate/load/short haul" $16.27 vs $17.00). | Consider integrating the unit prices basis/reference worksheet into the model to reduce inconsistencies and reduce standalone components. | AtkinsRéalis | Discrepancies a result of rounding (need to confrim)
9 | Application of Mining RECLAIM Model feedback into the Oil and Gas RECLAIM Model. | Oil and Gas Producers utilize the "Oil and Gas RECLAIM Model". A similar consultation process should be facilitated for any proposed updates to the Oil and Gas RECLAIM Model. | Conduct a similar consultation and stakeholder engagement process for the Oil and Gas RECLAIM Model 8.0. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
WLWB - Meghan Schnurr
1 | Implementation of RECLAIM V8 | It may help reviewers if the authors could describe how they envision the updated model being implemented. For example: - Do the authors intend to start submitting closure cost estimates generated via RECLAIM V8 for all security-related reviews from the date of publication onward? Would this approach include existing projects that have previously had closure costs estimated using V7? Will the authors expect licensees and applicants to use RECLAIM V8 for all closure cost estimates from the date of publication onward? | Please describe how the authors intend to implement RECLAIM V8. | GNWT/CIRNAC
2 | Comparison against current estimates using RECLAIM V7 | The proposed updates in RECLAIM V8 are noted. Based on the proposed updates, closure cost estimates will be higher than when estimated using RECLAIM V7. This could have implications to the mining industry in the north, so it may be helpful for reviewers to have examples of how closure cost estimates using RECLAIM V8 differ from those generated using RECLAIM V7. | Is there data available that compares how closure cost estimates generated using RECLAIM V8 differ from previous estimates generated using RECLAIM V7? If not, could this data be prepared and shared? Or perhaps the authors could estimate how different the closure cost estimates will be? What are the potential implications to the mining industry in the north? | GNWT/CIRNAC
3 | Comparison against known costs to close and reclaim sites | Further to the comment and recommendation above, it may also help reviewers understand the purpose of the proposed changes to the RECLAIM model if data could be provided that compares actual costs to close and reclaim sites to estimates generated using RECLAIM V7 and V8, though, it is not apparent whether this data is available. | Have the authors undertaken an analysis that compares the actual costs to close and reclaim sites against closure cost estimates generated using RECLAIM V7 or V8? Can this data be provided? | GNWT/CIRNAC | There are sensitives with sharing this data
4 | RECLAIM Oil and Gas Model | It is noted this update pertains to the mining version of RECLAIM. Do the authors intend to update the oil and gas model as well? | Are there plans to update the RECLAIM Model for oil and gas? If so, are approximate timelines available, and would the process be similar to this update? If not, please explain why the oil and gas model will not be updated. | GNWT/CIRNAC
5 | User Manual - Discussion throughout on the status of Closure and Reclamation Plans. | The User Manual speaks to the need for applicants and licensees to have CRPs in order to develop closure cost estimates. In some instances, these speak to the need for an approved CRP. For example: - Section 2 Considerations for Northern Settings, “To derive accurate closure cost estimates, it is imperative that the company have an approved CRP which demonstrates a comprehensive understanding…”; and - Section 4.3.1 Engineering Desing, "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities." While it is important to develop a CRP to the point where it can be fully approved, this can take years (specifically for projects that require a type A water licence). This means that closure cost estimates developed during the application phase (pre-construction), during construction, and for the majority of the operational lifespan will be based on CRPs that have not been fully approved. This seems to be acknowledged in Section 4.3.6 Contingency where it is discussed that most CRPs for mining and associated estimates are at the feasibility or advanced conceptual level until near the end of operations. While this helps, it may reduce confusion further if the entirety of the User Manual recognized that CRPs typically require years of development to receive full approval. And for closure cost estimating purposes, it may be more realistic to indicate the applicant/licensee should advance the CRP as early as possible in the project lifecycle. | Consider whether the User Manual should be updated to clarify that it typically requires years to get a CRP fully approved and that applicants/licensees are encouraged to advance closure planning as early as possible. Consider revising certain messages, for example Section 2, to indicate, for closure cost estimating purposes, it is imperative that the applicant/licensee advance the CRP as early as possible in the project lifecycle. | Brodie
6 | User Manual - Definition of Contingency | A definition for contingency is provided in the Definitions and Acronyms table on page 4. A reference is provided from AACE costing terminology which seems to indicate this definition has been accepted by the construction or engineering community for costing purposes. However, it is not clear whether this definition aligns with how the term contingency is used throughout the document (specifically Section 4.3.6. Contingency) as well as how it is used for the purpose of generating a closure cost estimate via RECLAIM. For example the definition indicates contingency is "Typically estimated using statistical analysis or judgment based on past asset or project experience." Section 4.3.6 does not speak to statistical analysis, rather, the description in this section states "The determination of the contingency percentage is a subjective and project-specific task that relies on the judgement of the estimator." This could create confusion for applicants and licensees in terms of what they are expected to do when proposing contingency percentages. | Review the definition of contingency and consider whether it appropriately speaks to how users of the model are expected to derive contingencies. | Brodie
7 | User Manual - Section 4.2.5 | This section describes a worksheet within RECLAIM V8 for Interim Care and Maintenance. It states that this worksheet captures the costs from cessation of mining activities to when active remediation begins. Is this meant to only cover the time period from cessation until active remediation? What about the period up to executing closure activities - perhaps the use of the term remediation in this case is analogous to closure activities? Please note that remediation and reclamation in the general sense have different meanings. | Consider whether a revision is necessary to ensure this messaging covers the entirety of the intended period. For example, "the period between cessation of mining activities and when active remediation, or closure and reclamation begins." | Brodie
8 | User Manual - Section 4.2.6 | This section states "These should reflect the monitoring and maintenance plans and commitments identified in the Closure and Reclamation Plan" and later that "it reflects the monitoring and maintenance commitments in the Closure and Reclamation Plan." The LWBs' Standard Water Licence Conditions include Post-Closure Monitoring and Maintenance Plans, and it is typical for LWBs to require these for projects that require a water licence. Post-Closure Monitoring and Maintenance Plans are the home for the licensee to describe their approach to post-closure monitoring and maintenance. | Consider whether this section should be updated to also reference Post-Closure Monitoring and Maintenance Plans. | Brodie
9 | User Manual - Section 4.3 | The introductory sentence of this section speaks to indirect costs, indicating they are "typically allocated or spread across all activities on a predetermined basis." It is not clear what is meant by "predetermined basis," though, the final sentence in this section indicates indirect costs are calculated based on professional judgement. Either way, please note that this term / the way it is used could lead the user to think that they determine indirect costs, when, regulatory process-wise, the user proposes indirect costs, just like any other cost, and determinations are by the Land and Water Boards. | Consider clarifying the intent of the term "predetermined basis" and its usage, or whether another term could be used instead. | Brodie
10 | User Manual - Section 4.3 | The introductory sentence to this section seems incomplete: "Costs not directly attributable to the completion of an activity, which are typically allocated or spread across all activities on a predetermined basis." Pending any revisions as per the above comment and recommendation, should this sentence read as follows?: "Indirect costs are costs that are not directly attributable to the completion of an activity. They are typically allocated or spread across all activities on a predetermined basis." | Consider revising the sentence to improve clarity. | Brodie
11 | User Manual - Section 4.3 | RECLAIM V8 proposes an increase of 21% in indirect costs over RECLAIM V7, applied to the summary tab. The LWBs are responsible for setting the amount of security. Overall, it is challenging to consider what evidence is required to justify deviations from the "pre-determined" indirect costs when it is unclear how the "pre-determined costs" were derived. It is unclear what considerations went into deriving these percentages, except for the contingency indirect cost, and therefore how any deviations could be considered in the future. | Please clarify whether RECLAIM has considered deviations from the "pre-determined costs" proposed in section 4.3. Is additional information to support these pre-determined costs available? What evidence could be provided to support a deviation from these costs? | Brodie
12 | User Manual - Administrative Edits | It seems the hyperlinks in the User Manual do not work. | Review and insert links as necessary. | Brodie
13 | User Manual - Administrative Edits | Should Table 2 Column 3 be titled "Typical CRP Phase"? | For consideration. | Brodie
14 | Supplementary Information on RECLAIM V8 February 18,2025 | The supplemental information document references a "Technical Work Group and review of actual cost for Mine Closure and Reclamation at various locations across Canada." Further information beyond this has not been provided. It may be helpful to understand the range of projects and range of costs/percentages considered as part of developing the proposed indirect cost percentages. For example, the supporting information for Owners Representative states "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | If possible, provide additional information to understand the range of projects (e.g. size of project, type of mine: open pit, underground, etc.) and range of costs/percentages that were considered as part of developing the proposed indirect cost percentages in RECLAIM V8. | GNWT/CIRNAC
15 | RECLAIM V8 - New Line Item - Finalize CRP (% Closure Costs) | The ICM [Interim Care and Maintenance] tab of RECLAIM V8 includes a new line item titled, "Finalize Closure and Reclamation Plan (% Closure Costs)." This is calculated as 4% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between the cost of finalizing a CRP and the associated direct costs (i.e. closure work), and whether/how this considers how advanced the CRP is. This line item also does not seem to align with the text in section 4.3.1 of the Manual which states "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities (i.e. engineering is not required to develop a closure plan) and that there are no dramatic departures from the approved Closure and Reclamation Plan." | If possible, discuss how the 4% cost proposed was developed and whether/how this considers the varying degree of closure planning across different projects. | AtkinsRéalis
16 | RECLAIM V8 - New Line Item -HHERA (% Closure Costs) | The ICM tab of RECLAIM V8 includes a new line item "Human Health and Ecological Risk Assessment (HHERA; % Closure Costs)." This is calculated as 3% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between these direct costs and the development of an HHERA, and how the percentage was derived. | Please provide further information as to how the 3% cost proposed for HHERA was derived. | AtkinsRéalis
17 | Use of Historical Costs | The information provided indicates that costs to clean-up historical federal contaminated sites informed RECLAIM V8. It is noted that the regulatory context and expectations have changed significantly since some of those sites were operational/abandoned. It is unclear how/whether the change in regulatory regime and expectations was considered when reviewing these historical clean-up costs. | Please describe how/whether the change in regulatory expectations was considered when reviewing the historic clean-up costs of federally contaminated sites. | GNWT/CIRNAC
18 | Owners Representative | The supplemental information provided to support the indirect cost associated with "Owners Representative" references support to CIRNAC and scrutiny of the Federal Contaminated Sites Program. Given that the GNWT would be responsible for clean-up for the majority of current projects in the Mackenzie Valley, it is unclear whether GNWT has adopted this same approach to the clean-up of abandoned sites. | Clarify whether the GNWT has adopted this same approach of hiring an Owners Representative. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Independent Environmental Monitoring Agency - Jamie Mistry
1 | Post Closure – Annual Requirements | The Post-Closure sheet requires an estimate of annual costs and the number of years of post closure activities. The overall sum of activities is then multiplied by the number of years to give a total cost. Some post-closure activities will likely occur less frequently than annually, and the spreadsheet calculation will not function correctly in these cases. | Revise the Post-Closure sheet to include columns that list the frequency of each activity, and the number of events expected over the post-closure period, rather than assuming that all costs are annual costs. | AtkinsRéalis
2 | ICM – Water Management | The ICM sheet does not include activities specifically focused on water management during interim care-and-maintenance. These costs are also not specifically addressed in the Water Management or Water Treatment sheets. However, water management is often (perhaps usually) a primary focus of interim care-and-maintenance activities at mine sites, including during temporary closures and in the early stages before active implementation of a closure and reclamation plan. Requirements for accessing security bonds typically arise when there is an early, unplanned mine closure. In these circumstances water management is likely to be a significant activity for maintaining water levels in tailings ponds, managing flood flows, managing runoff from disturbed areas, and dewatering of mines (pits and underground). It is not uncommon for dewatering of mines to continue during periods of interim care-and-maintenance, especially in the event of early/unplanned closure when there may be interest in selling the project – allowing mines to flood is often considered to devalue the “asset” and therefore is part of the necessary care-and-maintenance activities. While there are currently no heap leach projects in NWT, water and solution management at heap leach mines is likely to be the largest cost during periods of interim care-and-maintenance. | Revise the ICM sheet to include activities focused on water management that will be required during interim care-and-maintenance. | AtkinsRéalis
3 | Interim Care-and-Maintenance | The Supplementary Information states that the default interim care-and-maintenance period in RECLAIM is 2 years, but the Interim Care-and-Maintenance (ICM) sheet in the model sets the value at 3 years. Past experience indicates that, in the event of early/unplanned mine closure, interim care-and-maintenance periods can be lengthy because of the time required to sort out financial matters, explore sale/re-opening options, complete CRP development/permitting and procure contractors. 3 years should be the minimum period applied. | Clarify the default duration of interim care-and-maintenance as 3 years, as currently applied in the model. | AtkinsRéalis
4 | Water Management - Sediment/Erosion Management and Control | The Water Management sheet addresses closure and reclamation of operational sediment control facilities. However, it does not directly address the potential need for continued sediment control measures during reclamation activities, or after reclamation activities are complete. This could require construction of new sediment control facilities or improvement (e.g., expansion, armouring) of existing ones. It could also require ongoing operational activities to manage sediment. | Revise the Water Management sheet to include lines related to development and implementation of sediment control measures for the closure and post-closure periods. | AtkinsRéalis
5 | UG Mine – Contact Water Management | The UG (Underground) Mine sheet does not include costs for treatment of mine water. The sheet appears to assume that underground mines will be flooded but no treatment would be required. Some mines may fill and drain over time, with water quality that is not acceptable for discharge. In other cases, leakage from the mine through groundwater is possible, again raising possible water quality concerns. These conditions may require some measures for ongoing or periodic water management or water treatment, including possible active or passive treatment outside of the underground mine, or some form of mine-pool treatment within the mine. | Add water management and treatment as potential costs in the UG Mine sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
6 | Chemicals – Soil Handling | The Chemicals sheet includes costs for excavating contaminated soils and transporting them to an onsite remediation facility, for example a land-farm. There will also be costs for rehandling these soils to a final disposal location at the conclusion of land-farming. | Revise the Chemicals sheet to include lines for final disposal of remediated soils. | AtkinsRéalis
7 | Post Closure – Maintenance | The scope of maintenance activities described in the Post Closure sheet is limited to covers, spillways and wetland treatment systems. For many mine sites, the maintenance requirements will be much more extensive. For example, tailings dams, diversions and sediment control facilities may all require maintenance. Passive treatment systems other than wetlands may also require maintenance or replacement. Wetlands may also require maintenance that is more extensive than what is described, including removal and replacement of substrates and vegetation after some period of time. In most cases, “passive” treatment systems require some periodic maintenance and operational activities, and are therefore better described as semi-passive. | Expand the maintenance components of the Post Closure sheet to address a broader scope of expected maintenance requirements. | AtkinsRéalis
8 | Rock Pile – Heap Leaching | According to the manual, the Rock Pile sheet is intended to address not only waste rock piles, but also heap leach facilities. Closure of heap leach facilities is usually substantially more complex than for rock piles. Heap leach facility closure entails continued solution circulation, heap rinsing, heap detoxification and associated water treatment, managed draindown, decommissioning of pumping and piping equipment, establishment of permanent drainage systems, among other things. The activities listed in the Rock Pile sheet are not adequate to address potential heap leach facility closure. | Incorporate specific activities and costing for heap leach facility closure in the model. | AtkinsRéalis
9 | Bldgs & Equip – Roads | The Bldgs & Equip sheet is missing some activities that may be common for closure and reclamation of roads. Reclamation frequently includes flattening of safety berms along the length of the road, and establishment of effective road blocks and any access points. Also, complete removal of roads back to the native landscape may be necessary in some cases, or overall re-grading of road embankments. Construction or upgrading of drainage works along road alignments may also be required. | Additional road reclamation and closure activities should be added to the Bldgs & Equip sheet. | AtkinsRéalis
10 | Mobilization – Annual Mobilization | The Mobilization sheet includes a column for quantity of mobilization with each type of equipment or supply. In some cases, mobilization/demobilization of equipment could be required annually through the closure and reclamation phase, or periodically during post-closure. For transparency, it would be useful to separate the quantity and the number of annual mobilization requirements – e.g., how many dump trucks have to be mobilized to site in each year. This would provide a better understanding of the equipment requirements and costs over time, and information about what equipment would be expected to remain on site year-round, versus mobilization each year. | Revise the Mobilization sheet to separately identify the annual mobilization requirements. | AtkinsRéalis
11 | Indirect Costs | The Summary Report and Supplementary Information describe the rationale for proposed changes in the default percentages for indirect costs. The rationale is consistent with experience from mine closure and reclamation projects and with current approaches to engineering. The Summary Report also notes that costs for mobilization and interim care-and-maintenance are now included in the base costs for calculating indirect costs. This also makes sense because both of these costs will be subject to the same indirect costs as the rest of the capital costs. | Retain the proposed default indirect costs percentages and the inclusion of mobilization and interim care-and-maintenance costs as part of the capital cost for calculating indirect costs. | AtkinsRéalis
12 | Summary – Indirect Costs | N/a | The updates to the recommended percentages for indirect costs appear to reflect the experience with mine closure and reclamation projects and should be retained. | AtkinsRéalis
13 | User Manual – Section 1 | The final bullet in the list of principles in Section 1 of the User Manual states that financial security must retain its full value throughout the life of the mine and if applicable, beyond. The value of required security may vary through the life of the mine and the wording of the principle should be clarified | The final bullet in the list of principles should be reworded to clearly state that adequate security must be in place throughout the life of the mine and in post-closure to fully address the liabilities associated with the site. | Brodie
14 | Summary – Future Value | The future value calculations appear to assume that the 3 year period of Interim Care-and-Maintenance starts immediately at the time the calculations are completed. This means that if the security amount is set based on today’s calculations, but unplanned closure begins 1 year later, the security will be 3% too low, or 16% too low if closure begins 5 years later. | The potential shortfall in liability estimates caused by assumptions about timing for the start of interim care-and-maintenance should be addressed in the model. One option is to establish requirements for frequent adjustments of security (e.g., every 2 years) to account for these shortfalls. | AtkinsRéalis
15 | Summary – Future Value | N/a | The addition of future value is a good idea and should be retained. | AtkinsRéalis
16 | Land Reclamation Activities | In response to a comment/recommendation to include a more comprehensive list of land reclamation activities in the model, the Supplementary Information responds that site-specific activities should be proposed based on end land use and the CRP. The response does not address the comment that was raised. Of course, site-specific closure activities should be defined in site-specific CRPs. However, the model is intended to provide a comprehensive tool for estimating costs of closure and reclamation activities, no matter what activities are selected for a specific site. As a result, the model should include a more comprehensive list of land reclamation activities and provide for estimating their costs, as suggested in the comment. The following comments below identify several specific instances where the model should be revised to include more comprehensive listings of activities. While this is likely not a complete list, it should be considered a starting point for more thoroughly identifying potential closure measures and activities. | Undertake a process to develop a more comprehensive list of possible closure and reclamation activities and incorporate these into the costing model. | AtkinsRéalis & Brodie
17 | Water Management - Reclamation Quarries | The Water Management sheet includes costs for installing and removing pumping systems for managing water in a reclamation quarry. Other costs associated with both quarry development (e.g., material testing, land clearing, road development, etc.) and water management (e.g., diversions, sediment control) for reclamation quarries are not addressed. Reclamation activities often require development of new quarries (in undisturbed areas, or in waste [e.g., overburden] storage facilities) or expansion of existing ones to provide the materials necessary for closure and reclamation. | The Water Management sheet should be revised to include lines that address additional water management activities that may be associated with quarries. Costs for quarry development should also be addressed within the overall model. | AtkinsRéalis
18 | Water Management – Passive Treatment | The activities identified for passive treatment are all associated with construction of wetland treatment. There are other forms of passive treatment that may also be relevant, for example permeable reactive barriers, bioreactors or underground mine pool or groundwater treatment. | The Water Management sheet should be revised to include activities that may be associated with other forms of passive treatment that are not wetlands. | AtkinsRéalis
19 | User Manual – Section 4.2.5 | Section 4.2.5 of the User Manual describes expectations for costing for interim care-and-maintenance activities. The description of a typical scenario states that open pit and underground mines would be allowed to flood. In cases of early or unplanned mine closures (i.e., where there are draws on security bonds), there are often lengthy periods of discussion about mine re-opening and sale. In these cases, mine dewatering often continues in order to avoid reducing the value of a potential asset. The assumption that mine dewatering would be discontinued may underestimate the actual costs that would be incurred. | The default assumption for interim care-and-maintenance costing should be that mine-dewatering will continue for this period. | Brodie
20 | Future Value and Unit Cost Updates | The Supplementary Information describes the new approach taken for estimating the future value for liability estimates. This approach is a positive addition and attempts to address the challenge that the security bonding regime and the forms of security do not allow for bond amounts to grow to address inflation and other escalation of costs. The User Manual defines “escalation” as “a provision in costs or prices for uncertain changes in technical, economic, and market conditions over time. Inflation (or deflation) is a component of escalation.” | Revise the User Manual and the model to require consideration of other factors for cost escalation. This should include requirements in the User Manual for proponents to provide rationale for selected escalation factors. In the model, it would be useful to include separate entries for inflation and other cost escalators so that there is a requirement to consider whether other escalators are relevant or not. | AtkinsRéalis & Brodie
This acknowledges that inflation is only one component of escalation, with other components (e.g., labour market conditions in northern Canada, or availability of construction contractors) that may also lead to increases in costs. Nonetheless, the User Manual and model only rely on inflation as a cost escalator when calculating future value (Summary sheet) or for updating unit costs (Unit Cost sheet). Other than in the definition of “escalation” there is little further mention of other possible influences on cost escalation, though Section 4.5.1 of the User Manual does identify some other possible sources of information about escalation.
21 | General Comment – Site Management | The model lacks clear information about person-hours for ongoing administrative responsibilities at the site, for example security, health and safety, personnel management, etc. during the implementation of the closure. Some of these are addressed for interim care-and-maintenance (e.g., on-site caretaker), but would also be required throughout the implementation of closure and reclamation. | Costs for ongoing site management should be addressed either in the Summary sheet, or an additional Site Management sheet should be added. | AtkinsRéalis
22 | Water Treatment – Post Closure | The post-closure component of the Water Treatment sheet does not address major maintenance and equipment replacement activities. Water treatment facilities that have to operate in a long post-closure period will wear out and require refurbishment and replacement at some point in time. Costs and timing for these major capital expenditures need to be included. | Revise the Water Treatment sheet to include lines for costs related to major refurbishment or replacement of post-closure water treatment facilities. | AtkinsRéalis
23 | General | The Independent Environmental Monitoring Agency (Agency) has reviewed the proposed changes for RECLAIM v8.0 and associated user manual (RECLAIM) submitted by Crown-Indigenous Relations and Northern Affairs Canada (CIRNAC) and the Government of Northwest Territories (GNWT). The Agency submits the following comments for your consideration. | N/A | AtkinsRéalis | See Comments 24 to 32
24 | User Manual – Section 1 | Section 1 of the User Manual states a principle that costs should be based on having a third-party contractor carry out the reclamation work. On-site equipment including both mobile equipment and fixed facilities (e.g., water treatment plants) may not be owned by the proponent and costs would be incurred to access the equipment and facilities. | The principle that costs should be based on the cost of having work done by a third-party contractor should be expanded to clarify that the costs must also be estimated assuming that all equipment, supplies and facilities will be provided separately. | Brodie
25 | Tailings – Water Treatment | The Tailings sheet refers to treatment of seepage, which may not be the only treatment that is required for a tailings facility. In some cases, treatment of tailings pond supernatant water may also be required, either during implementation of closure and reclamation, or post-closure. | Revise the water treatment references in the Tailings sheet to include broader references to types of treatment that may be required. | AtkinsRéalis
26 | Open Pit – Pit Closure Methods | The Open Pit sheet considers a narrow range of potential closure options for pits, focused on flooding of pits. There are other options for closure of pits that need to be addressed. For example, some pits may be closed in a dry condition, with associated water management, or some may be backfilled with waste and covered (e.g., Giant Mine Remediation Project). | Revise the Pits sheet to address a broader range of closure options for pits. | AtkinsRéalis
27 | Open Pit – Contact Water Management | The only water treatment option addressed in the Open Pit sheet is the possible addition of in-pit treatment during flooding – either by chemical or biological means. There is no water treatment line linked to the Water Treatment sheet. However, there are some instances where it may be necessary to actively pump and treat water that has accumulated in a pit, potentially before flooding, or to establish dry conditions. | Add active water treatment as a potential cost in the Open Pit sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
28 | HHERA and Regulatory | The Summary Report states that the model was revised to include 3% indirect costs for Human Health and Ecological Risk Assessment (HHERA), and 4% indirect costs to finalize the Closure Reclamation Plan (CRP). These additions make sense, but it is unclear where they are included in the model. If they are already included in the Summary sheet calculations, they should be specifically identified. | Provide additional clarity about where the indirect costs for HHERA and CRP finalization are incorporated into the model. | AtkinsRéalis & Brodie
29 | General Comment – Winter Road costs | The Water Treatment and Mobilization sheets include lines for costs associated with use of the winter road. In Water Treatment this appears to be related to site access and reagents, while in Mobilization it is related to equipment, fuel and accommodation (i.e., camp), with a focus on materials that must be brought to site. However, closure for some other components (e.g., buildings, hazardous wastes, contaminated soils) may require shipping off site. Also, it is not clear that winter road costs have been incorporated for all closure and reclamation supplies, for example liner construction materials. These activities may also incur winter road costs. | Where closure and reclamation activities will require off-site shipping or the delivery of supplies to site, sheets should be revised to include lines for winter road costs and other shipping costs. | AtkinsRéalis
30 | Summary – Future Value | The spreadsheet requires the user to enter timing for “when will post-closure begin”, by entering a number. Some additional clarity should be provided about what this number represents: Is it the number of years from the current time until post-closure, or the number of years between cessation of operations and post-closure, or the number of years after completion of interim care-and-maintenance before post-closure begins, or some other value? If the timing is intended to start at the time that the estimate is made, then the same shortfall issues identified above for the interim care-and-maintenance timing will also apply to the timing for start of post-closure. | Clarify the intended definitions of timing for when post-closure will begin. | AtkinsRéalis
31 | User Manual – Section 2 | Section 2 of the User Manual describes special considerations for estimating costs for reclamation activities in northern settings. One important factor that appears to be missing is the potential cost implications of meeting requirements for northern participation in contracting and work opportunities. | The bullet list of factors that may affect costs for projects in northern settings should be expanded to include the potential for increased costs associated with meeting requirements for northern participation in reclamation activities. | Brodie
32 | Buildings & Equipment (Bldgs & Equip) – Landfill | The Bldgs & Equip sheet addresses closure of landfills (e.g., placement of cover material) but it does not cover the cost of constructing a landfill. Even for non-hazardous materials, construction of landfills can be a substantial cost. Landfills developed and used during mine operations typically do not have capacity to contain all of the material arising from closure and reclamation. Costs for non-hazardous landfill construction can be substantial in some cases (e.g., Giant Mine). | Revise the Bldgs & Equip sheet to include costs for development and construction of landfills. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Teck Metals Ltd. - Dr. Bjorn Weeks
1 | Feedback Letter | Please see initial feedback in the attached letter. Inflation Application Without Discounting. The RECLAIM 8.0 update proposes incorporating inflation into cost estimates but does not address the standard practice of discounting to reflect the time value of money. Applying inflation without discounting leads to distorted financial obligations, potentially resulting in excessive and unrealistic financial security requirements. Without discounting, even minimal recurring annual costs (e.g., $20,000 per year) would result in infinite bonding requirements, which contradicts financial principles and international best practices. Financial assurance practices that deviate substantially from international best practices may place the region at a competitive disadvantage, while failing to deliver real benefits | Paraphrased: Include discounting into cost estimate | GNWT/CIRNAC
2 | Feedback Letter | Please see initial feedback in the attached letter. Absence of Any Credit for Company Size and Environmental Performance We believe the bonding requirements should take into account both past environmental performance and the financial resources available to the company to meet its environmental liabilities. Teck is one of several International Council on Mining and Metals (ICMM) member companies operating in the region. No ICMM member company has ever defaulted on its closure obligations, nor would doing so be feasible in the context of maintaining a global social license to operate. | Paraphrased: Credit for environmental performance and the financial resources | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm
1 | Increased Unit Costs | Please see initial feedback in the attached letter. The justification for increased excavation and hauling costs (e.g., short-haul soil movement increasing from $4.3/m³ to $17/m³) lacks transparency on how these figures were derived. What specific contractor quotes, productivity rates, or haul distances were used in these calculations? Were regional variations considered, or was a blanket rate applied regardless of site-specific factors? Can industry propose alternative short-hauling costs based on regional/site-specific factors such as terrain, available borrow pits, road conditions, access to rail, and equipment availability? For example, a mine site with established all weather and paved road networks and short, efficient haul routes may have significantly lower hauling costs than a remote site requiring seasonal ice road access. Will proponents have flexibility in presenting alternative cost estimates to justify lower unit costs? | Paraphrased: Provide more detail on unit rate development. Unit rates should include regional variation. Clarify if user-specified rates can be used in RECLAIM. | AtkinsRéalis
2 | Higher Indirect Cost Percentages | Questions Asked Contingency Increase (20% to 25%): While uncertainty exists in closure planning, what empirical data justifies a 25% contingency rather than the previous 20%? Can examplesof cost overruns from past projects be provided to support this increase? Engineering Design (5% to 8%) & Project Management (5% to 10%): These increases suggest significantly greater complexity in closure execution. What historical data from northern mine sites demonstrate that these cost assumptions are necessary? Bonding/Insurance (1% to 3%): Can specific case studies or actuarial assessments be provided to validate this change? | Paraphrased: Provide further justification to increased contingency percentages. Provide further northern justification to increased engineering design percentages. Provide case studies to justify increase in bonding/insurance percentage. | AtkinsRéalis
3 | Reclassification of Mobilization and Interim Care & Maintenance (ICM) as Capital Costs | Moving these costs to Capital Costs now subjects them to contingency and indirect cost multipliers. How does this align with the principle of accurately reflecting third-party contractor costs? Industry projects varying durations of ICM depending on site conditions. How was the assumption of a minimum 3-year ICM period determined, and why is it being applied universally? | Paraphrased: Include more rationale as to why Mob and ICM were moved to Capital Costs and whether this accurately reflects third-party contractor costs. Provide rationale and justification for minimum 3-year ICM period. | AtkinsRéalis
4 | Owner’s Representative Cost (10% of Direct Costs) | This is a new addition to RECLAIM. While we acknowledge the role of an Owner’s Representative in some government-managed projects, why is this now mandated for all projects, including those with active operator management? Can industry proponents provide alternative methodologies for project oversight rather than defaulting to a 10% additional cost? | Paraphrased: Provide rationale for why Owners Rep costs are applied to all mines. Can industry propose an alternate methodology for oversight rather than the default. | AtkinsRéalis
5 | Human Health and Ecological Risk Assessment (HHERA) Cost (3% of Capital Costs) | Industry already conducts environmental monitoring as part of regulatory requirements. What additional studies are being assumed under this cost, and how is the 3% figure justified? Given that mines with comprehensive monitoring programs may already demonstrate minimal risk, why is this cost not applied selectively based on site-specific needs? Can proponents outline their monitoring programs and propose a more phased cost-structure alignment with project-specific timelines? | Paraphrased: Can CIRNAC and GNWT provide additional studies to industry to justify the 3%? HHERA should be applied to mines selectively based on environmental performance. There should phased cost structure that could align with project timelines. | AtkinsRéalis | Not sure what is meant with third recommendation.
6 | Future Value Calculation (3% Inflation Rate) | While inflation is a factor in cost projections, applying a fixed 3% escalation rate does not account for fluctuating economic conditions. Has any sensitivity analysis been conducted to assess alternative inflation scenarios? Can proponents propose their own escalation methodologies based on contractual arrangements and project-specific timelines? | Paraphrased: Sensitivity analysis should be conducted on applying a fixed inflation rate for future value calculations. Proponents should be able to propose their own escalation methodologies based on contractual arrangements and project-specific timelines. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
De Beers Canada Inc. - Gahcho Kue - Kurtis Trefry
1 |  | De Beers is supportive extended engagement period granted to allow further opportunity for industry feedback to be considered into any changes. The initial deadline coincided with our annual reporting timelines, creating challenges in dedicating the necessary time and resources to this review. The additional time granted will allow us to prepare a thorough and well-considered submission that adequately addresses the updates. Given the potential for significant implications to the mining industry, the proposed changes to the RECLAIM model require significant time and resources to allow for a detailed review by all parties. De Beers looks forward to partaking in further engagement sessions and will provide more detailed comments following that period. | N/A | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Fisheries and Oceans Canada (DFO) - Mr. Derek Donald
1 | Financial security associated with Fisheries Offsetting Plans. Specified under Section 2 (1)(b) and Schedule 1, Section 16, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations. | Fisheries and Oceans Canada (DFO) would like to thank CIRNAC and the GNWT, for developing and updating the RECLAIM model and providing this opportunity for review and comment. The RECLAIM model can be an important part of the Fisheries Act authorization process in that the model is often used by proponents when developing an itemized list of costs for conducting the Offsetting work and monitoring the project to inform the Letter of Credit associated with an Offsetting Pan, and by DFO when reviewing the financial liability associated with these plans. Fisheries Act authorizations can follow the lifecycle of a mine from pre-operational permitting to post-closure Offsetting Project monitoring. Financial liability and associated security in the form of an irrevocable Letter of Credit, is a key component of the Fisheries Act and associated Regulations. Mine development in Nunavut and the Northwest Territories often necessitates activities that directly or indirectly result in the Death of Fish, the Harmful Alteration, Disruption or Destruction of fish habitat, and/or the deposit of deleterious substances in water frequented by fish, governed respectively by Section 34.4, 35, and 36 of the Fisheries Act. These activities can be authorized under the Fisheries Act so that the activity is carried out in accordance with conditions set out in the authorization and the Regulations. Section 2 (1)(b) and Section 16 of Schedule 1, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations, requires the development of a Fish Offsetting Plan, including the financial liability and associated security, to cover the costs of implementing the fish Offsetting Plan. These Fish Offsetting Plans often include activities associated with general construction, ground and water works, culvert installation, long-term monitoring, etc. Costs associated with these Fish Offsetting Plan activities can be subject to individual cost estimates based on a proponent’s experience and can also be scrutinized with limited referenceable sources. This type of subjective cost estimation and review creates risk and introduces uncertainty, for both proponents and liable governmental parties (DFO and ECCC). DFO believes this update to the RECLAIM model is an excellent opportunity and the appropriate location to include constrained cost estimates for these types of activities. DFO would like to discuss this further with CIRNAC and the GNWT during the week of May 12 - 16, 2025. DFO would also be interested in hearing feedback from all interested parties. | DFO recommends that the RECLAIM Model include in a Summary line item, and associated sheet in the Excel model specific to the implementation of a fish Offsetting Plan. This could include, but not limited to works associated with discipline specific construction, ground and water works, culvert installation, and long-term monitoring. Adding this to the model would reduce financial risk by providing a more predictable process of securing a Fish Offsetting Plan, which is ultimately tied to the final reclamations of a mine site that has impacted fish and fish habitat. DFO would like to discuss this possibility with CIRNAC, the GNWT, and all interested parties during this update of the RECLAIM model. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo
1 | Letter | Please see attached letter.
2 | Origin of Unit Rates | Burgundy Diamond Mines (Burgundy) and other proponents have been requesting that CIRNAC and GNWT provide the level of transparency and justification for RECLAIM unit rates that is demanded of proponents who put forward site-specific unit rates. This long-standing request remains wholly unsatisfied by the information provided with RECLAIM 8.0. For example, the proposed "load/haul/place" unit rates are described as being derived from "First Principles". However, simply referencing "First Principles" and listing a few assumptions under additional notes does not provide proponents with the information needed to adequately understand the unit rate or assess appropriateness for a specific site. | RECLAIM 8.0 should be accompanied by clear, detailed data on the derivation of the proposed unit rates, ensuring proponents can adequately understand the rates and make a rational determination of their appropriateness for an individual site or closure activity. | AtkinsRéalis
3 | Moving Mobilization and ICM to Capital Costs | Mobilization and ICM costs were previously included under Indirect Costs which excluded them from the indirect percentage calculations. The new approach introduces a compounding effect and will significantly inflate the overall security estimate. This would result in overestimations that do not accurately reflect actual closure and reclamation needs particularly for major operations such as Ekati Diamond Mine (Ekati) with substantial security requirements. | The Mobilization and ICM costs should be maintained under Indirect Costs where the existing indirect cost percentages can adequately account for variations. This would avoid the compounding effect introduced by their inclusion in Capital Costs while still ensuring these costs are adequately captured within the model. | AtkinsRéalis
4 | Owner's Representative | A new line has been added under Indirect Costs for Owners Representative to ensure that project objectives are met, with a default percentage of 10% of the direct costs assigned. The assigned percentage appears excessively high particularly for licencees with substantial direct costs. | The assigned 10% default percentage should be reevaluated and a reduction considered to better align with actual project requirements and industry norms. Additionally, more information should be provided to clarify the methodology and rationale behind determining this percentage and to assess its applicability across different projects. An alternate approach, such as an estimated cost (rather than a percentage) should also be developed and evaluated. | AtkinsRéalis
5 | HHERA and Final CRP Costs | The cost to complete a Human Health and Ecological Risk Assessment (HHERA) and Final Closure and Reclamation Plan (FCRP) has been added to the model at 3% and 4% of Capital Costs, respectively. While it is acknowledged that FCRP costs may not have been explicitly included in RECLAIM 7.0, the regular review of security estimates has ensured their incorporation for operations like Ekati. The most recent review by the GNWT in 2022 determined a significantly lower FCRP rate of approximately 1% of direct costs. There is no rationale for applying these items as a percentage of total rather than an estimated cost. These items are well established and well defined in scope and cost such that actual estimates can readily be developed. A percentage of total as proposed provides a grossly over-costed estimate for large site such as Ekati. Moreover, the risks addressed by HHERA are already evaluated as part of the permitting process. Monitoring data is utilized to assess operational and closure risks, which are accounted for in interim CRPs that are mandatory and regularly updated. As such, the addition of these costs in the proposed model is deemed unnecessary and the proposed percentages appear excessively high. | Burgundy recommends that HHERA and FCRP costs be excluded from the model. Alternatively, these percentages should not be based on Capital Costs given that risk evaluations and FCRP development will rely significantly on existing assessments and CRP plans developed during ongoing operations. A reduction or redefinition of these percentages is necessary to ensure they more accurately reflect the actual scope of work and associated costs. An alternate approach of an estimated cost (i.e., not a percentage) should be developed and evaluated. | AtkinsRéalis
6 | Future Value Calculation | The future value calculation has been introduced to capture the anticipated costs of activities based on when they are expected to occur. A default inflation rate of 3% is applied which corresponds to the Bank of Canada’s upper target for annual inflation. For example, a cost estimate developed in 2028 using RECLAIM 8.0 standard rates would undergo a 3% annual inflation increase over four years (2024 to 2028). However, applying a predetermined, singular inflation rate is not appropriate when actual data is available. It is also not always suitable to apply the same inflation rate across all work included in a closure estimate. RECLAIM 8.0 documentation acknowledges the existence of various inflation estimates beyond the broad-based consumer-oriented CPI, but it discounts these approaches. Since the majority of mine closure plan costs are not consumer-oriented, it may not be appropriate to apply the general CPI across the entire estimate. Ekati's security estimates already incorporate an inflation calculator developed with stakeholders' input. This calculator considers the development year of each unit cost and applies inflation rates accordingly, resulting in inflation rates of less than 2%. Applying the upper target of the Bank of Canada’s inflation range may lead to overestimations, given that average inflation rates have remained between 1.5% and 2%. This approach is not ideal for long-term mine closure costing, as it introduces inflation without accounting for interest. It assumes that the financial security is cash in hand, which does not accrue interest over time. By comparison, the Province of British Columbia uses a net discount factor (i.e., net of both inflation and interest) for recurring long-term costs. The approach proposed in RECLAIM 8.0 introduces a substantial cost factor that could significantly affect project viability. This issue requires detailed engagement and financial analysis by the government before any consideration for implementation. | 1. RECLAIM 8.0 should provide a clear rationale for adopting a single pre-determined inflation factor and consider developing an alternative approach that utilizes inflation rates most appropriate to the specific work and costs within the closure cost estimate. The future value inflation rate should be revised to reflect a more accurate figure, such as the average of historical inflation data over a relevant timeframe, rather than defaulting to the upper target of 3%. This adjustment would result in a more balanced and accurate estimate, avoiding excessive conservatism in the model. Additionally, greater transparency is needed in how inflation rates are applied to different unit costs over time to ensure consistency and confidence. 2. This cost item should not be implemented without specific, in-depth engagement and financial analysis including an evaluation of experiences in other regulatory jurisdictions. | GNWT/CIRNAC
7 | Incentivizing Progressive Reclamation | The proposed updates to RECLAIM 8.0 emphasize increasing securities to address potential reclamation costs. It is equally important to incentivize progressive reclamation during operations. Progressive reclamation not only reduces overall closure liabilities but also demonstrates ongoing commitment to environmental stewardship. Models used in jurisdictions such as Quebec and the Alberta oilsands provide practical examples of incentivizing progressive reclamation by allowing operators to utilize existing securities during operations, thereby encouraging earlier action rather than deferring it until closure. | Burgundy recommends that the GNWT implement mechanisms to incentivize progressive reclamation activities during operations. This could include provisions that allow for the partial release or reallocation of securities to fund reclamation efforts. Such measures would enhance operational efficiency, reduce the financial burden of increasing securities and encourage operators to proactively incorporate reclamation into their operational plans. This approach would ultimately lead to more sustainable and cost-effective closure outcomes. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Tlicho Government - Jessica Pacunayen
1 | General | The Tłı̨chǫ Government reviewed CIRNAC and GNWT's proposed revisions to RECLAIM 8.0, the RECLAIM User Manual, and supporting documentation. These documents are used by the GNWT, CIRNAC, mining companies, and the Land and Water Boards to set mining security deposits. RECLAIM and the User Manual are also a resource for all parties reviewing security deposits. Tłı̨chǫ Government may also wish to use RECLAIM to estimate security deposits for future mines on Tłı̨chǫ Lands. | N/A | GNWT/CIRNAC
2 | Increased security deposits | RECLAIM 8.0 includes numerous substantial increases. Most unit costs went up to varying degrees, and a few went down. On average unit costs appear to have more than doubled. Some key unit costs have increased far more than this, for example the lower estimate for winter road construction went up by more than 10 times. Indirect costs are now up to 58% of direct costs instead of 32%, plus there are new costs for a human health and ecological risk assessment and finalization of the closure plan (totaling 7% of capital costs). There is also a newly proposed cost for inflation during closure and post-closure. Post-closure monitoring and maintenance and mobilization/demobilization now have indirect costs (as percentages) added to them. These and other increases would result in very large increases to security deposits at existing mines. CIRNAC/GNWT explained that the increases are because the current unit costs (in RECLAIM 7) are more than 10 years old and because costs in the current RECLAIM spreadsheet (version 7.0) are too low compared to actual costs the government has incurred for actual reclamation projects. As noted in "Review of Mine Financial Security Estimates and RECLAIM": "it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." CIRNAC and its consultants are perhaps in the best position to provide actual costs of closure activities. There has been talk over the years that RECLAIM is dramatically underestimating closure costs. It is possible that even with the proposed revisions, RECLAIM 8.0 would continue to underestimate reclamation costs. For example, the Supplementary Information provided on Feb 18 says that the Owner's Representative costs are actually 12% to over 20% of costs, not the 8% adopted in the proposed revisions to RECLAIM. This is just one of several examples that may mean the RECLAIM 8.0 continues to underestimate reclamation costs. Others are in comments below. | RECLAIM should estimate the actual costs of closure and reclamation, even though it appears that the new estimates will likely be much greater than current security deposits. However, this does not mean that the Boards should immediately increase all security deposits in the North to reflect actual reclamation costs. This could have serious economic and social repercussions, and could undermine the objectives set for resource management under the modern treaties, to balance conservation and development for 'optimum benefit'. Instead, updating RECLAIM to reflect actual costs is a necessary first step to fixing some serious and far-reaching problems related to security deposits and more broadly to sustainable and responsible mining in the North. Actual reclamation costs must be known and on the table in order to have informed discussions about the impacts, benefits, and risks of mining, including the risk of having to pay for cleanup of abandoned mines. Underestimating security can also enable companies with insufficient financial resources to mine in the North, which poses a serious risk to the Northern economy and the environment. Greater attention should be given to a mining company's financial health and the risks for each project (e.g., risks from market conditions, remoteness, logistical issues, etc.) when weighing the impacts, benefits, and risks of approving a full-scale mine. Decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis, and input from citizens and residents. If the federal and territorial governments, or the Boards in working to achieve the treaty-based objectives for resource management, wish to offset the burden of posting security for actual reclamation costs, this should be done in a transparent, carefully considered manner informed by the actual costs of clean-up and the views of all parties. The Tłı̨chǫ Government would like to be involved in any such discussions, and as a treaty partner, must be involved in these discussions. Other topics raised in our comments are inextricably intertwined with the issue of RECLAIM estimates, for example relinquishment of liability, promoting progressive reclamation, and financial security for potential disasters. These issues should be discussed holistically along with RECLAIM updates. Some of these issues may need legislative amendments to properly address them in the long run. | GNWT/CIRNAC
3 | Increased security deposits - incentives for progressive reclamation | The RECLAIM Manual includes a policy that the security deposit cannot be reduced for progressive reclamation (reclamation completed during operations) until the mining company has completed the reclamation work. This is a sensible approach to ensure there is always enough money for reclamation if a company goes bankrupt. However, a more refined and strategic approach to this problem should be considered to enable work to proceed while limiting risks if a company goes bankrupt. This would allow more parts of a mine to be reclaimed early in the mine life, which benefits the environment, the taxpayer, and the company. A company's financial capacity, the financial and environmental risks of leaving parts of the mine unreclaimed, and other factors would need to be considered. | Financial mechanisms to promote progressive reclamation should be evaluated and discussed with all parties. | GNWT/CIRNAC
4 | Increased security deposits - case studies | Based on our participation at the meeting hosted by CIRNAC and GNWT during the PDAC conference in March 2025, we understand there may be disagreement over whether RECLAIM 8.0 is overestimating or underestimating closure costs. CIRNAC and the GNWT have actual cost data from abandoned mine reclamation in the North. Using this data to validate RECLAIM 8.0 is an indispensable step to deal with these opposing views and to ensure security deposits cover the full costs of reclamation without unduly burdening industry. The Discussion Paper says that CIRNAC and GNWT had originally intended to use historical data to help populate RECLAIM 8.0 (which is different than historical data for validation). However, the Discussion Paper says this did not happen because "contractor confidentiality, limited examples available to provide a sufficient range and average of costs (which can vary considerably depending on the size and scope), and the effort required to synthesize data." While these issues might make it challenging to use historical cost information to update RECLAIM 8.0's costs and assumptions, it should not prevent validation of the model. Validation is about running information from past projects through RECLAIM 8.0 and comparing this to the actual cost of the project. If confidentiality issues cannot be addressed, CIRNAC and GNWT should at least conduct this validation step internally and publicize whether the exercise validated the model. Further, "the effort required to synthesize data" may be a barrier, but it is arguably a relatively small price to pay compared to the benefits of improved cost estimates. In addition to this validation step, CIRNAC and GNWT should use historical cost data to improve RECLAIM. Based on the unit cost reference tables provided as supporting documentation, it appears this may have been done to some extent. If not, CIRNAC and GNWT should take advantage of historic cost data in ways that maintain confidentiality and account for limitations in the data. | 1. Before finalizing RECLAIM 8.0, CIRNAC and GNWT should validate it, by running RECLAIM (i.e., entering actual quantities, selecting the appropriate unit costs, etc.) with information from actual reclamation projects at abandoned mine sites. The resulting RECLAIM 8.0 estimate should be compared to the actual cost. If these are substantially different, adjustments should then be made to RECLAIM 8.0 from lessons learned from this comparison. 2. Historical cost data should also be used, to the extent possible, to update RECLAIM with actual cost information, without compromising confidentiality. | GNWT/CIRNAC
5 | Internal government costs | RECLAIM does not include the substantial internal costs for CIRNAC and GNWT, for example government employee salaries. This means there is no transparency about what these costs are or what the actual costs are when a mine is abandoned. | Please explain why these costs are not considered when estimating the costs of reclaiming a mine. | GNWT/CIRNAC
6 | Calculating security annually | The proposed RECLAIM Manual update includes a new requirement that "The total financial security for final reclamation required at any time during the life of the mine should be equal to the total outstanding reclamation liability for land and water combined (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period)." This mirrors the Mine Site Reclamation Policy for the NT, which is well over 20 years old. It is not clear how this would be implemented. Is GNWT/CIRNAC anticipating that water licences would have a schedule with annual increases to security? This has not been recent practice. Or is a RECLAIM review anticipated each year? TG is concerned that this would place a big resource demand on all parties. Also, how would the common practice of increasing security at project milestones (e.g., commencement of construction, mining, or milling, percent of pit filled, etc.) fit into this approach? | Clarify how this requirement would be implemented. | GNWT/CIRNAC & Brodie
7 | Human health and ecological risk assessment | The proposed revisions to RECAIM include the cost of a human health and ecological risk assessment (HHERA). The User's Manual notes that this is completed in accordance with federal risk assessment guidance. Modern mines are different than mines abandoned in the past in that they have approved closure objectives and in many cases, approved closure criteria. It is our understanding that, in the past, HHERAs at federal sites have been used to set the standard for cleanup, for example the water or soil contaminant thresholds that must be met. If a modern mine is abandoned during operations and is in compliance with its water licence, land use permit, and other authorizations, unexpected contamination (beyond what is addressed in the approved closure plan) may be less than in the past. Some mines may include an HHERA in their approved closure plan to confirm predicted risks. However, it is not clear what role an HHERA would play at an abandoned mine. We are concerned that use of HHERA's could lower the standard compared to approved closure criteria. Closure criteria have been publicly reviewed, vetted and debated in countless workshops, and represent substantial input from all parties. Closure criteria have been deliberated by the Boards and Board decisions on them have been transparently documented. Ignoring approved closure criteria after abandonment would be inconsistent with the land claim agreements that established the Land and Water Boards. | If an HHERA is part of an approved closure and reclamation plan, then the cost of it should be in RECLAIM. Also, if the GNWT and CIRNAC expect that new risks will emerge after abandonment of mines with modern, approved closure plans, then an HHERA should be a default cost in RECLAIM. However, the RECLAIM Manual should acknowledge that Board-approved closure criteria are the clean-up standard at abandoned mines, unless it is demonstrated that these cannot be achieved or that new criteria are needed for risks that developed after abandonment. An HHERA may play a role in this effort, but HHERA's should not be a replacement for closure objectives and criteria. | AtkinsRéalis & Brodie
8 | Monitoring | The draft RECLAIM Manual says that monitoring will be conducted "with respect to the effectiveness of the mitigative measures, the accuracy of the environmental assessment and any unforeseen environmental impacts". Although true, this statement does not appear to reflect current practice. To our knowledge, all closure plans (and therefore security deposits) in the NT are founded on the MVLWB/AANDC Guidelines for the Closure and Reclamation of Advanced Mineral Exploration and Mine Sites in the Northwest Territories. Therefore, all mines have Board-approved modern closure plans that are based on closure goals, principles, closure objectives and closure criteria. This means closure criteria will dictate monitoring plans and duration. The effectiveness of mitigative measures and the accuracy of the environmental assessment will be reflected in the criteria. If there are unforeseen environmental impacts, closure criteria should be updated. | The RECLAIM Manual should state that monitoring will depend on closure criteria. | Brodie
9 | Relinquishment of liability | The revised Manual states that "Following mine closure, mining companies or their future owners should continue to be responsible for the site , including the remediation of any additional environmental complications which develop." This raises questions about relinquishment of liability. For many years, many parties have been requesting clarity on how liability will be relinquished at mine closure. This is especially important with mines like Diavik approaching the end of operations. This gap creates uncertainty and may inhibit investment in sustainable and responsible mining in the North. | 1. It is understood that additional policy, legislative, or regulatory amendments may be needed to address how and to what extent companies are released from liability once all closure criteria have been met. For example, will companies be required to leave funds for future monitoring, maintenance, or unforeseeable events at the closed mine? These funds may require supporting legislation and/or policy. Even if the GNWT cannot undertake an effort to better address relinquishment before the RECLAIM updates are finalized, the Manual (or another document) should include more information on this topic. This would assist all parties in understanding how GNWT and CIRNAC will approach relinquishment of liability under existing legislation. 2. The GNWT and CIRNAC should immediately begin the effort to outline the conditions and criteria that will allow relinquishment, establish how much money will be required for monitoring, maintenance and unforeseeable events, clarify the extent to which companies will be released from liability, and develop a relinquishment process. This effort will need to involve Indigenous Governments early on. | GNWT/CIRNAC
10 | Performance holdback | The revised Manual states that "If the company carries out progressive reclamation during operations as proposed, such as revegetation of disturbed areas during operations, then the closure cost estimate could be reduced by the associated costs for that component when the company demonstrates that the closure activity has been successfully completed and closure objectives and criteria have been met." It is our understanding that the LWB/GNWT/CIRNAC Guidelines for Closure and Reclamation Cost Estimates for Mines allows for some money to be refunded to companies, even if criteria have not been met. This is allowed so long as a performance holdback is set. The same Guidelines explain how a performance holdback could be set, including three different methods. The first method uses a simple percentage-based approach by mine component, the second method uses RECLAIM, and third uses a "factored risk" approach. | RECLAIM should reflect the CIRNAC/GNWT/LWB Guidelines as they relate to performance holdbacks. Calculations based on the Guidelines should be inserted into RECLAIM. This would include simple calculations supporting Table 1 of the Guidelines (the percentage-based approach). It could also include calculations to support the "factored risk" approach on page 19 of the Guidelines. Support for companies to estimate performance holdbacks will promote a quicker and more efficient security refund process. Although all regulators that use RECLAIM may not require performance holdbacks, those regulators could simply ignore the calculations, or the GNWT could develop them for use in the NT only. While it is beneficial to have only one version of the RECLAIM model across the North, add-ons to reflect jurisdictional differences could help to ensure that RECLAIM is useful everywhere while maintaining a core set of shared calculations and inputs. | GNWT/CIRNAC & Brodie
11 | Documentation of security refunds | Similarly, security refunds for completed progressive reclamation or completed work during active closure is becoming more common and is an important way to promote and reward early closure work. Currently, RECLAIM does not document these refunds, which means there is no record of the original estimate, the refunds given, and what the refund was based on. This may make it difficult to determine refunds during active closure, since it may not be clear what has already been refunded and what is still being held as security. | RECLAIM should document all security refunds. For example, RECLAIM could include a refund summary sheet showing the original estimate, all refunds, and links to documentation supporting the refund (e.g., RECLAIM estimates used to calculate refunds, Board decisions, etc.) | Brodie | This cost estimating tool is not the mechanism for tracking security refunds
12 | Disasters | RECLAIM does not cover the costs of disasters. With numerous mines using the RECLAIM model across Canada's North, there is a significant risk that one or more of these mines will have an environmental disaster during the life of the mine. Currently, disaster clean-up costs would fall entirely to the taxpayer. The recent disaster at the Eagle Mine in Yukon is an excellent demonstration of how the taxpayer will be forced to carry the burden of disaster clean-up. Such costs could easily be in the hundreds of millions of dollars or more. The Mount Polley disaster in 2014 is another example of taxpayers covering significant costs for a mining disaster. Although this may be considered a policy decision that is outside of the scope of RECLAIM, RECLAIM by necessity houses many policy decisions by virtue of the costs it includes or excludes. RECLAIM unavoidably sets policy through its underlying principles and assumptions. Excluding disaster costs is as much a policy decision as including them. | Security for potential future disasters should be required. Since most mines are unlikely to experience a disaster, the amount held by any single mine should only be a fraction of potential disaster clean-up costs. This could be determined based on the risk profile of a project (e.g., potential for acid drainage, geotechnical failures, proximity to highly valued areas, etc.). If disaster costs are not included in RECLAIM, another mechanism is urgently needed to ensure that industry contributes towards a pot of money for future disasters. | GNWT/CIRNAC
13 | Revegetation | Revegetation of a site after closure is an important part of restoring the land, enabling long-term future cultural use, making the site look and feel like the surrounding area, and supporting wildlife. The revegetation unit costs in RECLAIM include seeding and tree planting. Planting cuttings, transplants, or plugs are other examples of revegetation, and likely have different costs than seeding and tree planting. Placement of stockpiled reclamation materials such as topsoil, till, lakebed sediments, etc. should also be included in direct costs for revegetation. | RECLAIM should include the cost for all types of revegetation, including cuttings, plugs, transplants, and spreading stockpiled dirt and soil. | AtkinsRéalis & Brodie | Suggest a User Specified activity and cost in RECLAIM
14 | Traditional Knowledge monitoring | Traditional Knowledge (TK) Monitoring is a critical part of ensuring the closed site meets closure objectives and goals. TK Monitoring is also essential for building community confidence in the closed site to enable long-term future use of the site. (For example, we note that the WLWB requires Diavik to prepare a TK Monitoring Plan). | RECLAIM should include the costs of a Traditional Knowledge Monitoring Program. This would involve regular (e.g., initially annual) site visits from Elders, youth, and staff to evaluate water quality, wildlife safety and movement, vegetation, and more. It is important to note that this is not the same as engagement or regulatory costs. This TK Monitoring Program is similar to other monitoring programs and should be a line item in the Post Closure sheet along with the scientific monitoring programs. | GNWT/CIRNAC | AtkinsRéalis supports this as its something that would like fall on governments books if a site were to be abandoned and this cost can be substantial.
15 | Net Present Value | To date, RECLAIM has included the ability to calculate the net present value. This was used for very long-term costs (e.g., more than 20 years) such as maintenance of constructed wetlands. This reduced the amount of security a company needed to post, without exposing the tax payer to increased risk. This is because the net present value accounted for the fact that money set aside for the future can be invested and will grow. The discount rate used in those calculations was generally an assumed modest growth in investment (e.g., 5%) minus an assumed inflation (e.g., 2%). | Why has the net present value function been removed from the draft RECLAIM? | AtkinsRéalis & Brodie
16 | Interim Care and Maintenance | The RECLAIM model includes an estimate for interim care and maintenance, meaning the period after bankruptcy and abandonment and before active closure begins. The total cost is based on an annual cost (commonly a few million dollars) times the number of years the site is likely to be in interim care and maintenance. The draft RECLAIM 8.0 model includes a default of 3 years of interim care and maintenance. However, the supporting documentation for the RECLAIM updates (Review of Mine Financial Security Estimates and RECLAIM) says "Importantly, the duration of Interim Care and Maintenance is typically limited to two to three years. It is known that government experience has been much different than this, both in scope and duration. This is an obvious category for which government could be under secured". The same document provides some evidence that the actual period could be five to ten years. | The estimated time a site is in interim care should be based on the expected or average duration not the minimum. | GNWT/CIRNAC | AtkinsRéalis agrees that even 3 years is low for ICM. However, we question whether its fair to hold additional securities to account for a transfer from the mine to government. For discussion.
17 | Unit costs - reference table and sources | During the public review, a reference table showing the source for unit cost assumptions was provided. | 1. This reference table is a significant improvement and should be included in the finalized model. It improves transparency and credibility of the unit costs and enables industry and decision-makers to discuss alternative site-specific unit costs. 2. Unit costs adopted from projects in the South (e.g., Sudbury) should be increased if these costs are going to be higher in northern, remote conditions. | AtkinsRéalis
18 | Fish habitat | The Open Pit tab does not explicitly include costs for building fish habitat (littoral zones), even though these may be required in pit lakes or pits that will be reconnected with larger lakes. Some of the activities in the tab may address fish habitat construction (e.g., placing fill), but it is not clear whether all activities required to build littoral zones are in RECLAIM. (Fish habitat construction may be required by the Department of Fisheries and Oceans and/or the Land and Water Boards. In either case the estimate should be included in RECLAIM. If DFO already holds security for this activity, it can be subtracted from the RECLAIM estimate. If it is only required by the Land and Water Boards, then it would remain in the final total.) | RECLAIM should include costs for construction of fish habitat in pits. | GNWT/CIRNAC | Seems out of scope of for the default RECLAIM, but if it has been agreed with DFO costs are not held with them then it should be captured here.
19 | Scientific and Traditional Knowledge research | Typically, the CRP will have several approved reclamation research plans. If a mining company abandons a mine, important reclamation research may not have been carried out. The results of this research will be needed to properly reclaim the site. | RECLAIM should include the costs of scientific and Traditional Knowledge reclamation research. As noted by BCL in their memo, this could result in mines not proposing research, in order to avoid higher security deposits. BCL proposed some alternatives to address this problem (page 18 and 19 of the BCL memo). These could be considered, provided the details of the approaches are publicly reviewed. | GNWT/CIRNAC
20 | Risk communication | The RECLAIM model does not include the costs of risk communication. In order to restore confidence in the mine site area so that closure objectives related to cultural use can be met, a good risk communication plan must be developed and carried out. This may involve public meetings, posters, online tools, social media, radio, newspapers, etc. | RECLAM should include the cost of risk communication. If this cost is lumped in with other costs (e.g., engagement and regulatory compliance costs), this should be mentioned in the User's Manual. This will ensure that the portion of security held for risk communication is not returned until it has been carried out. It will also inform any future disagreements about the percentage of direct costs that should be held for engagement and regulatory compliance. | Brodie | This should be added to User Manual
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Diavik Diamond Mines (2012) Inc. - Sean Sinclair
1 | General | DDMI appreciates the opportunity to take part in this important review process. Since receiving preliminary feedback at the January 23rd, 2025 engagement session, DDMI understands that on February 18th, 2025 and on March 11th, 2025 the RECLAIM v8.0 team uploaded additional information to explain the rationale for some proposed changes to the model. DDMI has not yet been able to review all posted materials. DDMI also understands the RECLAIM v8.0 team will be providing further additional information including but not limited to a jurisdictional scan to support this review process. This complete set of information will inform ongoing collaborative discussion on this proposed update. | Given the complexity and importance of this review process DDMI recommends that the review timeline allows for thorough review and analysis of all information. DDMI is pleased to see the initial extended engagement process proposed by CIRNAC and GNWT and DDMI recommends the next steps for the RECLAIM v8.0 review process are discussed in detail and agreed at the GNWT and CIRNAC in-person workshop the week of May 14th, 2025. | GNWT/CIRNAC
2 | General | An initial review of the proposed changes to the RECLAIM model suggest that its application could have a very significant increase on securities. Current proposed changes are focussed on: 1) increased unit rates, 2) increased indirect costs, 3) increased owners costs, 4) increases regulatory costs, 5) increased mobilization and ICM costs, and 6) a future value calculation without corresponding discounting. | DDMI recommends this review process also consider changes focussed on: 1) incentivizing progressive reclamation, 2) managing the return of security process, 3) managing the security holdback process, 4) consideration of financial mechanisms to provide security as a function of both the liability and asset value, and 5) risk associated with a proponents commitment to orderly closure of the site including its financial and technical capacity to carry it out. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
A Member of the Public - Todd Slack
1 | Model Utility - One Long Comment, Pt. 1 | Obviously an updated reclaim model is in the interests of all parties. Recent years have seen significant increases in costs and an adjustment to better reflect this is a valuable effort to protect taxpayers and ensure that the polluter pays principle is effectively applied. However, the operational modifications of the model are not the only step needed to ensure our territory is protected. A higher-level review focusing on the overall effectiveness of the bonding system should be undertaken using real world closure examples to test the predictive utility of the RECLAIM approach. No model is perfect and the review should be asking if this model meaningfully serves the polluter pays principle. Ground-truthing with real world examples is essential. For example, the MVLWB held approximately $70M in security for Snap Lake (it isn’t particularly easy to know exactly what the security amount was). According to public reporting, as of 2023 De Beers had spent $135M. In that case, it seems that NWT taxpayers – with a government already seeking financial relief - were considerably exposed. Should this be an indicator of a larger trend, the risk is even larger as it seems a widely held belief that industry, already mobilized and familiar with their site, can complete a closure in a more cost effective manner. Yet, the final cost for this site, with a modern security bond, will be more than twice what was held. | Starting with the NWT, publish real world examples of closed sites versus the reclaim estimates | GNWT/CIRNAC
2 | Model Utility - Pt. 2 | Other real world examples available to test the utility of RECLAIM estimates can be found in ongoing Strategic Oil abandonment and closure as well as the 2014 Snowfield property. Based on anecdotal information (as accounts have not been published, despite the expenditure of public monies), for the former, the GNWT has paid tens of millions for the reclamation, while the in the latter, the GNWT paid far in excess of the security held (nevermind the six-figure pre-existing debts that the company owed GNWT). Examples from Nunavut can be researched as well, extending back to Tahera/Jericho which was established with a modern regulatory regime and cost taxpayers more than the security that was held (as opposed to GIANT which is not appropriate as a test case). Yukon examples, over which there are a number of selections (Victoria, Wolverine, Minto) may provide further insight into the effective security estimates and bonding (considering the Yukon government has appropriated $100M for early stages of the Victoria mine they’ve inherited, which was permitted in a modern system). To summarize, before undertaking minor adjustments to the mechanics of the model, the overall utility needs to be verified, confirming fit for purpose. Notwithstanding the financial limitations of GNWT means that they lack the robustness to absorb and large mine failures (noting the daily cost cutting measures that are occurring), more importantly, the citizens of the NWT should have confidence that those overseeing the accessing and sale of our public resources are ensuring that the closure is paid for and completed by those exploiting the resource. | 1) Undertake analysis that looks at closure estimates versus the security held for sites across the NWT, Nunavut, and the Yukon. 2) Search for similar examples in Southern Canada were the structures ensuring the protection of taxpayers and governments are similar to those employed in the north. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Qikiqtani Inuit Association – Conor Goddard
1 | Updated Unit Rates | Understanding unit rates are based on first principles; however further detail on unit rate development and assumptions is required. For Example. Load and haul costs have been split into ‘short haul’ and ‘long haul’; however, there is no detail on what haul distance constitutes a short vs. long haul. To provide greater accuracy in haulage costs, specific unit rates should be calculated based on the actual haul distance between stockpiles and the facility being reclaimed. Dozer equipment rates are classified as either ‘small’ or ‘large’ scale equipment; however, no detail is provided on what is classified as a large dozer. This results in greater uncertainty in which equipment rate should be used when calculating equipment costs. | Paraphrased: Provide additional details on how unit rates were derived. | AtkinsRéalis | Additional details were provided in the follow up memorandum. Short haul and long haul are defined in Table 2: RECLAIM v 8.0 Price Sources, Basis and References. This could be defined in the user manual but a decision was made to keep the details out of the text portion of the manual for ease of future updates. These unit rates could be used as a starting point but should be refined based on actual mine closure and reclamation plans and site conditions. Dozer unit rates were escalated from RECLAIM 7.0. It was assumed large dozers would be utilized given the scale of work. The cost per cubic meter depends on several factors including fuel costs, labour, maintenance and efficiency. On average large dozers (D10/D11 Class) range in price from 1.50 to 3.50 per cubic meter. However, in remote Arctic operations the costs can be 20 to 50% higher. The range for dozing in RECLAIM 8.0 is $1.52/m3 to $6.08/m3
2 | Increased Indirect Percentages | An alternate methodology for calculating indirect costs should be provided. For example, engineering design could be estimated to be 8% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outlined in the reclamation and closure plan. This would allow engineering costs to depend on the level of project definition and the work to be completed. This incentivises further project definition within closure designs earlier in the life of project. | An alternate methodology for calculating indirect costs should be provided. | AtkinsRéalis
3 | Mobilization and Interim Care and Maintenance as Capital Costs | Mobilization / demobilization of equipment is typically considered as an indirect cost when it is being calculated as a percentage of direct costs. As RECLAIM calculates mobilization / demobilization costs directly, Okane supports its inclusion as a direct cost such that contingency can be applied. If mobilization / demobilization costs change to being calculated based on percentage, Okane does not support it being included as a direct cost. | Okane recommends mobilization / demobilization to be calculated via percentage of direct costs, similar to other Canadian jurisdictions. The quantity of equipment, and therefore the cost to mobilization / demobilization equipment, is tied to the reclamation timeframe and schedule. In the event of sudden closure, CIRNAC may implement closure activities on an alternate timeframe than what is outlined within the closure plan. | AtkinsRéalis & Brodie
4 | Owners Representative | Okane supports the costing of an Owners Representative within closure cost estimates. However, Okane is interested in the percentage used for determining this cost. In comparison, the updated project management cost of the entire reclamation phase is estimated to be 10% and includes costs for project coordination, accounting and project control, quality assurance/quality control and oversight, change orders and as-built reports. Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | AtkinsRéalis
5 | HHERA and Finalize CRP | An alternate methodology for calculating HHERA and CRP costs should be provided. For example, finalizing the CRP could be estimated to be 4% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outline in the reclamation and closure plan. This would allow the costs for finalizing the CRP depending on the level of project definition and the work to be completed. | An alternate methodology for calculating HHERA and CRP costs should be provided. | AtkinsRéalis & Brodie
6 | Future Value Calculation | Okane supports the consideration of future valuation with respect to years associated with ICM; however, does not agree on how it is being represented within RECLAIM with respect to post closure activities and the removal of net present value calculations as outlined in the virtual engagement session. While inflation can add considerable costs to reclamation, solely accounting for inflation does not capture the true costs and value of money. | Okane would recommend included inflation within a real discount rate to be used within a net present value analysis | AtkinsRéalis
7 | Detail for Unit Rates | Although RECLAIM provides a list of potential closure activities for each facility, it lacks the level of detail required to understand how these activities have been costed and relies strictly on unit rates and lump sum estimates. | To improve transparency and accuracy withing closure cost estimates, more inputs should be provided to show how that activity is being costed. Specifically, within post-closure activities such as monitoring the current RECLAIM model only provides an annual lump sum input for a monitoring activity. To improve transparency, it should provide more detail such as sampling/monitoring frequencies, number of sampling locations, analytic costs, reporting, etc. | AtkinsRéalis
8 | Post-closure monitoring and maintenance contingency | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. Post-closure maintenance activities are not excluded from having uncertainty and a contingency should be applied within this cost category. Specifically, activities such as long-term water treatment which is tied closely to geochemistry which typically carries large uncertainty. | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. | GNWT/CIRNAC
9 | Timeframe and Post-Closure Activities | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. There is potential for post-closure monitoring and maintenance activities to extend into perpetuity, such as DSIs, DSRs, and water treatment. What is the expected period of which these activities should be assessed over. | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. | GNWT/CIRNAC
10 | Discount Rates | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. Okane would welcome guidance on what ‘real’ discount rate should be applied to post-closure activities. | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Baffinland Iron Mines Corporation – Lou Kamermans
1 | Procedural Fairness | Due to the short timeline to review the proposed changes, Baffinland has not had a full opportunity to conduct an in-depth review of the technical information supporting the RECLAIM 8.0 update. Respectfully, the timeline that was provided to industry for this initial round of comments is not adequate given the importance of RECLAIM to the Nunavut mining industry and the very serious potential impacts that have already been identified through the minimal consultation that has occurred to date. We are concerned that RECLAIM 8.0 could be advanced further despite these procedural deficiencies and the serious concerns expressed by industry to date. Given the significance of these changes to the mining industry in Nunavut and the Northwest Territories, and the potential direct impacts that it will have on Baffinland, we are providing initial high-level comments and recommendations below. In providing these comments, we reserve the right to provide further and more detailed comments, following further industry engagement and once better information is shared by CIRNAC and GNWT. | A. CIRNAC should engage stakeholders and Inuit organizations in a meaningful consultation process before finalizing the changes. Respectfully, the process described in the letter to the Chamber of March 18, 2025 does not achieve this standard. B. Third public review and comment period should only occur after CIRNAC has produced a version of RECLAIM 8.0 revised based on comments. A further workshop may be necessary to review this revised RECLAIM 8.0 before any final comment period. C. The overall timelines suggested in the process letter of March 18 are inadequate. For example, with respect to the suggested expected date of implementation of RECLAIM 8.0 [August 1, 2025], it is apparent that there would be no meaningful opportunity for feedback provided during the third round of public feedback (due July 16, 2025). D. CIRNAC should advise how they intend to engage with NTI and RIOs on impacts to their rights resulting from this policy change, with associated timelines, before RECLAIM 8.0 is adopted. E. CIRNAC should advise how they intend to engage with GN resulting on impacts relating to devolution resulting from this policy change (including spinoff economic effects), with associated timelines, before RECLAIM 8.0 is adopted. | GNWT/CIRNAC | A-E: CIRNAC and GNWT to discuss.
2 | Economic impact of RECLAIM 8.0 | As Canada is trying to promote economic development and critical minerals development, which includes high grade iron ore, the additional security concepts and requirements proposed by CIRNAC in RECLAIM 8.0 will only make it harder to develop and maintain what we have. The changes proposed by CIRNAC will negatively impact mine financing and development by increasing security requirements and financial obligations without an adequate and corresponding industry consultation process. Any potential lack of engagement with industry and designated Inuit organizations undermines the legitimacy of these updates as a policy framework. Furthermore, as highlighted above, the RECLAIM 8.0 approach appears to disincentive projects with longer lifespans and greater water liability marks, which is in direct opposition to existing territorial and federal economic development policies and mandates. Without proper consultation, these changes will create uncertainty and deter investment in northern mining projects. Baffinland recommends that a comprehensive economic impact analysis be conducted to assess the implications of RECLAIM 8.0 on northern mining investment and development. Given the closure of major diamond mines in the North-West Territories and the absence of advanced stage projects in both the North-West Territories and Nunavut, apart from government funded infrastructure, the economic consequences of these changes should be thoroughly evaluated before implementation. An industry-commissioned economist could provide valuable insight into these potential impacts, and the results should be available before major policy decisions are finalized. | A. CIRNAC should conduct a comprehensive economic impact analysis to assess how RECLAIM 8.0 will affect mining investment and development in Nunavut. Industry and other stakeholders should be engaged on this question specifically as part of this analysis. B. As part of this analysis, CIRNAC should produce a third party expert prepared report on the potential economic impact of the proposed cost escalations on the mining industry in Nunavut. RECLAIM 8.0 has been provided without assessment of the negative economic impacts that could result from the significant policy change RECLAIM 8.0 represents. The independent economist selected for this task should have experience representing industry and have Northern expertise. | GNWT/CIRNAC | A: Agreed – third part economist could provide valuable insight as to the economic implication for mineral development in the NWT and Nunavut. B: As above.
3 | Rates and Cost Estimates | The proposed updates to RECLAIM 8.0 introduce significant cost increases that could have long-term economic implications for mining projects in the North. These cost escalations require careful scrutiny to ensure they align with real-world reclamation expenditures and do not hinder responsible resource development. | A. Review and adjust cost estimates to ensure they are reasonable, justified, and do not include duplication in indirect costs. B. Develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. | AtkinsRéalis & Brodie | A: There was every attempt to ensure costs were reasonable, justified and did not include duplication. We will review the rates again to ensure they meet these criteria. B: We do not suggest that CIRNAC develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. It should be clear in RECLAIM User Manual as to why the default percentages are chosen and the mining company should propose the appropriate rate for their own mines and current stage within the lifecycle.
4 | Rates and Cost Estimates | The unit rates proposed for RECLAIM 8.0 are substantially higher than those in RECLAIM 7.0, often reflecting worst-case scenarios without adequate justification, despite the additional materials provided following the January Workshop in Vancouver. While CIRNAC states that proponents may propose alternative rates, industry experience suggests that the highest rates are typically applied in practice, unless a clear security policy is in place (see Section 3 – Security Policy). First principles derivations for these rates has not been provided (as is typical when justifying modifying rates in a security estimate) and the references are highly generalized, which hinders review, especially in light of the limited review timeline. | C. CIRNAC and GNWT must provide more detailed first principles derivations for rates, at a level that would be expected of a proponent justifying its own rates in an estimate. Specific references are required and generalized references provided to date are not adequate to provide expert feedback and advice. | AtkinsRéalis | C: CIRNAC provided links and references to the majority of the sources for increased rates applicable to remote mine working in NWT and Nunavut. CIRNAC used First Principles to develop rates for soil and rock movement and provided the factors considered in the costs estimating tool. Its is up to the mining company to counter these rates and provide rationale as why a different unit rates should be proposed (high or lower).
5 | Rates and Cost Estimates | The increase in indirect percentages represents an overall 23% increase in costs, and several of these items overlap, resulting in duplication of costs (see Table 1). For example the increase in contingency seems to be duplicated by an increase in project management, engagement and regulatory compliance, and owner’s representative costs. These increases do not appear to be justified through a detailed cost analysis. | D. Justification must be provided by CIRNAC to address the duplication described in the comment, and a detailed cost analysis must be provided to justify these statements | AtkinsRéalis | D: AR to investigate
6 | Rates and Cost Estimates | Upon initial review, the observations regarding indirect costs provided in the ”Review of Mine Financial Security Estimates and RECLAIM” (Brodie, 2020) do not align with the proposed Reclaim 8.0 Indirect costing changes. For example, the report states “BCL recommends that the default percentage for Project Management be increased based upon CIRNAC’s experience. Whereas the default percentage for Engineering should be maintained but with the RECLAIM User Manual revised to be even more explicit as to what is and is not assumed to be covered in this amount.: Baffinland notes that the proposed Reclaim 8.0 changes include an increase in project management indirect percentages (an increase from 5% to 8%), an additional owners engineer indirect (an increase of 8%) and an increase in engineering design indirects (5% to 8%). This appears to be in contradiction to the recommendations of the review report. | E. CIRNAC should align observations re indirect costs in RECLAIM 8.0 with Brodie, 2020 (subject to adjustment based on further submissions in future on each of these categories) | AtkinsRéalis & Brodie | E: Default increases in percentage of indirects were increased from the Brody recommendations based on consultation with our consultants cost estimators and based on incurred cost at other orphaned and abandoned mine across Canada.
7 | Rates and Cost Estimates | Within the proposed update, contingency has been increased to a maximum of 25%, which the Reclaim review report (Brodie, 2020) describes as appropriate for “Very basic engineering only and costs based upon typical unit costs”. This guidance is not provided in the proposed RECLAIM 8.0 documentation. As Baffinland has noted above, in its experience when Reclaim is applied by reviewers the highest level of contingency/indirect is used as a manner of course, as there is little specific guidance provided how to select an appropriate contingency/indirect within the provided model. For example, although Baffinland’s closure plan has advanced to the ICRP stage and has had significant engineering completed, a 20% contingency has been consistently applied by CIRNAC reviewers. Without specific risk based guidance regarding how to select indirect percentages based on project stage and level of engineering completed, Reclaim 8.0 could be used in an overconservative manner due to the lack of specific guidance, which could have a significant impact on Baffinland and other resource development projects in Nunavut. | F. 25% is not an appropriate contingency percentage for most advanced projects with current RECLAIM 8.0 guidance there is a risk this value is applied broadly, like 20% contingency is now. Adjust contingency percentage to reflect a range of risk based standards adjustable based on criteria, such as reductions below 20% where projects already have significant completion of engineering | AtkinsRéalis | F: CIRNAC could develop a matrix to define
8 | Rates and Cost Estimates | The future value calculation for water treatment and other long-term liabilities places a significant financial burden on mining companies, particularly in the absence of strong offsetting mechanisms, such as security discounting based on known reserves—an approach used in other jurisdictions like British Columbia (BC) and Quebec (Government of BC, 2022; Government of Quebec, 2017). For instance, in 2022, the BC Ministry of Energy, Mines and Low Carbon Innovation introduced the Major Mines Reclamation Security Policy, which considers a mine’s stage of development and promotes long-term operations by applying different security rates at various points in a mine’s lifespan based on default risk. The policy states that “mines that have been operating for more than five years, and that have economically viable reserves for at least the next ten years at the permitted production rate, will be eligible to secure up to 25% of the reclamation liability against a portion of the reserve value.” (Government of BC, 2022). Adopting a similar approach in Nunavut provide much-needed financial flexibility for long-term mining projects like Baffinland, reducing upfront security costs while maintaining strong environmental protection measures. This would enhance the economic viability of long-life mines, encourage continued investment, and support sustainable resource development in the region. Tying financial security to the mine life cycle would help mining companies spread out financial security payments over the mine’s life, which would increase investor confidence while supporting responsible mining development that considers the projected mine life. | G.RECLAIM 8.0 should be revised to provide a clear mechanism for discounting security based on reserves, similar to those adopted in other jurisdictions such as BC and Quebec. | GNWT/CIRNAC | The BC “interim” policy is based on years of operations and mineral reserves. Proven final securities through the Exploration Incentive. Shifting security to mineral reserves could be an issue as Canada is not in the mining business and if a site were abandoned, they would need to reopen a mine to get access to the money required to close it. The BC policy mentions that mines with proven reserves are attractive to other operators if a mine were to go bankrupt. STILL SEEMS RISKY TO ME, TULSEQUAH, MINTO, ETC. “This policy seeks to ensure that permittees for major mines pay the full cost of environmental cleanup and reclamation for their mine. New mines and any existing mines (whether in operation, in care & maintenance or closed) having less than five years of remaining mineral reserves will be required to post full reclamation security equal to the company’s reclamation liability on the mine site. A partial exploration incentive security will be available to mines that have invested in sufficient exploration to demonstrate at least five years of remaining reserves. The policy seeks to ensure that new mines are fully bonded moving forward and seeks to reduce the differential between reclamation liabilities and reclamation securities for existing mines.” 0 to 5 years: (100% posted cash security) > 5 years: (75% posted cash security and 25% against the mineral reserves) > 5 years but less than 10 years (85% posted cash security and 15% against the mineral reserves) No more than 10% of the value of the reserve used reclamation security Discount rate of 8% applied to the mineral reserves Default contingency set to 15% but higher may be required depending on the level of risk or uncertainty. Lower may be proposed by the permittee
9 | Update of 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) is required. | Before publishing a RECLAIM 8.0 model, Baffinland recommends that the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) be revised to reflect current conditions in the mining industry. There has been no suggestion that current Nunavut production mines are undersecured – as an example, Baffinland’s security is reviewed annually in a comprehensive process. The investment decision for Mary River was made on the suite of government and Inuit approvals in place, including RECLAIM 7.0. | A. Before RECLAIM 8.0 is adopted for Nunavut projects, the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) should be updated to reflect current conditions in the mining industry and best practices across Canada and globally. B. Current approved Nunavut projects should follow RECLAIM 7.0, unless the proponent consents to application of RECLAIM 8.0. | GNWT/CIRNAC | A: TBD B: Current mine securities are set. At the time of renewal, RECLAIM v 8.0 will be in place and new indirects and calculations of contingencies and future costs will be negotiated.
10 | Misc. | No Comment | A. Only a simple markup of the updates to the User Manual has been provided. A detailed markup is requested as a simple markup does not clearly present the changes. | Brodie
11 | Misc. | No Comment | B. With reference to the “proprietary civil rate tool” referenced at p. 20 of the User Manual for RECLAIM 8.0, if a tool is being adopted in a government policy, it must be made publicly available. If it is not publicly available, it should not be included in the policy. This is a matter of fairness and transparency. | AtkinsRéalis | B: AtkinsRéalis suggests removal “proprietary” replace with “construction cost estimating”
12 | Misc. | No Comment | C. Costs relating to the Crown’s legal obligation to consult (which would be incurred in any event, whether the Crown steps in as director of reclamation or participates in review of closure plans led by a proponent) should not be included in RECLAIM 8.0, as this is a fixed government cost, not a cost of reclamation. The suggested 3% includes items that are fixed government obligations that do not belong in a reclamation estimate. | GNWT/CIRNAC | C: The 3% Owners Costs are meant to capture expenses required to complete consultation during the ICM and Post Closure Phase that typically are budgeted for in day to day government spending (i.e., flights, vehicle rentals, accommodations, per diems to northern and remote communities to discuss the remediation, reclamation and closure plan. Costs of permitting and other third party costs related to government activities would be captured here.
13 | Misc. | No Comment | D. How is RECLAIM 8.0 accounting for Nunavut devolution relating to lands and waters from CIRNAC to the GN? | GNWT/CIRNAC | D: CIRNAC to elaborate.
14 | Misc. | No Comment | E. RECLAIM 8.0 should recognize reasonable salvage value where justified by the proponents estimate. The current position is unreasonably conservative and results in over bonding in many circumstances. This statement should be revised accordingly “GNWT/CIRNAC does not recognize salvage value because of the problems associated with creditors rights, sale of equipment and uncertainty as to the actual value at the time of insolvency”. | GNWT/CIRNAC | E: Revised text looks appropriate to AtkinsRéalis.
15 | Misc. | No Comment | F. Citation for precautionary principle definition should be to the CEPA not to the CEPA guide. | Brodie | F: Revision seems appropriate to AtkinsRéalis
16 | Misc. | No Comment | G. Progressive reclamation should be credited in mine reclamation costs. This aligns with the following statement from the 2002 Nunavut Reclamation Policy – “Mining operators should be credited for approved progressive reclamation, and the value of financial security required should be adjusted in a timely fashion” | GNWT/CIRNAC | G: CIRNAC recognizes this statement and has worked with mining companies to reduce securities based on progressive reclamation activities and will continue to do so on a case by case basis.
17 | Misc. | No Comment | H. RECLAIM 8.0 adds an additional owners representative indirect cost, which is in addition to the proposed project management indirect cost. The owners representative indirect has been insufficiently justifying in the provided accompanying documentation, and it should be noted that an owners representative is not required during proponent lead reclamation. This overly conservative indirect requirement could have significant implicants on mine financing and development. | AtkinsRéalis | H: CIRNAC and GNWT would not lead the development and finalization of the Closure and Reclamation Plan, nor would they oversee the construction or monitoring and maintenance activities. It has been shown that this is not the case as seen at Faro and Giant mines. CIRNAC and GNWT would hire an engineering firm to provide Owners Representative services (technical resources to government) to manage and oversee another engineering firm (e.g. a design-build team) who would be contracted to complete the closure, reclamation and long term monitoring activities.
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
B2G Back River Corp. Nunavut – Merle Keefe
1 | Review Data Extension | B2Gold Nunavut is presently unable to meet the requested date for the submission of comments and therefore supports a recent request made by the NWT& Nunavut Chamber of Mines (Chamber) to extend the comment period deadline. B2Gold Nunavut also supports the request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM. The Chamber submission is attached to this letter. | Request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
NWT & Nunavut, Chamber of Mines – Karen Costello
1 | Review Data Extension | The Chamber respectfully requests a 4-month review period (including potential options for a workshop) to fulfill the first step in the review process. We would also ask for access to the Review of Mine Financial Security Estimates dated March 2020 at your earliest convenience. | Four month date extension for review comments | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Agnico Eagle Mines Limited – Jamie Quesnel
1 | Review Data Extension | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. As was apparent at the January 23, 2025 Engagement and Feedback Session, and echoed again in the NWT & Nunavut Chamber of Mines letter, there were many uncertainties and risks identified by Industry, including time to complete a detailed and adequate review of all the proposed changes under RECLAIM 8.0. As outlined in Section 2 of this letter, Agnico Eagle has undertook an initial review and provided some comments and recommendations; however, a detailed fulsome review has not been executed at this stage. | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. | GNWT/CIRNAC
2 | Documents received | This is a preliminary review due to the short timeline | More time is required to complete a comprehensive review of the documentation provided | GNWT/CIRNAC
3 | Reclamation Policy | As the reason is unknown why the Reclaim V8 was changed, plus we have an undefined process we are following, and this creates uncerntainity. | Develop a plocy update with a defined process of consulation, etc., and define the triggers for a material change. | GNWT/CIRNAC
4 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" and "'Work week for earthwork (rock, soil, riprap excavation, hauling to waste dump is 7 days a week x 10 hours per day = 70 hours per week" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No overnight work is considered. | Unit rates should be developed assuming 24 hour operation where practical. SUPPORTING RATIONALE: Operating Mines, particularly in the North, require round the clock operation for maximum equipment utilization and operation effectiveness. Haul trucks engines must be active around the clock to ensure operability and neglecting night shift utilization ignores real operating expenditures. | AtkinsRéalis
5 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No night work is considered. | Operating Mines, particularly in the North require round the clock operation for maximum equipment utilization and operation effectiveness. SUPPORTING RATIONALE: Neglecting potential night shift work unnecessarily extends project schedule and therefore unnecessarily inflates overall project costs. | AtkinsRéalis
6 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'The labour cost included in the unit rates considered the following cost: … - Indirect labour" | The battery limits for "indirect labour" included in unit rate development is not adequately defined. RECLAIM includes indirect activities such as Project Management and Engineering Design applied as a general percentage of direct costs. | Clarify what indirect labour is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | AtkinsRéalis
7 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "The labour cost included in the unit rates considered the following cost: … - Site supervision and administration" | The labour cost included in the unit rates considered the following cost: Site supervision and administration | Clarify what site supervision and administration is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.). SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. Project management, Health and Safety Monitoring & QC as an indirect cost is applied as a blanket % to all costs. | AtkinsRéalis
8 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "Exclusion ...- Project indirect cost" | The battery limits for "indirect cost" included in unit rate development is not adequately defined. | Clarify what indirect cost is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | AtkinsRéalis
9 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 5 Exclusions LINE: "- First Fills" | First fills are excluded from unit cost build up. | Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup that excludes first fills. SUPPORTING RATIONALE: Consistent application inclusions and exclusions are important for usability of RECLAIM. Suggest using one data source for all unit rate buildup. | AtkinsRéalis
10 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- Freight for the bulk materials such as granular, concrete and HDPE pipes are included with the unit rates" | Proposed unit rate buildup includes freight for bulk materials. This necessitates site specific unit rate for all bulk materials as freight costs can very substantially between sites. There is already a section within the RECALIM mobilization tab to capture freight cost. | Bulk material default unit rates should exclude freight. Freight for materials should be included separately based on a site specific unit cost for material mobilization, captured in the RECLAIM Mobilization tab. | AtkinsRéalis
11 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- It is assumed there is no batch plant required. All concrete will be delivered to site to use" | The clarification that no batch plant will be required constricts operational planning. In some cases it is more cost effective to commission a batch plant and ship bulk concrete than to use premix product. | Freight of premix concrete products is not always practical for northern projects based on mobilization constraints and the use of a batch plant should be considered when operationally and financially advantageous. | AtkinsRéalis
12 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects LINE: Mobilization/Demobilization 6.0% | Contractor indirects, specifically mobilization/demobilization, are shown as separate adders to the base rates for equipment and labour direct costs. RECLAIM considers mobilization and demobilization costs separately from operating unit rates as part of the Mobilization tab. | Exclude mobilization/demobilization cost from unit rate development. Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup and if mobilization/demobilization cost has been accounted for with respect to the overall RECLAIM workbook. | AtkinsRéalis
13 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects | A variety of sources for equipment operating costs as well as labour costs are indicated as being used as a basis for unit rate calculations. There are substantial differences in the factors included in each of the sources for equipment operating costs. For example, BC Blue Book and Alberta Equipment Rental Rates Guide are used interchangeably in FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Rates but BC Blue Book equipment operating rates do not explicitly include contractor overhead and profit whereas Alberta Equipment Rental Rates Guide does. The provided unit rate example in FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects, if using Alberta Equipment Rental Rates Guide for equipment or manpower hourly rates is applying an additional 12.50% Mark-up & Profit on a rate that already includes Mark-up & Profit. | Default unit rates provided in RECLAIM 8 should use a consistent source reference for all equipment and manpower hourly rates with clearly defined buildup of direct and indirect components. | AtkinsRéalis
14 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Buildings - Remove" COST CODE: BRW, BRC, BRS1, BRS2 | Cost Codes: BRW, BRC, BRS1, BRS2 have no default HIGH unit rate provided as part of RECLAIM 8.0 example. RECLAIM 7.0 provided a HIGH unit rate for these cost codes resulting in a 1:1 comparison between RECLAIM 8.0 default unit costs and RECLAIM 7.0 unit costs. | RECLAIM 8.0 should include a default HIGH unit rate for all default cost codes that have a defined HIGH unit rate in RECLAIM 7.0 | AtkinsRéalis
15 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB1, RB2 | The detail defining what activity COST CODES RB1 and RB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines RB1 as "drill/blast/load/short haul" RECLAIM 8.0 defines RB1 as "load/haul/place"RECLAIM 7.0 defines RB2 as "drill/blast/load/long haul" RECLAIM 8.0 defines RB2 as "RB1 + spread and compact"This respondent uses COST CODE RB2 to represent activities requiring "drill/blast/load/long haul" but NOT "spread and compact" To accommodate the change in COST CODE detail from RECLAIM 7.0 to RECLAIM 8.0 >$10 million of activities on a single site would need to be recoded to avoid implying "spread and compact" is required for these activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
16 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB3, RB4 | COST CODE: RB3 and RB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RB3 DETAIL: "RB1 + spread and compact" is the same as RECLAIM 8.0 CODE RB2 DETAIL: "RB1 + spread and compact"RECLAIM 7.0 COST CODE RB4 DETAIL: "RB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RB3 and RB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
17 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - High Spec (i.e. Rip Rap, Screened)" COST CODE: RC3, RC4 | COST CODE: RC3 and RC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RC3 DETAIL: "RC1 + spread and compact" is the same as RECLAIM 8.0 CODE RC2 DETAIL: "RC1 + spread and compact"RECLAIM 7.0 COST CODE RC4 DETAIL: "RC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RC3 and RC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
18 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB1, SB2 | The detail defining what activity COST CODES SB1 and SB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SB1 as "excavate/load/short haul" RECLAIM 8.0 defines SB1 as "excavate/load/haul/place"RECLAIM 7.0 defines SB2 as "excavate/load/long haul" RECLAIM 8.0 defines SB2 as "SB1 + spread and compact"This respondent uses COST CODE SB2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
19 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB3, SB4 | COST CODE: SB3 and SB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SB3 DETAIL: "SB1 + spread and compact" is the same as RECLAIM 8.0 CODE SB2 DETAIL: "SB1 + spread and compact"RECLAIM 7.0 COST CODE SB4 DETAIL: "SB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SB3 and SB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. This respondent would need to recode >$35 million of activities at one site. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
20 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC1, SC2 | The detail defining what activity COST CODES SC1 and SC2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SC1 as "excavate/load/short haul" RECLAIM 8.0 defines SC1 as "excavate/load/haul/place"RECLAIM 7.0 defines SC2 as "excavate/load/long haul" RECLAIM 8.0 defines SC2 as "SC1 + spread and compact"This respondent uses COST CODE SC2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
21 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC3, SC4 | COST CODE: SC3 and SC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SC3 DETAIL: "SC1 + spread and compact" is the same as RECLAIM 8.0 CODE SC2 DETAIL: "SC1 + spread and compact"RECLAIM 7.0 COST CODE SC4 DETAIL: "SC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SC3 and SC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | AtkinsRéalis
22 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, small (<6in dia.)" COST CODE: PSS, PSI | COST CODES: PSS and PSI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes. | AtkinsRéalis
23 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, large (>6in dia.)" COST CODE: PPLR, PLS, PLI | COST CODES: PLR, PLS and PLI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes | AtkinsRéalis
24 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: PS | Pumps, Pump shipping COST CODE: PS unit changed from RECLAIM 7.0 lump sum (each) to, RECLAIM 8.0 percentage (%) of pump cost.Existing RECLAIM 7.0 projects have taken to account shipping of pumps, by lump sum (each) as part of the mobilization calculation. Shipping cost is generally site specific and existing calculations should remain valid. Shipping cost as a % of pump capital cost could be a useful default unit rate for establishing projects. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND adding new cost code for shipping as a % of capital cost | AtkinsRéalis
25 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: POC | Pumps, Pump operating cost COST CODE: POC unit changed from RECLAIM 7.0 m3 (volume pumped) to, RECLAIM 8.0 kw-h (power cost).Pump operating cost is certainly predicated on site power cost but the relationship between pumped volume and power draw is based on site specific conditions. Volume of water is the unit of measure for reclamation activities and using a second unit of measure to determine cost would introduce additional complexity. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND pump operation based on cost per volume pumped. | AtkinsRéalis
26 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Human Health and Ecological Risk Assessment (% Closure Costs) | Human Health and Ecological Risk Assessment (% Closure Costs): Cost to develop a site specific HHERA is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for HHERA related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
27 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Finalize Closure and Reclamation Plan (% Closure Costs) | Finalize Closure and Reclamation Plan (% Closure Costs): Cost to develop Final Closure and Reclamation plan is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Finalize Closure and Reclamation Plan related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
28 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engineering Design | Indirect Costs: Engineering Design : Cost for engineering design is warranted and should consider work already completed to capture the real effort and cost to achieve closure | Implement a sliding scale for Engineering Design Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
29 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Project Management | Indirect Costs: Project Management : Cost for project management is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Project Management Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
30 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Health and Safety Plans/Monitoring & QC | Indirect Costs: Health and Safety Plans/Monitoring & QC : Cost for Health and Safety Plans/Monitoring & QC is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale to account for project maturity and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
31 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Bonding / Insurance | Indirect Costs: Bonding / Insurance : Cost for Bonding and Insurance is warranted and should consider work already completed to capture the real effort and cost to achieve closure. This cost should also account for the reliability and ease of use of the financial assurance instrument used by the mine owner as well as the financial reliability of the mine owner, represented by third party credit rating. Typical operating project bonding and insurance costs for third parties are historically <1% total project cost. | Implement a sliding scale to account for owner reliability, project maturity, and the cost and effort required to achieve closure. Established mining companies at low risk of becoming insolvent should have their efforts to achieve closure recognized. | GNWT/CIRNAC | For group discussion
32 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engagement and Regulatory Compliance | Indirect Costs: engagement and regulatory compliance cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations, including through regulatory compliance and engagement, should not be made to bear burden of costs outside their influence. | GNWT/CIRNAC
33 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Contingency | Indirect Costs: Contingency : Cost for contingency is warranted and should consider work already completed to capture the real effort and cost to achieve closure. There is currently a sliding scale for contingency, codified in the RECALIM 7.0 user manual, but the benchmarks set out are not representative of the level of contingency requested by CIRNAC and recommended by Brodie Consulting. The RECLAIM 8.0 contingency scale, based on AACE International Recommended Practice No. 10S- 90 representative of current industry practice and can be augmented with other factors such as owner financial strength, path to closure, and financial instrument of security. | Contingency sliding scale should reflect project lifecycle maturity, the financial strength of the owner, the financial instrument of closure security and the cost and effort required to achieve closure. | GNWT/CIRNAC | For group discussion
34 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Owners Representative | Indirect Costs: Owners representative cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations should not be made to bear burden of costs outside their influence. This line item addition represents a significant burden to all mining companies and it may impact the viability of future developments. | GNWT/CIRNAC
35 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Site Specific Future Value Inputs | FILE: reclaim 8.0 User Manual_Working Copy.pdf affirms that the determination of future costs must include all parameters including the Net Present Value of those costs. The Site Specific Future Value Inputs projects a future cost without including for the future value of the security | If RECLAIM is to project factors such as inflation it should also account for the present value of money at the time of projection. A prescribed NPV calculation with appropriate discount rate should be applied alongside all Post-Closure costs and future projections. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Kivalliq Inuit Association – Luis Manzo
1 | General comment | The Kivalliq Inuit Association (KivIA), as the responsible DOI, through Security Management Agreement holds 50% of the financial security estimates for Meadowbank, Meliadine and Whale Tail mines Canada holds the other 50%. Therefore, any changes to the RECLAIM financial model must be reviewed and agreed by KivIA. | Paraphrased: Table 1 provides the comments and recommendations from KivIA and are summarized in comments 2 to 20 below. Table 2 provides operational costs for drill/blast/load/haul/spread/compact unit rates. Assumption is we should consider these rates. Table 3 includes an example comparison of the increased costs based on the new percentages for indirects. It is recommended that any changes to the RECLAIM financial model must be reviewed and agreed by KivIA | GNWT/CIRNAC
2 | General comment | The timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site needs to be explained. | The KivIA requests that CIRNAC explain the timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site. | GNWT/CIRNAC
3 | General comment | Project or mine’s asset value to a company. Will CIRNAC consider the asset value of an advanced project or mine as part of the initial financial security. | The KivIA requests that CIRNAC explain if there would be consideration of the asset value of an advanced project or mine as part of the initial financial security. | GNWT/CIRNAC
4 | General comment | What is the procedure for the return of financial security to the proponent? | The KivIA requests that CIRNAC explain the procedure for returning financial security to the proponent. | GNWT/CIRNAC
5 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | The changes made to the direct costs need to reflect each individual project/mine site. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that direct costs will need to be project specific versus “one cost fits all” with a range of costs being a more appropriate approach. | AtkinsRéalis
6 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References -Excavation costs. | Excavation costs for load/haul/place for excavating and spreading rock and soil show significant increases from RECLAIM 7.0 to RECLAIM 8.0. Using known operating costs from a northern gold mine calculated in RECLAIM 7.0 and comparing these costs to the proposed rates in RECLAIM 8.0 the costs for load/haul/place for excavating and spreading rock and soil have increased by 50% to 430% (see Table 2 attached). In addition, the RECLAIM 7.0 costs included drill and blast which the RECLAIM 8.0 costs do not. However, without any detail provided on how the Civil Est. Tool calculates the RECLAIM 8.0 costs it is not possible to evaluate these cost differences. | The KivIA requests that CIRNAC and their engineering consultants provide the detail on how the Civil Est. Tool calculates the RECALIM 8.0 excavation costs. | AtkinsRéalis
7 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | Will an inflation factor be used. Will this factor be applied to direct costs? Or to Indirect costs? Will an inflation factor be used on the direct costs? Or indirect costs? Over what time period will the inflation facto be reviewed. | The KivIA requests that CIRNAC and their engineering consultants respond to their proposed plan for an inflation factor. | AtkinsRéalis
8 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Indirect Costs | The changes made to the percentages used for Indirect Costs from RECLAIM 7.0 (31%) to RECLAIM 8.0 (58%). Using the $100M Direct Cost example in Table 2 the changes made to the percentages would result in an 87% increase to the InDirect Costs from $31M to $58M. | A cost increase of 87% is significant and will have a negative impact on the business model used to develop currently operating advanced projects and mines. In addition, a cost increase of this magnitude will have a negative impact on new investment “North of 60”. The KivIA’s comments on the recommended changes make up the remainer of this table (Table 1). | GNWT/CIRNAC
9 | RECLAIM 8.0 – User Manual – Indirect Costs – Engineering Design; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engineering Design | The percentage change made to the Engineering Design component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (8%). This should be a range from 5% to 8% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
10 | RECLAIM 8.0 – User Manual – Indirect Costs – Project Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Project Management | The percentage change made to the Project Management component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (10%). This should be a range from 5% to 10% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
11 | RECLAIM 8.0 – User Manual – Indirect Costs – Engagement and Regulatory Compliance; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engagement and Regulatory Compliance | The Engagement and Regulatory Compliance component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (3%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2)the cost information that was used to determined that this new category would cost $3M per every $100M of financial security. | AtkinsRéalis
12 | RECLAIM 8.0 – User Manual – Indirect Costs – Contingency Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Contingency | The percentage change made to the Contingency component of Indirect Costs from RECLAIM 7.0 (20%) to RECLAIM 8.0 (25%). This should be a range from 15% to 25% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | AtkinsRéalis
13 | RECLAIM 8.0 – User Manual – Indirect Costs – Owners Representative; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Owners Representative | The Owners Representative component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (8%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2) the cost information that was used to determined that this new category would cost $8M per every $100M of financial security. | AtkinsRéalis
14 | RECLAIM 8.0 – User Manual – Future Value calculations: Summary Report: Proposed Changes to RECLAIM Version 8.0 – Future Value calculations | It states that the Future Value calculations will capture Closure and post-Closure activities and that a default inflation rate of 3% will be applied. Will there be an annual or a multi-year review of the inflation rate in order to adjust the financial security. | The KivIA requests that CIRNAC and their engineering consultants provide the timeline over which the inflation rate will be reviewed (ie. Annually review? Multi-year review?). | GNWT/CIRNAC
15 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet; Table 1 – Basis of Unit Rates Development | It states that “The below references are used in unit rates development -Published data sources”. All the published data sources used are from southern Canada. Are there any “North of 60” data sources? Are there any permafrost related data sources? Also, are these labour and contractor rates union or non-union rates? | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) northern data sources or explain why these cannot be provided. 2) Are the labour and contractor rates union or non-union rates. | AtkinsRéalis
16 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References – column Price Base/References | In the column for price Base/References several price references are either Civil Est. Tool or Historical Database. For transparency and ensuring a proper evaluation of costs by all intervenor’s full disclosure of all price references is necessary. | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) the details of the Civil Est. Tool. 2) the Historical Database. | AtkinsRéalis
17 | RECLAIM 8 Model Working Copy – Excel Sheet; Instruction Tab – Conditions of Use | It states that “This model is not intended to dictate how much should be spent on reclamation.” What is the purpose of this financial model if it is not supposed to dictate how much should be spent on reclamation by the proponent? Is it possible that if a proponent disagrees with CIRNAC’s final dollar amount created by this model that the proponent could set their own financial security? | The KivIA requests that CIRNAC: 1) provide clarity on the purpose of the RECLAIM financial model. 2) provide clarity on the proponents responsibility to adhere to the final dollar amount calculated by the RECLAIM financial model. | GNWT/CIRNAC
18 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Fuel and Electricity | Fuel costs for gas and diesel are listed. No fuel costs for Jet A, Jet B or Av gas are included. | The KivIA requests that CIRNAC and their engineering consultants provide fuel costs for Jet A, Jet B and Av gas. | AtkinsRéalis
19 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Mobilize Workers (round trip) | Hourly costs for small, medium and heavy helicopters. Are these hourly costs “dry” (do not include fuel cost) or “wet” (do included fuel cost). | The KivIA requests that CIRNAC and their engineering consultants determine if the hourly costs for small, medium and heavy helicopters are “dry” or “wet”. | AtkinsRéalis
20 | RECLAIM 8 Model Working Copy – Excel Sheet; Estimator Tab – Excavator Ratings | The cycle times and productivity for excavators are based on southern Canadian conditions (ie. digging in sandstone and caliche; non-Arctic conditions). There is no reference to permafrost or Arctic conditions for the cycle times and productivity for excavators. | The KivIA requests that CIRNAC and their engineering consultants determine what changes to the cycle times and productivity for excavators will occur in permafrost and Arctic conditions, in particular, metal fatigue under extremely cold conditions (ie. > -40oC). | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Burgundy Diamond Mines Ltd – Sheila Chernys
1 | Transparency of Unit Rates Derivation | The derivation of the proposed RECLAIM 8.0 unit rates remains unclear, which makes it challenging for proponents to assess their applicability to specific sites. | Provide detailed explanations and supporting data for these rates would enhance understanding and confidence in their application. | AtkinsRéalis
2 | Mobilization and Indirect Cost Management (ICM) Costs | Reassigning these costs to Capital Costs introduces a compounding effect that significantly inflates estimates. | Retaining them under Indirect Costs would better account for site-specific variations without leading to overestimations. | AtkinsRéalis
3 | Default Percentages for Costs | The percentages allocated for Owners Representative, HHERA, and Final CRP costs are high and do not align with typical closure project requirements in the region. | Revisiting these percentages and considering fixed cost estimates will ensure more balanced and accurate calculations. | AtkinsRéalis
4 | Inflation Rate Methodology | Applying a fixed 3% inflation rate across all closure costs is not appropriate for all closure activities. | A more flexible approach based on historical inflation data and specific project conditions will better reflect actual cost variability. | AtkinsRéalis
5 | Incentives for Progressive Reclamation | The updates focus on increasing securities but could also include measures to encourage progressive reclamation during operations. For example, allowing partial release of securities to execute reclamation activities would promote progressive reclamation, reduce liabilities and support sustainable closure outcomes. | Update should encourage progressive reclamation during operations. | GNWT/CIRNAC

## March 2025 Comments
| No. | Reviewer | No. | Topic | Reviewer Comment | Reviewer Recommendation | Topic | Proponent Response
| 1 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 1 | Letter | Please see attached letter. | N/A | Policy | The Working Group recognizes "given the complexity and importance of these updates, we appreciate the opportunity for a second round of review and ongoing engagement. We would like to emphasize the need for additional time to conduct a more comprehensive analysis." The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025.
| 2 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 2 | Origin of Unit Rates | Burgundy Diamond Mines (Burgundy) and other proponents have been requesting that CIRNAC and GNWT provide the level of transparency and justification for RECLAIM unit rates that is demanded of proponents who put forward site-specific unit rates. This long-standing request remains wholly unsatisfied by the information provided with RECLAIM 8.0. For example, the proposed "load/haul/place" unit rates are described as being derived from "First Principles". However, simply referencing "First Principles" and listing a few assumptions under additional notes does not provide proponents with the information needed to adequately understand the unit rate or assess appropriateness for a specific site. | RECLAIM 8.0 should be accompanied by clear, detailed data on the derivation of the proposed unit rates, ensuring proponents can adequately understand the rates and make a rational determination of their appropriateness for an individual site or closure activity. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes.
| 3 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 3 | Moving Mobilization and ICM to Capital Costs | Mobilization and ICM costs were previously included under Indirect Costs which excluded them from the indirect percentage calculations. The new approach introduces a compounding effect and will significantly inflate the overall security estimate. This would result in overestimations that do not accurately reflect actual closure and reclamation needs particularly for major operations such as Ekati Diamond Mine (Ekati) with substantial security requirements. | The Mobilization and ICM costs should be maintained under Indirect Costs where the existing indirect cost percentages can adequately account for variations. This would avoid the compounding effect introduced by their inclusion in Capital Costs while still ensuring these costs are adequately captured within the model. | Indirects | Mobilizing is moved back to an indirect cost.
| 4 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 4 | Owner's Representative | A new line has been added under Indirect Costs for Owners Representative to ensure that project objectives are met, with a default percentage of 10% of the direct costs assigned. The assigned percentage appears excessively high particularly for licencees with substantial direct costs. | The assigned 10% default percentage should be reevaluated and a reduction considered to better align with actual project requirements and industry norms. Additionally, more information should be provided to clarify the methodology and rationale behind determining this percentage and to assess its applicability across different projects. An alternate approach, such as an estimated cost (rather than a percentage) should also be developed and evaluated. | Indirects | The owners representative default has been adjusted to 5%. More information on the rational in determining the scaled percentage is available in the User Manual.
| 5 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 5 | HHERA and Final CRP Costs | The cost to complete a Human Health and Ecological Risk Assessment (HHERA) and Final Closure and Reclamation Plan (FCRP) has been added to the model at 3% and 4% of Capital Costs, respectively. While it is acknowledged that FCRP costs may not have been explicitly included in RECLAIM 7.0, the regular review of security estimates has ensured their incorporation for operations like Ekati. The most recent review by the GNWT in 2022 determined a significantly lower FCRP rate of approximately 1% of direct costs. There is no rationale for applying these items as a percentage of total rather than an estimated cost. These items are well established and well defined in scope and cost such that actual estimates can readily be developed. A percentage of total as proposed provides a grossly over-costed estimate for large site such as Ekati. Moreover, the risks addressed by HHERA are already evaluated as part of the permitting process. Monitoring data is utilized to assess operational and closure risks, which are accounted for in interim CRPs that are mandatory and regularly updated. As such, the addition of these costs in the proposed model is deemed unnecessary and the proposed percentages appear excessively high. | Burgundy recommends that HHERA and FCRP costs be excluded from the model. Alternatively, these percentages should not be based on Capital Costs given that risk evaluations and FCRP development will rely significantly on existing assessments and CRP plans developed during ongoing operations. A reduction or redefinition of these percentages is necessary to ensure they more accurately reflect the actual scope of work and associated costs. An alternate approach of an estimated cost (i.e., not a percentage) should be developed and evaluated. | Indirects | Reference to Health and Safety Plans was removed from the indirects as these costs will be covered under contingency amounts.
| 6 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 6 | Future Value Calculation | The future value calculation has been introduced to capture the anticipated costs of activities based on when they are expected to occur. A default inflation rate of 3% is applied which corresponds to the Bank of Canada’s upper target for annual inflation. For example, a cost estimate developed in 2028 using RECLAIM 8.0 standard rates would undergo a 3% annual inflation increase over four years (2024 to 2028). However, applying a predetermined, singular inflation rate is not appropriate when actual data is available. It is also not always suitable to apply the same inflation rate across all work included in a closure estimate. RECLAIM 8.0 documentation acknowledges the existence of various inflation estimates beyond the broad-based consumer-oriented CPI, but it discounts these approaches. Since the majority of mine closure plan costs are not consumer-oriented, it may not be appropriate to apply the general CPI across the entire estimate. Ekati's security estimates already incorporate an inflation calculator developed with stakeholders' input. This calculator considers the development year of each unit cost and applies inflation rates accordingly, resulting in inflation rates of less than 2%. Applying the upper target of the Bank of Canada’s inflation range may lead to overestimations, given that average inflation rates have remained between 1.5% and 2%. This approach is not ideal for long-term mine closure costing, as it introduces inflation without accounting for interest. It assumes that the financial security is cash in hand, which does not accrue interest over time. By comparison, the Province of British Columbia uses a net discount factor (i.e., net of both inflation and interest) for recurring long-term costs. The approach proposed in RECLAIM 8.0 introduces a substantial cost factor that could significantly affect project viability. This issue requires detailed engagement and financial analysis by the government before any consideration for implementation. | 1. RECLAIM 8.0 should provide a clear rationale for adopting a single pre-determined inflation factor and consider developing an alternative approach that utilizes inflation rates most appropriate to the specific work and costs within the closure cost estimate. The future value inflation rate should be revised to reflect a more accurate figure, such as the average of historical inflation data over a relevant timeframe, rather than defaulting to the upper target of 3%. This adjustment would result in a more balanced and accurate estimate, avoiding excessive conservatism in the model. Additionally, greater transparency is needed in how inflation rates are applied to different unit costs over time to ensure consistency and confidence. 2. This cost item should not be implemented without specific, in-depth engagement and financial analysis including an evaluation of experiences in other regulatory jurisdictions. | NPV | Details have been provided by the Working Group on how the inflation rates were determined. The Working Group is considering this recommendation and will add it to the agenda of the upcoming engagement workshop.
| 7 | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo | 7 | Incentivizing Progressive Reclamation | The proposed updates to RECLAIM 8.0 emphasize increasing securities to address potential reclamation costs. It is equally important to incentivize progressive reclamation during operations. Progressive reclamation not only reduces overall closure liabilities but also demonstrates ongoing commitment to environmental stewardship. Models used in jurisdictions such as Quebec and the Alberta oilsands provide practical examples of incentivizing progressive reclamation by allowing operators to utilize existing securities during operations, thereby encouraging earlier action rather than deferring it until closure. | Burgundy recommends that the GNWT implement mechanisms to incentivize progressive reclamation activities during operations. This could include provisions that allow for the partial release or reallocation of securities to fund reclamation efforts. Such measures would enhance operational efficiency, reduce the financial burden of increasing securities and encourage operators to proactively incorporate reclamation into their operational plans. This approach would ultimately lead to more sustainable and cost-effective closure outcomes. | Policy | The Working Groups appreciates the comment and recommendation. However, this topic falls outside the scope of the RECLAIM tool update. The GNWT commit to engaging directly with Burgundy to discuss this comment on the topic of progressive reclamation. It is also noted that in the NWT, the LWBs set the security and make decisions on how progressive reclamation is accounted for. The GNWT only hold the security funds, there is no mechanism by which the GNWT can hold less than the amount set by the Board. CIRNAC supports and encourages progressive reclamation activities during operations. The Mine Site Reclamation Policy for Nunavut and the Mine Site Reclamation Policy for the Northwest Territories requires the total financial security for final reclamation required at any time during the life of a mine to be equal to the total outstanding reclamation liability (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period). Similarly, when ongoing reclamation work reduces the outstanding environmental liability, it will result in a reduction in the level of financial security required to be maintained, but not in advance of reclamation works being completed. Any deviation from these principles would require the review and revision of the Reclamation Policies and is beyond the scope of the current RECLAIM revision. The comment is well noted and will be considered in any subsequent approaches to revising the northern reclamation regime.
|  | Agnico Eagle Mines Limited – Jamie Quesnel | 1 | Review Data Extension | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. As was apparent at the January 23, 2025 Engagement and Feedback Session, and echoed again in the NWT & Nunavut Chamber of Mines letter, there were many uncertainties and risks identified by Industry, including time to complete a detailed and adequate review of all the proposed changes under RECLAIM 8.0. As outlined in Section 2 of this letter, Agnico Eagle has undertook an initial review and provided some comments and recommendations; however, a detailed fulsome review has not been executed at this stage. | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. | Policy | The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025.
| 2 | Agnico Eagle Mines Limited – Jamie Quesnel | 2 | Documents received | This is a preliminary review due to the short timeline | More time is required to complete a comprehensive review of the documentation provided | Policy | The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025.
| 3 | Agnico Eagle Mines Limited – Jamie Quesnel | 3 | Reclamation Policy | As the reason is unknown why the Reclaim V8 was changed, plus we have an undefined process we are following, and this creates uncerntainity. | Develop a policy update with a defined process of consulation, etc., and define the triggers for a material change. | Policy | CIRNAC appreciates the feedback on aligning RECLAIM 8.0 with broader policy and regulatory frameworks, particularly within the context of Nunavut’s evolving mining landscape. CIRNAC agrees that the 2002 Mine Site Reclamation Policy for Nunavut requires revision to reflect advancements in mine closure science, regulatory best practices across Canada, and contemporary environmental, social, and economic conditions in the North. CIRNAC is currently looking at options to develop a modernized mine reclamation framework in consultation with Indigenous governments, co-management boards, the Government of Nunavut, the Government of the Northwest Territories, and industry partners. Any updates to the policy will align with RECLAIM 8.0 and other federal risk management standards.
| 4 | Agnico Eagle Mines Limited – Jamie Quesnel | 4 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" and "'Work week for earthwork (rock, soil, riprap excavation, hauling to waste dump is 7 days a week x 10 hours per day = 70 hours per week" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No overnight work is considered. | Unit rates should be developed assuming 24 hour operation where practical. SUPPORTING RATIONALE: Operating Mines, particularly in the North, require round the clock operation for maximum equipment utilization and operation effectiveness. Haul trucks engines must be active around the clock to ensure operability and neglecting night shift utilization ignores real operating expenditures. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes. Operating mines may work different hours and seasons from a site being managed by a third party. The rates provided are a guildine for costs incurred during the rclamation process and not during any one phase of the production lifecycle of the mine. Hours worked may be different . The number is to be used as a guide in development of the estimate.
| 5 | Agnico Eagle Mines Limited – Jamie Quesnel | 5 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No night work is considered. | Operating Mines, particularly in the North require round the clock operation for maximum equipment utilization and operation effectiveness. SUPPORTING RATIONALE: Neglecting potential night shift work unnecessarily extends project schedule and therefore unnecessarily inflates overall project costs. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes. Operating mines may work different hours and seasons from a site being managed by a third party. The rates provided are a guildine for costs incurred during the rclamation process and not during any one phase of the production lifecycle of the mine. Hours worked may be different . The number is to be used as a guide in development of the estimate.
| 6 | Agnico Eagle Mines Limited – Jamie Quesnel | 6 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'The labour cost included in the unit rates considered the following cost: … - Indirect labour" | The battery limits for "indirect labour" included in unit rate development is not adequately defined. RECLAIM includes indirect activities such as Project Management and Engineering Design applied as a general percentage of direct costs. | Clarify what indirect labour is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | Unit Rates | The Working Group will update the definition in User Manual
| 7 | Agnico Eagle Mines Limited – Jamie Quesnel | 7 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "The labour cost included in the unit rates considered the following cost: … - Site supervision and administration" | The labour cost included in the unit rates considered the following cost: Site supervision and administration | Clarify what site supervision and administration is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.). SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. Project management, Health and Safety Monitoring & QC as an indirect cost is applied as a blanket % to all costs. | Unit Rates | Captured in the Project Management Indirects (define in User Manual)
| 8 | Agnico Eagle Mines Limited – Jamie Quesnel | 8 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "Exclusion ...- Project indirect cost" | The battery limits for "indirect cost" included in unit rate development is not adequately defined. | Clarify what indirect cost is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | Indirects | Double counting of indirects in published unit rates is not occuring.
| 9 | Agnico Eagle Mines Limited – Jamie Quesnel | 9 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 5 Exclusions LINE: "- First Fills" | First fills are excluded from unit cost build up. | Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup that excludes first fills. SUPPORTING RATIONALE: Consistent application inclusions and exclusions are important for usability of RECLAIM. Suggest using one data source for all unit rate buildup. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes.
| 10 | Agnico Eagle Mines Limited – Jamie Quesnel | 10 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- Freight for the bulk materials such as granular, concrete and HDPE pipes are included with the unit rates" | Proposed unit rate buildup includes freight for bulk materials. This necessitates site specific unit rate for all bulk materials as freight costs can very substantially between sites. There is already a section within the RECALIM mobilization tab to capture freight cost. | Bulk material default unit rates should exclude freight. Freight for materials should be included separately based on a site specific unit cost for material mobilization, captured in the RECLAIM Mobilization tab. | Unit Rates | First Principle Unit rates will be updated to remove indirects. Unit rates to be discussed at the upcoming engagement workshop.
| 11 | Agnico Eagle Mines Limited – Jamie Quesnel | 11 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- It is assumed there is no batch plant required. All concrete will be delivered to site to use" | The clarification that no batch plant will be required constricts operational planning. In some cases it is more cost effective to commission a batch plant and ship bulk concrete than to use premix product. | Freight of premix concrete products is not always practical for northern projects based on mobilization constraints and the use of a batch plant should be considered when operationally and financially advantageous. | Unit Rates | Proponent can propose a batch plant as part of the development of their site-specific closure costs.
| 12 | Agnico Eagle Mines Limited – Jamie Quesnel | 12 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects LINE: Mobilization/Demobilization 6.0% | Contractor indirects, specifically mobilization/demobilization, are shown as separate adders to the base rates for equipment and labour direct costs. RECLAIM considers mobilization and demobilization costs separately from operating unit rates as part of the Mobilization tab. | Exclude mobilization/demobilization cost from unit rate development. Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup and if mobilization/demobilization cost has been accounted for with respect to the overall RECLAIM workbook. | Unit Rates | First Principle Unit rates will be updated to remove indirects. Unit rates are to be discussed at the upcoming engagement workshop.
| 13 | Agnico Eagle Mines Limited – Jamie Quesnel | 13 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects | A variety of sources for equipment operating costs as well as labour costs are indicated as being used as a basis for unit rate calculations. There are substantial differences in the factors included in each of the sources for equipment operating costs. For example, BC Blue Book and Alberta Equipment Rental Rates Guide are used interchangeably in FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Rates but BC Blue Book equipment operating rates do not explicitly include contractor overhead and profit whereas Alberta Equipment Rental Rates Guide does. The provided unit rate example in FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects, if using Alberta Equipment Rental Rates Guide for equipment or manpower hourly rates is applying an additional 12.50% Mark-up & Profit on a rate that already includes Mark-up & Profit. | Default unit rates provided in RECLAIM 8 should use a consistent source reference for all equipment and manpower hourly rates with clearly defined buildup of direct and indirect components. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes. The Alberta Equipment Rental Rates Guide does not include contractor overhead and profit
| 14 | Agnico Eagle Mines Limited – Jamie Quesnel | 14 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Buildings - Remove" COST CODE: BRW, BRC, BRS1, BRS2 | Cost Codes: BRW, BRC, BRS1, BRS2 have no default HIGH unit rate provided as part of RECLAIM 8.0 example. RECLAIM 7.0 provided a HIGH unit rate for these cost codes resulting in a 1:1 comparison between RECLAIM 8.0 default unit costs and RECLAIM 7.0 unit costs. | RECLAIM 8.0 should include a default HIGH unit rate for all default cost codes that have a defined HIGH unit rate in RECLAIM 7.0 | Unit Rates | RECLAIM V8.0 does not include a "High" unit rate. The proponent can propose a new rate based on site specific factors.
| 15 | Agnico Eagle Mines Limited – Jamie Quesnel | 15 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB1, RB2 | The detail defining what activity COST CODES RB1 and RB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines RB1 as "drill/blast/load/short haul" RECLAIM 8.0 defines RB1 as "load/haul/place"RECLAIM 7.0 defines RB2 as "drill/blast/load/long haul" RECLAIM 8.0 defines RB2 as "RB1 + spread and compact"This respondent uses COST CODE RB2 to represent activities requiring "drill/blast/load/long haul" but NOT "spread and compact" To accommodate the change in COST CODE detail from RECLAIM 7.0 to RECLAIM 8.0 >$10 million of activities on a single site would need to be recoded to avoid implying "spread and compact" is required for these activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | Disagree with recommendation. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed
| 16 | Agnico Eagle Mines Limited – Jamie Quesnel | 16 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB3, RB4 | COST CODE: RB3 and RB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RB3 DETAIL: "RB1 + spread and compact" is the same as RECLAIM 8.0 CODE RB2 DETAIL: "RB1 + spread and compact"RECLAIM 7.0 COST CODE RB4 DETAIL: "RB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RB3 and RB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 17 | Agnico Eagle Mines Limited – Jamie Quesnel | 17 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - High Spec (i.e. Rip Rap, Screened)" COST CODE: RC3, RC4 | COST CODE: RC3 and RC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RC3 DETAIL: "RC1 + spread and compact" is the same as RECLAIM 8.0 CODE RC2 DETAIL: "RC1 + spread and compact"RECLAIM 7.0 COST CODE RC4 DETAIL: "RC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RC3 and RC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 18 | Agnico Eagle Mines Limited – Jamie Quesnel | 18 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB1, SB2 | The detail defining what activity COST CODES SB1 and SB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SB1 as "excavate/load/short haul" RECLAIM 8.0 defines SB1 as "excavate/load/haul/place"RECLAIM 7.0 defines SB2 as "excavate/load/long haul" RECLAIM 8.0 defines SB2 as "SB1 + spread and compact"This respondent uses COST CODE SB2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 19 | Agnico Eagle Mines Limited – Jamie Quesnel | 19 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB3, SB4 | COST CODE: SB3 and SB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SB3 DETAIL: "SB1 + spread and compact" is the same as RECLAIM 8.0 CODE SB2 DETAIL: "SB1 + spread and compact"RECLAIM 7.0 COST CODE SB4 DETAIL: "SB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SB3 and SB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. This respondent would need to recode >$35 million of activities at one site. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 20 | Agnico Eagle Mines Limited – Jamie Quesnel | 20 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC1, SC2 | The detail defining what activity COST CODES SC1 and SC2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SC1 as "excavate/load/short haul" RECLAIM 8.0 defines SC1 as "excavate/load/haul/place"RECLAIM 7.0 defines SC2 as "excavate/load/long haul" RECLAIM 8.0 defines SC2 as "SC1 + spread and compact"This respondent uses COST CODE SC2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 21 | Agnico Eagle Mines Limited – Jamie Quesnel | 21 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC3, SC4 | COST CODE: SC3 and SC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SC3 DETAIL: "SC1 + spread and compact" is the same as RECLAIM 8.0 CODE SC2 DETAIL: "SC1 + spread and compact"RECLAIM 7.0 COST CODE SC4 DETAIL: "SC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SC3 and SC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed.
| 22 | Agnico Eagle Mines Limited – Jamie Quesnel | 22 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, small (<6in dia.)" COST CODE: PSS, PSI | COST CODES: PSS and PSI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed. Will consider retaining <6 in dia. Pipe but will update the costs to 2024 dollars. To be discussed at the planned workshop.
| 23 | Agnico Eagle Mines Limited – Jamie Quesnel | 23 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, large (>6in dia.)" COST CODE: PPLR, PLS, PLI | COST CODES: PLR, PLS and PLI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed. Will consider retaining <6 in dia. Pipe but will update the costs to 2024 dollars. To be discussed at the upcoming engagement workshop.
| 24 | Agnico Eagle Mines Limited – Jamie Quesnel | 24 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: PS | Pumps, Pump shipping COST CODE: PS unit changed from RECLAIM 7.0 lump sum (each) to, RECLAIM 8.0 percentage (%) of pump cost.Existing RECLAIM 7.0 projects have taken to account shipping of pumps, by lump sum (each) as part of the mobilization calculation. Shipping cost is generally site specific and existing calculations should remain valid. Shipping cost as a % of pump capital cost could be a useful default unit rate for establishing projects. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND adding new cost code for shipping as a % of capital cost | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed. Mobilization of pumps is included in rates as per Table 1
| 25 | Agnico Eagle Mines Limited – Jamie Quesnel | 25 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: POC | Pumps, Pump operating cost COST CODE: POC unit changed from RECLAIM 7.0 m3 (volume pumped) to, RECLAIM 8.0 kw-h (power cost).Pump operating cost is certainly predicated on site power cost but the relationship between pumped volume and power draw is based on site specific conditions. Volume of water is the unit of measure for reclamation activities and using a second unit of measure to determine cost would introduce additional complexity. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND pump operation based on cost per volume pumped. | Unit Rates | The Working Group agrees that using RECLAIM 7.0 cost codes in RECLAIM 8.0 may cause some issues if the code is not describing the same activity. We will compare the cost codes and activities, discuss them at the planned workshop with industry and make changes where appropriate. RECLAIM was refreshed to reflect modern mine closure and as such some Cost Codes were added or Changed. Power costs are the most common method and is used in RECLAIM V8
| 26 | Agnico Eagle Mines Limited – Jamie Quesnel | 26 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Human Health and Ecological Risk Assessment (% Closure Costs) | Human Health and Ecological Risk Assessment (% Closure Costs): Cost to develop a site specific HHERA is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for HHERA related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | The Government of Canada currently maintains a clear position under its Mine Site Reclamation Policies that it does not assume any financial liability for mine reclamation. Until there is a change in this current policy position, any proposal under consideration must be assessed against this policy principle. The key issue is whether the proposal aligns with industry best practices and maintains the integrity of the “polluter pays” principle. It is essential to ensure that the proposed approach does not create conditions under which the Crown could be held liable—directly or indirectly—for reclamation costs.
| 27 | Agnico Eagle Mines Limited – Jamie Quesnel | 27 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Finalize Closure and Reclamation Plan (% Closure Costs) | Finalize Closure and Reclamation Plan (% Closure Costs): Cost to develop Final Closure and Reclamation plan is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Finalize Closure and Reclamation Plan related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | In line with the Government of Canada’s current policy on mine site reclamation, the Crown does not assume any financial liability for reclamation costs. Proponents are fully responsible for covering the cost of closure and remediation through financial securities. While the introduction of a sliding scale for estimating certain costs—such as Final Closure and Reclamation Plan (FCRP) components—could help better reflect project-specific uncertainties and the level of planning detail, similar to existing contingency allowances in the RECLAIM model, any such methodology would require further technical development and analysis. This approach may enhance internal consistency within the model, while promoting transparency, predictability, and alignment with the policy objective of protecting taxpayers and upholding Indigenous and public interests. Any proposed updates must continue to ensure that reclamation liabilities are appropriately estimated and secured, without transferring risk to the federal government. However the government , if a site is abandoned, may or may not follow any exisiting plan and in fact may be required to develop a new plan in the event that a final plan was not already aproved. These costs must also be accounted for in the development of the estimate.
| 28 | Agnico Eagle Mines Limited – Jamie Quesnel | 28 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engineering Design | Indirect Costs: Engineering Design : Cost for engineering design is warranted and should consider work already completed to capture the real effort and cost to achieve closure | Implement a sliding scale for Engineering Design Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | For discussion at the upcoming engagement workshop. See revised model.
| 29 | Agnico Eagle Mines Limited – Jamie Quesnel | 29 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Project Management | Indirect Costs: Project Management : Cost for project management is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Project Management Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | For discussion at the upcoming engagement workshop. See revised model.
| 30 | Agnico Eagle Mines Limited – Jamie Quesnel | 30 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Health and Safety Plans/Monitoring & QC | Indirect Costs: Health and Safety Plans/Monitoring & QC : Cost for Health and Safety Plans/Monitoring & QC is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale to account for project maturity and the cost and effort required to achieve closure. | Indirects | For discussion at the upcoming engagement workshop.
| 31 | Agnico Eagle Mines Limited – Jamie Quesnel | 31 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Bonding / Insurance | Indirect Costs: Bonding / Insurance : Cost for Bonding and Insurance is warranted and should consider work already completed to capture the real effort and cost to achieve closure. This cost should also account for the reliability and ease of use of the financial assurance instrument used by the mine owner as well as the financial reliability of the mine owner, represented by third party credit rating. Typical operating project bonding and insurance costs for third parties are historically <1% total project cost. | Implement a sliding scale to account for owner reliability, project maturity, and the cost and effort required to achieve closure. Established mining companies at low risk of becoming insolvent should have their efforts to achieve closure recognized. | Indirects | For discussion at the upcoming engagement workshop.
| 32 | Agnico Eagle Mines Limited – Jamie Quesnel | 32 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engagement and Regulatory Compliance | Indirect Costs: engagement and regulatory compliance cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations, including through regulatory compliance and engagement, should not be made to bear burden of costs outside their influence. | Indirects | In line with the Government of Canada’s current policy on mine site reclamation, the Crown does not assume any financial liability for reclamation costs. Proponents are fully responsible for covering the cost of closure and remediation through financial securities.
| 33 | Agnico Eagle Mines Limited – Jamie Quesnel | 33 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Contingency | Indirect Costs: Contingency : Cost for contingency is warranted and should consider work already completed to capture the real effort and cost to achieve closure. There is currently a sliding scale for contingency, codified in the RECALIM 7.0 user manual, but the benchmarks set out are not representative of the level of contingency requested by CIRNAC and recommended by Brodie Consulting. The RECLAIM 8.0 contingency scale, based on AACE International Recommended Practice No. 10S- 90 representative of current industry practice and can be augmented with other factors such as owner financial strength, path to closure, and financial instrument of security. | Contingency sliding scale should reflect project lifecycle maturity, the financial strength of the owner, the financial instrument of closure security and the cost and effort required to achieve closure. | Contingency | For discussion at the upcoming engagement workshop.
| 34 | Agnico Eagle Mines Limited – Jamie Quesnel | 34 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Owners Representative | Indirect Costs: Owners representative cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations should not be made to bear burden of costs outside their influence. This line item addition represents a significant burden to all mining companies and it may impact the viability of future developments. | Indirects | In line with the Government of Canada’s current policy on mine site reclamation, the Crown does not assume any financial liability for reclamation costs. Proponents are fully responsible for covering the cost of closure and remediation through financial securities.See revised model for updated percentage.
| 35 | Agnico Eagle Mines Limited – Jamie Quesnel | 35 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Site Specific Future Value Inputs | FILE: reclaim 8.0 User Manual_Working Copy.pdf affirms that the determination of future costs must include all parameters including the Net Present Value of those costs. The Site Specific Future Value Inputs projects a future cost without including for the future value of the security | If RECLAIM is to project factors such as inflation it should also account for the present value of money at the time of projection. A prescribed NPV calculation with appropriate discount rate should be applied alongside all Post-Closure costs and future projections. | NPV | The FV costs was added as interest is not being made on the held security. To ensure the appropriate funds are available at the time of construction an inflation factor based on CPI was added. Set timeframes for security reviews, timed with license renewals could be considered. Furthermore, Discount Rates are not appropriate when projecting actual dollars spent in the future.
| 1 | B2G Back River Corp. Nunavut – Merle Keefe | 1 | Review Data Extension | B2Gold Nunavut is presently unable to meet the requested date for the submission of comments and therefore supports a recent request made by the NWT& Nunavut Chamber of Mines (Chamber) to extend the comment period deadline. B2Gold Nunavut also supports the request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM. The Chamber submission is attached to this letter. | Request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM | Policy | The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025. An engagement workshop is being planned for Fall 2025.
| 2 | B2G Back River Corp. Nunavut – Merle Keefe | 2 | N/A | In Table A of the Supplementary Information on RECLAIM V8 February 18,2025, Comment from Technical Working Group only includes very high-level information with no supporting evidence for decisions made. | Provide detailed supporting evidence to support the Technical Working Group Comments, both in the nature of the decision (e.g., to include additional cost), as well as the magnitude associated with the decision (e.g., The default percentages for project management and engineering were both increased as per later recommendations). | Policy | The Working Group has provided this information.
| 3 | B2G Back River Corp. Nunavut – Merle Keefe | 3 | N/A | In Table B of the Supplementary Information on RECLAIM V8 February 18,2025, the Rationale provided includes "actual cost for Mine Closure and Reclamation at various locations across Canada". No visibility is provided as to the size of these projects. While it is acknowledged that smaller projects could have a larger percent of Indirect Costs, no justification or evidence is provided to demonstrate the 58% of Indirect Costs of larger projects (i.e., greater than $100M in Direct Costs) is justifiable. | Provide detailed supporting evidence to outline the significant increase in Indirect Costs is justified for projects greater than $100M in Direct Costs. | Indirects | Additonal supporting evidence will not be provided. Actual costs incurred can be represented by recent mine work in the Yukon and other well know projects such as Faro and Giant.
| 4 | B2G Back River Corp. Nunavut – Merle Keefe | 4 | N/A | Insufficient evidence was provided to justify the addition of Site Specific Future Value Inputs to the RECLAIM model. Insufficient instructions were provided on the Site Specific Future Value Inputs. | Provide detailed supporting evidence to justify the addition of the Site Specific Future Value Inputs. Provide detailed instructions and examples for use of Site Specific Future Value Inputs. Why are Site Specific Future Value Inputs included when the model currently includes the Market Factor Price Adjustment under Indirect Costs? How are Site Specific Future Value Inputs any different than Market Factor Price Adjustment and is there any discount factor applied to future value? | NPV | User Manual to provide more instructions Held securities do not earn money and therefore cannot cover future costs, CIRNAC and GNWT is under secured. The Site Specific Future Value Inputs are used to calculate the FV, whereas the Market Factor Price Adjustment was retained to provide the proponent the opportunity to account for current or localized market variations (regional, economic or market-driven) that impact cost of materials, labour and equipment beyond base estimating data. No Discount factor for FV, see other responses
| 5 | B2G Back River Corp. Nunavut – Merle Keefe | 5 | N/A | Under Owner's Representative in the Supplementary Information on RECLAIM V8 February 18,2025, it is stated "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | Provide detailed evidence to validate Owner's Representative costs "ranged from 12% to greater than 20%". | Indirects | The Working Group is not proposing 20% and these costs are not public information. In line with the Government of Canada’s current policy on mine site reclamation, the Crown does not assume any financial liability for reclamation costs. Proponents are fully responsible for covering the cost of closure and remediation through financial securities.
| 6 | B2G Back River Corp. Nunavut – Merle Keefe | 6 | N/A | In Attachment A to the Supplementary info provided Feb 18 2025, the short load/haul/place unit rates includes approximately 59% of Indirect costs within this hourly rate. Once this unit rate is used, an additional 58% Indirect Costs would be applied to this value on the Summary tab of the RECLAIM model. | Provide detailed evidence to justify why the indirect costs built into the hourly rate are not duplicative of the Indirect Costs applied on the RECLAIM model summary tab. | Indirects | First Principle Unit rates will be updated to remove indirects. Unit rates to be discussed at the upcoming engagement workshop.
| 7 | B2G Back River Corp. Nunavut – Merle Keefe | 7 | N/A | Under Conclusion in the Supplementary Information on RECLAIM V8 February 18,2025, it is stated "Progressive reclamation activities should also be considered to minimize held securities and reduce overall contingencies." However no additional information is provided on progressive reclamation and the RECLAIM model includes no mechanism/system/guidance to allow owners to recover funds for reclamation work completed. | Include a formal mechanism within the RECLAIM model to calculate and account for progressive reclamation and include in the RECLAIM manual steps and guidance for how owner will recover funds for reclamation work completed. | Policy | RECLAIM V8 is a tool to calculate environmental liability. Progressive reclamation, including the "mechanism/system/guidance to allow owners to recover funds for reclamation work complete", is jurisdiction specific. CIRNAC acknowledges the recommendation for a formal mechanism outside the RECLAIM tool to calculate and account for progressive reclamation, as well as to provide guidance on the potential return of financial securities for completed reclamation activities. This issue is currently under consideration as part of broader updates to CIRNAC’s 2002 Mine Site Reclamation Policy and the ongoing technical review of the RECLAIM model. While no formal mechanism is currently in place, CIRNAC recognizes the value of progressive reclamation in reducing overall closure liability and is exploring policy and procedural options to support its recognition—where appropriate—within the security framework. Any future changes would need to be developed in close coordination with territorial regulators, Indigenous partners, and other stakeholders to ensure consistency, transparency, and alignment with CIRNAC’s policy objective to fully secure liability while safeguarding public and Indigenous interests.
| 1 | Baffinland Iron Mines Corporation – Lou Kamermans | 1 | Procedural Fairness | Due to the short timeline to review the proposed changes, Baffinland has not had a full opportunity to conduct an in-depth review of the technical information supporting the RECLAIM 8.0 update. Respectfully, the timeline that was provided to industry for this initial round of comments is not adequate given the importance of RECLAIM to the Nunavut mining industry and the very serious potential impacts that have already been identified through the minimal consultation that has occurred to date. We are concerned that RECLAIM 8.0 could be advanced further despite these procedural deficiencies and the serious concerns expressed by industry to date. Given the significance of these changes to the mining industry in Nunavut and the Northwest Territories, and the potential direct impacts that it will have on Baffinland, we are providing initial high-level comments and recommendations below. In providing these comments, we reserve the right to provide further and more detailed comments, following further industry engagement and once better information is shared by CIRNAC and GNWT. | A. CIRNAC should engage stakeholders and Inuit organizations in a meaningful consultation process before finalizing the changes. Respectfully, the process described in the letter to the Chamber of March 18, 2025 does not achieve this standard. B. Third public review and comment period should only occur after CIRNAC has produced a version of RECLAIM 8.0 revised based on comments. A further workshop may be necessary to review this revised RECLAIM 8.0 before any final comment period. C. The overall timelines suggested in the process letter of March 18 are inadequate. For example, with respect to the suggested expected date of implementation of RECLAIM 8.0 [August 1, 2025], it is apparent that there would be no meaningful opportunity for feedback provided during the third round of public feedback (due July 16, 2025). D. CIRNAC should advise how they intend to engage with NTI and RIOs on impacts to their rights resulting from this policy change, with associated timelines, before RECLAIM 8.0 is adopted. E. CIRNAC should advise how they intend to engage with GN resulting on impacts relating to devolution resulting from this policy change (including spinoff economic effects), with associated timelines, before RECLAIM 8.0 is adopted. | Policy | A. CIRNAC/GNWT door remains open to productive engagement and new or innovative ideas in the shaping of the RECLAIM tool - and are open to scheduling additional one-on-one meetings throughout this process. B. The Working Group commits to releasing a revised version of RECLAIM 8.0 based on comments with the June 16, 2025 summary of feedback to date. This is in advance of, and available for, the third round of public feedback commenting period deadline of August 15, 2025. C. The Working Group provided March 30, 2025 and May 30, 2025 commenting deadilnes and we feel this was sufficient. Upcoming commenting deadlines and workshop are detailed in the June 16, 2025 correspondence letter from CIRNAC/GNWT. D. RECLAIM is a tool for calculating environmental liability. It does not usurp the security management agreements between CIRNAC and the Regional Inuit Associations (RIAs). The RIAs participated in the roll out of the updated RECLAIM 8.0 tool on January 23, 2025, and provided written feedback by the close of the first public engagement and commenting period deadline. CIRNAC is open to further discussions with RIAs on RECLAIM. E. CIRNAC has invited the GN to be part of the RECLAIM update process. The GN sent a representative to participate in the roll out of the updated RECLAIM 8.0 tool on January 23, 2025 Vancouver, and to the CIRNAC RECLAIM presentation at the Nunavut Mining Symposium on April 9, 2025.
| 2 | Baffinland Iron Mines Corporation – Lou Kamermans | 2 | Economic impact of RECLAIM 8.0 | As Canada is trying to promote economic development and critical minerals development, which includes high grade iron ore, the additional security concepts and requirements proposed by CIRNAC in RECLAIM 8.0 will only make it harder to develop and maintain what we have. The changes proposed by CIRNAC will negatively impact mine financing and development by increasing security requirements and financial obligations without an adequate and corresponding industry consultation process. Any potential lack of engagement with industry and designated Inuit organizations undermines the legitimacy of these updates as a policy framework. Furthermore, as highlighted above, the RECLAIM 8.0 approach appears to disincentive projects with longer lifespans and greater water liability marks, which is in direct opposition to existing territorial and federal economic development policies and mandates. Without proper consultation, these changes will create uncertainty and deter investment in northern mining projects. Baffinland recommends that a comprehensive economic impact analysis be conducted to assess the implications of RECLAIM 8.0 on northern mining investment and development. Given the closure of major diamond mines in the North-West Territories and the absence of advanced stage projects in both the North-West Territories and Nunavut, apart from government funded infrastructure, the economic consequences of these changes should be thoroughly evaluated before implementation. An industry-commissioned economist could provide valuable insight into these potential impacts, and the results should be available before major policy decisions are finalized. | A. CIRNAC should conduct a comprehensive economic impact analysis to assess how RECLAIM 8.0 will affect mining investment and development in Nunavut. Industry and other stakeholders should be engaged on this question specifically as part of this analysis. B. As part of this analysis, CIRNAC should produce a third party expert prepared report on the potential economic impact of the proposed cost escalations on the mining industry in Nunavut. RECLAIM 8.0 has been provided without assessment of the negative economic impacts that could result from the significant policy change RECLAIM 8.0 represents. The independent economist selected for this task should have experience representing industry and have Northern expertise. | Policy | CIRNAC acknowledges the recommendation to conduct a comprehensive economic impact analysis related to the proposed RECLAIM 8.0 updates. We recognize the importance of understanding the broader implications of changes to the RECLAIM model, particularly for mining investment and development in Nunavut. CIRNAC notes that RECLAIM is a technical tool designed to support the accurate calculation of mine site reclamation liabilities. Maintaining the model’s integrity and alignment with regulatory requirements is a key priority. At the same time, CIRNAC is undertaking a broader update to its 2002 Mine Site Reclamation Policy, which may provide an appropriate framework to consider the type of economic analysis proposed. Options to conduct economic modelling of the impact of RECLAIM updates on the business environment in Nunavut undertaken and presented by Industry will be explored, as part of potential updates to CIRNAC's Mine Reclamation Policy; . Options to incorporate economic modelling or expert review into the finalization of the policy update process will be presented to senior management for consideration in Summer 2025. A decision regarding third-party analysis will be made in collaboration with territorial governments, co-management boards, and Indigenous partners.
| 3 | Baffinland Iron Mines Corporation – Lou Kamermans | 3 | Rates and Cost Estimates | The proposed updates to RECLAIM 8.0 introduce significant cost increases that could have long-term economic implications for mining projects in the North. These cost escalations require careful scrutiny to ensure they align with real-world reclamation expenditures and do not hinder responsible resource development. | A. Review and adjust cost estimates to ensure they are reasonable, justified, and do not include duplication in indirect costs. B. Develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. | User Manual | A: There was every attempt to ensure costs were reasonable, justified and did not include duplication. We will review the rates again in the upcoming engagement workshop to ensure they meet these criteria. B: Guidance on how to select the range of default percentages will be provided in the User Manual, where appropriate. To be discussed at the upcoming engagement workshop.
| 4 | Baffinland Iron Mines Corporation – Lou Kamermans | 4 | Rates and Cost Estimates | The unit rates proposed for RECLAIM 8.0 are substantially higher than those in RECLAIM 7.0, often reflecting worst-case scenarios without adequate justification, despite the additional materials provided following the January Workshop in Vancouver. While CIRNAC states that proponents may propose alternative rates, industry experience suggests that the highest rates are typically applied in practice, unless a clear security policy is in place (see Section 3 – Security Policy). First principles derivations for these rates has not been provided (as is typical when justifying modifying rates in a security estimate) and the references are highly generalized, which hinders review, especially in light of the limited review timeline. | C. CIRNAC and GNWT must provide more detailed first principles derivations for rates, at a level that would be expected of a proponent justifying its own rates in an estimate. Specific references are required and generalized references provided to date are not adequate to provide expert feedback and advice. | Unit Rates | C: Disagree. The Working Group provided links and references to the majority of the sources for increased rates applicable to remote mine working in NWT and Nunavut. The Working Group used First Principles to develop rates for soil and rock movement and provided the factors considered in the costs estimating tool. It is up to the mining company to counter these rates and provide rationale as why a different unit rates should be proposed (high or lower).
| 5 | Baffinland Iron Mines Corporation – Lou Kamermans | 5 | Rates and Cost Estimates | The increase in indirect percentages represents an overall 23% increase in costs, and several of these items overlap, resulting in duplication of costs (see Table 1). For example the increase in contingency seems to be duplicated by an increase in project management, engagement and regulatory compliance, and owner’s representative costs. These increases do not appear to be justified through a detailed cost analysis. | D. Justification must be provided by CIRNAC to address the duplication described in the comment, and a detailed cost analysis must be provided to justify these statements | Indirects | D: Duplication not found.
| 6 | Baffinland Iron Mines Corporation – Lou Kamermans | 6 | Rates and Cost Estimates | Upon initial review, the observations regarding indirect costs provided in the ”Review of Mine Financial Security Estimates and RECLAIM” (Brodie, 2020) do not align with the proposed Reclaim 8.0 Indirect costing changes. For example, the report states “BCL recommends that the default percentage for Project Management be increased based upon CIRNAC’s experience. Whereas the default percentage for Engineering should be maintained but with the RECLAIM User Manual revised to be even more explicit as to what is and is not assumed to be covered in this amount.: Baffinland notes that the proposed Reclaim 8.0 changes include an increase in project management indirect percentages (an increase from 5% to 8%), an additional owners engineer indirect (an increase of 8%) and an increase in engineering design indirects (5% to 8%). This appears to be in contradiction to the recommendations of the review report. | E. CIRNAC should align observations re indirect costs in RECLAIM 8.0 with Brodie, 2020 (subject to adjustment based on further submissions in future on each of these categories) | Indirects | E: Default increases in percentage of indirects were increased from the Brodie recommendations based on consultation with our consultants' cost estimators and based on incurred cost at other orphaned and abandoned mine sites across Canada.
| 7 | Baffinland Iron Mines Corporation – Lou Kamermans | 7 | Rates and Cost Estimates | Within the proposed update, contingency has been increased to a maximum of 25%, which the Reclaim review report (Brodie, 2020) describes as appropriate for “Very basic engineering only and costs based upon typical unit costs”. This guidance is not provided in the proposed RECLAIM 8.0 documentation. As Baffinland has noted above, in its experience when Reclaim is applied by reviewers the highest level of contingency/indirect is used as a manner of course, as there is little specific guidance provided how to select an appropriate contingency/indirect within the provided model. For example, although Baffinland’s closure plan has advanced to the ICRP stage and has had significant engineering completed, a 20% contingency has been consistently applied by CIRNAC reviewers. Without specific risk based guidance regarding how to select indirect percentages based on project stage and level of engineering completed, Reclaim 8.0 could be used in an overconservative manner due to the lack of specific guidance, which could have a significant impact on Baffinland and other resource development projects in Nunavut. | F. 25% is not an appropriate contingency percentage for most advanced projects with current RECLAIM 8.0 guidance there is a risk this value is applied broadly, like 20% contingency is now. Adjust contingency percentage to reflect a range of risk based standards adjustable based on criteria, such as reductions below 20% where projects already have significant completion of engineering | Contingency | F: Contingency will be based on engineering design and completion, environmental performance, compliance and non-compliance, stage of development. Refer to user manual for details.
| 8 | Baffinland Iron Mines Corporation – Lou Kamermans | 8 | Rates and Cost Estimates | The future value calculation for water treatment and other long-term liabilities places a significant financial burden on mining companies, particularly in the absence of strong offsetting mechanisms, such as security discounting based on known reserves—an approach used in other jurisdictions like British Columbia (BC) and Quebec (Government of BC, 2022; Government of Quebec, 2017). For instance, in 2022, the BC Ministry of Energy, Mines and Low Carbon Innovation introduced the Major Mines Reclamation Security Policy, which considers a mine’s stage of development and promotes long-term operations by applying different security rates at various points in a mine’s lifespan based on default risk. The policy states that “mines that have been operating for more than five years, and that have economically viable reserves for at least the next ten years at the permitted production rate, will be eligible to secure up to 25% of the reclamation liability against a portion of the reserve value.” (Government of BC, 2022). Adopting a similar approach in Nunavut provide much-needed financial flexibility for long-term mining projects like Baffinland, reducing upfront security costs while maintaining strong environmental protection measures. This would enhance the economic viability of long-life mines, encourage continued investment, and support sustainable resource development in the region. Tying financial security to the mine life cycle would help mining companies spread out financial security payments over the mine’s life, which would increase investor confidence while supporting responsible mining development that considers the projected mine life. | G.RECLAIM 8.0 should be revised to provide a clear mechanism for discounting security based on reserves, similar to those adopted in other jurisdictions such as BC and Quebec. | Policy | CIRNAC recognizes the potential role that proven mineral reserves and project economics can play in informing the financial capacity of a proponent to manage closure obligations. However, the primary objective of the RECLAIM model remains to ensure that the Crown is fully protected from the risk of unfunded reclamation liabilities at all stages of a project’s life cycle. While jurisdictions such as British Columbia and Quebec have adopted reserve-based discounting mechanisms under specific regulatory frameworks, these systems are typically supported by additional legal and financial assurances. Before adopting a similar mechanism, CIRNAC will need to carefully consider the following steps: Conduct a detailed comparative assessment of reserve-based discounting practices across Canadian jurisdictions to understand their scope, safeguards, and effectiveness; Evaluate the implications of such discounting on risk exposure, particularly in the event of market volatility, premature closure, or bankruptcy; and Consult with Indigenous governments, co-management boards, territorial regulators, and industry stakeholders to assess acceptability and identify appropriate risk mitigation tools. Until such a framework is clearly defined and aligned with federal policy objectives, CIRNAC will continue to apply the precautionary principle in estimating full-cost security requirements.
| 9 | Baffinland Iron Mines Corporation – Lou Kamermans | 9 | Update of 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) is required. | Before publishing a RECLAIM 8.0 model, Baffinland recommends that the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) be revised to reflect current conditions in the mining industry. There has been no suggestion that current Nunavut production mines are undersecured – as an example, Baffinland’s security is reviewed annually in a comprehensive process. The investment decision for Mary River was made on the suite of government and Inuit approvals in place, including RECLAIM 7.0. | A. Before RECLAIM 8.0 is adopted for Nunavut projects, the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) should be updated to reflect current conditions in the mining industry and best practices across Canada and globally. B. Current approved Nunavut projects should follow RECLAIM 7.0, unless the proponent consents to application of RECLAIM 8.0. | Policy | A: CIRNAC recognizes the potential role that proven mineral reserves and project economics can play in informing the financial capacity of a proponent to manage closure obligations. However, the primary objective of the RECLAIM model remains to ensure that the Crown is fully protected from the risk of unfunded reclamation liabilities at all stages of a project’s life cycle. While jurisdictions such as British Columbia and Quebec have adopted reserve-based discounting mechanisms under specific regulatory frameworks, these systems are typically supported by additional legal and financial assurances. Before adopting a similar mechanism, CIRNAC will need to carefully consider the following steps: Conduct a detailed comparative assessment of reserve-based discounting practices across Canadian jurisdictions to understand their scope, safeguards, and effectiveness; Evaluate the implications of such discounting on risk exposure, particularly in the event of market volatility, premature closure, or bankruptcy; and Consult with Indigenous governments, co-management boards, territorial regulators, and industry stakeholders to assess acceptability and identify appropriate risk mitigation tools. Until such a framework is clearly defined and aligned with federal policy objectives, CIRNAC will continue to apply the precautionary principle in estimating full-cost security requirements. B: Grandfathering has not taken place with previous versions of RECLAIM. For equitable treatment of all proponents, CIRNAC will utilize RECLAIM 8.0 version in all environmental liability calculations once it has been implemented.
RW: | 10 | Baffinland Iron Mines Corporation – Lou Kamermans | 10 | Misc. | No Comment | A. Only a simple markup of the updates to the User Manual has been provided. A detailed markup is requested as a simple markup does not clearly present the changes. | User Manual | The Working Group does not see the value in a more detailed markup since all changes are tracked in the current version.
| 11 | Baffinland Iron Mines Corporation – Lou Kamermans | 11 | Misc. | No Comment | G. With reference to the “proprietary civil rate tool” referenced at p. 20 of the User Manual for RECLAIM 8.0, if a tool is being adopted in a government policy, it must be made publicly available. If it is not publicly available, it should not be included in the policy. This is a matter of fairness and transparency. | User Manual | G: AtkinsRéalis suggests removal “proprietary” replace with “construction cost estimating”
| 12 | Baffinland Iron Mines Corporation – Lou Kamermans | 12 | Misc. | No Comment | C. Costs relating to the Crown’s legal obligation to consult (which would be incurred in any event, whether the Crown steps in as director of reclamation or participates in review of closure plans led by a proponent) should not be included in RECLAIM 8.0, as this is a fixed government cost, not a cost of reclamation. The suggested 3% includes items that are fixed government obligations that do not belong in a reclamation estimate. | Policy | C: The 3% Owners Costs are meant to capture expenses required to complete consultation during the ICM and Post Closure Phase that typically are budgeted for in day to day government spending (i.e., flights, vehicle rentals, accommodations, per diems to northern and remote communities to discuss the remediation, reclamation and closure plan). Costs of permitting and other third party costs related to government activities would be captured here. This excludes CIRNAC's consultation costs under Section 35 Duty to consult.
| 13 | Baffinland Iron Mines Corporation – Lou Kamermans | 13 | Misc. | No Comment | D. How is RECLAIM 8.0 accounting for Nunavut devolution relating to lands and waters from CIRNAC to the GN? | Policy | D: RECLAIM is a tool for calculating environmental liability. Implementation of the tool is up to the jurisdiction that chooses to use it.
| 14 | Baffinland Iron Mines Corporation – Lou Kamermans | 14 | Misc. | No Comment | E. RECLAIM 8.0 should recognize reasonable salvage value where justified by the proponents estimate. The current position is unreasonably conservative and results in over bonding in many circumstances. This statement should be revised accordingly “GNWT/CIRNAC does not recognize salvage value because of the problems associated with creditors rights, sale of equipment and uncertainty as to the actual value at the time of insolvency”. | Policy | E: Revised text looks appropriate to the Working Group.
| 15 | Baffinland Iron Mines Corporation – Lou Kamermans | 15 | Misc. | No Comment | F. Citation for precautionary principle definition should be to the CEPA not to the CEPA guide. | User Manual | F: Revision seems appropriate to the Working Group.
| 16 | Baffinland Iron Mines Corporation – Lou Kamermans | 16 | Misc. | No Comment | G. Progressive reclamation should be credited in mine reclamation costs. This aligns with the following statement from the 2002 Nunavut Reclamation Policy – “Mining operators should be credited for approved progressive reclamation, and the value of financial security required should be adjusted in a timely fashion” | Policy | G: CIRNAC supports and encourages progressive reclamation activities during operations. The Mine Site Reclamation Policy for Nunavut and the Mine Site Reclamation Policy for the Northwest Territories requires the total financial security for final reclamation required at any time during the life of a mine to be equal to the total outstanding reclamation liability (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period). Similarly, when ongoing reclamation work reduces the outstanding environmental liability, it will result in a reduction in the level of financial security required to be maintained, but not in advance of reclamation works being completed. Any deviation from these principles would require the review and revision of the Reclamation Policies and is beyond the scope of the current RECLAIM update. The comment is well noted and will be considered in any subsequent approaches to revising the northern reclamation regime.
| 17 | Baffinland Iron Mines Corporation – Lou Kamermans | 17 | Misc. | No Comment | H. RECLAIM 8.0 adds an additional owners representative indirect cost, which is in addition to the proposed project management indirect cost. The owners representative indirect has been insufficiently justifying in the provided accompanying documentation, and it should be noted that an owners representative is not required during proponent lead reclamation. This overly conservative indirect requirement could have significant implicants on mine financing and development. | Indirects | H: CIRNAC and GNWT would not lead the development and finalization of the Closure and Reclamation Plan, nor would they oversee the construction or monitoring and maintenance activities. It has been shown that this is not the case as seen at Faro and Giant mines. CIRNAC and GNWT would hire an engineering firm to provide Owners Representative services (technical resources to government) to manage and oversee another engineering firm (e.g. a design-build team) who would be contracted to complete the closure, reclamation and long term monitoring activities.
| 1 | Burgundy Diamond Mines Ltd – Sheila Chernys | 1 | Transparency of Unit Rates Derivation | The derivation of the proposed RECLAIM 8.0 unit rates remains unclear, which makes it challenging for proponents to assess their applicability to specific sites. | Provide detailed explanations and supporting data for these rates would enhance understanding and confidence in their application. | Unit Rates | Details have been provided by the Working Group on how the unit rates were determined. It is up to the proponent to derive and propose their own site specific unit rates for consideration in their respective regulatory processes. To be discussed further at the upcoming engagement workshop.
| 2 | Burgundy Diamond Mines Ltd – Sheila Chernys | 2 | Mobilization and Indirect Cost Management (ICM) Costs | Reassigning these costs to Capital Costs introduces a compounding effect that significantly inflates estimates. | Retaining them under Indirect Costs would better account for site-specific variations without leading to overestimations. | Indirects | Mobilizing is moved back to an indirect cost.
| 3 | Burgundy Diamond Mines Ltd – Sheila Chernys | 3 | Default Percentages for Costs | The percentages allocated for Owners Representative, HHERA, and Final CRP costs are high and do not align with typical closure project requirements in the region. | Revisiting these percentages and considering fixed cost estimates will ensure more balanced and accurate calculations. | Indirects | Refer to the summary document for changes made.
| 4 | Burgundy Diamond Mines Ltd – Sheila Chernys | 4 | Inflation Rate Methodology | Applying a fixed 3% inflation rate across all closure costs is not appropriate for all closure activities. | A more flexible approach based on historical inflation data and specific project conditions will better reflect actual cost variability. | NPV | The rates was 3.4% over the last 5. Its a default value and can be adjusted. To be discussed at the upcoming engagement workshop.
| 5 | Burgundy Diamond Mines Ltd – Sheila Chernys | 5 | Incentives for Progressive Reclamation | The updates focus on increasing securities but could also include measures to encourage progressive reclamation during operations. For example, allowing partial release of securities to execute reclamation activities would promote progressive reclamation, reduce liabilities and support sustainable closure outcomes. | Update should encourage progressive reclamation during operations. | Policy | CIRNAC and GNWT acknowledges that while the updates to RECLAIM 8.0 focus on enhancing the accuracy and sufficiency of calculating environmental liability, complementary policy measures can play a critical role in promoting progressive reclamation during mine operations. Progressive reclamation is a recognized best practice that contributes to reducing final closure liabilities, improving environmental outcomes, and demonstrating a proponent’s commitment to responsible resource development. CIRNAC and GNWT supports, in principle, the use of partial security release mechanisms where: reclamation activities have been demonstrably completed to an approved standard; site-specific performance criteria, as defined in regulatory authorizations and closure plans, have been met; and adequate monitoring and verification by the regulatory authority confirms the success of the reclaimed areas. As such, CIRNAC is open to integrating clear guidance on progressive reclamation incentives into its mine reclamation policy update. Updates in the reclamation policy may include provisions for: milestone-based security adjustments; third-party verification requirements; and enhanced transparency in decision-making regarding security reductions. Implementation of these measures will ensure that financial incentives for progressive reclamation are aligned with environmental performance, while maintaining full coverage of outstanding liabilities at all stages of a project’s life cycle.
| 1 | NWT & Nunavut, Chamber of Mines – Karen Costello | 1 | Review Data Extension | The Chamber respectfully requests a 4-month review period (including potential options for a workshop) to fulfill the first step in the review process. We would also ask for access to the Review of Mine Financial Security Estimates dated March 2020 at your earliest convenience. | N/A | Policy | The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025. The March 2020 Review of Mine Financial Security Estimates uploaded the NWT and NWB online public registries in February 2025.
| 1 | De Beers Canada Inc. - Gahcho Kue - Kurtis Trefry | 1 |  | De Beers is supportive extended engagement period granted to allow further opportunity for industry feedback to be considered into any changes. The initial deadline coincided with our annual reporting timelines, creating challenges in dedicating the necessary time and resources to this review. The additional time granted will allow us to prepare a thorough and well-considered submission that adequately addresses the updates. Given the potential for significant implications to the mining industry, the proposed changes to the RECLAIM model require significant time and resources to allow for a detailed review by all parties. De Beers looks forward to partaking in further engagement sessions and will provide more detailed comments following that period. | N/A | Policy | The Working Group appreciates the comment and look forward to additional engagement.
| 1 | Fisheries and Oceans Canada (DFO) - Mr. Derek Donald | 1 | Financial security associated with Fisheries Offsetting Plans. Specified under Section 2 (1)(b) and Schedule 1, Section 16, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations. | Fisheries and Oceans Canada (DFO) would like to thank CIRNAC and the GNWT, for developing and updating the RECLAIM model and providing this opportunity for review and comment. The RECLAIM model can be an important part of the Fisheries Act authorization process in that the model is often used by proponents when developing an itemized list of costs for conducting the Offsetting work and monitoring the project to inform the Letter of Credit associated with an Offsetting Pan, and by DFO when reviewing the financial liability associated with these plans. Fisheries Act authorizations can follow the lifecycle of a mine from pre-operational permitting to post-closure Offsetting Project monitoring. Financial liability and associated security in the form of an irrevocable Letter of Credit, is a key component of the Fisheries Act and associated Regulations. Mine development in Nunavut and the Northwest Territories often necessitates activities that directly or indirectly result in the Death of Fish, the Harmful Alteration, Disruption or Destruction of fish habitat, and/or the deposit of deleterious substances in water frequented by fish, governed respectively by Section 34.4, 35, and 36 of the Fisheries Act. These activities can be authorized under the Fisheries Act so that the activity is carried out in accordance with conditions set out in the authorization and the Regulations. Section 2 (1)(b) and Section 16 of Schedule 1, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations, requires the development of a Fish Offsetting Plan, including the financial liability and associated security, to cover the costs of implementing the fish Offsetting Plan. These Fish Offsetting Plans often include activities associated with general construction, ground and water works, culvert installation, long-term monitoring, etc. Costs associated with these Fish Offsetting Plan activities can be subject to individual cost estimates based on a proponent’s experience and can also be scrutinized with limited referenceable sources. This type of subjective cost estimation and review creates risk and introduces uncertainty, for both proponents and liable governmental parties (DFO and ECCC). DFO believes this update to the RECLAIM model is an excellent opportunity and the appropriate location to include constrained cost estimates for these types of activities. DFO would like to discuss this further with CIRNAC and the GNWT during the week of May 12 - 16, 2025. DFO would also be interested in hearing feedback from all interested parties. | DFO recommends that the RECLAIM Model include in a Summary line item, and associated sheet in the Excel model specific to the implementation of a fish Offsetting Plan. This could include, but not limited to works associated with discipline specific construction, ground and water works, culvert installation, and long-term monitoring. Adding this to the model would reduce financial risk by providing a more predictable process of securing a Fish Offsetting Plan, which is ultimately tied to the final reclamations of a mine site that has impacted fish and fish habitat. DFO would like to discuss this possibility with CIRNAC, the GNWT, and all interested parties during this update of the RECLAIM model. | Policy | RECLAIM is a tool for calculating environmental liablity. The financial implications of offsetting are beyond the scope of the RECLAIM tool. CIRNAC, with the support of GNWT, may look into this as part of its mine site reclamation policy update.
| 1 | Diavik Diamond Mines (2012) Inc. - Sean Sinclair | 1 | General | DDMI appreciates the opportunity to take part in this important review process. Since receiving preliminary feedback at the January 23rd, 2025 engagement session, DDMI understands that on February 18th, 2025 and on March 11th, 2025 the RECLAIM v8.0 team uploaded additional information to explain the rationale for some proposed changes to the model. DDMI has not yet been able to review all posted materials. DDMI also understands the RECLAIM v8.0 team will be providing further additional information including but not limited to a jurisdictional scan to support this review process. This complete set of information will inform ongoing collaborative discussion on this proposed update. | Given the complexity and importance of this review process DDMI recommends that the review timeline allows for thorough review and analysis of all information. DDMI is pleased to see the initial extended engagement process proposed by CIRNAC and GNWT and DDMI recommends the next steps for the RECLAIM v8.0 review process are discussed in detail and agreed at the GNWT and CIRNAC in-person workshop the week of May 14th, 2025. | Policy | The Working Group extended the intial commenting period deadline to March 31, 2025 and added two addtional commenting period deadlines of May 30, 2025 and August 15, 2025. Upcoming workshop dates were discussed at the in-person meeting the week of May 14th, 2025 in Yellowknife.
| 2 | Diavik Diamond Mines (2012) Inc. - Sean Sinclair | 2 | General | An initial review of the proposed changes to the RECLAIM model suggest that its application could have a very significant increase on securities. Current proposed changes are focussed on: 1) increased unit rates, 2) increased indirect costs, 3) increased owners costs, 4) increases regulatory costs, 5) increased mobilization and ICM costs, and 6) a future value calculation without corresponding discounting. | DDMI recommends this review process also consider changes focussed on: 1) incentivizing progressive reclamation, 2) managing the return of security process, 3) managing the security holdback process, 4) consideration of financial mechanisms to provide security as a function of both the liability and asset value, and 5) risk associated with a proponents commitment to orderly closure of the site including its financial and technical capacity to carry it out. | Policy | The Working Group appreciate the comment and recommendation but note that these recommendations expand the scope of the model update into larger policy discussions. All of the topics presented by DDMI are important for further discussions with industry, IGIOs and the regulatory boards of the North. However, it is preferred that current engagement and discussions be focused on specific updates to the model and corresponding manual. The Working Group commit to further discussions with DDMI on these topics in the immediate future. 1. CIRNAC and GNWT recognize progressive reclamation as a critical tool for minimizing final closure liabilities and improving long-term environmental outcomes. The updated policy framework development (to happen outside RECLAIM update process) will explore milestone-based security release mechanisms, aligned with independent verification and clear performance standards, to encourage timely and high-quality progressive reclamation activities during operations. 2. CIRNAC and GNWT are committed to improving clarity, transparency, and timeliness in the process for returning securities following closure milestones. Future guidance will establish standardized criteria and timelines for the partial and full return of securities, contingent on demonstrated success of reclamation and closure activities. 3. To ensure financial coverage of potential residual risks post-closure, CIRNAC and GNWT will maintain a security holdback provision. However, the criteria, amount, and duration of holdbacks will be further defined in the forthcoming policy update, with input from co-management boards, Indigenous governments, and industry to ensure both risk mitigation and fairness. 4. While CIRNAC’s priority remains ensuring full financial coverage of environmental liabilities, it is open to exploring financial security instruments that also reflect a project’s asset value and proponent’s demonstrated financial strength. Comparative jurisdictional analysis will inform whether and how such mechanisms can be safely integrated into federal policy, without compromising the Crown's protection from unfunded liabilities. 5. CIRNAC is open to exploring the concept of risk-based security evaluations which do not only consider the scale of environmental liability but also the proponent’s financial and technical capacity to carry out orderly closure. To this end, future updates to CIRNAC’s mine reclamation policy will include the establishment of working groups to examine how proponent risk profiles—including track record, regulatory compliance history, and financial strength—can be systematically incorporated into security determination frameworks. This exploration will be guided by the following principles: any risk-based adjustments must not compromise the Government of Canada's ability to secure full funding for mine site reclamation under all scenarios, including proponent insolvency or abandonment; risk assessment methodologies must be clearly defined, evidence-based, and consistently applied across jurisdictions and project types; the framework will be informed by comparable models used in other Canadian jurisdictions and international benchmarks that balance environmental protection with investment certainty.
| 1 | Environmental Monitoring Advisory Board - EMAB | 1 | Evaluate RECLAIM estimates versus actual expenditures | EMAB's view is that the cost of mine closure should be borne by the proponent, not the taxpayer. The comment on p. 1 of the CIRNAC review that "However, it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." raises a major concern. Security should cover the entire cost of closure, and RECLAIM should calculate security that meets the full cost of closure. | CIRNAC/GNWT should carry out a quantitative evaluation of how much current RECLAIM estimates differ from actual expenditures. | Policy | The Working Group have carried out this quantitative analysis. RECLAIM 8.0 estimates are lower than the actual expenditures of historical abandoned mine closures.
| 2 | Environmental Monitoring Advisory Board - EMAB | 2 | Depositing waste rock in open pit | Some mines have included depositing waste rock into open pits as a means of disposal. This activity does not appear to be addressed in the RECLAIM manual or tables. | Expand tables, and manual, to include placing waste rock and other materials, into open pits. | Unit Rates | Yes this can be added or can be entered manually into the RECLAIM tool.
| 3 | Environmental Monitoring Advisory Board - EMAB | 3 | Revegetation | The reference tables for vegetation include hydroseeding and tree planting. This is a good start, but the range of activities should be expanded to include all activities required for successful revegetation. | Reference tables for vegetation should also include application of amendments and planting of container forb seedlings as well as other activities required for successful revegetation. | Unit Rates | The RECLAIM Tool is not an exhaustive list of reclamation activities. Add Other Specific if not there already
| 4 | Environmental Monitoring Advisory Board - EMAB | 4 | Long-term maintenance and monitoring | Traditional Knowledge Monitoring by members of Affected Communities is an important component of ensuring successful closure and future use of the area affected by the mine for cultural activities by the Indigenous people who live in the area and use it. | Add Traditional Knowledge Monitoring to the list of post-closure activities. | Policy | Traditional knowledge (TK) monitoring is an essential consideration for the successful closure of a site. However, there are not enough standard practices or costs associated with this activity that could be applied to a general costing tool, such as RECLAIM. Typically, these costs are site-specific and developed as part of IBAs or agreements with proponents and IGIOs. TK monitoring would be considered in a review of the closure plan submitted to the applicable northern regulatory board, which would direct parties to consider if TK monitoring costs should be added to a site-specific security estimate.
| 5 | Environmental Monitoring Advisory Board - EMAB | 5 | Long-term maintenance and monitoring | EMAB was pleased to see the expansion of the Mobilization sheet to include construction and use of winter roads for both mobilization and demobilization. It is not clear whether this is intended to cover mob/demob for post-closure maintenance. Once the mine closes there is no guarantee that the winter road will continue to exist. If there is a significant maintenance requirement, there may be a need to build a winter road to mobilize heavy equipment etc., and to demobilize it after the maintenance is completed. | Include the cost of building a winter road to the mine as part of long-term maintenance, if this is the only means for mobilizing/demobilizing heavy equipment required for maintenance. Costing should include building the winter road for the following season to demobilize heavy equipment. | Unit Rates | Cost for annual maintenance of roads, where applicable, should be factored into the overall costs but on a site by site basis.
| 6 | Environmental Monitoring Advisory Board - EMAB | 6 | Long-term maintenance and monitoring | Post-closure monitoring activities may require air transportation to and from the site, which could involve use of the airstrip. In order to use the airstrip it will need to be maintained until all monitoring is completed. | Include costs to maintain the airstrip until post-closure monitoring is completed. | Unit Rates | Yes this will be consider and discussed at the upcoming engagement workshop.
| 7 | Environmental Monitoring Advisory Board - EMAB | 7 | Long-term maintenance and monitoring | The scope of post-closure maintenance activities includes cover maintenance and spillway maintenance. Maintenance could include other components such as tailings dams, discharge channels, revegetation, or emergency or ongoing water treatment; so the list should be expanded to provide for these and other potential maintenance activities. | Expand the scope of post-closure maintenance activities to include dams and discharge channels, revegetation maintenance, and a category for other potential maintenance requirements. | Unit Rates | Agreed – to be discussed at the upcoming engagement workshop
| 8 | Environmental Monitoring Advisory Board - EMAB | 8 | RECLAIM User Manual | The User Manual will need to be updated to reflect all changes and additions to the RECLAIM tables. | Ensure the RECLAIM User Manual is updated to provide clear explanations of all the activities and changes to the tables. | User Manual | The User Manual will reflect the changes.
| 1 | Independent Environmental Monitoring Agency - Jamie Mistry | 1 | Post Closure – Annual Requirements | The Post-Closure sheet requires an estimate of annual costs and the number of years of post closure activities. The overall sum of activities is then multiplied by the number of years to give a total cost. Some post-closure activities will likely occur less frequently than annually, and the spreadsheet calculation will not function correctly in these cases. | Revise the Post-Closure sheet to include columns that list the frequency of each activity, and the number of events expected over the post-closure period, rather than assuming that all costs are annual costs. | Unit Rates | To be discussed at the upcoming engagement workshop
| 2 | Independent Environmental Monitoring Agency - Jamie Mistry | 2 | ICM – Water Management | The ICM sheet does not include activities specifically focused on water management during interim care-and-maintenance. These costs are also not specifically addressed in the Water Management or Water Treatment sheets. However, water management is often (perhaps usually) a primary focus of interim care-and-maintenance activities at mine sites, including during temporary closures and in the early stages before active implementation of a closure and reclamation plan. Requirements for accessing security bonds typically arise when there is an early, unplanned mine closure. In these circumstances water management is likely to be a significant activity for maintaining water levels in tailings ponds, managing flood flows, managing runoff from disturbed areas, and dewatering of mines (pits and underground). It is not uncommon for dewatering of mines to continue during periods of interim care-and-maintenance, especially in the event of early/unplanned closure when there may be interest in selling the project – allowing mines to flood is often considered to devalue the “asset” and therefore is part of the necessary care-and-maintenance activities. While there are currently no heap leach projects in NWT, water and solution management at heap leach mines is likely to be the largest cost during periods of interim care-and-maintenance. | Revise the ICM sheet to include activities focused on water management that will be required during interim care-and-maintenance. | Unit Rates | The costs for water treatment during ICM are covered on the Water Treatment worksheet. The ICM worksheet references the worksheet where the costs are calculated. Considering an update to formatting for clarity. Listing "Water Treatment" as the Activity, and then under Notes pointing the user to the tab "ICM Water Treatment" being referenced. To be discussed at the upcoming engagement workshop.
| 3 | Independent Environmental Monitoring Agency - Jamie Mistry | 3 | Interim Care-and-Maintenance | The Supplementary Information states that the default interim care-and-maintenance period in RECLAIM is 2 years, but the Interim Care-and-Maintenance (ICM) sheet in the model sets the value at 3 years. Past experience indicates that, in the event of early/unplanned mine closure, interim care-and-maintenance periods can be lengthy because of the time required to sort out financial matters, explore sale/re-opening options, complete CRP development/permitting and procure contractors. 3 years should be the minimum period applied. | Clarify the default duration of interim care-and-maintenance as 3 years, as currently applied in the model. | Unit Rates | Noted - the default ICM phase will be consistent at 5 years.
| 4 | Independent Environmental Monitoring Agency - Jamie Mistry | 4 | Water Management - Sediment/Erosion Management and Control | The Water Management sheet addresses closure and reclamation of operational sediment control facilities. However, it does not directly address the potential need for continued sediment control measures during reclamation activities, or after reclamation activities are complete. This could require construction of new sediment control facilities or improvement (e.g., expansion, armouring) of existing ones. It could also require ongoing operational activities to manage sediment. | Revise the Water Management sheet to include lines related to development and implementation of sediment control measures for the closure and post-closure periods. | Unit Rates | A new Activity may be added to allow for the maintenance of sediment control facilities. To be discussed at the upcoming engagement workshop. Web search - 1000-5000 annually for small facilities (dry pond example), increasing with more complex Sites
| 5 | Independent Environmental Monitoring Agency - Jamie Mistry | 5 | UG Mine – Contact Water Management | The UG (Underground) Mine sheet does not include costs for treatment of mine water. The sheet appears to assume that underground mines will be flooded but no treatment would be required. Some mines may fill and drain over time, with water quality that is not acceptable for discharge. In other cases, leakage from the mine through groundwater is possible, again raising possible water quality concerns. These conditions may require some measures for ongoing or periodic water management or water treatment, including possible active or passive treatment outside of the underground mine, or some form of mine-pool treatment within the mine. | Add water management and treatment as potential costs in the UG Mine sheet, linked as appropriate to additional content in the Water Treatment sheet. | Unit Rates | Disagree. The cost for water treatment are captured in the Water Treatment worksheet. This sheet is not specific to a mine feature and could be used for water treatment related to the underground mine, waste rock storage areas, tailings, heap leach pads, etc.
| 6 | Independent Environmental Monitoring Agency - Jamie Mistry | 6 | Chemicals – Soil Handling | The Chemicals sheet includes costs for excavating contaminated soils and transporting them to an onsite remediation facility, for example a land-farm. There will also be costs for rehandling these soils to a final disposal location at the conclusion of land-farming. | Revise the Chemicals sheet to include lines for final disposal of remediated soils. | Unit Rates | The updated version may include a disposal cost for remediated soils. This will be discussed at the upcoming engagement workshop. Note this appears to comprise ~two unit rate line items depending on disposal location: ex. excavate+long haul and disposal tipping fee etc.
| 7 | Independent Environmental Monitoring Agency - Jamie Mistry | 7 | Post Closure – Maintenance | The scope of maintenance activities described in the Post Closure sheet is limited to covers, spillways and wetland treatment systems. For many mine sites, the maintenance requirements will be much more extensive. For example, tailings dams, diversions and sediment control facilities may all require maintenance. Passive treatment systems other than wetlands may also require maintenance or replacement. Wetlands may also require maintenance that is more extensive than what is described, including removal and replacement of substrates and vegetation after some period of time. In most cases, “passive” treatment systems require some periodic maintenance and operational activities, and are therefore better described as semi-passive. | Expand the maintenance components of the Post Closure sheet to address a broader scope of expected maintenance requirements. | Unit Rates | The updated version may include more maintenance activities. This will be discussed at the upcoming engagement workshop.
| 8 | Independent Environmental Monitoring Agency - Jamie Mistry | 8 | Rock Pile – Heap Leaching | According to the manual, the Rock Pile sheet is intended to address not only waste rock piles, but also heap leach facilities. Closure of heap leach facilities is usually substantially more complex than for rock piles. Heap leach facility closure entails continued solution circulation, heap rinsing, heap detoxification and associated water treatment, managed draindown, decommissioning of pumping and piping equipment, establishment of permanent drainage systems, among other things. The activities listed in the Rock Pile sheet are not adequate to address potential heap leach facility closure. | Incorporate specific activities and costing for heap leach facility closure in the model. | Unit Rates | Disagree. This could be added on a site by site basis (user specified activity). The main activities include Cease Leaching (drain and recover as much leach as possible), Rinse and Neutralize, Cover the Heap (low permeability), Drainage and Water Management and long term monitor SW, GW and gas if sulphide oxidation is a concern.
| 9 | Independent Environmental Monitoring Agency - Jamie Mistry | 9 | Bldgs & Equip – Roads | The Bldgs & Equip sheet is missing some activities that may be common for closure and reclamation of roads. Reclamation frequently includes flattening of safety berms along the length of the road, and establishment of effective road blocks and any access points. Also, complete removal of roads back to the native landscape may be necessary in some cases, or overall re-grading of road embankments. Construction or upgrading of drainage works along road alignments may also be required. | Additional road reclamation and closure activities should be added to the Bldgs & Equip sheet. | Unit Rates | Safety berm removal, road block to access points and recontour to natural grade may be added. This will be discussed at the upcoming engagement workshop.
| 10 | Independent Environmental Monitoring Agency - Jamie Mistry | 10 | Mobilization – Annual Mobilization | The Mobilization sheet includes a column for quantity of mobilization with each type of equipment or supply. In some cases, mobilization/demobilization of equipment could be required annually through the closure and reclamation phase, or periodically during post-closure. For transparency, it would be useful to separate the quantity and the number of annual mobilization requirements – e.g., how many dump trucks have to be mobilized to site in each year. This would provide a better understanding of the equipment requirements and costs over time, and information about what equipment would be expected to remain on site year-round, versus mobilization each year. | Revise the Mobilization sheet to separately identify the annual mobilization requirements. | Unit Rates | For the purposes of RECLAIM V8, we assume equipment required for closure would be shipping up and back from the mine . If a site specific closure plan requires additional mobilizations, this should be documented and budgeted.
| 11 | Independent Environmental Monitoring Agency - Jamie Mistry | 11 | Indirect Costs | The Summary Report and Supplementary Information describe the rationale for proposed changes in the default percentages for indirect costs. The rationale is consistent with experience from mine closure and reclamation projects and with current approaches to engineering. The Summary Report also notes that costs for mobilization and interim care-and-maintenance are now included in the base costs for calculating indirect costs. This also makes sense because both of these costs will be subject to the same indirect costs as the rest of the capital costs. | Retain the proposed default indirect costs percentages and the inclusion of mobilization and interim care-and-maintenance costs as part of the capital cost for calculating indirect costs. | Indirects | Noted. Mobilization was moved back to Indirects
| 12 | Independent Environmental Monitoring Agency - Jamie Mistry | 12 | Summary – Indirect Costs | N/a | The updates to the recommended percentages for indirect costs appear to reflect the experience with mine closure and reclamation projects and should be retained. | Indirects | Noted. Some default percentages were reduced based on discussions in Yellowknife engagement session.
| 13 | Independent Environmental Monitoring Agency - Jamie Mistry | 13 | User Manual – Section 1 | The final bullet in the list of principles in Section 1 of the User Manual states that financial security must retain its full value throughout the life of the mine and if applicable, beyond. The value of required security may vary through the life of the mine and the wording of the principle should be clarified | The final bullet in the list of principles should be reworded to clearly state that adequate security must be in place throughout the life of the mine and in post-closure to fully address the liabilities associated with the site. | User Manual | This bullet point is quoted from the "Mine site reclamation policy for the Northwest Territories (DIAND, 2002a) and Mine site reclamation policy for Nunavut (DIAND, 2002b)"
| 14 | Independent Environmental Monitoring Agency - Jamie Mistry | 14 | Summary – Future Value | The future value calculations appear to assume that the 3 year period of Interim Care-and-Maintenance starts immediately at the time the calculations are completed. This means that if the security amount is set based on today’s calculations, but unplanned closure begins 1 year later, the security will be 3% too low, or 16% too low if closure begins 5 years later. | The potential shortfall in liability estimates caused by assumptions about timing for the start of interim care-and-maintenance should be addressed in the model. One option is to establish requirements for frequent adjustments of security (e.g., every 2 years) to account for these shortfalls. | NPV | Costs for ICM and Post Closure monitoring are inflated for based on the Site Specific future value inputs to account for when the activities are proposed. Additional suret comes form reviews as required by the water license. In Tandem these safeguards are felt to be sufficient.
| 15 | Independent Environmental Monitoring Agency - Jamie Mistry | 15 | Summary – Future Value | N/a | The addition of future value is a good idea and should be retained. | NPV | Noted.
| 16 | Independent Environmental Monitoring Agency - Jamie Mistry | 16 | Land Reclamation Activities | In response to a comment/recommendation to include a more comprehensive list of land reclamation activities in the model, the Supplementary Information responds that site-specific activities should be proposed based on end land use and the CRP. The response does not address the comment that was raised. Of course, site-specific closure activities should be defined in site-specific CRPs. However, the model is intended to provide a comprehensive tool for estimating costs of closure and reclamation activities, no matter what activities are selected for a specific site. As a result, the model should include a more comprehensive list of land reclamation activities and provide for estimating their costs, as suggested in the comment. The following comments below identify several specific instances where the model should be revised to include more comprehensive listings of activities. While this is likely not a complete list, it should be considered a starting point for more thoroughly identifying potential closure measures and activities. | Undertake a process to develop a more comprehensive list of possible closure and reclamation activities and incorporate these into the costing model. | Unit Rates | Disagree. Proponent should develop a site specific list of closure and reclamation activities and costs. RECLAIM is not inclusive of all mine closure tasks.
| 17 | Independent Environmental Monitoring Agency - Jamie Mistry | 17 | Water Management - Reclamation Quarries | The Water Management sheet includes costs for installing and removing pumping systems for managing water in a reclamation quarry. Other costs associated with both quarry development (e.g., material testing, land clearing, road development, etc.) and water management (e.g., diversions, sediment control) for reclamation quarries are not addressed. Reclamation activities often require development of new quarries (in undisturbed areas, or in waste [e.g., overburden] storage facilities) or expansion of existing ones to provide the materials necessary for closure and reclamation. | The Water Management sheet should be revised to include lines that address additional water management activities that may be associated with quarries. Costs for quarry development should also be addressed within the overall model. | Unit Rates | Noted - quarry development costs will be considered and may included in the Water Management worksheet. To be discussed at the upcoming engagement workshop.
| 18 | Independent Environmental Monitoring Agency - Jamie Mistry | 18 | Water Management – Passive Treatment | The activities identified for passive treatment are all associated with construction of wetland treatment. There are other forms of passive treatment that may also be relevant, for example permeable reactive barriers, bioreactors or underground mine pool or groundwater treatment. | The Water Management sheet should be revised to include activities that may be associated with other forms of passive treatment that are not wetlands. | Unit Rates | Disagree. Proponent should develop a site specific list of closure and reclamation activities and costs. RECLAIM is not inclusive of all mine closure tasks.
| 19 | Independent Environmental Monitoring Agency - Jamie Mistry | 19 | User Manual – Section 4.2.5 | Section 4.2.5 of the User Manual describes expectations for costing for interim care-and-maintenance activities. The description of a typical scenario states that open pit and underground mines would be allowed to flood. In cases of early or unplanned mine closures (i.e., where there are draws on security bonds), there are often lengthy periods of discussion about mine re-opening and sale. In these cases, mine dewatering often continues in order to avoid reducing the value of a potential asset. The assumption that mine dewatering would be discontinued may underestimate the actual costs that would be incurred. | The default assumption for interim care-and-maintenance costing should be that mine-dewatering will continue for this period. | User Manual | Agreed. Proponents can already propose actual costs for indirects rather than defaulting to the assigned percentages provided in the Tool.
| 20 | Independent Environmental Monitoring Agency - Jamie Mistry | 20 | Future Value and Unit Cost Updates | The Supplementary Information describes the new approach taken for estimating the future value for liability estimates. This approach is a positive addition and attempts to address the challenge that the security bonding regime and the forms of security do not allow for bond amounts to grow to address inflation and other escalation of costs. The User Manual defines “escalation” as “a provision in costs or prices for uncertain changes in technical, economic, and market conditions over time. Inflation (or deflation) is a component of escalation.” This acknowledges that inflation is only one component of escalation, with other components (e.g., labour market conditions in northern Canada, or availability of construction contractors) that may also lead to increases in costs. Nonetheless, the User Manual and model only rely on inflation as a cost escalator when calculating future value (Summary sheet) or for updating unit costs (Unit Cost sheet). Other than in the definition of “escalation” there is little further mention of other possible influences on cost escalation, though Section 4.5.1 of the User Manual does identify some other possible sources of information about escalation. | Revise the User Manual and the model to require consideration of other factors for cost escalation. This should include requirements in the User Manual for proponents to provide rationale for selected escalation factors. In the model, it would be useful to include separate entries for inflation and other cost escalators so that there is a requirement to consider whether other escalators are relevant or not. | NPV | To be discussed at the upcoming engagement workshop
| 21 | Independent Environmental Monitoring Agency - Jamie Mistry | 21 | General Comment – Site Management | The model lacks clear information about person-hours for ongoing administrative responsibilities at the site, for example security, health and safety, personnel management, etc. during the implementation of the closure. Some of these are addressed for interim care-and-maintenance (e.g., on-site caretaker), but would also be required throughout the implementation of closure and reclamation. | Costs for ongoing site management should be addressed either in the Summary sheet, or an additional Site Management sheet should be added. | Unit Rates | Captured in the Project Management Indirects (define in User Manual)
| 22 | Independent Environmental Monitoring Agency - Jamie Mistry | 22 | Water Treatment – Post Closure | The post-closure component of the Water Treatment sheet does not address major maintenance and equipment replacement activities. Water treatment facilities that have to operate in a long post-closure period will wear out and require refurbishment and replacement at some point in time. Costs and timing for these major capital expenditures need to be included. | Revise the Water Treatment sheet to include lines for costs related to major refurbishment or replacement of post-closure water treatment facilities. | Unit Rates | Agreed - the updated version may include maintenance costs.
| 23 | Independent Environmental Monitoring Agency - Jamie Mistry | 23 | General Comment – Labour and Accommodation | Overall, the model does not provide a transparent mechanism to track and understand labour and accommodation requirements. The sheets for each individual component identify the specific reclamation activities that are to be completed. The estimator sheet indicates that costs for equipment operators and other people directly involved in completing the work are included in many of the unit rates. However, there is no clear information in any of the sheets about total person-hours associated with the activities. The costs for accommodation are addressed in the Mobilization sheet, but in the absence of more detailed information about person-hours required for each of the activities, there is no transparency for the basis of accommodation cost estimates. | The model should be revised so that each sheet includes estimates of person-hours for the specific reclamation activities, and these should be used to form the basis for estimates of accommodation costs. | Unit Rates | See responses 24 to 32
| 24 | Independent Environmental Monitoring Agency - Jamie Mistry | 24 | User Manual – Section 1 | Section 1 of the User Manual states a principle that costs should be based on having a third-party contractor carry out the reclamation work. On-site equipment including both mobile equipment and fixed facilities (e.g., water treatment plants) may not be owned by the proponent and costs would be incurred to access the equipment and facilities. | The principle that costs should be based on the cost of having work done by a third-party contractor should be expanded to clarify that the costs must also be estimated assuming that all equipment, supplies and facilities will be provided separately. | User Manual | The Working Group agrees.
| 25 | Independent Environmental Monitoring Agency - Jamie Mistry | 25 | Tailings – Water Treatment | The Tailings sheet refers to treatment of seepage, which may not be the only treatment that is required for a tailings facility. In some cases, treatment of tailings pond supernatant water may also be required, either during implementation of closure and reclamation, or post-closure. | Revise the water treatment references in the Tailings sheet to include broader references to types of treatment that may be required. | Unit Rates | Noted. Will update the reference to "Treatment of Tailings Contact Water". Reference to containment and the prevention of ARD/ML are to be reviewed and included.
| 26 | Independent Environmental Monitoring Agency - Jamie Mistry | 26 | Open Pit – Pit Closure Methods | The Open Pit sheet considers a narrow range of potential closure options for pits, focused on flooding of pits. There are other options for closure of pits that need to be addressed. For example, some pits may be closed in a dry condition, with associated water management, or some may be backfilled with waste and covered (e.g., Giant Mine Remediation Project). | Revise the Pits sheet to address a broader range of closure options for pits. | Unit Rates | Noted. Pit Lake, Dry Cover and Backfilling, Engineered Landform (Geomorphic Reclamation) and all may include Isolation and containment for pits (i.e. grouting) with very high ML/ARD or are planned to store contaminated water
| 27 | Independent Environmental Monitoring Agency - Jamie Mistry | 27 | Open Pit – Contact Water Management | The only water treatment option addressed in the Open Pit sheet is the possible addition of in-pit treatment during flooding – either by chemical or biological means. There is no water treatment line linked to the Water Treatment sheet. However, there are some instances where it may be necessary to actively pump and treat water that has accumulated in a pit, potentially before flooding, or to establish dry conditions. | Add active water treatment as a potential cost in the Open Pit sheet, linked as appropriate to additional content in the Water Treatment sheet. | Unit Rates | Noted - this will be considered for the next draft and discussed at the upcoming engagement workshop.
| 28 | Independent Environmental Monitoring Agency - Jamie Mistry | 28 | HHERA and Regulatory | The Summary Report states that the model was revised to include 3% indirect costs for Human Health and Ecological Risk Assessment (HHERA), and 4% indirect costs to finalize the Closure Reclamation Plan (CRP). These additions make sense, but it is unclear where they are included in the model. If they are already included in the Summary sheet calculations, they should be specifically identified. | Provide additional clarity about where the indirect costs for HHERA and CRP finalization are incorporated into the model. | Indirects | They are included on the ICM worksheet. This is discussed in the User Manual.
| 29 | Independent Environmental Monitoring Agency - Jamie Mistry | 29 | General Comment – Winter Road costs | The Water Treatment and Mobilization sheets include lines for costs associated with use of the winter road. In Water Treatment this appears to be related to site access and reagents, while in Mobilization it is related to equipment, fuel and accommodation (i.e., camp), with a focus on materials that must be brought to site. However, closure for some other components (e.g., buildings, hazardous wastes, contaminated soils) may require shipping off site. Also, it is not clear that winter road costs have been incorporated for all closure and reclamation supplies, for example liner construction materials. These activities may also incur winter road costs. | Where closure and reclamation activities will require off-site shipping or the delivery of supplies to site, sheets should be revised to include lines for winter road costs and other shipping costs. | Unit Rates | Winter road use in captured in the Mobilization worksheet. The Road Maintenance cost is meant to capture onsite road clearing activities which is separate from offsite winter road costs.
| 30 | Independent Environmental Monitoring Agency - Jamie Mistry | 30 | Summary – Future Value | The spreadsheet requires the user to enter timing for “when will post-closure begin”, by entering a number. Some additional clarity should be provided about what this number represents: Is it the number of years from the current time until post-closure, or the number of years between cessation of operations and post-closure, or the number of years after completion of interim care-and-maintenance before post-closure begins, or some other value? If the timing is intended to start at the time that the estimate is made, then the same shortfall issues identified above for the interim care-and-maintenance timing will also apply to the timing for start of post-closure. | Clarify the intended definitions of timing for when post-closure will begin. | Unit Rates | More definitions and instructions will be incorporated into the User Manual.
| 31 | Independent Environmental Monitoring Agency - Jamie Mistry | 31 | User Manual – Section 2 | Section 2 of the User Manual describes special considerations for estimating costs for reclamation activities in northern settings. One important factor that appears to be missing is the potential cost implications of meeting requirements for northern participation in contracting and work opportunities. | The bullet list of factors that may affect costs for projects in northern settings should be expanded to include the potential for increased costs associated with meeting requirements for northern participation in reclamation activities. | User Manual | Engagement and Regulatory compliance costs have been included in the RECLAIM tool.
| 32 | Independent Environmental Monitoring Agency - Jamie Mistry | 32 | Buildings & Equipment (Bldgs & Equip) – Landfill | The Bldgs & Equip sheet addresses closure of landfills (e.g., placement of cover material) but it does not cover the cost of constructing a landfill. Even for non-hazardous materials, construction of landfills can be a substantial cost. Landfills developed and used during mine operations typically do not have capacity to contain all of the material arising from closure and reclamation. Costs for non-hazardous landfill construction can be substantial in some cases (e.g., Giant Mine). | Revise the Bldgs & Equip sheet to include costs for development and construction of landfills. | Unit Rates | To be discussed at the upcoming engagement workshop
| 1 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 1 | Owners Representative Cost | Costs for the Owners Representative are included at a rate of 8% of the total capital costs estimate. This appears to be a duplication of costs associated with Engineering Design (8%) and Project Management (10%). | Suggest removing the Owners Representative line item in the Indirect Costs summary or reducing the default factor to 2% of Capital Costs or providing a description and basis for this percentage and how it differs. | Indirects | Owners costs are separate from PM costs. See other responses.
| 2 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 2 | Human Health and Ecological Risk Assessment | Human Health and Ecological Risk Assessment (3% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | Indirects | Agreed - this was corrected
| 3 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 3 | Finalize Closure and Reclamation Plan | Finalize Closure and Reclamation Plan (4% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | Indirects | Agreed - this was corrected
| 4 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 4 | Unit Price Cost References are not Regional | There do not appear to be any references to NWT or Nunavut specific unit costs in UR-Short list in workbook RECLAIM 8 Reference Tables_WorkingCopy.xlsx | Suggest that V8 include reference to northern unit price equivalents. | Unit Rates | There are no dedicated equipment and rental rates guide for NWT or Nunavut. Common practice is to use guides from other jurisdictions. Labour rates were marked up 1.35 times to account for northern wages.
| 5 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 5 | Remediation | There are no referenced unit prices for remediation of any sort – bioremediation and landfill unit prices do not have any reference or backup. | Add unit prices for standard remediation techniques (e.g. biocell) | Unit Rates | Will include refences based on a web search (landfarming 15-23)(bioremediation 50-130) (offsite treatment such as incineration or landfill 200-1,000) Biopiles: $20,000 to $50,000 per hectare; Landfarming: $5,000 to $20,000 per hectare - https://www.inogenalliance.com/blog-post/how-much-does-it-cost-site-remediation Alt web search - landfarming 50-150/m3, bioremediation 30-250/m3
| 6 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 6 | Land Ownership | The Reclaim Model Version 8.0 does not consider the value of owned land in determining (i.e., reducing) security. | Add consideration for land ownership as a reduction for overall security. | Policy | The Working Group will engage with Imperial Oil Resources to discuss this recommendation to understand the intent better.
| 7 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 7 | Identify Unit Components without a reference for unit price | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Unit Rates | Proponent should obtain site specific costs where unit rate is missing.
| 8 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 8 | Unit Prices different from Price Sources | The unit prices in the Reference Table (TABLE 2: RECLAIM v 8.0 Price Sources, Basis and References) do not always match the unit prices in the RECLAIM 8.0 Unit Cost Table. For example, see the unit rate SB1 for "excavate/load/short haul" $16.27 vs $17.00). | Consider integrating the unit prices basis/reference worksheet into the model to reduce inconsistencies and reduce standalone components. | Unit Rates | RECLAIM V8.0 was rounded - the updated version will not include rounding.
| 9 | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han | 9 | Application of Mining RECLAIM Model feedback into the Oil and Gas RECLAIM Model. | Oil and Gas Producers utilize the "Oil and Gas RECLAIM Model". A similar consultation process should be facilitated for any proposed updates to the Oil and Gas RECLAIM Model. | Conduct a similar consultation and stakeholder engagement process for the Oil and Gas RECLAIM Model 8.0. | Policy | GNWT agrees to the recommendation and will commence a process following the completion of this update.
| 1 | Kivalliq Inuit Association – Luis Manzo | 1 | General comment | The Kivalliq Inuit Association (KivIA), as the responsible DOI, through Security Management Agreement holds 50% of the financial security estimates for Meadowbank, Meliadine and Whale Tail mines Canada holds the other 50%. Therefore, any changes to the RECLAIM financial model must be reviewed and agreed by KivIA. | N/A | Policy | Changes to the environmental liability calculated, where Inuit Owned Land is involved, must be reviewed and agreed to by the corresponding RIA.
| 2 | Kivalliq Inuit Association – Luis Manzo | 2 | General comment | The timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site needs to be explained. | The KivIA requests that CIRNAC explain the timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site. | Policy | CIRNAC contaminated sites will contact KIA directly to discuss further.
| 3 | Kivalliq Inuit Association – Luis Manzo | 3 | General comment | Project or mine’s asset value to a company. Will CIRNAC consider the asset value of an advanced project or mine as part of the initial financial security. | The KivIA requests that CIRNAC explain if there would be consideration of the asset value of an advanced project or mine as part of the initial financial security. | Policy | At present, CIRNAC’s policy framework prioritizes ensuring that the full estimated environmental liability of a project is secured independently of a proponent’s asset value or projected revenues. This approach is rooted in the principle of “polluter pays” and is designed to ensure the Crown is not exposed to unfunded reclamation costs, particularly in scenarios of financial distress or project abandonment. However, CIRNAC is open to further policy exploration and stakeholder engagement on how asset value and financial capacity may be integrated into a risk-based security model, provided: the primary security obligation remains linked to the full cost of reclamation; the value of assets considered is verifiable, liquid, and sufficiently tied to the project; appropriate safeguards are in place to mitigate risks of under-securing, especially during market downturns or corporate restructuring. CIRNAC will further examine this option as part of the broader reclamation policy modernization effort. Future policy direction will be informed by a comparative analysis of practices in other jurisdictions and discussions with Indigenous governments, territorial partners, co-management boards, and industry.
| 4 | Kivalliq Inuit Association – Luis Manzo | 4 | General comment | What is the procedure for the return of financial security to the proponent? | The KivIA requests that CIRNAC explain the procedure for returning financial security to the proponent. | Policy | In Nunavut, financial security is typically returned in stages based on verified completion of reclamation activities, as outlined in the approved Closure and Reclamation Plan. The proponent must submit a formal request, followed by an inspection to confirm that environmental objectives have been met. Regulatory boards or CIRNAC assess the request and authorize full or partial return accordingly. Final release typically occurs after all closure obligations, including any long-term monitoring, are fulfilled and verified.
| 5 | Kivalliq Inuit Association – Luis Manzo | 5 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | The changes made to the direct costs need to reflect each individual project/mine site. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that direct costs will need to be project specific versus “one cost fits all” with a range of costs being a more appropriate approach. | Unit Rates | Noted. Direct costs will need to be project specific versus “one cost fits all” with a range of costs being a more appropriate approach. The Tool is a starting point for assessing liabilities at a mine.
| 6 | Kivalliq Inuit Association – Luis Manzo | 6 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References -Excavation costs. | Excavation costs for load/haul/place for excavating and spreading rock and soil show significant increases from RECLAIM 7.0 to RECLAIM 8.0. Using known operating costs from a northern gold mine calculated in RECLAIM 7.0 and comparing these costs to the proposed rates in RECLAIM 8.0 the costs for load/haul/place for excavating and spreading rock and soil have increased by 50% to 430% (see Table 2 attached). In addition, the RECLAIM 7.0 costs included drill and blast which the RECLAIM 8.0 costs do not. However, without any detail provided on how the Civil Est. Tool calculates the RECLAIM 8.0 costs it is not possible to evaluate these cost differences. | The KivIA requests that CIRNAC and their engineering consultants provide the detail on how the Civil Est. Tool calculates the RECALIM 8.0 excavation costs. | Unit Rates | Drilling, blasting and screening are a new unit cost. Details were already provided on how these costs were developed.
| 7 | Kivalliq Inuit Association – Luis Manzo | 7 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | Will an inflation factor be used. Will this factor be applied to direct costs? Or to Indirect costs? Will an inflation factor be used on the direct costs? Or indirect costs? Over what time period will the inflation facto be reviewed. | The KivIA requests that CIRNAC and their engineering consultants respond to their proposed plan for an inflation factor. | Unit Rates | Future Value is meant to capture inflation. This is applied to Capital costs. CIRNAC and GNWT applied a 3% based on a Canada average.
| 8 | Kivalliq Inuit Association – Luis Manzo | 8 | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Indirect Costs | The changes made to the percentages used for Indirect Costs from RECLAIM 7.0 (31%) to RECLAIM 8.0 (58%). Using the $100M Direct Cost example in Table 2 the changes made to the percentages would result in an 87% increase to the InDirect Costs from $31M to $58M. | A cost increase of 87% is significant and will have a negative impact on the business model used to develop currently operating advanced projects and mines. In addition, a cost increase of this magnitude will have a negative impact on new investment “North of 60”. The KivIA’s comments on the recommended changes make up the remainer of this table (Table 1). | Indirects | CIRNAC acknowledges that an estimated cost increase of this magnitude may have implications for existing projects and future investment in the North. The intent of RECLAIM 8.0 is to improve the accuracy and completeness of closure cost estimates to better protect landowners and the environment. Options to conduct an econ omic modelling of impact RECLAIM updates on the business environment in Nunavut will be presented for consideration by senior management in Summer 2025. A decision on whether to pursue third-party economic analysis will be made following broader consultation with co-management boards, territorial partners, and Indigenous organizations. The option for industry to undertake this review is also available.
| 9 | Kivalliq Inuit Association – Luis Manzo | 9 | RECLAIM 8.0 – User Manual – Indirect Costs – Engineering Design; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engineering Design | The percentage change made to the Engineering Design component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (8%). This should be a range from 5% to 8% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Indirects | In Nunavut, financial security is typically returned in stages based on verified completion of reclamation activities, as outlined in the approved Closure and Reclamation Plan. The proponent must submit a formal request, followed by an inspection to conf
| 10 | Kivalliq Inuit Association – Luis Manzo | 10 | RECLAIM 8.0 – User Manual – Indirect Costs – Project Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Project Management | The percentage change made to the Project Management component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (10%). This should be a range from 5% to 10% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Indirects | The proponent can suggest a different base percentage backed with clear rationale as to why it should be lower or higher.
| 11 | Kivalliq Inuit Association – Luis Manzo | 11 | RECLAIM 8.0 – User Manual – Indirect Costs – Engagement and Regulatory Compliance; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engagement and Regulatory Compliance | The Engagement and Regulatory Compliance component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (3%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2)the cost information that was used to determined that this new category would cost $3M per every $100M of financial security. | Indirects | 1) Project Management costs are for the contractor doing the work. 2) Yes, that is correct.
| 12 | Kivalliq Inuit Association – Luis Manzo | 12 | RECLAIM 8.0 – User Manual – Indirect Costs – Contingency Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Contingency | The percentage change made to the Contingency component of Indirect Costs from RECLAIM 7.0 (20%) to RECLAIM 8.0 (25%). This should be a range from 15% to 25% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Contingency | Contingency will be based on engineering design and completion, environmental performance, compliance and non-compliance, stage of development. Refer to manual for details.
| 13 | Kivalliq Inuit Association – Luis Manzo | 13 | RECLAIM 8.0 – User Manual – Indirect Costs – Owners Representative; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Owners Representative | The Owners Representative component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (8%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2) the cost information that was used to determined that this new category would cost $8M per every $100M of financial security. | Indirects | 1) This cost is for government to hire an engineering firm to provide technical services and to oversee the construction team. 2) Yes, that is correct
| 14 | Kivalliq Inuit Association – Luis Manzo | 14 | RECLAIM 8.0 – User Manual – Future Value calculations: Summary Report: Proposed Changes to RECLAIM Version 8.0 – Future Value calculations | It states that the Future Value calculations will capture Closure and post-Closure activities and that a default inflation rate of 3% will be applied. Will there be an annual or a multi-year review of the inflation rate in order to adjust the financial security. | The KivIA requests that CIRNAC and their engineering consultants provide the timeline over which the inflation rate will be reviewed (ie. Annually review? Multi-year review?). | NPV | CIRNAC commites to providing further clarification on the inflation rate calculation in the User Manual.
| 15 | Kivalliq Inuit Association – Luis Manzo | 15 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet; Table 1 – Basis of Unit Rates Development | It states that “The below references are used in unit rates development -Published data sources”. All the published data sources used are from southern Canada. Are there any “North of 60” data sources? Are there any permafrost related data sources? Also, are these labour and contractor rates union or non-union rates? | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) northern data sources or explain why these cannot be provided. 2) Are the labour and contractor rates union or non-union rates. | Unit Rates | 1) There are no Bluebook or Rental guides for the NWT or Nunavut 2) Non-union Rates
| 16 | Kivalliq Inuit Association – Luis Manzo | 16 | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References – column Price Base/References | In the column for price Base/References several price references are either Civil Est. Tool or Historical Database. For transparency and ensuring a proper evaluation of costs by all intervenor’s full disclosure of all price references is necessary. | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) the details of the Civil Est. Tool. 2) the Historical Database. | Unit Rates | 1) Details were provided such that another costing team could build their own rates. 2) Costs were derived from work done at other mines and is therefore not public information
| 17 | Kivalliq Inuit Association – Luis Manzo | 17 | RECLAIM 8 Model Working Copy – Excel Sheet; Instruction Tab – Conditions of Use | It states that “This model is not intended to dictate how much should be spent on reclamation.” What is the purpose of this financial model if it is not supposed to dictate how much should be spent on reclamation by the proponent? Is it possible that if a proponent disagrees with CIRNAC’s final dollar amount created by this model that the proponent could set their own financial security? | The KivIA requests that CIRNAC: 1) provide clarity on the purpose of the RECLAIM financial model. 2) provide clarity on the proponents responsibility to adhere to the final dollar amount calculated by the RECLAIM financial model. | Policy | 1) RECLAIM is a tool to calculate environmental liability. 2) The RECLAIM model provides an evidence-based estimate to inform the amount of liability for site reclamation. While the final dollar amount calculated by RECLAIM is subject to regulatory review and approval by the appropriate land and water board, proponents are expected to adhere to the approved financial security amount as a condition of their licence or permit. This amount is enforceable and may be adjusted over time to reflect project changes or updated closure plans.
| 18 | Kivalliq Inuit Association – Luis Manzo | 18 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Fuel and Electricity | Fuel costs for gas and diesel are listed. No fuel costs for Jet A, Jet B or Av gas are included. | The KivIA requests that CIRNAC and their engineering consultants provide fuel costs for Jet A, Jet B and Av gas. | Unit Rates | This may be added based on discussions at the planned workshop
| 19 | Kivalliq Inuit Association – Luis Manzo | 19 | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Mobilize Workers (round trip) | Hourly costs for small, medium and heavy helicopters. Are these hourly costs “dry” (do not include fuel cost) or “wet” (do included fuel cost). | The KivIA requests that CIRNAC and their engineering consultants determine if the hourly costs for small, medium and heavy helicopters are “dry” or “wet”. | Unit Rates | Typically wet for small and medium but dry for heavy
| 20 | Kivalliq Inuit Association – Luis Manzo | 20 | RECLAIM 8 Model Working Copy – Excel Sheet; Estimator Tab – Excavator Ratings | The cycle times and productivity for excavators are based on southern Canadian conditions (ie. digging in sandstone and caliche; non-Arctic conditions). There is no reference to permafrost or Arctic conditions for the cycle times and productivity for excavators. | The KivIA requests that CIRNAC and their engineering consultants determine what changes to the cycle times and productivity for excavators will occur in permafrost and Arctic conditions, in particular, metal fatigue under extremely cold conditions (ie. > -40oC). | Unit Rates | Reclamation activities would be targeted for summer months with a prolonged schedule. Winter work could have significant impacts on cost.
| 1 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 1 | Increased Unit Costs | Please see initial feedback in the attached letter. The justification for increased excavation and hauling costs (e.g., short-haul soil movement increasing from $4.3/m³ to $17/m³) lacks transparency on how these figures were derived. What specific contractor quotes, productivity rates, or haul distances were used in these calculations? Were regional variations considered, or was a blanket rate applied regardless of site-specific factors? Can industry propose alternative short-hauling costs based on regional/site-specific factors such as terrain, available borrow pits, road conditions, access to rail, and equipment availability? For example, a mine site with established all weather and paved road networks and short, efficient haul routes may have significantly lower hauling costs than a remote site requiring seasonal ice road access. Will proponents have flexibility in presenting alternative cost estimates to justify lower unit costs? | N/A | Unit Rates | Refer to User Manual & Tables 1 and 2
| 2 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 2 | Higher Indirect Cost Percentages | Questions Asked Contingency Increase (20% to 25%): While uncertainty exists in closure planning, what empirical data justifies a 25% contingency rather than the previous 20%? Can examplesof cost overruns from past projects be provided to support this increase? Engineering Design (5% to 8%) & Project Management (5% to 10%): These increases suggest significantly greater complexity in closure execution. What historical data from northern mine sites demonstrate that these cost assumptions are necessary? Bonding/Insurance (1% to 3%): Can specific case studies or actuarial assessments be provided to validate this change? | N/A | Indirects | Sliding scales based on Life of Mine for engineering design and Owners Rep. Other factors to consider include Environmental Performance and Progressive Reclamation
| 3 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 3 | Reclassification of Mobilization and Interim Care & Maintenance (ICM) as Capital Costs | Moving these costs to Capital Costs now subjects them to contingency and indirect cost multipliers. How does this align with the principle of accurately reflecting third-party contractor costs? Industry projects varying durations of ICM depending on site conditions. How was the assumption of a minimum 3-year ICM period determined, and why is it being applied universally? | N/A | Indirects | Blue Book cost include ownership costs (depreciation, insurance) and Operating Costs (fuel, lube, tires, etc.) and do not include Indirect Costs (overhead, PM, Mob, Mark-up, etc.) Posted ICM can be low based on recent examples in Yukon.
| 4 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 4 | Owner’s Representative Cost (10% of Direct Costs) | This is a new addition to RECLAIM. While we acknowledge the role of an Owner’s Representative in some government-managed projects, why is this now mandated for all projects, including those with active operator management? Can industry proponents provide alternative methodologies for project oversight rather than defaulting to a 10% additional cost? | N/A | Indirects | Yes, Default percentage is negotiable based on life of mine phase. User Manual to be updated to define.
| 5 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 5 | Human Health and Ecological Risk Assessment (HHERA) Cost (3% of Capital Costs) | Industry already conducts environmental monitoring as part of regulatory requirements. What additional studies are being assumed under this cost, and how is the 3% figure justified? Given that mines with comprehensive monitoring programs may already demonstrate minimal risk, why is this cost not applied selectively based on site-specific needs? Can proponents outline their monitoring programs and propose a more phased cost-structure alignment with project-specific timelines? | N/A | Indirects | An HHERA assess the actual risks to receptors and defines what areas of the Site require remediation. The ENV monitoring assess the site against predicted values which is not the same. The Working Group is unclear on third recommendation and cannot respond to it at this time.
| 6 | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm | 6 | Future Value Calculation (3% Inflation Rate) | While inflation is a factor in cost projections, applying a fixed 3% escalation rate does not account for fluctuating economic conditions. Has any sensitivity analysis been conducted to assess alternative inflation scenarios? Can proponents propose their own escalation methodologies based on contractual arrangements and project-specific timelines? | N/A | NPV | A detailed sensitivity analysis was not completed. The 3% escalation rate is being proposed as the default starting point.
| 1 | Qikiqtani Inuit Association – Conor Goddard | 1 | Updated Unit Rates | Understanding unit rates are based on first principles; however further detail on unit rate development and assumptions is required. For Example. Load and haul costs have been split into ‘short haul’ and ‘long haul’; however, there is no detail on what haul distance constitutes a short vs. long haul. To provide greater accuracy in haulage costs, specific unit rates should be calculated based on the actual haul distance between stockpiles and the facility being reclaimed. Dozer equipment rates are classified as either ‘small’ or ‘large’ scale equipment; however, no detail is provided on what is classified as a large dozer. This results in greater uncertainty in which equipment rate should be used when calculating equipment costs. | N/A | Unit Rates | Additional details were provided in the follow up memorandum. Short haul and long haul are defined in Table 2: RECLAIM v 8.0 Price Sources, Basis and References. This could be defined in the user manual but a decision was made to keep the details out of the text portion of the manual for ease of future updates. These unit rates could be used as a starting point but should be refined based on actual mine closure and reclamation plans and site conditions. Dozer unit rates were escalated from RECLAIM 7.0. It was assumed large dozers would be utilized given the scale of work. The cost per cubic meter depends on several factors including fuel costs, labour, maintenance and efficiency. On average large dozers (D10/D11 Class) range in price from 1.50 to 3.50 per cubic meter. However, in remote Arctic operations the costs can be 20 to 50% higher. The range for dozing in RECLAIM 8.0 is $1.52/m3 to $6.08/m3
| 2 | Qikiqtani Inuit Association – Conor Goddard | 2 | Increased Indirect Percentages | An alternate methodology for calculating indirect costs should be provided. For example, engineering design could be estimated to be 8% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outlined in the reclamation and closure plan. This would allow engineering costs to depend on the level of project definition and the work to be completed. This incentivises further project definition within closure designs earlier in the life of project. | An alternate methodology for calculating indirect costs should be provided. | Indirects | Agreed. Proponents can already propose actual costs for indirects rather than defaulting to the assigned percentages provided in the Tool.
| 3 | Qikiqtani Inuit Association – Conor Goddard | 3 | Mobilization and Interim Care and Maintenance as Capital Costs | Mobilization / demobilization of equipment is typically considered as an indirect cost when it is being calculated as a percentage of direct costs. As RECLAIM calculates mobilization / demobilization costs directly, Okane supports its inclusion as a direct cost such that contingency can be applied. If mobilization / demobilization costs change to being calculated based on percentage, Okane does not support it being included as a direct cost. | Okane recommends mobilization / demobilization to be calculated via percentage of direct costs, similar to other Canadian jurisdictions. The quantity of equipment, and therefore the cost to mobilization / demobilization equipment, is tied to the reclamation timeframe and schedule. In the event of sudden closure, CIRNAC may implement closure activities on an alternate timeframe than what is outlined within the closure plan. | Indirects | RECLAIM calculates mobilization / demobilization costs directly such that contingency can be applied. Mobilization moved back to indirects. NOTE: Adding other percentage based indrects such as PM, Owners Rep to mob costs may over secure the government as mob doesn't directly cause extra burden on these tasks.
| 4 | Qikiqtani Inuit Association – Conor Goddard | 4 | Owners Representative | Okane supports the costing of an Owners Representative within closure cost estimates. However, Okane is interested in the percentage used for determining this cost. In comparison, the updated project management cost of the entire reclamation phase is estimated to be 10% and includes costs for project coordination, accounting and project control, quality assurance/quality control and oversight, change orders and as-built reports. Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Indirects | A range could be used and described on the Users Manual. Default percentages were lowered. Refer to manual for guidance.
| 5 | Qikiqtani Inuit Association – Conor Goddard | 5 | HHERA and Finalize CRP | An alternate methodology for calculating HHERA and CRP costs should be provided. For example, finalizing the CRP could be estimated to be 4% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outline in the reclamation and closure plan. This would allow the costs for finalizing the CRP depending on the level of project definition and the work to be completed. | An alternate methodology for calculating HHERA and CRP costs should be provided. | Indirects | Point taken on a scaled plan. Default percentages were lowered. Alternate methods to calculate liability can be discussed at the planned workshop.
| 6 | Qikiqtani Inuit Association – Conor Goddard | 6 | Future Value Calculation | Okane supports the consideration of future valuation with respect to years associated with ICM; however, does not agree on how it is being represented within RECLAIM with respect to post closure activities and the removal of net present value calculations as outlined in the virtual engagement session. While inflation can add considerable costs to reclamation, solely accounting for inflation does not capture the true costs and value of money. | Okane would recommend included inflation within a real discount rate to be used within a net present value analysis | NPV | The FV costs was added as the held security as interest is not being made. To ensure the appropriate funds are available at the time of construction an inflation factor based on CPI was added. Set timeframes for security reviews, timed with license renewals could be considered. Furthermore, Discount Rates are not appropriate when projecting actual dollars spend in the future.
| 7 | Qikiqtani Inuit Association – Conor Goddard | 7 | Detail for Unit Rates | Although RECLAIM provides a list of potential closure activities for each facility, it lacks the level of detail required to understand how these activities have been costed and relies strictly on unit rates and lump sum estimates. | To improve transparency and accuracy withing closure cost estimates, more inputs should be provided to show how that activity is being costed. Specifically, within post-closure activities such as monitoring the current RECLAIM model only provides an annual lump sum input for a monitoring activity. To improve transparency, it should provide more detail such as sampling/monitoring frequencies, number of sampling locations, analytic costs, reporting, etc. | Unit Rates | Annual costs are reported in RECLAIM. It is up to the proponent to detail the costs for each site. There are too many options and site specific factors to create a one size fits all. The User Manual can provide some details on what is expected.
| 8 | Qikiqtani Inuit Association – Conor Goddard | 8 | Post-closure monitoring and maintenance contingency | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. Post-closure maintenance activities are not excluded from having uncertainty and a contingency should be applied within this cost category. Specifically, activities such as long-term water treatment which is tied closely to geochemistry which typically carries large uncertainty. | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. | Policy | To be discussed at the upcoming engagement workshop
| 9 | Qikiqtani Inuit Association – Conor Goddard | 9 | Timeframe and Post-Closure Activities | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. There is potential for post-closure monitoring and maintenance activities to extend into perpetuity, such as DSIs, DSRs, and water treatment. What is the expected period of which these activities should be assessed over. | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. | Policy | CIRNAC recognizes the tool could benefit from clearer guidance on timeframes for post-closure activities that may extend into the long term, including water treatment, detailed site investigations, and detailed site reports. While “in perpetuity” is often referenced, the RECLAIM model will be accopmanied by updated guidance recommending that cost estimates for such activities be based on site-specific risk assessments and clearly justified assumptions, typically projected over a 100-year horizon unless evidence supports a shorter or longer duration. This approach aligns with best practices and ensures estimates are both precautionary and defensible. Further engagement on this guidance will occur as the reclamation policy update progresses.
| 10 | Qikiqtani Inuit Association – Conor Goddard | 10 | Discount Rates | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. Okane would welcome guidance on what ‘real’ discount rate should be applied to post-closure activities. | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. | NPV | To be included in the User Manual
| 1 | Teck Metals Ltd. - Dr. Bjorn Weeks | 1 | Feedback Letter | Please see initial feedback in the attached letter. Inflation Application Without Discounting. The RECLAIM 8.0 update proposes incorporating inflation into cost estimates but does not address the standard practice of discounting to reflect the time value of money. Applying inflation without discounting leads to distorted financial obligations, potentially resulting in excessive and unrealistic financial security requirements. Without discounting, even minimal recurring annual costs (e.g., $20,000 per year) would result in infinite bonding requirements, which contradicts financial principles and international best practices. Financial assurance practices that deviate substantially from international best practices may place the region at a competitive disadvantage, while failing to deliver real benefits | N/A | NPV | The Working Group will consider this comment and will update reviewers as part of the upcoming engagement workshops.
| 2 | Teck Metals Ltd. - Dr. Bjorn Weeks | 2 | Feedback Letter | Please see initial feedback in the attached letter. Absence of Any Credit for Company Size and Environmental Performance We believe the bonding requirements should take into account both past environmental performance and the financial resources available to the company to meet its environmental liabilities. Teck is one of several International Council on Mining and Metals (ICMM) member companies operating in the region. No ICMM member company has ever defaulted on its closure obligations, nor would doing so be feasible in the context of maintaining a global social license to operate. | N/A | Policy | CIRNAC acknowledges that some operators—such as members of the International Council on Mining and Metals (ICMM)—maintain strong track records in environmental stewardship and closure compliance. While these factors reflect responsible corporate practices and should be encouraged, the currently policy requires 100% security. RECLAIM is a technical tool designed to estimate actual reclamation liability. Allowing corporate characteristics to adjust those cost estimates could undermine transparency and raise concerns among other stakeholders, including Indigenous rights-holders and the public. CIRNAC notes that leading jurisdictions—including Australia and several U.S. states—require full-cost bonding to protect public interests, regardless of the operator’s corporate profile. This ensures a level playing field and avoids moral hazard. That said, CIRNAC is open to exploring performance-based incentives outside of financial security reductions—such as streamlined administrative processes, phased release of security during progressive reclamation, or public recognition of exemplary operators".
| 1 | Tlicho Government - Jessica Pacunayen | 1 | General | The Tłı̨chǫ Government reviewed CIRNAC and GNWT's proposed revisions to RECLAIM 8.0, the RECLAIM User Manual, and supporting documentation. These documents are used by the GNWT, CIRNAC, mining companies, and the Land and Water Boards to set mining security deposits. RECLAIM and the User Manual are also a resource for all parties reviewing security deposits. Tłı̨chǫ Government may also wish to use RECLAIM to estimate security deposits for future mines on Tłı̨chǫ Lands. | N/A | Policy | The Working Group support the Tłı̨chǫ Government's use of RECLAIM as it will ensure greater consistency in how reclamation environmental liablity is calculated.
| 2 | Tlicho Government - Jessica Pacunayen | 2 | Increased security deposits | RECLAIM 8.0 includes numerous substantial increases. Most unit costs went up to varying degrees, and a few went down. On average unit costs appear to have more than doubled. Some key unit costs have increased far more than this, for example the lower estimate for winter road construction went up by more than 10 times. Indirect costs are now up to 58% of direct costs instead of 32%, plus there are new costs for a human health and ecological risk assessment and finalization of the closure plan (totaling 7% of capital costs). There is also a newly proposed cost for inflation during closure and post-closure. Post-closure monitoring and maintenance and mobilization/demobilization now have indirect costs (as percentages) added to them. These and other increases would result in very large increases to security deposits at existing mines. CIRNAC/GNWT explained that the increases are because the current unit costs (in RECLAIM 7) are more than 10 years old and because costs in the current RECLAIM spreadsheet (version 7.0) are too low compared to actual costs the government has incurred for actual reclamation projects. As noted in "Review of Mine Financial Security Estimates and RECLAIM": "it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." CIRNAC and its consultants are perhaps in the best position to provide actual costs of closure activities. There has been talk over the years that RECLAIM is dramatically underestimating closure costs. It is possible that even with the proposed revisions, RECLAIM 8.0 would continue to underestimate reclamation costs. For example, the Supplementary Information provided on Feb 18 says that the Owner's Representative costs are actually 12% to over 20% of costs, not the 8% adopted in the proposed revisions to RECLAIM. This is just one of several examples that may mean the RECLAIM 8.0 continues to underestimate reclamation costs. Others are in comments below. | RECLAIM should estimate the actual costs of closure and reclamation, even though it appears that the new estimates will likely be much greater than current security deposits. However, this does not mean that the Boards should immediately increase all security deposits in the North to reflect actual reclamation costs. This could have serious economic and social repercussions, and could undermine the objectives set for resource management under the modern treaties, to balance conservation and development for 'optimum benefit'. Instead, updating RECLAIM to reflect actual costs is a necessary first step to fixing some serious and far-reaching problems related to security deposits and more broadly to sustainable and responsible mining in the North. Actual reclamation costs must be known and on the table in order to have informed discussions about the impacts, benefits, and risks of mining, including the risk of having to pay for cleanup of abandoned mines. Underestimating security can also enable companies with insufficient financial resources to mine in the North, which poses a serious risk to the Northern economy and the environment. Greater attention should be given to a mining company's financial health and the risks for each project (e.g., risks from market conditions, remoteness, logistical issues, etc.) when weighing the impacts, benefits, and risks of approving a full-scale mine. Decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis, and input from citizens and residents. If the federal and territorial governments, or the Boards in working to achieve the treaty-based objectives for resource management, wish to offset the burden of posting security for actual reclamation costs, this should be done in a transparent, carefully considered manner informed by the actual costs of clean-up and the views of all parties. The Tłı̨chǫ Government would like to be involved in any such discussions, and as a treaty partner, must be involved in these discussions. Other topics raised in our comments are inextricably intertwined with the issue of RECLAIM estimates, for example relinquishment of liability, promoting progressive reclamation, and financial security for potential disasters. These issues should be discussed holistically along with RECLAIM updates. Some of these issues may need legislative amendments to properly address them in the long run. | Policy | CIRNAC and GNWT appreciate the comment and recommendation. We agree on the importance of this update and the potential implications for the mining sector in the north. CIRNAC and GNWT have committed to directly engaging with the Tlicho Government following the upcoming engagement session to discuss these topics further. We would like to note that we agree that decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis and input from citizens and residents. Further discussions with the Tlicho Government, other IGIOs and the LWBs is still required before any decisions are made on how the model update is implanted or adopted by the Territorial and Federal governments. We look forward to these discussions, recognizing that the Tlicho Government must be part of them.
| 3 | Tlicho Government - Jessica Pacunayen | 3 | Increased security deposits - incentives for progressive reclamation | The RECLAIM Manual includes a policy that the security deposit cannot be reduced for progressive reclamation (reclamation completed during operations) until the mining company has completed the reclamation work. This is a sensible approach to ensure there is always enough money for reclamation if a company goes bankrupt. However, a more refined and strategic approach to this problem should be considered to enable work to proceed while limiting risks if a company goes bankrupt. This would allow more parts of a mine to be reclaimed early in the mine life, which benefits the environment, the taxpayer, and the company. A company's financial capacity, the financial and environmental risks of leaving parts of the mine unreclaimed, and other factors would need to be considered. | Financial mechanisms to promote progressive reclamation should be evaluated and discussed with all parties. | Policy | CIRNAC and GNWT will consider this recommendation and will update reviewers as part of the upcoming engagement workshop.
| 4 | Tlicho Government - Jessica Pacunayen | 4 | Increased security deposits - case studies | Based on our participation at the meeting hosted by CIRNAC and GNWT during the PDAC conference in March 2025, we understand there may be disagreement over whether RECLAIM 8.0 is overestimating or underestimating closure costs. CIRNAC and the GNWT have actual cost data from abandoned mine reclamation in the North. Using this data to validate RECLAIM 8.0 is an indispensable step to deal with these opposing views and to ensure security deposits cover the full costs of reclamation without unduly burdening industry. The Discussion Paper says that CIRNAC and GNWT had originally intended to use historical data to help populate RECLAIM 8.0 (which is different than historical data for validation). However, the Discussion Paper says this did not happen because "contractor confidentiality, limited examples available to provide a sufficient range and average of costs (which can vary considerably depending on the size and scope), and the effort required to synthesize data." While these issues might make it challenging to use historical cost information to update RECLAIM 8.0's costs and assumptions, it should not prevent validation of the model. Validation is about running information from past projects through RECLAIM 8.0 and comparing this to the actual cost of the project. If confidentiality issues cannot be addressed, CIRNAC and GNWT should at least conduct this validation step internally and publicize whether the exercise validated the model. Further, "the effort required to synthesize data" may be a barrier, but it is arguably a relatively small price to pay compared to the benefits of improved cost estimates. In addition to this validation step, CIRNAC and GNWT should use historical cost data to improve RECLAIM. Based on the unit cost reference tables provided as supporting documentation, it appears this may have been done to some extent. If not, CIRNAC and GNWT should take advantage of historic cost data in ways that maintain confidentiality and account for limitations in the data. | 1. Before finalizing RECLAIM 8.0, CIRNAC and GNWT should validate it, by running RECLAIM (i.e., entering actual quantities, selecting the appropriate unit costs, etc.) with information from actual reclamation projects at abandoned mine sites. The resulting RECLAIM 8.0 estimate should be compared to the actual cost. If these are substantially different, adjustments should then be made to RECLAIM 8.0 from lessons learned from this comparison. 2. Historical cost data should also be used, to the extent possible, to update RECLAIM with actual cost information, without compromising confidentiality. | Policy | The Working Group have carried out this quantitative analysis. RECLAIM 8.0 estimates are lower than the actual expenditures of historical abandoned mine closures.
| 5 | Tlicho Government - Jessica Pacunayen | 5 | Internal government costs | RECLAIM does not include the substantial internal costs for CIRNAC and GNWT, for example government employee salaries. This means there is no transparency about what these costs are or what the actual costs are when a mine is abandoned. | Please explain why these costs are not considered when estimating the costs of reclaiming a mine. | Policy | Government salaries are not included in the model update or principles of RECLAIM. Typically, these costs are outside the scope of the reclamation security. However, all government salaries are available to the public for transparency. CIRNAC and GNWT would be open to hearing more from the TG on this topic during the upcoming engagement sessions.
| 6 | Tlicho Government - Jessica Pacunayen | 6 | Calculating security annually | The proposed RECLAIM Manual update includes a new requirement that "The total financial security for final reclamation required at any time during the life of the mine should be equal to the total outstanding reclamation liability for land and water combined (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period)." This mirrors the Mine Site Reclamation Policy for the NT, which is well over 20 years old. It is not clear how this would be implemented. Is GNWT/CIRNAC anticipating that water licences would have a schedule with annual increases to security? This has not been recent practice. Or is a RECLAIM review anticipated each year? TG is concerned that this would place a big resource demand on all parties. Also, how would the common practice of increasing security at project milestones (e.g., commencement of construction, mining, or milling, percent of pit filled, etc.) fit into this approach? | Clarify how this requirement would be implemented. | Policy | CIRNAC and GNWT are not proposing a standard yearly update to security estimates, agreeing with TG that this would be burdensome to the public. The updated language is intended to capture the approved liability set by the LWBs within the term of the water licence and land use permits. How this is reviewed and paid (i.e., phasing) will be up to the LWBs, with input from the public.
| 7 | Tlicho Government - Jessica Pacunayen | 7 | Human health and ecological risk assessment | The proposed revisions to RECAIM include the cost of a human health and ecological risk assessment (HHERA). The User's Manual notes that this is completed in accordance with federal risk assessment guidance. Modern mines are different than mines abandoned in the past in that they have approved closure objectives and in many cases, approved closure criteria. It is our understanding that, in the past, HHERAs at federal sites have been used to set the standard for cleanup, for example the water or soil contaminant thresholds that must be met. If a modern mine is abandoned during operations and is in compliance with its water licence, land use permit, and other authorizations, unexpected contamination (beyond what is addressed in the approved closure plan) may be less than in the past. Some mines may include an HHERA in their approved closure plan to confirm predicted risks. However, it is not clear what role an HHERA would play at an abandoned mine. We are concerned that use of HHERA's could lower the standard compared to approved closure criteria. Closure criteria have been publicly reviewed, vetted and debated in countless workshops, and represent substantial input from all parties. Closure criteria have been deliberated by the Boards and Board decisions on them have been transparently documented. Ignoring approved closure criteria after abandonment would be inconsistent with the land claim agreements that established the Land and Water Boards. | If an HHERA is part of an approved closure and reclamation plan, then the cost of it should be in RECLAIM. Also, if the GNWT and CIRNAC expect that new risks will emerge after abandonment of mines with modern, approved closure plans, then an HHERA should be a default cost in RECLAIM. However, the RECLAIM Manual should acknowledge that Board-approved closure criteria are the clean-up standard at abandoned mines, unless it is demonstrated that these cannot be achieved or that new criteria are needed for risks that developed after abandonment. An HHERA may play a role in this effort, but HHERA's should not be a replacement for closure objectives and criteria. | Indirects | Point taken on the approved closure objectives and criteria. An HHERA would be to confirm predicted risks. Government assumes liability of the chemical risks at the Site and must be assessed under the contaminated sites program. Additional details to be added to User Manual.
| 8 | Tlicho Government - Jessica Pacunayen | 8 | Monitoring | The draft RECLAIM Manual says that monitoring will be conducted "with respect to the effectiveness of the mitigative measures, the accuracy of the environmental assessment and any unforeseen environmental impacts". Although true, this statement does not appear to reflect current practice. To our knowledge, all closure plans (and therefore security deposits) in the NT are founded on the MVLWB/AANDC Guidelines for the Closure and Reclamation of Advanced Mineral Exploration and Mine Sites in the Northwest Territories. Therefore, all mines have Board-approved modern closure plans that are based on closure goals, principles, closure objectives and closure criteria. This means closure criteria will dictate monitoring plans and duration. The effectiveness of mitigative measures and the accuracy of the environmental assessment will be reflected in the criteria. If there are unforeseen environmental impacts, closure criteria should be updated. | The RECLAIM Manual should state that monitoring will depend on closure criteria. | User Manual | Text has been revised for clarity.
| 9 | Tlicho Government - Jessica Pacunayen | 9 | Relinquishment of liability | The revised Manual states that "Following mine closure, mining companies or their future owners should continue to be responsible for the site , including the remediation of any additional environmental complications which develop." This raises questions about relinquishment of liability. For many years, many parties have been requesting clarity on how liability will be relinquished at mine closure. This is especially important with mines like Diavik approaching the end of operations. This gap creates uncertainty and may inhibit investment in sustainable and responsible mining in the North. | 1. It is understood that additional policy, legislative, or regulatory amendments may be needed to address how and to what extent companies are released from liability once all closure criteria have been met. For example, will companies be required to leave funds for future monitoring, maintenance, or unforeseeable events at the closed mine? These funds may require supporting legislation and/or policy. Even if the GNWT cannot undertake an effort to better address relinquishment before the RECLAIM updates are finalized, the Manual (or another document) should include more information on this topic. This would assist all parties in understanding how GNWT and CIRNAC will approach relinquishment of liability under existing legislation. 2. The GNWT and CIRNAC should immediately begin the effort to outline the conditions and criteria that will allow relinquishment, establish how much money will be required for monitoring, maintenance and unforeseeable events, clarify the extent to which companies will be released from liability, and develop a relinquishment process. This effort will need to involve Indigenous Governments early on. | Policy | The Working Group agree that the discussions on relinquishments must occur with Indigenous governments and that these topics fall outside the scope of this model update. The Working Group commit to further discussions with TG and other IGIOs on this topic. CIRNAC recognize the importance of clarifying the conditions under which mine proponents may be fully or partially released from liability following successful mine closure. While current regulatory instruments ((e.g., Type A licence amendments, Board decisions, or land tenure changes) allow for the staged return of financial security, there is limited guidance on long-term obligations, such as post-closure monitoring, maintenance, and responses to unforeseen events. To address this, CIRNAC and GNWT will co-develop supplementary guidance that outlines criteria for closure completion, expectations for monitoring duration, and the potential need to retain a portion of security for residual risks associated with unpredictable impacts for high risk mine sites. CIRNAC agrees that future policy or legislative amendments may be necessary to establish formal mechanisms for relinquishment, including options such as long-term care trusts, residual risk payments, or institutional control programs. A collaborative policy development process will be initiated with Indigenous Governments, co-management Boards, and other stakeholders to co-develop a transparent and risk-based approach to liability relinquishment. This process will define the conditions under which relinquishment may occur, determine how long-term risks will be managed and funded, and identify the legal instruments required to support this transition. Indigenous participation will be central to this work, ensuring that future frameworks reflect Indigenous governance, land stewardship roles, and rights. While this broader policy development may extend beyond the RECLAIM model update, interim guidance will help ensure transparency and alignment with existing legal authorities.
| 10 | Tlicho Government - Jessica Pacunayen | 10 | Performance holdback | The revised Manual states that "If the company carries out progressive reclamation during operations as proposed, such as revegetation of disturbed areas during operations, then the closure cost estimate could be reduced by the associated costs for that component when the company demonstrates that the closure activity has been successfully completed and closure objectives and criteria have been met." It is our understanding that the LWB/GNWT/CIRNAC Guidelines for Closure and Reclamation Cost Estimates for Mines allows for some money to be refunded to companies, even if criteria have not been met. This is allowed so long as a performance holdback is set. The same Guidelines explain how a performance holdback could be set, including three different methods. The first method uses a simple percentage-based approach by mine component, the second method uses RECLAIM, and third uses a "factored risk" approach. | RECLAIM should reflect the CIRNAC/GNWT/LWB Guidelines as they relate to performance holdbacks. Calculations based on the Guidelines should be inserted into RECLAIM. This would include simple calculations supporting Table 1 of the Guidelines (the percentage-based approach). It could also include calculations to support the "factored risk" approach on page 19 of the Guidelines. Support for companies to estimate performance holdbacks will promote a quicker and more efficient security refund process. Although all regulators that use RECLAIM may not require performance holdbacks, those regulators could simply ignore the calculations, or the GNWT could develop them for use in the NT only. While it is beneficial to have only one version of the RECLAIM model across the North, add-ons to reflect jurisdictional differences could help to ensure that RECLAIM is useful everywhere while maintaining a core set of shared calculations and inputs. | Policy | The Working Group will consider this recommendation and will update reviewers as part of the upcoming engagement workshop.
| 11 | Tlicho Government - Jessica Pacunayen | 11 | Documentation of security refunds | Similarly, security refunds for completed progressive reclamation or completed work during active closure is becoming more common and is an important way to promote and reward early closure work. Currently, RECLAIM does not document these refunds, which means there is no record of the original estimate, the refunds given, and what the refund was based on. This may make it difficult to determine refunds during active closure, since it may not be clear what has already been refunded and what is still being held as security. | RECLAIM should document all security refunds. For example, RECLAIM could include a refund summary sheet showing the original estimate, all refunds, and links to documentation supporting the refund (e.g., RECLAIM estimates used to calculate refunds, Board decisions, etc.) | Policy | This cost estimating tool is not the mechanism for tracking security refunds
| 12 | Tlicho Government - Jessica Pacunayen | 12 | Disasters | RECLAIM does not cover the costs of disasters. With numerous mines using the RECLAIM model across Canada's North, there is a significant risk that one or more of these mines will have an environmental disaster during the life of the mine. Currently, disaster clean-up costs would fall entirely to the taxpayer. The recent disaster at the Eagle Mine in Yukon is an excellent demonstration of how the taxpayer will be forced to carry the burden of disaster clean-up. Such costs could easily be in the hundreds of millions of dollars or more. The Mount Polley disaster in 2014 is another example of taxpayers covering significant costs for a mining disaster. Although this may be considered a policy decision that is outside of the scope of RECLAIM, RECLAIM by necessity houses many policy decisions by virtue of the costs it includes or excludes. RECLAIM unavoidably sets policy through its underlying principles and assumptions. Excluding disaster costs is as much a policy decision as including them. | Security for potential future disasters should be required. Since most mines are unlikely to experience a disaster, the amount held by any single mine should only be a fraction of potential disaster clean-up costs. This could be determined based on the risk profile of a project (e.g., potential for acid drainage, geotechnical failures, proximity to highly valued areas, etc.). If disaster costs are not included in RECLAIM, another mechanism is urgently needed to ensure that industry contributes towards a pot of money for future disasters. | Policy | The Working Group agree that disasters are not included in the model, as it is not intended to cost worst-case scenarios. These topics should be discussed as part of the public review of the closure and reclamation plans, where recommendations to the LWB on what is appropriate for costing long-term scenarios should be discussed. The co-management regulatory system intends to see best practices in the authorizations to ensure disasters are accounted for in the design and management plans. If a party is of the opinion that there is a significant risk to the public from inadequate plans or conditions in the authorizations, this should be presented to the regulatory boards for action. It is agreed that RECLAIM does not capture the costs of unforseen remediation costs associated with catastrophic mine failures and disasters, the costs of which have been shown to be prohibitive for a single operator to absorb. By definition, mine reclamation security is to protect against a cost that is foreseen, can be estimated and will have to be incurred. It cannot be expected to deal with catastrophic or unforeseen events without security requirements increasing to the point where they become prohibitive to all mining development in the North. While the RECLAIM model is primarily designed to estimate the foreseeable, site-specific costs of mine closure and reclamation, CIRNAC agrees that a complementary approach is warranted to manage financial risks associated with unforeseen or catastrophic events. For this reason, as part of broader policy work, CIRNAC is also exploring the feasibility of establishing a shared industry-funded disaster relief pool to address catastrophic mine failures. CIRNAC will engage with Indigenous governments, industry, territorial partners, and regulators to assess governance models, contribution formulas, and legislative tools needed to support such a mechanism.
| 13 | Tlicho Government - Jessica Pacunayen | 13 | Revegetation | Revegetation of a site after closure is an important part of restoring the land, enabling long-term future cultural use, making the site look and feel like the surrounding area, and supporting wildlife. The revegetation unit costs in RECLAIM include seeding and tree planting. Planting cuttings, transplants, or plugs are other examples of revegetation, and likely have different costs than seeding and tree planting. Placement of stockpiled reclamation materials such as topsoil, till, lakebed sediments, etc. should also be included in direct costs for revegetation. | RECLAIM should include the cost for all types of revegetation, including cuttings, plugs, transplants, and spreading stockpiled dirt and soil. | Unit Rates | The working group respectfully disagrees with the recommendation. The Working Group suggest a User Specified activity and cost in RECLAIM to keep the Tool streamlined.
| 14 | Tlicho Government - Jessica Pacunayen | 14 | Traditional Knowledge monitoring | Traditional Knowledge (TK) Monitoring is a critical part of ensuring the closed site meets closure objectives and goals. TK Monitoring is also essential for building community confidence in the closed site to enable long-term future use of the site. (For example, we note that the WLWB requires Diavik to prepare a TK Monitoring Plan). | RECLAIM should include the costs of a Traditional Knowledge Monitoring Program. This would involve regular (e.g., initially annual) site visits from Elders, youth, and staff to evaluate water quality, wildlife safety and movement, vegetation, and more. It is important to note that this is not the same as engagement or regulatory costs. This TK Monitoring Program is similar to other monitoring programs and should be a line item in the Post Closure sheet along with the scientific monitoring programs. | Policy | The Working Group will consider this recommendation and will update reviewers as part of the upcoming engagement workshops. Also see EMAB-4.
| 15 | Tlicho Government - Jessica Pacunayen | 15 | Net Present Value | To date, RECLAIM has included the ability to calculate the net present value. This was used for very long-term costs (e.g., more than 20 years) such as maintenance of constructed wetlands. This reduced the amount of security a company needed to post, without exposing the tax payer to increased risk. This is because the net present value accounted for the fact that money set aside for the future can be invested and will grow. The discount rate used in those calculations was generally an assumed modest growth in investment (e.g., 5%) minus an assumed inflation (e.g., 2%). | Why has the net present value function been removed from the draft RECLAIM? | NPV | NPV is not include as the posted security is not gaining interest. Need to account for inflation to ensure the government is not under secured.
| 16 | Tlicho Government - Jessica Pacunayen | 16 | Interim Care and Maintenance | The RECLAIM model includes an estimate for interim care and maintenance, meaning the period after bankruptcy and abandonment and before active closure begins. The total cost is based on an annual cost (commonly a few million dollars) times the number of years the site is likely to be in interim care and maintenance. The draft RECLAIM 8.0 model includes a default of 3 years of interim care and maintenance. However, the supporting documentation for the RECLAIM updates (Review of Mine Financial Security Estimates and RECLAIM) says "Importantly, the duration of Interim Care and Maintenance is typically limited to two to three years. It is known that government experience has been much different than this, both in scope and duration. This is an obvious category for which government could be under secured". The same document provides some evidence that the actual period could be five to ten years. | The estimated time a site is in interim care should be based on the expected or average duration not the minimum. | Policy | The RECLAIM Working Group agreed the ICM default should be 5 years based on government experience managing abandoned sites.
| 17 | Tlicho Government - Jessica Pacunayen | 17 | Unit costs - reference table and sources | During the public review, a reference table showing the source for unit cost assumptions was provided. | 1. This reference table is a significant improvement and should be included in the finalized model. It improves transparency and credibility of the unit costs and enables industry and decision-makers to discuss alternative site-specific unit costs. 2. Unit costs adopted from projects in the South (e.g., Sudbury) should be increased if these costs are going to be higher in northern, remote conditions. | Unit Rates | Noted.
| 18 | Tlicho Government - Jessica Pacunayen | 18 | Fish habitat | The Open Pit tab does not explicitly include costs for building fish habitat (littoral zones), even though these may be required in pit lakes or pits that will be reconnected with larger lakes. Some of the activities in the tab may address fish habitat construction (e.g., placing fill), but it is not clear whether all activities required to build littoral zones are in RECLAIM. (Fish habitat construction may be required by the Department of Fisheries and Oceans and/or the Land and Water Boards. In either case the estimate should be included in RECLAIM. If DFO already holds security for this activity, it can be subtracted from the RECLAIM estimate. If it is only required by the Land and Water Boards, then it would remain in the final total.) | RECLAIM should include costs for construction of fish habitat in pits. | Policy | CIRNAC and GNWT appreciate the comment and recommendation. The requirement of fish habitat falls out of the scope of this model update, but based on comments from DFO (see DFO-1), CIRNAC and GNWT are open to further discussion on this topic.
| 19 | Tlicho Government - Jessica Pacunayen | 19 | Scientific and Traditional Knowledge research | Typically, the CRP will have several approved reclamation research plans. If a mining company abandons a mine, important reclamation research may not have been carried out. The results of this research will be needed to properly reclaim the site. | RECLAIM should include the costs of scientific and Traditional Knowledge reclamation research. As noted by BCL in their memo, this could result in mines not proposing research, in order to avoid higher security deposits. BCL proposed some alternatives to address this problem (page 18 and 19 of the BCL memo). These could be considered, provided the details of the approaches are publicly reviewed. | Policy | CIRNAC and GNWT supports the principle that all necessary studies—whether scientific, traditional knowledge-based, or otherwise—should be considered when estimating the costs of preparatory work for future reclamation activities. Ensuring these costs are reflected in project planning helps promote comprehensive, responsible, and inclusive reclamation.
| 20 | Tlicho Government - Jessica Pacunayen | 20 | Risk communication | The RECLAIM model does not include the costs of risk communication. In order to restore confidence in the mine site area so that closure objectives related to cultural use can be met, a good risk communication plan must be developed and carried out. This may involve public meetings, posters, online tools, social media, radio, newspapers, etc. | RECLAM should include the cost of risk communication. If this cost is lumped in with other costs (e.g., engagement and regulatory compliance costs), this should be mentioned in the User's Manual. This will ensure that the portion of security held for risk communication is not returned until it has been carried out. It will also inform any future disagreements about the percentage of direct costs that should be held for engagement and regulatory compliance. | User Manual | This will be added to User Manual upon further discussion.
| 1 | A Member of the Public - Todd Slack | 1 | Model Utility - One Long Comment, Pt. 1 | Obviously an updated reclaim model is in the interests of all parties. Recent years have seen significant increases in costs and an adjustment to better reflect this is a valuable effort to protect taxpayers and ensure that the polluter pays principle is effectively applied. However, the operational modifications of the model are not the only step needed to ensure our territory is protected. A higher-level review focusing on the overall effectiveness of the bonding system should be undertaken using real world closure examples to test the predictive utility of the RECLAIM approach. No model is perfect and the review should be asking if this model meaningfully serves the polluter pays principle. Ground-truthing with real world examples is essential. For example, the MVLWB held approximately $70M in security for Snap Lake (it isn’t particularly easy to know exactly what the security amount was). According to public reporting, as of 2023 De Beers had spent $135M. In that case, it seems that NWT taxpayers – with a government already seeking financial relief - were considerably exposed. Should this be an indicator of a larger trend, the risk is even larger as it seems a widely held belief that industry, already mobilized and familiar with their site, can complete a closure in a more cost effective manner. Yet, the final cost for this site, with a modern security bond, will be more than twice what was held. | Starting with the NWT, publish real world examples of closed sites versus the reclaim estimates | Policy | Please see EMAB-1. Additionally, the Working Group appreciates the comment and recommendation. CIRNAC and GNWTi ntendintends to ensure that appropriate security is held for projects in the north to protect the public from the costs. As part of this update, we have provided published updates to current and expected costs for reclamation in the north, which underpins the changes to the model. Finally, no historical projects have approved RECLAIM estimates, which are CIRNAC's responsibility.
| 2 | A Member of the Public - Todd Slack | 2 | Model Utility - Pt. 2 | Other real world examples available to test the utility of RECLAIM estimates can be found in ongoing Strategic Oil abandonment and closure as well as the 2014 Snowfield property. Based on anecdotal information (as accounts have not been published, despite the expenditure of public monies), for the former, the GNWT has paid tens of millions for the reclamation, while the in the latter, the GNWT paid far in excess of the security held (nevermind the six-figure pre-existing debts that the company owed GNWT). Examples from Nunavut can be researched as well, extending back to Tahera/Jericho which was established with a modern regulatory regime and cost taxpayers more than the security that was held (as opposed to GIANT which is not appropriate as a test case). Yukon examples, over which there are a number of selections (Victoria, Wolverine, Minto) may provide further insight into the effective security estimates and bonding (considering the Yukon government has appropriated $100M for early stages of the Victoria mine they’ve inherited, which was permitted in a modern system). To summarize, before undertaking minor adjustments to the mechanics of the model, the overall utility needs to be verified, confirming fit for purpose. Notwithstanding the financial limitations of GNWT means that they lack the robustness to absorb and large mine failures (noting the daily cost cutting measures that are occurring), more importantly, the citizens of the NWT should have confidence that those overseeing the accessing and sale of our public resources are ensuring that the closure is paid for and completed by those exploiting the resource. | 1) Undertake analysis that looks at closure estimates versus the security held for sites across the NWT, Nunavut, and the Yukon. 2) Search for similar examples in Southern Canada were the structures ensuring the protection of taxpayers and governments are similar to those employed in the north. | Policy | CIRNAC and GNWT appreciate the comment and recommendation, as it serves as a reminder of the intent of the reclamation security and this model update. Further discussion on security policy is expected in the near future, but CIRNAC and GNWT have taken input from other abandoned sites to inform the updates to unit costs.
| 1 | Wek'èezhii Land and Water Board - Meghan Schnurr | 1 | Implementation of RECLAIM V8 | It may help reviewers if the authors could describe how they envision the updated model being implemented. For example: - Do the authors intend to start submitting closure cost estimates generated via RECLAIM V8 for all security-related reviews from the date of publication onward? Would this approach include existing projects that have previously had closure costs estimated using V7? Will the authors expect licensees and applicants to use RECLAIM V8 for all closure cost estimates from the date of publication onward? | Please describe how the authors intend to implement RECLAIM V8. | Policy | The Working Group understand there is much interest in how the update model will be implemented. Details on this are still being considered, and the GNWT are seeking input as part of this public review on how best to do this from reviewers and participants in the northern regulatory system.
| 2 | Wek'èezhii Land and Water Board - Meghan Schnurr | 2 | Comparison against current estimates using RECLAIM V7 | The proposed updates in RECLAIM V8 are noted. Based on the proposed updates, closure cost estimates will be higher than when estimated using RECLAIM V7. This could have implications to the mining industry in the north, so it may be helpful for reviewers to have examples of how closure cost estimates using RECLAIM V8 differ from those generated using RECLAIM V7. | Is there data available that compares how closure cost estimates generated using RECLAIM V8 differ from previous estimates generated using RECLAIM V7? If not, could this data be prepared and shared? Or perhaps the authors could estimate how different the closure cost estimates will be? What are the potential implications to the mining industry in the north? | Policy | The Working Group have not completed a costing exercise for specific sites at this time, but it is understood that costs using the proposed update would be significant for some operations. CIRNAC and GNWT are actively engaging with Industry to understand the implications better and we will provide updates on this topic as the public review commences.
| 3 | Wek'èezhii Land and Water Board - Meghan Schnurr | 3 | Comparison against known costs to close and reclaim sites | Further to the comment and recommendation above, it may also help reviewers understand the purpose of the proposed changes to the RECLAIM model if data could be provided that compares actual costs to close and reclaim sites to estimates generated using RECLAIM V7 and V8, though, it is not apparent whether this data is available. | Have the authors undertaken an analysis that compares the actual costs to close and reclaim sites against closure cost estimates generated using RECLAIM V7 or V8? Can this data be provided? | Policy | The Working Group have carried out this quantitative analysis. RECLAIM 8.0 estimates are lower than the actual expenditures of historical abandoned mine closures. There are sensitivities with sharing detailed actual cost data.
| 4 | Wek'èezhii Land and Water Board - Meghan Schnurr | 4 | RECLAIM Oil and Gas Model | It is noted this update pertains to the mining version of RECLAIM. Do the authors intend to update the oil and gas model as well? | Are there plans to update the RECLAIM Model for oil and gas? If so, are approximate timelines available, and would the process be similar to this update? If not, please explain why the oil and gas model will not be updated. | Policy | See response to IOR-9.
| 5 | Wek'èezhii Land and Water Board - Meghan Schnurr | 5 | User Manual - Discussion throughout on the status of Closure and Reclamation Plans. | The User Manual speaks to the need for applicants and licensees to have CRPs in order to develop closure cost estimates. In some instances, these speak to the need for an approved CRP. For example: - Section 2 Considerations for Northern Settings, “To derive accurate closure cost estimates, it is imperative that the company have an approved CRP which demonstrates a comprehensive understanding…”; and - Section 4.3.1 Engineering Desing, "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities." While it is important to develop a CRP to the point where it can be fully approved, this can take years (specifically for projects that require a type A water licence). This means that closure cost estimates developed during the application phase (pre-construction), during construction, and for the majority of the operational lifespan will be based on CRPs that have not been fully approved. This seems to be acknowledged in Section 4.3.6 Contingency where it is discussed that most CRPs for mining and associated estimates are at the feasibility or advanced conceptual level until near the end of operations. While this helps, it may reduce confusion further if the entirety of the User Manual recognized that CRPs typically require years of development to receive full approval. And for closure cost estimating purposes, it may be more realistic to indicate the applicant/licensee should advance the CRP as early as possible in the project lifecycle. | Consider whether the User Manual should be updated to clarify that it typically requires years to get a CRP fully approved and that applicants/licensees are encouraged to advance closure planning as early as possible. Consider revising certain messages, for example Section 2, to indicate, for closure cost estimating purposes, it is imperative that the applicant/licensee advance the CRP as early as possible in the project lifecycle. | User Manual | User Manual text is revised.
| 6 | Wek'èezhii Land and Water Board - Meghan Schnurr | 6 | User Manual - Definition of Contingency | A definition for contingency is provided in the Definitions and Acronyms table on page 4. A reference is provided from AACE costing terminology which seems to indicate this definition has been accepted by the construction or engineering community for costing purposes. However, it is not clear whether this definition aligns with how the term contingency is used throughout the document (specifically Section 4.3.6. Contingency) as well as how it is used for the purpose of generating a closure cost estimate via RECLAIM. For example the definition indicates contingency is "Typically estimated using statistical analysis or judgment based on past asset or project experience." Section 4.3.6 does not speak to statistical analysis, rather, the description in this section states "The determination of the contingency percentage is a subjective and project-specific task that relies on the judgement of the estimator." This could create confusion for applicants and licensees in terms of what they are expected to do when proposing contingency percentages. | Web Search - HHERA can cost between 1 to 5% of the total Capital closure costs and varies based on site complexity, remoteness, receptors present and number of contaminants. 4% is the default starting point and can be negotiated. Note to clarify the relationship between the HHERA and Finalize Closure and Reclamation Plan line items on the ICM tab. Ultimately these %'s are a starting point and can be negotiated. | User Manual | Re: statisical analysis, Table 2, includes one description of "Engineering may be 10%", which could have a Contingency of 25% assigned. All contigency is based on general guidelines and then judgment. Additional context has been added to the definition to expand on AACE defintion and its tie-in to this application.
| 7 | Wek'èezhii Land and Water Board - Meghan Schnurr | 7 | User Manual - Section 4.2.5 | This section describes a worksheet within RECLAIM V8 for Interim Care and Maintenance. It states that this worksheet captures the costs from cessation of mining activities to when active remediation begins. Is this meant to only cover the time period from cessation until active remediation? What about the period up to executing closure activities - perhaps the use of the term remediation in this case is analogous to closure activities? Please note that remediation and reclamation in the general sense have different meanings. | Web Search - 0.5 to 2% - Progressive reclamation efforts can result in a lower % NOTE, this note may be mixed up with ROW 34 above | User Manual | Yes, the terms were meant to be analogous. Text has been revised for clarity.
| 8 | Wek'èezhii Land and Water Board - Meghan Schnurr | 8 | User Manual - Section 4.2.6 | This section states "These should reflect the monitoring and maintenance plans and commitments identified in the Closure and Reclamation Plan" and later that "it reflects the monitoring and maintenance commitments in the Closure and Reclamation Plan." The LWBs' Standard Water Licence Conditions include Post-Closure Monitoring and Maintenance Plans, and it is typical for LWBs to require these for projects that require a water licence. Post-Closure Monitoring and Maintenance Plans are the home for the licensee to describe their approach to post-closure monitoring and maintenance. | Consider whether this section should be updated to also reference Post-Closure Monitoring and Maintenance Plans. | User Manual | Text has been updated to include reference to Post-Closure Monitoring and Maintenance Plans.
| 9 | Wek'èezhii Land and Water Board - Meghan Schnurr | 9 | User Manual - Section 4.3 | The introductory sentence of this section speaks to indirect costs, indicating they are "typically allocated or spread across all activities on a predetermined basis." It is not clear what is meant by "predetermined basis," though, the final sentence in this section indicates indirect costs are calculated based on professional judgement. Either way, please note that this term / the way it is used could lead the user to think that they determine indirect costs, when, regulatory process-wise, the user proposes indirect costs, just like any other cost, and determinations are by the Land and Water Boards. | Consider clarifying the intent of the term "predetermined basis" and its usage, or whether another term could be used instead. | User Manual | Both statements are meant to be correct. The predetermined allocations are the % laid out in the model, e.g. Engineering (2-3%). Some of these % have ranges, are all meant to be based on professional judgement.
| 10 | Wek'èezhii Land and Water Board - Meghan Schnurr | 10 | User Manual - Section 4.3 | The introductory sentence to this section seems incomplete: "Costs not directly attributable to the completion of an activity, which are typically allocated or spread across all activities on a predetermined basis." Pending any revisions as per the above comment and recommendation, should this sentence read as follows?: "Indirect costs are costs that are not directly attributable to the completion of an activity. They are typically allocated or spread across all activities on a predetermined basis." | Consider revising the sentence to improve clarity. | User Manual | Text has been updated for clarity.
| 11 | Wek'èezhii Land and Water Board - Meghan Schnurr | 11 | User Manual - Section 4.3 | RECLAIM V8 proposes an increase of 21% in indirect costs over RECLAIM V7, applied to the summary tab. The LWBs are responsible for setting the amount of security. Overall, it is challenging to consider what evidence is required to justify deviations from the "pre-determined" indirect costs when it is unclear how the "pre-determined costs" were derived. It is unclear what considerations went into deriving these percentages, except for the contingency indirect cost, and therefore how any deviations could be considered in the future. | Please clarify whether RECLAIM has considered deviations from the "pre-determined costs" proposed in section 4.3. Is additional information to support these pre-determined costs available? What evidence could be provided to support a deviation from these costs? | User Manual | % ranges are now included in the model for the indirect costs, to assist with their proper assignment. All cost estimating requires some level of professional judgment. The model should not be thought at a tool to remove sound professional judgement.
| 12 | Wek'èezhii Land and Water Board - Meghan Schnurr | 12 | User Manual - Administrative Edits | It seems the hyperlinks in the User Manual do not work. | Review and insert links as necessary. | User Manual | Hyperlinks has been checked and corrected.
| 13 | Wek'èezhii Land and Water Board - Meghan Schnurr | 13 | User Manual - Administrative Edits | Should Table 2 Column 3 be titled "Typical CRP Phase"? | For consideration. | User Manual | Yes, title has been corrected.
| 14 | Wek'èezhii Land and Water Board - Meghan Schnurr | 14 | Supplementary Information on RECLAIM V8 February 18,2025 | The supplemental information document references a "Technical Work Group and review of actual cost for Mine Closure and Reclamation at various locations across Canada." Further information beyond this has not been provided. It may be helpful to understand the range of projects and range of costs/percentages considered as part of developing the proposed indirect cost percentages. For example, the supporting information for Owners Representative states "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | If possible, provide additional information to understand the range of projects (e.g. size of project, type of mine: open pit, underground, etc.) and range of costs/percentages that were considered as part of developing the proposed indirect cost percentages in RECLAIM V8. | Policy | CIRNAC and GNWT will consider this recommendation and will update reviewers as part of the upcoming engagement workshop.
| 15 | Wek'èezhii Land and Water Board - Meghan Schnurr | 15 | RECLAIM V8 - New Line Item - Finalize CRP (% Closure Costs) | The ICM [Interim Care and Maintenance] tab of RECLAIM V8 includes a new line item titled, "Finalize Closure and Reclamation Plan (% Closure Costs)." This is calculated as 4% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between the cost of finalizing a CRP and the associated direct costs (i.e. closure work), and whether/how this considers how advanced the CRP is. This line item also does not seem to align with the text in section 4.3.1 of the Manual which states "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities (i.e. engineering is not required to develop a closure plan) and that there are no dramatic departures from the approved Closure and Reclamation Plan." | If possible, discuss how the 4% cost proposed was developed and whether/how this considers the varying degree of closure planning across different projects. | Indirects | Based on a websearch, HHERA can cost between 1 to 5% of the total Capital closure costs and varies based on site complexity, remoteness, receptors present and number of contaminants. 4% is the default starting point and can be negotiated. Note to clarify the relationship between the HHERA and Finalize Closure and Reclamation Plan line items on the ICM tab. Ultimately these %'s are a starting point and can be negotiated.
| 16 | Wek'èezhii Land and Water Board - Meghan Schnurr | 16 | RECLAIM V8 - New Line Item -HHERA (% Closure Costs) | The ICM tab of RECLAIM V8 includes a new line item "Human Health and Ecological Risk Assessment (HHERA; % Closure Costs)." This is calculated as 3% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between these direct costs and the development of an HHERA, and how the percentage was derived. | Please provide further information as to how the 3% cost proposed for HHERA was derived. | Indirects | Web Search - 0.5 to 2% - Progressive reclamation efforts can result in a lower % NOTE, this note may be mixed up with comment 15 above
| 17 | Wek'èezhii Land and Water Board - Meghan Schnurr | 17 | Use of Historical Costs | The information provided indicates that costs to clean-up historical federal contaminated sites informed RECLAIM V8. It is noted that the regulatory context and expectations have changed significantly since some of those sites were operational/abandoned. It is unclear how/whether the change in regulatory regime and expectations was considered when reviewing these historical clean-up costs. | Please describe how/whether the change in regulatory expectations was considered when reviewing the historic clean-up costs of federally contaminated sites. | Policy | Federal contaminated sites are remediated based on their national program protocols.
| 18 | Wek'èezhii Land and Water Board - Meghan Schnurr | 18 | Owners Representative | The supplemental information provided to support the indirect cost associated with "Owners Representative" references support to CIRNAC and scrutiny of the Federal Contaminated Sites Program. Given that the GNWT would be responsible for clean-up for the majority of current projects in the Mackenzie Valley, it is unclear whether GNWT has adopted this same approach to the clean-up of abandoned sites. | Clarify whether the GNWT has adopted this same approach of hiring an Owners Representative. | Policy | GNWT has not adopted this approach at this time.

## Comment Tracker (hidden)
No. | Proponent | Topic | Reviewer Comment | Reviewer Recommendation | Topic | Assigned To | Proponent Response
1 | EMAB | Evaluate RECLAIM estimates versus actual expenditures | EMAB's view is that the cost of mine closure should be borne by the proponent, not the taxpayer. The comment on p. 1 of the CIRNAC review that "However, it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." raises a major concern. Security should cover the entire cost of closure, and RECLAIM should calculate security that meets the full cost of closure. | CIRNAC/GNWT should carry out a quantitative evaluation of how much current RECLAIM estimates differ from actual expenditures. | Policy | GNWT/CIRNAC
2 | EMAB | Depositing waste rock in open pit | Some mines have included depositing waste rock into open pits as a means of disposal. This activity does not appear to be addressed in the RECLAIM manual or tables. | Expand tables, and manual, to include placing waste rock and other materials, into open pits. | Unit Rates | AtkinsRéalis
3 | EMAB | Revegetation | The reference tables for vegetation include hydroseeding and tree planting. This is a good start, but the range of activities should be expanded to include all activities required for successful revegetation. | Reference tables for vegetation should also include application of amendments and planting of container forb seedlings as well as other activities required for successful revegetation. | Unit Rates | AtkinsRéalis | Add Other Specific if not there already
4 | EMAB | Long-term maintenance and monitoring | Traditional Knowledge Monitoring by members of Affected Communities is an important component of ensuring successful closure and future use of the area affected by the mine for cultural activities by the Indigenous people who live in the area and use it. | Add Traditional Knowledge Monitoring to the list of post-closure activities. | Policy | GNWT/CIRNAC
5 | EMAB | Long-term maintenance and monitoring | EMAB was pleased to see the expansion of the Mobilization sheet to include construction and use of winter roads for both mobilization and demobilization. It is not clear whether this is intended to cover mob/demob for post-closure maintenance. Once the mine closes there is no guarantee that the winter road will continue to exist. If there is a significant maintenance requirement, there may be a need to build a winter road to mobilize heavy equipment etc., and to demobilize it after the maintenance is completed. | Include the cost of building a winter road to the mine as part of long-term maintenance, if this is the only means for mobilizing/demobilizing heavy equipment required for maintenance. Costing should include building the winter road for the following season to demobilize heavy equipment. | Unit Rates | AtkinsRéalis | Maintaining a road for the duration of the Post Closure Monitoring may be expensive.
6 | EMAB | Long-term maintenance and monitoring | Post-closure monitoring activities may require air transportation to and from the site, which could involve use of the airstrip. In order to use the airstrip it will need to be maintained until all monitoring is completed. | Include costs to maintain the airstrip until post-closure monitoring is completed. | Unit Rates | AtkinsRéalis | Yes this maybe required.
7 | EMAB | Long-term maintenance and monitoring | The scope of post-closure maintenance activities includes cover maintenance and spillway maintenance. Maintenance could include other components such as tailings dams, discharge channels, revegetation, or emergency or ongoing water treatment; so the list should be expanded to provide for these and other potential maintenance activities. | Expand the scope of post-closure maintenance activities to include dams and discharge channels, revegetation maintenance, and a category for other potential maintenance requirements. | Unit Rates | AtkinsRéalis | Agreed – but any list would not be exhaustive
8 | EMAB | RECLAIM User Manual | The User Manual will need to be updated to reflect all changes and additions to the RECLAIM tables. | Ensure the RECLAIM User Manual is updated to provide clear explanations of all the activities and changes to the tables. | User Manual | Brodie
1 | IOR | Owners Representative Cost | Costs for the Owners Representative are included at a rate of 8% of the total capital costs estimate. This appears to be a duplication of costs associated with Engineering Design (8%) and Project Management (10%). | Suggest removing the Owners Representative line item in the Indirect Costs summary or reducing the default factor to 2% of Capital Costs or providing a description and basis for this percentage and how it differs. | Indirects | AtkinsRéalis and Brodie
2 | IOR | Human Health and Ecological Risk Assessment | Human Health and Ecological Risk Assessment (3% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | Indirects | AtkinsRéalis
3 | IOR | Finalize Closure and Reclamation Plan | Finalize Closure and Reclamation Plan (4% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | Indirects | AtkinsRéalis
4 | IOR | Unit Price Cost References are not Regional | There do not appear to be any references to NWT or Nunavut specific unit costs in UR-Short list in workbook RECLAIM 8 Reference Tables_WorkingCopy.xlsx | Suggest that V8 include reference to northern unit price equivalents. | Unit Rates | AtkinsRéalis
5 | IOR | Remediation | There are no referenced unit prices for remediation of any sort – bioremediation and landfill unit prices do not have any reference or backup. | Add unit prices for standard remediation techniques (e.g. biocell) | Unit Rates | AtkinsRéalis | We don’t have a ref for this costs
6 | IOR | Land Ownership | The Reclaim Model Version 8.0 does not consider the value of owned land in determining (i.e., reducing) security. | Add consideration for land ownership as a reduction for overall security. | Policy | GNWT/CIRNAC
7 | IOR | Identify Unit Components without a reference for unit price | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Unit Rates | AtkinsRéalis & Brodie
8 | IOR | Unit Prices different from Price Sources | The unit prices in the Reference Table (TABLE 2: RECLAIM v 8.0 Price Sources, Basis and References) do not always match the unit prices in the RECLAIM 8.0 Unit Cost Table. For example, see the unit rate SB1 for "excavate/load/short haul" $16.27 vs $17.00). | Consider integrating the unit prices basis/reference worksheet into the model to reduce inconsistencies and reduce standalone components. | Unit Rates | AtkinsRéalis | Discrepancies a result of rounding (need to confrim)
9 | IOR | Application of Mining RECLAIM Model feedback into the Oil and Gas RECLAIM Model. | Oil and Gas Producers utilize the "Oil and Gas RECLAIM Model". A similar consultation process should be facilitated for any proposed updates to the Oil and Gas RECLAIM Model. | Conduct a similar consultation and stakeholder engagement process for the Oil and Gas RECLAIM Model 8.0. | Policy | GNWT/CIRNAC
1 | WLWB | Implementation of RECLAIM V8 | It may help reviewers if the authors could describe how they envision the updated model being implemented. For example: - Do the authors intend to start submitting closure cost estimates generated via RECLAIM V8 for all security-related reviews from the date of publication onward? Would this approach include existing projects that have previously had closure costs estimated using V7? Will the authors expect licensees and applicants to use RECLAIM V8 for all closure cost estimates from the date of publication onward? | Please describe how the authors intend to implement RECLAIM V8. | Policy | GNWT/CIRNAC
2 | WLWB | Comparison against current estimates using RECLAIM V7 | The proposed updates in RECLAIM V8 are noted. Based on the proposed updates, closure cost estimates will be higher than when estimated using RECLAIM V7. This could have implications to the mining industry in the north, so it may be helpful for reviewers to have examples of how closure cost estimates using RECLAIM V8 differ from those generated using RECLAIM V7. | Is there data available that compares how closure cost estimates generated using RECLAIM V8 differ from previous estimates generated using RECLAIM V7? If not, could this data be prepared and shared? Or perhaps the authors could estimate how different the closure cost estimates will be? What are the potential implications to the mining industry in the north? | Policy | GNWT/CIRNAC
3 | WLWB | Comparison against known costs to close and reclaim sites | Further to the comment and recommendation above, it may also help reviewers understand the purpose of the proposed changes to the RECLAIM model if data could be provided that compares actual costs to close and reclaim sites to estimates generated using RECLAIM V7 and V8, though, it is not apparent whether this data is available. | Have the authors undertaken an analysis that compares the actual costs to close and reclaim sites against closure cost estimates generated using RECLAIM V7 or V8? Can this data be provided? | Policy | GNWT/CIRNAC | There are sensitives with sharing this data
4 | WLWB | RECLAIM Oil and Gas Model | It is noted this update pertains to the mining version of RECLAIM. Do the authors intend to update the oil and gas model as well? | Are there plans to update the RECLAIM Model for oil and gas? If so, are approximate timelines available, and would the process be similar to this update? If not, please explain why the oil and gas model will not be updated. | Policy | GNWT/CIRNAC
5 | WLWB | User Manual - Discussion throughout on the status of Closure and Reclamation Plans. | The User Manual speaks to the need for applicants and licensees to have CRPs in order to develop closure cost estimates. In some instances, these speak to the need for an approved CRP. For example: - Section 2 Considerations for Northern Settings, “To derive accurate closure cost estimates, it is imperative that the company have an approved CRP which demonstrates a comprehensive understanding…”; and - Section 4.3.1 Engineering Desing, "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities." While it is important to develop a CRP to the point where it can be fully approved, this can take years (specifically for projects that require a type A water licence). This means that closure cost estimates developed during the application phase (pre-construction), during construction, and for the majority of the operational lifespan will be based on CRPs that have not been fully approved. This seems to be acknowledged in Section 4.3.6 Contingency where it is discussed that most CRPs for mining and associated estimates are at the feasibility or advanced conceptual level until near the end of operations. While this helps, it may reduce confusion further if the entirety of the User Manual recognized that CRPs typically require years of development to receive full approval. And for closure cost estimating purposes, it may be more realistic to indicate the applicant/licensee should advance the CRP as early as possible in the project lifecycle. | Consider whether the User Manual should be updated to clarify that it typically requires years to get a CRP fully approved and that applicants/licensees are encouraged to advance closure planning as early as possible. Consider revising certain messages, for example Section 2, to indicate, for closure cost estimating purposes, it is imperative that the applicant/licensee advance the CRP as early as possible in the project lifecycle. | User Manual | Brodie
6 | WLWB | User Manual - Definition of Contingency | A definition for contingency is provided in the Definitions and Acronyms table on page 4. A reference is provided from AACE costing terminology which seems to indicate this definition has been accepted by the construction or engineering community for costing purposes. However, it is not clear whether this definition aligns with how the term contingency is used throughout the document (specifically Section 4.3.6. Contingency) as well as how it is used for the purpose of generating a closure cost estimate via RECLAIM. For example the definition indicates contingency is "Typically estimated using statistical analysis or judgment based on past asset or project experience." Section 4.3.6 does not speak to statistical analysis, rather, the description in this section states "The determination of the contingency percentage is a subjective and project-specific task that relies on the judgement of the estimator." This could create confusion for applicants and licensees in terms of what they are expected to do when proposing contingency percentages. | Review the definition of contingency and consider whether it appropriately speaks to how users of the model are expected to derive contingencies. | User Manual | Brodie
7 | WLWB | User Manual - Section 4.2.5 | This section describes a worksheet within RECLAIM V8 for Interim Care and Maintenance. It states that this worksheet captures the costs from cessation of mining activities to when active remediation begins. Is this meant to only cover the time period from cessation until active remediation? What about the period up to executing closure activities - perhaps the use of the term remediation in this case is analogous to closure activities? Please note that remediation and reclamation in the general sense have different meanings. | Consider whether a revision is necessary to ensure this messaging covers the entirety of the intended period. For example, "the period between cessation of mining activities and when active remediation, or closure and reclamation begins." | User Manual | Brodie
8 | WLWB | User Manual - Section 4.2.6 | This section states "These should reflect the monitoring and maintenance plans and commitments identified in the Closure and Reclamation Plan" and later that "it reflects the monitoring and maintenance commitments in the Closure and Reclamation Plan." The LWBs' Standard Water Licence Conditions include Post-Closure Monitoring and Maintenance Plans, and it is typical for LWBs to require these for projects that require a water licence. Post-Closure Monitoring and Maintenance Plans are the home for the licensee to describe their approach to post-closure monitoring and maintenance. | Consider whether this section should be updated to also reference Post-Closure Monitoring and Maintenance Plans. | User Manual | Brodie
9 | WLWB | User Manual - Section 4.3 | The introductory sentence of this section speaks to indirect costs, indicating they are "typically allocated or spread across all activities on a predetermined basis." It is not clear what is meant by "predetermined basis," though, the final sentence in this section indicates indirect costs are calculated based on professional judgement. Either way, please note that this term / the way it is used could lead the user to think that they determine indirect costs, when, regulatory process-wise, the user proposes indirect costs, just like any other cost, and determinations are by the Land and Water Boards. | Consider clarifying the intent of the term "predetermined basis" and its usage, or whether another term could be used instead. | User Manual | Brodie
10 | WLWB | User Manual - Section 4.3 | The introductory sentence to this section seems incomplete: "Costs not directly attributable to the completion of an activity, which are typically allocated or spread across all activities on a predetermined basis." Pending any revisions as per the above comment and recommendation, should this sentence read as follows?: "Indirect costs are costs that are not directly attributable to the completion of an activity. They are typically allocated or spread across all activities on a predetermined basis." | Consider revising the sentence to improve clarity. | User Manual | Brodie
11 | WLWB | User Manual - Section 4.3 | RECLAIM V8 proposes an increase of 21% in indirect costs over RECLAIM V7, applied to the summary tab. The LWBs are responsible for setting the amount of security. Overall, it is challenging to consider what evidence is required to justify deviations from the "pre-determined" indirect costs when it is unclear how the "pre-determined costs" were derived. It is unclear what considerations went into deriving these percentages, except for the contingency indirect cost, and therefore how any deviations could be considered in the future. | Please clarify whether RECLAIM has considered deviations from the "pre-determined costs" proposed in section 4.3. Is additional information to support these pre-determined costs available? What evidence could be provided to support a deviation from these costs? | User Manual | Brodie
12 | WLWB | User Manual - Administrative Edits | It seems the hyperlinks in the User Manual do not work. | Review and insert links as necessary. | User Manual | Brodie
13 | WLWB | User Manual - Administrative Edits | Should Table 2 Column 3 be titled "Typical CRP Phase"? | For consideration. | User Manual | Brodie
14 | WLWB | Supplementary Information on RECLAIM V8 February 18,2025 | The supplemental information document references a "Technical Work Group and review of actual cost for Mine Closure and Reclamation at various locations across Canada." Further information beyond this has not been provided. It may be helpful to understand the range of projects and range of costs/percentages considered as part of developing the proposed indirect cost percentages. For example, the supporting information for Owners Representative states "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | If possible, provide additional information to understand the range of projects (e.g. size of project, type of mine: open pit, underground, etc.) and range of costs/percentages that were considered as part of developing the proposed indirect cost percentages in RECLAIM V8. | Policy | GNWT/CIRNAC
15 | WLWB | RECLAIM V8 - New Line Item - Finalize CRP (% Closure Costs) | The ICM [Interim Care and Maintenance] tab of RECLAIM V8 includes a new line item titled, "Finalize Closure and Reclamation Plan (% Closure Costs)." This is calculated as 4% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between the cost of finalizing a CRP and the associated direct costs (i.e. closure work), and whether/how this considers how advanced the CRP is. This line item also does not seem to align with the text in section 4.3.1 of the Manual which states "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities (i.e. engineering is not required to develop a closure plan) and that there are no dramatic departures from the approved Closure and Reclamation Plan." | If possible, discuss how the 4% cost proposed was developed and whether/how this considers the varying degree of closure planning across different projects. | Indirects | AtkinsRéalis
16 | WLWB | RECLAIM V8 - New Line Item -HHERA (% Closure Costs) | The ICM tab of RECLAIM V8 includes a new line item "Human Health and Ecological Risk Assessment (HHERA; % Closure Costs)." This is calculated as 3% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between these direct costs and the development of an HHERA, and how the percentage was derived. | Please provide further information as to how the 3% cost proposed for HHERA was derived. | Indirects | AtkinsRéalis
17 | WLWB | Use of Historical Costs | The information provided indicates that costs to clean-up historical federal contaminated sites informed RECLAIM V8. It is noted that the regulatory context and expectations have changed significantly since some of those sites were operational/abandoned. It is unclear how/whether the change in regulatory regime and expectations was considered when reviewing these historical clean-up costs. | Please describe how/whether the change in regulatory expectations was considered when reviewing the historic clean-up costs of federally contaminated sites. | Policy | GNWT/CIRNAC
18 | WLWB | Owners Representative | The supplemental information provided to support the indirect cost associated with "Owners Representative" references support to CIRNAC and scrutiny of the Federal Contaminated Sites Program. Given that the GNWT would be responsible for clean-up for the majority of current projects in the Mackenzie Valley, it is unclear whether GNWT has adopted this same approach to the clean-up of abandoned sites. | Clarify whether the GNWT has adopted this same approach of hiring an Owners Representative. | Policy | GNWT/CIRNAC
1 | IEMA | Post Closure – Annual Requirements | The Post-Closure sheet requires an estimate of annual costs and the number of years of post closure activities. The overall sum of activities is then multiplied by the number of years to give a total cost. Some post-closure activities will likely occur less frequently than annually, and the spreadsheet calculation will not function correctly in these cases. | Revise the Post-Closure sheet to include columns that list the frequency of each activity, and the number of events expected over the post-closure period, rather than assuming that all costs are annual costs. | Unit Rates | AtkinsRéalis
2 | IEMA | ICM – Water Management | The ICM sheet does not include activities specifically focused on water management during interim care-and-maintenance. These costs are also not specifically addressed in the Water Management or Water Treatment sheets. However, water management is often (perhaps usually) a primary focus of interim care-and-maintenance activities at mine sites, including during temporary closures and in the early stages before active implementation of a closure and reclamation plan. Requirements for accessing security bonds typically arise when there is an early, unplanned mine closure. In these circumstances water management is likely to be a significant activity for maintaining water levels in tailings ponds, managing flood flows, managing runoff from disturbed areas, and dewatering of mines (pits and underground). It is not uncommon for dewatering of mines to continue during periods of interim care-and-maintenance, especially in the event of early/unplanned closure when there may be interest in selling the project – allowing mines to flood is often considered to devalue the “asset” and therefore is part of the necessary care-and-maintenance activities. While there are currently no heap leach projects in NWT, water and solution management at heap leach mines is likely to be the largest cost during periods of interim care-and-maintenance. | Revise the ICM sheet to include activities focused on water management that will be required during interim care-and-maintenance. | Unit Rates | AtkinsRéalis
3 | IEMA | Interim Care-and-Maintenance | The Supplementary Information states that the default interim care-and-maintenance period in RECLAIM is 2 years, but the Interim Care-and-Maintenance (ICM) sheet in the model sets the value at 3 years. Past experience indicates that, in the event of early/unplanned mine closure, interim care-and-maintenance periods can be lengthy because of the time required to sort out financial matters, explore sale/re-opening options, complete CRP development/permitting and procure contractors. 3 years should be the minimum period applied. | Clarify the default duration of interim care-and-maintenance as 3 years, as currently applied in the model. | Unit Rates | AtkinsRéalis
4 | IEMA | Water Management - Sediment/Erosion Management and Control | The Water Management sheet addresses closure and reclamation of operational sediment control facilities. However, it does not directly address the potential need for continued sediment control measures during reclamation activities, or after reclamation activities are complete. This could require construction of new sediment control facilities or improvement (e.g., expansion, armouring) of existing ones. It could also require ongoing operational activities to manage sediment. | Revise the Water Management sheet to include lines related to development and implementation of sediment control measures for the closure and post-closure periods. | Unit Rates | AtkinsRéalis
5 | IEMA | UG Mine – Contact Water Management | The UG (Underground) Mine sheet does not include costs for treatment of mine water. The sheet appears to assume that underground mines will be flooded but no treatment would be required. Some mines may fill and drain over time, with water quality that is not acceptable for discharge. In other cases, leakage from the mine through groundwater is possible, again raising possible water quality concerns. These conditions may require some measures for ongoing or periodic water management or water treatment, including possible active or passive treatment outside of the underground mine, or some form of mine-pool treatment within the mine. | Add water management and treatment as potential costs in the UG Mine sheet, linked as appropriate to additional content in the Water Treatment sheet. | Unit Rates | AtkinsRéalis
6 | IEMA | Chemicals – Soil Handling | The Chemicals sheet includes costs for excavating contaminated soils and transporting them to an onsite remediation facility, for example a land-farm. There will also be costs for rehandling these soils to a final disposal location at the conclusion of land-farming. | Revise the Chemicals sheet to include lines for final disposal of remediated soils. | Unit Rates | AtkinsRéalis
7 | IEMA | Post Closure – Maintenance | The scope of maintenance activities described in the Post Closure sheet is limited to covers, spillways and wetland treatment systems. For many mine sites, the maintenance requirements will be much more extensive. For example, tailings dams, diversions and sediment control facilities may all require maintenance. Passive treatment systems other than wetlands may also require maintenance or replacement. Wetlands may also require maintenance that is more extensive than what is described, including removal and replacement of substrates and vegetation after some period of time. In most cases, “passive” treatment systems require some periodic maintenance and operational activities, and are therefore better described as semi-passive. | Expand the maintenance components of the Post Closure sheet to address a broader scope of expected maintenance requirements. | Unit Rates | AtkinsRéalis
8 | IEMA | Rock Pile – Heap Leaching | According to the manual, the Rock Pile sheet is intended to address not only waste rock piles, but also heap leach facilities. Closure of heap leach facilities is usually substantially more complex than for rock piles. Heap leach facility closure entails continued solution circulation, heap rinsing, heap detoxification and associated water treatment, managed draindown, decommissioning of pumping and piping equipment, establishment of permanent drainage systems, among other things. The activities listed in the Rock Pile sheet are not adequate to address potential heap leach facility closure. | Incorporate specific activities and costing for heap leach facility closure in the model. | Unit Rates | AtkinsRéalis
9 | IEMA | Bldgs & Equip – Roads | The Bldgs & Equip sheet is missing some activities that may be common for closure and reclamation of roads. Reclamation frequently includes flattening of safety berms along the length of the road, and establishment of effective road blocks and any access points. Also, complete removal of roads back to the native landscape may be necessary in some cases, or overall re-grading of road embankments. Construction or upgrading of drainage works along road alignments may also be required. | Additional road reclamation and closure activities should be added to the Bldgs & Equip sheet. | Unit Rates | AtkinsRéalis
10 | IEMA | Mobilization – Annual Mobilization | The Mobilization sheet includes a column for quantity of mobilization with each type of equipment or supply. In some cases, mobilization/demobilization of equipment could be required annually through the closure and reclamation phase, or periodically during post-closure. For transparency, it would be useful to separate the quantity and the number of annual mobilization requirements – e.g., how many dump trucks have to be mobilized to site in each year. This would provide a better understanding of the equipment requirements and costs over time, and information about what equipment would be expected to remain on site year-round, versus mobilization each year. | Revise the Mobilization sheet to separately identify the annual mobilization requirements. | Unit Rates | AtkinsRéalis
11 | IEMA | Indirect Costs | The Summary Report and Supplementary Information describe the rationale for proposed changes in the default percentages for indirect costs. The rationale is consistent with experience from mine closure and reclamation projects and with current approaches to engineering. The Summary Report also notes that costs for mobilization and interim care-and-maintenance are now included in the base costs for calculating indirect costs. This also makes sense because both of these costs will be subject to the same indirect costs as the rest of the capital costs. | Retain the proposed default indirect costs percentages and the inclusion of mobilization and interim care-and-maintenance costs as part of the capital cost for calculating indirect costs. | Indirects | AtkinsRéalis
12 | IEMA | Summary – Indirect Costs | N/a | The updates to the recommended percentages for indirect costs appear to reflect the experience with mine closure and reclamation projects and should be retained. | Indirects | AtkinsRéalis
13 | IEMA | User Manual – Section 1 | The final bullet in the list of principles in Section 1 of the User Manual states that financial security must retain its full value throughout the life of the mine and if applicable, beyond. The value of required security may vary through the life of the mine and the wording of the principle should be clarified | The final bullet in the list of principles should be reworded to clearly state that adequate security must be in place throughout the life of the mine and in post-closure to fully address the liabilities associated with the site. | User Manual | Brodie
14 | IEMA | Summary – Future Value | The future value calculations appear to assume that the 3 year period of Interim Care-and-Maintenance starts immediately at the time the calculations are completed. This means that if the security amount is set based on today’s calculations, but unplanned closure begins 1 year later, the security will be 3% too low, or 16% too low if closure begins 5 years later. | The potential shortfall in liability estimates caused by assumptions about timing for the start of interim care-and-maintenance should be addressed in the model. One option is to establish requirements for frequent adjustments of security (e.g., every 2 years) to account for these shortfalls. | NPV | AtkinsRéalis
15 | IEMA | Summary – Future Value | N/a | The addition of future value is a good idea and should be retained. | NPV | AtkinsRéalis
16 | IEMA | Land Reclamation Activities | In response to a comment/recommendation to include a more comprehensive list of land reclamation activities in the model, the Supplementary Information responds that site-specific activities should be proposed based on end land use and the CRP. The response does not address the comment that was raised. Of course, site-specific closure activities should be defined in site-specific CRPs. However, the model is intended to provide a comprehensive tool for estimating costs of closure and reclamation activities, no matter what activities are selected for a specific site. As a result, the model should include a more comprehensive list of land reclamation activities and provide for estimating their costs, as suggested in the comment. The following comments below identify several specific instances where the model should be revised to include more comprehensive listings of activities. While this is likely not a complete list, it should be considered a starting point for more thoroughly identifying potential closure measures and activities. | Undertake a process to develop a more comprehensive list of possible closure and reclamation activities and incorporate these into the costing model. | Unit Rates | AtkinsRéalis & Brodie
17 | IEMA | Water Management - Reclamation Quarries | The Water Management sheet includes costs for installing and removing pumping systems for managing water in a reclamation quarry. Other costs associated with both quarry development (e.g., material testing, land clearing, road development, etc.) and water management (e.g., diversions, sediment control) for reclamation quarries are not addressed. Reclamation activities often require development of new quarries (in undisturbed areas, or in waste [e.g., overburden] storage facilities) or expansion of existing ones to provide the materials necessary for closure and reclamation. | The Water Management sheet should be revised to include lines that address additional water management activities that may be associated with quarries. Costs for quarry development should also be addressed within the overall model. | Unit Rates | AtkinsRéalis
18 | IEMA | Water Management – Passive Treatment | The activities identified for passive treatment are all associated with construction of wetland treatment. There are other forms of passive treatment that may also be relevant, for example permeable reactive barriers, bioreactors or underground mine pool or groundwater treatment. | The Water Management sheet should be revised to include activities that may be associated with other forms of passive treatment that are not wetlands. | Unit Rates | AtkinsRéalis
19 | IEMA | User Manual – Section 4.2.5 | Section 4.2.5 of the User Manual describes expectations for costing for interim care-and-maintenance activities. The description of a typical scenario states that open pit and underground mines would be allowed to flood. In cases of early or unplanned mine closures (i.e., where there are draws on security bonds), there are often lengthy periods of discussion about mine re-opening and sale. In these cases, mine dewatering often continues in order to avoid reducing the value of a potential asset. The assumption that mine dewatering would be discontinued may underestimate the actual costs that would be incurred. | The default assumption for interim care-and-maintenance costing should be that mine-dewatering will continue for this period. | User Manual | Brodie
20 | IEMA | Future Value and Unit Cost Updates | The Supplementary Information describes the new approach taken for estimating the future value for liability estimates. This approach is a positive addition and attempts to address the challenge that the security bonding regime and the forms of security do not allow for bond amounts to grow to address inflation and other escalation of costs. The User Manual defines “escalation” as “a provision in costs or prices for uncertain changes in technical, economic, and market conditions over time. Inflation (or deflation) is a component of escalation.” This acknowledges that inflation is only one component of escalation, with other components (e.g., labour market conditions in northern Canada, or availability of construction contractors) that may also lead to increases in costs. Nonetheless, the User Manual and model only rely on inflation as a cost escalator when calculating future value (Summary sheet) or for updating unit costs (Unit Cost sheet). Other than in the definition of “escalation” there is little further mention of other possible influences on cost escalation, though Section 4.5.1 of the User Manual does identify some other possible sources of information about escalation. | Revise the User Manual and the model to require consideration of other factors for cost escalation. This should include requirements in the User Manual for proponents to provide rationale for selected escalation factors. In the model, it would be useful to include separate entries for inflation and other cost escalators so that there is a requirement to consider whether other escalators are relevant or not. | NPV | AtkinsRéalis & Brodie
21 | IEMA | General Comment – Site Management | The model lacks clear information about person-hours for ongoing administrative responsibilities at the site, for example security, health and safety, personnel management, etc. during the implementation of the closure. Some of these are addressed for interim care-and-maintenance (e.g., on-site caretaker), but would also be required throughout the implementation of closure and reclamation. | Costs for ongoing site management should be addressed either in the Summary sheet, or an additional Site Management sheet should be added. | Unit Rates | AtkinsRéalis
22 | IEMA | Water Treatment – Post Closure | The post-closure component of the Water Treatment sheet does not address major maintenance and equipment replacement activities. Water treatment facilities that have to operate in a long post-closure period will wear out and require refurbishment and replacement at some point in time. Costs and timing for these major capital expenditures need to be included. | Revise the Water Treatment sheet to include lines for costs related to major refurbishment or replacement of post-closure water treatment facilities. | Unit Rates | AtkinsRéalis
23 | IEMA | General | The Independent Environmental Monitoring Agency (Agency) has reviewed the proposed changes for RECLAIM v8.0 and associated user manual (RECLAIM) submitted by Crown-Indigenous Relations and Northern Affairs Canada (CIRNAC) and the Government of Northwest Territories (GNWT). The Agency submits the following comments for your consideration. | N/A | Policy | AtkinsRéalis | See Comments 24 to 32
24 | IEMA | User Manual – Section 1 | Section 1 of the User Manual states a principle that costs should be based on having a third-party contractor carry out the reclamation work. On-site equipment including both mobile equipment and fixed facilities (e.g., water treatment plants) may not be owned by the proponent and costs would be incurred to access the equipment and facilities. | The principle that costs should be based on the cost of having work done by a third-party contractor should be expanded to clarify that the costs must also be estimated assuming that all equipment, supplies and facilities will be provided separately. | User Manual | Brodie
25 | IEMA | Tailings – Water Treatment | The Tailings sheet refers to treatment of seepage, which may not be the only treatment that is required for a tailings facility. In some cases, treatment of tailings pond supernatant water may also be required, either during implementation of closure and reclamation, or post-closure. | Revise the water treatment references in the Tailings sheet to include broader references to types of treatment that may be required. | Unit Rates | AtkinsRéalis
26 | IEMA | Open Pit – Pit Closure Methods | The Open Pit sheet considers a narrow range of potential closure options for pits, focused on flooding of pits. There are other options for closure of pits that need to be addressed. For example, some pits may be closed in a dry condition, with associated water management, or some may be backfilled with waste and covered (e.g., Giant Mine Remediation Project). | Revise the Pits sheet to address a broader range of closure options for pits. | Unit Rates | AtkinsRéalis
27 | IEMA | Open Pit – Contact Water Management | The only water treatment option addressed in the Open Pit sheet is the possible addition of in-pit treatment during flooding – either by chemical or biological means. There is no water treatment line linked to the Water Treatment sheet. However, there are some instances where it may be necessary to actively pump and treat water that has accumulated in a pit, potentially before flooding, or to establish dry conditions. | Add active water treatment as a potential cost in the Open Pit sheet, linked as appropriate to additional content in the Water Treatment sheet. | Unit Rates | AtkinsRéalis
28 | IEMA | HHERA and Regulatory | The Summary Report states that the model was revised to include 3% indirect costs for Human Health and Ecological Risk Assessment (HHERA), and 4% indirect costs to finalize the Closure Reclamation Plan (CRP). These additions make sense, but it is unclear where they are included in the model. If they are already included in the Summary sheet calculations, they should be specifically identified. | Provide additional clarity about where the indirect costs for HHERA and CRP finalization are incorporated into the model. | Indirects | AtkinsRéalis & Brodie
29 | IEMA | General Comment – Winter Road costs | The Water Treatment and Mobilization sheets include lines for costs associated with use of the winter road. In Water Treatment this appears to be related to site access and reagents, while in Mobilization it is related to equipment, fuel and accommodation (i.e., camp), with a focus on materials that must be brought to site. However, closure for some other components (e.g., buildings, hazardous wastes, contaminated soils) may require shipping off site. Also, it is not clear that winter road costs have been incorporated for all closure and reclamation supplies, for example liner construction materials. These activities may also incur winter road costs. | Where closure and reclamation activities will require off-site shipping or the delivery of supplies to site, sheets should be revised to include lines for winter road costs and other shipping costs. | Unit Rates | AtkinsRéalis
30 | IEMA | Summary – Future Value | The spreadsheet requires the user to enter timing for “when will post-closure begin”, by entering a number. Some additional clarity should be provided about what this number represents: Is it the number of years from the current time until post-closure, or the number of years between cessation of operations and post-closure, or the number of years after completion of interim care-and-maintenance before post-closure begins, or some other value? If the timing is intended to start at the time that the estimate is made, then the same shortfall issues identified above for the interim care-and-maintenance timing will also apply to the timing for start of post-closure. | Clarify the intended definitions of timing for when post-closure will begin. | Unit Rates | AtkinsRéalis
31 | IEMA | User Manual – Section 2 | Section 2 of the User Manual describes special considerations for estimating costs for reclamation activities in northern settings. One important factor that appears to be missing is the potential cost implications of meeting requirements for northern participation in contracting and work opportunities. | The bullet list of factors that may affect costs for projects in northern settings should be expanded to include the potential for increased costs associated with meeting requirements for northern participation in reclamation activities. | User Manual | Brodie
32 | IEMA | Buildings & Equipment (Bldgs & Equip) – Landfill | The Bldgs & Equip sheet addresses closure of landfills (e.g., placement of cover material) but it does not cover the cost of constructing a landfill. Even for non-hazardous materials, construction of landfills can be a substantial cost. Landfills developed and used during mine operations typically do not have capacity to contain all of the material arising from closure and reclamation. Costs for non-hazardous landfill construction can be substantial in some cases (e.g., Giant Mine). | Revise the Bldgs & Equip sheet to include costs for development and construction of landfills. | Unit Rates | AtkinsRéalis
1 | Teck | Feedback Letter | Please see initial feedback in the attached letter. Inflation Application Without Discounting. The RECLAIM 8.0 update proposes incorporating inflation into cost estimates but does not address the standard practice of discounting to reflect the time value of money. Applying inflation without discounting leads to distorted financial obligations, potentially resulting in excessive and unrealistic financial security requirements. Without discounting, even minimal recurring annual costs (e.g., $20,000 per year) would result in infinite bonding requirements, which contradicts financial principles and international best practices. Financial assurance practices that deviate substantially from international best practices may place the region at a competitive disadvantage, while failing to deliver real benefits | Paraphrased: Include discounting into cost estimate | NPV | GNWT/CIRNAC
2 | Teck | Feedback Letter | Please see initial feedback in the attached letter. Absence of Any Credit for Company Size and Environmental Performance We believe the bonding requirements should take into account both past environmental performance and the financial resources available to the company to meet its environmental liabilities. Teck is one of several International Council on Mining and Metals (ICMM) member companies operating in the region. No ICMM member company has ever defaulted on its closure obligations, nor would doing so be feasible in the context of maintaining a global social license to operate. | Paraphrased: Credit for environmental performance and the financial resources | Policy | GNWT/CIRNAC
1 | PPML | Increased Unit Costs | Please see initial feedback in the attached letter. The justification for increased excavation and hauling costs (e.g., short-haul soil movement increasing from $4.3/m³ to $17/m³) lacks transparency on how these figures were derived. What specific contractor quotes, productivity rates, or haul distances were used in these calculations? Were regional variations considered, or was a blanket rate applied regardless of site-specific factors? Can industry propose alternative short-hauling costs based on regional/site-specific factors such as terrain, available borrow pits, road conditions, access to rail, and equipment availability? For example, a mine site with established all weather and paved road networks and short, efficient haul routes may have significantly lower hauling costs than a remote site requiring seasonal ice road access. Will proponents have flexibility in presenting alternative cost estimates to justify lower unit costs? | Paraphrased: Provide more detail on unit rate development. Unit rates should include regional variation. Clarify if user-specified rates can be used in RECLAIM. | Unit Rates | AtkinsRéalis
2 | PPML | Higher Indirect Cost Percentages | Questions Asked Contingency Increase (20% to 25%): While uncertainty exists in closure planning, what empirical data justifies a 25% contingency rather than the previous 20%? Can examplesof cost overruns from past projects be provided to support this increase? Engineering Design (5% to 8%) & Project Management (5% to 10%): These increases suggest significantly greater complexity in closure execution. What historical data from northern mine sites demonstrate that these cost assumptions are necessary? Bonding/Insurance (1% to 3%): Can specific case studies or actuarial assessments be provided to validate this change? | Paraphrased: Provide further justification to increased contingency percentages. Provide further northern justification to increased engineering design percentages. Provide case studies to justify increase in bonding/insurance percentage. | Indirects | AtkinsRéalis
3 | PPML | Reclassification of Mobilization and Interim Care & Maintenance (ICM) as Capital Costs | Moving these costs to Capital Costs now subjects them to contingency and indirect cost multipliers. How does this align with the principle of accurately reflecting third-party contractor costs? Industry projects varying durations of ICM depending on site conditions. How was the assumption of a minimum 3-year ICM period determined, and why is it being applied universally? | Paraphrased: Include more rationale as to why Mob and ICM were moved to Capital Costs and whether this accurately reflects third-party contractor costs. Provide rationale and justification for minimum 3-year ICM period. | Indirects | AtkinsRéalis
4 | PPML | Owner’s Representative Cost (10% of Direct Costs) | This is a new addition to RECLAIM. While we acknowledge the role of an Owner’s Representative in some government-managed projects, why is this now mandated for all projects, including those with active operator management? Can industry proponents provide alternative methodologies for project oversight rather than defaulting to a 10% additional cost? | Paraphrased: Provide rationale for why Owners Rep costs are applied to all mines. Can industry propose an alternate methodology for oversight rather than the default. | Indirects | AtkinsRéalis
5 | PPML | Human Health and Ecological Risk Assessment (HHERA) Cost (3% of Capital Costs) | Industry already conducts environmental monitoring as part of regulatory requirements. What additional studies are being assumed under this cost, and how is the 3% figure justified? Given that mines with comprehensive monitoring programs may already demonstrate minimal risk, why is this cost not applied selectively based on site-specific needs? Can proponents outline their monitoring programs and propose a more phased cost-structure alignment with project-specific timelines? | Paraphrased: Can CIRNAC and GNWT provide additional studies to industry to justify the 3%? HHERA should be applied to mines selectively based on environmental performance. There should phased cost structure that could align with project timelines. | Indirects | AtkinsRéalis | Not sure what is meant with third recommendation.
6 | PPML | Future Value Calculation (3% Inflation Rate) | While inflation is a factor in cost projections, applying a fixed 3% escalation rate does not account for fluctuating economic conditions. Has any sensitivity analysis been conducted to assess alternative inflation scenarios? Can proponents propose their own escalation methodologies based on contractual arrangements and project-specific timelines? | Paraphrased: Sensitivity analysis should be conducted on applying a fixed inflation rate for future value calculations. Proponents should be able to propose their own escalation methodologies based on contractual arrangements and project-specific timelines. | NPV | AtkinsRéalis
1 | De Beers |  | De Beers is supportive extended engagement period granted to allow further opportunity for industry feedback to be considered into any changes. The initial deadline coincided with our annual reporting timelines, creating challenges in dedicating the necessary time and resources to this review. The additional time granted will allow us to prepare a thorough and well-considered submission that adequately addresses the updates. Given the potential for significant implications to the mining industry, the proposed changes to the RECLAIM model require significant time and resources to allow for a detailed review by all parties. De Beers looks forward to partaking in further engagement sessions and will provide more detailed comments following that period. | N/A | Policy | GNWT/CIRNAC
1 | DFO | Financial security associated with Fisheries Offsetting Plans. Specified under Section 2 (1)(b) and Schedule 1, Section 16, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations. | Fisheries and Oceans Canada (DFO) would like to thank CIRNAC and the GNWT, for developing and updating the RECLAIM model and providing this opportunity for review and comment. The RECLAIM model can be an important part of the Fisheries Act authorization process in that the model is often used by proponents when developing an itemized list of costs for conducting the Offsetting work and monitoring the project to inform the Letter of Credit associated with an Offsetting Pan, and by DFO when reviewing the financial liability associated with these plans. Fisheries Act authorizations can follow the lifecycle of a mine from pre-operational permitting to post-closure Offsetting Project monitoring. Financial liability and associated security in the form of an irrevocable Letter of Credit, is a key component of the Fisheries Act and associated Regulations. Mine development in Nunavut and the Northwest Territories often necessitates activities that directly or indirectly result in the Death of Fish, the Harmful Alteration, Disruption or Destruction of fish habitat, and/or the deposit of deleterious substances in water frequented by fish, governed respectively by Section 34.4, 35, and 36 of the Fisheries Act. These activities can be authorized under the Fisheries Act so that the activity is carried out in accordance with conditions set out in the authorization and the Regulations. Section 2 (1)(b) and Section 16 of Schedule 1, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations, requires the development of a Fish Offsetting Plan, including the financial liability and associated security, to cover the costs of implementing the fish Offsetting Plan. These Fish Offsetting Plans often include activities associated with general construction, ground and water works, culvert installation, long-term monitoring, etc. Costs associated with these Fish Offsetting Plan activities can be subject to individual cost estimates based on a proponent’s experience and can also be scrutinized with limited referenceable sources. This type of subjective cost estimation and review creates risk and introduces uncertainty, for both proponents and liable governmental parties (DFO and ECCC). DFO believes this update to the RECLAIM model is an excellent opportunity and the appropriate location to include constrained cost estimates for these types of activities. DFO would like to discuss this further with CIRNAC and the GNWT during the week of May 12 - 16, 2025. DFO would also be interested in hearing feedback from all interested parties. | DFO recommends that the RECLAIM Model include in a Summary line item, and associated sheet in the Excel model specific to the implementation of a fish Offsetting Plan. This could include, but not limited to works associated with discipline specific construction, ground and water works, culvert installation, and long-term monitoring. Adding this to the model would reduce financial risk by providing a more predictable process of securing a Fish Offsetting Plan, which is ultimately tied to the final reclamations of a mine site that has impacted fish and fish habitat. DFO would like to discuss this possibility with CIRNAC, the GNWT, and all interested parties during this update of the RECLAIM model. | Policy | GNWT/CIRNAC
1 | ACDC | Letter | Please see attached letter. | N/A | Policy
2 | ACDC | Origin of Unit Rates | Burgundy Diamond Mines (Burgundy) and other proponents have been requesting that CIRNAC and GNWT provide the level of transparency and justification for RECLAIM unit rates that is demanded of proponents who put forward site-specific unit rates. This long-standing request remains wholly unsatisfied by the information provided with RECLAIM 8.0. For example, the proposed "load/haul/place" unit rates are described as being derived from "First Principles". However, simply referencing "First Principles" and listing a few assumptions under additional notes does not provide proponents with the information needed to adequately understand the unit rate or assess appropriateness for a specific site. | RECLAIM 8.0 should be accompanied by clear, detailed data on the derivation of the proposed unit rates, ensuring proponents can adequately understand the rates and make a rational determination of their appropriateness for an individual site or closure activity. | Unit Rates | AtkinsRéalis
3 | ACDC | Moving Mobilization and ICM to Capital Costs | Mobilization and ICM costs were previously included under Indirect Costs which excluded them from the indirect percentage calculations. The new approach introduces a compounding effect and will significantly inflate the overall security estimate. This would result in overestimations that do not accurately reflect actual closure and reclamation needs particularly for major operations such as Ekati Diamond Mine (Ekati) with substantial security requirements. | The Mobilization and ICM costs should be maintained under Indirect Costs where the existing indirect cost percentages can adequately account for variations. This would avoid the compounding effect introduced by their inclusion in Capital Costs while still ensuring these costs are adequately captured within the model. | Indirects | AtkinsRéalis
4 | ACDC | Owner's Representative | A new line has been added under Indirect Costs for Owners Representative to ensure that project objectives are met, with a default percentage of 10% of the direct costs assigned. The assigned percentage appears excessively high particularly for licencees with substantial direct costs. | The assigned 10% default percentage should be reevaluated and a reduction considered to better align with actual project requirements and industry norms. Additionally, more information should be provided to clarify the methodology and rationale behind determining this percentage and to assess its applicability across different projects. An alternate approach, such as an estimated cost (rather than a percentage) should also be developed and evaluated. | Indirects | AtkinsRéalis
5 | ACDC | HHERA and Final CRP Costs | The cost to complete a Human Health and Ecological Risk Assessment (HHERA) and Final Closure and Reclamation Plan (FCRP) has been added to the model at 3% and 4% of Capital Costs, respectively. While it is acknowledged that FCRP costs may not have been explicitly included in RECLAIM 7.0, the regular review of security estimates has ensured their incorporation for operations like Ekati. The most recent review by the GNWT in 2022 determined a significantly lower FCRP rate of approximately 1% of direct costs. There is no rationale for applying these items as a percentage of total rather than an estimated cost. These items are well established and well defined in scope and cost such that actual estimates can readily be developed. A percentage of total as proposed provides a grossly over-costed estimate for large site such as Ekati. Moreover, the risks addressed by HHERA are already evaluated as part of the permitting process. Monitoring data is utilized to assess operational and closure risks, which are accounted for in interim CRPs that are mandatory and regularly updated. As such, the addition of these costs in the proposed model is deemed unnecessary and the proposed percentages appear excessively high. | Burgundy recommends that HHERA and FCRP costs be excluded from the model. Alternatively, these percentages should not be based on Capital Costs given that risk evaluations and FCRP development will rely significantly on existing assessments and CRP plans developed during ongoing operations. A reduction or redefinition of these percentages is necessary to ensure they more accurately reflect the actual scope of work and associated costs. An alternate approach of an estimated cost (i.e., not a percentage) should be developed and evaluated. | Indirects | AtkinsRéalis
6 | ACDC | Future Value Calculation | The future value calculation has been introduced to capture the anticipated costs of activities based on when they are expected to occur. A default inflation rate of 3% is applied which corresponds to the Bank of Canada’s upper target for annual inflation. For example, a cost estimate developed in 2028 using RECLAIM 8.0 standard rates would undergo a 3% annual inflation increase over four years (2024 to 2028). However, applying a predetermined, singular inflation rate is not appropriate when actual data is available. It is also not always suitable to apply the same inflation rate across all work included in a closure estimate. RECLAIM 8.0 documentation acknowledges the existence of various inflation estimates beyond the broad-based consumer-oriented CPI, but it discounts these approaches. Since the majority of mine closure plan costs are not consumer-oriented, it may not be appropriate to apply the general CPI across the entire estimate. Ekati's security estimates already incorporate an inflation calculator developed with stakeholders' input. This calculator considers the development year of each unit cost and applies inflation rates accordingly, resulting in inflation rates of less than 2%. Applying the upper target of the Bank of Canada’s inflation range may lead to overestimations, given that average inflation rates have remained between 1.5% and 2%. This approach is not ideal for long-term mine closure costing, as it introduces inflation without accounting for interest. It assumes that the financial security is cash in hand, which does not accrue interest over time. By comparison, the Province of British Columbia uses a net discount factor (i.e., net of both inflation and interest) for recurring long-term costs. The approach proposed in RECLAIM 8.0 introduces a substantial cost factor that could significantly affect project viability. This issue requires detailed engagement and financial analysis by the government before any consideration for implementation. | 1. RECLAIM 8.0 should provide a clear rationale for adopting a single pre-determined inflation factor and consider developing an alternative approach that utilizes inflation rates most appropriate to the specific work and costs within the closure cost estimate. The future value inflation rate should be revised to reflect a more accurate figure, such as the average of historical inflation data over a relevant timeframe, rather than defaulting to the upper target of 3%. This adjustment would result in a more balanced and accurate estimate, avoiding excessive conservatism in the model. Additionally, greater transparency is needed in how inflation rates are applied to different unit costs over time to ensure consistency and confidence. 2. This cost item should not be implemented without specific, in-depth engagement and financial analysis including an evaluation of experiences in other regulatory jurisdictions. | NPV | GNWT/CIRNAC
7 | ACDC | Incentivizing Progressive Reclamation | The proposed updates to RECLAIM 8.0 emphasize increasing securities to address potential reclamation costs. It is equally important to incentivize progressive reclamation during operations. Progressive reclamation not only reduces overall closure liabilities but also demonstrates ongoing commitment to environmental stewardship. Models used in jurisdictions such as Quebec and the Alberta oilsands provide practical examples of incentivizing progressive reclamation by allowing operators to utilize existing securities during operations, thereby encouraging earlier action rather than deferring it until closure. | Burgundy recommends that the GNWT implement mechanisms to incentivize progressive reclamation activities during operations. This could include provisions that allow for the partial release or reallocation of securities to fund reclamation efforts. Such measures would enhance operational efficiency, reduce the financial burden of increasing securities and encourage operators to proactively incorporate reclamation into their operational plans. This approach would ultimately lead to more sustainable and cost-effective closure outcomes. | Policy | GNWT/CIRNAC
1 | Tlicho | General | The Tłı̨chǫ Government reviewed CIRNAC and GNWT's proposed revisions to RECLAIM 8.0, the RECLAIM User Manual, and supporting documentation. These documents are used by the GNWT, CIRNAC, mining companies, and the Land and Water Boards to set mining security deposits. RECLAIM and the User Manual are also a resource for all parties reviewing security deposits. Tłı̨chǫ Government may also wish to use RECLAIM to estimate security deposits for future mines on Tłı̨chǫ Lands. | N/A | Policy | GNWT/CIRNAC
2 | Tlicho | Increased security deposits | RECLAIM 8.0 includes numerous substantial increases. Most unit costs went up to varying degrees, and a few went down. On average unit costs appear to have more than doubled. Some key unit costs have increased far more than this, for example the lower estimate for winter road construction went up by more than 10 times. Indirect costs are now up to 58% of direct costs instead of 32%, plus there are new costs for a human health and ecological risk assessment and finalization of the closure plan (totaling 7% of capital costs). There is also a newly proposed cost for inflation during closure and post-closure. Post-closure monitoring and maintenance and mobilization/demobilization now have indirect costs (as percentages) added to them. These and other increases would result in very large increases to security deposits at existing mines. CIRNAC/GNWT explained that the increases are because the current unit costs (in RECLAIM 7) are more than 10 years old and because costs in the current RECLAIM spreadsheet (version 7.0) are too low compared to actual costs the government has incurred for actual reclamation projects. As noted in "Review of Mine Financial Security Estimates and RECLAIM": "it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." CIRNAC and its consultants are perhaps in the best position to provide actual costs of closure activities. There has been talk over the years that RECLAIM is dramatically underestimating closure costs. It is possible that even with the proposed revisions, RECLAIM 8.0 would continue to underestimate reclamation costs. For example, the Supplementary Information provided on Feb 18 says that the Owner's Representative costs are actually 12% to over 20% of costs, not the 8% adopted in the proposed revisions to RECLAIM. This is just one of several examples that may mean the RECLAIM 8.0 continues to underestimate reclamation costs. Others are in comments below. | RECLAIM should estimate the actual costs of closure and reclamation, even though it appears that the new estimates will likely be much greater than current security deposits. However, this does not mean that the Boards should immediately increase all security deposits in the North to reflect actual reclamation costs. This could have serious economic and social repercussions, and could undermine the objectives set for resource management under the modern treaties, to balance conservation and development for 'optimum benefit'. Instead, updating RECLAIM to reflect actual costs is a necessary first step to fixing some serious and far-reaching problems related to security deposits and more broadly to sustainable and responsible mining in the North. Actual reclamation costs must be known and on the table in order to have informed discussions about the impacts, benefits, and risks of mining, including the risk of having to pay for cleanup of abandoned mines. Underestimating security can also enable companies with insufficient financial resources to mine in the North, which poses a serious risk to the Northern economy and the environment. Greater attention should be given to a mining company's financial health and the risks for each project (e.g., risks from market conditions, remoteness, logistical issues, etc.) when weighing the impacts, benefits, and risks of approving a full-scale mine. Decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis, and input from citizens and residents. If the federal and territorial governments, or the Boards in working to achieve the treaty-based objectives for resource management, wish to offset the burden of posting security for actual reclamation costs, this should be done in a transparent, carefully considered manner informed by the actual costs of clean-up and the views of all parties. The Tłı̨chǫ Government would like to be involved in any such discussions, and as a treaty partner, must be involved in these discussions. Other topics raised in our comments are inextricably intertwined with the issue of RECLAIM estimates, for example relinquishment of liability, promoting progressive reclamation, and financial security for potential disasters. These issues should be discussed holistically along with RECLAIM updates. Some of these issues may need legislative amendments to properly address them in the long run. | Policy | GNWT/CIRNAC
3 | Tlicho | Increased security deposits - incentives for progressive reclamation | The RECLAIM Manual includes a policy that the security deposit cannot be reduced for progressive reclamation (reclamation completed during operations) until the mining company has completed the reclamation work. This is a sensible approach to ensure there is always enough money for reclamation if a company goes bankrupt. However, a more refined and strategic approach to this problem should be considered to enable work to proceed while limiting risks if a company goes bankrupt. This would allow more parts of a mine to be reclaimed early in the mine life, which benefits the environment, the taxpayer, and the company. A company's financial capacity, the financial and environmental risks of leaving parts of the mine unreclaimed, and other factors would need to be considered. | Financial mechanisms to promote progressive reclamation should be evaluated and discussed with all parties. | Policy | GNWT/CIRNAC
4 | Tlicho | Increased security deposits - case studies | Based on our participation at the meeting hosted by CIRNAC and GNWT during the PDAC conference in March 2025, we understand there may be disagreement over whether RECLAIM 8.0 is overestimating or underestimating closure costs. CIRNAC and the GNWT have actual cost data from abandoned mine reclamation in the North. Using this data to validate RECLAIM 8.0 is an indispensable step to deal with these opposing views and to ensure security deposits cover the full costs of reclamation without unduly burdening industry. The Discussion Paper says that CIRNAC and GNWT had originally intended to use historical data to help populate RECLAIM 8.0 (which is different than historical data for validation). However, the Discussion Paper says this did not happen because "contractor confidentiality, limited examples available to provide a sufficient range and average of costs (which can vary considerably depending on the size and scope), and the effort required to synthesize data." While these issues might make it challenging to use historical cost information to update RECLAIM 8.0's costs and assumptions, it should not prevent validation of the model. Validation is about running information from past projects through RECLAIM 8.0 and comparing this to the actual cost of the project. If confidentiality issues cannot be addressed, CIRNAC and GNWT should at least conduct this validation step internally and publicize whether the exercise validated the model. Further, "the effort required to synthesize data" may be a barrier, but it is arguably a relatively small price to pay compared to the benefits of improved cost estimates. In addition to this validation step, CIRNAC and GNWT should use historical cost data to improve RECLAIM. Based on the unit cost reference tables provided as supporting documentation, it appears this may have been done to some extent. If not, CIRNAC and GNWT should take advantage of historic cost data in ways that maintain confidentiality and account for limitations in the data. | 1. Before finalizing RECLAIM 8.0, CIRNAC and GNWT should validate it, by running RECLAIM (i.e., entering actual quantities, selecting the appropriate unit costs, etc.) with information from actual reclamation projects at abandoned mine sites. The resulting RECLAIM 8.0 estimate should be compared to the actual cost. If these are substantially different, adjustments should then be made to RECLAIM 8.0 from lessons learned from this comparison. 2. Historical cost data should also be used, to the extent possible, to update RECLAIM with actual cost information, without compromising confidentiality. | Policy | GNWT/CIRNAC
5 | Tlicho | Internal government costs | RECLAIM does not include the substantial internal costs for CIRNAC and GNWT, for example government employee salaries. This means there is no transparency about what these costs are or what the actual costs are when a mine is abandoned. | Please explain why these costs are not considered when estimating the costs of reclaiming a mine. | Policy | GNWT/CIRNAC
6 | Tlicho | Calculating security annually | The proposed RECLAIM Manual update includes a new requirement that "The total financial security for final reclamation required at any time during the life of the mine should be equal to the total outstanding reclamation liability for land and water combined (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period)." This mirrors the Mine Site Reclamation Policy for the NT, which is well over 20 years old. It is not clear how this would be implemented. Is GNWT/CIRNAC anticipating that water licences would have a schedule with annual increases to security? This has not been recent practice. Or is a RECLAIM review anticipated each year? TG is concerned that this would place a big resource demand on all parties. Also, how would the common practice of increasing security at project milestones (e.g., commencement of construction, mining, or milling, percent of pit filled, etc.) fit into this approach? | Clarify how this requirement would be implemented. | Policy | GNWT/CIRNAC & Brodie
7 | Tlicho | Human health and ecological risk assessment | The proposed revisions to RECAIM include the cost of a human health and ecological risk assessment (HHERA). The User's Manual notes that this is completed in accordance with federal risk assessment guidance. Modern mines are different than mines abandoned in the past in that they have approved closure objectives and in many cases, approved closure criteria. It is our understanding that, in the past, HHERAs at federal sites have been used to set the standard for cleanup, for example the water or soil contaminant thresholds that must be met. If a modern mine is abandoned during operations and is in compliance with its water licence, land use permit, and other authorizations, unexpected contamination (beyond what is addressed in the approved closure plan) may be less than in the past. Some mines may include an HHERA in their approved closure plan to confirm predicted risks. However, it is not clear what role an HHERA would play at an abandoned mine. We are concerned that use of HHERA's could lower the standard compared to approved closure criteria. Closure criteria have been publicly reviewed, vetted and debated in countless workshops, and represent substantial input from all parties. Closure criteria have been deliberated by the Boards and Board decisions on them have been transparently documented. Ignoring approved closure criteria after abandonment would be inconsistent with the land claim agreements that established the Land and Water Boards. | If an HHERA is part of an approved closure and reclamation plan, then the cost of it should be in RECLAIM. Also, if the GNWT and CIRNAC expect that new risks will emerge after abandonment of mines with modern, approved closure plans, then an HHERA should be a default cost in RECLAIM. However, the RECLAIM Manual should acknowledge that Board-approved closure criteria are the clean-up standard at abandoned mines, unless it is demonstrated that these cannot be achieved or that new criteria are needed for risks that developed after abandonment. An HHERA may play a role in this effort, but HHERA's should not be a replacement for closure objectives and criteria. | Indirects | AtkinsRéalis & Brodie
8 | Tlicho | Monitoring | The draft RECLAIM Manual says that monitoring will be conducted "with respect to the effectiveness of the mitigative measures, the accuracy of the environmental assessment and any unforeseen environmental impacts". Although true, this statement does not appear to reflect current practice. To our knowledge, all closure plans (and therefore security deposits) in the NT are founded on the MVLWB/AANDC Guidelines for the Closure and Reclamation of Advanced Mineral Exploration and Mine Sites in the Northwest Territories. Therefore, all mines have Board-approved modern closure plans that are based on closure goals, principles, closure objectives and closure criteria. This means closure criteria will dictate monitoring plans and duration. The effectiveness of mitigative measures and the accuracy of the environmental assessment will be reflected in the criteria. If there are unforeseen environmental impacts, closure criteria should be updated. | The RECLAIM Manual should state that monitoring will depend on closure criteria. | User Manual | Brodie
9 | Tlicho | Relinquishment of liability | The revised Manual states that "Following mine closure, mining companies or their future owners should continue to be responsible for the site , including the remediation of any additional environmental complications which develop." This raises questions about relinquishment of liability. For many years, many parties have been requesting clarity on how liability will be relinquished at mine closure. This is especially important with mines like Diavik approaching the end of operations. This gap creates uncertainty and may inhibit investment in sustainable and responsible mining in the North. | 1. It is understood that additional policy, legislative, or regulatory amendments may be needed to address how and to what extent companies are released from liability once all closure criteria have been met. For example, will companies be required to leave funds for future monitoring, maintenance, or unforeseeable events at the closed mine? These funds may require supporting legislation and/or policy. Even if the GNWT cannot undertake an effort to better address relinquishment before the RECLAIM updates are finalized, the Manual (or another document) should include more information on this topic. This would assist all parties in understanding how GNWT and CIRNAC will approach relinquishment of liability under existing legislation. 2. The GNWT and CIRNAC should immediately begin the effort to outline the conditions and criteria that will allow relinquishment, establish how much money will be required for monitoring, maintenance and unforeseeable events, clarify the extent to which companies will be released from liability, and develop a relinquishment process. This effort will need to involve Indigenous Governments early on. | Policy | GNWT/CIRNAC
10 | Tlicho | Performance holdback | The revised Manual states that "If the company carries out progressive reclamation during operations as proposed, such as revegetation of disturbed areas during operations, then the closure cost estimate could be reduced by the associated costs for that component when the company demonstrates that the closure activity has been successfully completed and closure objectives and criteria have been met." It is our understanding that the LWB/GNWT/CIRNAC Guidelines for Closure and Reclamation Cost Estimates for Mines allows for some money to be refunded to companies, even if criteria have not been met. This is allowed so long as a performance holdback is set. The same Guidelines explain how a performance holdback could be set, including three different methods. The first method uses a simple percentage-based approach by mine component, the second method uses RECLAIM, and third uses a "factored risk" approach. | RECLAIM should reflect the CIRNAC/GNWT/LWB Guidelines as they relate to performance holdbacks. Calculations based on the Guidelines should be inserted into RECLAIM. This would include simple calculations supporting Table 1 of the Guidelines (the percentage-based approach). It could also include calculations to support the "factored risk" approach on page 19 of the Guidelines. Support for companies to estimate performance holdbacks will promote a quicker and more efficient security refund process. Although all regulators that use RECLAIM may not require performance holdbacks, those regulators could simply ignore the calculations, or the GNWT could develop them for use in the NT only. While it is beneficial to have only one version of the RECLAIM model across the North, add-ons to reflect jurisdictional differences could help to ensure that RECLAIM is useful everywhere while maintaining a core set of shared calculations and inputs. | Policy | GNWT/CIRNAC & Brodie
11 | Tlicho | Documentation of security refunds | Similarly, security refunds for completed progressive reclamation or completed work during active closure is becoming more common and is an important way to promote and reward early closure work. Currently, RECLAIM does not document these refunds, which means there is no record of the original estimate, the refunds given, and what the refund was based on. This may make it difficult to determine refunds during active closure, since it may not be clear what has already been refunded and what is still being held as security. | RECLAIM should document all security refunds. For example, RECLAIM could include a refund summary sheet showing the original estimate, all refunds, and links to documentation supporting the refund (e.g., RECLAIM estimates used to calculate refunds, Board decisions, etc.) | Policy | Brodie | This cost estimating tool is not the mechanism for tracking security refunds
12 | Tlicho | Disasters | RECLAIM does not cover the costs of disasters. With numerous mines using the RECLAIM model across Canada's North, there is a significant risk that one or more of these mines will have an environmental disaster during the life of the mine. Currently, disaster clean-up costs would fall entirely to the taxpayer. The recent disaster at the Eagle Mine in Yukon is an excellent demonstration of how the taxpayer will be forced to carry the burden of disaster clean-up. Such costs could easily be in the hundreds of millions of dollars or more. The Mount Polley disaster in 2014 is another example of taxpayers covering significant costs for a mining disaster. Although this may be considered a policy decision that is outside of the scope of RECLAIM, RECLAIM by necessity houses many policy decisions by virtue of the costs it includes or excludes. RECLAIM unavoidably sets policy through its underlying principles and assumptions. Excluding disaster costs is as much a policy decision as including them. | Security for potential future disasters should be required. Since most mines are unlikely to experience a disaster, the amount held by any single mine should only be a fraction of potential disaster clean-up costs. This could be determined based on the risk profile of a project (e.g., potential for acid drainage, geotechnical failures, proximity to highly valued areas, etc.). If disaster costs are not included in RECLAIM, another mechanism is urgently needed to ensure that industry contributes towards a pot of money for future disasters. | Policy | GNWT/CIRNAC
13 | Tlicho | Revegetation | Revegetation of a site after closure is an important part of restoring the land, enabling long-term future cultural use, making the site look and feel like the surrounding area, and supporting wildlife. The revegetation unit costs in RECLAIM include seeding and tree planting. Planting cuttings, transplants, or plugs are other examples of revegetation, and likely have different costs than seeding and tree planting. Placement of stockpiled reclamation materials such as topsoil, till, lakebed sediments, etc. should also be included in direct costs for revegetation. | RECLAIM should include the cost for all types of revegetation, including cuttings, plugs, transplants, and spreading stockpiled dirt and soil. | Unit Rates | AtkinsRéalis & Brodie | Suggest a User Specified activity and cost in RECLAIM
14 | Tlicho | Traditional Knowledge monitoring | Traditional Knowledge (TK) Monitoring is a critical part of ensuring the closed site meets closure objectives and goals. TK Monitoring is also essential for building community confidence in the closed site to enable long-term future use of the site. (For example, we note that the WLWB requires Diavik to prepare a TK Monitoring Plan). | RECLAIM should include the costs of a Traditional Knowledge Monitoring Program. This would involve regular (e.g., initially annual) site visits from Elders, youth, and staff to evaluate water quality, wildlife safety and movement, vegetation, and more. It is important to note that this is not the same as engagement or regulatory costs. This TK Monitoring Program is similar to other monitoring programs and should be a line item in the Post Closure sheet along with the scientific monitoring programs. | Policy | GNWT/CIRNAC | AtkinsRéalis supports this as its something that would like fall on governments books if a site were to be abandoned and this cost can be substantial.
15 | Tlicho | Net Present Value | To date, RECLAIM has included the ability to calculate the net present value. This was used for very long-term costs (e.g., more than 20 years) such as maintenance of constructed wetlands. This reduced the amount of security a company needed to post, without exposing the tax payer to increased risk. This is because the net present value accounted for the fact that money set aside for the future can be invested and will grow. The discount rate used in those calculations was generally an assumed modest growth in investment (e.g., 5%) minus an assumed inflation (e.g., 2%). | Why has the net present value function been removed from the draft RECLAIM? | NPV | AtkinsRéalis & Brodie
16 | Tlicho | Interim Care and Maintenance | The RECLAIM model includes an estimate for interim care and maintenance, meaning the period after bankruptcy and abandonment and before active closure begins. The total cost is based on an annual cost (commonly a few million dollars) times the number of years the site is likely to be in interim care and maintenance. The draft RECLAIM 8.0 model includes a default of 3 years of interim care and maintenance. However, the supporting documentation for the RECLAIM updates (Review of Mine Financial Security Estimates and RECLAIM) says "Importantly, the duration of Interim Care and Maintenance is typically limited to two to three years. It is known that government experience has been much different than this, both in scope and duration. This is an obvious category for which government could be under secured". The same document provides some evidence that the actual period could be five to ten years. | The estimated time a site is in interim care should be based on the expected or average duration not the minimum. | Policy | GNWT/CIRNAC | AtkinsRéalis agrees that even 3 years is low for ICM. However, we question whether its fair to hold additional securities to account for a transfer from the mine to government. For discussion.
17 | Tlicho | Unit costs - reference table and sources | During the public review, a reference table showing the source for unit cost assumptions was provided. | 1. This reference table is a significant improvement and should be included in the finalized model. It improves transparency and credibility of the unit costs and enables industry and decision-makers to discuss alternative site-specific unit costs. 2. Unit costs adopted from projects in the South (e.g., Sudbury) should be increased if these costs are going to be higher in northern, remote conditions. | Unit Rates | AtkinsRéalis
18 | Tlicho | Fish habitat | The Open Pit tab does not explicitly include costs for building fish habitat (littoral zones), even though these may be required in pit lakes or pits that will be reconnected with larger lakes. Some of the activities in the tab may address fish habitat construction (e.g., placing fill), but it is not clear whether all activities required to build littoral zones are in RECLAIM. (Fish habitat construction may be required by the Department of Fisheries and Oceans and/or the Land and Water Boards. In either case the estimate should be included in RECLAIM. If DFO already holds security for this activity, it can be subtracted from the RECLAIM estimate. If it is only required by the Land and Water Boards, then it would remain in the final total.) | RECLAIM should include costs for construction of fish habitat in pits. | Policy | GNWT/CIRNAC | Seems out of scope of for the default RECLAIM, but if it has been agreed with DFO costs are not held with them then it should be captured here.
19 | Tlicho | Scientific and Traditional Knowledge research | Typically, the CRP will have several approved reclamation research plans. If a mining company abandons a mine, important reclamation research may not have been carried out. The results of this research will be needed to properly reclaim the site. | RECLAIM should include the costs of scientific and Traditional Knowledge reclamation research. As noted by BCL in their memo, this could result in mines not proposing research, in order to avoid higher security deposits. BCL proposed some alternatives to address this problem (page 18 and 19 of the BCL memo). These could be considered, provided the details of the approaches are publicly reviewed. | Policy | GNWT/CIRNAC
20 | Tlicho | Risk communication | The RECLAIM model does not include the costs of risk communication. In order to restore confidence in the mine site area so that closure objectives related to cultural use can be met, a good risk communication plan must be developed and carried out. This may involve public meetings, posters, online tools, social media, radio, newspapers, etc. | RECLAM should include the cost of risk communication. If this cost is lumped in with other costs (e.g., engagement and regulatory compliance costs), this should be mentioned in the User's Manual. This will ensure that the portion of security held for risk communication is not returned until it has been carried out. It will also inform any future disagreements about the percentage of direct costs that should be held for engagement and regulatory compliance. | User Manual | Brodie | This should be added to User Manual
1 | Diavik | General | DDMI appreciates the opportunity to take part in this important review process. Since receiving preliminary feedback at the January 23rd, 2025 engagement session, DDMI understands that on February 18th, 2025 and on March 11th, 2025 the RECLAIM v8.0 team uploaded additional information to explain the rationale for some proposed changes to the model. DDMI has not yet been able to review all posted materials. DDMI also understands the RECLAIM v8.0 team will be providing further additional information including but not limited to a jurisdictional scan to support this review process. This complete set of information will inform ongoing collaborative discussion on this proposed update. | Given the complexity and importance of this review process DDMI recommends that the review timeline allows for thorough review and analysis of all information. DDMI is pleased to see the initial extended engagement process proposed by CIRNAC and GNWT and DDMI recommends the next steps for the RECLAIM v8.0 review process are discussed in detail and agreed at the GNWT and CIRNAC in-person workshop the week of May 14th, 2025. | Policy | GNWT/CIRNAC
2 | Diavik | General | An initial review of the proposed changes to the RECLAIM model suggest that its application could have a very significant increase on securities. Current proposed changes are focussed on: 1) increased unit rates, 2) increased indirect costs, 3) increased owners costs, 4) increases regulatory costs, 5) increased mobilization and ICM costs, and 6) a future value calculation without corresponding discounting. | DDMI recommends this review process also consider changes focussed on: 1) incentivizing progressive reclamation, 2) managing the return of security process, 3) managing the security holdback process, 4) consideration of financial mechanisms to provide security as a function of both the liability and asset value, and 5) risk associated with a proponents commitment to orderly closure of the site including its financial and technical capacity to carry it out. | Policy | GNWT/CIRNAC
1 | Todd Slack | Model Utility - One Long Comment, Pt. 1 | Obviously an updated reclaim model is in the interests of all parties. Recent years have seen significant increases in costs and an adjustment to better reflect this is a valuable effort to protect taxpayers and ensure that the polluter pays principle is effectively applied. However, the operational modifications of the model are not the only step needed to ensure our territory is protected. A higher-level review focusing on the overall effectiveness of the bonding system should be undertaken using real world closure examples to test the predictive utility of the RECLAIM approach. No model is perfect and the review should be asking if this model meaningfully serves the polluter pays principle. Ground-truthing with real world examples is essential. For example, the MVLWB held approximately $70M in security for Snap Lake (it isn’t particularly easy to know exactly what the security amount was). According to public reporting, as of 2023 De Beers had spent $135M. In that case, it seems that NWT taxpayers – with a government already seeking financial relief - were considerably exposed. Should this be an indicator of a larger trend, the risk is even larger as it seems a widely held belief that industry, already mobilized and familiar with their site, can complete a closure in a more cost effective manner. Yet, the final cost for this site, with a modern security bond, will be more than twice what was held. | Starting with the NWT, publish real world examples of closed sites versus the reclaim estimates | Policy | GNWT/CIRNAC
2 | Todd Slack | Model Utility - Pt. 2 | Other real world examples available to test the utility of RECLAIM estimates can be found in ongoing Strategic Oil abandonment and closure as well as the 2014 Snowfield property. Based on anecdotal information (as accounts have not been published, despite the expenditure of public monies), for the former, the GNWT has paid tens of millions for the reclamation, while the in the latter, the GNWT paid far in excess of the security held (nevermind the six-figure pre-existing debts that the company owed GNWT). Examples from Nunavut can be researched as well, extending back to Tahera/Jericho which was established with a modern regulatory regime and cost taxpayers more than the security that was held (as opposed to GIANT which is not appropriate as a test case). Yukon examples, over which there are a number of selections (Victoria, Wolverine, Minto) may provide further insight into the effective security estimates and bonding (considering the Yukon government has appropriated $100M for early stages of the Victoria mine they’ve inherited, which was permitted in a modern system). To summarize, before undertaking minor adjustments to the mechanics of the model, the overall utility needs to be verified, confirming fit for purpose. Notwithstanding the financial limitations of GNWT means that they lack the robustness to absorb and large mine failures (noting the daily cost cutting measures that are occurring), more importantly, the citizens of the NWT should have confidence that those overseeing the accessing and sale of our public resources are ensuring that the closure is paid for and completed by those exploiting the resource. | 1) Undertake analysis that looks at closure estimates versus the security held for sites across the NWT, Nunavut, and the Yukon. 2) Search for similar examples in Southern Canada were the structures ensuring the protection of taxpayers and governments are similar to those employed in the north. | Policy | GNWT/CIRNAC
1 | QIA | Updated Unit Rates | Understanding unit rates are based on first principles; however further detail on unit rate development and assumptions is required. For Example. Load and haul costs have been split into ‘short haul’ and ‘long haul’; however, there is no detail on what haul distance constitutes a short vs. long haul. To provide greater accuracy in haulage costs, specific unit rates should be calculated based on the actual haul distance between stockpiles and the facility being reclaimed. Dozer equipment rates are classified as either ‘small’ or ‘large’ scale equipment; however, no detail is provided on what is classified as a large dozer. This results in greater uncertainty in which equipment rate should be used when calculating equipment costs. | Paraphrased: Provide additional details on how unit rates were derived. | Unit Rates | AtkinsRéalis | Additional details were provided in the follow up memorandum. Short haul and long haul are defined in Table 2: RECLAIM v 8.0 Price Sources, Basis and References. This could be defined in the user manual but a decision was made to keep the details out of the text portion of the manual for ease of future updates. These unit rates could be used as a starting point but should be refined based on actual mine closure and reclamation plans and site conditions. Dozer unit rates were escalated from RECLAIM 7.0. It was assumed large dozers would be utilized given the scale of work. The cost per cubic meter depends on several factors including fuel costs, labour, maintenance and efficiency. On average large dozers (D10/D11 Class) range in price from 1.50 to 3.50 per cubic meter. However, in remote Arctic operations the costs can be 20 to 50% higher. The range for dozing in RECLAIM 8.0 is $1.52/m3 to $6.08/m3
2 | QIA | Increased Indirect Percentages | An alternate methodology for calculating indirect costs should be provided. For example, engineering design could be estimated to be 8% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outlined in the reclamation and closure plan. This would allow engineering costs to depend on the level of project definition and the work to be completed. This incentivises further project definition within closure designs earlier in the life of project. | An alternate methodology for calculating indirect costs should be provided. | Indirects | AtkinsRéalis
3 | QIA | Mobilization and Interim Care and Maintenance as Capital Costs | Mobilization / demobilization of equipment is typically considered as an indirect cost when it is being calculated as a percentage of direct costs. As RECLAIM calculates mobilization / demobilization costs directly, Okane supports its inclusion as a direct cost such that contingency can be applied. If mobilization / demobilization costs change to being calculated based on percentage, Okane does not support it being included as a direct cost. | Okane recommends mobilization / demobilization to be calculated via percentage of direct costs, similar to other Canadian jurisdictions. The quantity of equipment, and therefore the cost to mobilization / demobilization equipment, is tied to the reclamation timeframe and schedule. In the event of sudden closure, CIRNAC may implement closure activities on an alternate timeframe than what is outlined within the closure plan. | Indirects | AtkinsRéalis & Brodie
4 | QIA | Owners Representative | Okane supports the costing of an Owners Representative within closure cost estimates. However, Okane is interested in the percentage used for determining this cost. In comparison, the updated project management cost of the entire reclamation phase is estimated to be 10% and includes costs for project coordination, accounting and project control, quality assurance/quality control and oversight, change orders and as-built reports. Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Indirects | AtkinsRéalis
5 | QIA | HHERA and Finalize CRP | An alternate methodology for calculating HHERA and CRP costs should be provided. For example, finalizing the CRP could be estimated to be 4% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outline in the reclamation and closure plan. This would allow the costs for finalizing the CRP depending on the level of project definition and the work to be completed. | An alternate methodology for calculating HHERA and CRP costs should be provided. | Indirects | AtkinsRéalis & Brodie
6 | QIA | Future Value Calculation | Okane supports the consideration of future valuation with respect to years associated with ICM; however, does not agree on how it is being represented within RECLAIM with respect to post closure activities and the removal of net present value calculations as outlined in the virtual engagement session. While inflation can add considerable costs to reclamation, solely accounting for inflation does not capture the true costs and value of money. | Okane would recommend included inflation within a real discount rate to be used within a net present value analysis | NPV | AtkinsRéalis
7 | QIA | Detail for Unit Rates | Although RECLAIM provides a list of potential closure activities for each facility, it lacks the level of detail required to understand how these activities have been costed and relies strictly on unit rates and lump sum estimates. | To improve transparency and accuracy withing closure cost estimates, more inputs should be provided to show how that activity is being costed. Specifically, within post-closure activities such as monitoring the current RECLAIM model only provides an annual lump sum input for a monitoring activity. To improve transparency, it should provide more detail such as sampling/monitoring frequencies, number of sampling locations, analytic costs, reporting, etc. | Unit Rates | AtkinsRéalis
8 | QIA | Post-closure monitoring and maintenance contingency | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. Post-closure maintenance activities are not excluded from having uncertainty and a contingency should be applied within this cost category. Specifically, activities such as long-term water treatment which is tied closely to geochemistry which typically carries large uncertainty. | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. | Policy | GNWT/CIRNAC
9 | QIA | Timeframe and Post-Closure Activities | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. There is potential for post-closure monitoring and maintenance activities to extend into perpetuity, such as DSIs, DSRs, and water treatment. What is the expected period of which these activities should be assessed over. | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. | Policy | GNWT/CIRNAC
10 | QIA | Discount Rates | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. Okane would welcome guidance on what ‘real’ discount rate should be applied to post-closure activities. | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. | NPV | AtkinsRéalis
1 | BIMC | Procedural Fairness | Due to the short timeline to review the proposed changes, Baffinland has not had a full opportunity to conduct an in-depth review of the technical information supporting the RECLAIM 8.0 update. Respectfully, the timeline that was provided to industry for this initial round of comments is not adequate given the importance of RECLAIM to the Nunavut mining industry and the very serious potential impacts that have already been identified through the minimal consultation that has occurred to date. We are concerned that RECLAIM 8.0 could be advanced further despite these procedural deficiencies and the serious concerns expressed by industry to date. Given the significance of these changes to the mining industry in Nunavut and the Northwest Territories, and the potential direct impacts that it will have on Baffinland, we are providing initial high-level comments and recommendations below. In providing these comments, we reserve the right to provide further and more detailed comments, following further industry engagement and once better information is shared by CIRNAC and GNWT. | A. CIRNAC should engage stakeholders and Inuit organizations in a meaningful consultation process before finalizing the changes. Respectfully, the process described in the letter to the Chamber of March 18, 2025 does not achieve this standard. B. Third public review and comment period should only occur after CIRNAC has produced a version of RECLAIM 8.0 revised based on comments. A further workshop may be necessary to review this revised RECLAIM 8.0 before any final comment period. C. The overall timelines suggested in the process letter of March 18 are inadequate. For example, with respect to the suggested expected date of implementation of RECLAIM 8.0 [August 1, 2025], it is apparent that there would be no meaningful opportunity for feedback provided during the third round of public feedback (due July 16, 2025). D. CIRNAC should advise how they intend to engage with NTI and RIOs on impacts to their rights resulting from this policy change, with associated timelines, before RECLAIM 8.0 is adopted. E. CIRNAC should advise how they intend to engage with GN resulting on impacts relating to devolution resulting from this policy change (including spinoff economic effects), with associated timelines, before RECLAIM 8.0 is adopted. | Policy | GNWT/CIRNAC | A-E: CIRNAC and GNWT to discuss.
2 | BIMC | Economic impact of RECLAIM 8.0 | As Canada is trying to promote economic development and critical minerals development, which includes high grade iron ore, the additional security concepts and requirements proposed by CIRNAC in RECLAIM 8.0 will only make it harder to develop and maintain what we have. The changes proposed by CIRNAC will negatively impact mine financing and development by increasing security requirements and financial obligations without an adequate and corresponding industry consultation process. Any potential lack of engagement with industry and designated Inuit organizations undermines the legitimacy of these updates as a policy framework. Furthermore, as highlighted above, the RECLAIM 8.0 approach appears to disincentive projects with longer lifespans and greater water liability marks, which is in direct opposition to existing territorial and federal economic development policies and mandates. Without proper consultation, these changes will create uncertainty and deter investment in northern mining projects. Baffinland recommends that a comprehensive economic impact analysis be conducted to assess the implications of RECLAIM 8.0 on northern mining investment and development. Given the closure of major diamond mines in the North-West Territories and the absence of advanced stage projects in both the North-West Territories and Nunavut, apart from government funded infrastructure, the economic consequences of these changes should be thoroughly evaluated before implementation. An industry-commissioned economist could provide valuable insight into these potential impacts, and the results should be available before major policy decisions are finalized. | A. CIRNAC should conduct a comprehensive economic impact analysis to assess how RECLAIM 8.0 will affect mining investment and development in Nunavut. Industry and other stakeholders should be engaged on this question specifically as part of this analysis. B. As part of this analysis, CIRNAC should produce a third party expert prepared report on the potential economic impact of the proposed cost escalations on the mining industry in Nunavut. RECLAIM 8.0 has been provided without assessment of the negative economic impacts that could result from the significant policy change RECLAIM 8.0 represents. The independent economist selected for this task should have experience representing industry and have Northern expertise. | Policy | GNWT/CIRNAC | A: Agreed – third part economist could provide valuable insight as to the economic implication for mineral development in the NWT and Nunavut. B: As above.
3 | BIMC | Rates and Cost Estimates | The proposed updates to RECLAIM 8.0 introduce significant cost increases that could have long-term economic implications for mining projects in the North. These cost escalations require careful scrutiny to ensure they align with real-world reclamation expenditures and do not hinder responsible resource development. | A. Review and adjust cost estimates to ensure they are reasonable, justified, and do not include duplication in indirect costs. B. Develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. | User Manual | AtkinsRéalis & Brodie | A: There was every attempt to ensure costs were reasonable, justified and did not include duplication. We will review the rates again to ensure they meet these criteria. B: We do not suggest that CIRNAC develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. It should be clear in RECLAIM User Manual as to why the default percentages are chosen and the mining company should propose the appropriate rate for their own mines and current stage within the lifecycle.
4 | BIMC | Rates and Cost Estimates | The unit rates proposed for RECLAIM 8.0 are substantially higher than those in RECLAIM 7.0, often reflecting worst-case scenarios without adequate justification, despite the additional materials provided following the January Workshop in Vancouver. While CIRNAC states that proponents may propose alternative rates, industry experience suggests that the highest rates are typically applied in practice, unless a clear security policy is in place (see Section 3 – Security Policy). First principles derivations for these rates has not been provided (as is typical when justifying modifying rates in a security estimate) and the references are highly generalized, which hinders review, especially in light of the limited review timeline. | C. CIRNAC and GNWT must provide more detailed first principles derivations for rates, at a level that would be expected of a proponent justifying its own rates in an estimate. Specific references are required and generalized references provided to date are not adequate to provide expert feedback and advice. | Unit Rates | AtkinsRéalis | C: CIRNAC provided links and references to the majority of the sources for increased rates applicable to remote mine working in NWT and Nunavut. CIRNAC used First Principles to develop rates for soil and rock movement and provided the factors considered in the costs estimating tool. Its is up to the mining company to counter these rates and provide rationale as why a different unit rates should be proposed (high or lower).
5 | BIMC | Rates and Cost Estimates | The increase in indirect percentages represents an overall 23% increase in costs, and several of these items overlap, resulting in duplication of costs (see Table 1). For example the increase in contingency seems to be duplicated by an increase in project management, engagement and regulatory compliance, and owner’s representative costs. These increases do not appear to be justified through a detailed cost analysis. | D. Justification must be provided by CIRNAC to address the duplication described in the comment, and a detailed cost analysis must be provided to justify these statements | Indirects | AtkinsRéalis | D: AR to investigate
6 | BIMC | Rates and Cost Estimates | Upon initial review, the observations regarding indirect costs provided in the ”Review of Mine Financial Security Estimates and RECLAIM” (Brodie, 2020) do not align with the proposed Reclaim 8.0 Indirect costing changes. For example, the report states “BCL recommends that the default percentage for Project Management be increased based upon CIRNAC’s experience. Whereas the default percentage for Engineering should be maintained but with the RECLAIM User Manual revised to be even more explicit as to what is and is not assumed to be covered in this amount.: Baffinland notes that the proposed Reclaim 8.0 changes include an increase in project management indirect percentages (an increase from 5% to 8%), an additional owners engineer indirect (an increase of 8%) and an increase in engineering design indirects (5% to 8%). This appears to be in contradiction to the recommendations of the review report. | E. CIRNAC should align observations re indirect costs in RECLAIM 8.0 with Brodie, 2020 (subject to adjustment based on further submissions in future on each of these categories) | Indirects | AtkinsRéalis & Brodie | E: Default increases in percentage of indirects were increased from the Brody recommendations based on consultation with our consultants cost estimators and based on incurred cost at other orphaned and abandoned mine across Canada.
7 | BIMC | Rates and Cost Estimates | Within the proposed update, contingency has been increased to a maximum of 25%, which the Reclaim review report (Brodie, 2020) describes as appropriate for “Very basic engineering only and costs based upon typical unit costs”. This guidance is not provided in the proposed RECLAIM 8.0 documentation. As Baffinland has noted above, in its experience when Reclaim is applied by reviewers the highest level of contingency/indirect is used as a manner of course, as there is little specific guidance provided how to select an appropriate contingency/indirect within the provided model. For example, although Baffinland’s closure plan has advanced to the ICRP stage and has had significant engineering completed, a 20% contingency has been consistently applied by CIRNAC reviewers. Without specific risk based guidance regarding how to select indirect percentages based on project stage and level of engineering completed, Reclaim 8.0 could be used in an overconservative manner due to the lack of specific guidance, which could have a significant impact on Baffinland and other resource development projects in Nunavut. | F. 25% is not an appropriate contingency percentage for most advanced projects with current RECLAIM 8.0 guidance there is a risk this value is applied broadly, like 20% contingency is now. Adjust contingency percentage to reflect a range of risk based standards adjustable based on criteria, such as reductions below 20% where projects already have significant completion of engineering | Contingency | AtkinsRéalis | F: CIRNAC could develop a matrix to define
8 | BIMC | Rates and Cost Estimates | The future value calculation for water treatment and other long-term liabilities places a significant financial burden on mining companies, particularly in the absence of strong offsetting mechanisms, such as security discounting based on known reserves—an approach used in other jurisdictions like British Columbia (BC) and Quebec (Government of BC, 2022; Government of Quebec, 2017). For instance, in 2022, the BC Ministry of Energy, Mines and Low Carbon Innovation introduced the Major Mines Reclamation Security Policy, which considers a mine’s stage of development and promotes long-term operations by applying different security rates at various points in a mine’s lifespan based on default risk. The policy states that “mines that have been operating for more than five years, and that have economically viable reserves for at least the next ten years at the permitted production rate, will be eligible to secure up to 25% of the reclamation liability against a portion of the reserve value.” (Government of BC, 2022). Adopting a similar approach in Nunavut provide much-needed financial flexibility for long-term mining projects like Baffinland, reducing upfront security costs while maintaining strong environmental protection measures. This would enhance the economic viability of long-life mines, encourage continued investment, and support sustainable resource development in the region. Tying financial security to the mine life cycle would help mining companies spread out financial security payments over the mine’s life, which would increase investor confidence while supporting responsible mining development that considers the projected mine life. | G.RECLAIM 8.0 should be revised to provide a clear mechanism for discounting security based on reserves, similar to those adopted in other jurisdictions such as BC and Quebec. | Policy | GNWT/CIRNAC | The BC “interim” policy is based on years of operations and mineral reserves. Proven final securities through the Exploration Incentive. Shifting security to mineral reserves could be an issue as Canada is not in the mining business and if a site were abandoned, they would need to reopen a mine to get access to the money required to close it. The BC policy mentions that mines with proven reserves are attractive to other operators if a mine were to go bankrupt. STILL SEEMS RISKY TO ME, TULSEQUAH, MINTO, ETC. “This policy seeks to ensure that permittees for major mines pay the full cost of environmental cleanup and reclamation for their mine. New mines and any existing mines (whether in operation, in care & maintenance or closed) having less than five years of remaining mineral reserves will be required to post full reclamation security equal to the company’s reclamation liability on the mine site. A partial exploration incentive security will be available to mines that have invested in sufficient exploration to demonstrate at least five years of remaining reserves. The policy seeks to ensure that new mines are fully bonded moving forward and seeks to reduce the differential between reclamation liabilities and reclamation securities for existing mines.” 0 to 5 years: (100% posted cash security) > 5 years: (75% posted cash security and 25% against the mineral reserves) > 5 years but less than 10 years (85% posted cash security and 15% against the mineral reserves) No more than 10% of the value of the reserve used reclamation security Discount rate of 8% applied to the mineral reserves Default contingency set to 15% but higher may be required depending on the level of risk or uncertainty. Lower may be proposed by the permittee
9 | BIMC | Update of 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) is required. | Before publishing a RECLAIM 8.0 model, Baffinland recommends that the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) be revised to reflect current conditions in the mining industry. There has been no suggestion that current Nunavut production mines are undersecured – as an example, Baffinland’s security is reviewed annually in a comprehensive process. The investment decision for Mary River was made on the suite of government and Inuit approvals in place, including RECLAIM 7.0. | A. Before RECLAIM 8.0 is adopted for Nunavut projects, the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) should be updated to reflect current conditions in the mining industry and best practices across Canada and globally. B. Current approved Nunavut projects should follow RECLAIM 7.0, unless the proponent consents to application of RECLAIM 8.0. | Policy | GNWT/CIRNAC | A: TBD B: Current mine securities are set. At the time of renewal, RECLAIM v 8.0 will be in place and new indirects and calculations of contingencies and future costs will be negotiated.
10 | BIMC | Misc. | No Comment | A. Only a simple markup of the updates to the User Manual has been provided. A detailed markup is requested as a simple markup does not clearly present the changes. | User Manual | Brodie
11 | BIMC | Misc. | No Comment | B. With reference to the “proprietary civil rate tool” referenced at p. 20 of the User Manual for RECLAIM 8.0, if a tool is being adopted in a government policy, it must be made publicly available. If it is not publicly available, it should not be included in the policy. This is a matter of fairness and transparency. | User Manual | AtkinsRéalis | B: AtkinsRéalis suggests removal “proprietary” replace with “construction cost estimating”
12 | BIMC | Misc. | No Comment | C. Costs relating to the Crown’s legal obligation to consult (which would be incurred in any event, whether the Crown steps in as director of reclamation or participates in review of closure plans led by a proponent) should not be included in RECLAIM 8.0, as this is a fixed government cost, not a cost of reclamation. The suggested 3% includes items that are fixed government obligations that do not belong in a reclamation estimate. | Policy | GNWT/CIRNAC | C: The 3% Owners Costs are meant to capture expenses required to complete consultation during the ICM and Post Closure Phase that typically are budgeted for in day to day government spending (i.e., flights, vehicle rentals, accommodations, per diems to northern and remote communities to discuss the remediation, reclamation and closure plan. Costs of permitting and other third party costs related to government activities would be captured here.
13 | BIMC | Misc. | No Comment | D. How is RECLAIM 8.0 accounting for Nunavut devolution relating to lands and waters from CIRNAC to the GN? | Policy | GNWT/CIRNAC | D: CIRNAC to elaborate.
14 | BIMC | Misc. | No Comment | E. RECLAIM 8.0 should recognize reasonable salvage value where justified by the proponents estimate. The current position is unreasonably conservative and results in over bonding in many circumstances. This statement should be revised accordingly “GNWT/CIRNAC does not recognize salvage value because of the problems associated with creditors rights, sale of equipment and uncertainty as to the actual value at the time of insolvency”. | Policy | GNWT/CIRNAC | E: Revised text looks appropriate to AtkinsRéalis.
15 | BIMC | Misc. | No Comment | F. Citation for precautionary principle definition should be to the CEPA not to the CEPA guide. | User Manual | Brodie | F: Revision seems appropriate to AtkinsRéalis
16 | BIMC | Misc. | No Comment | G. Progressive reclamation should be credited in mine reclamation costs. This aligns with the following statement from the 2002 Nunavut Reclamation Policy – “Mining operators should be credited for approved progressive reclamation, and the value of financial security required should be adjusted in a timely fashion” | Policy | GNWT/CIRNAC | G: CIRNAC recognizes this statement and has worked with mining companies to reduce securities based on progressive reclamation activities and will continue to do so on a case by case basis.
17 | BIMC | Misc. | No Comment | H. RECLAIM 8.0 adds an additional owners representative indirect cost, which is in addition to the proposed project management indirect cost. The owners representative indirect has been insufficiently justifying in the provided accompanying documentation, and it should be noted that an owners representative is not required during proponent lead reclamation. This overly conservative indirect requirement could have significant implicants on mine financing and development. | Indirects | AtkinsRéalis | H: CIRNAC and GNWT would not lead the development and finalization of the Closure and Reclamation Plan, nor would they oversee the construction or monitoring and maintenance activities. It has been shown that this is not the case as seen at Faro and Giant mines. CIRNAC and GNWT would hire an engineering firm to provide Owners Representative services (technical resources to government) to manage and oversee another engineering firm (e.g. a design-build team) who would be contracted to complete the closure, reclamation and long term monitoring activities.
1 | B2G | Review Data Extension | B2Gold Nunavut is presently unable to meet the requested date for the submission of comments and therefore supports a recent request made by the NWT& Nunavut Chamber of Mines (Chamber) to extend the comment period deadline. B2Gold Nunavut also supports the request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM. The Chamber submission is attached to this letter. | Request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM | Policy | GNWT/CIRNAC
1 | Chamber | Review Data Extension | The Chamber respectfully requests a 4-month review period (including potential options for a workshop) to fulfill the first step in the review process. We would also ask for access to the Review of Mine Financial Security Estimates dated March 2020 at your earliest convenience. | Four month date extension for review comments | Policy | GNWT/CIRNAC
1 | Agnico | Review Data Extension | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. As was apparent at the January 23, 2025 Engagement and Feedback Session, and echoed again in the NWT & Nunavut Chamber of Mines letter, there were many uncertainties and risks identified by Industry, including time to complete a detailed and adequate review of all the proposed changes under RECLAIM 8.0. As outlined in Section 2 of this letter, Agnico Eagle has undertook an initial review and provided some comments and recommendations; however, a detailed fulsome review has not been executed at this stage. | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. | Policy | GNWT/CIRNAC
2 | Agnico | Documents received | This is a preliminary review due to the short timeline | More time is required to complete a comprehensive review of the documentation provided | Policy | GNWT/CIRNAC
3 | Agnico | Reclamation Policy | As the reason is unknown why the Reclaim V8 was changed, plus we have an undefined process we are following, and this creates uncerntainity. | Develop a policy update with a defined process of consulation, etc., and define the triggers for a material change. | Policy | GNWT/CIRNAC
4 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" and "'Work week for earthwork (rock, soil, riprap excavation, hauling to waste dump is 7 days a week x 10 hours per day = 70 hours per week" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No overnight work is considered. | Unit rates should be developed assuming 24 hour operation where practical. SUPPORTING RATIONALE: Operating Mines, particularly in the North, require round the clock operation for maximum equipment utilization and operation effectiveness. Haul trucks engines must be active around the clock to ensure operability and neglecting night shift utilization ignores real operating expenditures. | Unit Rates | AtkinsRéalis
5 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" | The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No night work is considered. | Operating Mines, particularly in the North require round the clock operation for maximum equipment utilization and operation effectiveness. SUPPORTING RATIONALE: Neglecting potential night shift work unnecessarily extends project schedule and therefore unnecessarily inflates overall project costs. | Unit Rates | AtkinsRéalis
6 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'The labour cost included in the unit rates considered the following cost: … - Indirect labour" | The battery limits for "indirect labour" included in unit rate development is not adequately defined. RECLAIM includes indirect activities such as Project Management and Engineering Design applied as a general percentage of direct costs. | Clarify what indirect labour is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | Unit Rates | AtkinsRéalis
7 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "The labour cost included in the unit rates considered the following cost: … - Site supervision and administration" | The labour cost included in the unit rates considered the following cost: Site supervision and administration | Clarify what site supervision and administration is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.). SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. Project management, Health and Safety Monitoring & QC as an indirect cost is applied as a blanket % to all costs. | Unit Rates | AtkinsRéalis
8 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "Exclusion ...- Project indirect cost" | The battery limits for "indirect cost" included in unit rate development is not adequately defined. | Clarify what indirect cost is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. | Indirects | AtkinsRéalis
9 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 5 Exclusions LINE: "- First Fills" | First fills are excluded from unit cost build up. | Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup that excludes first fills. SUPPORTING RATIONALE: Consistent application inclusions and exclusions are important for usability of RECLAIM. Suggest using one data source for all unit rate buildup. | Unit Rates | AtkinsRéalis
10 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- Freight for the bulk materials such as granular, concrete and HDPE pipes are included with the unit rates" | Proposed unit rate buildup includes freight for bulk materials. This necessitates site specific unit rate for all bulk materials as freight costs can very substantially between sites. There is already a section within the RECALIM mobilization tab to capture freight cost. | Bulk material default unit rates should exclude freight. Freight for materials should be included separately based on a site specific unit cost for material mobilization, captured in the RECLAIM Mobilization tab. | Unit Rates | AtkinsRéalis
11 | Agnico | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- It is assumed there is no batch plant required. All concrete will be delivered to site to use" | The clarification that no batch plant will be required constricts operational planning. In some cases it is more cost effective to commission a batch plant and ship bulk concrete than to use premix product. | Freight of premix concrete products is not always practical for northern projects based on mobilization constraints and the use of a batch plant should be considered when operationally and financially advantageous. | Unit Rates | AtkinsRéalis
12 | Agnico | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects LINE: Mobilization/Demobilization 6.0% | Contractor indirects, specifically mobilization/demobilization, are shown as separate adders to the base rates for equipment and labour direct costs. RECLAIM considers mobilization and demobilization costs separately from operating unit rates as part of the Mobilization tab. | Exclude mobilization/demobilization cost from unit rate development. Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup and if mobilization/demobilization cost has been accounted for with respect to the overall RECLAIM workbook. | Unit Rates | AtkinsRéalis
13 | Agnico | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects | A variety of sources for equipment operating costs as well as labour costs are indicated as being used as a basis for unit rate calculations. There are substantial differences in the factors included in each of the sources for equipment operating costs. For example, BC Blue Book and Alberta Equipment Rental Rates Guide are used interchangeably in FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Rates but BC Blue Book equipment operating rates do not explicitly include contractor overhead and profit whereas Alberta Equipment Rental Rates Guide does. The provided unit rate example in FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects, if using Alberta Equipment Rental Rates Guide for equipment or manpower hourly rates is applying an additional 12.50% Mark-up & Profit on a rate that already includes Mark-up & Profit. | Default unit rates provided in RECLAIM 8 should use a consistent source reference for all equipment and manpower hourly rates with clearly defined buildup of direct and indirect components. | Unit Rates | AtkinsRéalis
14 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Buildings - Remove" COST CODE: BRW, BRC, BRS1, BRS2 | Cost Codes: BRW, BRC, BRS1, BRS2 have no default HIGH unit rate provided as part of RECLAIM 8.0 example. RECLAIM 7.0 provided a HIGH unit rate for these cost codes resulting in a 1:1 comparison between RECLAIM 8.0 default unit costs and RECLAIM 7.0 unit costs. | RECLAIM 8.0 should include a default HIGH unit rate for all default cost codes that have a defined HIGH unit rate in RECLAIM 7.0 | Unit Rates | AtkinsRéalis
15 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB1, RB2 | The detail defining what activity COST CODES RB1 and RB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines RB1 as "drill/blast/load/short haul" RECLAIM 8.0 defines RB1 as "load/haul/place"RECLAIM 7.0 defines RB2 as "drill/blast/load/long haul" RECLAIM 8.0 defines RB2 as "RB1 + spread and compact"This respondent uses COST CODE RB2 to represent activities requiring "drill/blast/load/long haul" but NOT "spread and compact" To accommodate the change in COST CODE detail from RECLAIM 7.0 to RECLAIM 8.0 >$10 million of activities on a single site would need to be recoded to avoid implying "spread and compact" is required for these activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
16 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB3, RB4 | COST CODE: RB3 and RB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RB3 DETAIL: "RB1 + spread and compact" is the same as RECLAIM 8.0 CODE RB2 DETAIL: "RB1 + spread and compact"RECLAIM 7.0 COST CODE RB4 DETAIL: "RB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RB3 and RB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
17 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - High Spec (i.e. Rip Rap, Screened)" COST CODE: RC3, RC4 | COST CODE: RC3 and RC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RC3 DETAIL: "RC1 + spread and compact" is the same as RECLAIM 8.0 CODE RC2 DETAIL: "RC1 + spread and compact"RECLAIM 7.0 COST CODE RC4 DETAIL: "RC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RC3 and RC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
18 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB1, SB2 | The detail defining what activity COST CODES SB1 and SB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SB1 as "excavate/load/short haul" RECLAIM 8.0 defines SB1 as "excavate/load/haul/place"RECLAIM 7.0 defines SB2 as "excavate/load/long haul" RECLAIM 8.0 defines SB2 as "SB1 + spread and compact"This respondent uses COST CODE SB2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
19 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB3, SB4 | COST CODE: SB3 and SB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SB3 DETAIL: "SB1 + spread and compact" is the same as RECLAIM 8.0 CODE SB2 DETAIL: "SB1 + spread and compact"RECLAIM 7.0 COST CODE SB4 DETAIL: "SB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SB3 and SB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. This respondent would need to recode >$35 million of activities at one site. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
20 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC1, SC2 | The detail defining what activity COST CODES SC1 and SC2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SC1 as "excavate/load/short haul" RECLAIM 8.0 defines SC1 as "excavate/load/haul/place"RECLAIM 7.0 defines SC2 as "excavate/load/long haul" RECLAIM 8.0 defines SC2 as "SC1 + spread and compact"This respondent uses COST CODE SC2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
21 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC3, SC4 | COST CODE: SC3 and SC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SC3 DETAIL: "SC1 + spread and compact" is the same as RECLAIM 8.0 CODE SC2 DETAIL: "SC1 + spread and compact"RECLAIM 7.0 COST CODE SC4 DETAIL: "SC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SC3 and SC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified. | Unit Rates | AtkinsRéalis
22 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, small (<6in dia.)" COST CODE: PSS, PSI | COST CODES: PSS and PSI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes. | Unit Rates | AtkinsRéalis
23 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, large (>6in dia.)" COST CODE: PPLR, PLS, PLI | COST CODES: PLR, PLS and PLI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes | Unit Rates | AtkinsRéalis
24 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: PS | Pumps, Pump shipping COST CODE: PS unit changed from RECLAIM 7.0 lump sum (each) to, RECLAIM 8.0 percentage (%) of pump cost.Existing RECLAIM 7.0 projects have taken to account shipping of pumps, by lump sum (each) as part of the mobilization calculation. Shipping cost is generally site specific and existing calculations should remain valid. Shipping cost as a % of pump capital cost could be a useful default unit rate for establishing projects. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND adding new cost code for shipping as a % of capital cost | Unit Rates | AtkinsRéalis
25 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: POC | Pumps, Pump operating cost COST CODE: POC unit changed from RECLAIM 7.0 m3 (volume pumped) to, RECLAIM 8.0 kw-h (power cost).Pump operating cost is certainly predicated on site power cost but the relationship between pumped volume and power draw is based on site specific conditions. Volume of water is the unit of measure for reclamation activities and using a second unit of measure to determine cost would introduce additional complexity. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND pump operation based on cost per volume pumped. | Unit Rates | AtkinsRéalis
26 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Human Health and Ecological Risk Assessment (% Closure Costs) | Human Health and Ecological Risk Assessment (% Closure Costs): Cost to develop a site specific HHERA is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for HHERA related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | GNWT/CIRNAC | For group discussion
27 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Finalize Closure and Reclamation Plan (% Closure Costs) | Finalize Closure and Reclamation Plan (% Closure Costs): Cost to develop Final Closure and Reclamation plan is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Finalize Closure and Reclamation Plan related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | GNWT/CIRNAC | For group discussion
28 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engineering Design | Indirect Costs: Engineering Design : Cost for engineering design is warranted and should consider work already completed to capture the real effort and cost to achieve closure | Implement a sliding scale for Engineering Design Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | GNWT/CIRNAC | For group discussion
29 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Project Management | Indirect Costs: Project Management : Cost for project management is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale for Project Management Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure. | Indirects | GNWT/CIRNAC | For group discussion
30 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Health and Safety Plans/Monitoring & QC | Indirect Costs: Health and Safety Plans/Monitoring & QC : Cost for Health and Safety Plans/Monitoring & QC is warranted and should consider work already completed to capture the real effort and cost to achieve closure. | Implement a sliding scale to account for project maturity and the cost and effort required to achieve closure. | Indirects | GNWT/CIRNAC | For group discussion
31 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Bonding / Insurance | Indirect Costs: Bonding / Insurance : Cost for Bonding and Insurance is warranted and should consider work already completed to capture the real effort and cost to achieve closure. This cost should also account for the reliability and ease of use of the financial assurance instrument used by the mine owner as well as the financial reliability of the mine owner, represented by third party credit rating. Typical operating project bonding and insurance costs for third parties are historically <1% total project cost. | Implement a sliding scale to account for owner reliability, project maturity, and the cost and effort required to achieve closure. Established mining companies at low risk of becoming insolvent should have their efforts to achieve closure recognized. | Indirects | GNWT/CIRNAC | For group discussion
32 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engagement and Regulatory Compliance | Indirect Costs: engagement and regulatory compliance cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations, including through regulatory compliance and engagement, should not be made to bear burden of costs outside their influence. | Indirects | GNWT/CIRNAC
33 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Contingency | Indirect Costs: Contingency : Cost for contingency is warranted and should consider work already completed to capture the real effort and cost to achieve closure. There is currently a sliding scale for contingency, codified in the RECALIM 7.0 user manual, but the benchmarks set out are not representative of the level of contingency requested by CIRNAC and recommended by Brodie Consulting. The RECLAIM 8.0 contingency scale, based on AACE International Recommended Practice No. 10S- 90 representative of current industry practice and can be augmented with other factors such as owner financial strength, path to closure, and financial instrument of security. | Contingency sliding scale should reflect project lifecycle maturity, the financial strength of the owner, the financial instrument of closure security and the cost and effort required to achieve closure. | Contingency | GNWT/CIRNAC | For group discussion
34 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Owners Representative | Indirect Costs: Owners representative cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security. | Mine owners operating in good faith to service their closure obligations should not be made to bear burden of costs outside their influence. This line item addition represents a significant burden to all mining companies and it may impact the viability of future developments. | Indirects | GNWT/CIRNAC
35 | Agnico | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Site Specific Future Value Inputs | FILE: reclaim 8.0 User Manual_Working Copy.pdf affirms that the determination of future costs must include all parameters including the Net Present Value of those costs. The Site Specific Future Value Inputs projects a future cost without including for the future value of the security | If RECLAIM is to project factors such as inflation it should also account for the present value of money at the time of projection. A prescribed NPV calculation with appropriate discount rate should be applied alongside all Post-Closure costs and future projections. | NPV | AtkinsRéalis
1 | KIA | General comment | The Kivalliq Inuit Association (KivIA), as the responsible DOI, through Security Management Agreement holds 50% of the financial security estimates for Meadowbank, Meliadine and Whale Tail mines Canada holds the other 50%. Therefore, any changes to the RECLAIM financial model must be reviewed and agreed by KivIA. | Paraphrased: Table 1 provides the comments and recommendations from KivIA and are summarized in comments 2 to 20 below. Table 2 provides operational costs for drill/blast/load/haul/spread/compact unit rates. Assumption is we should consider these rates. Table 3 includes an example comparison of the increased costs based on the new percentages for indirects. It is recommended that any changes to the RECLAIM financial model must be reviewed and agreed by KivIA | Policy | GNWT/CIRNAC
2 | KIA | General comment | The timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site needs to be explained. | The KivIA requests that CIRNAC explain the timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site. | Policy | GNWT/CIRNAC
3 | KIA | General comment | Project or mine’s asset value to a company. Will CIRNAC consider the asset value of an advanced project or mine as part of the initial financial security. | The KivIA requests that CIRNAC explain if there would be consideration of the asset value of an advanced project or mine as part of the initial financial security. | Policy | GNWT/CIRNAC
4 | KIA | General comment | What is the procedure for the return of financial security to the proponent? | The KivIA requests that CIRNAC explain the procedure for returning financial security to the proponent. | Policy | GNWT/CIRNAC
5 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | The changes made to the direct costs need to reflect each individual project/mine site. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that direct costs will need to be project specific versus “one cost fits all” with a range of costs being a more appropriate approach. | Unit Rates | AtkinsRéalis
6 | KIA | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References -Excavation costs. | Excavation costs for load/haul/place for excavating and spreading rock and soil show significant increases from RECLAIM 7.0 to RECLAIM 8.0. Using known operating costs from a northern gold mine calculated in RECLAIM 7.0 and comparing these costs to the proposed rates in RECLAIM 8.0 the costs for load/haul/place for excavating and spreading rock and soil have increased by 50% to 430% (see Table 2 attached). In addition, the RECLAIM 7.0 costs included drill and blast which the RECLAIM 8.0 costs do not. However, without any detail provided on how the Civil Est. Tool calculates the RECLAIM 8.0 costs it is not possible to evaluate these cost differences. | The KivIA requests that CIRNAC and their engineering consultants provide the detail on how the Civil Est. Tool calculates the RECALIM 8.0 excavation costs. | Unit Rates | AtkinsRéalis
7 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Direct Costs | Will an inflation factor be used. Will this factor be applied to direct costs? Or to Indirect costs? Will an inflation factor be used on the direct costs? Or indirect costs? Over what time period will the inflation facto be reviewed. | The KivIA requests that CIRNAC and their engineering consultants respond to their proposed plan for an inflation factor. | Unit Rates | AtkinsRéalis
8 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Summary Tab – Summary of Costs (2024 Dollars) – Indirect Costs | The changes made to the percentages used for Indirect Costs from RECLAIM 7.0 (31%) to RECLAIM 8.0 (58%). Using the $100M Direct Cost example in Table 2 the changes made to the percentages would result in an 87% increase to the InDirect Costs from $31M to $58M. | A cost increase of 87% is significant and will have a negative impact on the business model used to develop currently operating advanced projects and mines. In addition, a cost increase of this magnitude will have a negative impact on new investment “North of 60”. The KivIA’s comments on the recommended changes make up the remainer of this table (Table 1). | Indirects | GNWT/CIRNAC
9 | KIA | RECLAIM 8.0 – User Manual – Indirect Costs – Engineering Design; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engineering Design | The percentage change made to the Engineering Design component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (8%). This should be a range from 5% to 8% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Indirects | AtkinsRéalis
10 | KIA | RECLAIM 8.0 – User Manual – Indirect Costs – Project Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Project Management | The percentage change made to the Project Management component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (10%). This should be a range from 5% to 10% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Indirects | AtkinsRéalis
11 | KIA | RECLAIM 8.0 – User Manual – Indirect Costs – Engagement and Regulatory Compliance; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Engagement and Regulatory Compliance | The Engagement and Regulatory Compliance component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (3%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2)the cost information that was used to determined that this new category would cost $3M per every $100M of financial security. | Indirects | AtkinsRéalis
12 | KIA | RECLAIM 8.0 – User Manual – Indirect Costs – Contingency Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Contingency | The percentage change made to the Contingency component of Indirect Costs from RECLAIM 7.0 (20%) to RECLAIM 8.0 (25%). This should be a range from 15% to 25% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus “one cost fits all” with a range of percentages being a more appropriate approach. | Contingency | AtkinsRéalis
13 | KIA | RECLAIM 8.0 – User Manual – Indirect Costs – Owners Representative; Summary Report: Proposed Changes to RECLAIM Version 8.0 – Owners Representative | The Owners Representative component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (8%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide: 1)the rationale for separating these tasks out from the Project Management category. 2) the cost information that was used to determined that this new category would cost $8M per every $100M of financial security. | Indirects | AtkinsRéalis
14 | KIA | RECLAIM 8.0 – User Manual – Future Value calculations: Summary Report: Proposed Changes to RECLAIM Version 8.0 – Future Value calculations | It states that the Future Value calculations will capture Closure and post-Closure activities and that a default inflation rate of 3% will be applied. Will there be an annual or a multi-year review of the inflation rate in order to adjust the financial security. | The KivIA requests that CIRNAC and their engineering consultants provide the timeline over which the inflation rate will be reviewed (ie. Annually review? Multi-year review?). | NPV | GNWT/CIRNAC
15 | KIA | RECLAIM 8 Reference Tables Working Copy – Excel Sheet; Table 1 – Basis of Unit Rates Development | It states that “The below references are used in unit rates development -Published data sources”. All the published data sources used are from southern Canada. Are there any “North of 60” data sources? Are there any permafrost related data sources? Also, are these labour and contractor rates union or non-union rates? | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) northern data sources or explain why these cannot be provided. 2) Are the labour and contractor rates union or non-union rates. | Unit Rates | AtkinsRéalis
16 | KIA | RECLAIM 8 Reference Tables Working Copy – Excel Sheet – Table 2: RECLAIM v8.0 Price Sources, Basics and References – column Price Base/References | In the column for price Base/References several price references are either Civil Est. Tool or Historical Database. For transparency and ensuring a proper evaluation of costs by all intervenor’s full disclosure of all price references is necessary. | The KivIA requests that CIIRNAC and their engineering consultants provide: 1) the details of the Civil Est. Tool. 2) the Historical Database. | Unit Rates | AtkinsRéalis
17 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Instruction Tab – Conditions of Use | It states that “This model is not intended to dictate how much should be spent on reclamation.” What is the purpose of this financial model if it is not supposed to dictate how much should be spent on reclamation by the proponent? Is it possible that if a proponent disagrees with CIRNAC’s final dollar amount created by this model that the proponent could set their own financial security? | The KivIA requests that CIRNAC: 1) provide clarity on the purpose of the RECLAIM financial model. 2) provide clarity on the proponents responsibility to adhere to the final dollar amount calculated by the RECLAIM financial model. | Policy | GNWT/CIRNAC
18 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Fuel and Electricity | Fuel costs for gas and diesel are listed. No fuel costs for Jet A, Jet B or Av gas are included. | The KivIA requests that CIRNAC and their engineering consultants provide fuel costs for Jet A, Jet B and Av gas. | Unit Rates | AtkinsRéalis
19 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Unit Cost Tab – Mobilize Workers (round trip) | Hourly costs for small, medium and heavy helicopters. Are these hourly costs “dry” (do not include fuel cost) or “wet” (do included fuel cost). | The KivIA requests that CIRNAC and their engineering consultants determine if the hourly costs for small, medium and heavy helicopters are “dry” or “wet”. | Unit Rates | AtkinsRéalis
20 | KIA | RECLAIM 8 Model Working Copy – Excel Sheet; Estimator Tab – Excavator Ratings | The cycle times and productivity for excavators are based on southern Canadian conditions (ie. digging in sandstone and caliche; non-Arctic conditions). There is no reference to permafrost or Arctic conditions for the cycle times and productivity for excavators. | The KivIA requests that CIRNAC and their engineering consultants determine what changes to the cycle times and productivity for excavators will occur in permafrost and Arctic conditions, in particular, metal fatigue under extremely cold conditions (ie. > -40oC). | Unit Rates | AtkinsRéalis
1 | Burgundy | Transparency of Unit Rates Derivation | The derivation of the proposed RECLAIM 8.0 unit rates remains unclear, which makes it challenging for proponents to assess their applicability to specific sites. | Provide detailed explanations and supporting data for these rates would enhance understanding and confidence in their application. | Unit Rates | AtkinsRéalis
2 | Burgundy | Mobilization and Indirect Cost Management (ICM) Costs | Reassigning these costs to Capital Costs introduces a compounding effect that significantly inflates estimates. | Retaining them under Indirect Costs would better account for site-specific variations without leading to overestimations. | Indirects | AtkinsRéalis
3 | Burgundy | Default Percentages for Costs | The percentages allocated for Owners Representative, HHERA, and Final CRP costs are high and do not align with typical closure project requirements in the region. | Revisiting these percentages and considering fixed cost estimates will ensure more balanced and accurate calculations. | Indirects | AtkinsRéalis
4 | Burgundy | Inflation Rate Methodology | Applying a fixed 3% inflation rate across all closure costs is not appropriate for all closure activities. | A more flexible approach based on historical inflation data and specific project conditions will better reflect actual cost variability. | NPV | AtkinsRéalis
5 | Burgundy | Incentives for Progressive Reclamation | The updates focus on increasing securities but could also include measures to encourage progressive reclamation during operations. For example, allowing partial release of securities to execute reclamation activities would promote progressive reclamation, reduce liabilities and support sustainable closure outcomes. | Update should encourage progressive reclamation during operations. | Policy | GNWT/CIRNAC

## Names (hidden)
Short Name | Long Name
ACDC | Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo
Agnico | Agnico Eagle Mines Limited – Jamie Quesnel
B2Gold | B2G Back River Corp. Nunavut – Merle Keefe
BIMC | Baffinland Iron Mines Corporation – Lou Kamermans
Burgundy | Burgundy Diamond Mines Ltd – Sheila Chernys
Chamber | NWT & Nunavut, Chamber of Mines – Karen Costello
De Beers | De Beers Canada Inc. - Gahcho Kue - Kurtis Trefry
DFO | Fisheries and Oceans Canada (DFO) - Mr. Derek Donald
Diavik | Diavik Diamond Mines (2012) Inc. - Sean Sinclair
EMAB | Environmental Monitoring Advisory Board - EMAB
IEMA | Independent Environmental Monitoring Agency - Jamie Mistry
IOR | Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han
KIA | Kivalliq Inuit Association – Luis Manzo
PPML | Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm
QIA | Qikiqtani Inuit Association – Conor Goddard
Teck | Teck Metals Ltd. - Dr. Bjorn Weeks
Tlicho | Tlicho Government - Jessica Pacunayen
Todd Slack | A Member of the Public - Todd Slack
WLWB | Wek'èezhii Land and Water Board - Meghan Schnurr

## Sheet2 (hidden)
No. | Topic | Reviewer Comment | Reviewer Recommendation | Assigned To | Proponent Response
Environmental Monitoring Advisory Board - EMAB
1 | Evaluate RECLAIM estimates versus actual expenditures | EMAB's view is that the cost of mine closure should be borne by the proponent, not the taxpayer. The comment on p. 1 of the CIRNAC review that "However, it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." raises a major concern. Security should cover the entire cost of closure, and RECLAIM should calculate security that meets the full cost of closure. | CIRNAC/GNWT should carry out a quantitative evaluation of how much current RECLAIM estimates differ from actual expenditures. | GNWT/CIRNAC
2 | Depositing waste rock in open pit | Some mines have included depositing waste rock into open pits as a means of disposal. This activity does not appear to be addressed in the RECLAIM manual or tables. | Expand tables, and manual, to include placing waste rock and other materials, into open pits. | AtkinsRéalis
3 | Revegetation | The reference tables for vegetation include hydroseeding and tree planting. This is a good start, but the range of activities should be expanded to include all activities required for successful revegetation. | Reference tables for vegetation should also include application of amendments and planting of container forb seedlings as well as other activities required for successful revegetation. | AtkinsRéalis | Add Other Specific if not there already
4 | Long-term maintenance and monitoring | Traditional Knowledge Monitoring by members of Affected Communities is an important component of ensuring successful closure and future use of the area affected by the mine for cultural activities by the Indigenous people who live in the area and use it. | Add Traditional Knowledge Monitoring to the list of post-closure activities. | GNWT/CIRNAC
5 | Long-term maintenance and monitoring | EMAB was pleased to see the expansion of the Mobilization sheet to include construction and use of winter roads for both mobilization and demobilization. It is not clear whether this is intended to cover mob/demob for post-closure maintenance. Once the mine closes there is no guarantee that the winter road will continue to exist. If there is a significant maintenance requirement, there may be a need to build a winter road to mobilize heavy equipment etc., and to demobilize it after the maintenance is completed. | Include the cost of building a winter road to the mine as part of long-term maintenance, if this is the only means for mobilizing/demobilizing heavy equipment required for maintenance. Costing should include building the winter road for the following season to demobilize heavy equipment. | AtkinsRéalis | Maintaining a road for the duration of the Post Closure Monitoring may be expensive.
6 | Long-term maintenance and monitoring | Post-closure monitoring activities may require air transportation to and from the site, which could involve use of the airstrip. In order to use the airstrip it will need to be maintained until all monitoring is completed. | Include costs to maintain the airstrip until post-closure monitoring is completed. | AtkinsRéalis | Yes this maybe required.
7 | Long-term maintenance and monitoring | The scope of post-closure maintenance activities includes cover maintenance and spillway maintenance. Maintenance could include other components such as tailings dams, discharge channels, revegetation, or emergency or ongoing water treatment; so the list should be expanded to provide for these and other potential maintenance activities. | Expand the scope of post-closure maintenance activities to include dams and discharge channels, revegetation maintenance, and a category for other potential maintenance requirements. | AtkinsRéalis | Agreed - but any list would not be exhaustive
8 | RECLAIM User Manual | The User Manual will need to be updated to reflect all changes and additions to the RECLAIM tables. | Ensure the RECLAIM User Manual is updated to provide clear explanations of all the activities and changes to the tables. | Brodie
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Imperial Oil Resources N.W.T. Limited - Mrs. Leanna Han
1 | Owners Representative Cost | Costs for the Owners Representative are included at a rate of 8% of the total capital costs estimate. This appears to be a duplication of costs associated with Engineering Design (8%) and Project Management (10%). | Suggest removing the Owners Representative line item in the Indirect Costs summary or reducing the default factor to 2% of Capital Costs or providing a description and basis for this percentage and how it differs. | AtkinsRéalis and Brodie
2 | Human Health and Ecological Risk Assessment | Human Health and Ecological Risk Assessment (3% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
3 | Finalize Closure and Reclamation Plan | Finalize Closure and Reclamation Plan (4% of Closure Costs) is added onto Interim Care and Maintenance and then factored again in the Indirect Costs summary. | This tasks should only be included in the Indirect Costs summary. | AtkinsRéalis
4 | Unit Price Cost References are not Regional | There do not appear to be any references to NWT or Nunavut specific unit costs in UR-Short list in workbook RECLAIM 8 Reference Tables_WorkingCopy.xlsx | Suggest that V8 include reference to northern unit price equivalents. | AtkinsRéalis
5 | Remediation | There are no referenced unit prices for remediation of any sort - bioremediation and landfill unit prices do not have any reference or backup. | Add unit prices for standard remediation techniques (e.g. biocell) | AtkinsRéalis | We don't have a ref for this costs
6 | Land Ownership | The Reclaim Model Version 8.0 does not consider the value of owned land in determining (i.e., reducing) security. | Add consideration for land ownership as a reduction for overall security. | GNWT/CIRNAC
7 | Identify Unit Components without a reference for unit price | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | Any unit components, for example "Remove Fuel Tanks" that do not have a corresponding unit price should be identified. | AtkinsRéalis & Brodie
8 | Unit Prices different from Price Sources | The unit prices in the Reference Table (TABLE 2: RECLAIM v 8.0 Price Sources, Basis and References) do not always match the unit prices in the RECLAIM 8.0 Unit Cost Table. For example, see the unit rate SB1 for "excavate/load/short haul" $16.27 vs $17.00). | Consider integrating the unit prices basis/reference worksheet into the model to reduce inconsistencies and reduce standalone components. | AtkinsRéalis | Discrepancies a result of rounding (need to confrim)
9 | Application of Mining RECLAIM Model feedback into the Oil and Gas RECLAIM Model. | Oil and Gas Producers utilize the "Oil and Gas RECLAIM Model". A similar consultation process should be facilitated for any proposed updates to the Oil and Gas RECLAIM Model. | Conduct a similar consultation and stakeholder engagement process for the Oil and Gas RECLAIM Model 8.0. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
WLWB - Meghan Schnurr
1 | Implementation of RECLAIM V8 | It may help reviewers if the authors could describe how they envision the updated model being implemented. For example: - Do the authors intend to start submitting closure cost estimates generated via RECLAIM V8 for all security-related reviews from the date of publication onward? Would this approach include existing projects that have previously had closure costs estimated using V7? Will the authors expect licensees and applicants to use RECLAIM V8 for all closure cost estimates from the date of publication onward? | Please describe how the authors intend to implement RECLAIM V8. | GNWT/CIRNAC
2 | Comparison against current estimates using RECLAIM V7 | The proposed updates in RECLAIM V8 are noted. Based on the proposed updates, closure cost estimates will be higher than when estimated using RECLAIM V7. This could have implications to the mining industry in the north, so it may be helpful for reviewers to have examples of how closure cost estimates using RECLAIM V8 differ from those generated using RECLAIM V7. | Is there data available that compares how closure cost estimates generated using RECLAIM V8 differ from previous estimates generated using RECLAIM V7?
If not, could this data be prepared and shared? Or perhaps the authors could estimate how different the closure cost estimates will be?
What are the potential implications to the mining industry in the north? | GNWT/CIRNAC
3 | Comparison against known costs to close and reclaim sites | Further to the comment and recommendation above, it may also help reviewers understand the purpose of the proposed changes to the RECLAIM model if data could be provided that compares actual costs to close and reclaim sites to estimates generated using RECLAIM V7 and V8, though, it is not apparent whether this data is available. | Have the authors undertaken an analysis that compares the actual costs to close and reclaim sites against closure cost estimates generated using RECLAIM V7 or V8?
Can this data be provided? | GNWT/CIRNAC | There are sensitives with sharing this data
4 | RECLAIM Oil and Gas Model | It is noted this update pertains to the mining version of RECLAIM. Do the authors intend to update the oil and gas model as well? | Are there plans to update the RECLAIM Model for oil and gas?
If so, are approximate timelines available, and would the process be similar to this update?
If not, please explain why the oil and gas model will not be updated. | GNWT/CIRNAC
5 | User Manual - Discussion throughout on the status of Closure and Reclamation Plans. | The User Manual speaks to the need for applicants and licensees to have CRPs in order to develop closure cost estimates. In some instances, these speak to the need for an approved CRP. For example: - Section 2 Considerations for Northern Settings, "To derive accurate closure cost estimates, it is imperative that the company have an approved CRP which demonstrates a comprehensive understanding…"; and - Section 4.3.1 Engineering Desing, "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities." While it is important to develop a CRP to the point where it can be fully approved, this can take years (specifically for projects that require a type A water licence). This means that closure cost estimates developed during the application phase (pre-construction), during construction, and for the majority of the operational lifespan will be based on CRPs that have not been fully approved. This seems to be acknowledged in Section 4.3.6 Contingency where it is discussed that most CRPs for mining and associated estimates are at the feasibility or advanced conceptual level until near the end of operations. While this helps, it may reduce confusion further if the entirety of the User Manual recognized that CRPs typically require years of development to receive full approval. And for closure cost estimating purposes, it may be more realistic to indicate the applicant/licensee should advance the CRP as early as possible in the project lifecycle. | Consider whether the User Manual should be updated to clarify that it typically requires years to get a CRP fully approved and that applicants/licensees are encouraged to advance closure planning as early as possible.
Consider revising certain messages, for example Section 2, to indicate, for closure cost estimating purposes, it is imperative that the applicant/licensee advance the CRP as early as possible in the project lifecycle. | Brodie
6 | User Manual - Definition of Contingency | A definition for contingency is provided in the Definitions and Acronyms table on page 4. A reference is provided from AACE costing terminology which seems to indicate this definition has been accepted by the construction or engineering community for costing purposes. However, it is not clear whether this definition aligns with how the term contingency is used throughout the document (specifically Section 4.3.6. Contingency) as well as how it is used for the purpose of generating a closure cost estimate via RECLAIM. For example the definition indicates contingency is "Typically estimated using statistical analysis or judgment based on past asset or project experience." Section 4.3.6 does not speak to statistical analysis, rather, the description in this section states "The determination of the contingency percentage is a subjective and project-specific task that relies on the judgement of the estimator." This could create confusion for applicants and licensees in terms of what they are expected to do when proposing contingency percentages. | Review the definition of contingency and consider whether it appropriately speaks to how users of the model are expected to derive contingencies. | Brodie
7 | User Manual - Section 4.2.5 | This section describes a worksheet within RECLAIM V8 for Interim Care and Maintenance. It states that this worksheet captures the costs from cessation of mining activities to when active remediation begins. Is this meant to only cover the time period from cessation until active remediation? What about the period up to executing closure activities - perhaps the use of the term remediation in this case is analogous to closure activities?
Please note that remediation and reclamation in the general sense have different meanings. | Consider whether a revision is necessary to ensure this messaging covers the entirety of the intended period. For example, "the period between cessation of mining activities and when active remediation, or closure and reclamation begins." | Brodie
8 | User Manual - Section 4.2.6 | This section states "These should reflect the monitoring and maintenance plans and commitments identified in the Closure and Reclamation Plan" and later that "it reflects the monitoring and maintenance commitments in the Closure and Reclamation Plan."
The LWBs' Standard Water Licence Conditions include Post-Closure Monitoring and Maintenance Plans, and it is typical for LWBs to require these for projects that require a water licence. Post-Closure Monitoring and Maintenance Plans are the home for the licensee to describe their approach to post-closure monitoring and maintenance. | Consider whether this section should be updated to also reference Post-Closure Monitoring and Maintenance Plans. | Brodie
9 | User Manual - Section 4.3 | The introductory sentence of this section speaks to indirect costs, indicating they are "typically allocated or spread across all activities on a predetermined basis." It is not clear what is meant by "predetermined basis," though, the final sentence in this section indicates indirect costs are calculated based on professional judgement. Either way, please note that this term / the way it is used could lead the user to think that they determine indirect costs, when, regulatory process-wise, the user proposes indirect costs, just like any other cost, and determinations are by the Land and Water Boards. | Consider clarifying the intent of the term "predetermined basis" and its usage, or whether another term could be used instead. | Brodie
10 | User Manual - Section 4.3 | The introductory sentence to this section seems incomplete: "Costs not directly attributable to the completion of an activity, which are typically allocated or spread across all activities on a predetermined basis."
Pending any revisions as per the above comment and recommendation, should this sentence read as follows?: "Indirect costs are costs that are not directly attributable to the completion of an activity. They are typically allocated or spread across all activities on a predetermined basis." | Consider revising the sentence to improve clarity. | Brodie
11 | User Manual - Section 4.3 | RECLAIM V8 proposes an increase of 21% in indirect costs over RECLAIM V7, applied to the summary tab. The LWBs are responsible for setting the amount of security. Overall, it is challenging to consider what evidence is required to justify deviations from the "pre-determined" indirect costs when it is unclear how the "pre-determined costs" were derived. It is unclear what considerations went into deriving these percentages, except for the contingency indirect cost, and therefore how any deviations could be considered in the future. | Please clarify whether RECLAIM has considered deviations from the "pre-determined costs" proposed in section 4.3. Is additional information to support these pre-determined costs available? What evidence could be provided to support a deviation from these costs? | Brodie
12 | User Manual - Administrative Edits | It seems the hyperlinks in the User Manual do not work. | Review and insert links as necessary. | Brodie
13 | User Manual - Administrative Edits | Should Table 2 Column 3 be titled "Typical CRP Phase"? | For consideration. | Brodie
14 | Supplementary Information on RECLAIM V8 February 18,2025 | The supplemental information document references a "Technical Work Group and review of actual cost for Mine Closure and Reclamation at various locations across Canada." Further information beyond this has not been provided. It may be helpful to understand the range of projects and range of costs/percentages considered as part of developing the proposed indirect cost percentages. For example, the supporting information for Owners Representative states "A review of recent projects where Owners Representative costs were incurred at mining closure and reclamation projects ranged from 12% to greater than 20%." | If possible, provide additional information to understand the range of projects (e.g. size of project, type of mine: open pit, underground, etc.) and range of costs/percentages that were considered as part of developing the proposed indirect cost percentages in RECLAIM V8. | GNWT/CIRNAC
15 | RECLAIM V8 - New Line Item - Finalize CRP (% Closure Costs) | The ICM [Interim Care and Maintenance] tab of RECLAIM V8 includes a new line item titled, "Finalize Closure and Reclamation Plan (% Closure Costs)." This is calculated as 4% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between the cost of finalizing a CRP and the associated direct costs (i.e. closure work), and whether/how this considers how advanced the CRP is. This line item also does not seem to align with the text in section 4.3.1 of the Manual which states "In preparing a closure cost estimate, it is typical to assume that there is an existing, approved Closure and Reclamation Plan that can be converted to contract ready documents for closure activities (i.e. engineering is not required to develop a closure plan) and that there are no dramatic departures from the approved Closure and Reclamation Plan." | If possible, discuss how the 4% cost proposed was developed and whether/how this considers the varying degree of closure planning across different projects. | AtkinsRéalis
16 | RECLAIM V8 - New Line Item -HHERA (% Closure Costs) | The ICM tab of RECLAIM V8 includes a new line item "Human Health and Ecological Risk Assessment (HHERA; % Closure Costs)." This is calculated as 3% of direct costs with the exception of ICM and post-closure activities. It is unclear if there is a linear relationship between these direct costs and the development of an HHERA, and how the percentage was derived. | Please provide further information as to how the 3% cost proposed for HHERA was derived. | AtkinsRéalis
17 | Use of Historical Costs | The information provided indicates that costs to clean-up historical federal contaminated sites informed RECLAIM V8. It is noted that the regulatory context and expectations have changed significantly since some of those sites were operational/abandoned. It is unclear how/whether the change in regulatory regime and expectations was considered when reviewing these historical clean-up costs. | Please describe how/whether the change in regulatory expectations was considered when reviewing the historic clean-up costs of federally contaminated sites. | GNWT/CIRNAC
18 | Owners Representative | The supplemental information provided to support the indirect cost associated with "Owners Representative" references support to CIRNAC and scrutiny of the Federal Contaminated Sites Program. Given that the GNWT would be responsible for clean-up for the majority of current projects in the Mackenzie Valley, it is unclear whether GNWT has adopted this same approach to the clean-up of abandoned sites. | Clarify whether the GNWT has adopted this same approach of hiring an Owners Representative. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Independent Environmental Monitoring Agency - Jamie Mistry
1 | Post Closure - Annual Requirements | The Post-Closure sheet requires an estimate of annual costs and the number of years of post closure activities. The overall sum of activities is then multiplied by the number of years to give a total cost. Some post-closure activities will likely occur less frequently than annually, and the spreadsheet calculation will not function correctly in these cases. | Revise the Post-Closure sheet to include columns that list the frequency of each activity, and the number of events expected over the post-closure period, rather than assuming that all costs are annual costs. | AtkinsRéalis
2 | ICM - Water Management | The ICM sheet does not include activities specifically focused on water management during interim care-and-maintenance. These costs are also not specifically addressed in the Water Management or Water Treatment sheets. However, water management is often (perhaps usually) a primary focus of interim care-and-maintenance activities at mine sites, including during temporary closures and in the early stages before active implementation of a closure and reclamation plan. Requirements for accessing security bonds typically arise when there is an early, unplanned mine closure. In these circumstances water management is likely to be a significant activity for maintaining water levels in tailings ponds, managing flood flows, managing runoff from disturbed areas, and dewatering of mines (pits and underground). It is not uncommon for dewatering of mines to continue during periods of interim care-and-maintenance, especially in the event of early/unplanned closure when there may be interest in selling the project - allowing mines to flood is often considered to devalue the "asset" and therefore is part of the necessary care-and-maintenance activities. While there are currently no heap leach projects in NWT, water and solution management at heap leach mines is likely to be the largest cost during periods of interim care-and-maintenance. | Revise the ICM sheet to include activities focused on water management that will be required during interim care-and-maintenance. | AtkinsRéalis
3 | Interim Care-and-Maintenance | The Supplementary Information states that the default interim care-and-maintenance period in RECLAIM is 2 years, but the Interim Care-and-Maintenance (ICM) sheet in the model sets the value at 3 years. Past experience indicates that, in the event of early/unplanned mine closure, interim care-and-maintenance periods can be lengthy because of the time required to sort out financial matters, explore sale/re-opening options, complete CRP development/permitting and procure contractors. 3 years should be the minimum period applied. | Clarify the default duration of interim care-and-maintenance as 3 years, as currently applied in the model. | AtkinsRéalis
4 | Water Management - Sediment/Erosion Management and Control | The Water Management sheet addresses closure and reclamation of operational sediment control facilities. However, it does not directly address the potential need for continued sediment control measures during reclamation activities, or after reclamation activities are complete. This could require construction of new sediment control facilities or improvement (e.g., expansion, armouring) of existing ones. It could also require ongoing operational activities to manage sediment. | Revise the Water Management sheet to include lines related to development and implementation of sediment control measures for the closure and post-closure periods. | AtkinsRéalis
5 | UG Mine - Contact Water Management | The UG (Underground) Mine sheet does not include costs for treatment of mine water. The sheet appears to assume that underground mines will be flooded but no treatment would be required. Some mines may fill and drain over time, with water quality that is not acceptable for discharge. In other cases, leakage from the mine through groundwater is possible, again raising possible water quality concerns. These conditions may require some measures for ongoing or periodic water management or water treatment, including possible active or passive treatment outside of the underground mine, or some form of mine-pool treatment within the mine. | Add water management and treatment as potential costs in the UG Mine sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
6 | Chemicals - Soil Handling | The Chemicals sheet includes costs for excavating contaminated soils and transporting them to an onsite remediation facility, for example a land-farm. There will also be costs for rehandling these soils to a final disposal location at the conclusion of land-farming. | Revise the Chemicals sheet to include lines for final disposal of remediated soils. | AtkinsRéalis
7 | Post Closure - Maintenance | The scope of maintenance activities described in the Post Closure sheet is limited to covers, spillways and wetland treatment systems. For many mine sites, the maintenance requirements will be much more extensive. For example, tailings dams, diversions and sediment control facilities may all require maintenance. Passive treatment systems other than wetlands may also require maintenance or replacement. Wetlands may also require maintenance that is more extensive than what is described, including removal and replacement of substrates and vegetation after some period of time. In most cases, "passive" treatment systems require some periodic maintenance and operational activities, and are therefore better described as semi-passive. | Expand the maintenance components of the Post Closure sheet to address a broader scope of expected maintenance requirements. | AtkinsRéalis
8 | Rock Pile - Heap Leaching | According to the manual, the Rock Pile sheet is intended to address not only waste rock piles, but also heap leach facilities. Closure of heap leach facilities is usually substantially more complex than for rock piles. Heap leach facility closure entails continued solution circulation, heap rinsing, heap detoxification and associated water treatment, managed draindown, decommissioning of pumping and piping equipment, establishment of permanent drainage systems, among other things. The activities listed in the Rock Pile sheet are not adequate to address potential heap leach facility closure. | Incorporate specific activities and costing for heap leach facility closure in the model. | AtkinsRéalis
9 | Bldgs & Equip - Roads | The Bldgs & Equip sheet is missing some activities that may be common for closure and reclamation of roads. Reclamation frequently includes flattening of safety berms along the length of the road, and establishment of effective road blocks and any access points. Also, complete removal of roads back to the native landscape may be necessary in some cases, or overall re-grading of road embankments. Construction or upgrading of drainage works along road alignments may also be required. | Additional road reclamation and closure activities should be added to the Bldgs & Equip sheet. | AtkinsRéalis
10 | Mobilization - Annual Mobilization | The Mobilization sheet includes a column for quantity of mobilization with each type of equipment or supply. In some cases, mobilization/demobilization of equipment could be required annually through the closure and reclamation phase, or periodically during post-closure. For transparency, it would be useful to separate the quantity and the number of annual mobilization requirements - e.g., how many dump trucks have to be mobilized to site in each year. This would provide a better understanding of the equipment requirements and costs over time, and information about what equipment would be expected to remain on site year-round, versus mobilization each year. | Revise the Mobilization sheet to separately identify the annual mobilization requirements. | AtkinsRéalis
11 | Indirect Costs | The Summary Report and Supplementary Information describe the rationale for proposed changes in the default percentages for indirect costs. The rationale is consistent with experience from mine closure and reclamation projects and with current approaches to engineering. The Summary Report also notes that costs for mobilization and interim care-and-maintenance are now included in the base costs for calculating indirect costs. This also makes sense because both of these costs will be subject to the same indirect costs as the rest of the capital costs. | Retain the proposed default indirect costs percentages and the inclusion of mobilization and interim care-and-maintenance costs as part of the capital cost for calculating indirect costs. | AtkinsRéalis
12 | Summary - Indirect Costs | N/a | The updates to the recommended percentages for indirect costs appear to reflect the experience with mine closure and reclamation projects and should be retained. | AtkinsRéalis
13 | User Manual - Section 1 | The final bullet in the list of principles in Section 1 of the User Manual states that financial security must retain its full value throughout the life of the mine and if applicable, beyond. The value of required security may vary through the life of the mine and the wording of the principle should be clarified | The final bullet in the list of principles should be reworded to clearly state that adequate security must be in place throughout the life of the mine and in post-closure to fully address the liabilities associated with the site. | Brodie
14 | Summary - Future Value | The future value calculations appear to assume that the 3 year period of Interim Care-and-Maintenance starts immediately at the time the calculations are completed. This means that if the security amount is set based on today's calculations, but unplanned closure begins 1 year later, the security will be 3% too low, or 16% too low if closure begins 5 years later. | The potential shortfall in liability estimates caused by assumptions about timing for the start of interim care-and-maintenance should be addressed in the model. One option is to establish requirements for frequent adjustments of security (e.g., every 2 years) to account for these shortfalls. | AtkinsRéalis
15 | Summary - Future Value | N/a | The addition of future value is a good idea and should be retained. | AtkinsRéalis
16 | Land Reclamation Activities | In response to a comment/recommendation to include a more comprehensive list of land reclamation activities in the model, the Supplementary Information responds that site-specific activities should be proposed based on end land use and the CRP. The response does not address the comment that was raised. Of course, site-specific closure activities should be defined in site-specific CRPs. However, the model is intended to provide a comprehensive tool for estimating costs of closure and reclamation activities, no matter what activities are selected for a specific site. As a result, the model should include a more comprehensive list of land reclamation activities and provide for estimating their costs, as suggested in the comment. The following comments below identify several specific instances where the model should be revised to include more comprehensive listings of activities. While this is likely not a complete list, it should be considered a starting point for more thoroughly identifying potential closure measures and activities. | Undertake a process to develop a more comprehensive list of possible closure and reclamation activities and incorporate these into the costing model. | AtkinsRéalis & Brodie
17 | Water Management - Reclamation Quarries | The Water Management sheet includes costs for installing and removing pumping systems for managing water in a reclamation quarry. Other costs associated with both quarry development (e.g., material testing, land clearing, road development, etc.) and water management (e.g., diversions, sediment control) for reclamation quarries are not addressed. Reclamation activities often require development of new quarries (in undisturbed areas, or in waste [e.g., overburden] storage facilities) or expansion of existing ones to provide the materials necessary for closure and reclamation. | The Water Management sheet should be revised to include lines that address additional water management activities that may be associated with quarries. Costs for quarry development should also be addressed within the overall model. | AtkinsRéalis
18 | Water Management - Passive Treatment | The activities identified for passive treatment are all associated with construction of wetland treatment. There are other forms of passive treatment that may also be relevant, for example permeable reactive barriers, bioreactors or underground mine pool or groundwater treatment. | The Water Management sheet should be revised to include activities that may be associated with other forms of passive treatment that are not wetlands. | AtkinsRéalis
19 | User Manual - Section 4.2.5 | Section 4.2.5 of the User Manual describes expectations for costing for interim care-and-maintenance activities. The description of a typical scenario states that open pit and underground mines would be allowed to flood. In cases of early or unplanned mine closures (i.e., where there are draws on security bonds), there are often lengthy periods of discussion about mine re-opening and sale. In these cases, mine dewatering often continues in order to avoid reducing the value of a potential asset. The assumption that mine dewatering would be discontinued may underestimate the actual costs that would be incurred. | The default assumption for interim care-and-maintenance costing should be that mine-dewatering will continue for this period. | Brodie
20 | Future Value and Unit Cost Updates | The Supplementary Information describes the new approach taken for estimating the future value for liability estimates. This approach is a positive addition and attempts to address the challenge that the security bonding regime and the forms of security do not allow for bond amounts to grow to address inflation and other escalation of costs. The User Manual defines "escalation" as "a provision in costs or prices for uncertain changes in technical, economic, and market conditions over time. Inflation (or deflation) is a component of escalation."
This acknowledges that inflation is only one component of escalation, with other components (e.g., labour market conditions in northern Canada, or availability of construction contractors) that may also lead to increases in costs. Nonetheless, the User Manual and model only rely on inflation as a cost escalator when calculating future value (Summary sheet) or for updating unit costs (Unit Cost sheet). Other than in the definition of "escalation" there is little further mention of other possible influences on cost escalation, though Section 4.5.1 of the User Manual does identify some other possible sources of information about escalation. | Revise the User Manual and the model to require consideration of other factors for cost escalation. This should include requirements in the User Manual for proponents to provide rationale for selected escalation factors. In the model, it would be useful to include separate entries for inflation and other cost escalators so that there is a requirement to consider whether other escalators are relevant or not. | AtkinsRéalis & Brodie
21 | General Comment - Site Management | The model lacks clear information about person-hours for ongoing administrative responsibilities at the site, for example security, health and safety, personnel management, etc. during the implementation of the closure. Some of these are addressed for interim care-and-maintenance (e.g., on-site caretaker), but would also be required throughout the implementation of closure and reclamation. | Costs for ongoing site management should be addressed either in the Summary sheet, or an additional Site Management sheet should be added. | AtkinsRéalis
22 | Water Treatment - Post Closure | The post-closure component of the Water Treatment sheet does not address major maintenance and equipment replacement activities. Water treatment facilities that have to operate in a long post-closure period will wear out and require refurbishment and replacement at some point in time. Costs and timing for these major capital expenditures need to be included. | Revise the Water Treatment sheet to include lines for costs related to major refurbishment or replacement of post-closure water treatment facilities. | AtkinsRéalis
23 | General | The Independent Environmental Monitoring Agency (Agency) has reviewed the proposed changes for RECLAIM v8.0 and associated user manual (RECLAIM) submitted by Crown-Indigenous Relations and Northern Affairs Canada (CIRNAC) and the Government of Northwest Territories (GNWT). The Agency submits the following comments for your consideration. | N/A | AtkinsRéalis | See Comments 24 to 32
24 | User Manual - Section 1 | Section 1 of the User Manual states a principle that costs should be based on having a third-party contractor carry out the reclamation work. On-site equipment including both mobile equipment and fixed facilities (e.g., water treatment plants) may not be owned by the proponent and costs would be incurred to access the equipment and facilities. | The principle that costs should be based on the cost of having work done by a third-party contractor should be expanded to clarify that the costs must also be estimated assuming that all equipment, supplies and facilities will be provided separately. | Brodie
25 | Tailings - Water Treatment | The Tailings sheet refers to treatment of seepage, which may not be the only treatment that is required for a tailings facility. In some cases, treatment of tailings pond supernatant water may also be required, either during implementation of closure and reclamation, or post-closure. | Revise the water treatment references in the Tailings sheet to include broader references to types of treatment that may be required. | AtkinsRéalis
26 | Open Pit - Pit Closure Methods | The Open Pit sheet considers a narrow range of potential closure options for pits, focused on flooding of pits. There are other options for closure of pits that need to be addressed. For example, some pits may be closed in a dry condition, with associated water management, or some may be backfilled with waste and covered (e.g., Giant Mine Remediation Project). | Revise the Pits sheet to address a broader range of closure options for pits. | AtkinsRéalis
27 | Open Pit - Contact Water Management | The only water treatment option addressed in the Open Pit sheet is the possible addition of in-pit treatment during flooding - either by chemical or biological means. There is no water treatment line linked to the Water Treatment sheet. However, there are some instances where it may be necessary to actively pump and treat water that has accumulated in a pit, potentially before flooding, or to establish dry conditions. | Add active water treatment as a potential cost in the Open Pit sheet, linked as appropriate to additional content in the Water Treatment sheet. | AtkinsRéalis
28 | HHERA and Regulatory | The Summary Report states that the model was revised to include 3% indirect costs for Human Health and Ecological Risk Assessment (HHERA), and 4% indirect costs to finalize the Closure Reclamation Plan (CRP). These additions make sense, but it is unclear where they are included in the model. If they are already included in the Summary sheet calculations, they should be specifically identified. | Provide additional clarity about where the indirect costs for HHERA and CRP finalization are incorporated into the model. | AtkinsRéalis & Brodie
29 | General Comment - Winter Road costs | The Water Treatment and Mobilization sheets include lines for costs associated with use of the winter road. In Water Treatment this appears to be related to site access and reagents, while in Mobilization it is related to equipment, fuel and accommodation (i.e., camp), with a focus on materials that must be brought to site. However, closure for some other components (e.g., buildings, hazardous wastes, contaminated soils) may require shipping off site. Also, it is not clear that winter road costs have been incorporated for all closure and reclamation supplies, for example liner construction materials. These activities may also incur winter road costs. | Where closure and reclamation activities will require off-site shipping or the delivery of supplies to site, sheets should be revised to include lines for winter road costs and other shipping costs. | AtkinsRéalis
30 | Summary - Future Value | The spreadsheet requires the user to enter timing for "when will post-closure begin", by entering a number. Some additional clarity should be provided about what this number represents: Is it the number of years from the current time until post-closure, or the number of years between cessation of operations and post-closure, or the number of years after completion of interim care-and-maintenance before post-closure begins, or some other value? If the timing is intended to start at the time that the estimate is made, then the same shortfall issues identified above for the interim care-and-maintenance timing will also apply to the timing for start of post-closure. | Clarify the intended definitions of timing for when post-closure will begin. | AtkinsRéalis
31 | User Manual - Section 2 | Section 2 of the User Manual describes special considerations for estimating costs for reclamation activities in northern settings. One important factor that appears to be missing is the potential cost implications of meeting requirements for northern participation in contracting and work opportunities. | The bullet list of factors that may affect costs for projects in northern settings should be expanded to include the potential for increased costs associated with meeting requirements for northern participation in reclamation activities. | Brodie
32 | Buildings & Equipment (Bldgs & Equip) - Landfill | The Bldgs & Equip sheet addresses closure of landfills (e.g., placement of cover material) but it does not cover the cost of constructing a landfill. Even for non-hazardous materials, construction of landfills can be a substantial cost. Landfills developed and used during mine operations typically do not have capacity to contain all of the material arising from closure and reclamation. Costs for non-hazardous landfill construction can be substantial in some cases (e.g., Giant Mine). | Revise the Bldgs & Equip sheet to include costs for development and construction of landfills. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Teck Metals Ltd. - Dr. Bjorn Weeks
1 | Feedback Letter | Please see initial feedback in the attached letter.
Inflation Application Without Discounting
The RECLAIM 8.0 update proposes incorporating inflation into cost estimates but does not
address the standard practice of discounting to reflect the time value of money. Applying inflation
without discounting leads to distorted financial obligations, potentially resulting in excessive and
unrealistic financial security requirements.
Without discounting, even minimal recurring annual costs (e.g., $20,000 per year) would result in
infinite bonding requirements, which contradicts financial principles and international best
practices.
Financial assurance practices that deviate substantially from international best practices may
place the region at a competitive disadvantage, while failing to deliver real benefits
| Paraphrased: Include discounting into cost estimate | GNWT/CIRNAC
2 | Feedback Letter | Please see initial feedback in the attached letter
Absence of Any Credit for Company Size and Environmental Performance
We believe the bonding requirements should take into account both past environmental performance and the financial resources available to the company to meet its environmental
liabilities.
Teck is one of several International Council on Mining and Metals (ICMM) member companies operating in the region. No ICMM member company has ever defaulted on its closure obligations, nor would doing so be feasible in the context of maintaining a global social license to operate.
| Paraphrased: Credit for environmental performance and the financial resources | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Pine Point Mining Limited (PPML) - Ms. Veronica Chisholm
1 | Increased Unit Costs | Please see initial feedback in the attached letter
The justification for increased excavation and hauling costs (e.g., short-haul soil movement increasing from $4.3/m³ to $17/m³) lacks transparency on how these figures were derived. What specific contractor quotes, productivity rates, or haul distances were used in these calculations?
Were regional variations considered, or was a blanket rate applied regardless of site-specific factors?
Can industry propose alternative short-hauling costs based on regional/site-specific factors such as terrain, available borrow pits, road conditions, access to rail, and equipment availability? For example, a mine site with established all weather and paved
road networks and short, efficient haul routes may have significantly lower hauling costs than a remote site requiring seasonal ice road access. Will proponents have flexibility in
presenting alternative cost estimates to justify lower unit costs?
Paraphrased:
Provide more detail on unit rate development.
Unit rates should include regional variation.
Clarify if user-specified rates can be used in RECLAIM. | AtkinsRéalis
2 | Higher Indirect Cost Percentages | Questions Asked
Contingency Increase (20% to 25%): While uncertainty exists in closure planning, what empirical data justifies a 25% contingency rather than the previous 20%? Can examples
of cost overruns from past projects be provided to support this increase?
Engineering Design (5% to 8%) & Project Management (5% to 10%): These increases suggest significantly greater complexity in closure execution. What historical data from northern mine sites demonstrate that these cost assumptions are necessary?
Bonding/Insurance (1% to 3%): Can specific case studies or actuarial assessments be provided to validate this change? | Paraphrased:
Provide further justification to increased contingency percentages.
Provide further northern justification to increased engineering design percentages.
Provide case studies to justify increase in bonding/insurance percentage. | AtkinsRéalis
3 | Reclassification of Mobilization and Interim Care & Maintenance (ICM) as Capital Costs | Moving these costs to Capital Costs now subjects them to contingency and indirect cost multipliers. How does this align with the principle of accurately reflecting third-party contractor costs?
Industry projects varying durations of ICM depending on site conditions. How was the assumption of a minimum 3-year ICM period determined, and why is it being applied
universally? | Paraphrased:
Include more rationale as to why Mob and ICM were moved to Capital Costs and whether this accurately reflects third-party contractor costs.
Provide rationale and justification for minimum 3-year ICM period. | AtkinsRéalis
4 | Owner's Representative Cost (10% of Direct Costs) | This is a new addition to RECLAIM. While we acknowledge the role of an Owner's Representative in some government-managed projects, why is this now mandated for all
projects, including those with active operator management?
Can industry proponents provide alternative methodologies for project oversight rather than defaulting to a 10% additional cost? | Paraphrased:
Provide rationale for why Owners Rep costs are applied to all mines. Can industry propose an alternate methodology for oversight rather than the default. | AtkinsRéalis
5 | Human Health and Ecological Risk Assessment (HHERA) Cost (3% of Capital Costs) | Industry already conducts environmental monitoring as part of regulatory requirements. What additional studies are being assumed under this cost, and how is the 3% figure justified?
Given that mines with comprehensive monitoring programs may already demonstrate minimal risk, why is this cost not applied selectively based on site-specific needs?
Can proponents outline their monitoring programs and propose a more phased cost-structure alignment with project-specific timelines? | Paraphrased:
Can CIRNAC and GNWT provide additional studies to industry to justify the 3%?
HHERA should be applied to mines selectively based on environmental performance.
There should phased cost structure that could align with project timelines. | AtkinsRéalis | Not sure what is meant with third recommendation.
6 | Future Value Calculation (3% Inflation Rate) | While inflation is a factor in cost projections, applying a fixed 3% escalation rate does not account for fluctuating economic conditions. Has any sensitivity analysis been conducted
to assess alternative inflation scenarios?
Can proponents propose their own escalation methodologies based on contractual arrangements and project-specific timelines? | Paraphrased:
Sensitivity analysis should be conducted on applying a fixed inflation rate for future value calculations.
Proponents should be able to propose their own escalation methodologies based on contractual arrangements and project-specific timelines. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
De Beers Canada Inc. - Gahcho Kue - Kurtis Trefry
1 |  | De Beers is supportive extended engagement period granted to allow further opportunity for industry feedback to be considered into any changes. The initial deadline coincided with our annual reporting timelines, creating challenges in dedicating the necessary time and resources to this review. The additional time granted will allow us to prepare a thorough and well-considered submission that adequately addresses the updates. Given the potential for significant implications to the mining industry, the proposed changes to the RECLAIM model require significant time and resources to allow for a detailed review by all parties.
De Beers looks forward to partaking in further engagement sessions and will provide more detailed comments following that period. | N/A | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Fisheries and Oceans Canada (DFO) - Mr. Derek Donald
1 | Financial security associated with Fisheries Offsetting Plans. Specified under Section 2 (1)(b) and Schedule 1, Section 16, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations. | Fisheries and Oceans Canada (DFO) would like to thank CIRNAC and the GNWT, for developing and updating the RECLAIM model and providing this opportunity for review and comment. The RECLAIM model can be an important part of the Fisheries Act authorization process in that the model is often used by proponents when developing an itemized list of costs for conducting the Offsetting work and monitoring the project to inform the Letter of Credit associated with an Offsetting Pan, and by DFO when reviewing the financial liability associated with these plans.
Fisheries Act authorizations can follow the lifecycle of a mine from pre-operational permitting to post-closure Offsetting Project monitoring. Financial liability and associated security in the form of an irrevocable Letter of Credit, is a key component of the Fisheries Act and associated Regulations. Mine development in Nunavut and the Northwest Territories often necessitates activities that directly or indirectly result in the Death of Fish, the Harmful Alteration, Disruption or Destruction of fish habitat, and/or the deposit of deleterious substances in water frequented by fish, governed respectively by Section 34.4, 35, and 36 of the Fisheries Act.
These activities can be authorized under the Fisheries Act so that the activity is carried out in accordance with conditions set out in the authorization and the Regulations. Section 2 (1)(b) and Section 16 of Schedule 1, of the Authorizations Concerning Fish and Fish Habitat Protection Regulations, requires the development of a Fish Offsetting Plan, including the financial liability and associated security, to cover the costs of implementing the fish Offsetting Plan.
These Fish Offsetting Plans often include activities associated with general construction, ground and water works, culvert installation, long-term monitoring, etc. Costs associated with these Fish Offsetting Plan activities can be subject to individual cost estimates based on a proponent's experience and can also be scrutinized with limited referenceable sources. This type of subjective cost estimation and review creates risk and introduces uncertainty, for both proponents and liable governmental parties (DFO and ECCC).
DFO believes this update to the RECLAIM model is an excellent opportunity and the appropriate location to include constrained cost estimates for these types of activities. DFO would like to discuss this further with CIRNAC and the GNWT during the week of May 12 - 16, 2025. DFO would also be interested in hearing feedback from all interested parties. | DFO recommends that the RECLAIM Model include in a Summary line item, and associated sheet in the Excel model specific to the implementation of a fish Offsetting Plan. This could include, but not limited to works associated with discipline specific construction, ground and water works, culvert installation, and long-term monitoring. Adding this to the model would reduce financial risk by providing a more predictable process of securing a Fish Offsetting Plan, which is ultimately tied to the final reclamations of a mine site that has impacted fish and fish habitat. DFO would like to discuss this possibility with CIRNAC, the GNWT, and all interested parties during this update of the RECLAIM model. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Arctic Canadian Diamond Company Ltd. - Feyisetan Adebayo
1 | Letter | Please see attached letter.
2 | Origin of Unit Rates | Burgundy Diamond Mines (Burgundy) and other proponents have been requesting that CIRNAC and GNWT provide the level of transparency and justification for RECLAIM unit rates that is demanded of proponents who put forward site-specific unit rates. This long-standing request remains wholly unsatisfied by the information provided with RECLAIM 8.0.
For example, the proposed "load/haul/place" unit rates are described as being derived from "First Principles". However, simply referencing "First Principles" and listing a few assumptions under additional notes does not provide proponents with the information needed to adequately understand the unit rate or assess appropriateness for a specific site. | RECLAIM 8.0 should be accompanied by clear, detailed data on the derivation of the proposed unit rates, ensuring proponents can adequately understand the rates and make a rational determination of their appropriateness for an individual site or closure activity. | AtkinsRéalis
3 | Moving Mobilization and ICM to Capital Costs | Mobilization and ICM costs were previously included under Indirect Costs which excluded them from the indirect percentage calculations. The new approach introduces a compounding effect and will significantly inflate the overall security estimate. This would result in overestimations that do not accurately reflect actual closure and reclamation needs particularly for major operations such as Ekati Diamond Mine (Ekati) with substantial security requirements. | The Mobilization and ICM costs should be maintained under Indirect Costs where the existing indirect cost percentages can adequately account for variations. This would avoid the compounding effect introduced by their inclusion in Capital Costs while still ensuring these costs are adequately captured within the model. | AtkinsRéalis
4 | Owner's Representative | A new line has been added under Indirect Costs for Owners Representative to ensure that project objectives are met, with a default percentage of 10% of the direct costs assigned. The assigned percentage appears excessively high particularly for licencees with substantial direct costs. | The assigned 10% default percentage should be reevaluated and a reduction considered to better align with actual project requirements and industry norms. Additionally, more information should be provided to clarify the methodology and rationale behind determining this percentage and to assess its applicability across different projects. An alternate approach, such as an estimated cost (rather than a percentage) should also be developed and evaluated. | AtkinsRéalis
5 | HHERA and Final CRP Costs | The cost to complete a Human Health and Ecological Risk Assessment (HHERA) and Final Closure and Reclamation Plan (FCRP) has been added to the model at 3% and 4% of Capital Costs, respectively. While it is acknowledged that FCRP costs may not have been explicitly included in RECLAIM 7.0, the regular review of security estimates has ensured their incorporation for operations like Ekati. The most recent review by the GNWT in 2022 determined a significantly lower FCRP rate of approximately 1% of direct costs. There is no rationale for applying these items as a percentage of total rather than an estimated cost. These items are well established and well defined in scope and cost such that actual estimates can readily be developed. A percentage of total as proposed provides a grossly over-costed estimate for large site such as Ekati.
Moreover, the risks addressed by HHERA are already evaluated as part of the permitting process. Monitoring data is utilized to assess operational and closure risks, which are accounted for in interim CRPs that are mandatory and regularly updated. As such, the addition of these costs in the proposed model is deemed unnecessary and the proposed percentages appear excessively high. | Burgundy recommends that HHERA and FCRP costs be excluded from the model. Alternatively, these percentages should not be based on Capital Costs given that risk evaluations and FCRP development will rely significantly on existing assessments and CRP plans developed during ongoing operations. A reduction or redefinition of these percentages is necessary to ensure they more accurately reflect the actual scope of work and associated costs. An alternate approach of an estimated cost (i.e., not a percentage) should be developed and evaluated. | AtkinsRéalis
6 | Future Value Calculation | The future value calculation has been introduced to capture the anticipated costs of activities based on when they are expected to occur. A default inflation rate of 3% is applied which corresponds to the Bank of Canada's upper target for annual inflation. For example, a cost estimate developed in 2028 using RECLAIM 8.0 standard rates would undergo a 3% annual inflation increase over four years (2024 to 2028). However, applying a predetermined, singular inflation rate is not appropriate when actual data is available. It is also not always suitable to apply the same inflation rate across all work included in a closure estimate. RECLAIM 8.0 documentation acknowledges the existence of various inflation estimates beyond the broad-based consumer-oriented CPI, but it discounts these approaches. Since the majority of mine closure plan costs are not consumer-oriented, it may not be appropriate to apply the general CPI across the entire estimate. Ekati's security estimates already incorporate an inflation calculator developed with stakeholders' input. This calculator considers the development year of each unit cost and applies inflation rates accordingly, resulting in inflation rates of less than 2%.
Applying the upper target of the Bank of Canada's inflation range may lead to overestimations, given that average inflation rates have remained between 1.5% and 2%. This approach is not ideal for long-term mine closure costing, as it introduces inflation without accounting for interest. It assumes that the financial security is cash in hand, which does not accrue interest over time. By comparison, the Province of British Columbia uses a net discount factor (i.e., net of both inflation and interest) for recurring long-term costs. The approach proposed in RECLAIM 8.0 introduces a substantial cost factor that could significantly affect project viability. This issue requires detailed engagement and financial analysis by the government before any consideration for implementation. | 1. RECLAIM 8.0 should provide a clear rationale for adopting a single pre-determined inflation factor and consider developing an alternative approach that utilizes inflation rates most appropriate to the specific work and costs within the closure cost estimate. The future value inflation rate should be revised to reflect a more accurate figure, such as the average of historical inflation data over a relevant timeframe, rather than defaulting to the upper target of 3%.
This adjustment would result in a more balanced and accurate estimate, avoiding excessive conservatism in the model. Additionally, greater transparency is needed in how inflation rates are applied to different unit costs over time to ensure consistency and confidence.
2. This cost item should not be implemented without specific, in-depth engagement and financial analysis including an evaluation of experiences in other regulatory jurisdictions. | GNWT/CIRNAC
7 | Incentivizing Progressive Reclamation | The proposed updates to RECLAIM 8.0 emphasize increasing securities to address potential reclamation costs. It is equally important to incentivize progressive reclamation during operations. Progressive reclamation not only reduces overall closure liabilities but also demonstrates ongoing commitment to environmental stewardship. Models used in jurisdictions such as Quebec and the Alberta oilsands provide practical examples of incentivizing progressive reclamation by allowing operators to utilize existing securities during operations, thereby encouraging earlier action rather than deferring it until closure. | Burgundy recommends that the GNWT implement mechanisms to incentivize progressive reclamation activities during operations. This could include provisions that allow for the partial release or reallocation of securities to fund reclamation efforts. Such measures would enhance operational efficiency, reduce the financial burden of increasing securities and encourage operators to proactively incorporate reclamation into their operational plans. This approach would ultimately lead to more sustainable and cost-effective closure outcomes. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Tlicho Government - Jessica Pacunayen
1 | General | The T???cho? Government reviewed CIRNAC and GNWT's proposed revisions to RECLAIM 8.0, the RECLAIM User Manual, and supporting documentation. These documents are used by the GNWT, CIRNAC, mining companies, and the Land and Water Boards to set mining security deposits. RECLAIM and the User Manual are also a resource for all parties reviewing security deposits. T???cho? Government may also wish to use RECLAIM to estimate security deposits for future mines on T???cho? Lands. | N/A | GNWT/CIRNAC
2 | Increased security deposits | RECLAIM 8.0 includes numerous substantial increases. Most unit costs went up to varying degrees, and a few went down. On average unit costs appear to have more than doubled. Some key unit costs have increased far more than this, for example the lower estimate for winter road construction went up by more than 10 times. Indirect costs are now up to 58% of direct costs instead of 32%, plus there are new costs for a human health and ecological risk assessment and finalization of the closure plan (totaling 7% of capital costs). There is also a newly proposed cost for inflation during closure and post-closure. Post-closure monitoring and maintenance and mobilization/demobilization now have indirect costs (as percentages) added to them. These and other increases would result in very large increases to security deposits at existing mines. CIRNAC/GNWT explained that the increases are because the current unit costs (in RECLAIM 7) are more than 10 years old and because costs in the current RECLAIM spreadsheet (version 7.0) are too low compared to actual costs the government has incurred for actual reclamation projects. As noted in "Review of Mine Financial Security Estimates and RECLAIM": "it has been CIRNAC's experience with management of abandoned mines that the financial security held for these sites has fallen well short of actual expenditures." CIRNAC and its consultants are perhaps in the best position to provide actual costs of closure activities. There has been talk over the years that RECLAIM is dramatically underestimating closure costs. It is possible that even with the proposed revisions, RECLAIM 8.0 would continue to underestimate reclamation costs. For example, the Supplementary Information provided on Feb 18 says that the Owner's Representative costs are actually 12% to over 20% of costs, not the 8% adopted in the proposed revisions to RECLAIM. This is just one of several examples that may mean the RECLAIM 8.0 continues to underestimate reclamation costs. Others are in comments below. | RECLAIM should estimate the actual costs of closure and reclamation, even though it appears that the new estimates will likely be much greater than current security deposits. However, this does not mean that the Boards should immediately increase all security deposits in the North to reflect actual reclamation costs. This could have serious economic and social repercussions, and could undermine the objectives set for resource management under the modern treaties, to balance conservation and development for 'optimum benefit'. Instead, updating RECLAIM to reflect actual costs is a necessary first step to fixing some serious and far-reaching problems related to security deposits and more broadly to sustainable and responsible mining in the North.
Actual reclamation costs must be known and on the table in order to have informed discussions about the impacts, benefits, and risks of mining, including the risk of having to pay for cleanup of abandoned mines.
Underestimating security can also enable companies with insufficient financial resources to mine in the North, which poses a serious risk to the Northern economy and the environment. Greater attention should be given to a mining company's financial health and the risks for each project (e.g., risks from market conditions, remoteness, logistical issues, etc.) when weighing the impacts, benefits, and risks of approving a full-scale mine.
Decisions about how much risk is acceptable and what the right balance are ultimately policy decisions to be made by Indigenous and public governments, informed by robust evidence and analysis, and input from citizens and residents. If the federal and territorial governments, or the Boards in working to achieve the treaty-based objectives for resource management, wish to offset the burden of posting security for actual reclamation costs, this should be done in a transparent, carefully considered manner informed by the actual costs of clean-up and the views of all parties. The T???cho? Government would like to be involved in any such discussions, and as a treaty partner, must be involved in these discussions.
Other topics raised in our comments are inextricably intertwined with the issue of RECLAIM estimates, for example relinquishment of liability, promoting progressive reclamation, and financial security for potential disasters. These issues should be discussed holistically along with RECLAIM updates. Some of these issues may need legislative amendments to properly address them in the long run. | GNWT/CIRNAC
3 | Increased security deposits - incentives for progressive reclamation | The RECLAIM Manual includes a policy that the security deposit cannot be reduced for progressive reclamation (reclamation completed during operations) until the mining company has completed the reclamation work. This is a sensible approach to ensure there is always enough money for reclamation if a company goes bankrupt. However, a more refined and strategic approach to this problem should be considered to enable work to proceed while limiting risks if a company goes bankrupt. This would allow more parts of a mine to be reclaimed early in the mine life, which benefits the environment, the taxpayer, and the company. A company's financial capacity, the financial and environmental risks of leaving parts of the mine unreclaimed, and other factors would need to be considered. | Financial mechanisms to promote progressive reclamation should be evaluated and discussed with all parties. | GNWT/CIRNAC
4 | Increased security deposits - case studies | Based on our participation at the meeting hosted by CIRNAC and GNWT during the PDAC conference in March 2025, we understand there may be disagreement over whether RECLAIM 8.0 is overestimating or underestimating closure costs. CIRNAC and the GNWT have actual cost data from abandoned mine reclamation in the North. Using this data to validate RECLAIM 8.0 is an indispensable step to deal with these opposing views and to ensure security deposits cover the full costs of reclamation without unduly burdening industry.
The Discussion Paper says that CIRNAC and GNWT had originally intended to use historical data to help populate RECLAIM 8.0 (which is different than historical data for validation). However, the Discussion Paper says this did not happen because "contractor confidentiality, limited examples available to provide a sufficient range and average of costs (which can vary considerably depending on the size and scope), and the effort required to synthesize data." While these issues might make it challenging to use historical cost information to update RECLAIM 8.0's costs and assumptions, it should not prevent validation of the model. Validation is about running information from past projects through RECLAIM 8.0 and comparing this to the actual cost of the project. If confidentiality issues cannot be addressed, CIRNAC and GNWT should at least conduct this validation step internally and publicize whether the exercise validated the model. Further, "the effort required to synthesize data" may be a barrier, but it is arguably a relatively small price to pay compared to the benefits of improved cost estimates.
In addition to this validation step, CIRNAC and GNWT should use historical cost data to improve RECLAIM. Based on the unit cost reference tables provided as supporting documentation, it appears this may have been done to some extent. If not, CIRNAC and GNWT should take advantage of historic cost data in ways that maintain confidentiality and account for limitations in the data. | 1. Before finalizing RECLAIM 8.0, CIRNAC and GNWT should validate it, by running RECLAIM (i.e., entering actual quantities, selecting the appropriate unit costs, etc.) with information from actual reclamation projects at abandoned mine sites. The resulting RECLAIM 8.0 estimate should be compared to the actual cost. If these are substantially different, adjustments should then be made to RECLAIM 8.0 from lessons learned from this comparison.
2. Historical cost data should also be used, to the extent possible, to update RECLAIM with actual cost information, without compromising confidentiality. | GNWT/CIRNAC
5 | Internal government costs | RECLAIM does not include the substantial internal costs for CIRNAC and GNWT, for example government employee salaries. This means there is no transparency about what these costs are or what the actual costs are when a mine is abandoned. | Please explain why these costs are not considered when estimating the costs of reclaiming a mine. | GNWT/CIRNAC
6 | Calculating security annually | The proposed RECLAIM Manual update includes a new requirement that "The total financial security for final reclamation required at any time during the life of the mine should be equal to the total outstanding reclamation liability for land and water combined (calculated at the beginning of the work year, to be sufficient to cover the highest liability over that time period)." This mirrors the Mine Site Reclamation Policy for the NT, which is well over 20 years old.
It is not clear how this would be implemented. Is GNWT/CIRNAC anticipating that water licences would have a schedule with annual increases to security? This has not been recent practice. Or is a RECLAIM review anticipated each year? TG is concerned that this would place a big resource demand on all parties. Also, how would the common practice of increasing security at project milestones (e.g., commencement of construction, mining, or milling, percent of pit filled, etc.) fit into this approach? | Clarify how this requirement would be implemented. | GNWT/CIRNAC & Brodie
7 | Human health and ecological risk assessment | The proposed revisions to RECAIM include the cost of a human health and ecological risk assessment (HHERA). The User's Manual notes that this is completed in accordance with federal risk assessment guidance. Modern mines are different than mines abandoned in the past in that they have approved closure objectives and in many cases, approved closure criteria. It is our understanding that, in the past, HHERAs at federal sites have been used to set the standard for cleanup, for example the water or soil contaminant thresholds that must be met. If a modern mine is abandoned during operations and is in compliance with its water licence, land use permit, and other authorizations, unexpected contamination (beyond what is addressed in the approved closure plan) may be less than in the past.
Some mines may include an HHERA in their approved closure plan to confirm predicted risks. However, it is not clear what role an HHERA would play at an abandoned mine. We are concerned that use of HHERA's could lower the standard compared to approved closure criteria. Closure criteria have been publicly reviewed, vetted and debated in countless workshops, and represent substantial input from all parties. Closure criteria have been deliberated by the Boards and Board decisions on them have been transparently documented. Ignoring approved closure criteria after abandonment would be inconsistent with the land claim agreements that established the Land and Water Boards. | If an HHERA is part of an approved closure and reclamation plan, then the cost of it should be in RECLAIM. Also, if the GNWT and CIRNAC expect that new risks will emerge after abandonment of mines with modern, approved closure plans, then an HHERA should be a default cost in RECLAIM. However, the RECLAIM Manual should acknowledge that Board-approved closure criteria are the clean-up standard at abandoned mines, unless it is demonstrated that these cannot be achieved or that new criteria are needed for risks that developed after abandonment. An HHERA may play a role in this effort, but HHERA's should not be a replacement for closure objectives and criteria. | AtkinsRéalis & Brodie
8 | Monitoring | The draft RECLAIM Manual says that monitoring will be conducted "with respect to the effectiveness of the mitigative measures, the accuracy of the environmental assessment and any unforeseen environmental impacts". Although true, this statement does not appear to reflect current practice. To our knowledge, all closure plans (and therefore security deposits) in the NT are founded on the MVLWB/AANDC Guidelines for the Closure and Reclamation of Advanced Mineral Exploration and Mine Sites in the Northwest Territories. Therefore, all mines have Board-approved modern closure plans that are based on closure goals, principles, closure objectives and closure criteria. This means closure criteria will dictate monitoring plans and duration. The effectiveness of mitigative measures and the accuracy of the environmental assessment will be reflected in the criteria. If there are unforeseen environmental impacts, closure criteria should be updated. | The RECLAIM Manual should state that monitoring will depend on closure criteria. | Brodie
9 | Relinquishment of liability | The revised Manual states that "Following mine closure, mining companies or their future owners should continue to be responsible for the site , including the remediation of any additional environmental complications which develop." This raises questions about relinquishment of liability. For many years, many parties have been requesting clarity on how liability will be relinquished at mine closure. This is especially important with mines like Diavik approaching the end of operations. This gap creates uncertainty and may inhibit investment in sustainable and responsible mining in the North. | 1. It is understood that additional policy, legislative, or regulatory amendments may be needed to address how and to what extent companies are released from liability once all closure criteria have been met. For example, will companies be required to leave funds for future monitoring, maintenance, or unforeseeable events at the closed mine? These funds may require supporting legislation and/or policy.
Even if the GNWT cannot undertake an effort to better address relinquishment before the RECLAIM updates are finalized, the Manual (or another document) should include more information on this topic. This would assist all parties in understanding how GNWT and CIRNAC will approach relinquishment of liability under existing legislation.
2. The GNWT and CIRNAC should immediately begin the effort to outline the conditions and criteria that will allow relinquishment, establish how much money will be required for monitoring, maintenance and unforeseeable events, clarify the extent to which companies will be released from liability, and develop a relinquishment process. This effort will need to involve Indigenous Governments early on. | GNWT/CIRNAC
10 | Performance holdback | The revised Manual states that "If the company carries out progressive reclamation during operations as proposed, such as revegetation of disturbed areas during operations, then the closure cost estimate could be reduced by the associated costs for that component when the company demonstrates that the closure activity has been successfully completed and closure objectives and criteria have been met." It is our understanding that the LWB/GNWT/CIRNAC Guidelines for Closure and Reclamation Cost Estimates for Mines allows for some money to be refunded to companies, even if criteria have not been met. This is allowed so long as a performance holdback is set. The same Guidelines explain how a performance holdback could be set, including three different methods. The first method uses a simple percentage-based approach by mine component, the second method uses RECLAIM, and third uses a "factored risk" approach. | RECLAIM should reflect the CIRNAC/GNWT/LWB Guidelines as they relate to performance holdbacks. Calculations based on the Guidelines should be inserted into RECLAIM. This would include simple calculations supporting Table 1 of the Guidelines (the percentage-based approach). It could also include calculations to support the "factored risk" approach on page 19 of the Guidelines. Support for companies to estimate performance holdbacks will promote a quicker and more efficient security refund process.
Although all regulators that use RECLAIM may not require performance holdbacks, those regulators could simply ignore the calculations, or the GNWT could develop them for use in the NT only. While it is beneficial to have only one version of the RECLAIM model across the North, add-ons to reflect jurisdictional differences could help to ensure that RECLAIM is useful everywhere while maintaining a core set of shared calculations and inputs. | GNWT/CIRNAC & Brodie
11 | Documentation of security refunds | Similarly, security refunds for completed progressive reclamation or completed work during active closure is becoming more common and is an important way to promote and reward early closure work. Currently, RECLAIM does not document these refunds, which means there is no record of the original estimate, the refunds given, and what the refund was based on. This may make it difficult to determine refunds during active closure, since it may not be clear what has already been refunded and what is still being held as security. | RECLAIM should document all security refunds. For example, RECLAIM could include a refund summary sheet showing the original estimate, all refunds, and links to documentation supporting the refund (e.g., RECLAIM estimates used to calculate refunds, Board decisions, etc.) | Brodie | This cost estimating tool is not the mechanism for tracking security refunds
12 | Disasters | RECLAIM does not cover the costs of disasters. With numerous mines using the RECLAIM model across Canada's North, there is a significant risk that one or more of these mines will have an environmental disaster during the life of the mine. Currently, disaster clean-up costs would fall entirely to the taxpayer. The recent disaster at the Eagle Mine in Yukon is an excellent demonstration of how the taxpayer will be forced to carry the burden of disaster clean-up. Such costs could easily be in the hundreds of millions of dollars or more. The Mount Polley disaster in 2014 is another example of taxpayers covering significant costs for a mining disaster. Although this may be considered a policy decision that is outside of the scope of RECLAIM, RECLAIM by necessity houses many policy decisions by virtue of the costs it includes or excludes. RECLAIM unavoidably sets policy through its underlying principles and assumptions. Excluding disaster costs is as much a policy decision as including them. | Security for potential future disasters should be required. Since most mines are unlikely to experience a disaster, the amount held by any single mine should only be a fraction of potential disaster clean-up costs. This could be determined based on the risk profile of a project (e.g., potential for acid drainage, geotechnical failures, proximity to highly valued areas, etc.). If disaster costs are not included in RECLAIM, another mechanism is urgently needed to ensure that industry contributes towards a pot of money for future disasters. | GNWT/CIRNAC
13 | Revegetation | Revegetation of a site after closure is an important part of restoring the land, enabling long-term future cultural use, making the site look and feel like the surrounding area, and supporting wildlife. The revegetation unit costs in RECLAIM include seeding and tree planting. Planting cuttings, transplants, or plugs are other examples of revegetation, and likely have different costs than seeding and tree planting. Placement of stockpiled reclamation materials such as topsoil, till, lakebed sediments, etc. should also be included in direct costs for revegetation. | RECLAIM should include the cost for all types of revegetation, including cuttings, plugs, transplants, and spreading stockpiled dirt and soil. | AtkinsRéalis & Brodie | Suggest a User Specified activity and cost in RECLAIM
14 | Traditional Knowledge monitoring | Traditional Knowledge (TK) Monitoring is a critical part of ensuring the closed site meets closure objectives and goals. TK Monitoring is also essential for building community confidence in the closed site to enable long-term future use of the site. (For example, we note that the WLWB requires Diavik to prepare a TK Monitoring Plan). | RECLAIM should include the costs of a Traditional Knowledge Monitoring Program. This would involve regular (e.g., initially annual) site visits from Elders, youth, and staff to evaluate water quality, wildlife safety and movement, vegetation, and more. It is important to note that this is not the same as engagement or regulatory costs. This TK Monitoring Program is similar to other monitoring programs and should be a line item in the Post Closure sheet along with the scientific monitoring programs. | GNWT/CIRNAC | AtkinsRéalis supports this as its something that would like fall on governments books if a site were to be abandoned and this cost can be substantial.
15 | Net Present Value | To date, RECLAIM has included the ability to calculate the net present value. This was used for very long-term costs (e.g., more than 20 years) such as maintenance of constructed wetlands. This reduced the amount of security a company needed to post, without exposing the tax payer to increased risk. This is because the net present value accounted for the fact that money set aside for the future can be invested and will grow. The discount rate used in those calculations was generally an assumed modest growth in investment (e.g., 5%) minus an assumed inflation (e.g., 2%). | Why has the net present value function been removed from the draft RECLAIM? | AtkinsRéalis & Brodie
16 | Interim Care and Maintenance | The RECLAIM model includes an estimate for interim care and maintenance, meaning the period after bankruptcy and abandonment and before active closure begins. The total cost is based on an annual cost (commonly a few million dollars) times the number of years the site is likely to be in interim care and maintenance. The draft RECLAIM 8.0 model includes a default of 3 years of interim care and maintenance. However, the supporting documentation for the RECLAIM updates (Review of Mine Financial Security Estimates and RECLAIM) says "Importantly, the duration of Interim Care and Maintenance is typically limited to two to three years. It is known that government experience has been much different than this, both in scope and duration. This is an obvious category for which government could be under secured". The same document provides some evidence that the actual period could be five to ten years. | The estimated time a site is in interim care should be based on the expected or average duration not the minimum. | GNWT/CIRNAC | AtkinsRéalis agrees that even 3 years is low for ICM. However, we question whether its fair to hold additional securities to account for a transfer from the mine to government. For discussion.
17 | Unit costs - reference table and sources | During the public review, a reference table showing the source for unit cost assumptions was provided. | 1. This reference table is a significant improvement and should be included in the finalized model. It improves transparency and credibility of the unit costs and enables industry and decision-makers to discuss alternative site-specific unit costs.
2. Unit costs adopted from projects in the South (e.g., Sudbury) should be increased if these costs are going to be higher in northern, remote conditions.
AtkinsRéalis
18 | Fish habitat | The Open Pit tab does not explicitly include costs for building fish habitat (littoral zones), even though these may be required in pit lakes or pits that will be reconnected with larger lakes. Some of the activities in the tab may address fish habitat construction (e.g., placing fill), but it is not clear whether all activities required to build littoral zones are in RECLAIM. (Fish habitat construction may be required by the Department of Fisheries and Oceans and/or the Land and Water Boards. In either case the estimate should be included in RECLAIM. If DFO already holds security for this activity, it can be subtracted from the RECLAIM estimate. If it is only required by the Land and Water Boards, then it would remain in the final total.) | RECLAIM should include costs for construction of fish habitat in pits. | GNWT/CIRNAC | Seems out of scope of for the default RECLAIM, but if it has been agreed with DFO costs are not held with them then it should be captured here.
19 | Scientific and Traditional Knowledge research | Typically, the CRP will have several approved reclamation research plans. If a mining company abandons a mine, important reclamation research may not have been carried out. The results of this research will be needed to properly reclaim the site. | RECLAIM should include the costs of scientific and Traditional Knowledge reclamation research. As noted by BCL in their memo, this could result in mines not proposing research, in order to avoid higher security deposits. BCL proposed some alternatives to address this problem (page 18 and 19 of the BCL memo). These could be considered, provided the details of the approaches are publicly reviewed. | GNWT/CIRNAC
20 | Risk communication | The RECLAIM model does not include the costs of risk communication. In order to restore confidence in the mine site area so that closure objectives related to cultural use can be met, a good risk communication plan must be developed and carried out. This may involve public meetings, posters, online tools, social media, radio, newspapers, etc. | RECLAM should include the cost of risk communication. If this cost is lumped in with other costs (e.g., engagement and regulatory compliance costs), this should be mentioned in the User's Manual. This will ensure that the portion of security held for risk communication is not returned until it has been carried out. It will also inform any future disagreements about the percentage of direct costs that should be held for engagement and regulatory compliance. | Brodie | This should be added to User Manual
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Diavik Diamond Mines (2012) Inc. - Sean Sinclair
1 | General | DDMI appreciates the opportunity to take part in this important review process. Since receiving preliminary feedback at the January 23rd, 2025 engagement session, DDMI understands that on February 18th, 2025 and on March 11th, 2025 the RECLAIM v8.0 team uploaded additional information to explain the rationale for some proposed changes to the model. DDMI has not yet been able to review all posted materials. DDMI also understands the RECLAIM v8.0 team will be providing further additional information including but not limited to a jurisdictional scan to support this review process. This complete set of information will inform ongoing collaborative discussion on this proposed update. | Given the complexity and importance of this review process DDMI recommends that the review timeline allows for thorough review and analysis of all information. DDMI is pleased to see the initial extended engagement process proposed by CIRNAC and GNWT and DDMI recommends the next steps for the RECLAIM v8.0 review process are discussed in detail and agreed at the GNWT and CIRNAC in-person workshop the week of May 14th, 2025. | GNWT/CIRNAC
2 | General | An initial review of the proposed changes to the RECLAIM model suggest that its application could have a very significant increase on securities. Current proposed changes are focussed on: 1) increased unit rates, 2) increased indirect costs, 3) increased owners costs, 4) increases regulatory costs, 5) increased mobilization and ICM costs, and 6) a future value calculation without corresponding discounting. | DDMI recommends this review process also consider changes focussed on: 1) incentivizing progressive reclamation, 2) managing the return of security process, 3) managing the security holdback process, 4) consideration of financial mechanisms to provide security as a function of both the liability and asset value, and 5) risk associated with a proponents commitment to orderly closure of the site including its financial and technical capacity to carry it out. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
A Member of the Public - Todd Slack
1 | Model Utility - One Long Comment, Pt. 1 | Obviously an updated reclaim model is in the interests of all parties. Recent years have seen significant increases in costs and an adjustment to better reflect this is a valuable effort to protect taxpayers and ensure that the polluter pays principle is effectively applied.
However, the operational modifications of the model are not the only step needed to ensure our territory is protected. A higher-level review focusing on the overall effectiveness of the bonding system should be undertaken using real world closure examples to test the predictive utility of the RECLAIM approach. No model is perfect and the review should be asking if this model meaningfully serves the polluter pays principle.
Ground-truthing with real world examples is essential. For example, the MVLWB held approximately $70M in security for Snap Lake (it isn't particularly easy to know exactly what the security amount was). According to public reporting, as of 2023 De Beers had spent $135M. In that case, it seems that NWT taxpayers - with a government already seeking financial relief - were considerably exposed. Should this be an indicator of a larger trend, the risk is even larger as it seems a widely held belief that industry, already mobilized and familiar with their site, can complete a closure in a more cost effective manner. Yet, the final cost for this site, with a modern security bond, will be more than twice what was held. | Starting with the NWT, publish real world examples of closed sites versus the reclaim estimates | GNWT/CIRNAC
2 | Model Utility - Pt. 2 | Other real world examples available to test the utility of RECLAIM estimates can be found in ongoing Strategic Oil abandonment and closure as well as the 2014 Snowfield property. Based on anecdotal information (as accounts have not been published, despite the expenditure of public monies), for the former, the GNWT has paid tens of millions for the reclamation, while the in the latter, the GNWT paid far in excess of the security held (nevermind the six-figure pre-existing debts that the company owed GNWT).
Examples from Nunavut can be researched as well, extending back to Tahera/Jericho which was established with a modern regulatory regime and cost taxpayers more than the security that was held (as opposed to GIANT which is not appropriate as a test case). Yukon examples, over which there are a number of selections (Victoria, Wolverine, Minto) may provide further insight into the effective security estimates and bonding (considering the Yukon government has appropriated $100M for early stages of the Victoria mine they've inherited, which was permitted in a modern system).
To summarize, before undertaking minor adjustments to the mechanics of the model, the overall utility needs to be verified, confirming fit for purpose. Notwithstanding the financial limitations of GNWT means that they lack the robustness to absorb and large mine failures (noting the daily cost cutting measures that are occurring), more importantly, the citizens of the NWT should have confidence that those overseeing the accessing and sale of our public resources are ensuring that the closure is paid for and completed by those exploiting the resource. | 1) Undertake analysis that looks at closure estimates versus the security held for sites across the NWT, Nunavut, and the Yukon.
2) Search for similar examples in Southern Canada were the structures ensuring the protection of taxpayers and governments are similar to those employed in the north. | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Qikiqtani Inuit Association - Conor Goddard
1 | Updated Unit Rates | Understanding unit rates are based on first principles; however further detail on unit rate development and assumptions is required. For Example. Load and haul costs have been split into 'short haul' and 'long haul'; however, there is no detail on what haul distance constitutes a short vs. long haul. To provide greater accuracy in haulage costs, specific unit rates should be calculated based on the actual haul distance between stockpiles and the facility being reclaimed. Dozer equipment rates are classified as either 'small' or 'large' scale equipment; however, no detail is provided on what is classified as a large dozer. This results in greater uncertainty in which equipment rate should be used when calculating equipment costs. | Paraphrased:
Provide additional details on how unit rates were derived. | AtkinsRéalis | Additional details were provided in the follow up memorandum. Short haul and long haul are defined in Table 2: RECLAIM v 8.0 Price Sources, Basis and References. This could be defined in the user manual but a decision was made to keep the details out of the text portion of the manual for ease of future updates. These unit rates could be used as a starting point but should be refined based on actual mine closure and reclamation plans and site conditions.
Dozer unit rates were escalated from RECLAIM 7.0. It was assumed large dozers would be utilized given the scale of work. The cost per cubic meter depends on several factors including fuel costs, labour, maintenance and efficiency. On average large dozers (D10/D11 Class) range in price from 1.50 to 3.50 per cubic meter. However, in remote Arctic operations the costs can be 20 to 50% higher. The range for dozing in RECLAIM 8.0 is $1.52/m3 to $6.08/m3
2 | Increased Indirect Percentages | An alternate methodology for calculating indirect costs should be provided. For example, engineering design could be estimated to be 8% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outlined in the reclamation and closure plan. This would allow engineering costs to depend on the level of project definition and the work to be completed. This incentivises further project definition within closure designs earlier in the life of project. | An alternate methodology for calculating indirect costs should be provided. | AtkinsRéalis
3 | Mobilization and Interim Care and Maintenance as Capital Costs | Mobilization / demobilization of equipment is typically considered as an indirect cost when it is being calculated as a percentage of direct costs. As RECLAIM calculates mobilization /
demobilization costs directly, Okane supports its inclusion as a direct cost such that contingency can be applied. If mobilization / demobilization costs change to being calculated based on
percentage, Okane does not support it being included as a direct cost. | Okane recommends mobilization / demobilization to be calculated via percentage of direct costs, similar to other Canadian jurisdictions. The quantity of equipment, and therefore the cost to mobilization / demobilization equipment, is tied to the reclamation timeframe and schedule. In the event of sudden closure, CIRNAC may implement closure activities on an alternate timeframe than what is outlined within the closure plan. | AtkinsRéalis & Brodie
4 | Owners Representative | Okane supports the costing of an Owners Representative within closure cost estimates. However, Okane is interested in the percentage used for determining this cost. In comparison, the updated project management cost of the entire reclamation phase is estimated to be 10% and includes costs for project coordination, accounting and project control, quality assurance/quality control and oversight, change orders and as-built reports. Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | Is the level of effort of the Owners Representative comparable to the full project management for reclamation? | AtkinsRéalis
5 | HHERA and Finalize CRP | An alternate methodology for calculating HHERA and CRP costs should be provided. For example, finalizing the CRP could be estimated to be 4% of direct costs, or based on a cost estimate provided by an engineering firm to complete the activities outline in the reclamation and closure plan. This would allow the costs for finalizing the CRP depending on the level of project definition and the work to be completed. | An alternate methodology for calculating HHERA and CRP costs should be provided. | AtkinsRéalis & Brodie
6 | Future Value Calculation | Okane supports the consideration of future valuation with respect to years associated with ICM; however, does not agree on how it is being represented within RECLAIM with respect to post closure activities and the removal of net present value calculations as outlined in the virtual engagement session. While inflation can add considerable costs to reclamation, solely
accounting for inflation does not capture the true costs and value of money. | Okane would recommend included inflation within a real discount rate to be used within a net present value analysis | AtkinsRéalis
7 | Detail for Unit Rates | Although RECLAIM provides a list of potential closure activities for each facility, it lacks the level of detail required to understand how these activities have been costed and relies strictly on unit
rates and lump sum estimates.
To improve transparency and accuracy withing closure cost estimates, more inputs should be provided to show how that activity is being costed. Specifically,
within post-closure activities such as monitoring the current RECLAIM model only provides an annual lump sum input for a monitoring activity. To improve transparency, it should provide more detail such as sampling/monitoring frequencies, number of sampling locations, analytic costs, reporting, etc. | AtkinsRéalis
8 | Post-closure monitoring and maintenance contingency | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. Post-closure maintenance activities are not excluded from having uncertainty and a contingency should be applied within this cost category. Specifically, activities such as long-term water treatment which is tied closely to geochemistry which typically carries large uncertainty. | Okane recommend that a contingency be applied to post-closure monitoring and maintenance activities. | GNWT/CIRNAC
9 | Timeframe and Post-Closure Activities | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. There is potential for post-closure monitoring and maintenance activities to extend into perpetuity, such as DSIs, DSRs, and water treatment. What is the expected period of which these activities should be assessed over. | Additional guidance is required within the revised RECLAIM model on the timeframe to be considered within the cost model associated with activities extending into perpetuity. | GNWT/CIRNAC
10 | Discount Rates | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. Okane would welcome guidance on what 'real'
discount rate should be applied to post-closure activities. | Further guidance should be provided within the revised RECLAIM model for discount rates to be applied within net present value calculations. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Baffinland Iron Mines Corporation - Lou Kamermans
1 | Procedural Fairness | Due to the short timeline to review the proposed changes, Baffinland has not had a full opportunity to conduct an in-depth review of the technical information supporting the RECLAIM 8.0 update. Respectfully, the timeline that was provided to industry for this initial round of comments is not adequate given the importance of RECLAIM to the Nunavut mining industry and the very serious potential impacts that have already been identified through the minimal consultation that has occurred to date. We are concerned that RECLAIM 8.0 could be advanced further despite these procedural deficiencies and the serious concerns expressed by industry to date. Given the significance of these changes to the mining industry in Nunavut and the Northwest Territories, and the potential direct impacts that it will have on Baffinland, we are providing initial high-level comments and recommendations below. In providing these comments, we reserve the right to provide further and more detailed comments, following further industry engagement and once better information is shared by CIRNAC and GNWT.
A. CIRNAC should engage stakeholders and Inuit organizations in a meaningful consultation process before finalizing the changes. Respectfully, the process described in the letter to the Chamber of March 18, 2025 does not achieve this standard.
B. Third public review and comment period should only occur after CIRNAC has produced a version of RECLAIM 8.0 revised based on comments. A further workshop may be necessary to review this revised RECLAIM 8.0 before any final comment period.
C. The overall timelines suggested in the process letter of March 18 are inadequate. For example, with respect to the suggested expected date of implementation of RECLAIM 8.0 [August 1, 2025], it is apparent that there would be no meaningful opportunity for feedback provided during the third round of public feedback (due July 16, 2025).
D. CIRNAC should advise how they intend to engage with NTI and RIOs on impacts to their rights resulting from this policy change, with associated timelines, before RECLAIM 8.0 is adopted.
E. CIRNAC should advise how they intend to engage with GN resulting on impacts relating to devolution resulting from this policy change (including spinoff economic effects), with associated timelines, before RECLAIM 8.0 is adopted.
| GNWT/CIRNAC | A-E: CIRNAC and GNWT to discuss.
2 | Economic impact of RECLAIM 8.0 | As Canada is trying to promote economic development and critical minerals development, which includes high grade iron ore, the additional security concepts and requirements proposed by CIRNAC in RECLAIM 8.0 will only make it harder to develop and maintain what we have. The changes proposed by CIRNAC will negatively impact mine financing and development by increasing security requirements and financial obligations without an adequate and corresponding industry consultation process. Any potential lack of engagement with industry and designated Inuit organizations undermines the legitimacy of these updates as a policy framework. Furthermore, as highlighted above, the RECLAIM 8.0 approach appears to disincentive projects with longer lifespans and greater water liability marks, which is in direct opposition to existing territorial and federal economic development policies and mandates. Without proper consultation, these changes will create uncertainty and deter investment in northern mining projects. Baffinland recommends that a comprehensive economic impact analysis be conducted to assess the implications of RECLAIM 8.0 on northern mining investment and development. Given the closure of major diamond mines in the North-West Territories and the absence of advanced stage projects in both the North-West Territories and Nunavut, apart from government funded infrastructure, the economic consequences of these changes should be thoroughly evaluated before implementation. An industry-commissioned economist could provide valuable insight into these potential impacts, and the results should be available before major policy decisions are finalized.
A. CIRNAC should conduct a comprehensive economic impact analysis to assess how RECLAIM 8.0 will affect mining investment and development in Nunavut. Industry and other stakeholders should be engaged on this question specifically as part of this analysis.
B. As part of this analysis, CIRNAC should produce a third party expert prepared report on the potential economic impact of the proposed cost escalations on the mining industry in Nunavut. RECLAIM 8.0 has been provided without assessment of the negative economic impacts that could result from the significant policy change RECLAIM 8.0 represents. The independent economist selected for this task should have experience representing industry and have Northern expertise. | GNWT/CIRNAC | A: Agreed - third part economist could provide valuable insight as to the economic implication for mineral development in the NWT and Nunavut.
B: As above.
3 | Rates and Cost Estimates
The proposed updates to RECLAIM 8.0 introduce significant cost increases that could have long-term economic implications for mining projects in the North. These cost escalations require careful scrutiny to ensure they align with real-world reclamation expenditures and do not hinder responsible resource development.
A. Review and adjust cost estimates to ensure they are reasonable, justified, and do not include duplication in indirect costs.
B. Develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. | AtkinsRéalis & Brodie | A: There was every attempt to ensure costs were reasonable, justified and did not include duplication. We will review the rates again to ensure they meet these criteria.
B: We do not suggest that CIRNAC develop specific guidance for reviewers and users of Reclaim 8.0 regarding appropriate selection of indirects and unit rates given project stage and lifecycle. It should be clear in RECLAIM User Manual as to why the default percentages are chosen and the mining company should propose the appropriate rate for their own mines and current stage within the lifecycle.
4 | Rates and Cost Estimates
The unit rates proposed for RECLAIM 8.0 are substantially higher than those in RECLAIM 7.0, often reflecting worst-case scenarios without adequate justification, despite the additional materials provided following the January Workshop in Vancouver. While CIRNAC states that proponents may propose alternative rates, industry experience suggests that the highest rates are typically applied in practice, unless a clear security policy is in place (see Section 3 - Security Policy).
First principles derivations for these rates has not been provided (as is typical when justifying modifying rates in a security estimate) and the references are highly generalized, which hinders review, especially in light of the limited review timeline.
C. CIRNAC and GNWT must provide more detailed first principles derivations for rates, at a level that would be expected of a proponent justifying its own rates in an estimate. Specific references are required and generalized references provided to date are not adequate to provide expert feedback and advice.
| AtkinsRéalis | C: CIRNAC provided links and references to the majority of the sources for increased rates applicable to remote mine working in NWT and Nunavut. CIRNAC used First Principles to develop rates for soil and rock movement and provided the factors considered in the costs estimating tool. Its is up to the mining company to counter these rates and provide rationale as why a different unit rates should be proposed (high or lower).
5 | Rates and Cost Estimates
The increase in indirect percentages represents an overall 23% increase in costs, and several of these items overlap, resulting in duplication of costs (see Table 1). For example the increase in contingency seems to be duplicated by an increase in project management, engagement and regulatory compliance, and owner's representative costs. These increases do not appear to be justified through a detailed cost analysis.
D. Justification must be provided by CIRNAC to address the duplication described in the comment, and a detailed cost analysis must be provided to justify these statements
| AtkinsRéalis | D: AR to investigate
6 | Rates and Cost Estimates
| Upon initial review, the observations regarding indirect costs provided in the "Review of Mine Financial Security Estimates and RECLAIM" (Brodie, 2020) do not align with the proposed Reclaim 8.0 Indirect costing changes. For example, the report states "BCL recommends that the default percentage for Project Management be increased based upon CIRNAC's experience. Whereas the default percentage for Engineering should be maintained but with the RECLAIM User Manual revised to be even more explicit as to what is and is not assumed to be covered in this amount.: Baffinland notes that the proposed Reclaim 8.0 changes include an increase in project management indirect percentages (an increase from 5% to 8%), an additional owners engineer indirect (an increase of 8%) and an increase in engineering design indirects (5% to 8%). This appears to be in contradiction to the recommendations of the review report. | E. CIRNAC should align observations re indirect costs in RECLAIM 8.0 with Brodie, 2020 (subject to adjustment based on further submissions in future on each of these categories)
| AtkinsRéalis & Brodie | E: Default increases in percentage of indirects were increased from the Brody recommendations based on consultation with our consultants cost estimators and based on incurred cost at other orphaned and abandoned mine across Canada.
7 | Rates and Cost Estimates
Within the proposed update, contingency has been increased to a maximum of 25%, which the Reclaim review report (Brodie, 2020) describes as appropriate for "Very basic engineering only and costs based upon typical unit costs". This guidance is not provided in the proposed RECLAIM 8.0 documentation. As Baffinland has noted above, in its experience when Reclaim is applied by reviewers the highest level of contingency/indirect is used as a manner of course, as there is little specific guidance provided how to select an appropriate contingency/indirect within the provided model.
For example, although Baffinland's closure plan has advanced to the ICRP stage and has had significant engineering completed, a 20% contingency has been consistently applied by CIRNAC reviewers.
Without specific risk based guidance regarding how to select indirect percentages based on project stage and level of engineering completed, Reclaim 8.0 could be used in an overconservative manner due to the lack of specific guidance, which could have a significant impact on Baffinland and other resource development projects in Nunavut.
| F. 25% is not an appropriate contingency percentage for most advanced projects with current RECLAIM 8.0 guidance there is a risk this value is applied broadly, like 20% contingency is now. Adjust contingency percentage to reflect a range of risk based standards adjustable based on criteria, such as reductions below 20% where projects already have significant completion of engineering | AtkinsRéalis | F: CIRNAC could develop a matrix to define, for example
Mine Life Stage | Contingency Level | Rationale
Exploration | 25-40% | High uncertainty due to lack of detailed closure planning; site conditions may change significantly.
Development and Construction | 20-35% | Costs can be escalated due to unforeseen geotechnical or environmental conditions; reclamation planning is still ongoing (draft CRP)
Active Operations | 15-25% | Some reclamation activities may be already underway but long-term treatment and closure plans as still being developed (ICRP) and unforeseen liabilities remain.
Late-Stage Operations (approaching closure) | 10-20% | More certainty in closure costs but risks like water treatment or tailings stability may pose cost overruns
Closure and Reclamation | 10-15% | Final closure costs are better defined however post closure risks remain (i.e., monitoring and maintenance, unforeseen environmental impacts, climate change, etc. persist)
Post Closure Monitoring | 5-10% | Residual risks remain, particularly for water treatment and long term geotechnical and chemical stability but overall cost uncertainty is lower.
8 | Rates and Cost Estimates
The future value calculation for water treatment and other long-term liabilities places a significant financial burden on mining companies, particularly in the absence of strong offsetting mechanisms, such as security discounting based on known reserves-an approach used in other jurisdictions like British Columbia (BC) and Quebec (Government of BC, 2022; Government of Quebec, 2017).
For instance, in 2022, the BC Ministry of Energy, Mines and Low Carbon Innovation introduced the Major Mines Reclamation Security Policy, which considers a mine's stage of development and promotes long-term operations by applying different security rates at various points in a mine's lifespan based on default risk. The policy states that "mines that have been operating for more than five years, and that have economically viable reserves for at least the next ten years at the permitted production rate, will be eligible to secure up to 25% of the reclamation liability against a portion of the reserve value." (Government of BC, 2022).
Adopting a similar approach in Nunavut provide much-needed financial flexibility for long-term mining projects like Baffinland, reducing upfront security costs while maintaining strong environmental protection measures. This would enhance the economic viability of long-life mines, encourage continued investment, and support sustainable resource development in the region.
Tying financial security to the mine life cycle would help mining companies spread out financial security payments over the mine's life, which would increase investor confidence while supporting responsible mining development that considers the projected mine life.
G.RECLAIM 8.0 should be revised to provide a clear mechanism for discounting security based on reserves, similar to those adopted in other jurisdictions such as BC and Quebec.
| GNWT/CIRNAC | The BC "interim" policy is based on years of operations and mineral reserves. Proven final securities through the Exploration Incentive. Shifting security to mineral reserves could be an issue as Canada is not in the mining business and if a site were abandoned, they would need to reopen a mine to get access to the money required to close it. The BC policy mentions that mines with proven reserves are attractive to other operators if a mine were to go bankrupt. STILL SEEMS RISKY TO ME, TULSEQUAH, MINTO, ETC.
This policy seeks to ensure that permittees for major mines pay the full cost of environmental cleanup and reclamation for their mine. New mines and any existing mines (whether in operation, in care & maintenance or closed) having less than five years of remaining mineral reserves will be required to post full reclamation security equal to the company's reclamation liability on the mine site. A partial exploration incentive security will be available to mines that have invested in sufficient exploration to demonstrate at least five years of remaining reserves. The policy seeks to ensure that new mines are fully bonded moving forward and seeks to reduce the differential between reclamation liabilities and reclamation securities for existing mines.
0 to 5 years: (100% posted cash security)
> 5 years: (75% posted cash security and 25% against the mineral reserves)
> 5 years but less than 10 years (85% posted cash security and 15% against the mineral reserves)
No more than 10% of the value of the reserve used reclamation security
Discount rate of 8% applied to the mineral reserves
Default contingency set to 15% but higher may be required depending on the level of risk or uncertainty. Lower may be proposed by the permittee
9 | Update of 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) is required.
Before publishing a RECLAIM 8.0 model, Baffinland recommends that the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) be revised to reflect current conditions in the mining industry.
There has been no suggestion that current Nunavut production mines are undersecured - as an example, Baffinland's security is reviewed annually in a comprehensive process. The investment decision for Mary River was made on the suite of government and Inuit approvals in place, including RECLAIM 7.0. | A. Before RECLAIM 8.0 is adopted for Nunavut projects, the 2002 Mine Site Reclamation Policy for Nunavut (CIRNAC, 2002) should be updated to reflect current conditions in the mining industry and best practices across Canada and globally.
B. Current approved Nunavut projects should follow RECLAIM 7.0, unless the proponent consents to application of RECLAIM 8.0. | GNWT/CIRNAC | A: TBD
B: Current mine securities are set. At the time of renewal, RECLAIM v 8.0 will be in place and new indirects and calculations of contingencies and future costs will be negotiated.
10 | Misc. | No Comment | A. Only a simple markup of the updates to the User Manual has been provided. A detailed markup is requested as a simple markup does not clearly present the changes.
Brodie
11 | Misc. | No Comment | B. With reference to the "proprietary civil rate tool" referenced at p. 20 of the User Manual for RECLAIM 8.0, if a tool is being adopted in a government policy, it must be made publicly available. If it is not publicly available, it should not be included in the policy. This is a matter of fairness and transparency.
| AtkinsRéalis | B: AtkinsRéalis suggests removal "proprietary" replace with "construction cost estimating"
12 | Misc. | No Comment | C. Costs relating to the Crown's legal obligation to consult (which would be incurred in any event, whether the Crown steps in as director of reclamation or participates in review of closure plans led by a proponent) should not be included in RECLAIM 8.0, as this is a fixed government cost, not a cost of reclamation. The suggested 3% includes items that are fixed government obligations that do not belong in a reclamation estimate.
| GNWT/CIRNAC | C: The 3% Owners Costs are meant to capture expenses required to complete consultation during the ICM and Post Closure Phase that typically are budgeted for in day to day government spending (i.e., flights, vehicle rentals, accommodations, per diems to northern and remote communities to discuss the remediation, reclamation and closure plan. Costs of permitting and other third party costs related to government activities would be captured here.
13 | Misc. | No Comment | D. How is RECLAIM 8.0 accounting for Nunavut devolution relating to lands and waters from CIRNAC to the GN? | GNWT/CIRNAC | D: CIRNAC to elaborate.
14 | Misc. | No Comment | E. RECLAIM 8.0 should recognize reasonable salvage value where justified by the proponents estimate. The current position is unreasonably conservative and results in over bonding in many circumstances. This statement should be revised accordingly "GNWT/CIRNAC does not recognize salvage value because of the problems associated with creditors rights, sale of equipment and uncertainty as to the actual value at the time of insolvency".
| GNWT/CIRNAC | E: Revised text looks appropriate to AtkinsRéalis.
15 | Misc. | No Comment | F. Citation for precautionary principle definition should be to the CEPA not to the CEPA guide. | Brodie | F: Revision seems appropriate to AtkinsRéalis
16 | Misc. | No Comment | G. Progressive reclamation should be credited in mine reclamation costs. This aligns with the following statement from the 2002 Nunavut Reclamation Policy - "Mining operators should be credited for approved progressive reclamation, and the value of financial security required should be adjusted in a timely fashion" | GNWT/CIRNAC | G: CIRNAC recognizes this statement and has worked with mining companies to reduce securities based on progressive reclamation activities and will continue to do so on a case by case basis.
17 | Misc. | No Comment | H. RECLAIM 8.0 adds an additional owners representative indirect cost, which is in addition to the proposed project management indirect cost. The owners representative indirect has been insufficiently justifying in the provided accompanying documentation, and it should be noted that an owners representative is not required during proponent lead reclamation. This overly conservative indirect requirement could have significant implicants on mine financing and development.
| AtkinsRéalis | H: CIRNAC and GNWT would not lead the development and finalization of the Closure and Reclamation Plan, nor would they oversee the construction or monitoring and maintenance activities. It has been shown that this is not the case as seen at Faro and Giant mines. CIRNAC and GNWT would hire an engineering firm to provide Owners Representative services (technical resources to government) to manage and oversee another engineering firm (e.g. a design-build team) who would be contracted to complete the closure, reclamation and long term monitoring activities.
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
B2G Back River Corp. Nunavut - Merle Keefe
1 | Review Data Extension | B2Gold Nunavut is presently unable to meet the requested date for the submission of comments and therefore supports a recent request made by the NWT& Nunavut Chamber of Mines (Chamber) to extend the comment period deadline. B2Gold Nunavut also supports the request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM. The Chamber submission is attached to this letter. | Request for an additional workshop or working session to support this collaborative review of the proposed updates to RECLAIM | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
NWT & Nunavut, Chamber of Mines - Karen Costello
1 | Review Data Extension | The Chamber respectfully requests a 4-month review period (including potential options for a workshop) to fulfill the first step in the review process. We would also ask for access to the Review of Mine Financial Security Estimates dated March 2020 at your earliest convenience. | Four month date extension for review comments | GNWT/CIRNAC
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Agnico Eagle Mines Limited - Jamie Quesnel
1 | Review Data Extension | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0.
As was apparent at the January 23, 2025 Engagement and Feedback Session, and echoed again in the NWT & Nunavut Chamber of Mines letter, there were many uncertainties and risks identified by Industry, including time to complete a detailed and adequate review of all the proposed changes under RECLAIM 8.0. As outlined in Section 2 of this letter, Agnico Eagle has undertook an initial review and provided some comments and recommendations; however, a detailed fulsome review has not been executed at this stage. | Agnico Eagle supports the letter issued by the NWT & Nunavut Chamber of Mines1 which requested an extension to fulfill the review and provide comment on RECLAIM 8.0. | GNWT/CIRNAC
2 | Documents received | This is a preliminary review due to the short timeline
| More time is required to complete a comprehensive review of the documentation provided | GNWT/CIRNAC
3 | Reclamation Policy | As the reason is unknown why the Reclaim V8 was changed, plus we have an undefined process we are following, and this creates uncerntainity. | Develop a plocy update with a defined process of consulation, etc., and define the triggers for a material change. | GNWT/CIRNAC
4 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered" and "'Work week for earthwork (rock, soil, riprap excavation, hauling to waste dump is 7 days a week x 10 hours per day = 70 hours per week"
The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No overnight work is considered.
Unit rates should be developed assuming 24 hour operation where practical. SUPPORTING RATIONALE: Operating Mines, particularly in the North, require round the clock operation for maximum equipment utilization and operation effectiveness. Haul trucks engines must be active around the clock to ensure operability and neglecting night shift utilization ignores real operating expenditures.
AtkinsRéalis
5 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'Only a day shift is considered"
The example breakout of unit rate development, expanded on by FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) indicates that only 10 hours per day, on day shift, is used for unit rate development. No night work is considered.
Operating Mines, particularly in the North require round the clock operation for maximum equipment utilization and operation effectiveness. SUPPORTING RATIONALE: Neglecting potential night shift work unnecessarily extends project schedule and therefore unnecessarily inflates overall project costs.
AtkinsRéalis
6 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "'The labour cost included in the unit rates considered the following cost: … - Indirect labour"
The battery limits for "indirect labour" included in unit rate development is not adequately defined. RECLAIM includes indirect activities such as Project Management and Engineering Design applied as a general percentage of direct costs.
Clarify what indirect labour is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses.
AtkinsRéalis
7 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "The labour cost included in the unit rates considered the following cost: … - Site supervision and administration"
The labour cost included in the unit rates considered the following cost: Site supervision and administration
Clarify what site supervision and administration is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.). SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses. Project management, Health and Safety Monitoring & QC as an indirect cost is applied as a blanket % to all costs.
AtkinsRéalis
8 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 3 Unit Rate Development LINE: "Exclusion ...- Project indirect cost" | The battery limits for "indirect cost" included in unit rate development is not adequately defined.
Clarify what indirect cost is included in the calculated unit rates based on the data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) SUPPORTING RATIONALE: Consistent application of included cost is important to avoid applying blanket percentage based indirect cost to already existing indirect expenses.
AtkinsRéalis
9 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 5 Exclusions LINE: "- First Fills" | First fills are excluded from unit cost build up.
| Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup that excludes first fills. SUPPORTING RATIONALE: Consistent application inclusions and exclusions are important for usability of RECLAIM. Suggest using one data source for all unit rate buildup. | AtkinsRéalis
10 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- Freight for the bulk materials such as granular, concrete and HDPE pipes are included with the unit rates"
Proposed unit rate buildup includes freight for bulk materials. This necessitates site specific unit rate for all bulk materials as freight costs can very substantially between sites. There is already a section within the RECALIM mobilization tab to capture freight cost.
Bulk material default unit rates should exclude freight. Freight for materials should be included separately based on a site specific unit cost for material mobilization, captured in the RECLAIM Mobilization tab.
AtkinsRéalis
11 | FILE: (RECLAIM 8 Reference Tables_Working Copy.xlsx) TAB: Table 1 SECTION: 4 Clarifications and Qualifications LINE: "- It is assumed there is no batch plant required. All concrete will be delivered to site to use" | The clarification that no batch plant will be required constricts operational planning. In some cases it is more cost effective to commission a batch plant and ship bulk concrete than to use premix product.
Freight of premix concrete products is not always practical for northern projects based on mobilization constraints and the use of a batch plant should be considered when operationally and financially advantageous.
AtkinsRéalis
12 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects LINE: Mobilization/Demobilization 6.0% | Contractor indirects, specifically mobilization/demobilization, are shown as separate adders to the base rates for equipment and labour direct costs. RECLAIM considers mobilization and demobilization costs separately from operating unit rates as part of the Mobilization tab.
| Exclude mobilization/demobilization cost from unit rate development. Clarify which data source (i.e. BC Blue Book, Alberta Equipment Rental Rates Guide, etc.) is being used for each buildup and if mobilization/demobilization cost has been accounted for with respect to the overall RECLAIM workbook. | AtkinsRéalis
13 | FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects
| A variety of sources for equipment operating costs as well as labour costs are indicated as being used as a basis for unit rate calculations. There are substantial differences in the factors included in each of the sources for equipment operating costs. For example, BC Blue Book and Alberta Equipment Rental Rates Guide are used interchangeably in FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Rates but BC Blue Book equipment operating rates do not explicitly include contractor overhead and profit whereas Alberta Equipment Rental Rates Guide does. The provided unit rate example in FILE: (Attachment A to the Supplementary info provided Feb 18 2025.pdf) SECTION: contractor indirects, if using Alberta Equipment Rental Rates Guide for equipment or manpower hourly rates is applying an additional 12.50% Mark-up & Profit on a rate that already includes Mark-up & Profit. | Default unit rates provided in RECLAIM 8 should use a consistent source reference for all equipment and manpower hourly rates with clearly defined buildup of direct and indirect components.
AtkinsRéalis
14 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Buildings - Remove" COST CODE: BRW, BRC, BRS1, BRS2
Cost Codes: BRW, BRC, BRS1, BRS2 have no default HIGH unit rate provided as part of RECLAIM 8.0 example. RECLAIM 7.0 provided a HIGH unit rate for these cost codes resulting in a 1:1 comparison between RECLAIM 8.0 default unit costs and RECLAIM 7.0 unit costs.
| RECLAIM 8.0 should include a default HIGH unit rate for all default cost codes that have a defined HIGH unit rate in RECLAIM 7.0 | AtkinsRéalis
15 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB1, RB2 | The detail defining what activity COST CODES RB1 and RB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines RB1 as "drill/blast/load/short haul" RECLAIM 8.0 defines RB1 as "load/haul/place"RECLAIM 7.0 defines RB2 as "drill/blast/load/long haul" RECLAIM 8.0 defines RB2 as "RB1 + spread and compact"This respondent uses COST CODE RB2 to represent activities requiring "drill/blast/load/long haul" but NOT "spread and compact" To accommodate the change in COST CODE detail from RECLAIM 7.0 to RECLAIM 8.0 >$10 million of activities on a single site would need to be recoded to avoid implying "spread and compact" is required for these activities.
Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
16 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - Low Spec (e.g. Stockpile Source, Bulk Fill)" COST CODE: RB3, RB4 | COST CODE: RB3 and RB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RB3 DETAIL: "RB1 + spread and compact" is the same as RECLAIM 8.0 CODE RB2 DETAIL: "RB1 + spread and compact"RECLAIM 7.0 COST CODE RB4 DETAIL: "RB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RB3 and RB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities.
Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
17 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Rock - High Spec (i.e. Rip Rap, Screened)" COST CODE: RC3, RC4
| COST CODE: RC3 and RC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE RC3 DETAIL: "RC1 + spread and compact" is the same as RECLAIM 8.0 CODE RC2 DETAIL: "RC1 + spread and compact"RECLAIM 7.0 COST CODE RC4 DETAIL: "RC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes RC3 and RC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
18 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB1, SB2 | The detail defining what activity COST CODES SB1 and SB2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SB1 as "excavate/load/short haul" RECLAIM 8.0 defines SB1 as "excavate/load/haul/place"RECLAIM 7.0 defines SB2 as "excavate/load/long haul" RECLAIM 8.0 defines SB2 as "SB1 + spread and compact"This respondent uses COST CODE SB2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact"
Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
19 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - Low Spec (i.e. bulk fill and excavation)" COST CODE: SB3, SB4
| COST CODE: SB3 and SB4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SB3 DETAIL: "SB1 + spread and compact" is the same as RECLAIM 8.0 CODE SB2 DETAIL: "SB1 + spread and compact"RECLAIM 7.0 COST CODE SB4 DETAIL: "SB2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SB3 and SB4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. This respondent would need to recode >$35 million of activities at one site. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
20 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC1, SC2 | The detail defining what activity COST CODES SC1 and SC2, refers to has been changed in RECLAIM 8.0 from RECLAIM 7.0.RECLAIM 7.0 defines SC1 as "excavate/load/short haul" RECLAIM 8.0 defines SC1 as "excavate/load/haul/place"RECLAIM 7.0 defines SC2 as "excavate/load/long haul" RECLAIM 8.0 defines SC2 as "SC1 + spread and compact"This respondent uses COST CODE SC2 to represent activities requiring "excavate/load/long haul" but NOT "spread and compact" | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
21 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Excavate Soil - High Spec (i.e. Engineered Covers, Spillway Clearing, etc.)" COST CODE: SC3, SC4
| COST CODE: SC3 and SC4 have been removed from RECLAIM 8.0RECLAIM 7.0 COST CODE SC3 DETAIL: "SC1 + spread and compact" is the same as RECLAIM 8.0 CODE SC2 DETAIL: "SC1 + spread and compact"RECLAIM 7.0 COST CODE SC4 DETAIL: "SC2 + spread and compact" has no equivalent in RECLAIM 8.0Where cost codes SC3 and SC4 are used in existing RECLAIM 7.0 a port of activities to RECLAIM 8.0 will result in an REF# error necessitating a custom unit rate to restore the value of previously evaluated activities. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or modified.
AtkinsRéalis
22 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, small (<6in dia.)" COST CODE: PSS, PSI
COST CODES: PSS and PSI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained.
Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified.
RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes.
AtkinsRéalis
23 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pipes, large (>6in dia.)" COST CODE: PPLR, PLS, PLI
COST CODES: PLR, PLS and PLI have been removed from RECLAIM 8.0 and have been replaced more precisely defined pipe sizes. For projects with established closure designs the new cost codes will allow for increased costing precision and where applicable existing projects should update their RECLAIM accordingly. The RECLAIM 7.0 cost codes are still applicable to projects without established closure designs and should be retained.
Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified.
RECOMMEND retain cost codes for RECLAIM 7.0 pipe size categories <6in dia. and preserve additional defined pipe size cost codes
AtkinsRéalis
24 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: PS | Pumps, Pump shipping COST CODE: PS unit changed from RECLAIM 7.0 lump sum (each) to, RECLAIM 8.0 percentage (%) of pump cost.Existing RECLAIM 7.0 projects have taken to account shipping of pumps, by lump sum (each) as part of the mobilization calculation. Shipping cost is generally site specific and existing calculations should remain valid. Shipping cost as a % of pump capital cost could be a useful default unit rate for establishing projects. | Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified.
RECOMMEND adding new cost code for shipping as a % of capital cost
AtkinsRéalis
25 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Unit_Costs ITEM: "Pumps" COST CODE: POC | Pumps, Pump operating cost COST CODE: POC unit changed from RECLAIM 7.0 m3 (volume pumped) to, RECLAIM 8.0 kw-h (power cost).Pump operating cost is certainly predicated on site power cost but the relationship between pumped volume and power draw is based on site specific conditions. Volume of water is the unit of measure for reclamation activities and using a second unit of measure to determine cost would introduce additional complexity.
| Follow consistent database practice: cost code details and units should not change. New cost codes should be used for new activities. Existing cost codes should not be removed or have details modified. RECOMMEND pump operation based on cost per volume pumped. | AtkinsRéalis
26 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Human Health and Ecological Risk Assessment (% Closure Costs) | Human Health and Ecological Risk Assessment (% Closure Costs): Cost to develop a site specific HHERA is warranted and should consider work already completed to capture the real effort and cost to achieve closure.
Implement a sliding scale for HHERA related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
27 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: ICM ITEM: Finalize Closure and Reclamation Plan (% Closure Costs) | Finalize Closure and Reclamation Plan (% Closure Costs): Cost to develop Final Closure and Reclamation plan is warranted and should consider work already completed to capture the real effort and cost to achieve closure.
Implement a sliding scale for Finalize Closure and Reclamation Plan related costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
28 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engineering Design | Indirect Costs: Engineering Design : Cost for engineering design is warranted and should consider work already completed to capture the real effort and cost to achieve closure
Implement a sliding scale for Engineering Design Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
29 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Project Management
Indirect Costs: Project Management : Cost for project management is warranted and should consider work already completed to capture the real effort and cost to achieve closure.
Implement a sliding scale for Project Management Indirect Costs similar to the already existing table for contingency cost based on project maturity, and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
30 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Health and Safety Plans/Monitoring & QC
Indirect Costs: Health and Safety Plans/Monitoring & QC : Cost for Health and Safety Plans/Monitoring & QC is warranted and should consider work already completed to capture the real effort and cost to achieve closure.
Implement a sliding scale to account for project maturity and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
31 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Bonding / Insurance | Indirect Costs: Bonding / Insurance : Cost for Bonding and Insurance is warranted and should consider work already completed to capture the real effort and cost to achieve closure. This cost should also account for the reliability and ease of use of the financial assurance instrument used by the mine owner as well as the financial reliability of the mine owner, represented by third party credit rating. Typical operating project bonding and insurance costs for third parties are historically <1% total project cost.
Implement a sliding scale to account for owner reliability, project maturity, and the cost and effort required to achieve closure. Established mining companies at low risk of becoming insolvent should have their efforts to achieve closure recognized.
| GNWT/CIRNAC | For group discussion
32 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Engagement and Regulatory Compliance
Indirect Costs: engagement and regulatory compliance cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security.
Mine owners operating in good faith to service their closure obligations, including through regulatory compliance and engagement, should not be made to bear burden of costs outside their influence.
GNWT/CIRNAC
33 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Contingency | Indirect Costs: Contingency : Cost for contingency is warranted and should consider work already completed to capture the real effort and cost to achieve closure.
There is currently a sliding scale for contingency, codified in the RECALIM 7.0 user manual, but the benchmarks set out are not representative of the level of contingency requested by CIRNAC and recommended by Brodie Consulting. The RECLAIM 8.0 contingency scale, based on AACE International Recommended Practice No. 10S- 90 representative of current industry practice and can be augmented with other factors such as owner financial strength, path to closure, and financial instrument of security.
Contingency sliding scale should reflect project lifecycle maturity, the financial strength of the owner, the financial instrument of closure security and the cost and effort required to achieve closure.
| GNWT/CIRNAC | For group discussion
34 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Owners Representative
Indirect Costs: Owners representative cost is unwarranted and should not be borne by the mine owner. The addition of this indirect cost is inconsistent with the polluter pays principal that guides the development of closure security.
Mine owners operating in good faith to service their closure obligations should not be made to bear burden of costs outside their influence.
This line item addition represents a significant burden to all mining companies and it may impact the viability of future developments.
GNWT/CIRNAC
35 | FILE: (20250116_Reclaim_8.0_MineExample.xlsm) TAB: Summary ITEM: Site Specific Future Value Inputs
FILE: reclaim 8.0 User Manual_Working Copy.pdf affirms that the determination of future costs must include all parameters including the Net Present Value of those costs. The Site Specific Future Value Inputs projects a future cost without including for the future value of the security
| If RECLAIM is to project factors such as inflation it should also account for the present value of money at the time of projection. A prescribed NPV calculation with appropriate discount rate should be applied alongside all Post-Closure costs and future projections. | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Kivalliq Inuit Association - Luis Manzo
1 | General comment | The Kivalliq Inuit Association (KivIA), as the responsible DOI, through Security Management Agreement holds 50% of the financial security estimates for Meadowbank, Meliadine and Whale Tail mines Canada holds the other 50%. Therefore, any changes to the RECLAIM financial model must be reviewed and agreed by KivIA. | Paraphrased:
Table 1 provides the comments and recommendations from KivIA and are summarized in comments 2 to 20 below.
Table 2 provides operational costs for drill/blast/load/haul/spread/compact unit rates. Assumption is we should consider these rates.
Table 3 includes an example comparison of the increased costs based on the new percentages for indirects.
It is recommended that any changes to the RECLAIM financial model must be reviewed and agreed by KivIA
GNWT/CIRNAC
2 | General comment | The timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site needs to be explained. | The KivIA requests that CIRNAC explain the timeline and criteria for an advanced project or mine site changing from active to care & maintenance to a contaminated site. | GNWT/CIRNAC
3 | General comment | Project or mine's asset value to a company. Will CIRNAC consider the asset value of an advanced project or mine as part of the initial financial security. | The KivIA requests that CIRNAC explain if there would be consideration of the asset value of an advanced project or mine as part of the initial financial security. | GNWT/CIRNAC
4 | General comment | What is the procedure for the return of financial security to the proponent? | The KivIA requests that CIRNAC explain the procedure for returning financial security to the proponent. | GNWT/CIRNAC
5 | RECLAIM 8 Model Working Copy - Excel Sheet; Summary Tab - Summary of Costs (2024 Dollars) - Direct Costs | The changes made to the direct costs need to reflect each individual project/mine site. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that direct costs will need to be project specific versus "one cost fits all" with a range of costs being a more appropriate approach. | AtkinsRéalis
6 | RECLAIM 8 Reference Tables Working Copy - Excel Sheet - Table 2: RECLAIM v8.0 Price Sources, Basics and References -Excavation costs. | Excavation costs for load/haul/place for excavating and spreading rock and soil show significant increases from RECLAIM 7.0 to RECLAIM 8.0. Using known operating costs from a northern gold mine calculated in RECLAIM 7.0 and comparing these costs to the proposed rates in RECLAIM 8.0 the costs for load/haul/place for excavating and spreading rock and soil have increased by 50% to 430% (see Table 2 attached). In addition, the RECLAIM 7.0 costs included drill and blast which the RECLAIM 8.0 costs do not. However, without any detail provided on how the Civil Est. Tool calculates the RECLAIM 8.0 costs it is not possible to evaluate these cost differences. | The KivIA requests that CIRNAC and their engineering consultants provide the detail on how the Civil Est. Tool calculates the RECALIM 8.0 excavation costs. | AtkinsRéalis
7 | RECLAIM 8 Model Working Copy - Excel Sheet; Summary Tab - Summary of Costs (2024 Dollars) - Direct Costs | Will an inflation factor be used. Will this factor be applied to direct costs?
Or to Indirect costs? Will an inflation factor be used on the direct costs? Or indirect costs? Over what time period will the inflation facto be reviewed. | The KivIA requests that CIRNAC and their engineering consultants respond to their proposed plan for an inflation factor. | AtkinsRéalis
8 | RECLAIM 8 Model Working Copy - Excel Sheet; Summary Tab - Summary of Costs (2024 Dollars) - Indirect Costs | The changes made to the percentages used for Indirect Costs from RECLAIM 7.0 (31%) to RECLAIM 8.0 (58%). Using the $100M Direct Cost example in Table 2 the changes made to the percentages would result in an 87% increase to the InDirect Costs from $31M to $58M. | A cost increase of 87% is significant and will have a negative impact on the business model used to develop currently operating advanced projects and mines. In addition, a cost increase of this magnitude will have a negative impact on new investment "North of 60". The KivIA's comments on the recommended changes make up the remainer of this table (Table 1). | GNWT/CIRNAC
9 | RECLAIM 8.0 - User Manual - Indirect Costs - Engineering Design; Summary Report: Proposed Changes to RECLAIM Version 8.0 - Engineering Design | The percentage change made to the Engineering Design component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (8%). This should be a range from 5% to 8% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus "one cost fits all" with a range of percentages being a more appropriate approach. | AtkinsRéalis
10 | RECLAIM 8.0 - User Manual - Indirect Costs - Project Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 - Project Management | The percentage change made to the Project Management component of Indirect Costs from RECLAIM 7.0 (5%) to RECLAIM 8.0 (10%). This should be a range from 5% to 10% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus "one cost fits all" with a range of percentages being a more appropriate approach. | AtkinsRéalis
11 | RECLAIM 8.0 - User Manual - Indirect Costs - Engagement and Regulatory Compliance; Summary Report: Proposed Changes to RECLAIM Version 8.0 - Engagement and Regulatory Compliance | The Engagement and Regulatory Compliance component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (3%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide:
1)the rationale for separating these tasks out from the Project Management category.
2)the cost information that was used to determined that this new category would cost $3M per every $100M of financial security. | AtkinsRéalis
12 | RECLAIM 8.0 - User Manual - Indirect Costs - Contingency Management; Summary Report: Proposed Changes to RECLAIM Version 8.0 - Contingency | The percentage change made to the Contingency component of Indirect Costs from RECLAIM 7.0 (20%) to RECLAIM 8.0 (25%). This should be a range from 15% to 25% to be project specific instead of one cost fits all. | The KivIA requests that CIRNAC and their engineering consultants acknowledge that indirect costs will need to be project specific versus "one cost fits all" with a range of percentages being a more appropriate approach. | AtkinsRéalis
13 | RECLAIM 8.0 - User Manual - Indirect Costs - Owners Representative; Summary Report: Proposed Changes to RECLAIM Version 8.0 - Owners Representative | The Owners Representative component of Indirect Costs is a new addition from RECLAIM 7.0 (0%) to RECLAIM 8.0 (8%). The tasks listed under this new category are usually part of the project management tasks. | The KivIA requests that CIRNAC and their engineering consultants provide:
1)the rationale for separating these tasks out from the Project Management category.
2) the cost information that was used to determined that this new category would cost $8M per every $100M of financial security. | AtkinsRéalis
14 | RECLAIM 8.0 - User Manual - Future Value calculations: Summary Report: Proposed Changes to RECLAIM Version 8.0 - Future Value calculations | It states that the Future Value calculations will capture Closure and post-Closure activities and that a default inflation rate of 3% will be applied. Will there be an annual or a multi-year review of the inflation rate in order to adjust the financial security. | The KivIA requests that CIRNAC and their engineering consultants provide the timeline over which the inflation rate will be reviewed (ie. Annually review? Multi-year review?). | GNWT/CIRNAC
15 | RECLAIM 8 Reference Tables Working Copy - Excel Sheet; Table 1 - Basis of Unit Rates Development | It states that "The below references are used in unit rates development -
Published data sources". All the published data sources used are from southern Canada. Are there any "North of 60" data sources? Are there any permafrost related data sources? Also, are these labour and contractor rates union or non-union rates? | The KivIA requests that CIIRNAC and their engineering consultants provide:
1) northern data sources or explain why these cannot be provided.
2) Are the labour and contractor rates union or non-union rates. | AtkinsRéalis
16 | RECLAIM 8 Reference Tables Working Copy - Excel Sheet - Table 2: RECLAIM v8.0 Price Sources, Basics and References - column Price Base/References | In the column for price Base/References several price references are either Civil Est. Tool or Historical Database. For transparency and ensuring a proper evaluation of costs by all intervenor's full disclosure of all price references is necessary. | The KivIA requests that CIIRNAC and their engineering consultants provide:
1) the details of the Civil Est. Tool.
2) the Historical Database. | AtkinsRéalis
17 | RECLAIM 8 Model Working Copy - Excel Sheet; Instruction Tab - Conditions of Use | It states that "This model is not intended to dictate how much should be spent on reclamation." What is the purpose of this financial model if it is not supposed to dictate how much should be spent on reclamation by the proponent? Is it possible that if a proponent disagrees with CIRNAC's final dollar amount created by this model that the proponent could set their own financial security? | The KivIA requests that CIRNAC:
1) provide clarity on the purpose of the RECLAIM financial model.
2) provide clarity on the proponents responsibility to adhere to the final dollar amount calculated by the RECLAIM financial model.
GNWT/CIRNAC
18 | RECLAIM 8 Model Working Copy - Excel Sheet; Unit Cost Tab - Fuel and Electricity | Fuel costs for gas and diesel are listed. No fuel costs for Jet A, Jet B or Av gas are included. | The KivIA requests that CIRNAC and their engineering consultants provide fuel costs for Jet A, Jet B and Av gas. | AtkinsRéalis
19 | RECLAIM 8 Model Working Copy - Excel Sheet; Unit Cost Tab - Mobilize Workers (round trip) | Hourly costs for small, medium and heavy helicopters. Are these hourly costs "dry" (do not include fuel cost) or "wet" (do included fuel cost). | The KivIA requests that CIRNAC and their engineering consultants determine if the hourly costs for small, medium and heavy helicopters are "dry" or "wet".
AtkinsRéalis
20 | RECLAIM 8 Model Working Copy - Excel Sheet; Estimator Tab - Excavator Ratings | The cycle times and productivity for excavators are based on southern Canadian conditions (ie. digging in sandstone and caliche; non-Arctic conditions). There is no reference to permafrost or Arctic conditions for the cycle times and productivity for excavators. | The KivIA requests that CIRNAC and their engineering consultants determine what changes to the cycle times and productivity for excavators will occur in permafrost and Arctic conditions, in particular, metal fatigue under extremely cold conditions (ie. > -40oC). | AtkinsRéalis
No. | Topic | Reviewer Comment | Reviewer Recommendation |  | Proponent Response
Burgundy Diamond Mines Ltd - Sheila Chernys
1 | Transparency of Unit Rates Derivation | The derivation of the proposed RECLAIM 8.0 unit rates remains unclear, which makes it challenging for proponents to assess their applicability to specific sites. | Provide detailed explanations and supporting data for these rates would enhance understanding and confidence in their application. | AtkinsRéalis
2 | Mobilization and Indirect Cost Management (ICM) Costs | Reassigning these costs to Capital Costs introduces a compounding effect that significantly inflates estimates. | Retaining them under Indirect Costs would better account for site-specific variations without leading to overestimations. | AtkinsRéalis
3 | Default Percentages for Costs | The percentages allocated for Owners Representative, HHERA, and Final CRP costs are high and do not align with typical closure project requirements in the region. | Revisiting these percentages and considering fixed cost estimates will ensure more balanced and accurate calculations. | AtkinsRéalis
4 | Inflation Rate Methodology | Applying a fixed 3% inflation rate across all closure costs is not appropriate for all closure activities. | A more flexible approach based on historical inflation data and specific project conditions will better reflect actual cost variability. | AtkinsRéalis
5 | Incentives for Progressive Reclamation | The updates focus on increasing securities but could also include measures to encourage progressive reclamation during operations. For example, allowing partial release of securities to execute reclamation activities would promote progressive reclamation, reduce liabilities and support sustainable closure outcomes. | Update should encourage progressive reclamation during operations. | GNWT/CIRNAC